## Project Structure
Folder Structure | [5 empty] | Checklists
Site QA
9743 MoRDC
Switchboard
|  |  | MSSB-A |  |  | MSSB checklist
|  |  | MSSB-A.2 |  |  | MSSB checklist
|  |  | MSSB-CB |  |  | MSSB checklist
|  |  | MSSB-CH |  |  | MSSB checklist
|  |  | MSSB-DO |  |  | MSSB checklist
|  |  | MSSB-E |  |  | MSSB checklist
|  |  | MSSB-EC |  |  | MSSB checklist
|  |  | MSSB-GHN |  |  | MSSB checklist
|  |  | MSSB-GHS |  |  | MSSB checklist
|  |  | MSSB-PC |  |  | MSSB checklist
|  |  | MSSB-RO |  |  | MSSB checklist
|  |  | MSSB-SPINE |  |  | MSSB checklist
|  |  | MSSB-SPINE 1 |  |  | MSSB checklist
|  |  | MSSB-SPINE 2 |  |  | MSSB checklist
|  |  | MSSB-SPINE 3 |  |  | MSSB checklist
|  |  | MSSB-TM |  |  | MSSB checklist
|  |  | MSSB-WS |  |  | MSSB checklist
|  |  | MSSB-SP-1 |  |  | MSSB checklist
|  |  | MSSB-SP-2 |  |  | MSSB checklist
|  |  | MSSB-SP-3 |  |  | MSSB checklist
|  |  | MSSB-SP-4 |  |  | MSSB checklist
|  |  | MSSB-ESS |  |  | MSSB checklist
Variable Speed Drives
|  |  | VSD-SEF-HB-1 |  |  | VSD checklist
|  |  | VSD-SEF-HB-4 |  |  | VSD checklist
|  |  | VSD-SEF-HB-5 |  |  | VSD checklist
|  |  | VSD-SEF-HB-7 |  |  | VSD checklist
|  |  | VSD-SEF-CB-1 |  |  | VSD checklist
|  |  | VSD-SEF-CB-2 |  |  | VSD checklist
|  |  | VSD-SEF-CB-3 |  |  | VSD checklist
|  |  | VSD-SEF-CB-4 |  |  | VSD checklist
|  |  | VSD-SEF-CB-5 |  |  | VSD checklist
|  |  | VSD-SEF-CB-6 |  |  | VSD checklist
|  |  | VSD-SPF-1 |  |  | VSD checklist
|  |  | VSD-SPF-2 |  |  | VSD checklist
|  |  | VSD-SPF-3 |  |  | VSD checklist
|  |  | VSD-SPF-4 |  |  | VSD checklist
|  |  | VSD-EAF-PC-1 |  |  | VSD checklist
|  |  | VSD-EAF-PC-2 |  |  | VSD checklist
|  |  | VSD-EAF-PC-3 |  |  | VSD checklist
|  |  | VSD-EAF-PC-4 |  |  | VSD checklist
|  |  | VSD-SAF-EC-1A |  |  | VSD checklist
|  |  | VSD-SAF-EC-1B |  |  | VSD checklist
|  |  | VSD-SAF-EC-2 |  |  | VSD checklist
|  |  | VSD-CHWP-RL-1 |  |  | VSD checklist
|  |  | VSD-CHWP-RL-2 |  |  | VSD checklist
|  |  | VSD-CHWP-RL-3 |  |  | VSD checklist
|  |  | VSD-CHWP-RL-4 |  |  | VSD checklist
|  |  | VSD-CHWP-RL-5 |  |  | VSD checklist
|  |  | VSD-CHWP-RL-6 |  |  | VSD checklist
Smoke Clearance Fans
|  |  | SEF-HB-1 |  |  | Smoke Clearance Fans checklist
|  |  | SEF-HB-2 |  |  | Smoke Clearance Fans checklist
|  |  | SEF-HB-3 |  |  | Smoke Clearance Fans checklist
|  |  | SEF-HB-4 |  |  | Smoke Clearance Fans checklist
|  |  | SEF-HB-5 |  |  | Smoke Clearance Fans checklist
|  |  | SEF-HB-6 |  |  | Smoke Clearance Fans checklist
|  |  | SEF-HB-7 |  |  | Smoke Clearance Fans checklist
|  |  | SEF-HB-8 |  |  | Smoke Clearance Fans checklist
|  |  | SEF-HB-9 |  |  | Smoke Clearance Fans checklist
|  |  | SEF-CB-1 |  |  | Smoke Clearance Fans checklist
|  |  | SEF-CB-2 |  |  | Smoke Clearance Fans checklist
|  |  | SEF-CB-3 |  |  | Smoke Clearance Fans checklist
|  |  | SEF-CB-4 |  |  | Smoke Clearance Fans checklist
|  |  | SEF-CB-5 |  |  | Smoke Clearance Fans checklist
|  |  | SEF-CB-6 |  |  | Smoke Clearance Fans checklist
Stair Tunnel pressurisation
|  |  | SPF-1 |  |  | Stair / Tunnel Pressurisation Checklist
|  |  | SPF-2 |  |  | Stair / Tunnel Pressurisation Checklist
|  |  | SPF-3 |  |  | Stair / Tunnel Pressurisation Checklist
|  |  | SPF-4 |  |  | Stair / Tunnel Pressurisation Checklist
Ventilation Fans
|  |  | EAF-PC-1 |  |  | Ventilation Fans checklist
|  |  | EAF-PC-2 |  |  | Ventilation Fans checklist
|  |  | EAF-PC-3 |  |  | Ventilation Fans checklist
|  |  | EAF-PC-4 |  |  | Ventilation Fans checklist
|  |  | TEF-OA-G.1 |  |  | Ventilation Fans checklist
|  |  | TEF-OA-1.1 |  |  | Ventilation Fans checklist
|  |  | GEF-OA-1.1 |  |  | Ventilation Fans checklist
|  |  | OAF-OA-G.1 |  |  | Ventilation Fans checklist
|  |  | OAF-OA-1.1 |  |  | Ventilation Fans checklist
|  |  | OAF-OA-1.2 |  |  | Ventilation Fans checklist
|  |  | GEF-WS-1 |  |  | Ventilation Fans checklist
|  |  | GEF-WS-2 |  |  | Ventilation Fans checklist
|  |  | GEF-WB-1 |  |  | Ventilation Fans checklist
|  |  | GEF-WB-2 |  |  | Ventilation Fans checklist
|  |  | GEF-WB-1 |  |  | Ventilation Fans checklist
|  |  | OAF-DR-1 |  |  | Ventilation Fans checklist
|  |  | OAF-DR-2 |  |  | Ventilation Fans checklist
|  |  | OAF-IT-1 |  |  | Ventilation Fans checklist
|  |  | TEF-DC-1 |  |  | Ventilation Fans checklist
|  |  | TEF-DC-2 |  |  | Ventilation Fans checklist
|  |  | TEF-DO-1 |  |  | Ventilation Fans checklist
|  |  | OAF-DO-1 |  |  | Ventilation Fans checklist
|  |  | TEF-RO-1 |  |  | Ventilation Fans checklist
|  |  | OAF-RO-1 |  |  | Ventilation Fans checklist
|  |  | TEF-GHS-1 |  |  | Ventilation Fans checklist
|  |  | OAF-GHS-1 |  |  | Ventilation Fans checklist
|  |  | TEF-GHN-1 |  |  | Ventilation Fans checklist
|  |  | OAF-GHN-1 |  |  | Ventilation Fans checklist
|  |  | OAF-GHN-2 |  |  | Ventilation Fans checklist
|  |  | SAF-EC-1A |  |  | Ventilation Fans checklist
|  |  | SAF-EC-1B |  |  | Ventilation Fans checklist
|  |  | SAF-EC-2 |  |  | Ventilation Fans checklist
|  |  | TEF-TM-1 |  |  | Ventilation Fans checklist
|  |  | TEF-TM-2 |  |  | Ventilation Fans checklist
|  |  | OAF-TM-1 |  |  | Ventilation Fans checklist
|  |  | OAF-TM-2 |  |  | Ventilation Fans checklist
|  |  | OAF-TM-3 |  |  | Ventilation Fans checklist
|  |  | TEF-TW-1 |  |  | Ventilation Fans checklist
ERV / HRV Unit
|  |  | ERV-OA-1 |  |  | ERV / HRV Checklist
Packaged Unit
|  |  | PAC-CB-1 |  |  | PAC Units Checklist
|  |  | PAC-CB-2 |  |  | PAC Units Checklist
|  |  | PAC-CB-3 |  |  | PAC Units Checklist
|  |  | PAC-CB-4 |  |  | PAC Units Checklist
|  |  | PAC-CB-5 |  |  | PAC Units Checklist
|  |  | PAC-CB-6 |  |  | PAC Units Checklist
|  |  | PAC-CB-7 |  |  | PAC Units Checklist
|  |  | PAC-CB-8 |  |  | PAC Units Checklist
|  |  | PAC-CB-9 |  |  | PAC Units Checklist
|  |  | PAC-SP-1 |  |  | PAC Units Checklist
|  |  | PAC-SP-2 |  |  | PAC Units Checklist
|  |  | PAC-SP-3 |  |  | PAC Units Checklist
|  |  | PAC-SP-4 |  |  | PAC Units Checklist
|  |  | PAC-SP-5 |  |  | PAC Units Checklist
|  |  | PAC-SP-6 |  |  | PAC Units Checklist
|  |  | PAC-SP-7 |  |  | PAC Units Checklist
|  |  | PAC-SP-8 |  |  | PAC Units Checklist
|  |  | PAC-SP-9 |  |  | PAC Units Checklist
|  |  | PAC-SP-10 |  |  | PAC Units Checklist
|  |  | PAC-SP-11 |  |  | PAC Units Checklist
|  |  | PAC-SP-12 |  |  | PAC Units Checklist
|  |  | PAC-SP-13 |  |  | PAC Units Checklist
|  |  | PAC-SP-14 |  |  | PAC Units Checklist
|  |  | PAC-SP-15 |  |  | PAC Units Checklist
|  |  | PAC-SP-16 |  |  | PAC Units Checklist
Air Handling Unit
|  |  | AHU-HB-1 |  |  | AHU Checklist
|  |  | AHU-HB-2 |  |  | AHU Checklist
|  |  | AHU-HB-3 |  |  | AHU Checklist
|  |  | AHU-HB-4 |  |  | AHU Checklist
|  |  | AHU-HB-5 |  |  | AHU Checklist
|  |  | AHU-HB-6 |  |  | AHU Checklist
|  |  | AHU-HB-7 |  |  | AHU Checklist
|  |  | AHU-HB-8 |  |  | AHU Checklist
|  |  | AHU-HB-9 |  |  | AHU Checklist
|  |  | AHU-HB-10 |  |  | AHU Checklist
|  |  | AHU-HB-11 |  |  | AHU Checklist
|  |  | AHU-HB-12 |  |  | AHU Checklist
|  |  | AHU-HB-13 |  |  | AHU Checklist
|  |  | AHU-HB-14 |  |  | AHU Checklist
VRF / Split AC Unit
Operations
Ground Floor
[5 empty] | CU-OA-1 | AC Condensor checklist
[5 empty] | BB-OA-1 | Branch Box checklist
[5 empty] | FCU-OA-G.1 | FCU-AC checklist
[5 empty] | FCU-OA-G.2 | FCU-AC checklist
[5 empty] | AC-OA-G.3 | FCU-AC checklist
[5 empty] | AC-OA-G.4 | FCU-AC checklist
[5 empty] | FCU-OA-G.5 | FCU-AC checklist
[5 empty] | FCU-OA-G.6 | FCU-AC checklist
Operations
Ground Floor
[5 empty] | CU-OA-2 | AC Condensor checklist
[5 empty] | BB-OA-2 | Branch Box checklist
[5 empty] | AC-OA-G.7 | FCU-AC checklist
[5 empty] | FCU-OA-G.8 | FCU-AC checklist
[5 empty] | FCU-OA-G.9 | FCU-AC checklist
[5 empty] | FCU-OA-G.10 | FCU-AC checklist
[5 empty] | AC-OA-G.11 | FCU-AC checklist
[5 empty] | AC-OA-G.12 | FCU-AC checklist
[5 empty] | AC-OA-G.13 | FCU-AC checklist
[5 empty] | AC-OA-G.14 | FCU-AC checklist
Operations
First Floor
[5 empty] | CU-OA-3 | AC Condensor checklist
[5 empty] | BB-OA-3 | Branch Box checklist
[5 empty] | FCU-OA-1.1 | FCU-AC checklist
[5 empty] | FCU-OA-1.2 | FCU-AC checklist
[5 empty] | FCU-OA-1.3 | FCU-AC checklist
[5 empty] | FCU-OA-1.10 | FCU-AC checklist
[5 empty] | FCU-OA-1.11 | FCU-AC checklist
Operations
First Floor
[5 empty] | CU-OA-4 | AC Condensor checklist
[5 empty] | BB-OA-4 | Branch Box checklist
[5 empty] | FCU-OA-1.4 | FCU-AC checklist
[5 empty] | AC-OA-1.5 | FCU-AC checklist
[5 empty] | AC-OA-1.6 | FCU-AC checklist
[5 empty] | AC-OA-1.7 | FCU-AC checklist
[5 empty] | FCU-OA-1.8 | FCU-AC checklist
[5 empty] | FCU-OA-1.9 | FCU-AC checklist
[5 empty] | FCU-OA-1.12 | FCU-AC checklist
MHE Workshop
MHE / MHS
[5 empty] | CU-WS-1 | AC Condensor checklist
[5 empty] | AC-WS-1 | FCU-AC checklist
[5 empty] | AC-WS-2 | FCU-AC checklist
Gatehouse
North
[5 empty] | AC-GHN-1 | FCU-AC checklist
[5 empty] | CU-GHN-1 | AC Condensor checklist
[5 empty] | AC-GHN-2 | FCU-AC checklist
[5 empty] | CU-GHN-2 | AC Condensor checklist
[5 empty] | AC-GHN-3 | FCU-AC checklist
[5 empty] | CU-GHN-3 | AC Condensor checklist
South
[5 empty] | AC-GHS-1 | FCU-AC checklist
[5 empty] | CU-GHS-1 | AC Condensor checklist
[5 empty] | AC-GHS-2 | FCU-AC checklist
[5 empty] | CU-GHS-2 | AC Condensor checklist
Receiving Office
North
[5 empty] | AC-RO-1 | FCU-AC checklist
[5 empty] | CU-RO-1 | AC Condensor checklist
[5 empty] | AC-RO-2 | FCU-AC checklist
[5 empty] | CU-RO-2 | AC Condensor checklist
Dispatch Office
Office
[5 empty] | AC-DO-1 | FCU-AC checklist
[5 empty] | CU-DO-1 | AC Condensor checklist
GF Kiosk
Spine Data Room
[5 empty] | AC-K-1 | FCU-AC checklist
[5 empty] | CU-K-1 | AC Condensor checklist
[5 empty] | AC-K-2 | FCU-AC checklist
[5 empty] | CU-K-2 | AC Condensor checklist
Truck Maintenance
GF Office
[5 empty] | AC-TM-1 | FCU-AC checklist
[5 empty] | CU-TM-1 | AC Condensor checklist
[5 empty] | AC-TM-2 | FCU-AC checklist
[5 empty] | CU-TM-2 | AC Condensor checklist
[5 empty] | AC-TM-3 | FCU-AC checklist
[5 empty] | CU-TM-3 | AC Condensor checklist
Case Buffer IT
L1 IT workshop
[5 empty] | AC-IT-1 | FCU-AC checklist
[5 empty] | CU-IT-1 | AC Condensor checklist
Energy Centre
Inverter Room
[5 empty] | AC-EC-1 | FCU-AC checklist
[5 empty] | CU-EC-1 | AC Condensor checklist
[5 empty] | AC-EC-2 | FCU-AC checklist
[5 empty] | CU-EC-2 | AC Condensor checklist
[5 empty] | AC-EC-3 | FCU-AC checklist
[5 empty] | CU-EC-3 | AC Condensor checklist
[5 empty] | AC-EC-4 | FCU-AC checklist
[5 empty] | CU-EC-4 | AC Condensor checklist
CRAC Units
Operations
Data Room
[5 empty] | CRAC-OA-1 | CRAC unit Checklist
[5 empty] | CU-CRAC-OA-1 | CRAC Condensor Checklist
[5 empty] | CRAC-OA-2 | CRAC unit Checklist
[5 empty] | CU-CRAC-OA-2 | CRAC Condensor Checklist
Warehouse Spine
Data Room
[5 empty] | CRAC-SP-1 | CRAC unit Checklist
[5 empty] | CU-CRAC-SP-1 | CRAC Condensor Checklist
[5 empty] | CRAC-SP-2 | CRAC unit Checklist
[5 empty] | CU-CRAC-SP-2 | CRAC Condensor Checklist
Energy Complex
UPS Room
[5 empty] | CRAC-EC-1 | CRAC unit Checklist
[5 empty] | CU-CRAC-EC-1 | CRAC Condensor Checklist
[5 empty] | CRAC-EC-2 | CRAC unit Checklist
[5 empty] | CU-CRAC-EC-2 | CRAC Condensor Checklist
[5 empty] | CRAC-EC-3 | CRAC unit Checklist
[5 empty] | CU-CRAC-EC-3 | CRAC Condensor Checklist
Rotary Ventilator
Truck Maintenance
[5 empty] | RV-TM-1 | Rotary Ventilator Checklist
[5 empty] | RV-TM-2 | Rotary Ventilator Checklist
[5 empty] | RV-TM-3 | Rotary Ventilator Checklist
[5 empty] | RV-TM-4 | Rotary Ventilator Checklist
[5 empty] | RV-TM-5 | Rotary Ventilator Checklist
[5 empty] | RV-TM-6 | Rotary Ventilator Checklist
Truck Wash
[5 empty] | RV-TW-1 | Rotary Ventilator Checklist
[5 empty] | RV-TW-2 | Rotary Ventilator Checklist
[5 empty] | RV-TW-3 | Rotary Ventilator Checklist
[5 empty] | RV-TW-4 | Rotary Ventilator Checklist
Plant
Chilled Water Pump
[5 empty] | CHWP-1 | CHWP Checklist
[5 empty] | CHWP-2 | CHWP Checklist
[5 empty] | CHWP-3 | CHWP Checklist
[5 empty] | CHWP-4 | CHWP Checklist
[5 empty] | CHWP-5 | CHWP Checklist
[5 empty] | CHWP-6 | CHWP Checklist
Chiller
[5 empty] | CH-1 | Chiller Checklist
[5 empty] | CH-2 | Chiller Checklist
[5 empty] | CH-3 | Chiller Checklist
Fire Damper
JR-WD-M-A-2105
[5 empty] | FD-DR-1 | Fire Damper checklist
JR-WD-M-E-2100
[5 empty] | FD-EC-1 | Fire Damper checklist
[5 empty] | FD-EC-2 | Fire Damper checklist
[5 empty] | FD-EC-3 | Fire Damper checklist
[5 empty] | FD-EC-4 | Fire Damper checklist
[5 empty] | FD-EC-5 | Fire Damper checklist
[5 empty] | FD-EC-6 | Fire Damper checklist
[5 empty] | FD-EC-7 | Fire Damper checklist
[5 empty] | FD-EC-8 | Fire Damper checklist
[5 empty] | FD-EC-9 | Fire Damper checklist

## Checklists
type | name | values
checklist | Smoke Clearance Fans checklist
checkpoint | Technical data from Unit, Motor & drives match equipment schedules
checkpoint | Equipment Identification labels installed.
checkpoint | All components installed as per Mechanical shop drawings
checkpoint | Transport bolts and packing material Removed
checkpoint | Mounting and anti vibration mounts installed
checkpoint | Fan & motor rotate freely
checkpoint | Plenums / ducting & balance area clean and clear of debris
checkpoint | Electrical connections complete and Mains power available
checkpoint | Control wiring complete including any local operating controllers
checkpoint | Mechanical electrical contractor preformed Pre Commissioning ITP/ITC
checkpoint | Mechanical electrical contractor has verified operating voltage & amps
checkpoint | Fan rotation verified by electrical contractor
checkpoint | Controls functionality programmed and operational
checkpoint | System is ready to be put into manual / automatic operation.
checkpoint | System has been commissioned & balanced.
checkpoint | Fire interface connected and operational
checkpoint | System correctly operational & placed into Automatic service.
checklist | MSSB checklist
checkpoint | MSSB mounted in position
checkpoint | MSSB labelled correctly
checkpoint | Required clearance provided to MSSB
checkpoint | Cables connected into MSSB and all terminated and labelled
checkpoint | Main power connected to MSSB
checkpoint | MSSB energisation form provided to builder
checkpoint | Fire interface cable supplied & fitted off.
checkpoint | MSSB commissioned and operational
checklist | Fire Damper checklist
checkpoint | Fire damper installed correctly
checkpoint | Fire damper labelled
checkpoint | Fire damper sealed correctly
checkpoint | Photo required of installation
checklist | Ventilation Fans checklist
checkpoint | Technical data from Unit, Motor & drives match equipment schedules
checkpoint | Equipment Identification labels installed.
checkpoint | All components installed as per Mechanical shop drawings
checkpoint | Transport bolts and packing material Removed
checkpoint | Mounting and anti vibration mounts installed
checkpoint | Fan & motor rotate freely
checkpoint | Plenums / ducting & balance area clean and clear of debris
checkpoint | Electrical connections complete and Mains power available
checkpoint | Control wiring complete including any local operating controllers
checkpoint | Mechanical electrical contractor preformed Pre Commissioning ITP/ITC
checkpoint | Mechanical electrical contractor has verified operating voltage & amps
checkpoint | Fan rotation verified by electrical contractor
checkpoint | Controls functionality programmed and operational
checkpoint | System is ready to be put into manual / automatic operation.
checkpoint | System has been commissioned & balanced.
checkpoint | Fire interface connected and operational
checkpoint | System correctly operational & placed into Automatic service.
checklist | AC Condensor checklist
checkpoint | Technical data from Unit,Motor & drives match equipment schedules
checkpoint | All components installed as per Mechanical shop drawings
checkpoint | Equipment Identification labels installed.
checkpoint | Transport bolts and packing material Removed
checkpoint | Mounting and anti vibration mounts installed
checkpoint | Condensate drains / safety trays connected and tested for correct operation
checkpoint | Electrical connections complete and Mains power available
checkpoint | Control wiring complete including local wall & central controller
checkpoint | Refrigeration pipework confirmed as matching manufacturer's schematic
checkpoint | Associated interface cards installed and addressed as per manufacturers schematic
checkpoint | M.NET and refrigeration addressing set as per manufacturers schematic.
checkpoint | Mechanical electrical contractor preformed Pre Commissioning ITP/ITC
checkpoint | Mechanical electrical contractor has verified operating voltage & amps
checkpoint | Mechanical electrical contractor has energised Condensing units 24hrs prior to energising indoor equipment.
checkpoint | System is ready to be put into manual / automatic operation.
checkpoint | System has been commissioned & balanced.
checkpoint | Fire interface connected and operational
checkpoint | System correctly operational & placed into Automatic service.
checklist | Branch Box checklist
checkpoint | Technical data from Unit,Motor & drives match equipment schedules
checkpoint | All components installed as per Mechanical shop drawings
checkpoint | Equipment Identification labels installed.
checkpoint | Transport bolts and packing material Removed
checkpoint | Mounting and anti vibration mounts installed
checkpoint | Electrical connections complete and Mains power available
checkpoint | Control wiring complete including local wall & central controller
checkpoint | Refrigeration pipework confirmed as matching manufacturer's schematic
checkpoint | Associated interface cards installed and addressed as per manufacturers schematic
checkpoint | M.NET and refrigeration addressing set as per manufacturers schematic.
checkpoint | Mechanical electrical contractor preformed Pre Commissioning ITP/ITC
checkpoint | Mechanical electrical contractor has verified operating voltage & amps
checkpoint | Mechanical electrical contractor has energised Condensing units 24hrs prior to energising indoor equipment.
checkpoint | System is ready to be put into manual / automatic operation.
checkpoint | System has been commissioned & balanced.
checkpoint | Fire interface connected and operational
checkpoint | System correctly operational & placed into Automatic service.
checklist | FCU-AC checklist
checkpoint | Technical data from Unit,Motor & drives match equipment schedules
checkpoint | All components installed as per Mechanical shop drawings
checkpoint | Equipment Identification labels installed.
checkpoint | Transport bolts and packing material Removed
checkpoint | Mounting and anti vibration mounts installed
checkpoint | Condensate drains / safety trays connected and tested for correct operation
checkpoint | Plenums / ducting & balance area clean and clear of debris
checkpoint | Filters installed (temporary pre filter be installed if required)
checkpoint | Electrical connections complete and Mains power available
checkpoint | Control wiring complete including local wall & central controller
checkpoint | Refrigeration pipework confirmed as matching manufacturer's schematic
checkpoint | Associated interface cards installed and addressed as per manufacturers schematic
checkpoint | M.NET and refrigeration addressing set as per manufacturers schematic.
checkpoint | All volume control dampers in the open position (non motorised & motorised) & stroked correctly to match fire matrix intent
checkpoint | Mechanical electrical contractor preformed Pre Commissioning ITP/ITC
checkpoint | Mechanical electrical contractor has verified operating voltage & amps
checkpoint | Mechanical electrical contractor has energised Condensing units 24hrs prior to energising indoor equipment.
checkpoint | System is ready to be put into manual / automatic operation.
checkpoint | System has been commissioned & balanced.
checkpoint | Fire interface connected and operational
checkpoint | System correctly operational & placed into Automatic service.
checklist | CHWP Checklist
checkpoint | Technical data from Unit,Motor & drives match equipment schedules
checkpoint | All components installed as per Mechanical shop drawings
checkpoint | Equipment Identification labels installed.
checkpoint | Transport bolts and packing material Removed
checkpoint | Mounting and anti vibration mounts installed
checkpoint | Pipe work & valve train installation complete.
checkpoint | Mains water available for Hydrostatic testing & hydronic flushing.
checkpoint | Adequate drainage provided for hydronic flushing provided.
checkpoint | Temporary Commissioning filter sock has been placed over strainer.
checkpoint | Hydrostatic testing has been performed and results recorded.
checkpoint | System has been flushed full of water and bled of Air.
checkpoint | Control wiring complete including local DP & Flow sensors.
checkpoint | All manual, balancing & control valve in the open position.
checkpoint | Mechanical electrical contractor preformed Pre Commissioning ITP/ITC
checkpoint | Mechanical electrical contractor has verified operating voltage & amps
checkpoint | System is ready to be put into manual / automatic operation.
checkpoint | System has been commissioned & balanced.
checkpoint | Fire interface connected and operational
checkpoint | System correctly operational & placed into Automatic service.
Checklist | Chiller Checklist
checkpoint | Technical data from Unit,Motor & drives match equipment schedules
checkpoint | All components installed as per Mechanical shop drawings
checkpoint | Equipment Identification labels installed.
checkpoint | Transport bolts and packing material Removed
checkpoint | Mounting and anti vibration mounts installed
checkpoint | Mechanical electrical contractor preformed Pre Commissioning ITP/ITC
checkpoint | Mechanical electrical contractor has verified operating voltage & amps
checkpoint | System is ready to be put into manual / automatic operation.
checkpoint | Advise supplier of commissioning date and site attendance
checkpoint | Control wiring complete including local DP & Flow sensors.
checkpoint | System has been commissioned & balanced.
checkpoint | Unit parameters set up by Supplier. Control strategy meets design intent
checkpoint | System correctly operational & placed into Automatic service.
Checklist | CRAC Condensor Checklist
checkpoint | Technical data from Unit,Motor & drives match equipment schedules
checkpoint | All components installed as per Mechanical shop drawings
checkpoint | Equipment Identification labels installed.
checkpoint | Transport bolts and packing material Removed
checkpoint | Mounting and anti vibration mounts installed
checkpoint | Condensate drains / safety trays connected and tested for correct operation
checkpoint | Electrical connections complete and Mains power available
checkpoint | Control wiring complete including local wall & central controller
checkpoint | Refrigeration pipework confirmed as matching manufacturer's schematic
checkpoint | Mechanical electrical contractor preformed Pre Commissioning ITP/ITC
checkpoint | Mechanical electrical contractor has verified operating voltage & amps
checkpoint | System is ready to be put into manual / automatic operation.
checkpoint | System has been commissioned & balanced.
checkpoint | System correctly operational & placed into Automatic service.
Checklist | CRAC unit Checklist
checkpoint | Technical data from Unit,Motor & drives match equipment schedules
checkpoint | All components installed as per Mechanical shop drawings
checkpoint | Equipment Identification labels installed.
checkpoint | Transport bolts and packing material Removed
checkpoint | Mounting and anti vibration mounts installed
checkpoint | Make up water, and tundish locations noted as installed by others
checkpoint | Pipework pressure test conducted and recorded
checkpoint | Return air protected from debris and dust
checkpoint | Electrical and Plumbing connections terminated
checkpoint | Mechanical electrical contractor preformed Pre Commissioning ITP/ITC
checkpoint | Mechanical electrical contractor has verified operating voltage & amps
checkpoint | System is ready to be put into manual / automatic operation.
checkpoint | Advise supplier of commissioning date and site attendance
checkpoint | Remote temp sensors, and pressure sensors installed (if applicable)
checkpoint | BMS terminations completed to CRAC unit
checkpoint | System has been commissioned & balanced.
checkpoint | Unit parameters set up by Supplier. Control strategy meets design intent
checkpoint | System correctly operational & placed into Automatic service.
Checklist | Stair / Tunnel Pressurisation Checklist
checkpoint | Technical data from Unit, Motor & drives match equipment schedules
checkpoint | Equipment Identification labels installed.
checkpoint | All components installed as per Mechanical shop drawings
checkpoint | Transport bolts and packing material Removed
checkpoint | Mounting and anti vibration mounts installed
checkpoint | Fan & motor rotate freely
checkpoint | Plenums / ducting & balance area clean and clear of debris
checkpoint | Stairwell/corridor/tunnel envelope has been completely sealed, i.e. all penetrations through walls to be caulked, any speed panels to have recesses caulked
checkpoint | All doors to have closers tested that they safely self-close and latches are functioning correctly
checkpoint | All door closers have been tested and set to a maximum opening force of 6kg (60N) prior to any fan testing
checkpoint | Electrical connections complete and Mains power available
checkpoint | Control wiring complete including any local operating controllers
checkpoint | Mechanical electrical contractor preformed Pre Commissioning ITP/ITC
checkpoint | Variable speed,Drive commissioned programmed & Parameter list recorded.
checkpoint | Mechanical electrical contractor has verified operating voltage & amps
checkpoint | Fan rotation verified by electrical contractor
checkpoint | Controls functionality programmed and operational
checkpoint | System is ready to be put into manual / automatic operation.
checkpoint | System has been commissioned & balanced.
checkpoint | Fire interface connected and operational
checkpoint | System correctly operational & placed into Automatic service.
checklist | PAC Units Checklist
checkpoint | Technical data from Unit,Motor & drives match equipment schedules
checkpoint | All components installed as per Mechanical shop drawings
checkpoint | Equipment Identification labels installed.
checkpoint | Transport bolts and packing material Removed
checkpoint | Mounting and anti vibration mounts installed
checkpoint | Fans & Motors rotate freely
checkpoint | Condensate drains / safety trays connected and tested for correct operation
checkpoint | Plenums / ducting & balance area clean and clear of debris
checkpoint | Filters installed (temporary pre filter be installed if required)
checkpoint | All volume control dampers in the open position (non motorised & motorised) & stroked correctly to match fire matrix intent
checkpoint | Electrical connections complete and Mains power available
checkpoint | Control wiring complete including local wall & central controller
checkpoint | Mechanical electrical contractor preformed Pre Commissioning ITP/ITC
checkpoint | Mechanical electrical contractor has verified operating voltage & amps
checkpoint | System is ready to be put into manual / automatic operation.
checkpoint | System has been commissioned & balanced.
checkpoint | Fire interface connected and operational
checkpoint | System correctly operational & placed into Automatic service.
checklist | AHU Checklist
checkpoint | Technical data from Unit,Motor & drives match equipment schedules
checkpoint | All components installed as per Mechanical shop drawings
checkpoint | Equipment Identification labels installed.
checkpoint | Transport bolts and packing material Removed
checkpoint | Mounting and anti vibration mounts installed
checkpoint | CHW pipe system complete & connected to Unit
checkpoint | Fans & Motors rotate freely
checkpoint | Condensate drains / safety trays connected and tested for correct operation
checkpoint | Plenums / ducting & balance area clean and clear of debris
checkpoint | Filters installed (temporary pre filter be installed if required)
checkpoint | All volume control dampers in the open position (non motorised & motorised) & stroked correctly to match fire matrix intent
checkpoint | Electrical connections complete and Mains power available
checkpoint | Control wiring complete including local wall & central controller
checkpoint | Mechanical electrical contractor preformed Pre Commissioning ITP/ITC
checkpoint | Mechanical electrical contractor has verified operating voltage & amps
checkpoint | System is ready to be put into manual / automatic operation.
checkpoint | System has been commissioned & balanced.
checkpoint | Fire interface connected and operational
System correctly operational & placed into Automatic service.
checklist | ERV / HRV Checklist
checkpoint | Technical data from Unit,Motor & drives match equipment schedules
checkpoint | All components installed as per Mechanical shop drawings
checkpoint | Equipment Identification labels installed.
checkpoint | Transport bolts and packing material Removed
checkpoint | Mounting and anti vibration mounts installed
checkpoint | Fans & Motors rotate freely
checkpoint | Condensate drains / safety trays connected and tested for correct operation
checkpoint | Plenums / ducting & balance area clean and clear of debris
checkpoint | Filters installed (temporary pre filter be installed if required)
checkpoint | All volume control dampers in the open position (non motorised & motorised) & stroked correctly to match fire matrix intent
checkpoint | Electrical connections complete and Mains power available
checkpoint | Control wiring complete including local wall & central controller
checkpoint | Mechanical electrical contractor preformed Pre Commissioning ITP/ITC
checkpoint | Mechanical electrical contractor has verified operating voltage & amps
checkpoint | System is ready to be put into manual / automatic operation.
checkpoint | System has been commissioned & balanced.
checkpoint | Fire interface connected and operational
checkpoint | System correctly operational & placed into Automatic service.
checklist | VSD checklist
checkpoint | Technical data from VSD matches equipment schedules
checkpoint | VSD mounted in position
checkpoint | VSD labelled correctly
checkpoint | Cables connected into VSD and all terminated
checkpoint | Main power connected to MSSB
checkpoint | Mechanical electrical contractor preformed Pre Commissioning ITP/ITC
checkpoint | Mechanical electrical contractor has verified operating voltage & amps
checkpoint | System is ready to be put into manual / automatic operation.
checkpoint | VSD has been commissioned programmed & Parameter list recorded.
checkpoint | Fire interface connected and operational
checkpoint | System correctly operational & placed into Automatic service.
checklist | Rotary Ventilator Checklist
checkpoint | Technical data from RV matches equipment schedules
checkpoint | Equipment Labelled correctly
checkpoint | Volume control Damper mounted in position,& stroked correctly to match Fire Matrix intent.
checkpoint | Cables connected into Volume control Damper,associated controls and all terminated
checkpoint | Mechanical electrical contractor preformed Pre Commissioning ITP/ITC
checkpoint | Mechanical electrical contractor has verified operating voltage & amps
checkpoint | System is ready to be put into manual / automatic operation.
checkpoint | Fire interface connected and operational
checkpoint | System correctly operational & placed into Automatic service.