## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-sectioned |  |  | checklist | Apartments - Risers, Rough In, Fit Off, Electrical, Commissioning |  |  |  |  | Yes | Apartments - Risers, Rough In, Fit Off, Electrical, Commissioning | 1285ee48-08dc-4e0d-a237-46574204881a
checkpoint-group |  |  | section | Risers
checkpoint-status |  |  | checkpoint | Solid duct installed & connected to fire damper
checkpoint-status |  |  | checkpoint | Fire damper Installed /sealed & signed off
checkpoint-status |  |  | checkpoint | Piping installed including branches to level
checkpoint-status |  |  | checkpoint | Pipe system pressure tested for each level
checkpoint-status |  |  | checkpoint | Pipe lagging completed
checkpoint-status |  |  | checkpoint | Piping has been fire sealed & signed off
checkpoint-group |  |  | section | Rough In
checkpoint-status |  |  | checkpoint | Fan coil unit & Supply Duct installed
checkpoint-status |  |  | checkpoint | CHW & HHW pipe branches , valve sets
checkpoint-status |  |  | checkpoint | All drains fit off and tested
checkpoint-status |  |  | checkpoint | Fire Dampers installed & fire sealed
checkpoint-status |  |  | checkpoint | Plaster mounting frames installed by plasterer
checkpoint-status |  |  | checkpoint | Cushion boxes roughed in and sealed
checkpoint-status |  |  | checkpoint | Access panel marked on floor
checkpoint-status |  |  | checkpoint | Flex installed and free of other services or restrictions and correctly suspended
checkpoint-group |  |  | section | Fit Off
checkpoint-status |  |  | checkpoint | Grilles fit off and installed correctly
checkpoint-status |  |  | checkpoint | Ensure all rubbish and materials have been picked up and room is clean
checkpoint-group |  |  | section | Electrical
checkpoint-status |  |  | checkpoint | All electrical wiring has been installed correctly
checkpoint-status |  |  | checkpoint | Mechanical switchboard has been labelled and has legend installed
checkpoint-status |  |  | checkpoint | All isolators have been labelled
checkpoint-status |  |  | checkpoint | All essential services have correct isolators installed
checkpoint-status |  |  | checkpoint | Correct commissioning has been carried out and documented
checkpoint-status |  |  | checkpoint | Ensure all rubbish and materials have been picked up and roof is clean
checkpoint-status |  |  | checkpoint | ALL BMS points have been commissioned as per approved points list
checkpoint-group |  |  | section | Commissioning
checkpoint-status |  |  | checkpoint | Carry out test of condensate drain and physically view water draining away
checkpoint-status |  |  | checkpoint | Carry out air flow tests to ducted units and document
checkpoint-status |  |  | checkpoint | Ensure correct operation of smoke dampers for common riser ventilation system
checkpoint-status |  |  | checkpoint | Ensure correct and even temperatures in all rooms
checkpoint-status |  |  | checkpoint | Ensure we don’t have any rattles or vibration noises
checkpoint-status |  |  | checkpoint | Ensure installation is carried out correctly and all materials and rubbish have been cleaned up
checklist-flat |  |  | checklist | Variation - |  |  |  |  | Yes | Add Variation | 5264be83-1241-40fa-b19a-6aceb545a4e5
checkpoint-status |  |  | checkpoint | Variation Details Captured
radio | 6790d142-95a3-494a-a54b-4f792f4f9dc7 |  | radio | Variation Type | Addition to Scope of Works, General Note / Observation, Repairs, Submittal,Site Instruction
button | e1b79a5c-e8d4-4cfd-964a-5c49bf65c509 |  | button | Additional Costs? | No,Yes
text | b6dd5610-671a-41c4-9242-b28047654fa9 |  | textbox | Variation Description:
label | 1cb53d66-30aa-4374-9bb7-917fea70f2d8 |  | note | Hours:
text | a2727106-5bb2-424a-ac9e-2111ef810dcc |  | textbox | Date:
text | f3e5a32e-f9ed-48da-b91a-18cbaf3c5b34 |  | textbox | Start:
text | 58bca6e2-6619-474e-9ab8-95ca0cb3d304 |  | textbox | Finish:
text | 8c6f8c40-abe4-4070-bc1e-480eecddba17 |  | textbox | Total:
text | 6ac815df-799e-498a-bf41-763451979e37 |  | textbox | Materials Used:
text | 1c8dca8e-e9d9-4b20-9119-4e7b8d09635f |  | textbox | Plant Used:
checkpoint-status |  |  | checkpoint | Paramount Representative Sign Off
text | 6d9e643d-9c48-4572-a121-692ab368fb39 |  | textbox | Print Name
checkpoint-status |  |  | checkpoint | Client Representative Sign Off
text | cf42e208-5739-4229-a814-3cccd6b139b6 |  | textbox | Print Name
checklist-flat |  |  | checklist | Toolbox/Pre Start Talks |  |  |  |  | Yes | Toolbox/Pre Start Talks Checklist | 6941e9d9-1e76-48d4-bbc2-7909f07035e7
checkpoint-status |  |  | checkpoint | Toolbox/Pre Start Talks Details Completed
text | 5dd45524-ec99-478e-a3c1-5ba452de5fd4 |  | textbox | Subject of Talk:
text | 756ad882-6d47-4ff6-a76b-ff7ed30c97e9 |  | textbox | Presented By:
text | f5f68e04-e2bb-4c9f-a76f-596651486de5 |  | textbox | Duration:
text | 26195065-7fc6-444a-8bcd-e0962b1d33d3 |  | textbox | Date:
select | 028a7b3c-d794-4da0-808a-3146ed2b529e |  | dropdown | Persons Present | Aaron Ellery,Aiden Taylor ,Andrew Waugh ,Ayden Bares,Bowen Law,Brendan Hammill,Daniel Mailard,Dave Emmett,Dean Kovacic,Glenn Oakley,Hayden Battens,Jack Baxter,Mason Dunstone,Matthew Adam,Matthew Burnett,Matthew Kendall,Scott Forbes,Shaun Campbell,Shayne Rodger,Thanassis Karageorgopoulos,Thomas Smulders,Tim Johnston,Zak Johnston
text | dbb9ec44-2839-4c54-a201-f14916f737ba |  | textbox | Points Raised/Comments:
text | 0e732458-040f-4add-bd15-9f76f4af0c5c |  | textbox | Corrective Action:
text | b6c712d0-d3ae-40a4-add5-39b40ef9bed1 |  | textbox | Action By:
text | 5e1491e3-9c6b-49bb-869d-8d71600063e4 |  | textbox | Action Complete:
checklist-sectioned |  |  | checklist | Roof - Rough in and Fit Off |  |  |  |  | Yes | Roof - Rough in and Fit Off | 7444183b-808c-405f-ba3a-a82c5cdac742
checkpoint-group |  |  | section | Rough In
checkpoint-status |  |  | checkpoint | All fans correctly installed with correct hangers/supports
checkpoint-status |  |  | checkpoint | All duct to be fully sealed , flashed and cleaned
checkpoint-status |  |  | checkpoint | Ensure adequate room and access for future maintenance
checkpoint-status |  |  | checkpoint | Ensure all rubbish and materials have been picked up and roof is clean
checkpoint-status |  |  | checkpoint | Boiler positioned
checkpoint-status |  |  | checkpoint | Pumps positioned
checkpoint-status |  |  | checkpoint | Chiller positioned
checkpoint-status |  |  | checkpoint | Buffer Tank Positioned
checkpoint-status |  |  | checkpoint | AHU,s positioned
checkpoint-status |  |  | checkpoint | Mechanical Switch boards positioned
checkpoint-status |  |  | checkpoint | Mech elec wiring completed
checkpoint-status |  |  | checkpoint | Ensure duct discharges are covered with vermin mesh
checkpoint-status |  |  | checkpoint | CWH/HHW pipe work installed
checkpoint-status |  |  | checkpoint | CVHW /HHW pipe insulated & cladded
checkpoint-status |  |  | checkpoint | Pipe system pressure tested
checkpoint-status |  |  | checkpoint | Pipe system final system balance completed
checkpoint-group |  |  | section | Fit Off
checkpoint-status |  |  | checkpoint | Grilles fit off and installed correctly
checkpoint-status |  |  | checkpoint | Ensure all rubbish and materials have been picked up and room is clean
checkpoint-group |  |  | section | Commissioning
checkpoint-status |  |  | checkpoint | All electrical wiring has been installed correctly
checkpoint-status |  |  | checkpoint | Mechanical switchboard has been labelled and has legend installed
checkpoint-status |  |  | checkpoint | All isolators have been labelled
checkpoint-status |  |  | checkpoint | All essential services have correct isolators installed
checklist-flat |  |  | checklist | Site Issue/Delay: |  |  |  |  | Yes | Add Site Issue/Delay | 8e1b57d5-8c0e-4258-a0a5-7e3831349047
checkpoint-status |  |  | checkpoint | Description of Site Issue/Delay
checklist-sectioned |  |  | checklist | Common - Rough in and Fit Off |  |  |  |  | Yes | Common - Rough in and Fit Off | f4cfdc0a-98e6-4749-8da4-2227e80b7ec8
checkpoint-group |  |  | section | Rough In
checkpoint-status |  |  | checkpoint | Fan coil unit & Supply Duct installed
checkpoint-status |  |  | checkpoint | CHW & HHW pipe branches , valve sets
checkpoint-status |  |  | checkpoint | All drains fit off and tested
checkpoint-status |  |  | checkpoint | Fire Dampers installed & fire sealed
checkpoint-status |  |  | checkpoint | Plaster mounting frames installed by plasterer
checkpoint-status |  |  | checkpoint | Cushion boxes roughed in and sealed
checkpoint-status |  |  | checkpoint | Access panel marked on floor
checkpoint-status |  |  | checkpoint | Flex installed and free of other services or restrictions and correctly suspended
checkpoint-group |  |  | section | Fit Off
checkpoint-status |  |  | checkpoint | Grilles fit off and installed correctly
checkpoint-status |  |  | checkpoint | Ensure all rubbish and materials have been picked up and room is clean