## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-flat |  |  | checklist | Sprinkler Fit Off checklist |  |  |  |  | Yes | Sprinkler Fit Off checklist | 152af280-6bc5-4039-8405-0c58e7630405
checkpoint-status |  |  | checkpoint | Fit Off: Check all sprinklers have been fit off
checkpoint-status |  |  | checkpoint | Check sprinkler heights pre paint
checkpoint-status |  |  | checkpoint | Fit off Escutcheon plates
checkpoint-status |  |  | checkpoint | Air Test: Pressurized air test for a period of 30 mins (if applicable)
text | bdd67dab-32ee-586f-b633-428290eae56c |  | textbox | Start time:
text | 1255f001-ed46-5f41-b11c-96bd350e6b79 |  | textbox | Completion time:
checkpoint-status |  |  | checkpoint | Water Test: Pressure test to 1600Kpa for duration of 2 hours
text | a4891a2d-09f9-5b13-9ba3-eeeebd378b1b |  | textbox | Start time:
text | 610d1bff-b177-5247-a1c3-a4f4edcaf3e4 |  | textbox | Completion time:
checkpoint-status |  |  | checkpoint | PFP Foreman signature
checklist-sectioned |  |  | checklist | Toolbox Meeting Checklist |  |  |  |  | Yes | Toolbox Meeting Checklist | 231399a3-752e-49f3-b426-7900493c15c0
checkpoint-group |  |  | section | Attendance
checkpoint-status |  |  | checkpoint | Attendance - list of attendees added below
checkpoint-group |  |  | section | Minutes
checkpoint-status |  |  | checkpoint | Actions from last meeting
checkpoint-status |  |  | checkpoint | Safety: (including hazards / near misses / controls / site specific)
checkpoint-status |  |  | checkpoint | Plant, tools & Equipment all in good working order?
checkpoint-status |  |  | checkpoint | PPE-ensure everyone has PPE
checkpoint-status |  |  | checkpoint | Housekeeping to be maintained
checkpoint-status |  |  | checkpoint | Ensure Electrical equipment test and tagged
checkpoint-group |  |  | section | New Business / Other
checkpoint-status |  |  | checkpoint | Any new business / other comments added below
checkpoint-group |  |  | section | Meeting Closure
checkpoint-status |  |  | checkpoint | Meeting Closed
text | f3930291-759c-55fd-960c-6681e289feae |  | textbox | Meeting Closed time
text | 4bd6e1d7-e83e-5136-a13a-f951a4fd606a |  | textbox | Minutes taken by (Name)
checkpoint-status |  |  | checkpoint | Employee sign off
checklist-flat |  |  | checklist | Fire Booster Cupboard checklist |  |  |  |  | Yes | Fire Booster Cupboard checklist | 24a9514c-1c00-40e4-b281-2cfd69291b2d
checkpoint-status |  |  | checkpoint | Install Suction/ Millcocks & Hydrant, Sprinkler Boosters
checklist-flat |  |  | checklist | Commissioning |  |  |  |  | Yes | Commissioning | 4ccd0aaa-23c7-4e23-b642-8684f552a7ba
checkpoint-status |  |  | checkpoint | SCV-Locks/chain/labels/pipework stickers/sprinkler spares & spanner/block plans
checkpoint-status |  |  | checkpoint | Booster Cupboard-Signage/Locks/chain/labels/plan sleeve+block plans label/block plans
checkpoint-status |  |  | checkpoint | Hydrant Mains/Isolation Valves-Locks/chain/labels/pipework stickers
checkpoint-status |  |  | checkpoint | Water Meter Assembly-Locks/chain/labels
checkpoint-status |  |  | checkpoint | Check sluice valves & water meter valves are open
checkpoint-status |  |  | checkpoint | Fire Pump/Tank-Fuel full, Exhaust piped, Mains power, Drains/Relief Valve piped, Water Supply on, Locks/chain/labels/pipework stickers
checkpoint-status |  |  | checkpoint | Adjust Bermads & float Valves to fire tanks
checkpoint-status |  |  | checkpoint | Pump Room-Block Plans
checkpoint-status |  |  | checkpoint | FIP-Block plans/test all alarm devices
checkpoint-status |  |  | checkpoint | Test all Valves & Flow switches to ensure correct operation
checkpoint-status |  |  | checkpoint | Set Pressure switches to Jacking pump & alarm line
checkpoint-status |  |  | checkpoint | Block plans/Tactical Fire plans/FRV way finding plan
checkpoint-status |  |  | checkpoint | FRV Shortfall drawings & FRV stat signage ie: x2 30m hose
checkpoint-status |  |  | checkpoint | Individual Floor Block plans (If applicable)
checklist-flat |  |  | checklist | Site Diary Checklist |  |  |  |  | Yes | Site Diary Checklist | 6778f435-14df-4795-b2a6-4e295040b391
checkpoint-status |  |  | checkpoint | Comment/notes
checklist-flat |  |  | checklist | Sprinkler Rough In checklist |  |  |  |  | Yes | Sprinkler Rough In checklist | 843c4729-dd09-4bbe-a057-9ce8a3cad019
checkpoint-status |  |  | checkpoint | Rough In: All Mains, range pipes, clips installed & secured
checkpoint-status |  |  | checkpoint | Concealed Space Sprinklers & Flexible droppers Installed
checkpoint-status |  |  | checkpoint | Arm pieces / Under Duct pipework installed and secured
checkpoint-status |  |  | checkpoint | Balcony Sprinklers installed
checkpoint-status |  |  | checkpoint | Car Park Sprinklers Installed
checkpoint-status |  |  | checkpoint | Car Stackers pipework installed & secured (if applicable)
checkpoint-status |  |  | checkpoint | Install Remote Test drain pipework
checkpoint-status |  |  | checkpoint | Air Test: Pressurized air test for a period of 30 mins (if applicable)
text | 72715641-a9cb-55b5-8a0e-72cf2bb0a070 |  | textbox | Start time:
text | 00fd1739-9d8a-5d2c-8554-e70c37b8ee71 |  | textbox | Completion time:
checkpoint-status |  |  | checkpoint | Water Test: Pressure test to 1600Kpa for duration of 2 hours
text | 047e17ff-4b99-5ba5-91ce-e8c1ab7072ba |  | textbox | Start time:
text | 559362cf-a600-5f5d-9d59-88060576a5de |  | textbox | Completion time:
checkpoint-status |  |  | checkpoint | PFP Foreman signature
checklist-sectioned |  |  | checklist | Incident Reports |  |  |  |  | Yes | Incident Reports | 8ee29de3-3bab-4564-b493-fa323844c043
checkpoint-group |  |  | section | Details of accident/incident
checkpoint-status |  |  | checkpoint | Please attach any relevant photos & documents
text | 57a466ca-693a-5bd4-ae7c-a96656645bc2 |  | textbox | Date of incident
text | 5fad3336-7bf7-50d1-bf4c-f262110c435f |  | textbox | Time of incident:
text | 4e080ea7-149c-5edd-a5ce-b2d22af58fe3 |  | textbox | Time of report:
checkpoint-status |  |  | checkpoint | Nature of incident
boolean | 7f637208-3cd0-59a1-844d-f318e7171073 |  | tickbox | injury (attach completed WHSE Form 01 Injury report)
boolean | e310e54e-6ceb-5dab-b64b-cb0d56a124bb |  | tickbox | environmental (pollution)
boolean | 2a61b177-17ae-5c01-a651-d525dfd85a59 |  | tickbox | damage to property/assets/services
boolean | b7f391dc-bf20-5c0d-81ce-368b161b44d3 |  | tickbox | incident
checkpoint-group |  |  | section | Names of person(s) involved
checkpoint-status |  |  | checkpoint | Please attach any relevant photos & documents
text | 86c4f53c-3fe0-577f-b838-e7b4c5605f82 |  | textbox | Name
text | ed182c31-d2b2-56a2-83f0-a8fc7bcd4e15 |  | textbox | Phone Number
label | b94c40bd-4797-574e-9ca2-61cd556af80c |  | note | (home, mobile & work)
text | 33ea016d-c5dc-594e-8e4a-8c2989f23d2b |  | textbox | Address
text | d0494058-0c15-507c-953b-db523c203724 |  | textbox | D.O.B
text | 16d4d02a-ba67-5f04-9773-478d2457fe2c |  | textbox | Email
text | 11c9ab13-6964-5fab-8574-cbd9fdeb25d4 |  | textbox | Activity in which the person(s) was engaged at the time:
text | a1b8f17a-16d5-550a-add2-a2d410f0ef64 |  | textbox | Exact site location where injury/incident occurred:
text | 74860451-6b0e-5d21-9457-a1a7235d5d38 |  | textbox | Type of injury/pollution/damage/ incident:
text | 2c56f81e-67c5-516a-9956-06c84342ad7e |  | textbox | Describe the accident/incident in detail:
checkpoint-group |  |  | section | Witness to incident (each witness may need to provide an account of what happened
checkpoint-status |  |  | checkpoint | Please attach any relevant photos & documents
text | 4b880c1f-69f4-5d11-b903-6d86dc770f92 |  | textbox | Witness Name
text | 345dc5e7-c794-5798-b289-a16177827f94 |  | textbox | Witness Contact
text | 17bd5653-2c2a-5ed7-881f-a065301a745b |  | textbox | Witness Name
text | ca5faec3-05ea-5b5d-967d-c3b7cd5daf61 |  | textbox | Witness Contact
checkpoint-group |  |  | section | Are there any notable/significant factors relevant to the accident/incident?
checkpoint-status |  |  | checkpoint | Please attach any relevant photos & documents
text | 7bf19669-b9f1-5e99-a927-340c8dddf851 |  | textbox | Details
checkpoint-group |  |  | section | Arrangements made to store any equipment that believed to have contributed to injury/incident?
checkpoint-status |  |  | checkpoint | Please attach any relevant photos & documents
text | e4aff827-28ce-5757-a10e-345e2d3c3c60 |  | textbox | Details
checkpoint-group |  |  | section | Did any third parties (subcontractors, visitors, etc.,) contribute to the incident? If so, how?
checkpoint-status |  |  | checkpoint | Please attach any relevant photos & documents
text | 6d8f491e-5084-50e3-b6be-b389bec28482 |  | textbox | Details
checkpoint-group |  |  | section | Immediate corrective actions taken? (e.g., works ceased, area made safe, barriers erected, etc.,)
checkpoint-status |  |  | checkpoint | Please attach any relevant photos & documents
text | 97b80f21-a032-597f-a9b5-d0a3721832be |  | textbox | Details
checkpoint-group |  |  | section | Future actions taken (e.g., engineering solutions, training, toolbox talk, etc.,)
checkpoint-status |  |  | checkpoint | Please attach any relevant photos & documents
text | 5e757e04-df30-532c-ae7e-bbd0b76c92b6 |  | textbox | Details
checkpoint-group |  |  | section | Review & Sign off
checkpoint-status |  |  | checkpoint | Have all actions been completed and reviewed as effective?
checkpoint-status |  |  | checkpoint | Have all documents relating to the incident, including corrective action evidence been completed
holdpoint |  |  | signoff | Signed Off
checklist-flat |  |  | checklist | Undocumented Variations |  |  |  |  | Yes | Undocumented Variations | 975f9f11-120a-413f-b91b-1adf87e4e09b
checkpoint-status |  |  | checkpoint | Attach relevant details
checklist-flat |  |  | checklist | Fire Penetrations checklist |  |  |  |  | Yes | Fire Penetrations checklist | ab556ade-8163-402e-ad52-1a46de764d30
checkpoint-status |  |  | checkpoint | Fire Penetration labelled & caulked in accordance with AS 4072.1 Drawing Reference No.
checklist-flat |  |  | checklist | Fire Extinguishers/Blankets |  |  |  |  | Yes | Fire Extinguishers/Blankets | b267cd9a-9f0f-419d-8af9-da7b85b93647
checkpoint-status |  |  | checkpoint | Install Extinguishers
checkpoint-status |  |  | checkpoint | Install appropriate signage
checkpoint-status |  |  | checkpoint | Install Fire Blankets
checkpoint-status |  |  | checkpoint | Fire Hose Reel signs
checklist-flat |  |  | checklist | Sprinkler Control Valves checklist |  |  |  |  | Yes | Sprinkler Control Valves checklist | d1d293ed-3917-44e9-bd58-84203a2656d8
checkpoint-status |  |  | checkpoint | Install Sprinkler Control Valves/ Jacking Pump
checkpoint-status |  |  | checkpoint | Test full operation of Control Valves
checkpoint-status |  |  | checkpoint | Install Sprinkler Spares box, spare sprinklers & spanner
checkpoint-status |  |  | checkpoint | Set Jacking Pump pressure switch min 150 kPa above towns main/manifold pressure
checkpoint-status |  |  | checkpoint | Install Gong/Electric Bell & test operation
checkpoint-status |  |  | checkpoint | Check for adequate drainage and test
checklist-flat |  |  | checklist | Project Drawings |  |  |  |  | Yes | Project Drawings | d5a0ce30-37d5-4ec2-838b-d18ed8dcc907
checkpoint-status |  |  | checkpoint | Upload project drawings
checklist-flat |  |  | checklist | Fire Pumps/Tanks checklist |  |  |  |  | Yes | Fire Pumps/Tanks checklist | f0ec0e10-310b-4788-86a0-fd5b3c831c2f
checkpoint-status |  |  | checkpoint | Install Plinth & secure
checkpoint-status |  |  | checkpoint | Install Pumps & secure to plinths
checkpoint-status |  |  | checkpoint | Install all pipework/isolation valves to pumps
checkpoint-status |  |  | checkpoint | Install Annubar/coolant drains
checkpoint-status |  |  | checkpoint | Install Pump Exhaust to designated point
checkpoint-status |  |  | checkpoint | Water Test all Pipework to pumps
checkpoint-status |  |  | checkpoint | Install all Pipework and Valves to Fire Tank
checkpoint-status |  |  | checkpoint | Water test all pipework to and from Water Tank
checklist-flat |  |  | checklist | Hydrant/ Sprinkler Mains / Risers / Hose Reel checklist |  |  |  |  | Yes | Hydrant/ Sprinkler Mains / Risers / Hose Reel checklist | f0f4764f-4bd1-4186-978a-864f3ad28318
checkpoint-status |  |  | checkpoint | Rough In: All Mains & isolation valves installed
checkpoint-status |  |  | checkpoint | Install Hydrant/ Sprinkler/Test Drain Risers & Mill Cocks
checkpoint-status |  |  | checkpoint | Sprinkler Floor Control Valves installed and secured
checkpoint-status |  |  | checkpoint | Fit Off: Check all millcock clearances/angles/Mill cocks in closed position & Install 2400kPa pressure gauge to top of risers
checkpoint-status |  |  | checkpoint | Install Fire Hose Reels & pipework
checkpoint-status |  |  | checkpoint | Air Test: Pressurized air test for a period of 30 mins (if applicable)
text | 1d3290f6-64ae-572e-a652-a5f2c05ce10e |  | textbox | Start time:
text | 464ab9c2-9e46-5b14-a2c9-eed979c193a7 |  | textbox | Completion time:
checkpoint-status |  |  | checkpoint | Water Test: Pressure test to 1700Kpa for duration of 2 hours
text | 0de3b86d-1a42-5ddb-a5f3-5086491f4c35 |  | textbox | Start time:
text | 16d22ec5-1510-510a-9c91-076f35ce06db |  | textbox | Completion time:
checkpoint-status |  |  | checkpoint | FHR: All FHR been bled from excess air & proof of water
checkpoint-status |  |  | checkpoint | PFP Foreman signature
checklist-sectioned |  |  | checklist | Variations |  |  |  |  | Yes | Variations | fc2f5e99-e20d-4f57-99df-56a5b02bc871
checkpoint-group |  |  | section | Payer Details
checkpoint-status |  |  | checkpoint | Payer Details entered below
text | 93f0c49b-8cfb-5460-9be2-61f005cb0038 |  | textbox | Contact
text | 03506b8c-ab96-5b06-b719-d200b64e6702 |  | textbox | Company
text | 627900f1-6b73-560e-9034-474906d53afc |  | textbox | Contact No.
checkpoint-group |  |  | section | Variation Details
checkpoint-status |  |  | checkpoint | Variation Details Entered
text | 0bd5f1ed-6bcb-5a7e-aef9-9f4385bc4a0c |  | textbox | Description of work
text | b152750a-6ec8-5808-9b7b-985a73ccece6 |  | textbox | Reason for variation (unless stated in instruction)
text | 4408c22f-b265-5091-9256-2c60b0b84e40 |  | textbox | Area/Location
text | 696e9576-2d72-5c14-9c2e-59c542fa72e4 |  | textbox | As directed and requested by
text | 4290ab57-4e30-53dd-afea-41c8f54f5735 |  | textbox | Date
text | 2cdd1c83-9f0f-5015-983e-caa9e8ffc0c7 |  | textbox | Normal Hours
text | 0eda69e3-d6d6-5a5a-acb5-70337108f507 |  | textbox | Overtime Hours
text | a42fbb72-da56-574b-8ebf-298a5ecdbc63 |  | textbox | Material used to complete task
checkpoint-status |  |  | checkpoint | Variation Completed
checkpoint-group |  |  | section | Sign Off
checkpoint-status |  |  | checkpoint | Variation signed
label | f034977e-b9d3-5e0a-a184-1f823b07707d |  | note | I hereby authorise you to carry out the extra work detailed above and I agree that the same shall be paid as an addition to your original contract order
holdpoint |  |  | signoff | Builder / Client signature