## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | SYM-0388-ITP-003 Bored Piles [C] | itp |  |  |  |  | SYM-0388-ITP-003 Bored Piles [C]
section | 1.0 Preliminaries
checkpoint | 1.1 - Documentation
label | Ref docs - IFC Drawing
label | Acceptance criteria - Check that you have the latest site and engineering IFC drawings before starting each task/set of tasks.
button | Acceptance | Yes,No,N/A
label | Verification or test by
label | Symal Infrastructure: Key - S
textbox | Symal Infrastructure: Initial/date
checkpoint-no-status | 1.1.1 - Lot Map
button | Lot map uploaded | Yes,No,N/A
checkpoint | 1.2 - Safety measures and plans
label | Ref docs - Site Documents/ SWMS
label | Acceptance criteria - Traffic Control Plan, Safety Plan, Environmental Management Plan, Symal Infrastructure Site Documents, Subcontractor SWMS.
button | Acceptance | Yes,No,N/A
label | Verification or test by
label | Symal Infrastructure: Key - S
textbox | Symal Infrastructure: Initial/date
checkpoint | 1.3 - Excavation permit
label | Ref docs - Symal Infrastructure GPP
label | Acceptance criteria - Have services within the works area been identified and a group penetration permit covers the area, is current and signed onto by the works crew? Check underground and overheads services.
button | Acceptance | Yes,No,N/A
label | Verification or test by
label | Symal Infrastructure: Key - H
textbox | Symal Infrastructure: Initial/date |  | H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.4 - Piling Plant and Equipment
label | Ref docs - TfNSW B59 Cl 3.3
label | Acceptance criteria - Details of the proposed piling equipment and method are submitted with certification.
button | Acceptance | Yes,No,N/A
label | Verification or test by
label | Symal Infrastructure: Key - H
textbox | Symal Infrastructure: Initial/date
note | Shoalhaven City Council: Key - H
textbox | Shoalhaven City Council: Sign date
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.5 - Steel Reinforcement Material
label | Ref docs - IFC Drawing, TfNSW B59 Cl 2.3
label | Acceptance criteria - Certification Authority for Reinforcing Steel (ACRS) Certificate Submitted. Material test certificate Submitted.
button | Acceptance | Yes,No,N/A
label | Verification or test by
label | Symal Infrastructure: Key - S
textbox | Symal Infrastructure: Initial/date
note | Shoalhaven City Council: Key - W
textbox | Shoalhaven City Council: Sign date
label | Remarks / record (eg. test frequency, reports, certificates, checklist etc) - Steel reinforcement for piles must conform to Specification TfNSW B80.
checkpoint | 1.6 - Concrete Mix Design
label | Ref docs - TfNSW B59 Cl 2.2, TfNSW B80 Annexure B80/G
label | Acceptance criteria - Mix designs have been reviewed by the Superintendent. Use only self-compacting concrete or high workability concrete conforming to Annexure B80/G of TfNSW B80, as approved by the Principal.
button | Acceptance | Yes,No,N/A
label | Verification or test by
label | Symal Infrastructure: Key - S
textbox | Symal Infrastructure: Initial/date
note | Shoalhaven City Council: Key - H
textbox | Shoalhaven City Council: Sign date
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.7 - Engineering Certification
label | Ref docs - TfNSW B59 Cl 3.4.1
label | Acceptance criteria - Drawings and calculations certified by a Chartered Professional Geotechnical Engineer, verifying that under the proposed set up and site conditions, the proposed piling equipment and working platforms or supports will operate safely.
button | Acceptance | Yes,No,N/A
label | Verification or test by
label | Symal Infrastructure: Key - S
textbox | Symal Infrastructure: Initial/date
section | 2.0 Bored Pile Excavation and Cleaning
checkpoint | 2.1 - Set out
label | Ref docs - IFC Drawings
label | Acceptance criteria - Set out the site with adequate recovery pegs and survey markers so that the drilling and/or piling rig can be set up accurately at the specified location and aligned correctly for each pile.
button | Acceptance | Yes,No,N/A
label | Verification or test by
label | Symal Infrastructure: Key - S
textbox | Symal Infrastructure: Initial/date
note | Shoalhaven City Council: Key - H
textbox | Shoalhaven City Council: Sign date
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.2 - Commencement of excavation of bored pile
label | Ref docs - TfNSW B59 Cl 4.1
label | Acceptance criteria - Bored pile Set out and any additional borehole required are completed. Borehole logs are submitted.
label | • If not previously submitted, details of the following:
label | (i) Extent of temporary casing or details of drilling fluids where proposed for each bored pile.
label | (ii) Method of placing concrete in the bored pile including size and number of any proposed tremie pipes (refer to Clause 6.5).
button | Acceptance | Yes,No,N/A
label | Verification or test by
label | Symal Infrastructure: Key - H
textbox | Symal Infrastructure: Initial/date
note | Shoalhaven City Council: Key - H
textbox | Shoalhaven City Council: Sign date
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.3 - Temporary Casings
label | Ref docs - TfNSW B59 Cl 4.2
label | Acceptance criteria - Drive or sink the temporary casing through any inferior materials, without damaging it, to seal its toe in the founding layer.
label | • Control the alignment of the casing with sufficient accuracy to ensure that the drilling head can be inserted and withdrawn without fouling against the casing.
button | Acceptance | Yes,No,N/A
label | Verification or test by
label | Symal Infrastructure: Key - S
textbox | Symal Infrastructure: Initial/date
checkpoint | 2.4 - Drilling Fluids
label | Ref docs - TfNSW B59 Cl 4.3
label | Acceptance criteria - The drilling fluid is appropriate for the ground conditions and the groundwater at the site and the method of bored pile excavation.
button | Acceptance | Yes,No,N/A
label | Verification or test by
label | Symal Infrastructure: Key - S
textbox | Symal Infrastructure: Initial/date
checkpoint | 2.5 - Bored Pile Excavation
label | Ref docs - TfNSW B59 Cl 4.4
label | Acceptance criteria - Record and measure the operating parameters of the drilling rig when excavating the bored pile.
button | Acceptance | Yes,No,N/A
label | Verification or test by
label | Symal Infrastructure: Key - S
textbox | Symal Infrastructure: Initial/date
checkpoint | 2.6 - Excavated Spoil
label | Ref docs - TfNSW B59 Cl 3.5
label | Acceptance criteria - Removal all spoil off site during excavation works. Submission of methodology for any spoil stockpile and proposed cartage route and drop-off.
button | Acceptance | Yes,No,N/A
label | Verification or test by
label | Symal Infrastructure: Key - S
textbox | Symal Infrastructure: Initial/date
checkpoint | 2.7 - Final Pile Toe Level
label | Ref docs - TfNSW B59 Cl 4.5.1
label | Acceptance criteria - Inspection of the footing material at pile toe level by Symal’s Geotechnical Engineer to ensure rock socket depth is achieved.
label | • Symal’s Geotechnical Engineer directs excavation of a bored pile to a level lower than shown on the Drawings?
label | • Principal accepted the level as the final pile toe level to satisfy design requirement?
button | Acceptance | Yes,No,N/A
textbox | Final Level:
label | Verification or test by
label | Symal Infrastructure: Key - S
textbox | Symal Infrastructure: Initial/date
note | Shoalhaven City Council: Key - H
textbox | Shoalhaven City Council: Sign date
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.8 - Roughening Sides and Cleaning Bored Pile
label | Ref docs - TfNSW B59 Cl 4.5.2
label | Acceptance criteria - Roughen the side of the rock socket as specified. Remove debris and surface smear and expose intact rock over the side and base of the rock socket.
button | Acceptance | Yes,No,N/A
label | Verification or test by
label | Symal Infrastructure: Key - S
textbox | Symal Infrastructure: Initial/date
checkpoint | 2.9 - Acceptance of Bored Pile
label | Ref docs - TfNSW B59 Cl 4.5.3
label | Acceptance criteria - Notification that the bored pile excavation is complete.
label | • Submitted verification documents, verifying that the bored pile has been excavated to the design position, size and level.
label | • De-sanded and re-circulated the drilling fluid before concrete placing, drilling fluid samples are tested to verify conformity from the bottom of the bored pile.
button | Acceptance | Yes,No,N/A
label | Verification or test by
label | Symal Infrastructure: Key - H
textbox | Symal Infrastructure: Initial/date
note | Shoalhaven City Council: Key - H
textbox | Shoalhaven City Council: Sign date
label | Remarks / record (eg. test frequency, reports, certificates, checklist etc) - Following acceptance of bored pile, keep the bored pile side and base in a clean and stable condition without contamination or softening, until concrete is placed
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.10 - Indirect Examination of Bored Pile
label | Ref docs - TfNSW B59 Cl 4.6
label | Acceptance criteria - Verify conformity of the depth of each bored pile using a weighted tape at a minimum of three locations of the bored pile.
button | Acceptance | Yes,No,N/A
label | Verification or test by
label | Symal Infrastructure: Key - S
textbox | Symal Infrastructure: Initial/date
section | 3.0 Reinforcement Placing
checkpoint | 3.1 - Cage and Bored Pile Inspection
label | Ref docs - TfNSW B59 Cl 5.1
label | Acceptance criteria - Notify the Principal at least 24 hours prior to proposed time of placement of the reinforcement cage into bored pile.
button | Acceptance | Yes,No,N/A
label | Verification or test by
label | Symal Infrastructure: Key - W
textbox | Symal Infrastructure: Initial/date
note | Shoalhaven City Council: Key - W
textbox | Shoalhaven City Council: Sign date
checkpoint | 3.2 - Placing Steel Reinforcement Cage
label | Ref docs - TfNSW B59 Cl 5.2
label | Acceptance criteria - Certification that the bored pile is clean, and that all loose and adhering materials have been cleaned from the reinforcement cage.
button | Acceptance | Yes,No,N/A
label | Verification or test by
label | Symal Infrastructure: Key - H
textbox | Symal Infrastructure: Initial/date
note | Shoalhaven City Council: Key - H
textbox | Shoalhaven City Council: Sign date
label | Remarks / record (eg. test frequency, reports, certificates, checklist etc) - Place the steel reinforcement and concrete within 24 hours of the excavation of the pile hole.
holdpoint | AUTHORITY HOLDPOINT
section | 4.0 Concrete Supply and Placing
checkpoint | 4.1 - Dewatering
label | Ref docs - TfNSW B59 Cl 6.3
label | Acceptance criteria - Approval from Principal if dewatering is required.
label | Acceptance - Before Backfill
label | Verification or test by
label | Symal Infrastructure: Key - S
textbox | Symal Infrastructure: Initial/date
checkpoint | 4.2 - Concrete Supply
label | Ref docs - TfNSW B59 Cl 6.4
label | Acceptance criteria - Provide a continuous supply of concrete so that each bored pile is concreted in one uninterrupted operation.
button | Acceptance | Yes,No,N/A
label | Verification or test by
label | Symal Infrastructure: Key - S
textbox | Symal Infrastructure: Initial/date
note | Shoalhaven City Council: Key - H
textbox | Shoalhaven City Council: Sign date
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.3 - Concrete Placing
label | Ref docs - TfNSW B59 Cl 6.5, TfNSW B90 Cl 9.2
label | Acceptance criteria - Tremie pipe and hopper are used to place the concrete.
label | • Concrete is placed in a continuous process from the base to above the top of the pile.
label | • Concrete testing for compressive strength at 28 days
button | Acceptance | Yes,No,N/A
label | Verification or test by
label | Symal Infrastructure: Key - S
textbox | Symal Infrastructure: Initial/date
label | Remarks / record (eg. test frequency, reports, certificates, checklist etc) - Carry out placing of concrete on test members when there is uncertainty about the outcome of placing concrete in piles.
checkpoint | 4.4 - Tremie
label | Ref docs - TfNSW B59 Cl 6.6
label | Acceptance criteria - The tremie pipe is rigid and watertight throughout.
label | • Appropriate tremie pipe size.
label | • Appropriate tremie placement procedure as per B59 Cl 6.6.
button | Acceptance | Yes,No,N/A
label | Verification or test by
label | Symal Infrastructure: Key - S
textbox | Symal Infrastructure: Initial/date
note | Shoalhaven City Council: Key - W
textbox | Shoalhaven City Council: Sign date
checkpoint | 4.5 - Concreting Record
label | Ref docs - TfNSW B59 Cl 6.7
label | Acceptance criteria - The depth of the tremie pipe outlet.
label | • The level of the concrete in the bored pile.
label | • The corresponding volume of concrete placed.
button | Acceptance | Yes,No,N/A
label | Verification or test by
label | Symal Infrastructure: Key - S
textbox | Symal Infrastructure: Initial/date
checkpoint | 4.6 - Casing Extraction
label | Ref docs - TfNSW B59 Cl 6.8
label | Acceptance criteria - Withdraw any temporary casing slowly whilst the concrete is still fluid at close to the original slump.
label | • Maintain a sufficient head of concrete.
label | • Maintain the direction of pull on the temporary casing along the axis of the pile.
label | • Last section of casing not withdrawn until the concreting operation is completed.
button | Acceptance | Yes,No,N/A
label | Verification or test by
label | Symal Infrastructure: Key - S
textbox | Symal Infrastructure: Initial/date
checkpoint | 4.7 - Temporary Casings Left in Place
label | Ref docs - TfNSW B59 Cl 6.9
label | Acceptance criteria - Temporary casings may be left in place when approved by the Principal.
button | Acceptance | Yes,No,N/A
label | Verification or test by
label | Symal Infrastructure: Key - S
textbox | Symal Infrastructure: Initial/date
checkpoint | 4.8 - Cut-Off And Clean Up of Top of Pile
label | Ref docs - IFC Drawings, TfNSW B59 Cl 6.10
label | Acceptance criteria - Concrete and/or casing above the cut-off level is carefully removed without damaging the permanent work not earlier than 24 hours after completion of placement of concrete.
label | • The top of the pile to be embedded in the substructure is undamaged, sound, free of any laitance and loose material and have a surface roughness profile not less than 3 mm.
button | Acceptance | Yes,No,N/A
label | Verification or test by
label | Symal Infrastructure: Key - S
textbox | Symal Infrastructure: Initial/date
section | 5.0 Conformance Check
checkpoint | 5.1 - Tolerances
label | Ref docs - IFC Drawings
label | Acceptance criteria - Tolerances on pile installation must conform to Section 7 of AS 2159. Inclination tolerance for vertical piles must not exceed 1%.
button | Acceptance | Yes,No,N/A
label | Verification or test by
label | Symal Infrastructure: Key - S
textbox | Symal Infrastructure: Initial/date
checkpoint | Works complete
text | Name:
text | Position:
text | Date Completed:
holdpoint | Sign ITP
checkpoint | Lot Conformance
dropdown | Lot Status | Awaiting Hold Point Release, Awaiting NCR Closure, Awaiting Test Results, Awaiting Verification, Cancelled, Closed-out, Outstanding, Work In Progress
text | Lot opened date:
text | Lot opened by:
text | Date lot closed:
button | NCR raised? | Yes, No
text | NCR Raised Date:
button | NCR closed? | Yes, No
text | NCR Closed Date:
text | NCR Number:
text | Comments
holdpoint | Sign ITP