## Table 1
SPARK – North East Link – Primary Package Inspection and Test Plan (ITP)
ITP Title: Guard Fence Installation ITP Number: NEL-CNT-SDC-2990-PQA-ITP-0057 Rev 0
LOT Number:
Primary Asset Location Code:
Discipline:
OFFICIAL: Sensitive
Spark NELP Approval Record
Function |  |  |  | Position |  |  |  | Name |  | Signature |  |  |  | Date
Prepared By |  |  |  | Quality Representative |  |  |  | Abiola Olulana |  | Digitally Abiola Olulana Olulana Date: 20 +11'00' |  |  |  | signed by Abiola 22.11.03 16:42:20
Reviewed By |  |  |  | Project Engineer / Site Engineer |  |  |  | Nancy Gatto
Approved By |  |  |  | Quality Manager |  |  |  | Greg Iro |  | Digital Date: +11'00 |  |  |  | ly signed by Greg Iro 2022.11.03 08:49:53 '
Note:
1. Ensure all Records or Checklist References are attached and that each Inspection Requirement is clearly named, signed, and dated. 2. Ensure every Records or Checklist References attached are legible 3. This Inspection Test Plan may be generic – ensure the requirement is demographically clear to your scope of work 4. Verification Inspections where applicable for the IREA stated as “Witness” or “Hold” shall be formally notified for their engagement and with sufficient advance notice time (i.e. 3 days or as agreed with the Sub-IREA Representative and/or the Nominated Authority) 5. All Nominated Authority Hold Points are Witness Points for Sub-IREA 6. The Sub-IREA representative is not required to physically sign-off on ITPs
ITP – Guard Fence Installation Spark PMS Doc# MSF28-2-NEL Rev 3 Document Number: NEL-CNT-SDC-2990-PQA-ITP-0057. Revision: 0 Management System - Uncontrolled Document when Printed Webuild Source Doc# MSF28-2
OFFICIAL: Sensitive | [8 empty] | Page 1 of 5
Project: SPARK – North East Link Primary Package Client: State of Victoria and the North East Link State Tolling Corporation
ITP Title: Guard Rail Fence Installation Description: This ITP covers the installation of guard rail fence | [11 empty] | References: CQMP, IFC Drawings, PSDR, RDN 06-04 VicRoads 708, 703, 812, 820 Standards:
ITP No: NEL-CNT-SDC-2990-PQA-ITP-0057 Rev No: 0
Lot No: Location: Ch: to Offset: to Layer:
Item No. | Resp. Person | Inspection and Test Activity |  |  | Specification Reference |  | Acceptance Criteria |  |  |  | Test Method | Test Freq. | Inspection/Verification (Name, signature & date) | [6 empty] | Records/ Documents |  | Field Notes / Comments
[13 empty] | Sub- Contractor |  |  | Spark NEL Engineer |  | Nominated Authority | IREA
1 | Preliminaries (Include all aspects of Materials, Approvals, IFC Drawings, etc. Ensure all required permits have been raised prior to commencing works)
1.1 | PE | IFC Drawings Issued |  |  | CQMP |  | IFC Drawings, approved plans, technical specification issued for construction |  |  |  | V | PW | NR |  |  | HP |  | NR | NR | IFC Drawings
1.2 | PE | Crushed Rock Mix Approved |  |  | VR 812.04 |  | Crushed Rock Mix is registered with VicRoads certificate |  |  |  | V | PW | NR |  |  | HP |  | HP | WP | Mix Registered on InEight
1.3 | PE | Concrete Mix Approved |  |  | VicRoads 703.05 VicRoads 708.05 |  | Concrete shall comply with AS1379 and as specified in VicRoads 703 for either: - Portland cement-based concrete, N20 strength grade or - Geopolymer concrete, 20MPa strength Use of chemical admixtures to comply with requirements of Section 703 |  |  |  | V | PW | NR |  |  | HP |  | NR | NR | Mix design:
1.4 | PE | Guard Fence Components |  |  | VicRoads 708.05 VR708.04 VR Road Design Note 06-04 |  | Only safety barrier products listed in VicRoads Road Design Note 06-04 shall be used. Steel w-beams, posts and all plastic components of proprietary end treatments unobtrusively and permanent in text not more than 20mm high, the following information: - name of manufacturer - batch number or date - strength grade and base metal thickness - Test certificate demonstrating compliance of materials and components with the specification for the proprietary Guard Fence system and VicRoads 708 - Signed statement and certificates of compliance have been accepted by the Nominated Authority (14 days prior to installation) W-beams to AS1594 Grade HA350 Posts to AS1594 Grade HA250 Steel components hot dip galvanised |  |  |  | R | PW | NR |  |  | HP |  | HP | WP | ☐ Test certificates ☐ Manufacturer’s compliance certificate
Project: SPARK – North East Link Primary Package Client: State of Victoria and the North East Link State Tolling Corporation
ITP Title: Guard Rail Fence Installation Description: This ITP covers the installation of guard rail fence | [11 empty] | References: CQMP, IFC Drawings, PSDR, RDN 06-04 VicRoads 708, 703, 812, 820 Standards:
ITP No: NEL-CNT-SDC-2990-PQA-ITP-0057 Rev No: 0
Lot No: Location: Ch: to Offset: to Layer:
Item No. | Resp. Person | Inspection and Test Activity |  |  | Specification Reference |  | Acceptance Criteria |  |  |  | Test Method | Test Freq. | Inspection/Verification (Name, signature & date) | [6 empty] | Records/ Documents |  | Field Notes / Comments
[13 empty] | Sub- Contractor |  |  | Spark NEL Engineer |  | Nominated Authority | IREA
Non-Standard Post Lengths (if used) are to have details of the measures proposed and evidence of the effectiveness of the barrier system maintenance submitted for consideration by the NA
1.5 | SE | Material Supply inspection |  |  | VicRoads 708.06 |  | Materials are free from distortion and damage |  |  |  | V | PW | NR |  |  | WP |  | NR | NR | Completed incoming inspection checklist
2 | Operations (Include Work Execution – Installation / Manufacturing Process step-by-step)
2.1 | SE | Survey of guard fence alignment |  |  | VicRoads 708.08 IFC Drawings |  | Confirm and visually inspect survey set out as per the IFC drawing offsets Prior to installation, the contractor shall confirm with the Nominated Authority the required location and length of all guard fence |  |  |  | V | PL | NR |  |  | HP |  | HP | WP | Survey Report
2.2 | SE | Excavation of maintenance strip |  |  | VicRoads 703.20 |  | Excavation extents comply with IFC drawings. Extends minimum 300mm clear of the rear of the post and 300mm clear from the face of w-beam, 75mm deep |  |  |  | V | PL | NR |  |  | WP |  | NR | NR | Photos
2.3 | SE | Lay crushed rock |  |  | VicRoads 703.21 VicRoads 812 |  | Bedding material is a compacted size 20mm 3 crushed rock (Section 812) or Class 3 crushed concrete (section 820) |  |  |  | V | PL | NR |  |  | WP |  | NR | NR | Photos, Delivery Dockets
2.4 | SE | Install posts |  |  | VicRoads 708.7 VicRoads 708.8 VicRoads 708.9 |  | Post holes in rock shall have a 75mm minimum clearance from back of post to face of hole Post holes in rock to be backfilled with granular material. Other post holes to be backfilled with selected earth, free of rock. Backfilling compacted in 100mm layers. Variation from true plan position of posts ±20 mm Variation of posts from Vertical (measured at top of the post) ±15mm |  |  |  | V | PL | NR |  |  | WP |  | NR | NR | Photos
2.5 | SE | Install W- beams |  |  | VicRoads 708.8 VicRoads 708.11 |  | W-beam sections to be lapped so exposed ends face away from near-side approaching traffic. Variation of line of w-beams from specified vertical profile ±10 mm Variation of w-beams from specified horizontal |  |  |  | V | PL | NR |  |  | HP |  | NR | NR
Project: SPARK – North East Link Primary Package Client: State of Victoria and the North East Link State Tolling Corporation
ITP Title: Guard Rail Fence Installation Description: This ITP covers the installation of guard rail fence | [11 empty] | References: CQMP, IFC Drawings, PSDR, RDN 06-04 VicRoads 708, 703, 812, 820 Standards:
ITP No: NEL-CNT-SDC-2990-PQA-ITP-0057 Rev No: 0
Lot No: Location: Ch: to Offset: to Layer:
Item No. | Resp. Person | Inspection and Test Activity |  |  | Specification Reference |  | Acceptance Criteria |  |  |  | Test Method | Test Freq. | Inspection/Verification (Name, signature & date) | [6 empty] | Records/ Documents |  | Field Notes / Comments
[13 empty] | Sub- Contractor |  |  | Spark NEL Engineer |  | Nominated Authority | IREA
alignment ±20 mm Orientation of block and/or post to w-beam +0 mm, - 15 mm Top of bolt head relative to w-beam -0 mm, +5 mm All bolts to be fully tightened
2.6 | SE | Install end- treatments |  |  | VicRoads 708.8, |  | Ropes are not twisted Nuts at the end of each rope is tightened to a minimum torque of 50Nm or as per manufacturers requirements |  |  |  | V | PL | NR |  |  | WP |  | NR | NR
2.7 | SE | Concrete maintenance strip |  |  | VicRoads 708.12 |  | Edges of the infill area are boarded up prior to placing concrete or expansion joint is sawcut to 75% concrete depth. Where concrete strip is adjacent to kerb or pavement, a cork expansion joints is produced. Full depth expansion joints provided perpendicular to the line of steel beam guard fence, 200mm each side of every post Concrete is as per approved mix design |  |  |  | V | PL | NR |  |  | WP |  | NR | NR | Delivery Dockets, Maintenance Strip Location Record
3 | Post Operations (Include Inspection and Testing)
3.1 | SE | Concrete Strength Results |  |  | VicRoads 703.11 |  | Testing cylinders to be taken per 50m3, 28-day Compressive Strength = 20MPa |  |  |  | V | PL | NR |  |  | HP |  | NR | NR | Concrete Strength Results
3.2 | SE | Compliance Audit |  |  | VicRoads 708.10 |  | Safety Barrier compliance Audit undertaken for entire project Guard Fence Installation and Certificate of Compliance signed by the Contractor and Licensed supplier provided. |  |  |  | V | X1 | NR |  |  | HP |  | HP | WP | Compliance Audit Certificate of Compliance
4 | Quality
4.1 | QSR | Identification and control of non-conforming |  |  | CQMP Section 8.3 |  | Review and confirm closure of NCR’s and associated RFI’s prior to closing of construction lot |  |  |  | R | PL |  |  |  | HP |  |  |  | NCR closed with related documentation
Project: SPARK – North East Link Primary Package Client: State of Victoria and the North East Link State Tolling Corporation
ITP Title: Guard Rail Fence Installation Description: This ITP covers the installation of guard rail fence | [11 empty] | References: CQMP, IFC Drawings, PSDR, RDN 06-04 VicRoads 708, 703, 812, 820 Standards:
ITP No: NEL-CNT-SDC-2990-PQA-ITP-0057 Rev No: 0
Lot No: Location: Ch: to Offset: to Layer:
Item No. | Resp. Person | Inspection and Test Activity |  |  | Specification Reference |  | Acceptance Criteria |  |  |  | Test Method | Test Freq. | Inspection/Verification (Name, signature & date) | [6 empty] | Records/ Documents |  | Field Notes / Comments
[13 empty] | Sub- Contractor |  |  | Spark NEL Engineer |  | Nominated Authority | IREA
products or services (if applicable)
4.2 | QSR | Check all quality records for lot closure |  |  | CQMP Section 8.3 |  | All applicable quality records are complete |  |  |  | R | PL |  |  |  | HP |  |  |  | Compiled documents (all data reports and records)
Legend:
Responsibility | [10 empty] | Method |  | Inspection / Verification |  |  |  | Test Frequency |  |  | Other
SS: Site Supervisor SE: Site Engineer PE: Project Engineer SPE: Senior Project Engineer GE: Geotechnical Engineer PS: Project Surveyor | [5 empty] | PSM: Project Systems Manager QSR: Quality Site Rep. STR: Structural Engineer SSR: Site Safety Rep. EMR: Environmental Management Rep. NA: Nominated Authority (Release of HP) IREA: Independent Reviewer (Observer) |  |  |  |  | V: Verify I: Inspection R: Review T: Test |  | HP: Hold Point WP: Witness Point NR: Not Required |  |  |  | PW: Prior to Works PL: Per Lot F: Full or 100% Inspection or Testing X1: Inspect or Test at Specified Frequency X2: Random Inspection or Test |  |  | QP: Quality Plan RFI: Request for Information NCR: Non-Conformance VC: Verification Checklist XXXX: Sequential Number from Doc Control
DDD – Types: B – Building, C – Civil, G – General, M – Mechanical & Electrical, I – Motorway Operations System (ITS), S – Structure, O – Tolling, T – Tunnel, U – Urban Design & Landscape
Supplier/Subcontractor: (If applicable) |  |  | Name | [6 empty] | Signature and Date |  |  | Spark-NELP REP |  | Name | [5 empty] | Signature and Date
Lot closure comments:
Spark NELP QA Rep: Name Signature: Date:
Geoffrey Britto
3/11/22