## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-sectioned |  |  | checklist | NEL-CNT-SDC-2990-PQA-ITP-0027 Rev 1 - Type A Fill Placement | itp |  |  |  | Yes | NEL-CNT-SDC-2990-PQA-ITP-0027 Rev 1 - Type A Fill Placement | 2f612066-25d4-4a30-993e-48b3ea4845f1
checkpoint-group |  |  | section | 1.0 Preliminaries (Include all aspects of Materials, Approvals, IFC Drawings, etc. Ensure all required permits have been raised prior to commencing works)
checkpoint-status |  |  | checkpoint | 1.1 - IFC Drawings issued
label | d7ef18d2-87e0-5962-8058-efb287e9848f |  | note | Responsible Person - PE
label | 66102036-cc6f-5737-acd0-952e46f2426d |  | note | Specification Reference - IFC Drawing Number: PSDR Part 6 Section 2(h)
label | f71aa1d0-4f18-529d-b3fc-653fb0fc905b |  | note | Acceptance Criteria - IFC Drawings, approved plans, technical specification issued for construction
label | 1926385d-c194-5a25-8e5c-cb998fa81a10 |  | note | • Construction of any Construction Package must not commence until at least 5 Business days after the later of when:
label | 88b2f884-dea4-5cad-94b6-2380200f4fa0 |  | note | i). the Construction Documentation has been submitted to the State, the IREA and any Returned Asset Owner (if applicable) in accordance with section 2(f) and ii). Any requirements of the IREA under section 2(g) have been complied with.
label | 5b5a0dd8-fc79-59b8-b4c8-8bec213f352b |  | note | Test Method - V
label | 853ee677-b957-5f69-80c9-ff919f965e8b |  | note | Test Frequency - PW
label | 8570428b-2356-5ff2-a62e-1969de568f20 |  | note | Inspection/Verification (Name, signature & date): Sub-Contractor - NR
label | a99a717c-7116-539b-9cfe-6efa15bb1d7e |  | note | Inspection/Verification (Name, signature & date): Spark NEL Engineer - HP
label | 62be0e7c-8b64-5dcb-9ab2-94a2575f7906 |  | note | Inspection/Verification (Name, signature & date): Nominated Authority - NR
label | 3bc3f78f-ec67-5637-bfca-3561ca8a41b1 |  | note | Inspection/Verification (Name, signature & date): IREA - NR
label | 4c8bd0e7-8e9b-5601-a8d3-8b17011d4a7f |  | note | Records/Documents - IFC Drawings
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 1.2 - Survey Set Out
label | 72a4f229-ef83-5cbf-b7c9-3ad4c7246a36 |  | note | Responsible Person - PE
label | cef187d6-1f07-52e9-ad37-a5ea1a862d20 |  | note | Specification Reference - CQMP, IFC Drawings
label | 23a77b68-625a-5226-aa2d-42d3e6c58109 |  | note | Acceptance Criteria - Confirmation and visually inspect survey set out as per the IFC Drawing.
label | 7353232c-e854-5679-958a-f5316422ddea |  | note | Test Method - V
label | d554b5d8-baf8-576c-93fd-4ebbc7c2d79b |  | note | Test Frequency - PW
label | f7c2e6e5-e7c1-59e7-841e-81e933b6c878 |  | note | Inspection/Verification (Name, signature & date): Sub-Contractor - HP
label | 64bc7bb0-9f41-5c7d-a651-c7b6b11f2839 |  | note | Inspection/Verification (Name, signature & date): Spark NEL Engineer - HP
label | 1ac78ca0-6941-59f8-9d46-bc2e5e0afa28 |  | note | Inspection/Verification (Name, signature & date): Nominated Authority - NR
label | ca221210-a5bb-5d8c-873f-4bc356f9fd46 |  | note | Inspection/Verification (Name, signature & date): IREA - NR
label | 5d1f904f-f134-5d89-983b-d7e245005aa9 |  | note | Records/Documents -
text | 38e8c22c-76a0-572c-9764-cb3e6e017ecc |  | textbox | • InEight Document References:
label | cfe951f8-da7d-55c0-995a-c88ab425b9a6 |  | note | • Lot Map
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 1.3 - Calibration Approval
label | 4634d89d-da68-5dd5-8f61-bc65f4fba8f5 |  | note | Responsible Person - PE
label | 1a65c87d-d037-51c4-b666-805e0e82bbc1 |  | note | Specification Reference - CQMP
label | 93e3f8cf-4981-59f2-84f9-3acd1a0f841e |  | note | Acceptance Criteria - Equipment calibration certificates filed in Ineight. Ensure all equipment associated with the relevant works is calibrated.
label | 3eabe024-7be9-5014-ad62-8f58a04fd264 |  | note | Test Method - V
label | fd7bab21-7a85-5a7c-9acc-f5db0ea83243 |  | note | Test Frequency - PW
label | 69ca8d45-fe78-531a-b409-4289366b000d |  | note | Inspection/Verification (Name, signature & date): Spark NEL Engineer - WP
label | 1d5fdd0d-ac64-507c-8c53-a3db05790eb7 |  | note | Records/Documents -
text | f66b3493-e55e-5059-825b-e549d03bc833 |  | textbox | • InEight Document References:
checkpoint-group |  |  | section | 2.0 Operations (Include Work Execution – Installation / Manufacturing Process step-by-step)
checkpoint-status |  |  | checkpoint | 2.1 - Precondition
label | 1d462957-5a2c-5394-8a58-5e1239126d70 |  | note | Responsible Person - Nominated Authority
label | 17336f69-7995-50a0-af6c-2a9743f2a929 |  | note | Specification Reference - VR 204.10 (b), VR 204.04, VR 204.06
label | b087c5d8-4033-5a0c-8326-3924255a4006 |  | note | Acceptance Criteria - No fill placement shall commence on the prepared areas until the area has been reviewed by the Superintendent.
label | ad29d460-6ba6-5ff9-b265-ad40457e9a5b |  | note | • Note: Material classified as silt, either before of after compaction, is not acceptable as Type A material without stabilisation to the satisfaction of the Superintendent (VR204.04b).
label | e5b1fc31-3174-5860-a746-e36a4d7865e7 |  | note | Test Method - V
label | 34c4c9bb-97a4-5563-898e-3e37e00dfff5 |  | note | Test Frequency - PW
label | 93215ffc-74af-5a5a-8e70-76af3139c4dc |  | note | Inspection/Verification (Name, signature & date): Sub-Contractor - NR
label | 38f19707-e3d2-5697-a5e4-fec7f3dba77f |  | note | Inspection/Verification (Name, signature & date): Spark NEL Engineer - WP
label | 14627ae8-46ca-545d-9aa0-163db32d776e |  | note | Inspection/Verification (Name, signature & date): Nominated Authority - HP
label | 03a01b34-6152-591c-b639-16c67bb8d697 |  | note | Inspection/Verification (Name, signature & date): IREA - WP
label | 8f2d046d-08c4-56d8-ba9f-b577e29f2d85 |  | note | Records/Documents - Signed ITP
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.2 - Verify Material Properties
label | e0f51df7-60ac-5af0-9d27-5b3ed91eed99 |  | note | Responsible Person - PE
label | 5e946478-0e41-5461-ada5-311a7a642290 |  | note | Specification Reference - IFC Drawings VR 204.04
label | 74033381-7a32-5f8f-9a14-202356c6a96f |  | note | Acceptance Criteria - Approved material won from site or approved imported fill shall be moisture conditioned in accordance with the recommendations of the Geotechnical
label | 01761808-5853-570a-bccf-394209434b1e |  | note | • Report prior to being placed in uniform horizontal layers of 200mm maximum depth.
label | fe5467cb-7274-58a6-8758-a593fd0983e8 |  | note | Test Method - V
label | 1e7b1db4-e565-5cb4-81d6-6e6c9a533f91 |  | note | Test Frequency - PW
label | b0c5fcdf-7221-5f5a-be0f-8b514a81bc2a |  | note | Inspection/Verification (Name, signature & date): Sub-Contractor - NR
label | bfa7002f-ed97-5908-bd89-f847bd7289d4 |  | note | Inspection/Verification (Name, signature & date): Spark NEL Engineer - WP
label | c8e3fc73-6735-5f2a-abfe-b60bb8bc0d59 |  | note | Inspection/Verification (Name, signature & date): Nominated Authority - NR
label | 5f54e6c7-5bae-5ef0-9b9a-94309c1cafea |  | note | Inspection/Verification (Name, signature & date): IREA - NR
label | 3b502c76-ffa6-54dc-903b-002b83831162 |  | note | Records/Documents - NATA Test Reports
label | a3efda79-36a6-5df3-9d7b-924d94feabf4 |  | note | • Geotechnical Report
label | 1303754f-665e-5412-876a-42dc75072c01 |  | note | • Material Certificates
checkpoint-status |  |  | checkpoint | 2.3 - Fill Placement
label | d0a34f76-417b-594a-a937-2a9b5ea68aab |  | note | Responsible Person - SE
label | 7c73e22f-4c38-5391-900e-49d9f6de3241 |  | note | Specification Reference - IFC Drawing VR 204.10 (d)
label | fd802467-d540-50ba-9c8f-c289b3a7d044 |  | note | Acceptance Criteria - Type A Material
label | e3e4c3af-1099-518f-90bb-302592301d1e |  | note | • Shall be placed in locations shown on the drawings, if surplus Type A material is available, it may be used in locations specified for Type B material.
label | b682b9a5-6532-599d-a48a-1efa0a647597 |  | note | • Type A material shall be spread and compacted in layers not exceeding a compacted thickness of 200mm.
label | 99eb72f0-1988-56de-b053-175cdf2f6727 |  | note | • Type A structural material shall be in accordance with the requirements of clause 204.11 and 204.13 of the VicRoads standards.
label | 07bdb763-2a35-514e-b651-06a10a8d4b9a |  | note | Test Method - V
label | 0dbfd722-32a6-5d0c-b49c-49232896ecb1 |  | note | Test Frequency - PL
label | bfb9c4e8-0629-52b5-b088-67ac43b9081e |  | note | Inspection/Verification (Name, signature & date): Sub-Contractor - NR
label | 5e157d24-d034-59d9-baa1-9b8af2549dcf |  | note | Inspection/Verification (Name, signature & date): Spark NEL Engineer - WP
label | 9e735b7b-0545-5f14-9252-346432e521cf |  | note | Inspection/Verification (Name, signature & date): Nominated Authority - NR
label | a401e776-0d3f-5ea5-b571-6d278ffb35a6 |  | note | Inspection/Verification (Name, signature & date): IREA - NR
label | 71be7d03-0786-52c6-be4e-fd36f8c2740f |  | note | Records/Documents - Delivery Docket
checkpoint-status |  |  | checkpoint | 2.4 - Fill at Structures (If applicable)
label | 5ca00b82-571d-57ff-9cf2-990997c68385 |  | note | Responsible Person - SE
label | 1bcb2f2a-edbc-5f36-89a3-3b29015da717 |  | note | Specification Reference - VR 204.11 (b)
label | 4576b96b-67a0-5238-a4be-816240d4d467 |  | note | Acceptance Criteria - Note: No fill shall be placed against or within 3m of a structure until the foundation for the fill has been reviewed by the Superintendent.
label | 7c68512f-17be-5dc5-9a69-e34c0a598433 |  | note | • No material shall be placed against concrete within 14 days of curing.
label | 6b7f79bc-f564-5ca8-8a0f-d2eef6c220cc |  | note | • In addition to Type A placement at bridge abutments as structural material, embankment material or backfilling within 3m of retaining walls, wing walls, all crown units and culverts with an opening height greater than 1200mm, shall be material of at least Type A material quality.
label | e7525f48-76a6-54ab-9fda-ab18827de1f2 |  | note | Test Method - V
label | 6311263e-8787-55f1-af6c-a0766713612e |  | note | Test Frequency - PL
label | 89aca02b-e299-5a36-8ece-f3a2de7e9b3e |  | note | Inspection/Verification (Name, signature & date): Spark NEL Engineer - WP
label | 1bf00006-197e-5794-a1df-3af4feadd457 |  | note | Inspection/Verification (Name, signature & date): Nominated Authority - HP
label | bc58ba80-f2db-5021-96d9-bc57379c9056 |  | note | Inspection/Verification (Name, signature & date): IREA - WP
label | 07039318-94ef-5417-8974-cf0d16e542b6 |  | note | Records/Documents - Signed ITP
boolean | 5ea0e9d7-5c56-592e-a460-35ac6addcc6e |  | tickbox | • Applicable
boolean | 9850fd7e-7163-5aa1-b247-ed8aae79e29c |  | tickbox | • Not Applicable
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.5 - Test Roll
label | 7d780a65-c38c-5b54-bdd9-7a2a7b8c5973 |  | note | Responsible Person - Nominated Authority
label | 71d83d93-4427-5ab0-83a8-320cc778ba2c |  | note | Specification Reference - IFC Drawings VR 204.12 VR 204.13 VR 173.03
label | 3fc3f4a9-e70b-5ef9-930d-99dc4b1ffe1d |  | note | Acceptance Criteria - All subgrades are to be proof rolled and approved prior to constructing pavements and /or commencement of filling. Test Rolling to be in accordance with VR173.03.
label | 1e8b688f-c3ba-5ada-97a5-e3bedf8a3ff4 |  | note | • Note 1: Areas upon which structural fills are to be constructed, all layers of structural fill, and materials within 150mm of permanent subgrade level in cuttings should be compacted so as to be capable of withstanding test rolling without visible deformation or springing.
label | c9f2a8ad-0edb-5e67-84a0-a0f15b24590e |  | note | • Note 2: Where unstable areas exceed 20% of the area being considered by test rolling, the whole of the area should be ripped, recompacted and re-presented for test rolling.
label | ad50329d-356e-56b8-99f1-3ad2d008a466 |  | note | Test Method - IP
label | a70ba1ed-81b3-562b-9342-89a99850e9a0 |  | note | Test Frequency - PL
label | c8fca879-3ff2-57c1-aa46-04506f37a8c4 |  | note | Inspection/Verification (Name, signature & date): Sub-Contractor - NR
label | 17ddb0d2-b056-5a5c-86e3-046295a49389 |  | note | Inspection/Verification (Name, signature & date): Spark NEL Engineer - NR
label | 3081a47d-5da0-5b3d-99ec-8cf3c3c83061 |  | note | Inspection/Verification (Name, signature & date): Nominated Authority - HP
label | 2e92f83e-c640-50d1-b083-150776763076 |  | note | Inspection/Verification (Name, signature & date): IREA - WP
label | 2efaacbe-a0b3-514e-9b9a-d09f85a66734 |  | note | Records/Documents - Signed ITP
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.6 - Post compaction
label | 72d9a080-bfdf-5090-a31c-073a4ae288a9 |  | note | Responsible Person - SE
label | 3b8d5049-4cae-5581-9fd8-497294186103 |  | note | Specification Reference - IFC Drawings VR 204.14 VR 204.13
label | 739b6d9b-7b98-5489-935a-048085059dcc |  | note | Acceptance Criteria - Refer to table VR204.131 for Type A Material Compaction requirements.
label | 9272d39a-f583-5afb-99f0-6c272055d4ad |  | note | Test Method - T
label | c084f2ae-03a0-59f2-ba2c-ad4e76e01d4d |  | note | Test Frequency - PL
label | 66565325-0c80-54a7-8590-13d608861c6b |  | note | Inspection/Verification (Name, signature & date): Sub-Contractor - NR
label | ce9bf2b9-55bb-59ee-98ad-b804d8a805c6 |  | note | Inspection/Verification (Name, signature & date): Spark NEL Engineer - WP
label | 4e72cdcd-2d04-5100-8fa1-2ce6e6889405 |  | note | Inspection/Verification (Name, signature & date): Nominated Authority - NR
label | 162aa2e1-ddb7-5846-b725-ce157d6ef8c0 |  | note | Inspection/Verification (Name, signature & date): IREA - NR
label | b4933b8e-d504-5db3-ae58-aeef18f658ef |  | note | Records/Documents - NATA Test Records
checkpoint-group |  |  | section | 3.0 Post Operations (Include Inspection and Testing)
checkpoint-status |  |  | checkpoint | 3.1 - Testing Frequency
label | d2d71139-43c2-5ea0-9198-8d3c9e09d304 |  | note | Responsible Person - SE
label | 2166f1fe-f6f8-56ed-9768-7ec9a1c93202 |  | note | Specification Reference - VR 204.14 IFC Drawings
label | 7b984e1d-1c45-5b5d-94b2-8ff4fb394dbb |  | note | Acceptance Criteria - Small Developments Lot surface area <500m2.
label | 95837d61-0e4b-5316-a9c7-02891a1c9d41 |  | note | ○ Large Developments
label | 8ed8797b-2948-5b8b-a41f-65bb5c4cf561 |  | note | • Refer to table VR204.142 for Type A Acceptable lot size and minimum testing frequency.
label | 2e5b0c06-5945-599c-9ade-5d560694657c |  | note | ○ Note 1: where any test in a lot indicates that compliance with the specification has not been achieved, the lot is considered to have failed – the entire lot will need to be reworked and retested.
label | 7018ebc1-df2f-5aeb-995d-6e776eb1a4af |  | note | ○ Note 2: Selection of a lot for testing requires careful consideration.
label | ebce0fa8-2c1c-5d6a-b16a-ce6b161c2955 |  | note | Test Method - T
label | a2d984a8-ac05-571d-9e55-6eddf3391d97 |  | note | Test Frequency - PL
label | 1a290fd1-5ffe-5b37-b417-c7d40a340431 |  | note | Inspection/Verification (Name, signature & date): Sub-Contractor - NR
label | 3cceadb0-559e-53c5-aa98-c52651de8aec |  | note | Inspection/Verification (Name, signature & date): Spark NEL Engineer - WP
label | 6449f98b-151b-57aa-9f67-24cef6c26051 |  | note | Inspection/Verification (Name, signature & date): Nominated Authority - NR
label | 675747d5-3dd5-5a43-a0ee-76b84cc76017 |  | note | Inspection/Verification (Name, signature & date): IREA - NR
label | 7193c098-17db-52f9-aa3e-fa2092ca07ab |  | note | Records/Documents - Signed ITP
checkpoint-status |  |  | checkpoint | 3.2 - CBR/Swell Grading, PI, LL (Post Compaction)
label | 1938da55-6ef2-512e-bfa2-b950120cee3c |  | note | Responsible Person - SE
label | 7aaa8ff5-c6e2-57d7-be1a-39fbda2c10da |  | note | Specification Reference - VR 204 Table 204.041
label | 882883a2-1e85-5a50-a684-c670dfc513aa |  | note | Acceptance Criteria - (1) The Assigned CBR and percentage swell values are to be determined in accordance with VicRoads Code of Practice RC 500.20. Sampling for CBR testing shall be undertaken after field compaction.
label | fb02fc40-bd06-55af-83bf-bfa32686bd43 |  | note | (2) The permeability value is to be determined in accordance with VicRoads Code of Practice RC 500.16. The permeability value is to be determined on specimens manufactured from that fraction of material which passes a 19.0 mm AS sieve, compacted at optimum moisture content and 98% of maximum dry density as determined by testing using standard compactive effort for CBR and swell.
label | 1b0f6137-1960-569c-851b-0638de5bd2f5 |  | note | Test Method - T
label | f389cdd4-3963-57bc-8ce2-fe439d16360a |  | note | Test Frequency - PL
label | 9f1dd19e-6860-583d-8d63-9264081f8ff5 |  | note | Inspection/Verification (Name, signature & date): Sub-Contractor - NR
label | 0460b7da-a6c9-575b-aa45-149c07d55b0c |  | note | Inspection/Verification (Name, signature & date): Spark NEL Engineer - WP
label | 7c67d9db-486f-54ab-9e60-ccbd2dc0286f |  | note | Inspection/Verification (Name, signature & date): Nominated Authority - NR
label | 2fb44320-2721-51d1-956e-c6e11475d679 |  | note | Inspection/Verification (Name, signature & date): IREA - NR
label | bcbb6930-5ed2-5f77-93bc-40005a33c29d |  | note | Records/Documents - NATA Test Records
checkpoint-status |  |  | checkpoint | 3.3 - Conformity with drawings
label | bd168c79-60c3-5222-9c34-b93b9decaa25 |  | note | Responsible Person - SE
label | fceceeee-3a7a-53c1-9c7b-6a3225519406 |  | note | Specification Reference - VR 204.03 Table 204.031 IFC Drawings
label | d88e5161-19df-5d53-8f16-feccdd7f38f3 |  | note | Acceptance Criteria - Scale A requirements:
label | 5de10c09-3e1b-51f9-aa80-addfb24b7f02 |  | note | • The finished surface level to conform to a mean level of +5mm to -15mm and a standard deviation of 12 mm (max).
label | b9757cdc-e750-5fe5-b01f-f76598726116 |  | note | Test Method - V
label | bc546263-352f-547a-ab4c-25c70b774244 |  | note | Test Frequency - PL
label | 4fe81632-f1d3-5f7e-95b3-2d61712e3856 |  | note | Inspection/Verification (Name, signature & date): Sub-Contractor - NR
label | 6d9dcc6c-7b75-5cdb-b61f-4622b64d1388 |  | note | Inspection/Verification (Name, signature & date): Spark NEL Engineer - WP
label | c3e87d89-4653-5ce7-8c46-b62e3294f86b |  | note | Inspection/Verification (Name, signature & date): Nominated Authority - NR
label | 5e038b88-1ee3-54ad-a23f-2f0d5096f199 |  | note | Inspection/Verification (Name, signature & date): IREA - NR
label | bf4ad78f-ba90-5c27-8719-55ff8558117f |  | note | Records/Documents - Survey records
checkpoint-group |  |  | section | 4.0 Quality
checkpoint-status |  |  | checkpoint | 4.1 - Identification and control of nonconforming products or services (if applicable)
label | 195eef94-e975-5833-909f-72f278d76a6e |  | note | Responsible Person - QSR
label | e84f959a-fb6a-5880-a24c-bee2afb51846 |  | note | Specification Reference - CQMP
label | 00bd3ef7-7350-5ee7-97c6-589fc2b45e5a |  | note | Acceptance Criteria - Review and confirm closure of NCR’s and associated RFI’s prior to closing of construction lot
label | c3c97427-0ecb-589c-b3db-24ddfe092ce9 |  | note | Test Method - R
label | b99082ce-70a3-502e-a558-33461b22f108 |  | note | Test Frequency - PL
label | 9f89b365-7a6d-53d3-b74b-0ad4718a80e7 |  | note | Inspection/Verification (Name, signature & date): Sub-Contractor - NR
label | 23f79a72-18bb-5193-8227-597756f3a3ea |  | note | Inspection/Verification (Name, signature & date): Spark NEL Engineer - HP
label | a95ea878-617a-5db4-bfef-c0c52c52241b |  | note | Inspection/Verification (Name, signature & date): Nominated Authority - NR
label | 8b119031-4524-5a27-a5ea-4efa82b45549 |  | note | Inspection/Verification (Name, signature & date): IREA - NR
label | 2fe64c73-4c7e-565c-aeb0-88766992b583 |  | note | Records/Documents - NCR closed with related documentation
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 4.2 - Check all quality records for lot closure
label | 76ada7d1-3077-5212-81ce-ef16642dc54b |  | note | Responsible Person - QSR
label | 95a10bab-b953-5a17-a593-154d365a845f |  | note | Specification Reference - CQMP
label | edf804f8-bfaf-5883-aa8a-58e91c42b049 |  | note | Acceptance Criteria - All applicable quality records are complete.
label | aa6d2d14-0c20-5e0e-bbfc-b4e08afe8407 |  | note | Test Method - R
label | 659a984c-5011-53e3-ba6b-687b73ddcf72 |  | note | Test Frequency - PL
label | 41213930-cf3c-5559-9e2d-40bc5bcb1f77 |  | note | Inspection/Verification (Name, signature & date): Sub-Contractor - NR
label | 94a4ebbd-8189-5055-b640-5e96ee47d9b4 |  | note | Inspection/Verification (Name, signature & date): Spark NEL Engineer - HP
label | cfaf8f9b-a817-5730-b05c-8373ebc797ed |  | note | Inspection/Verification (Name, signature & date): Nominated Authority - NR
label | df1576f8-5cf8-5dc4-bc6e-f127254d3fea |  | note | Inspection/Verification (Name, signature & date): IREA - NR
label | dd1cbb10-cf9e-56c5-aad2-f9fd963cbe2c |  | note | Records/Documents - Compiled Documents, Forms (all data reports and records)
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checklist-sectioned |  |  | checklist | NEL-CNT-SDC-2990-PQA-ITP-0094 Rev 3 - Subsoil Drainage Installation | itp |  |  |  | Yes | NEL-CNT-SDC-2990-PQA-ITP-0094 Rev 3 - Subsoil Drainage Installation | 80f1478e-eb9d-4de4-9321-583c8c2c6fff
checkpoint-group |  |  | section | 1.0 Preliminaries (Include all aspects of Materials, Approvals, IFC Drawings, etc. Ensure all required permits have been raised prior to commencing works)
checkpoint-status |  |  | checkpoint | 1.1 - Construction Package Approval
label | 40f3044d-e091-5598-a753-f22a3afb469a |  | note | Resp. Person - PE
label | 4b1ac13c-7f87-5805-bd18-c983b83cb308 |  | note | Specification Reference - PSDR Part F6 2 (a) to (h)
label | 796cb039-7658-59a3-acd1-46ce0253c912 |  | note | Acceptance Criteria - Construction Documentation shall be submitted and approved prior to commencing work at site.
label | e1ca9c15-59cc-5403-afa9-ba1dce4455b7 |  | note | Test Method - R
label | 914dce14-9773-5e28-b795-80f37ed04dc9 |  | note | Test Freq. - PW
label | 61d689cf-d262-525f-9e68-d083032ab036 |  | note | Inspection/Verification (Name, signature & date): Sub-Contractor - NR
label | 09a258fd-dd9f-5949-ae97-b1d3ee5ed20d |  | note | Inspection/Verification (Name, signature & date): Spark NEL Engineer - HP
label | 8d418ae1-a395-5263-b0b3-1e8867a3dc86 |  | note | Inspection/Verification (Name, signature & date): Nominated Authority - NR
label | ef97ad50-fc64-5126-abd7-fbcf0b354c99 |  | note | Inspection/Verification (Name, signature & date): IREA - NR
label | 94795811-1668-5d7e-b04d-0ff4bfd5afa7 |  | note | Records/Documents - IFU Construction Package
text | 8fa5e10a-24bd-51ec-9a80-6500e6f9a2f4 |  | textbox | • InEight Reference #:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 1.2 - IFC Drawings Issued
label | 82f6cde3-f671-5d6e-a0b4-bbb034acfa03 |  | note | Resp. Person - PE
label | 32e154d3-bd37-5398-beea-bbdbc43f1a84 |  | note | Specification Reference - Construction Management Plan
label | 8df5eb30-10a2-5000-90c2-48d10287a122 |  | note | Acceptance Criteria - IFC Drawings, approved plans, technical specifications issued for construction.
label | d1889943-faea-5b86-a620-2c6aff2bb39f |  | note | Test Method - R
label | c99136d6-8d44-5669-8957-5f104e83254d |  | note | Test Freq. - PW
label | 9b828467-3c2c-55e3-8b3f-0995815e6113 |  | note | Inspection/Verification (Name, signature & date): Sub-Contractor - NR
label | 30105c0e-0058-55d3-9cad-4bf660556ccd |  | note | Inspection/Verification (Name, signature & date): Spark NEL Engineer - WP
label | 5450dd0b-fb01-5280-8497-9bee88f98072 |  | note | Inspection/Verification (Name, signature & date): Nominated Authority - NR
label | daa93fc3-72ce-59a6-b97e-4a60f12a59ab |  | note | Inspection/Verification (Name, signature & date): IREA - NR
label | bd84cff4-da4c-50c6-83d1-f5b272ef3014 |  | note | Records/Documents -
text | ab2ca92e-cdc3-5514-8e49-0f69484fd91b |  | textbox | • Design Package Number #:
checkpoint-status |  |  | checkpoint | 1.3 - All Equipment Calibrated (NATA Approved)
label | a41729dd-8665-57c5-9f97-5606fb292868 |  | note | Resp. Person - PE
label | 9f4d9f3e-8ba6-54c4-960f-a4623b0c761e |  | note | Specification Reference - CQMP Section 11.1
label | 61a51fb7-3103-5779-905a-47a942c6317e |  | note | Acceptance Criteria - Equipment calibration certificates filed in InEight. Ensure all equipment associated with the relevant works is calibrated
label | 007feef9-b29b-5922-86e6-91df6621552f |  | note | Test Method - R
label | cb8e75c7-e304-5fb7-bf48-fb509132aa73 |  | note | Test Freq. - PW
label | 3ac77feb-a45c-5c39-a1df-6e3fec66f652 |  | note | Inspection/Verification (Name, signature & date): Sub-Contractor - HP
label | bfbe08b7-e4eb-58d2-b5e6-bda7eeb11adf |  | note | Inspection/Verification (Name, signature & date): Spark NEL Engineer - WP
label | 12658b66-22a7-5f3a-b261-92a829c1b89f |  | note | Inspection/Verification (Name, signature & date): Nominated Authority - NR
label | 9368433f-3148-5071-bc44-4a17493a1bae |  | note | Inspection/Verification (Name, signature & date): IREA - NR
label | dd6dd5ed-5c82-56fb-8c9f-4bbb24e3040c |  | note | Records/Documents -
boolean | b27316de-4d0d-5fcb-b8b8-12c29ccbbd62 |  | tickbox | • InEight Reference:
boolean | 0b9f0496-18a7-5916-b983-ccf271cb7ca8 |  | tickbox | • Not Applicable
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 1.4 - Survey Set-Out
label | 09b72d71-3397-55b7-9b93-ff889eb23a59 |  | note | Resp. Person - PS
label | 8da9ab0e-113a-57b1-8ee9-b2f8127e7617 |  | note | Specification Reference - CQMP Survey MP
label | 75a9d57f-9d6e-5e52-a8ab-33a229827a15 |  | note | Acceptance Criteria - Confirm and visually inspect all survey set out points are in accordance to IFC Drawings.
label | 7c2c9a4c-b488-5b03-baec-b0762335463c |  | note | Test Method - R
label | 8094a676-28e5-546b-ac1c-19e164b7c5dc |  | note | Test Freq. - PW
label | dc32c58d-d33d-51d3-827b-c02e485cbe70 |  | note | Inspection/Verification (Name, signature & date): Sub-Contractor - HP
label | 6d72971c-f29c-592e-a9e0-8f1496e91ab8 |  | note | Inspection/Verification (Name, signature & date): Spark NEL Engineer - HP
label | ed44f84d-f717-5535-8ace-b42391448277 |  | note | Inspection/Verification (Name, signature & date): Nominated Authority - NR
label | 9f26f74b-e6f2-5f1b-9ce6-ad80da385b97 |  | note | Inspection/Verification (Name, signature & date): IREA - NR
label | 82814c6b-d1e0-549a-8bd2-fc7f199197b3 |  | note | Records/Documents -
boolean | 7c75c748-e809-5ecf-b92e-f3fc3524c11a |  | tickbox | • Photos of Survey Marks
boolean | 1b6797e5-7b8b-5bac-ab72-9bd8da295998 |  | tickbox | • Survey Records
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 1.5 - Sub-Contractor(s) Quality Documents + Inspection Test Plans
label | 0f58f2f2-affc-568a-80c9-133203b07308 |  | note | Resp. Person - PE
label | e2ae636e-24bc-5c79-9000-786f1fe84bac |  | note | Specification Reference - CQMP 8.2.2.4
label | 2014a5ce-e11c-5345-bfda-57f04af0db03 |  | note | Acceptance Criteria - Ensure Sub-Contractor(s) have submitted signed ITP’s and Checklists along with all relevant supporting documents.
label | 8957f302-103b-5389-8c4b-cb0c47eac38f |  | note | Test Method - R
label | 071eb02b-b2fd-503d-82e3-440619c15a5e |  | note | Test Freq. - PW
label | e1909a42-2d68-59a4-97d7-4a25a20ddedd |  | note | Inspection/Verification (Name, signature & date): Sub-Contractor - HP
label | 18a5ecda-512a-5d89-ab26-894296c9077e |  | note | Inspection/Verification (Name, signature & date): Spark NEL Engineer - HP
label | 936820e5-064d-5b00-9491-63dd5790952c |  | note | Inspection/Verification (Name, signature & date): Nominated Authority - NR
label | bd4608d6-4140-5f29-b943-51ada0e2a776 |  | note | Inspection/Verification (Name, signature & date): IREA - NR
label | 067fba41-700e-5380-900d-446bf8bf27b5 |  | note | Records/Documents -
boolean | 9a584a55-60ce-5168-b548-4389dac5a190 |  | tickbox | • InEight References:
boolean | 6d95293d-0558-5bce-858e-647e5de70fe1 |  | tickbox | • Approved ITP Review Checklist
boolean | a7575daf-b4dc-54fc-9a28-e7d89f57b479 |  | tickbox | • Not Applicable
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | 2.0 Material Compliance
checkpoint-status |  |  | checkpoint | 2.1 - Method of Compaction
label | 9d575cff-29e6-5f7a-8e97-1e8c1015a4c5 |  | note | Resp. Person - SE
label | b5c1ba31-d7e6-5673-9357-1c3b46e4945e |  | note | Specification Reference - VicRoads Section(s) 702.09
label | 0f625ea2-06b0-5e9e-8746-7a884f4f50f0 |  | note | Acceptance Criteria - The method of compaction shall be in accordance with the Contractor's quality procedures and shall be submitted for review by the Nominated Authority.
label | 631ec6d7-461e-51ac-bcff-af3bcb471c74 |  | note | • Where no fines concrete is used as filter material the Contractor shall submit quality procedures for review by the Nominated Authority which detail the method of placing the no-fines concrete to prevent segregation and the formation of a slurry layer at the surface of the concrete which may prevent the passage of water into the filter material.
label | 1a7646dc-be1e-5af7-9bd0-b68da8686c83 |  | note | Test Method - V
label | 36e7772e-c81a-50ca-bb37-682e946e6df8 |  | note | Test Freq. - PW
label | 25542874-32c8-5b62-a1c8-535b63d6a2a9 |  | note | Inspection/Verification (Name, signature & date): Sub-Contractor - HP
label | 65dfbd4c-a818-5161-bcde-73d5948a77ec |  | note | Inspection/Verification (Name, signature & date): Spark NEL Engineer - HP
label | 0ab74f1d-e398-529d-b63f-61f8e1107c18 |  | note | Inspection/Verification (Name, signature & date): Nominated Authority - HP
label | 1d9f9a86-b785-54e5-9893-a4bd44b7b6c3 |  | note | Inspection/Verification (Name, signature & date): IREA - WP
label | e6fbe593-433b-5051-a163-c7fbe30ae708 |  | note | Records/Documents -
boolean | 9f689de5-e3a9-578c-9ff8-7c11f5dcffa1 |  | tickbox | • InEight Hold Point Reference:
text | d0ef59da-5fef-5ffc-af00-0150204461fb |  | textbox | • InEight Document Reference No.:
boolean | 69a17729-ca8b-51f9-b229-c85d25c26ac6 |  | tickbox | • Not Applicable
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.2 - Material – Drainage pipe, granular filter and geotextile materials
label | 1531aae3-6d9e-5bcb-94ae-9952a760db9a |  | note | Resp. Person - SE
label | aade0abb-61af-5b7a-9833-57311cd7a988 |  | note | Specification Reference - VicRoads Section(s) 702.04, 702.05, 702.06 & IFC Drawings PSDR Part B Section 5.4 and 5.5
label | 5dcd86b8-f247-535f-be93-0b1a317f6da4 |  | note | Acceptance Criteria - Drainage pipes comply with specified requirements of Category 1:
label | 973a67ed-cd5a-5f26-98cb-9125b70e27ef |  | note | • Perforated plastics Class 1000
label | 7a336984-1500-5df6-83cc-d3d27c76c54c |  | note | • Precast concrete Class "2"
label | bc4cb649-1e33-5f1b-9bb6-bbcb27d961bf |  | note | • Perforation size to be less than 1.5mm and minimum length of 150mm/m2. Drainage pipes must be made of reinforced concrete and rubber-ring jointed, or other equivalent products approved by the State. Granular filter material must be obtained from a VicRoads accredited source. No Fines concrete must meet the following requirements:
label | 0b9d15bb-9463-5240-8014-f6acb80b01c9 |  | note | • Be a Type GP cement
label | 9d606535-21aa-5c2a-b738-59cca55c78ed |  | note | • Comply with section 703
label | 3d5a4a6a-1a4e-5881-9e9c-112abe780840 |  | note | • W/C range of 0.35 to 0.5
label | 3a626a9a-e97b-5028-bdfc-7aedd2fc7b58 |  | note | ○ Geotextile filter to have the following characteristics:
label | 3a8df9fd-702a-5934-bdcb-63ad4bca0e25 |  | note | • Minimum robustness G(1 ) of 900
label | db8bafc8-747c-5f43-8e07-5bcddf588b1a |  | note | • EOS(2) of 85-230 microns
label | 2e84edbf-39ef-5ad2-a2ac-341f22830941 |  | note | • Minimum elongation of 45%
label | 7b460b3d-d8f9-52b9-a2a4-01ba92230d33 |  | note | ○ Refer Table 702.131 on the last page of this ITP.
label | 1ea42317-518e-5904-817d-57b023f45fb0 |  | note | Test Method - V
label | 897bc9c7-89fa-5954-850d-ce8770982cbc |  | note | Test Freq. - X1
label | 3c926370-42e1-5922-8154-328978336352 |  | note | Inspection/Verification (Name, signature & date): Sub-Contractor - HP
label | cae5b6f6-c7a1-5dc7-9a13-49362c616d3c |  | note | Inspection/Verification (Name, signature & date): Spark NEL Engineer - HP
label | c582231e-e5e5-58dd-887a-704fadef6501 |  | note | Inspection/Verification (Name, signature & date): Nominated Authority - NR
label | 77506060-e2e8-53d8-a454-0a7706864a15 |  | note | Inspection/Verification (Name, signature & date): IREA - NR
label | 0ef936d6-4c00-54e2-a9fc-909f5af48656 |  | note | Records/Documents -
boolean | eda95e87-acdc-5f2b-98a8-b49324b171f0 |  | tickbox | • Delivery Dockets for Bedding Materials
boolean | a10fe799-003b-5511-acb2-b0cb62c38e42 |  | tickbox | • Manufacturers Compliance Certificates for pipes and geotextile materials
boolean | 22a6d414-9c17-549a-be23-1f8b3b4c0f92 |  | tickbox | • NATA Test Report(s)
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | 3.0 Construction Activities
checkpoint-status |  |  | checkpoint | 3.01 - Excavation
label | 7c2f633c-df5e-5cdb-bea4-6d7b0ab9f38c |  | note | Resp. Person - SE
label | 1e664b50-6e79-59dc-aa10-99866f35f166 |  | note | Specification Reference - VicRoads Section(s) 702.08
label | ad63d0bd-f195-5c1d-8841-5b83cfebfe83 |  | note | Acceptance Criteria - Trench walls excavated to allow geotextile filter to be in close contact with the wall. The bottom of the trench has been compacted and is not more than 50 mm below the specified level of the invert of the pipe.
label | c293b7a9-1ffb-55a6-b365-a8742a00b189 |  | note | • There are no departures from the grade of the base of the trench that would allow ponding of water.
label | 703723f5-87d9-5a1a-b6a2-b2984c545c26 |  | note | • Excess excavation made good by backfilling with like material. Loose material has been removed.
label | 9c462db2-36d7-5a37-ab87-bc90fd8ec22e |  | note | • Where existing subsurface drains are intercepted, an adequate outlet has been provided for the drain.
label | 6b6cbdf1-2174-5932-9c9b-42c6a77c93da |  | note | • Redundant subsurface drains have been removed and backfilled with Type A per section 204, or specified pavement material when found in new road pavement.
label | 0f664799-a166-5a54-9426-f0ec03ccba80 |  | note | Test Method - V
label | 73a674b7-0f5a-5365-95c7-11b4f0df087c |  | note | Test Freq. - PW
label | 6395f544-62bf-5820-812b-8cb781c1588a |  | note | Inspection/Verification (Name, signature & date): Sub-Contractor - WP
label | 7cc240cb-b0fd-5926-8302-5b90c83bcdf3 |  | note | Inspection/Verification (Name, signature & date): Spark NEL Engineer - WP
label | 8b2a3266-7041-5e28-8308-c8a654b0f873 |  | note | Inspection/Verification (Name, signature & date): Nominated Authority - NR
label | 1ea9a568-6878-5a36-b553-4f03fa211afd |  | note | Inspection/Verification (Name, signature & date): IREA - NR
label | 48865d90-70e5-505d-a901-df59c87c14de |  | note | Records/Documents -
boolean | 04e1dc1b-cd8f-584b-b8dc-29205a229952 |  | tickbox | • InEight Hold Point Number
text | c5e407b5-712b-5f41-9bd8-db4e3fe41c84 |  | textbox | • Hold Point Number:
boolean | 4899e75e-809d-5783-a308-14a275ca3df4 |  | tickbox | • Excavation and Penetration Permit No
text | bde56d37-d971-5f46-ae23-cf842a709e38 |  | textbox | • Permit No:
checkpoint-status |  |  | checkpoint | 3.02 - Inspection of Base Trench
label | b594a41e-f40c-5c56-b072-776fcf10f711 |  | note | Resp. Person - PE
label | 5310a604-5a66-5563-ad96-04b3d7a3bf87 |  | note | Specification Reference - VicRoads Section(s) 702.08
label | 47a147d4-f03e-57d4-9381-dba2ec933889 |  | note | Acceptance Criteria - The base of the trench shall be inspected to verify compliance prior to placing bedding in completed excavations. The Nominated Authority shall be notified at least 24 hours prior to the inspection.
label | d2fabe51-7b25-5efc-b11e-cfd64287619c |  | note | Test Method - V
label | 0dcdd434-6877-55bb-9b16-3daa7148937f |  | note | Test Freq. - PW
label | e1e41693-8927-507b-af73-1a5fcad9fb2d |  | note | Inspection/Verification (Name, signature & date): Sub-Contractor - HP
label | 6298ed16-ed7e-56d3-9bd9-e7dca83f2514 |  | note | Inspection/Verification (Name, signature & date): Spark NEL Engineer - HP
label | de8a3359-a830-568e-868f-f52cdb8181f3 |  | note | Inspection/Verification (Name, signature & date): Nominated Authority - HP
label | e2144fdf-1de5-5b6d-8f97-15c52e6481dd |  | note | Inspection/Verification (Name, signature & date): IREA - WP
label | c62466a5-bce2-5797-bfdb-df96c0e7c61e |  | note | Records/Documents -
text | 2f03a5f1-eafb-55da-8956-0bf8e784c2fe |  | textbox | • HP Release InEight Reference #:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.03 - Subsurface drains in expansive soils
label | 4ace39cf-6491-509d-acd1-11251b73036a |  | note | Resp. Person - SE
label | 2c45db99-1931-5ceb-8569-f0a82748b9f7 |  | note | Specification Reference - IFC Drawings
label | 24f16f13-abc7-533d-b4c1-796f3b0c33c1 |  | note | Acceptance Criteria - Where subsurface drains are installed in expansive soils (swell >2.5%) the drainage pipe must not touch the expansive material. Additionally, 150mm or more of capping must be provided below the floor of the trench.
label | d5377a17-36aa-5156-a236-d0d4e9b89d67 |  | note | Test Method - V
label | ac80cc2f-b587-5d06-83b6-fb0c9512d35e |  | note | Test Freq. - X1
label | 8a141625-66a5-53ac-8954-e28e6190bcd8 |  | note | Inspection/Verification (Name, signature & date): Sub-Contractor - HP
label | e36875f8-2bec-5629-ab1f-8ec1f94ba94b |  | note | Inspection/Verification (Name, signature & date): Spark NEL Engineer - HP
label | c0274be8-2189-5813-8463-2df27bfa4141 |  | note | Inspection/Verification (Name, signature & date): Nominated Authority - NR
label | 1b82dcc6-2f4d-5161-80c0-ce3d8b7a90ea |  | note | Inspection/Verification (Name, signature & date): IREA - NR
label | dd2db320-ae38-51a7-81f8-38a5951a4d72 |  | note | Records/Documents -
boolean | 9aba4068-de70-5e09-9dd1-f86f884c2dfc |  | tickbox | • Completed ITP
boolean | 9ec49cf0-957a-54dd-b0b1-5182df080f13 |  | tickbox | • NATA Swell Report for Subgrade
boolean | 2dae17bb-295e-5148-b42f-38132f9b125b |  | tickbox | • Not Applicable
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.04 - Bedding
label | e38f4a75-323f-599e-97bb-927ab843fe10 |  | note | Resp. Person - SE
label | 20dcb573-9536-5c7a-820d-dd4e697a2176 |  | note | Specification Reference - VicRoads Section(s) 702.09
label | 81fb7294-eb3e-58ef-b30a-25b32dcc0782 |  | note | Acceptance Criteria - A bedding of granular filter material of thickness between 25 mm and 50 mm has been placed across the bottom of the trench. The bedding has been tamped and screeded or graded to level.
label | 2c7fc497-ebe3-5484-8e1c-2568bc96b193 |  | note | Test Method - V
label | 420bbd75-7144-5cac-808b-463700f9389e |  | note | Test Freq. - PW
label | 0f872f36-bf89-50ed-8d86-454cb210dd1f |  | note | Inspection/Verification (Name, signature & date): Sub-Contractor - HP
label | eacab672-a8cf-5e55-b54d-4e96e0580b32 |  | note | Inspection/Verification (Name, signature & date): Spark NEL Engineer - HP
label | 5d934e44-aa01-5d05-a79b-615c9a0ff739 |  | note | Inspection/Verification (Name, signature & date): Nominated Authority - NR
label | 5ecd9efc-7e58-55b1-943f-912f6cdf93b2 |  | note | Inspection/Verification (Name, signature & date): IREA - NR
label | 4f547571-d68e-53f3-9963-19b2642e30e1 |  | note | Records/Documents -
boolean | a419391a-aa0c-51cd-a30a-aa68dcc0ba99 |  | tickbox | • Completed ITP
boolean | 57485fbc-ab49-5b3b-ae9d-d9b1d57b1446 |  | tickbox | • Not Applicable
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.05 - Installation
label | cc8d2a63-ac4c-53b1-82cd-bc278d57b73e |  | note | Resp. Person - SE
label | 917fb179-135c-5cd8-8be1-9dad7f0b1549 |  | note | Specification Reference - VicRoads Section(s) 702.09
label | 80a25a10-c7e1-50d1-853b-6e70b37df068 |  | note | • VicRoads Standard Drawing 1601 IFC Drawings PSDR Part B Section 5.4 and 5.5
label | 5a2553c6-db6e-532e-b25a-69c782c5aa76 |  | note | Acceptance Criteria - Subsurface drainage pipes have been laid to the depth shown on drawings. All road drainage pipes and culverts must be designed such that the top of the drain is at least 200 millimetres below the underside of pavement, except where capping or selected material is required beneath the pavement.
label | f0d3bee6-fd85-5c4a-b8ad-bf4afd2f705f |  | note | • The top of drain must be at least 200 millimetres below the underside of capping or selected material.
label | d248ee51-3695-5806-82f6-188619ef5cc5 |  | note | • The diameter of pipes placed under pavements must not be less than 375 millimetres and the height of box culverts must be not less than 300 millimetres.
label | 3a166312-3bae-5cb8-a253-41a8729939eb |  | note | • Except for drainage systems related to the Tunnel, or where agreed to by the State or the Returned Asset Owner (as applicable), all longitudinal, transverse drainage and subsurface drainage systems must be free draining.
label | b8c1975f-0ded-506a-8e32-eca20631e90a |  | note | • The incorporation of drainage systems that rely on pumping or siphoning is not permitted.
label | 1ef7cccf-f6f2-5c11-a2cc-714d1b4d7ee0 |  | note | • Corrugated metal pipes, pipe arches and arches must not be used.
label | cad7a7eb-d5f7-5fa7-acdf-527bdbf3a5ca |  | note | • All outlets to drainage systems must be provided by an underground
label | 0a40ea86-8a86-513e-8a42-7438d12613a3 |  | note | Test Method - V
label | 06a57548-7e1a-5547-92c9-348a232fbe66 |  | note | Test Freq. - PL
label | a91ae94f-54df-5f75-ac8a-d1e4e8443994 |  | note | Inspection/Verification (Name, signature & date): Sub-Contractor - WP
label | 18695597-374a-54c0-b779-19a072088383 |  | note | Inspection/Verification (Name, signature & date): Spark NEL Engineer - WP
label | e0ee953b-39d5-5e23-bda0-b43bbab6f460 |  | note | Inspection/Verification (Name, signature & date): Nominated Authority - NR
label | 98a4f8ae-716c-58f7-8401-9b654b38b544 |  | note | Inspection/Verification (Name, signature & date): IREA - NR
label | 1be8f29f-2043-5fb7-96ee-553ec3d62ea5 |  | note | Records/Documents -
boolean | 3a7d84be-90de-5a51-8b74-452db472acec |  | tickbox | • Completed ITP
checkpoint-status |  |  | checkpoint | 3.06 - Placing Granular Filter Material and Geotextile
label | e3fa9a37-16c1-52c0-89a6-16edfe67665f |  | note | Resp. Person - SE
label | e3f194c5-655c-5cdc-8fb5-817ebd2557ec |  | note | Specification Reference - VicRoads 702.09
label | 45091185-1611-548d-9ea9-3ddae93f643a |  | note | Acceptance Criteria - Filter material has been placed in accordance with the approved method of placement.
label | d9650d2f-4ea6-584b-a8ff-44a375979f5c |  | note | • No segregation of no fines nor formation of a slurry at the surface. No-fines concrete placed and compacted within 1 hour of mixing.
label | b2a74914-0b89-5cb7-bf69-38ef2ff239d0 |  | note | • Geotextile has been lapped over granular filter material by 150mm or more as per SD1601
label | 6f55c169-24c1-5006-ab7c-633754fd1078 |  | note | Test Method - V
label | 80fa2ebd-98b4-555c-aa81-bc5aabfba817 |  | note | Test Freq. - PL
label | c2787b83-5b78-5099-bfaf-790072ec84fb |  | note | Inspection/Verification (Name, signature & date): Sub-Contractor - WP
label | 89dc780e-a3ef-5499-ac37-f60ad1e44e72 |  | note | Inspection/Verification (Name, signature & date): Spark NEL Engineer - WP
label | 785e2901-0342-5063-8b7a-810e060cec3f |  | note | Inspection/Verification (Name, signature & date): Nominated Authority - NR
label | ca918362-abf8-5ad0-a169-8644396b5027 |  | note | Inspection/Verification (Name, signature & date): IREA - NR
label | cd374183-26a0-58a1-bc65-2cafae9c4327 |  | note | Records/Documents -
boolean | 30f5dda6-8b19-53c4-b4e8-030530db8682 |  | tickbox | • Completed ITP
boolean | 2690d85e-74aa-5fe2-85c4-c28fb11053d0 |  | tickbox | • Compaction Test
boolean | 05fc5bcd-408b-5be5-9a05-41943b0a1816 |  | tickbox | • Not Applicable
checkpoint-status |  |  | checkpoint | 3.07 - Flushing
label | 07706b91-352b-5560-bbbf-d4f93b62789a |  | note | Resp. Person - PE
label | 841091bf-6b5e-51c9-88c3-517cfde9f95d |  | note | Specification Reference - VicRoads 702.09
label | e15f3bd5-3249-5038-8b0d-6b0fca24d017 |  | note | Acceptance Criteria - A flush test has been carried out in the presence of a representative nominated by the Nominated Authority.
label | 2bb2fb1c-9ebc-537c-ba73-638dec633591 |  | note | Test Method - V
label | e77b72e1-472b-5481-8fe2-1ad22080629a |  | note | Test Freq. - PL
label | 1ee89b23-0654-505f-9c54-532fcc607193 |  | note | Inspection/Verification (Name, signature & date): Sub-Contractor - HP
label | b02201b2-d594-5532-8dc6-55275c6513e1 |  | note | Inspection/Verification (Name, signature & date): Spark NEL Engineer - HP
label | 911eed25-0ccf-5c7a-a645-f97c2c0fd4b3 |  | note | Inspection/Verification (Name, signature & date): Nominated Authority - HP
label | 7eaa6298-4d5f-5597-aa5a-778f4f6b5102 |  | note | Inspection/Verification (Name, signature & date): IREA - WP
label | e9056c78-ec7d-51ed-a79a-34816bc34577 |  | note | Records/Documents -
boolean | 82d5d9b4-64e5-578b-b994-2e2ef6dbdb27 |  | tickbox | • Record of flushing test
boolean | b1abd788-b943-5803-9388-cba58d64bd62 |  | tickbox | • Not Applicable
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.08 - Access points & inspection openings
label | 64bbc399-a68d-5f90-b792-d7bb05f4beec |  | note | Resp. Person - SE
label | 5a07e665-c386-546a-a433-fc4a5f1bee3a |  | note | Specification Reference - VicRoads 702.10
label | d8505c51-229b-533a-89ca-7ea6bbbbb114 |  | note | Acceptance Criteria - An access point has been provided at the beginning and end of each run and an inspection point at 100-150m intervals. Where stormwater pits have been used as access points, the invert at the beginning of the run has been located above the outlet of the pit and >100mm above the outlet of the pit at the end of the run.
label | b43dad66-8cfd-511c-8ad0-8ef9916e5f81 |  | note | Test Method - V
label | 81b16900-8b15-5c24-9fa9-48072f9a4900 |  | note | Test Freq. - PL
label | 826b803b-250e-58a3-b5b9-4a7625a8aefb |  | note | Inspection/Verification (Name, signature & date): Sub-Contractor - WP
label | 1dcde647-e0b4-5354-b470-c00f3909afe0 |  | note | Inspection/Verification (Name, signature & date): Spark NEL Engineer - WP
label | c5c8ecc7-0265-5416-8d05-8fb3ebad1b1a |  | note | Inspection/Verification (Name, signature & date): Nominated Authority - NR
label | 226d290b-2363-5582-8273-81bed8a6dde3 |  | note | Inspection/Verification (Name, signature & date): IREA - NR
label | e2e21346-4822-554a-985d-e375c6a17adb |  | note | Records/Documents -
boolean | 0ef52e7d-de06-59f2-987f-fcda3ec2e96c |  | tickbox | • Completed ITP
checkpoint-status |  |  | checkpoint | 3.09 - Marker Posts
label | 1d477ecf-3c2a-575c-8ab3-0cfd1bd56346 |  | note | Resp. Person - SE
label | 5f3e63ce-c4cb-5079-82bb-ce7030c6e6be |  | note | Specification Reference - VicRoads 702.11 PSDR Part B Section 5.4
label | 8dc0ba4b-ec9a-5f93-be66-95e1c25e3c1b |  | note | Acceptance Criteria - At all fill batter and drain outlets, supply and erect marker posts as shown on the drawings. Posts must be 75mm diameter x 1500mm treated pine posts inserted 600mm into the ground.
label | 3d34a3e7-ef21-5f42-95b6-8921b5d18230 |  | note | Test Method - V
label | 6c90ff23-9ac5-5e3f-8411-11bd5be28495 |  | note | Test Freq. - PL
label | dd066bbf-2b80-5982-9b7b-3a01995391e5 |  | note | Inspection/Verification (Name, signature & date): Sub-Contractor - WP
label | 97afe279-8199-50d7-962c-02f07f55ad01 |  | note | Inspection/Verification (Name, signature & date): Spark NEL Engineer - WP
label | 5fc87566-67c8-5dd2-9c0c-5f99c763fd23 |  | note | Inspection/Verification (Name, signature & date): Nominated Authority - NR
label | 664572c6-ca1d-53cc-830b-ce7c38aa6299 |  | note | Inspection/Verification (Name, signature & date): IREA - NR
label | cc71b2c4-8097-5b1c-8c5f-78659ab30c18 |  | note | Records/Documents -
boolean | 925bb2a4-b9f3-588f-b62f-e90338214987 |  | tickbox | • Completed ITP
boolean | 3a82e6fa-d895-5c68-886f-39a3ea1bfd16 |  | tickbox | • As Built Documents
checkpoint-status |  |  | checkpoint | 3.10 - Inspection of Subsurface Drainage Lines
label | fcd32e01-6f5b-5362-8073-c3f45c7fac82 |  | note | Resp. Person - SE
label | 336fd5d3-481c-5477-a443-02558cbe78ac |  | note | Specification Reference - VicRoads 702.09 (i) PSDR Part B section 5.5(b)
label | 95348e1d-fb58-5011-8439-d793a5f94e7b |  | note | Acceptance Criteria - All subsurface drainage lines constructed shall be inspected, after completion of the flushing test as stated in clause 702.09(h) and prior to placement of asphalt, by an independent testing organisation using closed circuit television (CCTV) to verify that the flow of water is not obstructed by waste construction material left inside and to check for visible signs of defects.
label | 92b9c9bd-64d7-50e6-89d8-a6c6181d6b0e |  | note | • Placement of asphalt shall not proceed until the CCTV inspection and flushing test have been completed, damaged or deformed subsurface drainage pipe has been removed and replaced and the waste and defects free condition of subsurface drainage lines has been verified by the Nominated Authority.
label | c216e1c1-ba66-54e8-9b5c-233f80bfb4f5 |  | note | Test Method - V
label | dea7b9ed-e9d3-5477-ac63-8f11d3b187e6 |  | note | Test Freq. - PL
label | dfd04895-ce71-5cc7-87e0-94675aa1939b |  | note | Inspection/Verification (Name, signature & date): Sub-Contractor - HP
label | b70f6da0-b7aa-5c00-914a-69e0111c7679 |  | note | Inspection/Verification (Name, signature & date): Spark NEL Engineer - HP
label | f89447d3-b453-5123-83fb-68ee27d17d9f |  | note | Inspection/Verification (Name, signature & date): Nominated Authority - HP
label | 0232c554-8ced-5024-847c-e0d85cb513cf |  | note | Inspection/Verification (Name, signature & date): IREA - WP
label | 6d99c276-ba66-5af5-92a4-e7bbee2d0e6e |  | note | Records/Documents -
boolean | 04cec814-2dd8-5953-af91-adb18cf67cc4 |  | tickbox | • CCTV Report
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | 4.0 Post Operations (Include Inspection and Testing)
checkpoint-status |  |  | checkpoint | 4.1 - Verification and lot records Complete
label | 7864fc8f-3a06-5b96-9b16-c8159a85a22e |  | note | Resp. Person - SE
label | 3f8785fd-70b4-50b3-80ed-c4f5f86dc331 |  | note | Specification Reference - CQMP Section 8.2.6.2
label | a8454d83-304b-565f-95ed-20c7898fc9ea |  | note | Acceptance Criteria - Ensure completed work checklists, inspection and test results and contractor conformance records are progressively and permanently saved and stored as soon as possible after they are received. Completed construction lot records are transferred to the project Quality Team for final record verification prior to being closed
label | c7667c25-9d72-598c-ad1d-7c2b2a3c1781 |  | note | Test Method - V
label | 9060d11a-f262-5457-a85d-3c420937b906 |  | note | Test Freq. - PL
label | e17639e8-6cf8-50cc-8168-410142be74b9 |  | note | Inspection/Verification (Name, signature & date): Sub-Contractor - HP
label | a2d0f700-29ee-53f9-b72c-f8197faad6f0 |  | note | Inspection/Verification (Name, signature & date): Spark NEL Engineer - HP
label | b89a3204-10a8-54f9-88d9-5d5d0364ebe4 |  | note | Inspection/Verification (Name, signature & date): Nominated Authority - NR
label | 3b9109b0-84cd-506d-b917-4744ca47b049 |  | note | Inspection/Verification (Name, signature & date): IREA - NR
label | 27f12a4f-87e1-5618-b7d0-f5e523b1bfcd |  | note | Records/Documents -
boolean | 5a925dbf-e247-511b-ae92-a4469874bdaf |  | tickbox | • Lot Map Lot Record
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 4.2 - NCR Close out (if applicable)
label | f049bdb9-4e53-5239-bb37-3fb3b09a1989 |  | note | Resp. Person - PE
label | f5500b58-b137-58b6-a21d-d008ef89c2c4 |  | note | Specification Reference - CQMP Section 8.3
label | 3cfdeb13-fe81-55a7-a8f8-1ddd09502681 |  | note | Acceptance Criteria - All NCR’s presented for closure
label | aac9e002-08d0-5781-a4b1-f8fcaca6f735 |  | note | Test Method - R
label | 6e355dc5-c380-5335-9b58-a4b316f8102f |  | note | Test Freq. - PL
label | f93f86d5-218e-5851-929f-4bfc7036dd7e |  | note | Inspection/Verification (Name, signature & date): Sub-Contractor - HP
label | eb3b4463-cc36-583a-9810-01827db957b6 |  | note | Inspection/Verification (Name, signature & date): Spark NEL Engineer - HP
label | a417a460-0dea-5a5a-be40-e4e6c4d9266f |  | note | Inspection/Verification (Name, signature & date): Nominated Authority - HP
label | 430f4335-705c-5fed-988d-1058af6bed09 |  | note | Inspection/Verification (Name, signature & date): IREA - WP
label | b2840994-a895-5f88-af0b-40f4c7195159 |  | note | Records/Documents -
text | 8e242a5b-df53-54d7-aba9-42ad2af43f6d |  | textbox | • HP Release InEight Reference #
text | 0d25a8cc-70ab-5b5a-a25c-9aafd8cda077 |  | textbox | • NCR InEight Reference #:
label | 98b580cf-5e15-5478-9246-d7992d44cb62 |  | note | • NCR Module
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | 5.0 Quality
checkpoint-status |  |  | checkpoint | 5.1 - Identification and control of nonconforming products or services (if applicable)
label | 7d83c868-a1ff-5a8b-a529-2c36e1dddb8b |  | note | Resp. Person - QSR
label | 2f546615-cd0b-51e3-b66a-77545c56e2af |  | note | Specification Reference - CQMP Section 8.3
label | 80f33120-4a97-5c5c-a8eb-ba11b39ef8ab |  | note | Acceptance Criteria - Review and confirm closure of NCR’s and associated RFI’s prior to closing of construction lot
label | 82a91778-486b-5743-a0a2-6bf195e4d9e0 |  | note | Test Method - R
label | 781c9150-9bd7-5361-b686-6549cbdc2314 |  | note | Test Freq. - PL
label | c88e335a-a7ef-53c0-a8e7-084ef566e797 |  | note | Inspection/Verification (Name, signature & date): Sub-Contractor - NR
label | cf7ff6e8-d80f-50cd-878a-4c8223658885 |  | note | Inspection/Verification (Name, signature & date): Spark NEL Engineer - HP
label | 3a96b70b-f196-510d-969b-c91bf1955090 |  | note | Inspection/Verification (Name, signature & date): Nominated Authority - NR
label | f4b57460-3dc7-5c87-957f-2f373759adac |  | note | Inspection/Verification (Name, signature & date): IREA - NR
label | a4172e80-9624-5b34-8c88-5789fd4e1733 |  | note | Records/Documents - NCR closed with related documentation
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 5.2 - Check all quality records for lot closure
label | a963152f-b2ea-5918-8c2d-a796fe3eeb42 |  | note | Resp. Person - QSR
label | 33d13cd9-ea84-5d77-807c-b62dea4c69bf |  | note | Specification Reference - CQMP Section 8.3
label | 8c4e689c-8be3-55f6-884d-7ed55e3b52d0 |  | note | Acceptance Criteria - All applicable quality records are complete
label | dde7b312-bd74-555c-a05c-137271e6c565 |  | note | Test Method - R
label | 7d6b04f6-2543-51fb-b292-6aab2cb06cc1 |  | note | Test Freq. - PL
label | 7ee6d26b-596e-546f-823a-0d5c2ca98542 |  | note | Inspection/Verification (Name, signature & date): Sub-Contractor - NR
label | 7fe20914-4aa6-599a-a3ba-b6cfb3e9c53c |  | note | Inspection/Verification (Name, signature & date): Spark NEL Engineer - HP
label | 2a5a22ff-a479-503e-b977-83127c69d7bd |  | note | Inspection/Verification (Name, signature & date): Nominated Authority - NR
label | 5edfc481-fac0-580c-b4ad-7e659663031a |  | note | Inspection/Verification (Name, signature & date): IREA - NR
label | 428cb8da-ae6b-5c69-8655-e2df67231d8e |  | note | Records/Documents - Compiled documents (all data reports and records)
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checklist-sectioned |  |  | checklist | NEL-CNT-SDC-2990-PQA-ITP-0024 Rev 0 - Stormwater Drainage Pits & Pipes | itp |  |  |  | Yes | NEL-CNT-SDC-2990-PQA-ITP-0024 Rev 0 - Stormwater Drainage Pits & Pipes | a7d718f7-39f5-40d8-8bb3-57958381adf4
checkpoint-group |  |  | section | 1.0 Preliminaries (Include all aspects of Materials, Approvals, IFC Drawings, etc. Ensure all required permits have been raised prior to commencing works)
checkpoint-status |  |  | checkpoint | 1.1 - Construction Package Approval
label | 9627682c-288f-5ce6-b0ec-dd195df2d1c0 |  | note | Resp. Person - PE
label | c1142622-4c22-5982-9d83-f840b5505dfc |  | note | Specification Reference - PSDR Part F6 2 (a) to (h)
label | 7b883660-629c-56ec-913b-b75fec6f3b4b |  | note | Acceptance Criteria - Construction Documentation shall be submitted and approved prior to commencing work at site.
label | f46ff04e-c826-51e7-9315-0a543f5cd0ec |  | note | Test Method - R
label | 410cac1b-7793-5ef6-a611-2879dcfe8d77 |  | note | Test Freq. - PW
label | 7a3af851-84cb-57a2-b4d3-9fc4f4c92e7d |  | note | Inspection/Verification (Name, signature & date): Sub-Contractor - NR
label | 9ea3da8f-8b2a-5784-aaa4-42bed8d2392f |  | note | Inspection/Verification (Name, signature & date): Spark NEL Engineer - HP
label | 0f650e8e-e622-551f-99f7-d88778312202 |  | note | Inspection/Verification (Name, signature & date): Nominated Authority - NR
label | a29cca3a-38bd-5f07-9d01-d07c2bbf575e |  | note | Inspection/Verification (Name, signature & date): IREA - NR
label | 4b690416-b727-5ddc-abab-e03f9d0b28f5 |  | note | Records/Documents - IFU Construction Package
text | 46e3276d-fba1-5dc9-95a0-0b8648e8e74a |  | textbox | • InEight Reference #:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 1.2 - Material Conformance Pit & Pipe
label | 8fa91d0c-1d8d-52ec-8f4f-906ec06cd2f8 |  | note | Resp. Person - PE
label | 35fee1fc-eccb-5c6d-b2a1-cd983154bd89 |  | note | Specification Reference - VR 701.04, 701.05, 701.06, 701.07, 701.08, 701.09, 705.04, 705.07, 705.09 IFC drawings
label | a46049ca-9a60-5be2-aa6c-f5f85ddba7f4 |  | note | Acceptance Criteria - Complies with specified requirements. Free from defects and to drawing dimensions.
label | ea395e9a-c78c-55a0-9c57-59ee955c5a79 |  | note | Test Method - R
label | e43e2d87-5573-5b01-8fca-5c4ef243b439 |  | note | Test Freq. - PW
label | 2e13e338-faef-52bb-b6cb-9edb9b6b2dfc |  | note | Inspection/Verification (Name, signature & date): Sub-Contractor - HP
label | 0301cc07-92e8-5a69-8c5c-e8cc02d0e6bf |  | note | Inspection/Verification (Name, signature & date): Spark NEL Engineer - HP
label | e2d904f6-37f2-5f16-aa6a-e7393ffdb056 |  | note | Inspection/Verification (Name, signature & date): Nominated Authority - NR
label | 55bf1874-732c-5033-90bb-6b9b8f2ace17 |  | note | Inspection/Verification (Name, signature & date): IREA - NR
label | cadfcaf2-b68c-5678-97bd-f6bd7cd1bbcf |  | note | Records/Documents -
text | c0cc9327-1e7e-587c-b51b-aa1fad8ae000 |  | textbox | • InEight Ref #
label | ae387154-8d9f-5f31-90db-11110a4e8680 |  | note | • Pipe delivery dockets Pit shop drawings
label | 3880de51-5f49-5d70-8cd2-b0bb87654590 |  | note | • Product Data Sheets
label | 94527b81-1679-5bab-83ed-93e731ea0de1 |  | note | • NATA Test Results
label | 5aae3e98-1943-5bf9-9b79-48d7ca1d99cc |  | note | • Material Conformance Certificates
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 1.3 - Material Conformance Bedding & Backfill
label | c2d245c2-1123-5360-8edd-5ca3de42f35d |  | note | Resp. Person - PE
label | bf2326f8-2454-5a7c-b190-853c021c5e32 |  | note | Specification Reference - VicRoads 701.09(d), Table 701.091, 701.092, 701.291, IFC drawings
label | c5524951-6968-5007-a7e7-b6533f7b038c |  | note | Acceptance Criteria - No perishable matter or lumps. Grading as per table 701.091 PI as per table 701.092 Grading and PI tests to be carried out once per 1000 tones or part thereof. Minimum testing requirements as per table 701.291 see table below
label | 0f9d71f5-81b4-5ebc-9d38-1815ee62d97c |  | note | Test Method - R
label | 51f70fe3-d6f0-57d9-92d0-41c754a77251 |  | note | Test Freq. - PW
label | 7e54fce6-8a87-5f1a-ad6d-3c951082fa6b |  | note | Inspection/Verification (Name, signature & date): Sub-Contractor - HP
label | 89691bf8-28fb-526e-ab90-2cf3ef960ced |  | note | Inspection/Verification (Name, signature & date): Spark NEL Engineer - HP
label | eb81ac45-cdce-5674-bdc9-4ae66ded45c2 |  | note | Inspection/Verification (Name, signature & date): Nominated Authority - NR
label | 7706dc39-1bfa-5bb9-8ba4-8261c79560b1 |  | note | Inspection/Verification (Name, signature & date): IREA - NR
label | f581cb56-421e-52bc-adcb-5abc909ad97f |  | note | Records/Documents -
text | cfdf65fc-995d-5c2d-ac15-37cededce6a9 |  | textbox | • InEight Ref #
label | af3cb330-ea01-51d9-a2b4-f7dae2d9dd63 |  | note | • Material conformance certificate
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 1.4 - Trench Shields
label | 3229d0a1-f2c6-5173-932a-d53c6b05fc41 |  | note | Resp. Person - SE
label | 0c2b30ee-317b-5dcc-99ca-b38f2d5cfbad |  | note | Specification Reference - AS 4744
label | 0b564690-0911-5348-b699-6b14f49a64c3 |  | note | Acceptance Criteria - Trench shield shall be manufactured and certified in accordance with AS4744
label | 88a5b4a9-affc-5458-88ad-78e5b00010a8 |  | note | Test Method - V
label | a284d398-d822-5644-9643-05db6c7334df |  | note | Test Freq. - PW
label | 88aa6f94-d52e-563e-bf9b-e6d108e05a2c |  | note | Inspection/Verification (Name, signature & date): Sub-Contractor - HP
label | 109f521a-e3b5-508a-9925-0070e49ce3f2 |  | note | Inspection/Verification (Name, signature & date): Spark NEL Engineer - HP
label | 30e3e966-2f09-51ba-81ad-8e482dc7c52a |  | note | Inspection/Verification (Name, signature & date): Nominated Authority - HP
label | 05aa7b0b-de90-5d52-bb3e-8c88cfae1a36 |  | note | Inspection/Verification (Name, signature & date): IREA - WP
label | 839eac55-eddf-5f82-842f-ec96500d1742 |  | note | Records/Documents - Engineering Certificate
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 1.5 - Material Conformance Mortar Grout
label | 54738164-0b6e-5f42-b068-9ea51f13a9a5 |  | note | Resp. Person - PE
label | 31080489-6fca-5899-b3bd-2a902cef3000 |  | note | Specification Reference - VR 610.07, VR610.33 IFC drawings
label | 0f3d06c1-d28a-5176-b3fd-0d36bd28028a |  | note | Acceptance Criteria - Grout mix designs shall be registered in accordance with the requirements of Section 610.07
label | e309d864-5780-56d7-a75d-3bd9a8642f39 |  | note | • Mortar used in the laying of box culvert sections or as jointing for pipes shall comply with the requirements of clause
label | aa3b88ba-facc-5244-9e6f-109168bb57f0 |  | note | Test Method - R
label | d4871c86-7f69-555e-9d0f-66e8fd99d149 |  | note | Test Freq. - PW
label | 535f0613-a3cf-5747-8cae-67a05418bdb3 |  | note | Inspection/Verification (Name, signature & date): Sub-Contractor - HP
label | 1a885254-f9c6-5857-9810-26bbfd7ec9f5 |  | note | Inspection/Verification (Name, signature & date): Spark NEL Engineer - HP
label | 8db06faa-aa79-5fcc-a933-6d2872195e32 |  | note | Inspection/Verification (Name, signature & date): Nominated Authority - HP
label | fe4d84c9-3c8f-523f-ba3d-748c34add105 |  | note | Inspection/Verification (Name, signature & date): IREA - WP
label | a8a0f48f-0ee4-5269-9723-bf3d30049823 |  | note | Records/Documents -
text | 24181d4d-7a23-5cfd-b52b-91c39778dc02 |  | textbox | • HP Release InEight Ref #
label | 32e8d210-9810-53a5-804c-29cfd7923d5d |  | note | • Grout Mix Design
label | 2c859a94-2a45-5eb9-a5ec-e481be5e3ab6 |  | note | • Material conformance cert /Material delivery docket
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 1.6 - Design status
label | 0863294a-ba1d-54e3-b884-25b6e2d177ac |  | note | Resp. Person - PE
label | 4ff55c19-0d45-5013-9dee-d9545e5e97d2 |  | note | Specification Reference - PSDR Part F5, 2(b) & (c)(i)
label | 42456198-9a7e-550f-9b79-85fe2945ce87 |  | note | Acceptance Criteria - Design to be IFC prior to works commencing
label | b8b27ca9-7899-52fc-8275-cfbdee699521 |  | note | Test Method - R
label | 85b6f64e-262d-5338-bae8-71976b48dea0 |  | note | Test Freq. - PW
label | e60f71fe-cac2-5019-9581-58eac981396c |  | note | Inspection/Verification (Name, signature & date): Sub-Contractor - NR
label | e537586a-30ef-5648-86c7-87d5bd410732 |  | note | Inspection/Verification (Name, signature & date): Spark NEL Engineer - HP
label | 744b7499-6ea0-5696-b9b7-570aa0a707a7 |  | note | Inspection/Verification (Name, signature & date): Nominated Authority - NR
label | 0c3baa31-14ff-5b2d-80cc-6972cd0cc992 |  | note | Inspection/Verification (Name, signature & date): IREA - NR
label | 215d5494-c33b-5126-b18d-6f0382d908e0 |  | note | Records/Documents -
text | 87e24245-184d-5176-b39e-527eb2494135 |  | textbox | • IFC Drawings InEight Reference #:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 1.7 - All Equipment Calibrated (NATA Approved)
label | 50e9c1a0-56cb-528f-afeb-e64f8c87c0b8 |  | note | Resp. Person - PE
label | e08b62c8-61ae-53fc-95ff-8e99e2949097 |  | note | Specification Reference - CQMP Section 11.1
label | db3fce6a-1d06-5d0a-b760-6652a16d5a4d |  | note | Acceptance Criteria - Equipment calibration certificates filed in InEight. Document Ensure all equipment associated with the relevant works is calibrated.
label | 5189e3a9-a5a8-55b2-81ca-134984e1924b |  | note | Test Method - V
label | aa146429-4b7a-545d-ab49-321c993fe50e |  | note | Test Freq. - PW
label | 02047ac0-6b22-56ee-be85-478f95f33d1a |  | note | Inspection/Verification (Name, signature & date): Sub-Contractor - HP
label | 67bf8209-09e1-5b93-b4e0-8a71d05da436 |  | note | Inspection/Verification (Name, signature & date): Spark NEL Engineer - HP
label | 1a36dfa8-0b1b-505c-8db5-8c6b1450d8c3 |  | note | Inspection/Verification (Name, signature & date): Nominated Authority - NR
label | 7955e37c-8c6f-5b27-a736-67e6c41435a2 |  | note | Inspection/Verification (Name, signature & date): IREA - NR
label | 558a159d-f1c6-5f8c-88a4-04deaa4952d5 |  | note | Records/Documents - Calibration Certificates
text | 9c2b049a-41e9-590a-a8e0-4d3126bb4229 |  | textbox | • InEight Reference #:
boolean | cac89748-21f5-547e-93a1-707ae55b277f |  | tickbox | • Not Applicable
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 1.8 - Survey Set Out
label | 556946bf-31ad-5fb6-b440-e7b557ba1837 |  | note | Resp. Person - SE
label | 1a293040-a6e8-50bf-893a-4b51a74a557d |  | note | Specification Reference - PSDR Part F4 Section 6 IFC Drawings
label | 2a51367f-b92d-567f-8533-8f862d4243ae |  | note | Acceptance Criteria - Clearly mark limit of works; Chainage, offsets, cut/fill level etc. (if required)
label | 592548b6-53f8-5143-b423-2c49aa9059ed |  | note | Test Method - V
label | 04a4c2b7-8f19-531d-abbc-0a9de6be22e9 |  | note | Test Freq. - PW
label | cc8a6850-4663-5296-845a-3849bebf9a07 |  | note | Inspection/Verification (Name, signature & date): Sub-Contractor - HP
label | 3e39e227-1c1c-5e45-8178-4be1eec63417 |  | note | Inspection/Verification (Name, signature & date): Spark NEL Engineer - HP
label | 0834ef96-89fd-5dac-b24b-15f0825f2bb9 |  | note | Inspection/Verification (Name, signature & date): Nominated Authority - NR
label | a918bd20-777e-5f09-ac12-0bdba02bd378 |  | note | Inspection/Verification (Name, signature & date): IREA - NR
label | 3a86e165-bbec-53a8-a1a5-5a96d82e89fc |  | note | Records/Documents -
text | 52b44aac-ae67-52b7-8c3a-54ee0e011804 |  | textbox | • Survey Record InEight Reference #:
label | cdce917d-2ef3-5952-ae50-680362135b7d |  | note | • This ITP Lot Map
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 1.9 - Acceptance of Precast Reinforced Concrete Pipes & Pits
label | 6afa1eeb-e00f-5b29-ab4c-c29f75475759 |  | note | Resp. Person - PE
label | 67221cf7-e705-5b53-b9cb-96476fb163d7 |  | note | Specification Reference - VR 619.22, VR 701.05, VR 705.07 IFC Drawings
label | 931b9984-f2d1-534a-9db5-91499c43d34c |  | note | Acceptance Criteria - Precast Reinforced Concrete pipes shall be of the required sizes and load classes as shown on the drawings. Aggregates for precast reinforced concrete pipes shall comply with the requirements of section 610
label | fad2ebc9-dfd7-537b-ad1c-5b3e0c0ba13c |  | note | • Any steel reinforced concrete pipes that have cracks wider than 0.2mm or are damaged prior to laying and backfilling shall be rejected.
label | dd569362-0991-5958-9e7c-f6ce412b9d60 |  | note | • Concrete mix designs used for the manufacture of precast reinforced concrete pipes shall not be more than 12 months old and shall be available for review by the Superintendent.
label | 5ecf610f-a31d-5f95-8fa8-a556552c8a2c |  | note | • Precast steel reinforced concrete drainage pits shall be manufactured, supplied and installed in accordance with the requirements of Section 610 and Section 611.
label | eb9821f0-8e91-5ba4-ae19-1d867bbd86c6 |  | note | Test Method - I
label | 8058c4b3-4275-5e3c-8815-a7455103036d |  | note | Test Freq. - PL
label | 6433c0ee-599f-5f3b-9a42-33954c89a59c |  | note | Inspection/Verification (Name, signature & date): Sub-Contractor - HP
label | 642422ff-7c6a-56a1-9ccb-39b2d65f29b2 |  | note | Inspection/Verification (Name, signature & date): Spark NEL Engineer - HP
label | 8f01c379-d70a-5f3a-b2a4-56df1982872d |  | note | Inspection/Verification (Name, signature & date): Nominated Authority - WP
label | cb6b352c-cbc3-5bb2-aa67-f87ad8e3d1c0 |  | note | Inspection/Verification (Name, signature & date): IREA - WP
label | 9349ad1d-6c4a-5e7d-bd1c-8b6882de3b65 |  | note | Records/Documents -
text | 86f3ee31-fd11-5d56-9d89-f12934199bfa |  | textbox | • WP Release InEight Ref #
label | 820cd41f-7864-51e1-98c7-4df98c2a0ae2 |  | note | • Product Data Sheets
label | 511c90ff-3274-5e30-b658-325c844a9087 |  | note | • Proof load Test Results
label | d39bf420-966d-5009-81e1-b24bc62fb55f |  | note | • Ultimate Load Test Result
label | 99eeacd0-b551-5661-b167-f2f732f09e7e |  | note | • Dimension measurement
label | 4239cbdb-b64b-5086-b8b9-905a0812a919 |  | note | • Record Measurements of clear Concrete mix design letter
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 1.10 - Supply Precast Covers, Grates, Box Culverts, Lids and Pits
label | 5b3ba47d-145f-5777-9185-919825192eef |  | note | Resp. Person - PE
label | a471f699-3a8b-5171-a5c8-6b9afb83b5ea |  | note | Specification Reference - VR Clause 705.04, 701.31 IFC Drawings
label | 607ca848-a6b0-5adb-83e9-42a01385b972 |  | note | Acceptance Criteria - Complies with specified requirements. Free of defects and to IFC specifications.
label | 40ef3278-7df9-56dc-8470-b971faaef0d8 |  | note | • Concrete mix design to be approved by Superintendent
label | dec9be20-8c97-5762-b061-0fc9f6b9ad16 |  | note | • Box culverts which do not comply with the requirements of clause 619.14 prior to laying and backfilling shall be rejected and removed from the site. Checks to be conducted on delivery an prior to placement to ensure the product meets the acceptance criteria.
label | 07214407-48a8-5658-963e-003d587ef775 |  | note | Test Method - V
label | 5412e0f4-77fc-5a01-aa98-d42410f6b7cc |  | note | Test Freq. - PL
label | 3ffce9c1-3310-5c5a-8c70-c190fcaf1c15 |  | note | Inspection/Verification (Name, signature & date): Sub-Contractor - HP
label | 29493b27-3382-54f2-8383-66b89a57070e |  | note | Inspection/Verification (Name, signature & date): Spark NEL Engineer - HP
label | f4a21631-752c-596f-8c69-170e92c1df00 |  | note | Inspection/Verification (Name, signature & date): Nominated Authority - HP
label | 86357c03-4308-5cf6-8e71-2172de71af2f |  | note | Inspection/Verification (Name, signature & date): IREA - WP
label | 8a1ead3e-e4ff-5b85-b6fb-a0dc2f023af9 |  | note | Records/Documents -
text | 421af18b-755e-569f-b5c4-9d5bf6bbca65 |  | textbox | • HP Release InEight Ref #
label | d5f0e3fa-efa2-5186-96d7-c3bc5ede002d |  | note | • Manufacturing Compliance Certificates
label | 6bcfa1d5-d816-5f1d-9cd3-7ba6f0d9a62b |  | note | • Incoming Material Checklist
label | 05220166-2c53-5c7c-820c-552f91b3e7ac |  | note | • Delivery Dockets
label | f04fa70e-624a-517e-b3d7-f0150a2888ed |  | note | • Registered Concrete mix design for precast unit
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | 2.0 Operations (Include Work Execution – Installation / Manufacturing Process step-by-step)
checkpoint-status |  |  | checkpoint | 2.1 - Set Out
label | c85a89d9-3409-57b5-b090-da8bd3ac214b |  | note | Resp. Person - SE
label | 26ab8af5-5239-576a-b46e-149f4bd34271 |  | note | Specification Reference - IFC drawings VR 701.10
label | 57e7e1db-3137-5ac0-b6b1-bdab9bb6cec1 |  | note | Acceptance Criteria - Prior to commencement of excavation for the culverts the Contractor shall confirm the position of all culverts with the Superintendent.
label | ca8ec646-a312-5eb1-8234-9d45dd4f1789 |  | note | • Pit Set out points as per IFC Design schedule. Confirm that the invert of drainage pipes on the pit schedule design drawing match the corresponding design long section drawings.
label | f960c7c4-03f2-5d20-a0fb-3339ef32f8cd |  | note | • Confirm that the pit set out points are the correct orientation / bearing and offset to kerb/barriers and the VicRoads Standard Drawings
label | f60710b4-cee4-5045-af1d-b736eea173f8 |  | note | Test Method - V
label | c6821b8e-1da8-5372-bdc0-913fe2f33b1e |  | note | Test Freq. - PL
label | e2253351-9daa-5223-a0b6-9742408b34a2 |  | note | Inspection/Verification (Name, signature & date): Sub-Contractor - HP
label | 796009ea-44f1-5120-81ca-f5154292c2da |  | note | Inspection/Verification (Name, signature & date): Spark NEL Engineer - HP
label | 5a754aa1-0e48-5b1b-95b6-1f9920b00eb6 |  | note | Inspection/Verification (Name, signature & date): Nominated Authority - HP
label | 1b921a8b-7c45-51b3-a935-377f51c0717a |  | note | Inspection/Verification (Name, signature & date): IREA - WP
label | 9ffd5b2b-436a-585b-ad71-8fab3e8ec63b |  | note | Records/Documents -
text | 9c9737c1-f95e-5e4c-85e0-06bb1c853222 |  | textbox | • HP Release InEight Ref #
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.2 - Installation of Culverts in fills under Construction
label | a6232be1-7779-5c57-93a5-9b64ca1c8a9b |  | note | Resp. Person - SE
label | 6309c992-7b3b-5c94-9e75-e88635c4cc3f |  | note | Specification Reference - VR 701.13 IFC Drawings
label | a84d9eba-6bc6-5f1a-9e8b-008d291f35c4 |  | note | Acceptance Criteria - The fill shall first be constructed and compacted to subgrade level or to a level 300mm above the top of the proposed culvert, whichever is lower, for distance of not less than 6m clear on either side of the proposed trench.
label | c44f4e56-79d7-5893-9d6b-27ebd2dcf483 |  | note | Test Method - V
label | 2ac41eda-5384-530f-ae8e-bd1e493684c3 |  | note | Test Freq. - PL
label | b0f96c3c-6e3e-58b1-aba7-1501192c990a |  | note | Inspection/Verification (Name, signature & date): Sub-Contractor - HP
label | 597f8303-8b3d-5342-b6a4-1fecad3fedeb |  | note | Inspection/Verification (Name, signature & date): Spark NEL Engineer - HP
label | a2d5ca85-9c13-5791-ba50-1accb5a3caaa |  | note | Inspection/Verification (Name, signature & date): Nominated Authority - NR
label | 8ec022e6-c5dd-50fb-92e3-1dc739f9c748 |  | note | Inspection/Verification (Name, signature & date): IREA - NR
label | ef6d185e-30c3-5a54-b25a-5aa01980dbe8 |  | note | Records/Documents - This ITP
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.3 - Waterway Diversions
label | 137df4a3-a731-5944-8cd4-0dd619969355 |  | note | Resp. Person - SE
label | d045cbe0-3ece-534b-bef2-d1e3d24e2e4d |  | note | Specification Reference - VR 701.12
label | f6ec5831-64fb-503b-968f-3075a8b4c794 |  | note | Acceptance Criteria - Before obstructing any waterway, channel, culvert, or pipe, the Contractor shall make Provisions for temporary waterway diversion of flow, and obtain prior written approval from the relevant waterway authority.
label | 1c5885a2-b30b-5d6a-87ed-c421132df5e3 |  | note | Test Method - V
label | aa04fb30-68e2-5a72-a8e8-5cd8464eb307 |  | note | Test Freq. - PL
label | 42f78611-e302-5cda-a4e4-447d42e8c78e |  | note | Inspection/Verification (Name, signature & date): Sub-Contractor - HP
label | fa9dd5b1-c116-550a-b47d-9c9879929e90 |  | note | Inspection/Verification (Name, signature & date): Spark NEL Engineer - HP
label | 7f09abc6-5569-538e-bfbe-5aed23232ad0 |  | note | Inspection/Verification (Name, signature & date): Nominated Authority - NR
label | c293b5da-e163-5e63-8a45-3ca60c71b15b |  | note | Inspection/Verification (Name, signature & date): IREA - NR
label | b163bb03-4246-57c8-976e-0af359f24c84 |  | note | Records/Documents - Dewatering Permit
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.4 - Construction Loading on Culverts
label | 36cb46f7-96c6-5c46-af46-97f7a7a6a14c |  | note | Resp. Person - SE
label | 8f66c0a6-b98a-5d73-aa9b-4c198ad4b3ec |  | note | Specification Reference - VR 701.14 Table 701.141
label | 0870b933-f013-5d39-b72a-ac726838ea83 |  | note | Acceptance Criteria - Construction Traffic shall not be allowed until the minimum cover achieved as per Table 701.141 (Attached Below)
label | 1de91d6e-9278-5dba-8029-b497c5f3f909 |  | note | Test Method - V
label | a7953efe-cecc-538c-b6de-2bde48607e56 |  | note | Test Freq. - PL
label | 050424ad-afc0-5c0c-8ddf-1411cc4f64b6 |  | note | Inspection/Verification (Name, signature & date): Sub-Contractor - HP
label | 0a629629-7699-58b2-96e1-822344ee9169 |  | note | Inspection/Verification (Name, signature & date): Spark NEL Engineer - HP
label | 7ea1c06a-535f-5c01-bc3f-4c5bb339bc5d |  | note | Inspection/Verification (Name, signature & date): Nominated Authority - NR
label | b93fb08d-f718-5fcf-ab00-9a6f0009c404 |  | note | Inspection/Verification (Name, signature & date): IREA - NR
label | ad17f6f5-4389-5ba4-ab07-418f0ab820ae |  | note | Records/Documents - This ITP
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.5 - Excavation of Trench for Culverts and Pits
label | 5d064a92-5a50-56fb-97b6-ce1986887434 |  | note | Resp. Person - SE
label | d80fc45b-3108-52c5-b704-f666700cf35c |  | note | Specification Reference - VR 701.14, VR 701.15 Table 701.151, VR 705.05 (b) IFC Drawings
label | 4d522c82-4cb0-5ccf-b034-f381167d3353 |  | note | Acceptance Criteria - Excavate to required depth which shall also include excavation necessary to prepare the culvert/pit foundation and provide the full specified depth of culvert/pit bedding. For pipe culverts, the width of trench at and below the level of the top of the pipe shall be such that the horizontal clearance from the outside of the pipe to the wall of the trench is within the limits shown in Table 701.151.
label | 72838649-dd72-5fff-b514-ef6b6caa4b64 |  | note | • For precast pits the excavation shall provide a clearance from all external faces of the pit to each face of the excavation of not less than 400 mm. Bedding conforming to the requirements of Section 701 shall be supplied, placed and compacted to a thickness not less than 80 mm on a clay foundation or 150 mm on a rock foundation.
label | 80c409e1-0de2-57bc-bd56-318f329dfd73 |  | note | Test Method - V
label | ba937b1b-7317-5ea3-a4fe-1f36c4361199 |  | note | Test Freq. - PL
label | 65a39dde-124f-58ec-ada5-437b530844cb |  | note | Inspection/Verification (Name, signature & date): Sub-Contractor - WP
label | 7950f1a1-f349-57af-b24a-62f4f22d77b8 |  | note | Inspection/Verification (Name, signature & date): Spark NEL Engineer - WP
label | 2339ae06-ca18-592e-a0ef-76e08530cde1 |  | note | Inspection/Verification (Name, signature & date): Nominated Authority - NR
label | b372623e-8ca4-564b-8826-51a175fdb629 |  | note | Inspection/Verification (Name, signature & date): IREA - NR
label | f83791b5-b4a1-56ca-a646-6d011ef0c03e |  | note | Records/Documents - This ITP
checkpoint-status |  |  | checkpoint | 2.6 - Base of Trench
label | 1cea6844-6e77-5802-a417-d1d023983a55 |  | note | Resp. Person - SE
label | bf091075-b05f-570c-bf4a-82ecb091b47d |  | note | Specification Reference - VR 701.15
label | ce682e9e-26f5-5665-9775-80dcb0cb3a0a |  | note | Acceptance Criteria - The base of the trench shall be compacted to refusal using mechanical plant. The Contractor shall treat or replace all soft, wet or unstable material below the level required to provide the minimum specified thickness of culvert bedding, as specified in clause 701.16.
label | 902fb9f1-1f7c-5fb1-b5c1-b71da7c64094 |  | note | • Replacement material if used, shall be compacted in accordance with clause 701.20.
label | 7912da7c-6d81-594b-b949-2f7126e3c29a |  | note | Test Method - V
label | 5eaf78ec-6c9d-5a7d-8d02-b8e26784f119 |  | note | Test Freq. - PL
label | 0d18ec49-61f8-5816-bc0f-1ea83f7f2693 |  | note | Inspection/Verification (Name, signature & date): Sub-Contractor - WP
label | 4d5dd767-39d8-508a-9f3b-6551dfda2e97 |  | note | Inspection/Verification (Name, signature & date): Spark NEL Engineer - WP
label | a8311b48-5961-5149-8b31-7abc67df240f |  | note | Inspection/Verification (Name, signature & date): Nominated Authority - NR
label | bdb68580-cff5-58ee-a05e-6dfdabea2567 |  | note | Inspection/Verification (Name, signature & date): IREA - NR
label | 47fda484-8c89-5f7f-8439-4b49243946d2 |  | note | Records/Documents - Photos
label | 24ee9781-0eb9-56ca-bd15-aa2c5f174bfb |  | note | • Material Conformance Docs (Imported Fill)
checkpoint-status |  |  | checkpoint | 2.7 - Bedding – Layer Thickness, Compaction and Moisture Content requirements
label | e034d49f-0078-56ac-80b4-a5e9136923a1 |  | note | Resp. Person - SE
label | 150b4f7d-47d5-5666-9690-0d2c17b2d238 |  | note | Specification Reference - VR 701.16, VR 701.20 IFC Drawings
label | e8cce19f-4efa-5010-99eb-1652c261dc34 |  | note | Acceptance Criteria - Bedding material shall be provided and placed for the full width of the trench or, where the culvert is to be placed without trenching, to a width 0.8 m greater than the overall width of the culvert. The compacted thickness of bedding material following any shaping necessary shall be not less than:
label | 53e75762-e965-57c2-9e97-b6b03fce0e96 |  | note | • 100 mm where D < 1500 mm
label | e5059aea-8b1d-5e93-98a9-c298abe8b50b |  | note | • 200 mm where D ≥ 1500 mm where D is the nominal pipe diameter or culvert width.
label | 653889d4-94af-50fa-a5a5-9473d2b098cd |  | note | ○ For Pits, bedding placed and compacted to a thickness not less than 80mm on clay foundations or 150mm on rock foundations.
label | cd554fa8-609f-5ede-b69e-de0e918f6f6d |  | note | ○ Bedding shall be compacted to refusal using hand held mechanical equipment. Bedding material which has a swell equal to or greater than 2.5% shall be maintained at a mean moisture ratio of 92% between the completion of rolling and the placement of the overlying layer.
label | 133a7ecd-8636-51c5-9958-5611023090ac |  | note | Test Method - V
label | f78cd4f0-236c-5b2c-a7e6-2d8d4dc560b6 |  | note | Test Freq. - PL
label | 227b45bc-c6a3-5055-9eee-6a9908272352 |  | note | Inspection/Verification (Name, signature & date): Sub-Contractor - WP
label | 497d8521-9a75-563a-a084-00f0caa22276 |  | note | Inspection/Verification (Name, signature & date): Spark NEL Engineer - WP
label | 35dd83f2-b21d-568c-96b7-c42f6efd2842 |  | note | Inspection/Verification (Name, signature & date): Nominated Authority - NR
label | dfc94024-a266-52c7-aeed-21e04763c2f7 |  | note | Inspection/Verification (Name, signature & date): IREA - NR
label | 9728fabd-abca-517f-a3ce-b0080a463bcd |  | note | Records/Documents - This ITP NATA Test Report
checkpoint-status |  |  | checkpoint | 2.8 - Laying of Pipes
label | a6eb1c2d-dd50-5bbf-9a78-49707a6c1ca8 |  | note | Resp. Person - SE
label | ade0950e-3f39-5ee7-ac3b-95ee1e857593 |  | note | Specification Reference - VR 701.04, VR 701.05, VR 701.17 (a), (b) IFC Drawings, Construction Packages PSDR Part B Section 5.5
label | 116b0f54-9d75-5802-a473-a72f6e44573a |  | note | Acceptance Criteria - Laying of pipes or box culverts shall not commence until the Contractor has verified that culvert bedding complies with the specified lines and levels and compaction requirements, and that box culverts and pipes are not damaged and comply with the requirements of clause 701.04 and Clause 701.05 respectively.
label | 3610bbb2-7b53-5178-9015-60b1939ed128 |  | note | • Laying of pipes or box culverts shall commence from the downstream end.
label | c7a46e26-a05c-55f2-9ce4-4992ffa7e679 |  | note | • Rebate and socket ends of pipe sections shall be placed facing upstream and be fully entered. The lower portion of the pipe shall be in contact with the bedding for the full length of each section.
label | cc0ff489-bcda-5064-9843-8e168cc2feed |  | note | • The compacted bedding shall be shaped to accommodate the joint collar and ensure that the pipe is supported along its full length.
label | d58bd2d5-ea60-54cc-9be9-3fd47392e948 |  | note | Test Method - V
label | b338ab80-d5e2-5ee0-98d4-90f4b9b2f3db |  | note | Test Freq. - PL
label | 00d32de7-fe36-55ee-979e-41b3c0239eb5 |  | note | Inspection/Verification (Name, signature & date): Sub-Contractor - HP
label | 8ff90a96-0cbd-54a2-a1f0-fa4d86725ca5 |  | note | Inspection/Verification (Name, signature & date): Spark NEL Engineer - HP
label | b494030b-5915-507e-907a-1fb7a86d7117 |  | note | Inspection/Verification (Name, signature & date): Nominated Authority - NR
label | 5e1e39e0-ebb5-59e8-8d0c-0c2adf6b6371 |  | note | Inspection/Verification (Name, signature & date): IREA - NR
label | 6f56b222-2d08-5a0e-b1de-1b7df30bef24 |  | note | Records/Documents - This ITP Photos
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.9 - Installation of Precast Steel Reinforced Concrete Drainage Pits
label | 546111e1-d64e-5518-8795-d54119e3acfb |  | note | Resp. Person - SE
label | 07fcbafa-576d-5c63-9d33-3f5a338f52cb |  | note | Specification Reference - VR 705.07, VR 705.09 (a), (b), (c) VR 705.10 IFC Drawings, PSDR Part B Section 5.5 Construction Package
label | a1a3261e-d7a0-583b-8f83-f350c4e9a9ec |  | note | Acceptance Criteria - Precast pits shall be installed at the locations and to the dimensions shown on the IFC drawings.
label | 372e1541-0553-5a1a-b922-ed06e719861e |  | note | • Subsurface Drainage Connection – Holes for subsurface drainage shall be 150mm diameter, cored only.
label | 50119ff3-55d9-5a9d-a666-782221bb0fb5 |  | note | • Segments – If a precast pit is cast in segments, each section of the pit shall be rebated to ensure correct alignment and to prevent horizontal movement. A minimum rebate of 15mm shall be used. All pits to comply with clauses 705.09 and 705.10 The spacing for multiple row culverts shall be as shown in Table 701.171.
label | 71d99850-fd28-5c4f-84f6-056b71cf2928 |  | note | Test Method - V
label | 046e59c3-9909-5126-a566-ec2602feca8a |  | note | Test Freq. - PL
label | d8760aea-5486-5042-914a-d7a35fb81c22 |  | note | Inspection/Verification (Name, signature & date): Sub-Contractor - HP
label | 589f30ed-d36d-5814-b056-0a4edcb38b21 |  | note | Inspection/Verification (Name, signature & date): Spark NEL Engineer - WP
label | 6623cec8-5bca-5078-8fa4-504191e9ac1c |  | note | Inspection/Verification (Name, signature & date): Nominated Authority - NR
label | 965fe62f-e8bd-55b9-8e70-5a3982e339f7 |  | note | Inspection/Verification (Name, signature & date): IREA - NR
label | 8ef2c51a-465b-5a7f-b2b6-e14533c8948f |  | note | Records/Documents - This ITP Photos
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.10 - Cast In Place Drainage Pit (If applicable)
label | d9a6909c-ec53-5a00-b51e-68483a2914c4 |  | note | Resp. Person - SE
label | f2c1142e-4dda-5ed4-a9ff-1fa9162bf6b6 |  | note | Specification Reference - VR705.06 IFC Drawings
label | 431711ea-9163-531f-9dc2-cab1c1133516 |  | note | Acceptance Criteria - Cast in place drainage pits shall be constructed at the locations and to the dimensions shown on the drawings.
label | 21d1ac70-8673-5d52-934e-1423b61bbd78 |  | note | • Cast in place drainage pits shall be constructed in accordance with the requirements of Section 610 and Section 611.
label | 580a7ae7-5093-5ded-acfe-c1b071af5b3f |  | note | • Cast in place drainage pits shall not be constructed with fibre reinforced concrete (FRC).
label | bcb864b2-3c45-54a3-a02d-21c0e6b21781 |  | note | Test Method - V
label | eed4b80d-c9c9-5e4c-97c8-a1a86c1bb312 |  | note | Test Freq. - PL
label | b5fd5f6d-fa5c-5da1-b9be-0dee86cd864f |  | note | Inspection/Verification (Name, signature & date): Sub-Contractor - HP
label | c2427815-675f-5eb2-81aa-10c3a62e7a1e |  | note | Inspection/Verification (Name, signature & date): Spark NEL Engineer - WP
label | dc185b3d-fc35-53cf-b1d7-ad6df676685d |  | note | Inspection/Verification (Name, signature & date): Nominated Authority - NR
label | fa9c9e45-b83f-57f1-b9c7-4a5f646f152c |  | note | Inspection/Verification (Name, signature & date): IREA - NR
label | fb9ea579-c823-58e5-88aa-b675b9599f0c |  | note | Records/Documents - This ITP Photos
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.11 - Precast Fibre Reinforced Concrete Drainage Pit (if applicable)
label | 36cde07e-f489-54f6-ba14-00d57695e10a |  | note | Resp. Person - SE
label | d771001e-68a6-5f80-9557-cb754c697fe7 |  | note | Specification Reference - VR705.08 (a) to (e) IFC Drawings PSDR Part B Section 5.5
label | 852dbd58-e7ba-5aea-81fe-5bd7a48edca7 |  | note | Acceptance Criteria - Precast fibre reinforced concrete (FRC) drainage pits shall be manufactured, supplied and installed in accordance with the requirements of Section 610 and relevant Australian Standards listed in clause705.02
label | 7fd24df9-d64a-53cc-988c-1d5085292c52 |  | note | • The worksheet and/or report for determination of fibre content shall be submitted for review by the Superintendent.
label | ba1e51ed-acc7-58ff-a817-acbc376b5391 |  | note | Test Method - I
label | c0dfd510-00b5-5c15-85ef-8e64a1b1f6f0 |  | note | Test Freq. - PL
label | 7d697c3a-f8d9-505d-94c0-3b3ce31ca242 |  | note | Inspection/Verification (Name, signature & date): Sub-Contractor - HP
label | a567b6d7-4fef-5f65-97c2-aff31138c5c0 |  | note | Inspection/Verification (Name, signature & date): Spark NEL Engineer - HP
label | 542d06ca-c1a8-5241-99fb-0f3d6f3f1463 |  | note | Inspection/Verification (Name, signature & date): Nominated Authority - WP
label | f9d28bbb-90e7-51c3-8bcf-73820bfdcadf |  | note | Inspection/Verification (Name, signature & date): IREA - WP
label | 4b3f2cb9-4646-5093-afec-2f40d2496c5a |  | note | Records/Documents -
text | 52505749-c9af-582d-9afc-b8a5201805a5 |  | textbox | • WP Release InEight Ref #
label | e71c6c84-2ee8-5aff-89c5-6c75fcd628ff |  | note | • This ITP
label | e416a65d-87ba-5a76-8436-65046a4c94f5 |  | note | • Load Test Report Fibre content Worksheet/Report
boolean | 387cc57c-a10a-52a8-9060-18cbd6102620 |  | tickbox | • Not applicable
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.12 - Drainage Pits in Shoulder (if applicable)
label | 681cd23c-c60d-5d95-a5a5-9af6479854d4 |  | note | Resp. Person - SE
label | e9891fb1-034f-5a19-96ec-08c6fbef1157 |  | note | Specification Reference - IFC Drawings PSDR Part B Section 5.6
label | 5ba69eed-be41-5769-af85-e44f10e26261 |  | note | Acceptance Criteria - Drainage pits must:
label | 95f0063f-53e4-51a1-9d19-5ddab99eecaf |  | note | (a) on the freeway carriageways, freeway ramps and the Doncaster Busway be located to avoid the intrusion of pits and grates into any traffic lane; and
label | 3b69e13e-f44e-5fb7-9dee-f10c203562da |  | note | (b) on arterial roads and local roads be located to avoid the intrusion of pits and grates into any traffic lane or on-road bicycle lane, and be trafficable for cyclists.
label | 75641b37-e142-56ab-8663-f0ef48a6ec07 |  | note | Test Method - I
label | 9d748bf1-9a7a-5bed-8280-6e929ea7eb9e |  | note | Test Freq. - PL
label | 1519f331-d670-5696-a87a-6fc98e6438dc |  | note | Inspection/Verification (Name, signature & date): Sub-Contractor - WP
label | 6117733f-9fe2-5543-8c3f-28625f2abdd7 |  | note | Inspection/Verification (Name, signature & date): Spark NEL Engineer - WP
label | 2b912ba6-0b3f-5e1b-8de6-3ef07367f236 |  | note | Inspection/Verification (Name, signature & date): Nominated Authority - NR
label | d1c8ea4c-4ed3-5350-aba1-acba9a86e9c8 |  | note | Inspection/Verification (Name, signature & date): IREA - NR
label | 7f005fd4-45f3-59e5-ad79-50c0612ca26b |  | note | Records/Documents - This ITP Photos
checkpoint-status |  |  | checkpoint | 2.13 - Step Iron Fitting
label | 60406fd0-249a-5d5a-908d-a9f55f316cc5 |  | note | Resp. Person - SE
label | c5e4450c-737b-507f-8f32-412ce4631c14 |  | note | Specification Reference - VR 705.04(d) VR 705.12 AS3679.1 AS4671 IFC Drawings
label | ac203703-c0b8-5d72-ad07-a224eb82022e |  | note | Acceptance Criteria - Drainage pits greater than 1.0 m deep shall be fitted with step irons as shown on the drawings. Steps shall be:
label | 7fbc56e5-294f-57e8-9ed9-205f92ce9c56 |  | note | – Located so that they do not obstruct openings and that water does not discharge onto them.
label | 50aa22ff-2565-50f2-9d9d-c10c6b7732dc |  | note | – Set into a wall which has no openings, or beside an opening, or across a corner of the pit.
label | ad48fc0e-2207-5d69-a536-31e5e6aa5468 |  | note | – Installed horizontal, vertically in line and shall project uniformly from drainage pit walls. Step irons of an approved proprietary type shall be installed in accordance with the manufacturer's instructions. Where drainage pits are extended in height from the lowest pit, step irons shall be located such that an equidistant spacing between step irons is still maintained.
label | 3e8f07bc-00c2-5c87-a4af-58a32742941c |  | note | • Where step irons are cast in place, they shall be epoxy mortared into drilled holes using an epoxy material and method approved by the Superintendent.
label | 62f12775-d0de-5b2e-a25d-5142135641c4 |  | note | Test Method - V
label | 92c05ff7-5402-5618-bc54-0d8600e641bd |  | note | Test Freq. - PL
label | 7ccad3e2-e114-5d5f-b4e2-6f485fbb4fa5 |  | note | Inspection/Verification (Name, signature & date): Sub-Contractor - HP
label | 773993b8-8f9b-574b-a3b2-bd6ee9ad2a77 |  | note | Inspection/Verification (Name, signature & date): Spark NEL Engineer - HP
label | 9d6f087b-7156-5957-8d09-ebb9fd312342 |  | note | Inspection/Verification (Name, signature & date): Nominated Authority - WP
label | 37bd6731-f722-5ffb-baae-d609cd5dd16f |  | note | Inspection/Verification (Name, signature & date): IREA - WP
label | 7a86b78c-a773-56a3-9350-94727e199ff6 |  | note | Records/Documents -
text | d8e86446-4c94-51b3-80eb-151ce82ba23a |  | textbox | • WP Release InEight Ref #
label | e8e63196-c43d-5a86-bd5a-45502ed248a2 |  | note | • Photos
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.14 - Shaping the Floor
label | 0c31d412-f6de-5c69-84c5-22f68fe74538 |  | note | Resp. Person - SE
label | 3793a657-0681-5af4-934a-4315df15ed84 |  | note | Specification Reference - VR 705.13 VR 610.33 IFC Drawings
label | 539102b8-cec3-5a24-9025-03e55d923e9f |  | note | Acceptance Criteria - Drainage pit floors shall be smoothly shaped from the inlets to the outlet for a height of one third of the diameter of the outlet pipe with cementitious mortar, to provide a profile that will ensure smooth flow conditions between the invert of inlet and outlet pipes and prevent any snagging of debris. The cementitious mortar shall comply with the requirements of clause 610.33.
label | 8f00d5e6-9d13-5480-aed5-66940e96183e |  | note | Test Method - V
label | 4792918c-7eab-5e66-ac9f-9ecf18586dcf |  | note | Test Freq. - PL
label | e69c5ba7-2d71-5e50-bf4e-4a79fb0b1fce |  | note | Inspection/Verification (Name, signature & date): Sub-Contractor - HP
label | d7562009-a62e-5481-aa92-b4747271df56 |  | note | Inspection/Verification (Name, signature & date): Spark NEL Engineer - WP
label | c6b1eb47-d1cd-5f42-abcc-d366a1dd4c47 |  | note | Inspection/Verification (Name, signature & date): Nominated Authority - NR
label | 3f1ca654-a89b-50de-a29e-afea071f01cf |  | note | Inspection/Verification (Name, signature & date): IREA - NR
label | a03d9ad5-ca16-52c4-b2a5-a8fd0a31ee59 |  | note | Records/Documents - This ITP
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.15 - Joints and Lifting Holes
label | ef171f4e-6343-5f31-9b6c-60c693335809 |  | note | Resp. Person - SE
label | 3ffe79b8-d47e-5d1a-8fdb-50188008523d |  | note | Specification Reference - VR 610.33 VR 701.18 VR 705.15 IFC Drawings Construction Package
label | 6dd3424c-0f00-5118-add7-61562a411379 |  | note | Acceptance Criteria - All interlocking (flush) joint reinforced concrete pipes shall be mortar jointed or wrapped with a 200 mm wide external joint rubber band.
label | f639866a-7a61-54f0-a585-0155b96eb015 |  | note | • Where lifting holes are provided, the pipes shall be laid with the hole uppermost. Lifting holes shall be plugged or otherwise closed off in accordance with the manufacturer’s instructions after the pipe is installed. Plugs shall not impair the pipe durability or serviceability.
label | 5831438d-054b-5fad-af6b-5fbfe7d4b2c6 |  | note | • The joints between various components such as drainage pits, access chambers and pipes shall be made watertight using a cementitious mortar in accordance with the requirements of clause 610.33. The joint areas shall be thoroughly cleaned and wetted just prior to filling.
label | 8fb7fc74-d22e-5a5f-aa96-93a4b1395512 |  | note | Test Method - R
label | e7949bbd-55e6-50b8-8802-9a80313b63b5 |  | note | Test Freq. - PL
label | 93c76631-3c0a-51ce-bbf3-45269a3258ff |  | note | Inspection/Verification (Name, signature & date): Sub-Contractor - HP
label | a0686862-f616-5ca0-8d5b-b596d5ab5fcc |  | note | Inspection/Verification (Name, signature & date): Spark NEL Engineer - WP
label | f07402c6-4830-5673-bc9f-edee4f8d7ec4 |  | note | Inspection/Verification (Name, signature & date): Nominated Authority - NR
label | 4f36ea04-eb30-5c23-9639-d7e2a355c3ef |  | note | Inspection/Verification (Name, signature & date): IREA - NR
label | 20ae7c14-4d37-5fde-b636-939a47ecbb7b |  | note | Records/Documents - This ITP Photos
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.16 - Placement of Filling
label | 400dc87c-1d7f-5f41-a455-93e9bbacbf3d |  | note | Resp. Person - SE
label | 62f74eec-5fd7-563b-a10c-4dd210378d29 |  | note | Specification Reference - VR 701.19 (a) VR 701.20 IFC Drawings
label | 0fc8fe13-b570-5834-a70c-88da0ad72c8b |  | note | Acceptance Criteria - Bedding and backfill materials shall be placed and compacted in layers not exceeding 150 mm loose thickness.
label | 08f8904b-d2ef-5f39-a2b1-8069e52fe1ee |  | note | (i) Culvert under area to be paved: Where the trench has been excavated from design subgrade level or above, the trench shall be backfilled to design subgrade level with selected backfill material, and above that level with appropriate pavement material. Where the trench is excavated from below design subgrade level the trench shall be filled with selected backfill material.
label | f43d4d48-3507-5c09-bb38-e320c121f306 |  | note | (ii) Culvert under areas not to be paved: The trench shall be backfilled with selected backfill material to a level 0.3m above the top of the culvert and with ordinary backfill material above that level.
label | 4ec8ee25-39c1-5377-9b8f-0f768e89ccaf |  | note | Test Method - V
label | f3fbebb5-4401-51a3-9574-8fc90cc4b37b |  | note | Test Freq. - PL
label | 9829cf34-1f0d-50f4-8194-0865ade0fbe5 |  | note | Inspection/Verification (Name, signature & date): Sub-Contractor - HP
label | 2a73449f-99e2-5098-9ad6-34da52849989 |  | note | Inspection/Verification (Name, signature & date): Spark NEL Engineer - WP
label | 39f31dfe-92d9-5f36-ae0c-e37877865f4a |  | note | Inspection/Verification (Name, signature & date): Nominated Authority - NR
label | 077d5069-f930-5ef6-9ab5-49477d1cbd30 |  | note | Inspection/Verification (Name, signature & date): IREA - NR
label | ef1923e9-3473-5648-b617-ce5e3bd34d04 |  | note | Records/Documents - This ITP Photos
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.17 - Backfill with Cement Stabilised Sand
label | d03939ae-e678-5774-b58e-ca798780a9e4 |  | note | Resp. Person - SE
label | a8e44187-e507-59d5-973d-7adf8c8c380a |  | note | Specification Reference - VR 701.19 (c) IFC Drawings
label | f135d70f-64d0-5581-ab44-defe6b94f028 |  | note | Acceptance Criteria - Where approved by the Superintendent, culverts in trenches may be backfilled to half the pipe diameter or box culvert height with 3% cement stabilised sand with a water content sufficient to ensure penetration beneath the pipe or box culvert invert without leaving free surface water.
label | cd21c664-a9c7-5196-a56e-f4d40d274931 |  | note | Test Method - R
label | e6d74be7-385a-5c0b-8d29-a8601dac1fd0 |  | note | Test Freq. - PL
label | 2c94161b-852a-5051-8a58-b3f10fff6d87 |  | note | Inspection/Verification (Name, signature & date): Sub-Contractor - HP
label | 6682cb53-b195-5adf-9dcb-485d55a9f24b |  | note | Inspection/Verification (Name, signature & date): Spark NEL Engineer - HP
label | 6ee732a2-bdca-5287-bedd-6986a89362aa |  | note | Inspection/Verification (Name, signature & date): Nominated Authority - WP
label | 0e26c21c-9311-5e1d-a868-e5ec2ef1f3af |  | note | Inspection/Verification (Name, signature & date): IREA - WP
label | d8e99349-59b3-586c-b8f5-d804af491876 |  | note | Records/Documents -
text | 8df00333-46aa-512d-90e0-0a7c38cacbe8 |  | textbox | • WP Release InEight Ref #
label | 239088b9-40e7-597e-b4cb-8f4318187f95 |  | note | • Photos
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.18 - Testing and Acceptance of Compaction and Moisture Content
label | e0049d8f-5b7b-599f-854c-d8cb5f67a95f |  | note | Resp. Person - SE
label | 6757937a-25c0-54e2-a6e1-990ff7b82b90 |  | note | Specification Reference - VR 701.20
label | 1f32874e-88c3-5c19-a183-c8eb4eb2d1e7 |  | note | Acceptance Criteria - The number of tests per lot shall be three.
label | b466b0b5-11b5-5714-9a02-941f104063df |  | note | • A lot shall consist of one layer of bedding or backfill for a culvert between adjacent pits or end wall. A minimum of 20% of all lots for each culvert shall be tested.
label | 1006eae3-44e6-55fa-bc1b-cc9abf9b9a49 |  | note | • Backfill material which will have a nominal size after compaction of 40 mm or less shall be compacted to a mean value of density ratio of not less than 97%. Backfill material which has a swell equal to or greater than 2.5% shall be maintained at a mean moisture ratio of 92% between the completion of rolling and the placement of the overlying layer.
label | f804169f-4943-582a-ac13-06c9a5db1d60 |  | note | Test Method - R
label | efb6c88d-70cc-5d5f-89c6-3b59b804fe05 |  | note | Test Freq. - PL
label | 71e6e490-2282-55f5-9f53-5849492f9808 |  | note | Inspection/Verification (Name, signature & date): Sub-Contractor - HP
label | 41688aca-d53f-5052-9961-46349a02a443 |  | note | Inspection/Verification (Name, signature & date): Spark NEL Engineer - HP
label | 74e86320-5c2d-5fab-9862-af17d1373742 |  | note | Inspection/Verification (Name, signature & date): Nominated Authority - NR
label | 312197a2-ad17-560f-94e2-8f00b7fd58a1 |  | note | Inspection/Verification (Name, signature & date): IREA - NR
label | 3cbbd1d9-9a69-5714-88eb-35746fb1721f |  | note | Records/Documents - NATA Test report: Compaction and Moisture Content
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.19 - Testing – Backfill Material
label | 8f7428b8-1348-53fd-a828-192a22e6a2af |  | note | Resp. Person - SE
label | 697db067-1367-5b48-b792-01a3d2becfde |  | note | Specification Reference - VR 701.19 VR 701.29 Table 701.291 IFC Drawings
label | 80b3c580-baa0-5e40-adf8-ec5ab9a7e7f5 |  | note | Acceptance Criteria - Grading and Plasticity Index testing
label | 706c71d2-36e9-50a9-a28b-69b027b56fc4 |  | note | Test Method - R
label | f88605d2-1c61-5a3d-9052-bebcdffe8a1d |  | note | Test Freq. - X1
label | 3ccfd59d-93c0-5b0f-a717-cccd782ce68d |  | note | Inspection/Verification (Name, signature & date): Sub-Contractor - HP
label | 02937134-9adf-54a6-9ae3-5fa3e72b595f |  | note | Inspection/Verification (Name, signature & date): Spark NEL Engineer - HP
label | 86790c7c-98bc-5557-9890-4785ae68d7d0 |  | note | Inspection/Verification (Name, signature & date): Nominated Authority - NR
label | 76bcd37e-d107-5d19-8b57-00901daf16b5 |  | note | Inspection/Verification (Name, signature & date): IREA - NR
label | 98cdf6f5-b116-52ea-a0a8-0ae0c9ac0d69 |  | note | Records/Documents - NATA Test Report: Grading and PI
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.20 - SE
label | 24445e2d-3d4d-5518-886f-a2621a1493dd |  | note | Resp. Person - Fitting of Covers
label | e797bf44-d393-5da4-ac32-b5495f483ea7 |  | note | Specification Reference - VR 705.04(c) VR 705.17 IFC Drawings
label | f83421c4-72d2-5d06-838f-f0bb07b33996 |  | note | Acceptance Criteria - Frames for drainage pit covers shall be cast into the top of the drainage pit or bedded on fresh mortar, 5 mm thick, consisting of two parts of sand, one part of cement and sufficient water to produce a mix of suitable consistency.
label | f03cb8fc-06a7-52ac-bae4-5eab31255cd8 |  | note | • The level at every point of the perimeter shall be within 10 mm of the design level for that point, and the line of the cover shall be within 10 mm of the design kerb line.
label | 51897c09-383c-5f35-a380-a2ea0455c041 |  | note | Test Method - R
label | a4758c03-27c3-5795-85ff-2ad52e0de4d9 |  | note | Test Freq. - X1
label | 04956162-164c-5819-acd0-4f3cfb78937b |  | note | Inspection/Verification (Name, signature & date): Sub-Contractor - HP
label | b8000e81-3f09-5ef4-b8ae-2a1b807c9b50 |  | note | Inspection/Verification (Name, signature & date): Spark NEL Engineer - HP
label | 76e0ee28-8e1c-5571-a6e6-f1b69d8ba791 |  | note | Inspection/Verification (Name, signature & date): Nominated Authority - NR
label | 61243b31-6f10-525a-bd61-87f15a14f833 |  | note | Inspection/Verification (Name, signature & date): IREA - NR
label | 6421d575-01a2-5b19-b4c8-a8c54b6b6c25 |  | note | Records/Documents - This ITP, Photos
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.21 - Flushing of Culverts
label | 9f59d0ae-04da-5494-8ec0-96cc3ca16468 |  | note | Resp. Person - SE
label | 5cbf06de-789a-5dd6-a1c8-bdd506a10f70 |  | note | Specification Reference - VR 701.28
label | 7bbc0fc4-3dab-5b96-bf39-23f3f808d9c5 |  | note | Acceptance Criteria - All culverts shall be flushed clean from end to end on completion and maintained in proper working order.
label | 40fd1cac-d905-5373-802b-c97fdfc92dbb |  | note | Test Method - R
label | 93f45646-7c5a-52f1-9fbe-d8f90416ccea |  | note | Test Freq. - PL
label | 56dbd966-abe3-5b00-9e0c-1d98e36cbd02 |  | note | Inspection/Verification (Name, signature & date): Sub-Contractor - HP
label | 22adea53-cd88-5d34-b6c8-2a2634cb40ab |  | note | Inspection/Verification (Name, signature & date): Spark NEL Engineer - WP
label | 4a46ba91-8e08-58c0-bf9f-8b13d87f0067 |  | note | Inspection/Verification (Name, signature & date): Nominated Authority - NR
label | a06e1a5d-167f-5524-a6ee-d9dc67588c9d |  | note | Inspection/Verification (Name, signature & date): IREA - NR
label | 5b9679e5-3d1e-5b61-9369-1d9d5c9fed61 |  | note | Records/Documents - This ITP
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.22 - Inspection of Drainage Lines
label | ec422f47-33e1-5a41-b96b-bc70f8e79140 |  | note | Resp. Person - SE
label | ae4bda9c-0828-5ebc-b5af-c5354742da6c |  | note | Specification Reference - VR 701.30 PSDR Part B Section 5.5
label | f4345616-0566-57b8-9153-ce8b49692e2b |  | note | Acceptance Criteria - All drainage lines constructed shall be inspected, after completion of earthworks to subgrade level and prior to construction of pavement layers, and after completion of landscaping by an independent testing organisation using closed circuit television (CCTV) to verify that the flow of water is not obstructed by waste construction material left inside and to check for visible signs of defects.
label | 67b8275a-43b2-51ee-b526-ef48e2a97d97 |  | note | Test Method - V
label | f284af69-12d0-59ed-a5d2-b4caf0089a4b |  | note | Test Freq. - PL
label | c581c46c-d33f-56ef-9074-78bd9091ec76 |  | note | Inspection/Verification (Name, signature & date): Sub-Contractor - HP
label | 25306b2f-8c85-530a-a54f-1eb72c409496 |  | note | Inspection/Verification (Name, signature & date): Spark NEL Engineer - HP
label | 55b6d562-d991-516a-8312-c17d294c0907 |  | note | Inspection/Verification (Name, signature & date): Nominated Authority - HP
label | 8192ff32-d854-5021-8b46-c35922b05c4d |  | note | Inspection/Verification (Name, signature & date): IREA - WP
label | d64fad71-aa38-508f-94cb-3063b265d297 |  | note | Records/Documents -
text | 78db408b-5c0e-5a56-b5e6-54e77f1e8ea4 |  | textbox | • HP Release InEight Ref #
label | 290bddf9-013c-5620-a748-0f59abedfa25 |  | note | • CCTV Footage and Report
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.23 - Repairs to Damaged Pipes
label | a8ea7ca4-0bba-501f-b768-4161a6a7ee69 |  | note | Resp. Person - SE
label | c25459a7-f19b-519d-a7b0-47613e1614e9 |  | note | Specification Reference - VR 701.31 PSDR Part B Section 5.5
label | 20937c5f-49bd-5bf4-acf5-6bafb0bace00 |  | note | Acceptance Criteria - Any steel reinforced concrete pipes that have cracks wider than 0.2 mm or are damaged prior to laying and backfilling shall be rejected. Any Defects identified by the visual inspection of drainage pipes must be rectified before pavement construction commences.
label | 63324fb8-5742-54f9-8252-798f8117a39d |  | note | ○ Where inspections after backfilling identify any of the following defects they shall be notified as a non-conformance:
label | e0cc8eae-bea6-5e9c-98e3-5de02e357f59 |  | note | • cracks wider than 0.5 mm
label | 23f2977b-2b4b-555a-9b2e-7cb9fec9312f |  | note | • spalling of concrete
label | 34a79e13-c94a-5c4e-9cfa-a7a1db293138 |  | note | • exposed reinforcement
label | d1462f66-3d89-5ce1-92d8-ccba284c6417 |  | note | • joints that are not fully engaged.
label | f8c77900-c192-5692-b794-9e5675d6c971 |  | note | ○ The Contractor shall submit details of proposed rectification treatments including manufacturer’s product specifications and warranties, the area and thickness of repair treatment, detailed repair procedures, and inspection and test plans.
label | 4d027c54-044e-58e4-81b5-bf9f8ee64878 |  | note | ○ No repairs shall be undertaken without the Superintendent’s approval of the repair materials and procedures.
label | 6e681d32-11fc-5d22-bc9d-60591e8afedb |  | note | Test Method - V
label | 6835df6f-7bab-5be3-a827-be274143bc38 |  | note | Test Freq. - X1
label | fb31b451-f3d6-5c0b-8b6e-638df8b20f0a |  | note | Inspection/Verification (Name, signature & date): Sub-Contractor - HP
label | 730af45c-70c9-55ef-9327-27471c57544e |  | note | Inspection/Verification (Name, signature & date): Spark NEL Engineer - HP
label | ffe311dc-ea05-55dc-94bf-6bf88c31f413 |  | note | Inspection/Verification (Name, signature & date): Nominated Authority - HP
label | 18cf7841-4c4c-566b-9435-5317be1d5ea0 |  | note | Inspection/Verification (Name, signature & date): IREA - WP
label | c6d15734-93eb-5f07-8cdf-60f4e2525ebc |  | note | Records/Documents -
text | fb5fca97-5470-5600-84ce-d7b0059232f9 |  | textbox | • HP Release InEight Ref #
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | 3.0 Post Operations (Include Inspection and Testing)
checkpoint-status |  |  | checkpoint | 3.1 - Survey As-Builts
label | 6640aa16-ef26-53e5-aef0-9cb2ff2578ac |  | note | Resp. Person - PE
label | 789c62a6-7dcc-5a29-91ee-6a7a4ccba90a |  | note | Specification Reference - IFC Drawings, Design Management Plan NEL-CNT-SDC-2990-PDM-MPL-0001 Section 5.4
label | 1db39d49-5a81-5b7e-a317-1bca499d0756 |  | note | Acceptance Criteria - Survey pickup of finished level
label | bce065f4-056e-5056-9a7a-b793f187e46d |  | note | • Ensure As-Built survey is compared within the required tolerance to Design specification.
label | e1becacb-455a-5b02-82fa-65c0369876e9 |  | note | • Minimum depth of piling pad to be confirmed by as-built
label | 82259633-1c41-5028-8c94-04683e879609 |  | note | • Ensure all locations and work area highlighted as per Construction Lot in Work Lot Map
label | 23ab7091-97ff-58b3-a152-bd9eff6dbaef |  | note | Test Method - V
label | 45cc544c-b127-5535-9f16-21c35653c9f2 |  | note | Test Freq. - PL
label | 42f533a3-b31e-5bfe-8d0e-d59868053ab3 |  | note | Inspection/Verification (Name, signature & date): Sub-Contractor - WP
label | 19c6c623-8d60-5494-b070-d77f55a2cf87 |  | note | Inspection/Verification (Name, signature & date): Spark NEL Engineer - WP
label | aeb6d056-4d85-5a48-90d8-3490484ca635 |  | note | Inspection/Verification (Name, signature & date): Nominated Authority - NR
label | c88bfe92-2f2d-5f5e-86ac-0f51c5ac0cfc |  | note | Inspection/Verification (Name, signature & date): IREA - NR
label | 5c762369-5bab-5424-9b65-c81d7c7b9863 |  | note | Records/Documents -
text | 44fb783a-4c00-5c72-bafa-97024f7cc1f1 |  | textbox | • As-Built Survey Report InEight Reference #:
label | c9d8b042-b450-5449-be75-4e14737d94b2 |  | note | • Work Lot Map
checkpoint-status |  |  | checkpoint | 3.2 - Redline Drawings
label | d61407c3-c428-5389-ab5b-1f069c870106 |  | note | Resp. Person - PE
label | 754d6b55-d6a2-551f-9db3-2eeb74115714 |  | note | Specification Reference - Design Management Plan NEL-CNT-SDC-2990-PDM-MPL-0001 Section 5.4
label | 088367bb-ac84-5341-a380-c06b1a6cb9e0 |  | note | Acceptance Criteria - Redline Drawings submitted to Project for creation of As-Built Drawings.
label | 82c1d78d-1423-519c-9293-7dedfec03baf |  | note | Test Method - V
label | 37ff4550-433c-5f8a-b35d-1efd0c551577 |  | note | Test Freq. - PL
label | a7e12e41-04e8-55e9-94ae-51a0cd968c01 |  | note | Inspection/Verification (Name, signature & date): Sub-Contractor - HP
label | 3847561a-7652-50c3-8dcb-0304982163e4 |  | note | Inspection/Verification (Name, signature & date): Spark NEL Engineer - HP
label | 2753a4db-d612-5e1c-818e-27f73d4063d9 |  | note | Inspection/Verification (Name, signature & date): Nominated Authority - NR
label | 56d95504-8959-5055-94cb-75c910ad47d2 |  | note | Inspection/Verification (Name, signature & date): IREA - NR
label | dd75335f-433a-5ca1-bbef-123481e11a34 |  | note | Records/Documents - Red-Line Marked Up IFC Drawing(s)
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.3 - Operations / Service & Maintenance Manuals
label | 572b4919-8784-5c34-9f6a-27d93eae784d |  | note | Resp. Person - PE
label | bd3413a4-23cf-58cb-9bd8-07590c3bb66c |  | note | Specification Reference - Completions Management Plan
label | f8db37db-cd0b-5e97-af61-bcb787fbe84a |  | note | Acceptance Criteria - Ensure all Operation and Maintenance Manuals are provided prior asset handover. Ensure all Warranty, Brochures, Product Data Sheets, Certificates and / or any relevant documents are provided prior asset handover.
label | 0372261e-571b-5683-b006-567351669981 |  | note | Test Method - R
label | fc897ba2-71aa-5f96-bb2c-c52e9e6e6071 |  | note | Test Freq. - PL
label | ad0f1f46-5177-587a-b6fd-f1dc5b5546a9 |  | note | Inspection/Verification (Name, signature & date): Sub-Contractor - HP
label | fc1375ce-2eca-5268-94dd-827c85596d2f |  | note | Inspection/Verification (Name, signature & date): Spark NEL Engineer - HP
label | 43c202a4-8332-517e-9c5d-59267b0b9464 |  | note | Inspection/Verification (Name, signature & date): Nominated Authority - NR
label | e2169e45-e355-5251-b42f-ed005c09e716 |  | note | Inspection/Verification (Name, signature & date): IREA - NR
label | f2706941-0318-5052-9c88-93a4d42911ff |  | note | Records/Documents - Completion Document O&M Manual
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.4 - Verification and Lot Records complete
label | 346ac3e0-c36f-5e47-bb84-89b9959b0615 |  | note | Resp. Person - PE
label | 53486509-8160-562e-814a-c48e2681405a |  | note | Specification Reference - CQMP Section 8.3
label | 2e41ba0c-9685-58ef-8f13-696f0170b757 |  | note | Acceptance Criteria - Progressive monitoring and signoff of Checklists occurs, and test records are collected. Ensure completed work checklists, inspection and test results and Subcontractor conformance records are progressively and permanently saved and stored as soon as possible after they are received. Completed construction lot records are transferred to the projet Quality Team for final record verification prior to being closed.
label | 261d3a2b-e5b3-5c0b-b86b-e6c7f83f45aa |  | note | Test Method - V
label | 96f925e1-1f1e-5314-b40f-dfb2210d8ba2 |  | note | Test Freq. - PL
label | 0696acbc-2d24-54b0-b9ec-2948b1b59cee |  | note | Inspection/Verification (Name, signature & date): Sub-Contractor - HP
label | e69aa1bb-ba0f-5dc7-99af-b29098c08a30 |  | note | Inspection/Verification (Name, signature & date): Spark NEL Engineer - HP
label | 4ec37d81-c21b-5210-ace2-827aca3eef47 |  | note | Inspection/Verification (Name, signature & date): Nominated Authority - NR
label | e57b03ec-f8ad-5fb7-8871-a17baa55c9cc |  | note | Inspection/Verification (Name, signature & date): IREA - NR
label | 862f01e7-31ed-5887-8aa5-794e3214a5b9 |  | note | Records/Documents - This ITP Lot Record
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.5 - NCR Close out (if applicable)
label | d30fefd7-4c00-58ff-bae8-12b2f7ae78ee |  | note | Resp. Person - PE/QSR
label | 5b32ead1-b72d-52ad-897e-d123e8f56634 |  | note | Specification Reference - CQMP Section 8.3
label | b397f045-95f1-5bb7-abd5-69069c720475 |  | note | Acceptance Criteria - All NCR's presented for closure
label | 029548ed-0898-5594-a2c0-8ba5181ab1f6 |  | note | Test Method - R
label | 1cb4ea1f-fcca-55e8-831b-83deef3a1a57 |  | note | Test Freq. - PL
label | 1c189be8-4619-584d-a0cd-a0ca97c00e4c |  | note | Inspection/Verification (Name, signature & date): Sub-Contractor - HP
label | 5e45b103-ceb7-53d1-9c7a-6e20f781b60c |  | note | Inspection/Verification (Name, signature & date): Spark NEL Engineer - HP
label | dc06873d-bd9a-57cb-9250-129e8693d924 |  | note | Inspection/Verification (Name, signature & date): Nominated Authority - HP
label | a44d380f-4ec5-55ff-8149-8d959463c468 |  | note | Inspection/Verification (Name, signature & date): IREA - WP
label | 64db5c7d-b0bf-501a-81d8-2debe1dc00a0 |  | note | Records/Documents -
text | a51a6f3d-624d-5fad-a7c8-497d755a31aa |  | textbox | • HP Release InEight Reference #:
text | 92d3f7db-6e07-58aa-b811-98d12003e551 |  | textbox | • NCR InEight Reference #:
label | 874fe129-16fd-5056-8066-65ec215d29c4 |  | note | • NCR Module
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | 4.0 Quality
checkpoint-status |  |  | checkpoint | 4.1 - Identification and control of non-confirming products or services (if applicable)
label | 6d501160-8726-5f57-a839-82d7300e96d7 |  | note | Resp. Person - QSR
label | 2106a3c6-4bd3-531b-bbff-680afbc5e7f7 |  | note | Specification Reference - CQMP Section 8.3
label | e942e451-5f61-57eb-9d7b-465a6feea804 |  | note | Acceptance Criteria - Review and confirm closure of NCR's and associated RFI's prior to closing of construction lot
label | 7c8b598b-8af5-578b-9c2e-905b016c336a |  | note | Test Method - R
label | 7292c013-8732-5020-947f-71e79c8ce755 |  | note | Test Freq. - PL
label | 5b6d13fd-a687-5a2e-ba8c-ecfe05063c1e |  | note | Inspection/Verification (Name, signature & date): Spark NEL Engineer - HP
label | 640f0ce6-25b2-57f3-8251-d152e478875f |  | note | Records/Documents - NCR closed with related documentation
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 4.2 - Check all quality records for lot closure
label | c248c5ea-bbde-5e63-919f-5d5373d38f3d |  | note | Resp. Person - QSR
label | 1a05904d-97c7-50a1-9c54-3ff137c64f3d |  | note | Specification Reference - CQMP Section 8.3
label | 3e626683-d49e-5b47-9fc5-5937bd21889c |  | note | Acceptance Criteria - All applicable quality records are complete
label | a64dc128-7356-5c09-838e-c90561a02196 |  | note | Test Method - R
label | a6e95635-eaa2-5d43-90d3-8597a094dcaa |  | note | Test Freq. - PL
label | ada31e79-7c05-5c64-933a-b633ec41f468 |  | note | Inspection/Verification (Name, signature & date): Spark NEL Engineer - HP
label | 37867caa-1e4f-5ad4-a94b-848abd0947c6 |  | note | Records/Documents - Compiled documents (all data reports and records)
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT