## 1.0 Preconstruction
Inspection and Test Plan Te Ara o Te Ata Excavation and Support ITP # MMA-QA-ITP-Z04-TUN-GE001
Rev Number | This ITP has been prepared by |  |  | Reviewed by Quality Manager |  |  | Reviewed by DSR/CPS |  |  | Approved by Construction Manager
| Name | Signature | Date | Name | Signature | Date | Name | Signature | Date | Name |  | Signature |  | Date
Rev 0 | Teringa Horton, Tarik Jony and Sam Tang | See Approvals Tab | 2024-05-09 | Whineray Arries | See Approvals Tab | 29/11/2024 | Katerina Howard | See Approvals Tab | 2024-05-12 | Hardus Pieters |  | See Approvals Tab |  | 2024-12-06
Rev 1 | Teringa Horton, Jamie Morris, Tarik Jony and Sam Tang | See Approvals Tab | 2025-06-25 | Manoj Jayasundara and Whineray Arries | See Approvals Tab | 2025-06-27 | Roque Alea, Sam Burgess and Ben Westgate | See Approvals Tab | 2025-07-01 | Hardus Pieters |  | See Approvals Tab |  | 2025-07-01
Rev 2
ITP NO: CONQA # |  |  | Project: Te Ara o Te Ata
Verification Method: Hold [H] – work will not proceed past Hold Point until released by organisation imposing hold; Inspection [I] – formal inspection activity to be undertaken and recorded; ensure correct verifying records are in place; Witness [W] – an inspection that may be witnessed by organisation imposing hold; allow reasonable notification period; Review [R] – review of reports, records or other evidence of compliance. Surveillance [S] – An Activity that is subject to ongoing monitoring. | [7 empty] | Responsibilities MTME = MTM Alliance Construction CPS = Construction Phase Services SE/PE = Site Engineer/Project Engineer SUP = Supervisor QM = Quality Manager
Activity/Specification: Excavation & Shotcrete
Item | Titles | Description |  | Specifications and Standards |  | Acceptance criteria and testing |  |  | Verification Activity by |  |  |  | Verifying Records
[6 empty] | Method/ Description | Test frequency | Conformance Criteria | Constructor | CPS | Lab | IOM
1. Pre construction
1.1 | CWP for tunnel excavation & support work | Approved CWP |  | Technical Specification - C0651 - Tunnel Shotcrete Technical Specification - C0652 - Tunnel Rock Reinforcement Clause 3.2 |  | Submission | Once prior to works commencing | Approval CWP has been transmitted via InEight | H | H |  |  | Approved CWP
1.2 | ITP for tunnel excavation & support work | Approved ITP |  | Technical Specification - C0651 - Tunnel Shotcrete Technical Specification - C0652 - Tunnel Rock Reinforcement Clause 3.2 |  | Submission | Once prior to works commencing | Approval ITP has been transmitted via InEight | H | H |  |  | Approved ITP
1.3 | IFC Drawings | Approved IFC Drawings |  | N/A |  | Submission | Once prior to works commencing | Ensure all drawings are approved and transmitted Via InEight with IFC status | H | H |  |  | IFC Drawings transmitted into InEight with IFC status
1.4 | IFC Specification | Approved IFC Specification |  | N/A |  | Submission | Once prior to works commencing | Ensure all relevant Specifications have been approved and transmitted Via InEight with IFC status | H | H |  |  | IFC Specification transmitted into InEight with IFC status
1.5 | Permit to tunnel/excavate template | No work shall commence until a valid Permit to Tunnel has been signed off for the current section of excavation |  | NZ Legislation |  | Submission | Prior to the commencement of the excavation work | Valid permit to tunnel | H | H |  |  | Permit to tunnel signed off by all nominated personnel
1.6 | The groundwater control system Methodology | The Constructor shall propose a method for a preconstruction trial of the groundwater control system and submit it to the Designer’s Representative for review. |  | Technical Specification - C0653 - Tunnel Groundwater Control Systems Clause 6 |  | Submission | Prior to the commencement of the excavation work | Designer’s Representative Approval | H | H |  |  | Groundwater control system methodology
1.7 | Post-installation Groundwater Control Methodology | Where the inflow into the tunnel exceeds 3L/m of length/day averaged over a 100m length of tunnel, appropriate post-installed drainage measures shall be proposed by the Constructor and approved by the Designer’s representative. |  | Technical Specification - C0653 - Tunnel Groundwater Control Systems Clause 6 |  | Submission | Prior to the commencement of the remedial work | Designer’s Representative Approval | H | H |  |  | Post-installation groundwater control system methodology
1.8 | The groundwater control system Trial | A preconstruction trial shall be carried out by the Constructor to demonstrate the effectiveness of the connections of strip drains from the top heading to the bench, unless using approved manufacturer's recommended connections installed to the manufacturer's specification. |  | Technical Specification - C0653 - Tunnel Groundwater Control Systems Clause 6 |  | Trial | Prior to the commencement of the excavation work | Designer’s Representative Witness | H | W |  |  | Groundwater control system Trial Results
1.9 | Cement Grout Encapsulation Test | A pre-construction trial shall be carried out by the constructure to demonstrate that the proposed grout used is able to fully encapsulate the bolt using the proposed installation method |  | Technical Specification - C0652 - Tunnel Rock Reinforcement Clause 6.2 |  | Trial | Prior to the commencement of the excavation work | Compliance with Technical Specification - C0652 - Tunnel Rock Reinforcement Clause 6.2. Designer’s Representative Approval | H | W |  |  | The rock reinforcement Trial Results
1.10 | Investigation Tests | The Constructor shall conduct a Investigation test (pre-production) on sacrificial rock reinforcements and tested progressively to failure. Investigation load test rock reinforcements are to be installed at locations, agreed with the Designer’s Representative. The Constructor shall notify the Designer’s Representative with a minimum of 48 hour notice. |  | Technical Specification - C0652 - Tunnel Rock Reinforcement Clause 6.1 |  | Trial | Prior to the commencement with A minimum of six investigation tests shall be carried out for each type of rock, grout mix, and rock bolt or dowel orientation, or as agreed upon with the Designer’s Representative. | Compliance with Technical Specification - C0652 - Tunnel Rock Reinforcement Clause 6.1. Designer’s Representative Approval | H | W |  |  | Investigation test results
1.11 | End Anchorage Tests | The Constructor shall conduct end anchorage test with a minimum of six rock bolts per proposed rock reinforcement system shall be tested in each ground type. For acceptance of end anchorage, all individual bolts shall achieve the pre-tension load shown on the Drawings. |  | Technical Specification - C0652 - Tunnel Rock Reinforcement Clause 6.3 |  | Trial | Prior to the commencement with A minimum of six tests shall be carried out in each ground type. | Compliance with Technical Specification - C0652 - Tunnel Rock Reinforcement Clause 6.3. Designer’s Representative Approval | H | W |  |  | End Anchorage test results
1.12 | Approval of shotcrete equipment | Details of all equipment to be approved by the designers representative |  | Technical Specification - C0651 - Tunnel Shotcrete Clause 3.2 |  | Review | Prior to the commencement of the excavation work | Designer’s Representative Approval | H | H |  |  | Equipment Technical Data Sheets
1.13 | Probing ahead trial | A trial shall be carried out in advance of tunnelling activities to identify optimum drill bit, drill diameter and flushing and percussion rates |  | Technical Specification - C0650 - Tunnel Sequential Excavation Section 5.5.g |  | Trial | Prior to start of tunnelling | Designer’s Representative Approval | H | H |  |  | Probe hole trial result

## 2. Material Compliance
Inspection and Test Plan Te Ara o Te Ata Excavation and Support ITP # MMA-QA-ITP-Z04-TUN-GE001
Rev Number | This ITP has been prepared by |  |  | Reviewed by Quality Manager |  |  | Reviewed by DSR/CPS |  |  | Approved by Construction Manager
| Name | Signature | Date | Name | Signature | Date | Name | Signature | Date | Name |  | Signature |  | Date
Rev 0 | Teringa Horton, Tarik Jony and Sam Tang | See Approvals Tab | 2024-05-09 | Whineray Arries | See Approvals Tab | 29/11/2024 | Katerina Howard | See Approvals Tab | 2024-05-12 | Hardus Pieters |  | See Approvals Tab |  | 2024-12-06
Rev 1 | Teringa Horton, Jamie Morris, Tarik Jony and Sam Tang | See Approvals Tab | 2025-06-25 | Manoj Jayasundara and Whineray Arries | See Approvals Tab | 2025-06-27 | Roque Alea, Sam Burgess and Ben Westgate | See Approvals Tab | 2025-07-01 | Hardus Pieters |  | See Approvals Tab |  | 2025-07-01
Rev 2
ITP NO: CONQA # |  |  | Project: Te Ara o Te Ata
Verification Method: Hold [H] – work will not proceed past Hold Point until released by organisation imposing hold; Inspection [I] – formal inspection activity to be undertaken and recorded; ensure correct verifying records are in place; Witness [W] – an inspection that may be witnessed by organisation imposing hold; allow reasonable notification period; Review [R] – review of reports, records or other evidence of compliance. Surveillance [S] – An Activity that is subject to ongoing monitoring. | [7 empty] | Responsibilities MTME = MTM Alliance Construction CPS = Construction Phase Services SE/PE = Site Engineer/Project Engineer SUP = Supervisor QM = Quality Manager
Activity/Specification: Excavation & Shotcrete
Item | Titles | Description |  | Specifications and Standards |  | Acceptance criteria and testing |  |  | Verification Activity by |  |  |  | Verifying Records
[6 empty] | Method/ Description | Test frequency | Conformance Criteria | Constructor | CPS | Lab | IOM
2. Material Compliance and approvals
2.1. Shotcrete
2.1.1. | Shotcrete base mix design | Compliance with Technical Specification - C0651 - Tunnel Shotcrete Clause 4 |  | Technical Specification - C0651 - Tunnel Shotcrete Clause 4 |  | Material Review | Prior to the commencement of the excavation work | as per Technical Specification - C0651 - Tunnel Shotcrete Clause 4 | H | H |  |  | Material Approval Record
2.1.2. | Shotcrete Accelerator | Type and dosage of shotcrete accelerator shall conform to the requirements of the Specification |  | Technical Specification - C0651 - Tunnel Shotcrete Clause 4.7.1 |  | Material Review | Prior to the commencement of the excavation work | Material Approval Record | H | H |  |  | Material Approval Record
2.1.3. | Nozzelman Certification | Nozzelman shall hold a verification of competence (VOC) issued by the constructor |  | Technical Specification - C0651 - Tunnel Shotcrete Clause 5.2 |  | Document Review | Prior to trial | Ensure only personnel hodling VOC are operating the shotcrete robot on site. | H | R |  |  | Nozzelman Certificate/ VOC
2.1.4. | Cement | Testing of cement properties in accordance with NZS 3122 and 3104 shall be carried out at least monthly |  | NZS3122, NZS 104 Technical Specification - C0651 - Tunnel Shotcrete Clause 4.2 |  | Document Review | Monthly | Comply with NZS3122 and NZS3104 | R | R |  |  | Cement Certificates
2.1.5. | Silica Fume | Compliance with Technical Specification - C0651 - Tunnel Shotcrete Clause 4.4 |  | Technical Specification - C0651 - Tunnel Shotcrete Clause 4.4 |  | Document Review | Monthly | Comply with NZS3122 and the tunnel shotcrete specifications C0651 | R | R |  |  | Silica Testing
2.2. Reinforcing Mesh
2.2.1. | Reinforcing Mesh | SE92 GR 500E mesh |  | AS/NZS 4671 |  | Material Review | Prior to the commencement of the excavation work | Material Approval Record | H | H |  |  | Material Approval Record
2.3. Rockbolts/Dowels Bar
2.3.1. | Tunnel rockbolts and plates | rockbolts material and corrosion protection |  | AS/NZS 4671, AS/NZS 3678, AS/NZ 4680 Technical Specification - C0652 - Tunnel Rock Reinforcement Clause 4.1 and 4.2 |  | Material Review | Prior to the commencement of the excavation work | Grade 500N, galvanised HDG to AS/NZS 4680 Material Approval Record including mill certificate | H | H |  |  | Material Approval Record
2.3.2. | Face Dowels | glass fibre reinforced face dowels material |  | ASTM D3916 Technical Specification - C0652 - Tunnel Rock Reinforcement Clause 4.2.2 |  | Material Review | Prior to the commencement of the excavation work | Material Approval Record | H | H |  |  | Material Approval Record
2.3.3. | Delivery acceptance | Inspect fabricated rock bolts and rock dowels prior to installation |  | Technical Specification - C0652 - Tunnel Rock Reinforcement Clause 3.2 |  | Visual Inspection | upon delivery | N/A | H | W |  |  | Delivery Docket/Mil Test cert
2.4. Spile bars
2.4.1. | Spile bars | spile bar material |  | AS/NZS 4671 Technical Specification - C0652 - Tunnel Rock Reinforcement Clause 4.2.3 AS 1391 |  | Material Review | Prior to the commencement of the excavation work | Material Approval Record | H | H |  |  | Material Approval Record
2.4.2. | Delivery acceptance | Visual confirmation of delivered items |  | N/A |  | Visual Inspection | Upon delivery | N/A | H | R |  |  | Delivery Docket/Mil Test cert
2.5. Cement grout for rock bolts, dowels, spiles
2.5.1. | cement grout | grout material and properties |  | Technical Specification - C0652 - Tunnel Rock Reinforcement Clause 4.3.1 NZS3122 |  | Material Review | Prior to the commencement of the excavation work | Material Approval Record | H | H |  |  | Material Approval Record
2.5.2. | Delivery acceptance | Visual confirmation of delivered items |  | N/A |  | Visual Inspection | Upon delivery |  | H | R |  |  | Delivery Docket
2.6. Resin
2.6.1. | resin grout | grout material and properties |  | Technical Specification - C0652 - Tunnel Rock Reinforcement Clause 4.3.2 |  | Material Review | Prior to the commencement of the excavation work | Material Approval Record | H | H |  |  | Material Approval Record
2.6.2. | Delivery acceptance | Visual confirmation of delivered items |  | N/A |  | Visual Inspection | Upon delivery | As per accepted MAR | H | W |  |  | Delivery Docket
2.7. Monitoring Instruments
2.7.1. | Monitoring instrumets | Compliance with Technical Specification C0660 - Tunnel Convergence Monitoring |  | Technical Specification C0660 - Tunnel Convergence Monitoring |  | Review | Prior to installation | Designer’s Representative Approval | H | H |  |  | Material Approval Record
2.8. Ground water control
2.8.1. | Strip Drain Materials | Compliance with Technical Specification C0653 - Tunnel Groundwater Control Systems MMA-DES-TUN-E1-SPC-54409 |  | Technical Specification C0653 - Tunnel Groundwater Control Systems |  | Review | Prior to installation | Designer’s Representative Approval | H | H |  |  | Material Approval Record
2.8.2. | Bored Drain Materials | Compliance with drawing MMA-DES-TUN-E1-DRG-8141 |  | MMA-DES-TUN-E1-DRG-8141 |  | Review | Prior to installation | Designer’s Representative Approval | H | H |  |  | Material Approval Record

## 3. Shotcrete Testing
Inspection and Test Plan Te Ara o Te Ata Excavation and Support ITP # MMA-QA-ITP-Z04-TUN-GE001
Rev Number | This ITP has been prepared by |  |  | Reviewed by Quality Manager |  |  | Reviewed by DSR/CPS |  |  | Approved by Construction Manager
| Name | Signature | Date | Name | Signature | Date | Name | Signature | Date | Name |  | Signature |  | Date
Rev 0 | Teringa Horton, Tarik Jony and Sam Tang | See Approvals Tab | 2024-05-09 | Whineray Arries | See Approvals Tab | 29/11/2024 | Katerina Howard | See Approvals Tab | 2024-05-12 | Hardus Pieters |  | See Approvals Tab |  | 2024-12-06
Rev 1 | Teringa Horton, Jamie Morris, Tarik Jony and Sam Tang | See Approvals Tab | 2025-06-25 | Manoj Jayasundara and Whineray Arries | See Approvals Tab | 2025-06-27 | Roque Alea, Sam Burgess and Ben Westgate | See Approvals Tab | 2025-07-01 | Hardus Pieters |  | See Approvals Tab |  | 2025-07-01
Rev 2
ITP NO: CONQA # |  |  | Project: Te Ara o Te Ata
Verification Method: Hold [H] – work will not proceed past Hold Point until released by organisation imposing hold; Inspection [I] – formal inspection activity to be undertaken and recorded; ensure correct verifying records are in place; Witness [W] – an inspection that may be witnessed by organisation imposing hold; allow reasonable notification period; Review [R] – review of reports, records or other evidence of compliance. Surveillance [S] – An Activity that is subject to ongoing monitoring. | [7 empty] | Responsibilities MTME = MTM Alliance Construction CPS = Construction Phase Services SE/PE = Site Engineer/Project Engineer SUP = Supervisor QM = Quality Manager
Activity/Specification: Excavation & Shotcrete
Item | Titles | Description |  | Specifications and Standards |  | Acceptance criteria and testing |  |  | Verification Activity by |  |  |  | Verifying Records
[6 empty] | Method/ Description | Test frequency | Conformance Criteria | Constructor | CPS | Lab | IOM
3.0 Shotcrete Testing
3.1 | Personnel Entry | Test prior to each personnel entry and/or face advance. Test results must be verified once a month during construction. |  | BS EN 14488-2 Technical Specification - C0651 - Tunnel Shotcrete Table 6.4 |  | Penetrometer test | Initially test prior to each personnel entry after spraying primary shotcrete. Once established, this curve must be verified once a month during construction. | ST1/1A/1B/2/3/3A - minimum of 50mm thick shotcrete layer that has achieved minimum compressive strength of 1mpa combined with remotely installed pattern rockbolts and spot bolts as required or as directed by the designer's representative. rockbolt grout to have achieved a compressive strength of at least 3mpa. ST3B - minimum 100mm thick shotcrete layer that has achieved minimum compressive strength of 1mpa | H | R |  |  | Beam End Test Results
3.2 | Beam End Test (early age compressive strength) | Safe shotcrete strength before next advancement to max. advance length |  | Technical Specification - C0651 - Tunnel Shotcrete Table 6.1 and 6.4 ASTM C116 |  | field test | Initially test prior to each personnel entry after spraying primary shotcrete. Once established, this curve must be verified once a month during construction. | From the Specification the following applies: Min. 1.00 MPa at 3 Hours Min. 5.00 MPa at 6 Hours Min. 7.00 MPa at 12 Hours Min. 12.00 MPa at 24-36 Hours | H | W |  |  | Beam End Test Results
3.3 | compressive strength (cast sample) | To prove compressive strength compliance requirement |  | NZS3112 Technical Specification - C0651 - Tunnel Shotcrete Table 6.1 and 6.4 |  | certified lab test | 1 test (I test shall include 4 cored specimen, 3 tested and 1 spare) for the first 50m3 of shotcrete and 1 test for every 250m3 of shotcrete thereafter | Min. 35 MPa at 28 days | W | R |  |  | IANZ lab test report
3.4 | compressive strength (cored sample) | To prove compressive strength compliance requirement |  | NZS3112 Technical Specification - C0651 - Tunnel Shotcrete Table 6.4 |  | certified lab test | 1 test for every 50m3 of sprayed shotcrete | Min. 20 MPa at 7 days Min. 35 MPa at 28 days Min. 35 MPa at 90 days | W | R |  |  | IANZ lab test report
3.3 | Residual Flexural Tensile Strength | To prove compliance with flexural strength requirements |  | BS EN 14651: 2005 + A1: 2007 Technical Specification - C0651 - Tunnel Shotcrete Table 6.4 and 6.1 |  | certified lab test | 1 test for the first 50m3 of shotcrete and 1 test for every 100m3 of shotcrete thereafter | Min. FR,1 of 1.25MPa and FR,4 at 1MPa | W | R |  |  | IANZ lab test report
3.4 | Drying Shrinkage Testing | To prove compliance with shrinkage requirements |  | AS1012.13 Technical Specification - C0651 - Tunnel Shotcrete Table 6.4 and 6.1 |  | certified lab test | 1 test for the first 50m3 of shotcrete and 1 test for every 250m3 of shotcrete thereafter | Max 850 micro strain | W | R |  |  | IANZ lab test report
3.5 | Permeability testing | to prove compliance with permeability requirements |  | BS EN 12390-8 Technical Specification - C0651 - Tunnel Shotcrete Table 6.4. and 6.1 |  | certified lab test | 3 tests for the first 50m3 of shotcrete then 1 test every 1 month thereafter | Maximum allowable penetration 25mm | W | R |  |  | IANZ lab test report
3.6 | Steel fibre content | To prove compliance with fibre content test requirement |  | BS EN 14488-7 (fresh concrete) Technical Specification - C0651 - Tunnel Shotcrete Section 4.8 |  | certified lab test | 1 test for the first 50m3 of shotcrete and 1 test for every 100m3 of shotcrete thereafter | Minimum 35kg/m3 | H | R |  |  | IANZ lab test report
3.5 | Relative density | To prove compliance with the relative density requirement |  | NZS 3112.1 Technical Specification - C0651 - Tunnel Shotcrete Table 6.4 and 6.1 |  | certified lab test | 1 test for the first 50m3 of shotcrete and 1 test for every 250m3 of shotcrete thereafter | Minimum 98% of the density measured from base mix | H | R |  |  | IANZ lab test report

## 4. Construction (Cut sheet)
Inspection and Test Plan Te Ara o Te Ata Excavation and Support ITP # MMA-QA-ITP-Z04-TUN-GE001
Rev Number | This ITP has been prepared by |  |  | Reviewed by Quality Manager |  |  | Reviewed by DSR/CPS |  |  | Approved by Construction Manager
| Name | Signature | Date | Name | Signature | Date | Name | Signature | Date | Name |  | Signature |  | Date
Rev 0 | Teringa Horton, Tarik Jony and Sam Tang | See Approvals Tab | 2024-05-09 | Whineray Arries | See Approvals Tab | 29/11/2024 | Katerina Howard | See Approvals Tab | 2024-05-12 | Hardus Pieters |  | See Approvals Tab |  | 2024-12-06
Rev 1 | Teringa Horton, Jamie Morris, Tarik Jony and Sam Tang | See Approvals Tab | 2025-06-25 | Manoj Jayasundara and Whineray Arries | See Approvals Tab | 2025-06-27 | Roque Alea, Sam Burgess and Ben Westgate | See Approvals Tab | 2025-07-01 | Hardus Pieters |  | See Approvals Tab |  | 2025-07-01
Rev 2
ITP NO: CONQA # |  |  | Project: Te Ara o Te Ata
Verification Method: Hold [H] – work will not proceed past Hold Point until released by organisation imposing hold; Inspection [I] – formal inspection activity to be undertaken and recorded; ensure correct verifying records are in place; Witness [W] – an inspection that may be witnessed by organisation imposing hold; allow reasonable notification period; Review [R] – review of reports, records or other evidence of compliance. Surveillance [S] – An Activity that is subject to ongoing monitoring. | [7 empty] | Responsibilities MTME = MTM Alliance Construction CPS = Construction Phase Services SE/PE = Site Engineer/Project Engineer SUP = Supervisor QM = Quality Manager
Activity/Specification: Excavation & Shotcrete
Item | Titles | Description |  | Specifications and Standards |  | Acceptance criteria and testing |  |  | Verification Activity by |  |  |  | Verifying Records
[6 empty] | Method/ Description | Test frequency | Conformance Criteria | Constructor | CPS | Lab | IOM
4.0 Construction
4.1. Excavation
4.1.1 | PTT | PTT shall define the planned excavation limits and support types (RESS) prior to each defined period of excavation in each heading or bench face. Tunnel excavation shall not commence on a shift until PTT has been signed off |  | Technical Specifications C0650 Tunnel Sequential Excavation Section 5.1 |  | PTT form | Every advance or as agreed in DRM | N/A | H | H |  |  | PTT
4.1.2 | Face Mapping | Recommend the required support type based on the Actual Ground Conditions. Determine any corrective measures required to ensure safety and stability of the excavation. Identify if the ground conditions depart from the expected range of conditions for which a support type has been designed and notify the Designer if new design is required. |  | Technical Specifications C0650 Tunnel Sequential Excavation Section 5.1 |  | Geological mapping record | Every advance or as agreed in DRM | N/A | H | H |  |  | Required Excavation and support sheet
4.1.3 | E-line control | Control the E-Line before, during and after excavation is finished |  | Drawing MMMA-DES-TUN-E1-DRG-8119 |  | Surveyor to set out and record as built. VMT system to provide e-line guidance | Every advance | Over excavation tolerance -0/+150mm | H | W |  |  | Strip Drain Check Sheet
4.2. Shotcrete
4.2.1 | Shotcrete Delivery and acceptance | delivery dockets check, slump and temperature check |  | Technical Specification - C0651 - Tunnel Shotcrete Clause 5.4 NZS 3109: 1997 |  | Document Review | Each truck | Slump range 200-240mm temperature range 5-35 celcius Delivery dockets to include the following; Batch number, Batch temperature at time of dispatch and delivery, Mix designation, Date and time of mixing, Quantity delivered, The delivery truck number, Date and time the delivery truck left the batching plant, Amounts of water, admixture, or any other ingredients made after despatch, and time at which such additions are made, Steel fibre type and content, Micro fibre type and content, and, any other relevant information. | H | R |  |  | Shotcrete Installation Record
4.2.3 | Rock and Shotcrete Surface Preparation | Prepare all surfaces to be shotcreted prior to application of shotcrete |  | Technical Specification - C0650 - Tunnel Civil Works Section 5.4 |  | Visual Inspection | Prior to spraying | Surface clean and free of loose material, pre-wet surface immediately prior to spraying. Any residual flowing or seeping water shall be controlled using channels, chases, pipes, or other approved means. Spalled, cracked, loose or contaminated shotcrete removed. | H | W |  |  | Shotcrete Check Sheet
4.2.5 | Shotcrete Thickness As-built | Provide control means to verify the thickness of final shotcrete layer |  | Technical Specification C0650 - Tunnel Sequential Excavation, section 5.7 Drawing MMA-DES-TUN-E1-DRG-8119 Drawing MMA-DES-TUN-E1-DRG-8130 |  | Survey Asbuilt | As-builts shall be taken of EACH layer of shotcrete | Shotcrete thickness shall be sprayed in accordance with drawing MMA-DES-TUN-E1-DRG-8129, 8130, and 3831 and within the tolerances outlined in drawing MMA-DES-TUN-E1-DRG-8119 | H | R |  |  | As-built Report
4.2.7 | Shotcrete Lining intrados As-built | Provide control means to verify the intrados clearance of the shotcrete lining |  | Technical Specification C0650 - Tunnel Sequential Excavation, section 5.7 Drawing MMA-DES-TUN-E1-DRG-8119 Drawing MMA-DES-TUN-E1-DRG-8131 |  | Survey Asbuilt | As-builts shall be taken of EACH layer of shotcrete | Shotcrete thickness shall be sprayed in accordance with drawing MMA-DES-TUN-E1-DRG-8129, 8130, and 3831 and within the tolerances outlined in drawing MMA-DES-TUN-E1-DRG-8120 | H | R |  |  | As-built Report
4.2.9 | Shotcrete Lining C-line As-built | Provide control means to verify the C-line clearance of the shotcrete lining |  | Technical Specification C0650 - Tunnel Sequential Excavation, section 5.7 Drawing MMA-DES-TUN-E1-DRG-8119 Drawing MMA-DES-TUN-E1-DRG-8132 |  | Survey Asbuilt | As-builts shall be taken of EACH layer of shotcrete | Shotcrete thickness shall be sprayed in accordance with drawing MMA-DES-TUN-E1-DRG-8129, 8130, and 3831 and within the tolerances outlined in drawing MMA-DES-TUN-E1-DRG-8121 | H | R |  |  | As-built Report
4.2.11 | Top heading to Bench Inspection | Underside of top heading lining at connection with bench lining to be cleaned by pressure air jet and water and inspected by the designer's representative prior to placement of bench shotcrete. |  | Technical Specification - C0651 - Tunnel Shotcrete Clause 3.2 Table 3.1 |  | Visual Inspection | Every Construction Joint | Hold point released by CPS | H | H |  |  | Shotcrete Check Sheet
4.2.13 | Footing Inspection | The footing invert (top heading and bench) shall be clean and clear of all debris and shotcrete rebound and inspected by designer's representative prior to placement of shotcrete. |  | Drawing MMA-DES-TUN-E1-DRG-8129 |  | Visual Inspection | Prior to each Spray | Hold point released by CPS | H | H |  |  | Shotcrete Check Sheet
4.2.15 | Curing | Curing to be carried out in accordance with the Specification |  | Technical Specification - C0651 - Tunnel Shotcrete Clause 5.5 |  |  | Each Spray |  | H | R |  |  | Shotcrete Check Sheet
4.2.17 | Defects and Repair | The final layer of shotcrete shall be inspected for any defects and repaired accordingly. At the completion of the lining, all core holes in the lining (resulting from testing or inspection) shall be backfilled with non-shrink mortar of an equivalent strength and fire resistance properties unless otherwise specified. The surface of the restored hole shall be similar to the surrounding surface in texture and colour. |  | Technical Specification C0650 - Tunnel Sequential Excavation, section 5.6 |  | Visual Inspection | Every defect on Every advance | Crack <0.5mm ,Crack >0.5mm -Non corformance report | H | W |  |  | Post spray inspection record
4.3. Reinforcing mesh
4.3.1. | Reinforcing mesh for primary lining | To prove position, cover and overlap are achieved |  | Drawing MMMA-DES-TUN-E1-DRG-8011 |  | Visual inspection and survey | Every advance | Longitudinal and transverse overlap of 250mm ( one mesh square plus 50mm) Min. cover 65mm at the extrados and 85mm at the intrados | H | W |  |  | Mesh Check Sheet As-built
4.4. Rockbolts
4.4.1 | Drilling and Installation | Bolts shall be drilled to the depth, diameter, alignment and position specified on the Drawings or instructed by the Designer. To ensure correct installation process for resin injection |  | Technical Specification C0652 - Tunnel Rock Reinforcement, section 5.2, 5.3 |  | Survey | Each bolt | bolts shall be installed perpendicular to the excavation face unless stated otherwise. Where rockbolts are not able to be installed perpendicular, the maximum deviation shall be 18 degrees from perpendicular. Position Tolerence +150,-150mm -The Constructor shall record a drilling log for each drillhole, including the date and time of installation and any difficulties or problems that were encountered. dowels to be clean or any other physical damage at the time of installation -Type of bolts, diameter, length, location, spacing and orientation according to detailed design -Sufficient volume of resin to be used with each rock reinforcement installation in accordance with the approved project specific procedure developed during the trials. daily records of all grouting works to be kept | H | W |  |  | Rock Bolt Installation Record Rock bolt Check Sheet
4.4.2 | Rockbolt As-built | Bolts to be installed in the position specified on the drawings or as instructed by the designer |  | Technical Specification C0652 - Tunnel Rock Reinforcement section 5.3 |  | Review | Each bolt | bolts shall be installed perpendicular to the excavation face unless stated otherwise. Where rockbolts are not able to be installed perpendicular, the maximum deviation shall be 18 degrees from perpendicular. Position Tolerence +150,-150mm | H | R |  |  | Rock Bolt As built Survey
4.4.3 | Pull test | Demonstrate that the installed rock reinforcements can provide at least the design working load capacity. . |  | Technical Specification - C0652 - Tunnel Rock Reinforcement Clause 6.5 |  | Test | 1. The first nine installations of each type of rock bolt and the first nine installations of each type of rock dowel shall be tested in each ground type as it presents in production. At least one test location of each type shall be in the tunnel crown unless otherwise directed by the Designer’s Representative. 2. 5% of the next 100 installations of rock bolts and rock dowels, proportionately throughout the ground types presenting. | The bolt or dowel is deemed acceptable if, during the cycle, the displacement of the bolt or dowel head relative to the measuring datum (after allowing for any temperature changes) does not exceed the criteria for 100% of the working load, as set out in Table 6.4 of the specification. Failure criteria: 2% Maximum Permissible Displacement or failure to maintain specified loads or ongoing creep of the rock bolt or rock dowel | H | W |  |  | Testing records
4.5. Spile installation
4.5.1 | Drilling and Installation | Bolts shall be drilled to the depth, diameter, alignment and position specified on the Drawings or instructed by the Designer. To ensure correct installation process for resin injection |  | Technical Specification C0652 - Tunnel Rock Reinforcement, section 5.2, 5.3 |  | Survey | Each bolt | bolts shall be installed perpendicular to the excavation face unless stated otherwise. -The Constructor shall record a drilling log for each drillhole, including the date and time of installation and any difficulties or problems that were encountered. bolts to be clean or any other physical damage at the time of installation -Type of bolts, diameter, length, location, spacing and orientation according to detailed design | H | W |  |  | Rock Bolt Installation Record Rock bolt Check Sheet
4.5.2 | Spile bar As-built | Bolts to be installed in the position specified on the drawings or as instructed by the designer |  | Technical Specification C0652 - Tunnel Rock Reinforcement section 5.3 |  | Review | Each dowel | Positional tolerance of portal spile bars not to exceed 25mm in any direction -Setout angle shall be as per drawing. Max. angular tolerance not to exceed 1 in 60. | H | W |  |  | Rock Bolt As built Survey
4.5.3 | Grouting mixing | To ensure correct practice and w/c ratio check |  | Technical Specification C0652 - Tunnel Rock Reinforcement section 5.4.1 NZ 3109 |  | Review | Every batch prior to grouting | Target w/c ratio as per MAR | H | W |  |  | Grout Record
4.5.4 | Grout test | Testing specimen to measure UCS |  | Technical Specification C0652 - Tunnel Rock Reinforcement section 6.4 NZ 3112.4:1986 |  | Compressive strength test | Evevery batch prior to grouting (three cubes at 1 day, three cubes at 28 days) | min 20MPa at 1 day min 40MPa at 28 days The average compressive strength determined from any group of cubes shall excess the specified characterisitc strength by: 1MPa at 1 day 3MPa at 28 days | H | W |  |  | IANZ lab test report
4.6. Face dowels
4.6.1 | Drilling and Installation | Bolts shall be drilled to the depth, diameter, alignment and position specified on the Drawings or instructed by the Designer. To ensure correct installation process for resin injection |  | Technical Specification C0652 - Tunnel Rock Reinforcement, section 5.2, 5.3 |  | Survey | Each bolt | bolts shall be installed perpendicular to the excavation face unless stated otherwise. -The Constructor shall record a drilling log for each drillhole, including the date and time of installation and any difficulties or problems that were encountered. bolts to be clean or any other physical damage at the time of installation -Type of bolts, diameter, length, location, spacing and orientation according to detailed design | H | W |  |  | Rock Bolt Installation Record Rock bolt Check Sheet
4.6.2 | Rockbolt As-built | Bolts to be installed in the position specified on the drawings or as instructed by the designer |  | Technical Specification C0652 - Tunnel Rock Reinforcement section 5.3 |  | Review | Each dowel | Dowels installed as per the drawings or as per designers instruction | H | W |  |  | Rock Bolt As built Survey
4.6.3 | Grouting mixing | To ensure correct practice and w/c ratio check |  | Technical Specification C0652 - Tunnel Rock Reinforcement section 5.4.1 NZ 3109 |  | Review | Every batch prior to grouting | Target w/c ratio as per MAR | H | W |  |  | Grout Record
4.6.4 | Grout test | Testing specimen to measure UCS |  | Technical Specification C0652 - Tunnel Rock Reinforcement section 6.4 NZ 3112.4:1986 |  | Compressive strength test | Evevery batch prior to grouting (three cubes at 1 day, three cubes at 28 days) | min 20MPa at 1 day min 40MPa at 28 days The average compressive strength determined from any group of cubes shall excess the specified characterisitc strength by: 1MPa at 1 day 3MPa at 28 days | H | W |  |  | IANZ lab test report
4.7. Probe holes
4.7.1. | Drilling probe holes | Record information during drilling Check the water inflow during and after drilling |  | Technical specification C0650 - Tunnel Sequential Excavation, section 5.5 - updated with RFI 225 |  | Geological monitoring | Maintain minimum one probe at 20 m ahead of the face at all times | Hole to be drilled with a 51mm cross bit At least 2 No. probes, at staggered distances The probes should be 40m long, maintaining a minimum 20m in front of the face and a 20m overlap | H | W |  |  | Probe hole record Survey As-Built
4.9. Ground water control
4.9.1 | Strip drain installations | Record location and ensure correct installation of materials |  | Technical Specification C0653 - Tunnel Groundwater Control Systems Section 5 |  | Review | Each installation | Location and quantity of the strip drains shall be as instructed on site by the Designer's representative | H | H |  |  | Strip Drain Check Sheet Survey As-Built
4.9.2 | Flushing Point installation | surveyor to confirm vertical position prior to encasement in shotcrete. Flushing tube connection point with proprietary fitting and cap |  | MMA-DES-TUN-E1-DRG-8145 |  | Visual Inspection | Each installation | Hold point released by CPS | H | H
4.9.3 | Strip drain Bench Connection | underside of top heading lining at connection with bench lining to be cleaned by pressure air jet and water, and inspected by the designers rep prior to placement of the bench shotcrete |  | MMA-DES-TUN-E1-DRG-8143 |  | Visual Inspection | Each installation | Hold point released by CPS | H | H
4.9.4 | Groundwater (rectification) | Where the inflow into the tunnel exceeds the design criteria,appropriate post-installed drainage measures shall be proposed by the Constructor and approved by the Designer’s representative. |  | Technical Specification - C0653 - Tunnel Groundwater Control Systems Clause 6 |  | Visual Inspection | Ongoing | Shall not be exceed 3L/m of length/day averaged over a 100m length of tunnel. Where exceeded, the post-installation groundwater methodology is to be followed. | H | H |  |  | Strip Drain Check Sheet
4.9.5 | Bored drains drilling and installation | Record location and ensure correct installation of materials |  | MMA-DES-TUN-E1-DRG-8141 |  | Review | Each installation | 4.5m long 76mm diameter holes drilled at 4m centres along the sides of the tunnel (location dependant on strip drains and rockbolt locations) | W | R
4.10. Monitoring
4.10.1 | Tunnel convergency (Extensometer) | Monitoring and reading records of the tunnel extensometer |  | Technical Specification C0660 - Tunnel Convergence Monitoring |  | Review | from excavation face >100m = Monthly 40m-100m = Weekly 15m - 40m = 2x weekly <15m = daily | outlined in MMA-DES-TUN-E1-DRG-8180 Table 3 | H | R |  |  | Monitoring Report
4.10.2 | In-Tunnel Optical Survey Convergence | Monitoring and reading records on the tunnel optical survey targets |  | Technical Specification C0660 - Tunnel Convergence Monitoring |  | Review | from excavation face >100m = Monthly 40m-100m = Weekly 15m - 40m = 2x weekly <15m = daily | outlined in MMA-DES-TUN-E1-DRG-8180 Table 3 | H | R |  |  | Monitoring Report

## 5. Post Construction
Inspection and Test Plan Te Ara o Te Ata Excavation and Support ITP # MMA-QA-ITP-Z04-TUN-GE001
Rev Number | This ITP has been prepared by |  |  | Reviewed by Quality Manager |  |  | Reviewed by DSR/CPS |  |  | Approved by Construction Manager
| Name | Signature | Date | Name | Signature | Date | Name | Signature | Date | Name |  | Signature |  | Date
Rev 0 | Teringa Horton, Tarik Jony and Sam Tang | See Approvals Tab | 2024-05-09 | Whineray Arries | See Approvals Tab | 29/11/2024 | Katerina Howard | See Approvals Tab | 2024-05-12 | Hardus Pieters |  | See Approvals Tab |  | 2024-12-06
Rev 1 | Teringa Horton, Jamie Morris, Tarik Jony and Sam Tang | See Approvals Tab | 2025-06-25 | Manoj Jayasundara and Whineray Arries | See Approvals Tab | 2025-06-27 | Roque Alea, Sam Burgess and Ben Westgate | See Approvals Tab | 2025-07-01 | Hardus Pieters |  | See Approvals Tab |  | 2025-07-01
Rev 2
ITP NO: CONQA # |  |  | Project: Te Ara o Te Ata
Verification Method: Hold [H] – work will not proceed past Hold Point until released by organisation imposing hold; Inspection [I] – formal inspection activity to be undertaken and recorded; ensure correct verifying records are in place; Witness [W] – an inspection that may be witnessed by organisation imposing hold; allow reasonable notification period; Review [R] – review of reports, records or other evidence of compliance. Surveillance [S] – An Activity that is subject to ongoing monitoring. | [7 empty] | Responsibilities MTME = MTM Alliance Construction CPS = Construction Phase Services SE/PE = Site Engineer/Project Engineer SUP = Supervisor QM = Quality Manager
Activity/Specification: Excavation & Shotcrete
Item | Titles | Description |  | Specifications and Standards |  | Acceptance criteria and testing |  |  | Verification Activity by |  |  |  | Verifying Records
[6 empty] | Method/ Description | Test frequency | Conformance Criteria | Constructor | CPS | Lab | IOM
5.0 Post construction
5.1 | Red Line Mark Up Drawings | As-built drawings to capture any deviation from the IFC drawings. |  |  |  | Submit | At Completion |  | H | R |  |  | Red Line Mark Up Drawings
5.2 | As-built Drawings | As-built drawings to capture any deviation from the IFC drawings. |  | Quality Management Plan |  | Submit | At Completion |  | H | R
5.3 | Tunnel Operation and maintenance report | Tunnel Operation and maintenance report to detail the maintenance frequency and maintenance procedures. |  |  |  | Submit | At Completion |  | H | R |  | R | Tunnel operation and maintenance report
5.4 | Final Handover Package | Collation of all QA, as-built drawings,as-built records, installation records, PTT, testing and monitoring documentation. Provision of asset management operation and maintenance report to NZTA, including Producer Statements. |  | Quality Management Plan |  | Submit | At Completion |  | H | R |  | R | As-built drawings, installation record, as built records, PTT, testing results, monitoring documentation, operation and maintenance report, Producer Statements

## Rock Bolt Installation Record
Tunnel Rock Bolt Installation Record
Cut # and CH |  |  |  | Support Type: |  |  |  | Date :
Bolt Information
Drill bit: |  |  |  | Drill Depth(m): |  |  |  | Bolt Type:
Operator: |  |  |  | Flush Type: |  |  |  | Grout Record? | Y / N
Bolt ID | CH Installed | Time Bolt Installation Commenced | Time Bolt Installation Finished | Rate of penetration Softer/Harder | Fluid loss? (Y/N) | Ground water present? (Y/ N) | All accessories installed on bolt? (Y/N) | Resin Volume inserted (L) (Part A and Part B) | Resin Returned? (Y/N) | 10s+ Hold (Y/N) | Comments
Tunnel Rock Bolt Installation Record
Comments:
CONSTR Rep: |  |  |  | Signature: |  |  |  | Date
CPS Rep: |  |  |  | Signature: |  |  |  | Date

## Repair Checksheet
Tunnel Lining Repair Checksheet
Date: |  |  |  | Drive: |  | Top Heading / Bench
# | Defect Type | Description |  | Cut # and position |  |  | Chainage
Item | Item |  | CPS Rep | Date | CONSTR Rep | Date | Comments
1 | Defect has been identified and repair methodology confirmed
2 | Materials used for repair are approved for use | [5 empty] | Sika 215 - W/C Ratio 1 bag = 5.5L - 6L of water
3 | defect is cleaned and free of dirst, dust, and loose debris before repair
4 | Non approved materials removed (breathing tubes, grouting lines, rags)
5 | Opening and gaps to defect blocked before remedial material is inserted | [5 empty] | Blocking method:
6 | Testing Samples are taken and left undistubred for 24 hours
7 | Final repair works visually satisfactory
Comments
CONSTR Rep: |  |  |  | Signature:
CPS Rep: |  |  |  | Signature:
DRAFT

## Rock Bolt CheckSheet
Tunnel Rock Bolts / Spile Bar / GRP Bolts Check Sheet
Installation Information:
Date: |  |  |  | Cut # and CH
| Bolt | Hole Size | Drill Bit | Hole Length | Bolt Length
| Spile bars | 76 | any | 8.95 | 9
| GRP (portal) | 51 | any | 4.15 | 4.3
| GRP (Tunnel) | 51 | any | 6.15 | 6.3
| 4m R32 SDA Bars | 51 | Cross | 4.025 | 4.05
| 5.5m R32 SDA Bars | 51 | Cross | 5.55 | 5.625
ITP No. | Item | CPS Rep | Date | CONSTR Rep | Date | Comments
2.3 | Correct bolts used and marked out as per RESS | H |  | H |  | MAR/Product:
2.5 | Cement Grout and/or Resin approved for use. Materials are not expired | H |  | H |  | MAR/Product:
3.4.1, 3.4.2 3.5.1, 3.5.2 | Bolts were free of dirt, detrimental rust or any other deleterious substance. | W |  | H
3.4.1 3.4.2 | Rock bolts position does not exceed 150mm in any direction unless noted otherwise | R |  | H |  | refer to as-built for final confirmation
3.4.1 3.4.2 | Rockbolts installed perpendicular to the face. Face plate sitting fully flush with shotcrete surface | W |  | H
3.5.1 3.5.2 | Spile Bars position does not exceed 25mm in any direction unless noted otherwise | W |  | H
3.4.5 | Holes clean before insertion of resin or grout. Ensure stinger is adequately secured to the face |  |  | H
3.4.5 | Resin stored in heated container above 16 degrees, resin then warmed via heated blankets on Jumbo |  |  | H
3.4.5 | Resin installed is not contaminated and is free of damage |  |  | H
3.4.3 | Cement Grouting shall: - Not be used more than 30 minutes after first mixing and shall be carried out with an approved mixer and pump, and - Be discontinued if the ambient temp or grout temp falls below 5°. |  |  | H
3.4.4 | Cement: 2x sets of grout cubes taken |  |  | H
Comments:
CONSTR Rep: |  |  |  | Signature:
CPS Rep: |  |  |  | Signature:

## Shotcrete Check Sheet
Shotcrete Check Sheet (REV01)
Date: |  |  |  | Drive: |  | Top Heading / Bench
Layers Sprayed |  | Cut # | Layer # |  |  | CH
|  | Cut # | Layer # |  |  | CH
|  | Cut # | Layer # |  |  | CH
Item | Item |  | CPS Rep | Date | CONSTR Rep | Date | Comments
1 | The footing invert (top heading and bench) shall be clean and clear of all debris and shotcrete rebound, and inspected by the designer's representative prior to application of shotcrete. |  | H |  | H
2 | Underside of top heading lining at connection with bench lining to be cleaned by pressure air jet and water and inspected by the designer's representative prior to placement of bench shotcrete. |  | H |  | H
3 | Shotcrete as-built taken of previous layers |  | R |  | H
4 | Shotcrete mix is approved for use |  | H |  | H |  | Mix: 3510SMMS440HOLCIM
5 | Nozzleman approved to spray |  | R |  | H |  | Name:
6 | Shotcrete equipment approved for use |  | R |  | H
7 | all surfaces clean and free of loose material |  | W |  | H
8 | all surface pre-wet immediately prior to spraying |  | W |  | H
9 | Spalled, cracked, loose or contaminated shotcrete removed. |  | W |  | H
10 | Deep pins installed for thickness control | [5 empty] | Cuts installed:
11 | Distance between the nozzle and the surface did not exceed 1.8m.
12 | Nozzle remained perpendicular to the application surface
13 | shotcrete application commenced at the bottom for vertical surfaces.
14 | Sample panel cleaned and left in sprayed location until 24hs after spray and allowed to cure. | [5 empty] | Panel ID:
15 | Layers cured (misted) after application |  | R |  | H
CONSTR Rep: |  |  |  | Signature:
CPS Rep: |  |  |  | Signature:

## Strip Drain Checksheet and Inst
Strip Drain Check Sheet and Install Record(REV01)
Date: |  |  | Advance (No. & CH):
Drive: | Top Heading / Bench |  | Support Type:
ITP # | Item | CPS Rep | Date | CONSTR Rep | Date | Comments
| BENCH: Surveyors to confirm vertical position of flushing tube connection point prior to encasement in shotcrete | H
| Connection between top heading and bench inspected by the designers representative | H
shotcrete as-built checked to ensure strip drain has 100mm cover
3.9 | All materials are clean and free of damage before installation
3.9 | Strip Drain and Flushing hose Installed as per designers instruction
3.9 | Surveyors to confirm position of PVC cross pipe in bench prior to encasement in shotcrete
3.9 | Drainage holes drilled: 45mm diameter 500mm radial distance Min 500mm drill depth into rock
3.9 | Adequatel securing points on the strip drain, fixings, and flushing hose is secured to the shotcrete
3.9 | Flushing hose inlet and strip drain ends protected
3.9 | For multiple strip drains in cut - Check that E-line over excavated as required for sacrificial shotcrete layer of 50mm
3.9 | Survey as-built taken
Top Heading Bench
CONSTR Rep: |  |  | Signature:
CPS Rep: |  |  | Signature:
Cut #

## Post Construction Checksheet
Tunnel Post-Pour Checklist
Cut: |  |  |  | Date:
Top Heading / Bench | Chainage Start: |  |  | Chainage End:
REPAIRS
Defect description | Date identified | Date Repaired | Chainage | Comments
SHOTCRETE
Description | Pass | Fail | Initials | Comments
No voids
No Sagging and lamination
No cracks exceedng 0.5mm
No rebound, over spray, and loose material
No holes and cores
Construction tolerances achieved |  |  |  | Supported by as-built
Final Lining Inspection | Pass | Fail | Name | Signature
Final lining inspected by tunnel engineer
Final lining inspected by CPS Rep
Final Lining Completion | Pass | Fail | Name | Signature
Final lining approved by tunnel engineer
Final lining approved by CPS Rep
Comments: _____________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________________

## Probe hole
Probe Hole Record
Installation Information
Date: |  |  | Advance (No. & CH):
Drill bit: |  |  | Drill Rig:
Flush Type: |  |  | Operator:
Probe hole Information
Probe hole ID |  |  | Position
Chainage |  |  | Probe Hole RL
Angle of drill boom |  |  | Probe hole Depth (m):
Drill Penetration Rate (m/min) |  |  | Drill Parameters
Nature of Ground
Drill set # and Length | Hole Depth | Start time | Drilling observations | Comments
# 1 -
# 2 -
# 3 -
# 4 -
# 5 -
# 6 -
# 7 -
# 8 -
# 9 -
# 10 -
# 11 -
CONSTR Rep |  |  | Date:
Probe Hole Record
,.
Comments

## Shotcrete Early Strength Record
PENETROMETER TEST | [6 empty] | Beam End test
Panel ID |  | Date Sprayed | Time Sprayed | Mix |  | Dosage | Beam 1 | Date Sprayed: |  | Time Sprayed: |  | Tester:
[7 empty] | Test 1 | Test Day: |  | Test Time: |  | Comments
[7 empty] | Results | Reading (bar) | 1- | 2- | 3-
Tester | [7 empty] | Average (bar) |  | Strength (MPa)
Time
Age | [6 empty] | Beam 2 | Date Sprayed: |  | Time Sprayed: |  | Tester:
1 | [6 empty] | Test 2 | Test Day: |  | Test Time: |  | Comments
2 | [6 empty] | Results | Reading (bar) | 1- | 2- | 3-
3 | [7 empty] | Average (bar) |  | Strength (MPa)
4
5 | [6 empty] | Beam 3 | Date Sprayed: |  | Time Sprayed: |  | Tester:
6 | [6 empty] | Test 3 | Test Day: |  | Test Time: |  | Comments
7 | [6 empty] | Results | Reading (bar) | 1- | 2- | 3-
8 | [7 empty] | Average (bar) |  | Strength (MPa)
9
10 | [6 empty] | Beam 4 | Date Sprayed: |  | Time Sprayed: |  | Tester:
Ave | [6 empty] | Test 4 | Test Day: |  | Test Time: |  | Comments
Mpa | [6 empty] | Results | Reading (bar) | 1- | 2- | 3-
STEPS | [7 empty] | Average (bar) |  | Strength (MPa)
1 | Ensure the force indicator is set to zero.
2 | Apply the device perpendicularly to the surface of the sprayed concrete layer and steadily push in the needle to a depth of 15 mm in a single continuous movement. If this is prevented, for instance because of a large aggregate particle or reinforcement, then discontinue the test and repeat in an adjacent location.
STEPS
3 | Read the resistance force from the scale, record the value on the protocol form and return indicator to original position. | [5 empty] | 1 | Set up beam mould on a 70 +- 5 degree angle from horizontal
4 | Clean the needle if necessary. | [5 empty] | 2 | Moulds to be slightly over filled and then trowel finished
5 | Repeat the test ten times as quickly as possible (and within 1 min for strengths below 0,5 MPa) in an area representative of the sprayed region. | [5 empty] | 3 | concrete to be atleast 0.5MPa to carry out test
9 | Compressive Strength (Mpa) = (Force (N) + 17.5) / 687 | [5 empty] | 4 | demould carefully
[7 empty] | 5 | turn beam 90 degrees so smooth sides are incontect with loading plates
Comments | [6 empty] | 6 | top and bottom plate should be carefully aligned with rouhgly 25mm of beam protruding
[7 empty] | 7 | beams to be loaded at rouhgly 1-2kN per second. Load should be applied continuously without shock
[7 empty] | 8 | the length of broken portions of beams shall be at least 125mm (50mm greater than the width)
MTMA Engineer: |  |  |  |  | Date: |  | MTMA Engineer: |  |  |  | Date:

## Grout record
Grout Installation Record
Date: |  | Ambient Temp:
Cut #: |  | Chainage:
Bolt Type:
Spile Bars | GRP | R32S SDA Bar | M24 Paddle Bolt
Theoretical Grout Volumes
Bolt | Length of hole | Diameter | Theoretical Volume (L)
Spile Bars | 8.95 | 76 | 12.9238
GRP Bolts (Portal) | 7.65 | 51 | 4.9744
GRP Bolts (Tunnel) | 4.25 | 51 | 2.7636
R32S SDA Bar (Silt) | 5.5 | 45 | 2.7844
R32S SDA Bar (Sand) | 5.5 | 45 | 2.7844
M24 Paddle Bolt (Silt) | 4 | 33 | 1.089
M24 Paddle Bolt (Sand) | 4 | 38 | 1.444
Bolt Type:
Sika 215 | RB 5.03 | RB 3.07 | Fosroc Conbextra HES
w/c: 0.24 1 bag = 6L of water | w/c: 0.3 1 bag = 6L of water | w/c: 0.192 1 bag = 4.8L of water | w/c: 0.13 1 bag = 2.6L of water
Batch # | Mix | Bolts Grouted | Time Grouted | Samples taken
Bags: Water (L):
Bags: Water (L):
Bags: Water (L):
Bags: Water (L):
Bags: Water (L):
Bleed Test
Constr Rep: |  |  | Date:

## Spile Install Record
Tunnel Spile Bars Installation Record
Cut # |  |  | Advance (No. & CH): |  |  | Date :
Bolt Information
Drill Depth (m): |  |  | Drill Dia (mm): |  |  | Drill Bit Type:
Support Type: |  |  | Flush Type: |  |  | Grout Record? | Y / N
Spile ID | CH Installed | Time Bolt Installation Commenced | Time Bolt Installation Finished | Rate of penetration Softer/Harder | Any ground water encounter (Y/No) | Operator | Time Grouted
Tunnel Spile Bars Installation Record
Comments:
CONSTR Rep: |  |  |  | Signature:
CPS Rep: |  |  |  | Signature:

## Shotcrete record
Te Ara o te Ata - Mt Messenger Bypass Mined Tunnels Shotcrete Trials
Shotcrete Installation Record
Date: |  |  |  | Slump range: |  | 200-240mm |  |  | Ambient temperature:
Approved Mix: | 3510SMMS440HOLCIM |  |  | Accelerator: |  | L530AF | % |  | Cuts Sprayed
Shotcrete Rig: | SPM500 |  |  | Nozzleman:
Delivery Docket Number | Volume (m3) | Correct Mix (✓) | Batch Time | Arrival Time | Slump (mm) | Temp. | Spraying Start Time | Spraying Finish Time | Samples Taken | Comments
CONSTR Rep: |  |  |  |  | Signature: |  |  | Date:
Nozzleman: |  |  |  |  | Signature: |  |  | Date:

## Delivery Docket
Material Delivery Inspection Report
Date Of Delivery
Date inspected
Date of Expiry
Item Delivered
Delivery Location
Lifting Equipment Used
Item | Initial | Comments
Delivery docket received
Items free of damage
Correct Items Delivered
Items Stored correctly
Pictures Taken
Name and Signature | Comments