## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource Id
checklist | ITP - Excavation and Support - 1.0 Preconstruction | itp |  |  |  |  | ITP - Excavation and Support - 1.0 Preconstruction Rev 1
section | 1.0 Pre construction
checkpoint | 1.1 - CWP for tunnel excavation & support work
label | Description - Approved CWP
label | Specifications and Standards - Technical Specification - C0651 - Tunnel Shotcrete
label | ○ Technical Specification - C0652 - Tunnel Rock Reinforcement Clause 3.2
label | Method/Description - Submission
label | Test frequency - Once prior to works commencing
label | Conformance Criteria - Approval CWP has been transmitted via InEight
label | Constructor - H
label | CPS - H
label | Verifying Records - Approved CWP
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.2 - ITP for tunnel excavation & support work
label | Description - Approved ITP
label | Specifications and Standards - Technical Specification - C0651 - Tunnel Shotcrete
label | ○ Technical Specification - C0652 - Tunnel Rock Reinforcement Clause 3.2
label | Method/Description - Submission
label | Test frequency - Once prior to works commencing
label | Conformance Criteria - Approval ITP has been transmitted via InEight
label | Constructor - H
label | CPS - H
label | Verifying Records - Approved ITP
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.3 - IFC Drawings
label | Description - Approved IFC Drawings
label | Specifications and Standards - N/A
label | Method/Description - Submission
label | Test frequency - Once prior to works commencing
label | Conformance Criteria - Ensure all drawings are approved and transmitted Via InEight with IFC status
label | Constructor - H
label | CPS - H
label | Verifying Records - IFC Drawings transmitted into InEight with IFC status
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.4 - IFC Specification
label | Description - Approved IFC Specification
label | Specifications and Standards - N/A
label | Method/Description - Submission
label | Test frequency - Once prior to works commencing
label | Conformance Criteria - Ensure all relevant Specifications have been approved and transmitted Via InEight with IFC status
label | Constructor - H
label | CPS - H
label | Verifying Records - IFC Specification transmitted into InEight with IFC status
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.5 - Permit to tunnel/excavate template
label | Description - No work shall commence until a valid Permit to Tunnel has been signed off for the current section of excavation
label | Specifications and Standards - NZ Legislation
label | Method/Description - Submission
label | Test frequency - Prior to the commencement of the excavation work
label | Conformance Criteria - Valid permit to tunnel
label | Constructor - H
label | CPS - H
label | Verifying Records - Permit to tunnel signed off by all nominated personnel
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.6 - The groundwater control system Methodology
label | Description - The Constructor shall propose a method for a preconstruction trial of the groundwater control system and submit it to the Designer’s Representative for review.
label | Specifications and Standards - Technical Specification - C0653 - Tunnel Groundwater Control Systems Clause 6
label | Method/Description - Submission
label | Test frequency - Prior to the commencement of the excavation work
label | Conformance Criteria - Designer’s Representative Approval
label | Constructor - H
label | CPS - H
label | Verifying Records - Groundwater control system methodology
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.7 - Post-installation Groundwater Control Methodology
label | Description - Where the inflow into the tunnel exceeds 3L/m of length/day averaged over a 100m length of tunnel, appropriate post-installed drainage measures shall be proposed by the Constructor and approved by the Designer’s representative.
label | Specifications and Standards - Technical Specification - C0653 - Tunnel Groundwater Control Systems Clause 6
label | Method/Description - Submission
label | Test frequency - Prior to the commencement of the remedial work
label | Conformance Criteria - Designer’s Representative Approval
label | Constructor - H
label | CPS - H
label | Verifying Records - Post-installation groundwater control system methodology
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.8 - The groundwater control system Trial
label | Description - A preconstruction trial shall be carried out by the Constructor to demonstrate the effectiveness of the connections of strip drains from the top heading to the bench, unless using approved manufacturer's recommended connections installed to the manufacturer's specification.
label | Specifications and Standards - Technical Specification - C0653 - Tunnel Groundwater Control Systems Clause 6
label | Method/Description - Trial
label | Test frequency - Prior to the commencement of the excavation work
label | Conformance Criteria - Designer’s Representative Witness
label | Constructor - H
label | CPS - W
label | Verifying Records - Groundwater control system Trial Results
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.9 - Cement Grout Encapsulation Test
label | Description - A pre-construction trial shall be carried out by the constructure to demonstrate that the proposed grout used is able to fully encapsulate the bolt using the proposed installation method
label | Specifications and Standards - Technical Specification - C0652 - Tunnel Rock Reinforcement Clause 6.2
label | Method/Description - Trial
label | Test frequency - Prior to the commencement of the excavation work
label | Conformance Criteria - Compliance with Technical Specification - C0652 - Tunnel Rock Reinforcement Clause 6.2.
label | ○ Designer’s Representative Approval
label | Constructor - H
label | CPS - W
label | Verifying Records - The rock reinforcement Trial Results
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.10 - Investigation Tests
label | Description - The Constructor shall conduct a Investigation test (pre-production) on sacrificial rock reinforcements and tested progressively to failure. Investigation load test rock reinforcements are to be installed at locations, agreed with the Designer’s Representative.
label | ○ The Constructor shall notify the Designer’s Representative with a minimum of 48 hour notice.
label | Specifications and Standards - Technical Specification - C0652 - Tunnel Rock Reinforcement Clause 6.1
label | Method/Description - Trial
label | Test frequency - Prior to the commencement with A minimum of six investigation tests shall be carried out for each type of rock, grout mix, and rock bolt or dowel orientation, or as agreed upon with the Designer’s Representative.
label | Conformance Criteria - Compliance with Technical Specification - C0652 - Tunnel Rock Reinforcement Clause 6.1.
label | ○ Designer’s Representative Approval
label | Constructor - H
label | CPS - W
label | Verifying Records - Investigation test results
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.11 - End Anchorage Tests
label | Description - The Constructor shall conduct end anchorage test with a minimum of six rock bolts per proposed rock reinforcement system shall be tested in each ground type. For acceptance of end anchorage, all individual bolts shall achieve the pre-tension load shown on the Drawings.
label | Specifications and Standards - Technical Specification - C0652 - Tunnel Rock Reinforcement Clause 6.3
label | Method/Description - Trial
label | Test frequency - Prior to the commencement with A minimum of six tests shall be carried out in each ground type.
label | Conformance Criteria - Compliance with Technical Specification - C0652 - Tunnel Rock Reinforcement Clause 6.3.
label | ○ Designer’s Representative Approval
label | Constructor - H
label | CPS - W
label | Verifying Records - End Anchorage test results
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.12 - Approval of shotcrete equipment
label | Description - Details of all equipment to be approved by the designers representative
label | Specifications and Standards - Technical Specification - C0651 - Tunnel Shotcrete Clause 3.2
label | Method/Description - Review
label | Test frequency - Prior to the commencement of the excavation work
label | Conformance Criteria - Designer’s Representative Approval
label | Constructor - H
label | CPS - H
label | Verifying Records - Equipment Technical Data Sheets
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.13 - Probing ahead trial
label | Description - A trial shall be carried out in advance of tunnelling activities to identify optimum drill bit, drill diameter and flushing and percussion rates
label | Specifications and Standards - Technical Specification - C0650 - Tunnel Sequential Excavation Section 5.5.g
label | Method/Description - Trial
label | Test frequency - Prior to start of tunnelling
label | Conformance Criteria - Designer’s Representative Approval
label | Constructor - H
label | CPS - H
label | Verifying Records - Probe hole trial result
holdpoint | AUTHORITY HOLDPOINT
checkpoint | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
textbox | Contractor's Rep Name:
textbox | Engineer's Rep. Name:
date | Date:
signoff | Add Signature
checklist | ITP - Excavation and Support - 2.0 Material Compliance and approvals | itp |  |  |  |  | ITP - Excavation and Support - 2.0 Material Compliance and approvals Rev 1
section | 2.1. Shotcrete
checkpoint | 2.1.1. - Shotcrete base mix design
label | Description - Compliance with Technical Specification - C0651 - Tunnel Shotcrete Clause 4
label | Specifications and Standards - Technical Specification - C0651 - Tunnel Shotcrete Clause 4
label | Method/Description - Material Review
label | Test frequency - Prior to the commencement of the excavation work
label | Conformance Criteria - as per Technical Specification - C0651 - Tunnel Shotcrete Clause 4
label | Constructor - H
label | CPS - H
label | Verifying Records - Material Approval Record
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.1.2. - Shotcrete Accelerator
label | Description - Type and dosage of shotcrete accelerator shall conform to the requirements of the Specification
label | Specifications and Standards - Technical Specification - C0651 - Tunnel Shotcrete Clause 4.7.1
label | Method/Description - Material Review
label | Test frequency - Prior to the commencement of the excavation work
label | Conformance Criteria - Material Approval Record
label | Constructor - H
label | CPS - H
label | Verifying Records - Material Approval Record
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.1.3. - Nozzelman Certification
label | Description - Nozzelman shall hold a verification of competence (VOC) issued by the constructor
label | Specifications and Standards - Technical Specification - C0651 - Tunnel Shotcrete Clause 5.2
label | Method/Description - Document Review
label | Test frequency - Prior to trial
label | Conformance Criteria - Ensure only personnel hodling VOC are operating the shotcrete robot on site.
label | Constructor - H
label | CPS - R
label | Verifying Records - Nozzelman Certificate/ VOC
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.1.4. - Cement
label | Description - Testing of cement properties in accordance with NZS 3122 and 3104 shall be carried out at least monthly
label | Specifications and Standards - NZS3122, NZS 104
label | ○ Technical Specification - C0651 - Tunnel Shotcrete Clause 4.2
label | Method/Description - Document Review
label | Test frequency - Monthly
label | Conformance Criteria - Comply with NZS3122 and NZS3104
label | Constructor - R
label | CPS - R
label | Verifying Records - Cement Certificates
checkpoint | 2.1.5. - Silica Fume
label | Description - Compliance with Technical Specification - C0651 - Tunnel Shotcrete Clause 4.4
label | Specifications and Standards - Technical Specification - C0651 - Tunnel Shotcrete Clause 4.4
label | Method/Description - Document Review
label | Test frequency - Monthly
label | Conformance Criteria - Comply with NZS3122 and the tunnel shotcrete specifications C0651
label | Constructor - R
label | CPS - R
label | Verifying Records - Silica Testing
section | 2.2. Reinforcing Mesh
checkpoint | 2.2.1. - Reinforcing Mesh
label | Description - SE92 GR 500E mesh
label | Specifications and Standards - AS/NZS 4671
label | Method/Description - Material Review
label | Test frequency - Prior to the commencement of the excavation work
label | Conformance Criteria - Material Approval Record
label | Constructor - H
label | CPS - H
label | Verifying Records - Material Approval Record
holdpoint | AUTHORITY HOLDPOINT
section | 2.3. Rockbolts/Dowels Bar
checkpoint | 2.3.1. - Tunnel rockbolts and plates
label | Description - rockbolts material and corrosion protection
label | Specifications and Standards - AS/NZS 4671, AS/NZS 3678, AS/NZ 4680
label | ○ Technical Specification - C0652 - Tunnel Rock Reinforcement Clause 4.1 and 4.2
label | Method/Description - Material Review
label | Test frequency - Prior to the commencement of the excavation work
label | Conformance Criteria - Grade 500N, galvanised HDG to AS/NZS 4680
label | ○ Material Approval Record including mill certificate
label | Constructor - H
label | CPS - H
label | Verifying Records - Material Approval Record
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.3.2. - Face Dowels
label | Description - glass fibre reinforced face dowels material
label | Specifications and Standards - ASTM D3916
label | ○ Technical Specification - C0652 - Tunnel Rock Reinforcement Clause 4.2.2
label | Method/Description - Material Review
label | Test frequency - Prior to the commencement of the excavation work
label | Conformance Criteria - Material Approval Record
label | Constructor - H
label | CPS - H
label | Verifying Records - Material Approval Record
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.3.3. - Delivery acceptance
label | Description - Inspect fabricated rock bolts and rock dowels prior to installation
label | Specifications and Standards - Technical Specification - C0652 - Tunnel Rock Reinforcement Clause 3.2
label | Method/Description - Visual Inspection
label | Test frequency - upon delivery
label | Conformance Criteria - N/A
label | Constructor - H
label | CPS - W
label | Verifying Records - Delivery Docket/Mil Test cert
holdpoint | AUTHORITY HOLDPOINT
section | 2.4. Spile bars
checkpoint | 2.4.1. - Spile bars
label | Description - spile bar material
label | Specifications and Standards - AS/NZS 4671
label | ○ Technical Specification - C0652 - Tunnel Rock Reinforcement Clause 4.2.3
label | ○ AS 1391
label | Method/Description - Material Review
label | Test frequency - Prior to the commencement of the excavation work
label | Conformance Criteria - Material Approval Record
label | Constructor - H
label | CPS - H
label | Verifying Records - Material Approval Record
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.4.2. - Delivery acceptance
label | Description - Visual confirmation of delivered items
label | Specifications and Standards - N/A
label | Method/Description - Visual Inspection
label | Test frequency - Upon delivery
label | Conformance Criteria - N/A
label | Constructor - H
label | CPS - R
label | Verifying Records - Delivery Docket/Mil Test cert
holdpoint | AUTHORITY HOLDPOINT
section | 2.5. Cement grout for rock bolts, dowels, spiles
checkpoint | 2.5.1. - cement grout
label | Description - grout material and properties
label | Specifications and Standards - Technical Specification - C0652 - Tunnel Rock Reinforcement Clause 4.3.1
label | ○ NZS3122
label | Method/Description - Material Review
label | Test frequency - Prior to the commencement of the excavation work
label | Conformance Criteria - Material Approval Record
label | Constructor - H
label | CPS - H
label | Verifying Records - Material Approval Record
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.5.2. - Delivery acceptance
label | Description - Visual confirmation of delivered items
label | Specifications and Standards - N/A
label | Method/Description - Visual Inspection
label | Test frequency - Upon delivery
label | Constructor - H
label | CPS - R
label | Verifying Records - Delivery Docket
holdpoint | AUTHORITY HOLDPOINT
section | 2.6. Resin
checkpoint | 2.6.1. - Resin Grout
label | Description - grout material and properties
label | Specifications and Standards - Technical Specification - C0652 - Tunnel Rock Reinforcement Clause 4.3.2
label | Method/Description - Material Review
label | Test frequency - Prior to the commencement of the excavation work
label | Conformance Criteria - Material Approval Record
label | Constructor - H
label | CPS - H
label | Verifying Records - Material Approval Record
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.6.2. - Delivery acceptance
label | Description - Visual confirmation of delivered items
label | Specifications and Standards - N/A
label | Method/Description - Visual Inspection
label | Test frequency - Upon delivery
label | Conformance Criteria - As per accepted MAR
label | Constructor - H
label | CPS - W
label | Verifying Records - Delivery Docket
holdpoint | AUTHORITY HOLDPOINT
section | 2.7. Monitoring Instruments
checkpoint | 2.7.1. - Monitoring instrumets
label | Description - Compliance with Technical Specification C0660 - Tunnel Convergence Monitoring
label | Specifications and Standards - Technical Specification C0660 - Tunnel Convergence Monitoring
label | Method/Description - Review
label | Test frequency - Prior to installation
label | Conformance Criteria - Designer’s Representative Approval
label | Constructor - H
label | CPS - H
label | Verifying Records - Material Approval Record
holdpoint | AUTHORITY HOLDPOINT
section | 2.8. Ground water control
checkpoint | 2.8.1. - Strip Drain Materials
label | Description - Compliance with Technical Specification C0653 - Tunnel Groundwater Control Systems MMA-DES-TUN-E1-SPC-54409
label | Specifications and Standards - Technical Specification C0653 - Tunnel Groundwater Control Systems
label | Method/Description - Review
label | Test frequency - Prior to installation
label | Conformance Criteria - Designer’s Representative Approval
label | Constructor - H
label | CPS - H
label | Verifying Records - Material Approval Record
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.8.2. - Bored Drain Materials
label | Description - Compliance with drawing MMA-DES-TUN-E1-DRG-8141
label | Specifications and Standards - MMA-DES-TUN-E1-DRG-8141
label | Method/Description - Review
label | Test frequency - Prior to installation
label | Conformance Criteria - Designer’s Representative Approval
label | Constructor - H
label | CPS - H
label | Verifying Records - Material Approval Record
holdpoint | AUTHORITY HOLDPOINT
checkpoint | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
textbox | Contractor's Rep Name:
textbox | Engineer's Rep. Name:
date | Date:
signoff | Add Signature
checklist | ITP - Excavation and Support - 3.0 Shotcrete Testing | itp |  |  |  |  | ITP - Excavation and Support - 3.0 Shotcrete Testing Rev 1
section | 3.0 Shotcrete Testing
checkpoint | 3.1 - Personnel Entry
label | Description - Test prior to each personnel entry and/or face advance.
label | ○ Test results must be verified once a month during construction.
label | Specifications and Standards - BS EN 14488-2
label | ○ Technical Specification - C0651 - Tunnel Shotcrete Table 6.4
label | Method/Description - Penetrometer test
label | Test frequency - Initially test prior to each personnel entry after spraying primary shotcrete. Once established, this curve must be verified once a month during construction.
label | Conformance Criteria - ST1/1A/1B/2/3/3A - minimum of 50mm thick shotcrete layer that has achieved minimum compressive strength of 1mpa combined with remotely installed pattern rockbolts and spot bolts as required or as directed by the designer's representative. rockbolt grout to have achieved a compressive strength of at least 3mpa.
label | ○ ST3B - minimum 100mm thick shotcrete layer that has achieved minimum compressive strength of 1mpa
label | Constructor - H
label | CPS - R
label | Verifying Records - Beam End Test Results
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.2 - Beam End Test (early age compressive strength)
label | Description - Safe shotcrete strength before next advancement to max. advance length
label | Specifications and Standards - Technical Specification - C0651 - Tunnel Shotcrete Table 6.1 and 6.4
label | ○ ASTM C116
label | Method/Description - field test
label | Test frequency - Initially test prior to each personnel entry after spraying primary shotcrete. Once established, this curve must be verified once a month during construction.
label | Conformance Criteria - From the Specification the following applies:
label | ○ Min. 1.00 MPa at 3 Hours
label | ○ Min. 5.00 MPa at 6 Hours
label | ○ Min. 7.00 MPa at 12 Hours
label | ○ Min. 12.00 MPa at 24-36 Hours
label | Constructor - H
label | CPS - W
label | Verifying Records - Beam End Test Results
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.3 - Compressive Strength (cast sample)
label | Description - To prove compressive strength compliance requirement
label | Specifications and Standards - NZS3112
label | ○ Technical Specification - C0651 - Tunnel Shotcrete Table 6.1 and 6.4
label | Method/Description - certified lab test
label | Test frequency - 1 test (I test shall include 4 cored specimen, 3 tested and 1 spare) for the first 50m3 of shotcrete and 1 test for every 250m3 of shotcrete thereafter
label | Conformance Criteria - Min. 35 MPa at 28 days
label | Constructor - W
label | CPS - R
label | Verifying Records - IANZ lab test report
checkpoint | 3.4 - Compressive Strength (cored sample)
label | Description - To prove compressive strength compliance requirement
label | Specifications and Standards - NZS3112
label | ○ Technical Specification - C0651 - Tunnel Shotcrete Table 6.4
label | Method/Description - certified lab test
label | Test frequency - 1 test for every 50m3 of sprayed shotcrete
label | Conformance Criteria - Min. 20 MPa at 7 days
label | ○ Min. 35 MPa at 28 days
label | ○ Min. 35 MPa at 90 days
label | Constructor - W
label | CPS - R
label | Verifying Records - IANZ lab test report
checkpoint | 3.3 - Residual Flexural Tensile Strength
label | Description - To prove compliance with flexural strength requirements
label | Specifications and Standards - BS EN 14651: 2005 + A1: 2007
label | ○ Technical Specification - C0651 - Tunnel Shotcrete Table 6.4 and 6.1
label | Method/Description - certified lab test
label | Test frequency - 1 test for the first 50m3 of shotcrete and 1 test for every 100m3 of shotcrete thereafter
label | Conformance Criteria - Min. FR,1 of 1.25MPa and FR,4 at 1MPa
label | Constructor - W
label | CPS - R
label | Verifying Records - IANZ lab test report
checkpoint | 3.4 - Drying Shrinkage Testing
label | Description - To prove compliance with shrinkage requirements
label | Specifications and Standards - AS1012.13
label | ○ Technical Specification - C0651 - Tunnel Shotcrete Table 6.4 and 6.1
label | Method/Description - certified lab test
label | Test frequency - 1 test for the first 50m3 of shotcrete and 1 test for every 250m3 of shotcrete thereafter
label | Conformance Criteria - Max 850 micro strain
label | Constructor - W
label | CPS - R
label | Verifying Records - IANZ lab test report
checkpoint | 3.5 - Permeability testing
label | Description - to prove compliance with permeability requirements
label | Specifications and Standards - BS EN 12390-8
label | ○ Technical Specification - C0651 - Tunnel Shotcrete Table 6.4. and 6.1
label | Method/Description - certified lab test
label | Test frequency - 3 tests for the first 50m3 of shotcrete then 1 test every 1 month thereafter
label | Conformance Criteria - Maximum allowable penetration 25mm
label | Constructor - W
label | CPS - R
label | Verifying Records - IANZ lab test report
checkpoint | 3.6 - Steel fibre content
label | Description - To prove compliance with fibre content test requirement
label | Specifications and Standards - BS EN 14488-7 (fresh concrete)
label | ○ Technical Specification - C0651 - Tunnel Shotcrete Section 4.8
label | Method/Description - certified lab test
label | Test frequency - 1 test for the first 50m3 of shotcrete and 1 test for every 100m3 of shotcrete thereafter
label | Conformance Criteria - Minimum 35kg/m3
label | Constructor - H
label | CPS - R
label | Verifying Records - IANZ lab test report
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.5 - Relative density
label | Description - To prove compliance with the relative density requirement
label | Specifications and Standards - NZS 3112.1
label | ○ Technical Specification - C0651 - Tunnel Shotcrete Table 6.4 and 6.1
label | Method/Description - certified lab test
label | Test frequency - 1 test for the first 50m3 of shotcrete and 1 test for every 250m3 of shotcrete thereafter
label | Conformance Criteria - Minimum 98% of the density measured from base mix
label | Constructor - H
label | CPS - R
label | Verifying Records - IANZ lab test report
holdpoint | AUTHORITY HOLDPOINT
checkpoint | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
textbox | Contractor's Rep Name:
textbox | Engineer's Rep. Name:
date | Date:
signoff | Add Signature
checklist | ITP - Excavation and Support - 4.0 Construction (Cut sheet) | itp |  |  |  |  | ITP - Excavation and Support - 4.0 Construction (Cut sheet) Rev 1
section | 4.1. Excavation
checkpoint | 4.1.1 - PTT
label | Description - PTT shall define the planned excavation limits and support types (RESS) prior to each defined period of excavation in each heading or bench face.
label | ○ Tunnel excavation shall not commence on a shift until PTT has been signed off
label | Specifications and Standards - Technical Specifications C0650 - Tunnel Sequential Excavation Section 5.1
label | Method/Description - PTT form
label | Test frequency - Every advance or as agreed in DRM
label | Conformance Criteria - N/A
label | Constructor - H
label | CPS - H
label | Verifying Records - PTT
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.1.2 - Face Mapping
label | Description - Recommend the required support type based on the Actual Ground Conditions.
label | ○ Determine any corrective measures required to ensure safety and stability of the excavation.
label | ○ Identify if the ground conditions depart from the expected range of conditions for which a support type has been designed and notify the Designer if new design is required.
label | Specifications and Standards - Technical Specifications C0650 - Tunnel Sequential Excavation Section 5.1
label | Method/Description - Geological mapping record
label | Test frequency - Every advance or as agreed in DRM
label | Conformance Criteria - N/A
label | Constructor - H
label | CPS - H
label | Verifying Records - Required Excavation and support sheet
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.1.3 - E-line control
label | Description - Control the E-Line before, during and after excavation is finished
label | Specifications and Standards - Drawing MMMA-DES-TUN-E1-DRG-8119
label | Method/Description - Surveyor to set out and record as built. VMT system to provide e-line guidance
label | Test frequency - Every advance
label | Conformance Criteria - Over excavation tolerance -0/+150mm
label | Constructor - H
label | CPS - W
label | Verifying Records - Strip Drain Check Sheet
holdpoint | AUTHORITY HOLDPOINT
section | 4.2. Shotcrete
checkpoint | 4.2.1 - Shotcrete Delivery and acceptance
label | Description - delivery dockets check, slump and temperature check
label | Specifications and Standards - Technical Specification - C0651 - Tunnel Shotcrete Clause 5.4
label | ○ NZS 3109: 1997
label | Method/Description - Document Review
label | Test frequency - Each truck
label | Conformance Criteria - Slump range 200-240mm
label | ○ Temperature range 5-35 celcius
label | ○ Delivery dockets to include the following; Batch number,
label | ○ Batch temperature at time of dispatch and delivery, Mix designation, Date and time of mixing, Quantity delivered, The delivery truck number, Date and time the delivery truck left the batching plant, Amounts of water, admixture, or any other ingredients made after despatch, and time at which such additions are made, Steel fibre type and content, Micro fibre type and content, and, any other relevant information.
label | Constructor - H
label | CPS - R
label | Verifying Records - Shotcrete Installation Record
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.2.3 - Rock and Shotcrete Surface Preparation
label | Description - Prepare all surfaces to be shotcreted prior to application of shotcrete
label | Specifications and Standards - Technical Specification - C0650 - Tunnel Civil Works Section 5.4
label | Method/Description - Visual Inspection
label | Test frequency - Prior to spraying
label | Conformance Criteria - Surface clean and free of loose material, pre-wet surface immediately prior to spraying.
label | ○ Any residual flowing or seeping water shall be controlled using channels, chases, pipes, or other approved means.
label | ○ Spalled, cracked, loose or contaminated shotcrete removed.
label | Constructor - H
label | CPS - W
label | Verifying Records - Shotcrete Check Sheet
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.2.5 - Shotcrete Thickness As-built
label | Description - Provide control means to verify the thickness of final shotcrete layer
label | Specifications and Standards - Technical Specification C0650 - Tunnel Sequential Excavation, section 5.7
label | ○ Drawing MMA-DES-TUN-E1-DRG-8119
label | ○ Drawing MMA-DES-TUN-E1-DRG-8130
label | Method/Description - Survey Asbuilt
label | Test frequency - As-builts shall be taken of EACH layer of shotcrete
label | Conformance Criteria - Shotcrete thickness shall be sprayed in accordance with drawing MMA-DES-TUN-E1-DRG-8129, 8130, and 3831 and within the tolerances outlined in drawing MMA-DES-TUN-E1-DRG-8119
label | Constructor - H
label | CPS - R
label | Verifying Records - As-built Report
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.2.7 - Shotcrete Lining intrados As-built
label | Description - Provide control means to verify the intrados clearance of the shotcrete lining
label | Specifications and Standards - Technical Specification C0650 - Tunnel Sequential Excavation, section 5.7
label | ○ Drawing MMA-DES-TUN-E1-DRG-8119
label | ○ Drawing MMA-DES-TUN-E1-DRG-8131
label | Method/Description - Survey Asbuilt
label | Test frequency - As-builts shall be taken of EACH layer of shotcrete
label | Conformance Criteria - Shotcrete thickness shall be sprayed in accordance with drawing MMA-DES-TUN-E1-DRG-8129, 8130, and 3831 and within the tolerances outlined in drawing MMA-DES-TUN-E1-DRG-8120
label | Constructor - H
label | CPS - R
label | Verifying Records - As-built Report
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.2.9 - Shotcrete Lining C-line As-built
label | Description - Provide control means to verify the C-line clearance of the shotcrete lining
label | Specifications and Standards - Technical Specification C0650 - Tunnel Sequential Excavation, section 5.7
label | ○ Drawing MMA-DES-TUN-E1-DRG-8119
label | ○ Drawing MMA-DES-TUN-E1-DRG-8132
label | Method/Description - Survey Asbuilt
label | Test frequency - As-builts shall be taken of EACH layer of shotcrete
label | Conformance Criteria - Shotcrete thickness shall be sprayed in accordance with drawing MMA-DES-TUN-E1-DRG-8129, 8130, and 3831 and within the tolerances outlined in drawing MMA-DES-TUN-E1-DRG-8121
label | Constructor - H
label | CPS - R
label | Verifying Records - As-built Report
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.2.11 - Top heading to Bench Inspection
label | Description - Underside of top heading lining at connection with bench lining to be cleaned by pressure air jet and water and inspected by the designer's representative prior to placement of bench shotcrete.
label | Specifications and Standards - Technical Specification - C0651 - Tunnel Shotcrete Clause 3.2 Table 3.1
label | Method/Description - Visual Inspection
label | Test frequency - Every Construction Joint
label | Conformance Criteria - Hold point released by CPS
label | Constructor - H
label | CPS - H
label | Verifying Records - Shotcrete Check Sheet
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.2.13 - Footing Inspection
label | Description - The footing invert (top heading and bench) shall be clean and clear of all debris and shotcrete rebound and inspected by designer's representative prior to placement of shotcrete.
label | Specifications and Standards - Drawing MMA-DES-TUN-E1-DRG-8129
label | Method/Description - Visual Inspection
label | Test frequency - Prior to each Spray
label | Conformance Criteria - Hold point released by CPS
label | Constructor - H
label | CPS - H
label | Verifying Records - Shotcrete Check Sheet
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.2.15 - Curing
label | Description - Curing to be carried out in accordance with the Specification
label | Specifications and Standards - Technical Specification - C0651 - Tunnel Shotcrete Clause 5.5
label | Test frequency - Each Spray
label | Constructor - H
label | CPS - R
label | Verifying Records - Shotcrete Check Sheet
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.2.17 - Defects and Repair
label | Description - The final layer of shotcrete shall be inspected for any defects and repaired accordingly.
label | ○ At the completion of the lining, all core holes in the lining (resulting from testing or inspection) shall be backfilled with non-shrink mortar of an equivalent strength and fire resistance properties unless otherwise specified. The surface of the restored hole shall be similar to the surrounding surface in texture and colour.
label | Specifications and Standards - Technical Specification C0650 - Tunnel Sequential Excavation, section 5.6
label | Method/Description - Visual Inspection
label | Test frequency - Every defect on Every advance
label | Conformance Criteria - Crack <0.5mm ,Crack >0.5mm -Non corformance report
label | Constructor - H
label | CPS - W
label | Verifying Records - Post spray inspection record
holdpoint | AUTHORITY HOLDPOINT
section | 4.3. Reinforcing mesh
checkpoint | 4.3.1. - Reinforcing mesh for primary lining
label | Description - To prove position, cover and overlap are achieved
label | Specifications and Standards - Drawing MMMA-DES-TUN-E1-DRG-8011
label | Method/Description - Visual inspection and survey
label | Test frequency - Every advance
label | Conformance Criteria - Longitudinal and transverse overlap of 250mm (one mesh square plus 50mm)
label | ○ Min. cover 65mm at the extrados and 85mm at the intrados
label | Constructor - H
label | CPS - W
label | Verifying Records - Mesh Check Sheet, As-built
holdpoint | AUTHORITY HOLDPOINT
section | 4.4. Rockbolts
checkpoint | 4.4.1 - Drilling and Installation
label | Description - Bolts shall be drilled to the depth, diameter, alignment and position specified on the Drawings or instructed by the Designer.
label | ○ To ensure correct installation process for resin injection
label | Specifications and Standards - Technical Specification C0652 - Tunnel Rock Reinforcement, section 5.2, 5.3
label | Method/Description - Survey
label | Test frequency - Each bolt
label | Conformance Criteria - Bolts shall be installed perpendicular to the excavation face unless stated otherwise.
label | ○ Where rockbolts are not able to be installed perpendicular, the maximum deviation shall be 18 degrees from perpendicular.
label | ○ Position Tolerence +150,-150mm
label | — The Constructor shall record a drilling log for each drillhole, including the date and time of installation and any difficulties or problems that were encountered.
label | — Dowels to be clean or any other physical damage at the time of installation
label | — Type of bolts, diameter, length, location, spacing and orientation according to detailed design
label | — Sufficient volume of resin to be used with each rock reinforcement installation in accordance with the approved project specific procedure developed during the trials.
label | — Daily records of all grouting works to be kept
label | Constructor - H
label | CPS - W
label | Verifying Records - Rock Bolt Installation Record, Rock bolt Check Sheet
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.4.2 - Rockbolt As-built
label | Description - Bolts to be installed in the position specified on the drawings or as instructed by the designer
label | Specifications and Standards - Technical Specification C0652 - Tunnel Rock Reinforcement section 5.3
label | Method/Description - Review
label | Test frequency - Each bolt
label | Conformance Criteria - bolts shall be installed perpendicular to the excavation face unless stated otherwise.
label | ○ Where rockbolts are not able to be installed perpendicular, the maximum deviation shall be 18 degrees from perpendicular.
label | ○ Position Tolerence +150,-150mm
label | Constructor - H
label | CPS - R
label | Verifying Records - Rock Bolt As built Survey
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.4.3 - Pull test
label | Description - Demonstrate that the installed rock reinforcements can provide at least the design working load capacity.
label | Specifications and Standards - Technical Specification - C0652 - Tunnel Rock Reinforcement Clause 6.5
label | Method/Description - Test
label | Test frequency - 1. The first nine installations of each type of rock bolt and the first nine installations of each type of rock dowel shall be tested in each ground type as it presents in production. At least one test location of each type shall be in the tunnel crown unless otherwise directed by the Designer’s Representative.
label | 2. 5% of the next 100 installations of rock bolts and rock dowels, proportionately throughout the ground types presenting.
label | Conformance Criteria - The bolt or dowel is deemed acceptable if, during the cycle, the displacement of the bolt or dowel head relative to the measuring datum (after allowing for any temperature changes) does not exceed the criteria for 100% of the working load, as set out in Table 6.4 of the specification.
label | ○ Failure criteria: 2% Maximum Permissible Displacement or failure to maintain specified loads or ongoing creep of the rock bolt or rock dowel
label | Constructor - H
label | CPS - W
label | Verifying Records - Testing records
holdpoint | AUTHORITY HOLDPOINT
section | 4.5. Spile installation
checkpoint | 4.5.1 - Drilling and Installation
label | Description - Bolts shall be drilled to the depth, diameter, alignment and position specified on the Drawings or instructed by the Designer.
label | ○ To ensure correct installation process for resin injection
label | Specifications and Standards - Technical Specification C0652 - Tunnel Rock Reinforcement, section 5.2, 5.3
label | Method/Description - Survey
label | Test frequency - Each bolt
label | Conformance Criteria - bolts shall be installed perpendicular to the excavation face unless stated otherwise.
label | — The Constructor shall record a drilling log for each drillhole, including the date and time of installation and any difficulties or problems that were encountered. bolts to be clean or any other physical damage at the time of installation
label | — Type of bolts, diameter, length, location, spacing and orientation according to detailed design
label | Constructor - H
label | CPS - W
label | Verifying Records - Rock Bolt Installation Record, Rock bolt Check Sheet
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.5.2 - Spile bar As-built
label | Description - Bolts to be installed in the position specified on the drawings or as instructed by the designer
label | Specifications and Standards - Technical Specification C0652 - Tunnel Rock Reinforcement section 5.3
label | Method/Description - Review
label | Test frequency - Each dowel
label | Conformance Criteria - Positional tolerance of portal spile bars not to exceed 25mm in any direction
label | — Setout angle shall be as per drawing. Max. angular tolerance not to exceed 1 in 60.
label | Constructor - H
label | CPS - W
label | Verifying Records - Rock Bolt As built Survey
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.5.3 - Grouting mixing
label | Description - To ensure correct practice and w/c ratio check
label | Specifications and Standards - Technical Specification C0652 - Tunnel Rock Reinforcement section 5.4.1
label | ○ NZ 3109
label | Method/Description - Review
label | Test frequency - Every batch prior to grouting
label | Conformance Criteria - Target w/c ratio as per MAR
label | Constructor - H
label | CPS - W
label | Verifying Records - Grout Record
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.5.4 - Grout test
label | Description - Testing specimen to measure UCS
label | Specifications and Standards - Technical Specification C0652 - Tunnel Rock Reinforcement section 6.4
label | ○ NZ 3112.4:1986
label | Method/Description - Compressive strength test
label | Test frequency - Evevery batch prior to grouting (three cubes at 1 day, three cubes at 28 days)
label | Conformance Criteria - min 20MPa at 1 day
label | ○ min 40MPa at 28 days
label | The average compressive strength determined from any group of cubes shall excess the specified characterisitc strength by:
label | ○ 1MPa at 1 day
label | ○ 3MPa at 28 days
label | Constructor - H
label | CPS - W
label | Verifying Records - IANZ lab test report
holdpoint | AUTHORITY HOLDPOINT
section | 4.6. Face dowels
checkpoint | 4.6.1 - Drilling and Installation
label | Description - Bolts shall be drilled to the depth, diameter, alignment and position specified on the Drawings or instructed by the Designer.
label | ○ To ensure correct installation process for resin injection
label | Specifications and Standards - Technical Specification C0652 - Tunnel Rock Reinforcement, section 5.2, 5.3
label | Method/Description - Survey
label | Test frequency - Each bolt
label | Conformance Criteria - bolts shall be installed perpendicular to the excavation face unless stated otherwise.
label | — The Constructor shall record a drilling log for each drillhole, including the date and time of installation and any difficulties or problems that were encountered.
label | — Bolts to be clean or any other physical damage at the time of installation
label | — Type of bolts, diameter, length, location, spacing and orientation according to detailed design
label | Constructor - H
label | CPS - W
label | Verifying Records - Rock Bolt Installation Record, Rock bolt Check Sheet
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.6.2 - Rockbolt As-built
label | Description - Bolts to be installed in the position specified on the drawings or as instructed by the designer
label | Specifications and Standards - Technical Specification C0652 - Tunnel Rock Reinforcement section 5.3
label | Method/Description - Review
label | Test frequency - Each dowel
label | Conformance Criteria - Dowels installed as per the drawings or as per designers instruction
label | Constructor - H
label | CPS - W
label | Verifying Records - Rock Bolt As built Survey
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.6.3 - Grouting mixing
label | Description - To ensure correct practice and w/c ratio check
label | Specifications and Standards - Technical Specification C0652 - Tunnel Rock Reinforcement section 5.4.1
label | ○ NZ 3109
label | Method/Description - Review
label | Test frequency - Every batch prior to grouting
label | Conformance Criteria - Target w/c ratio as per MAR
label | Constructor - H
label | CPS - W
label | Verifying Records - Grout Record
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.6.4 - Grout test
label | Description - Testing specimen to measure UCS
label | Specifications and Standards - Technical Specification C0652 - Tunnel Rock Reinforcement section 6.4
label | ○ NZ 3112.4:1986
label | Method/Description - Compressive strength test
label | Test frequency - Evevery batch prior to grouting (three cubes at 1 day, three cubes at 28 days)
label | Conformance Criteria - min 20MPa at 1 day
label | ○ min 40MPa at 28 days
label | The average compressive strength determined from any group of cubes shall excess the specified characterisitc strength by:
label | ○ 1MPa at 1 day
label | ○ 3MPa at 28 days
label | Constructor - H
label | CPS - W
label | Verifying Records - IANZ lab test report
holdpoint | AUTHORITY HOLDPOINT
section | 4.7. Probe holes
checkpoint | 4.7.1. - Drilling probe holes
label | Description - Record information during drilling
label | ○ Check the water inflow during and after drilling
label | Specifications and Standards - Technical specification C0650 - Tunnel Sequential Excavation, section 5.5 - updated with RFI 225
label | Method/Description - Geological monitoring
label | Test frequency - Maintain minimum one probe at 20 m ahead of the face at all times
label | Conformance Criteria - Hole to be drilled with a 51mm cross bit
label | ○ At least 2 No. probes, at staggered distances
label | ○ The probes should be 40m long, maintaining a minimum 20m in front of the face and a 20m overlap
label | Constructor - H
label | CPS - W
label | Verifying Records - Probe hole record, Survey As-Built
holdpoint | AUTHORITY HOLDPOINT
section | 4.9. Ground water control
checkpoint | 4.9.1 - Strip drain installations
label | Description - Record location and ensure correct installation of materials
label | Specifications and Standards - Technical Specification C0653 - Tunnel Groundwater Control Systems Section 5
label | Method/Description - Review
label | Test frequency - Each installation
label | Conformance Criteria - Location and quantity of the strip drains shall be as instructed on site by the Designer's representative
label | Constructor - H
label | CPS - H
label | Verifying Records - Strip Drain Check Sheet, Survey As-Built
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.9.2 - Flushing Point installation
label | Description - surveyor to confirm vertical position prior to encasement in shotcrete. Flushing tube connection point with proprietary fitting and cap
label | Specifications and Standards - MMA-DES-TUN-E1-DRG-8145
label | Method/Description - Visual Inspection
label | Test frequency - Each installation
label | Conformance Criteria - Hold point released by CPS
label | Constructor - H
label | CPS - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.9.3 - Strip drain Bench Connection
label | Description - underside of top heading lining at connection with bench lining to be cleaned by pressure air jet and water, and inspected by the designers rep prior to placement of the bench shotcrete
label | Specifications and Standards - MMA-DES-TUN-E1-DRG-8143
label | Method/Description - Visual Inspection
label | Test frequency - Each installation
label | Conformance Criteria - Hold point released by CPS
label | Constructor - H
label | CPS - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.9.4 - Groundwater (rectification)
label | Description - Where the inflow into the tunnel exceeds the design criteria,appropriate post-installed drainage measures shall be proposed by the Constructor and approved by the Designer’s representative.
label | Specifications and Standards - Technical Specification - C0653 - Tunnel Groundwater Control Systems Clause 6
label | Method/Description - Visual Inspection
label | Test frequency - Ongoing
label | Conformance Criteria - Shall not be exceed 3L/m of length/day averaged over a 100m length of tunnel. Where exceeded, the post-installation groundwater methodology is to be followed.
label | Constructor - H
label | CPS - H
label | Verifying Records - Strip Drain Check Sheet
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.9.5 - Bored drains drilling and installation
label | Description - Record location and ensure correct installation of materials
label | Specifications and Standards - MMA-DES-TUN-E1-DRG-8141
label | Method/Description - Review
label | Test frequency - Each installation
label | Conformance Criteria - 4.5m long 76mm diameter holes drilled at 4m centres along the sides of the tunnel (location dependant on strip drains and rockbolt locations)
label | Constructor - W
label | CPS - R
section | 4.10. Monitoring
checkpoint | 4.10.1 - Tunnel convergency (Extensometer)
label | Description - Monitoring and reading records of the tunnel extensometer
label | Specifications and Standards - Technical Specification C0660 - Tunnel Convergence Monitoring
label | Method/Description - Review
label | Test frequency - from excavation face
label | ○ >100m = Monthly
label | ○ 40m-100m = Weekly
label | ○ 15m - 40m = 2x weekly
label | ○ <15m = daily
label | Conformance Criteria - outlined in MMA-DES-TUN-E1-DRG-8180 Table 3
label | Constructor - H
label | CPS - R
label | Verifying Records - Monitoring Report
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.10.2 - In-Tunnel Optical Survey Convergence
label | Description - Monitoring and reading records on the tunnel optical survey targets
label | Specifications and Standards - Technical Specification C0660 - Tunnel Convergence Monitoring
label | Method/Description - Review
label | Test frequency - from excavation face
label | ○ >100m = Monthly
label | ○ 40m-100m = Weekly
label | ○ 15m - 40m = 2x weekly
label | ○ <15m = daily
label | Conformance Criteria - outlined in MMA-DES-TUN-E1-DRG-8180 Table 3
label | Constructor - H
label | CPS - R
label | Verifying Records - Monitoring Report
holdpoint | AUTHORITY HOLDPOINT
checkpoint | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
textbox | Contractor's Rep Name:
textbox | Engineer's Rep. Name:
date | Date:
signoff | Add Signature
checklist | ITP - Excavation and Support - 5.0 Post construction | itp |  |  |  |  | ITP - Excavation and Support - 5.0 Post construction Rev 1
section | 5.0 Post construction
checkpoint | 5.1 - Red Line Mark Up Drawings
label | Description - As-built drawings to capture any deviation from the IFC drawings.
label | Method/Description - Submit
label | Test frequency - At Completion
label | Constructor - H
label | CPS - R
label | Verifying Records - Red Line Mark Up Drawings
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5.2 - As-built Drawings
label | Description - As-built drawings to capture any deviation from the IFC drawings.
label | Specifications and Standards - Quality Management Plan
label | Method/Description - Submit
label | Test frequency - At Completion
label | Constructor - H
label | CPS - R
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5.3 - Tunnel Operation and maintenance report
label | Description - Tunnel Operation and maintenance report to detail the maintenance frequency and maintenance procedures.
label | Method/Description - Submit
label | Test frequency - At Completion
label | Constructor - H
label | CPS - R
label | IOM - R
label | Verifying Records - Tunnel operation and maintenance report
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5.4 - Final Handover Package
label | Description - Collation of all QA, as-built drawings,as-built records, installation records, PTT, testing and monitoring documentation. Provision of asset management operation and maintenance report to NZTA, including Producer Statements.
label | Specifications and Standards - Quality Management Plan
label | Method/Description - Submit
label | Test frequency - At Completion
label | Constructor - H
label | CPS - R
label | IOM - R
label | Verifying Records - As-built drawings, installation record, as built records, PTT, testing results, monitoring documentation, operation and maintenance report, Producer Statements
holdpoint | AUTHORITY HOLDPOINT
checkpoint | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
textbox | Contractor's Rep Name:
textbox | Engineer's Rep. Name:
date | Date:
signoff | Add Signature