## LQS Lot Breakdown
Activity | Location | Inspection Test Plan | Lot Number
Enabling Works | General | LQS-QA-6000 - ITP - Compliance Record | 1.1.1 - Southern Crane Pad
Enabling Works | General | LQS-QA-6000 - ITP - Compliance Record | 1.1.2 - Diversion Culvert + Inlet
Enabling Works | General | LQS-QA-6092 - ITP - Water Services | 1.1.3 - Salt Marsh Lane - MDPE 63mm
Three Waters | Water | LQS-QA-6092 - ITP - Water Services | 2.2.1 - Pipeline 1A - HDPE 355mm
Three Waters | Water | LQS-QA-6092 - ITP - Water Services | 2.2.3 - Pipeline 1B - HDPE 560mm
Three Waters | Water | LQS-QA-6092 - ITP - Water Services | 2.2.2 - Pipeline 1C - HDPE 450mm
Three Waters | Water | LQS-QA-6092 - ITP - Water Services | 2.2.4 - Pipeline 2 - HDPE 450mm
Three Waters | Water | LQS-QA-6092 - ITP - Water Services | 2.2.5 - Pipeline 3A - HDPE 450mm
Three Waters | Water | LQS-QA-6092 - ITP - Water Services | 2.1.6 - Pipeline 3B - PVC 150mm
Three Waters | Wastewater | LQS-QA-6092 - ITP - Water Services | 2.2.1 - Pipeline 5A - HDPE 63mm
Three Waters | Wastewater | LQS-QA-6092 - ITP - Water Services | 2.2.2 - Pipeline 5B - HDPE 180mm
Three Waters | Wastewater | LQS-QA-6092 - ITP - Water Services | 2.2.3 - Pipeline 5C - HDPE 75mm
Three Waters | Wastewater | LQS-QA-6092 - ITP - Water Services | 2.2.4 - Pipeline 8 - PVC 150mm + PVC 50mm Duct
Three Waters | Wastewater | LQS-QA-6092 - ITP - Water Services | 2.2.5 - Pipeline 9 - HDPE 90mm
Three Waters | Stormwater | LQS-QA-6007 - ITP - Drainage Installation | 2.3.1 - Pipeline 7 - SW DN600 RCP
Three Waters | Stormwater | LQS-QA-6007 - ITP - Drainage Installation | 2.3.2 - Pipeline 7 - SW DN900 RCP
Three Waters | Manholes, Structures & Sumps | LQS-QA-6006 - ITP-Insitu Concrete | 2.4.1 - Odour Unit
Three Waters | Manholes, Structures & Sumps | LQS-QA-6000 - ITP - Compliance Record | 2.4.2 - Odour Unit Comissioning
MSE Walls | Headingly Lane | LQS-QA-6013-ITP- MSE Retaining Wall | 3.1.1 - Geofabric MSE Wall
MSE Walls | Lower Queen St (Left) | LQS-QA-6013-ITP- MSE Retaining Wall | 3.2.1 - Geofabric MSE Wall
MSE Walls | Lower Queen St (Right) | LQS-QA-6013-ITP- MSE Retaining Wall | 3.2.1 - Geofabric MSE Wall
Temporary Bridge | Abutment A | LQS-QA-6031 - ITP-Bored Pile | 4.1.1 - Abutment Piling
Temporary Bridge | Abutment A | LQS-QA-6006 - ITP-Insitu Concrete | 4.1.2 - Pour 1 - Abutment Seat
Temporary Bridge | Abutment A | LQS-QA-6006 - ITP-Insitu Concrete | 4.1.3 - Pour 2 - Abutment headwall
Temporary Bridge | Pier B | LQS-QA-6031 - ITP-Bored Pile | 4.3.1 - Pier Piling
Temporary Bridge | Pier B | LQS-QA-6006 - ITP-Insitu Concrete | 4.3.2 - Pour 1 - Pier Seat
Temporary Bridge | Pier B | LQS-QA-6006 - ITP-Insitu Concrete | 4.3.3 - Pour 2 - Abutment headwall
Temporary Bridge | Pier C | LQS-QA-6031 - ITP-Bored Pile | 4.4.1 - Pier Piling
Temporary Bridge | Pier C | LQS-QA-6006 - ITP-Insitu Concrete | 4.4.2 - Pour 1 - Pier Seat
Temporary Bridge | Pier C | LQS-QA-6006 - ITP-Insitu Concrete | 4.4.3 - Pour 2 - Abutment headwall
Temporary Bridge | Abutment D | LQS-QA-6031 - ITP-Bored Pile | 4.4.1 - Abutment Piling
Temporary Bridge | Abutment D | LQS-QA-6006 - ITP-Insitu Concrete | 4.4.2 - Pour 1 - Abutment Seat
Temporary Bridge | Abutment D | LQS-QA-6006 - ITP-Insitu Concrete | 4.4.3 - Pour 2 - Abutment headwall
Temporary Bridge | Temporary Bridge Deck | LQS-QA-6000 - ITP - Compliance Record | 4.4.1 - Deck Placement
Temporary Bridge | Temporary Bridge Deck | LQS-QA-6000 - ITP - Compliance Record | 4.4.2 - Temp Bridge Comissioning
Permanent Bridge | Abutment A (Left) | LQS-QA-6031 - ITP-Bored Pile | 5.1.1 - Abutment Piling
Permanent Bridge | Abutment A (Left) | LQS-QA-6006 - ITP-Insitu Concrete | 5.1.2 - Pour 1 - Abutment Seat
Permanent Bridge | Abutment A (Left) | LQS-QA-6006 - ITP-Insitu Concrete | 5.1.3 - Pour 2 - Abutment headwall
Permanent Bridge | Abutment A (Left) | LQS-QA-6006 - ITP-Insitu Concrete | 5.1.4 - Pour 3 - Left Settlement Slab
Permanent Bridge | Pier B (Left) | LQS-QA-6031 - ITP-Bored Pile | 5.1.1 - Pier Piling
Permanent Bridge | Pier B (Left) | LQS-QA-6006 - ITP-Insitu Concrete | 5.1.2 - Pour 1 - Pier Seat
Permanent Bridge | Pier B (Left) | LQS-QA-6006 - ITP-Insitu Concrete | 5.1.3 - Pour 2 - Abutment headwall
Permanent Bridge | Pier C (Right) | LQS-QA-6031 - ITP-Bored Pile | 5.3.1 - Pier Piling
Permanent Bridge | Pier C (Right) | LQS-QA-6006 - ITP-Insitu Concrete | 5.3.2 - Pour 1 - Pier Seat
Permanent Bridge | Pier C (Right) | LQS-QA-6006 - ITP-Insitu Concrete | 5.3.3 - Pour 2 - Abutment headwall
Permanent Bridge | Abutment D (Right) | LQS-QA-6031 - ITP-Bored Pile | 5.4.1 - Abutment Piling
Permanent Bridge | Abutment D (Right) | LQS-QA-6006 - ITP-Insitu Concrete | 5.4.2 - Pour 1 - Abutment Seat
Permanent Bridge | Abutment D (Right) | LQS-QA-6006 - ITP-Insitu Concrete | 5.3.5 - Pour 3 - Right Settlement Slab
Permanent Bridge | Span 1 | LQS-QA-6049 - ITP-Precast Concrete | 5.5.1 - Pre-Cast Beam
Permanent Bridge | Span 1 | LQS-QA-6040 - ITP-Precast Installation | 5.5.2 - Pre-Cast Beam Installation
Permanent Bridge | Span 2 | LQS-QA-6049 - ITP-Precast Concrete | 5.5.1 - Pre-Cast Beam
Permanent Bridge | Span 2 | LQS-QA-6040 - ITP-Precast Installation | 5.5.2 - Pre-Cast Beam Installation
Permanent Bridge | Span 3 | LQS-QA-6049 - ITP-Precast Concrete | 5.5.1 - Pre-Cast Beam
Permanent Bridge | Span 3 | LQS-QA-6040 - ITP-Precast Installation | 5.5.2 - Pre-Cast Beam Installation
Permanent Bridge | Hand Rails | LQS-QA-6000 - ITP - Compliance Record | 5.5.1 - Road Barrier Installation
Permanent Bridge | Hand Rails | LQS-QA-6000 - ITP - Compliance Record | 5.5.1 - Hand Rail Installation
Electrical & Telecom | Power | LQS-QA-6090 - ITP - Service Installation | 6.1.1 - Pipeline 8 - Power PVC 100mm
Electrical & Telecom | Power | LQS-QA-6090 - ITP - Service Installation | 6.1.2 - McShane - Streetlight
Electrical & Telecom | Power | LQS-QA-6090 - ITP - Service Installation | 6.1.3 - Flow Meter Duct - LQS
Electrical & Telecom | Telecom | LQS-QA-6090 - ITP - Service Installation | 6.2.1 - Ductline 6
Earthworks | Structural Fill | LQS-QA-6004 - ITP - Earthworks Bulk Fill | 7.1.1 - Eastern Abutment
Earthworks | Structural Fill | LQS-QA-6004 - ITP - Earthworks Bulk Fill | 7.1.2 - Western Abutment
Earthworks | Bulk Earthworks | LQS-QA-6000 - ITP - Compliance Record | 7.2.1 - Downstream
Earthworks | Bulk Earthworks | LQS-QA-6000 - ITP - Compliance Record | 7.2.2 - Upstream
Earthworks | River Protection | LQS-QA-6000 - ITP - Compliance Record | 7.3.1 - Rip Rap
Pavements | Temporary Road | LQS-QA-6069 - ITP - Subgrade and Basecourse | 8.1.1 - Bypass - Basecourse
Pavements | Temporary Road | LQS-QA-6076 - ITP - Asphalt - Surfacing | 8.1.2 - Bypass - Surfacing
Pavements | East Lower Queen St | LQS-QA-6069 - ITP - Subgrade and Basecourse | 8.2.1 - Pavements
Pavements | East Lower Queen St | LQS-QA-6076 - ITP - Asphalt - Surfacing | 8.2.1 - Asphalt
Pavements | Bridge Lower Queen St | LQS-QA-6076 - ITP - Asphalt - Surfacing | 8.3.3 - Asphalt
Pavements | West Lower Queen St | LQS-QA-6069 - ITP - Subgrade and Basecourse | 8.4.1 - Pavements
Pavements | West Lower Queen St | LQS-QA-6076 - ITP - Asphalt - Surfacing | 8.4.3 - Asphalt