## Master Tracker
THIESS HARMONY Alliance - QA ITP Master Tracker
| Project |  | EVA Copper Mine Project
| Client |  | Harmony
| Contract Number |  | EVAMP001
| Lot Register |  | Lot Register Link
| ITP1 - C&G |  |  | ITP2 - Topsoil Strip |  |  | ITP3 - Subgrade Prep. |  |  | ITP4 - RCP Install |  |  | ITP5 - |  |  | ITP 6 - |  |  | ITP7 - |  |  | ITP8 - Emb. Con. |  |  | ITP9 - Unbound Gran. Pave. |  |  | ITP10 - |  |  | ITP11 - |  |  | ITP12 - |  |  | ITP13 - |  |  | ITP14 - |  |  | ITP15 - |  |  | ITP16 - |  |  | ITP17 - |  |  | ITP18 -
| % Completion |  |  | % Completion |  |  | % Completion |  |  | % Completion |  |  | % Completion |  |  | % Completion |  |  | % Completion |  |  | % Completion |  |  | % Completion |  |  | % Completion |  |  | % Completion |  |  | % Completion |  |  | % Completion |  |  | % Completion |  |  | % Completion |  |  | % Completion |  |  | % Completion |  |  | % Completion
| Code | Sub. | App. | Code | Sub. | App. | Code | Sub. | App. | Code | Sub. | App. | Code | Sub. | App. | Code | Sub. | App. | Code | Sub. | App. | Code | Sub. | App. | Code | Sub. | App. | Code | Sub. | App. | Code | Sub. | App. | Code | Sub. | App. | Code | Sub. | App. | Code | Sub. | App. | Code | Sub. | App. | Code | Sub. | App. | Code | Sub. | App. | Code | Sub. | App.
| MAR | 0% | 0% | MAR | 0% | 0% | MAR | 0% | 0% | MAR | 0% | 0% | MAR |  |  | MAR |  |  | MAR |  |  | MAR | 0% | 0% | MAR | 0% | 0% | MAR |  |  | MAR |  |  | MAR |  |  | MAR |  |  | MAR |  |  | MAR |  |  | MAR |  |  | MAR |  |  | MAR
| VAR | 0% | 0% | VAR | 0% | 0% | VAR | 0% | 0% | VAR | 0% | 0% | VAR |  |  | VAR |  |  | VAR |  |  | VAR | 0% | 0% | VAR | 0% | 0% | VAR |  |  | VAR |  |  | VAR |  |  | VAR |  |  | VAR |  |  | VAR |  |  | VAR |  |  | VAR |  |  | VAR
| TN | 0% | 0% | TN | 0% | 0% | TN | 0% | 0% | TN | 0% | 0% | TN |  |  | TN |  |  | TN |  |  | TN | 0% | 0% | TN | 0% | 0% | TN |  |  | TN |  |  | TN |  |  | TN |  |  | TN |  |  | TN |  |  | TN |  |  | TN |  |  | TN
| VP | 0% | 0% | VP | 0% | 0% | VP | 0% | 0% | VP | 0% | 0% | VP |  |  | VP |  |  | VP |  |  | VP | 0% | 0% | VP | 0% | 0% | VP |  |  | VP |  |  | VP |  |  | VP |  |  | VP |  |  | VP |  |  | VP |  |  | VP |  |  | VP
| PP | 0% | 0% | PP | 0% | 0% | PP | 0% | 0% | PP | 0% | 0% | PP |  |  | PP |  |  | PP |  |  | PP | 0% | 0% | PP | 0% | 0% | PP |  |  | PP |  |  | PP |  |  | PP |  |  | PP |  |  | PP |  |  | PP |  |  | PP |  |  | PP
| Q |  |  | Q |  |  | Q |  |  | Q |  |  | Q |  |  | Q |  |  | Q |  |  | Q |  |  | Q |  |  | Q |  |  | Q |  |  | Q |  |  | Q |  |  | Q |  |  | Q |  |  | Q |  |  | Q |  |  | Q
ITP1 Clear & Grub | MAR001 |  | MAR002 |  | MAR003 |  | MAR004 |  | MAR005 |  | MAR006 |  | MAR007 |  | MAR008 |  | MAR009 |  | MAR010 |  | MAR011 |  | MAR012 |  | MAR013 |  | MAR014 |  | MAR015 |  | MAR016 |  | MAR017 |  | VAR001 |  | VAR002 |  | TN001 |  | VP001 |  | PP001 |  | PP002 |  | PP003 |  | PP004 |  | PP005 |  | PP006
| Sub. | App. | Sub. | App. | Sub. | App. | Sub. | App. | Sub. | App. | Sub. | App. | Sub. | App. | Sub. | App. | Sub. | App. | Sub. | App. | Sub. | App. | Sub. | App. | Sub. | App. | Sub. | App. | Sub. | App. | Sub. | App. | Sub. | App. | Sub. | App. | Sub. | App. | Sub. | App. | Sub. | App. | Sub. | App. | Sub. | App. | Sub. | App. | Sub. | App. | Sub. | App. | Sub. | App.
GC1.1
GC1.2
GC1.3
GC1.4
GC1.5
GC1.6
GC1.7
GC1.8
GC1.9
GC1.10
GC2.11
GC2.12
GC2.13
GC2.14
GC3.15
Total | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
ITP2 Top. Strip | MAR001 |  | MAR002 |  | MAR003 |  | MAR004 |  | MAR005 |  | MAR006 |  | MAR007 |  | MAR008 |  | MAR009 |  | MAR010 |  | MAR011 |  | MAR012 |  | MAR013 |  | MAR014 |  | MAR015 |  | MAR016 |  | MAR017 |  | VAR001 |  | VAR002 |  | TN001 |  | VP001 |  | PP001 |  | PP002 |  | PP003 |  | PP004 |  | PP005 |  | PP006
| Sub. | App. | Sub. | App. | Sub. | App. | Sub. | App. | Sub. | App. | Sub. | App. | Sub. | App. | Sub. | App. | Sub. | App. | Sub. | App. | Sub. | App. | Sub. | App. | Sub. | App. | Sub. | App. | Sub. | App. | Sub. | App. | Sub. | App. | Sub. | App. | Sub. | App. | Sub. | App. | Sub. | App. | Sub. | App. | Sub. | App. | Sub. | App. | Sub. | App. | Sub. | App. | Sub. | App.
TS1.1
TS1.2
TS1.3
TS1.4
TS1.5
TS1.6
TS2.7
TS2.8
TS2.9
TS3.10
Total | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
ITP3 Sub. Prep. | MAR001 |  | MAR002 |  | MAR003 |  | MAR004 |  | MAR005 |  | MAR006 |  | MAR007 |  | MAR008 |  | MAR009 |  | MAR010 |  | MAR011 |  | MAR012 |  | MAR013 |  | MAR014 |  | MAR015 |  | MAR016 |  | MAR017 |  | VAR001 |  | VAR002 |  | TN001 |  | VP001 |  | PP001 |  | PP002 |  | PP003 |  | PP004 |  | PP005 |  | PP006
| Sub. | App. | Sub. | App. | Sub. | App. | Sub. | App. | Sub. | App. | Sub. | App. | Sub. | App. | Sub. | App. | Sub. | App. | Sub. | App. | Sub. | App. | Sub. | App. | Sub. | App. | Sub. | App. | Sub. | App. | Sub. | App. | Sub. | App. | Sub. | App. | Sub. | App. | Sub. | App. | Sub. | App. | Sub. | App. | Sub. | App. | Sub. | App. | Sub. | App. | Sub. | App. | Sub. | App.
SP1.1
SP1.2
SP1.3
SP1.4
SP1.5
SP1.6
SP2.7
SP2.8
SP2.9
SP2.10
SP3.11
Total | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
ITP4 RCP Ins. | MAR001 |  | MAR002 |  | MAR003 |  | MAR004 |  | MAR005 |  | MAR006 |  | MAR007 |  | MAR008 |  | MAR009 |  | MAR010 |  | MAR011 |  | MAR012 |  | MAR013 |  | MAR014 |  | MAR015 |  | MAR016 |  | MAR017 |  | VAR001 |  | VAR002 |  | TN001 |  | VP001 |  | PP001 |  | PP002 |  | PP003 |  | PP004 |  | PP005 |  | PP006
| Sub. | App. | Sub. | App. | Sub. | App. | Sub. | App. | Sub. | App. | Sub. | App. | Sub. | App. | Sub. | App. | Sub. | App. | Sub. | App. | Sub. | App. | Sub. | App. | Sub. | App. | Sub. | App. | Sub. | App. | Sub. | App. | Sub. | App. | Sub. | App. | Sub. | App. | Sub. | App. | Sub. | App. | Sub. | App. | Sub. | App. | Sub. | App. | Sub. | App. | Sub. | App. | Sub. | App.
RCP1.1
RCP1.2
RCP1.3
RCP1.4
RCP1.5
RCP1.6
RCP2.7
RCP2.8
RCP2.9
RCP2.10
RCP2.11
RCP2.12
RCP2.13
RCP2.14
RCP3.15
Total | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
ITP8 Emb. Con. | MAR001 |  | MAR002 |  | MAR003 |  | MAR004 |  | MAR005 |  | MAR006 |  | MAR007 |  | MAR008 |  | MAR009 |  | MAR010 |  | MAR011 |  | MAR012 |  | MAR013 |  | MAR014 |  | MAR015 |  | MAR016 |  | MAR017 |  | VAR001 |  | VAR002 |  | TN001 |  | VP001 |  | PP001 |  | PP002 |  | PP003 |  | PP004 |  | PP005 |  | PP006
| Sub. | App. | Sub. | App. | Sub. | App. | Sub. | App. | Sub. | App. | Sub. | App. | Sub. | App. | Sub. | App. | Sub. | App. | Sub. | App. | Sub. | App. | Sub. | App. | Sub. | App. | Sub. | App. | Sub. | App. | Sub. | App. | Sub. | App. | Sub. | App. | Sub. | App. | Sub. | App. | Sub. | App. | Sub. | App. | Sub. | App. | Sub. | App. | Sub. | App. | Sub. | App. | Sub. | App.
EC1.1
EC1.2
EC1.3
EC1.4
EC2.5
EC2.6
EC2.7
EC2.8
EC2.9
EC2.10
EC3.11
Total | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
ITP9 Pavements | MAR001 |  | MAR002 |  | MAR003 |  | MAR004 |  | MAR005 |  | MAR006 |  | MAR007 |  | MAR008 |  | MAR009 |  | MAR010 |  | MAR011 |  | MAR012 |  | MAR013 |  | MAR014 |  | MAR015 |  | MAR016 |  | MAR017 |  | VAR001 |  | VAR002 |  | TN001 |  | VP001 |  | PP001 |  | PP002 |  | PP003 |  | PP004 |  | PP005 |  | PP006
| Sub. | App. | Sub. | App. | Sub. | App. | Sub. | App. | Sub. | App. | Sub. | App. | Sub. | App. | Sub. | App. | Sub. | App. | Sub. | App. | Sub. | App. | Sub. | App. | Sub. | App. | Sub. | App. | Sub. | App. | Sub. | App. | Sub. | App. | Sub. | App. | Sub. | App. | Sub. | App. | Sub. | App. | Sub. | App. | Sub. | App. | Sub. | App. | Sub. | App. | Sub. | App. | Sub. | App.
GP1.1
GP1.2
GP1.3
GP1.4
GP1.5
GP1.6
GP1.7
GP2.8
GP2.9
GP2.10
GP2.11
GP2.12
GP3.13
Total | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
ITPX Road Signs | MAR001 |  | MAR002 |  | MAR003 |  | MAR004 |  | MAR005 |  | MAR006 |  | MAR007 |  | MAR008 |  | MAR009 |  | MAR010 |  | MAR011 |  | MAR012 |  | MAR013 |  | MAR014 |  | MAR015 |  | MAR016 |  | MAR017 |  | VAR001 |  | VAR002 |  | TN001 |  | VP001 |  | PP001 |  | PP002 |  | PP003 |  | PP004 |  | PP005 |  | PP006
| Sub. | App. | Sub. | App. | Sub. | App. | Sub. | App. | Sub. | App. | Sub. | App. | Sub. | App. | Sub. | App. | Sub. | App. | Sub. | App. | Sub. | App. | Sub. | App. | Sub. | App. | Sub. | App. | Sub. | App. | Sub. | App. | Sub. | App. | Sub. | App. | Sub. | App. | Sub. | App. | Sub. | App. | Sub. | App. | Sub. | App. | Sub. | App. | Sub. | App. | Sub. | App. | Sub. | App.
RS1.1
RS1.2
RS1.3
RS1.4
RS1.5
RS1.6
RS1.7
RS1.8
RS1.9
RS1.10
RS2.11
RS2.12
RS2.13
RS3.14
Total | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%

## ITP-Pre-construction
THIESS HARMONY Alliance - QA Register-ITP1 Pre-Construction
| Project |  | EVA Copper Mine Project |  |  |  |  | Total Hold Points |  | 18 | Total Witness Points |  | 18
| ITP Folder |  | EVAMP001-THS-QA-ITP-0001 |  |  |  |  | Remaining | #REF! |  | Remaining | 18
| Client |  | Harmony |  |  |  |  | Complete | #REF! | #REF! | Complete | 0 | 0%
| Contract Number |  | EVAMP001 |  |  |  |  | Incomplete | #REF! |  | Incomplete | #REF!
Master Tracker Code | Inspection / Test Point | Responsibility | Test Method | Conformance Criteria | Freguency | Thiess HP/WP Check | Inspector HP/WP Sign Off | AWP1A |  |  | AWP1A-MAR |  |  | AWP1A-VAR |  |  | AWP1A-Village Pad |  |  | AWP1B
[8 empty] | Complete | Date | Folder Link | Complete | Date | Folder Link | Complete | Date | Folder Link | Complete | Date | Folder Link | Complete | Date | Folder Link | Complete | Date | Folder Link | Complete | Date | Folder Link | Complete | Date | Folder Link | Complete | Date | Folder Link | Complete | Date | Folder Link | Complete | Date | Folder Link | Complete | Date | Folder Link | Complete | Date | Folder Link | Complete | Date | Folder Link | Complete | Date | Folder Link | Complete | Date | Folder Link | Complete | Date | Folder Link | Complete | Date | Folder Link | Complete | Date | Folder Link | Complete | Date | Folder Link | Complete | Date | Folder Link | Complete | Date | Folder Link | Complete | Date | Folder Link | Complete | Date | Folder Link | Complete | Date | Folder Link | Complete | Date | Folder Link | Complete | Date | Folder Link
PC1.1 | Construction Management Plan | ENG | Visual | Approved Construction Management Plan saved in Construction Team Sharepoint and detailed in register | Prior to works | HP | WP | Yes | [11 empty] | No
PC1.2 | Lot Register/ WBS | ENG | Visual | Lot register saved in Construction Team Sharepoint and detailed in register | Prior to works | WP | WP | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No
PC1.3 | Construction procedures | ENG | Visual | Construction procedures saved in Construction Team Sharepoint and detailed in register | Prior to works | HP | WP | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No
PC1.4 | Excavation permit | ENG | Visual | Approved Excavation Permit saved in Construction Team Sharepoint and detailed in register | Prior to works | HP | WP | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No
PC1.5 | Dial before you dig check | ENG | Visual | In date DBYD certificate saved in Construction Team Sharepoint and detailed in register | Prior to works | HP | WP | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No
PC1.6 | Traffic control plan | ENG | Visual | Traffic control plansaved in Construction Team Sharepoint and detailed in register | Prior to works | HP | WP | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No
PC1.7 | Inspection Test Plan (ITP) submitted and approved | ENG | Visual | Approved ITPs relevant to the works saved in Construction Team Sharepoint and detailed in register | Prior to works | HP | WP | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No
PC1.8 | IFC drawings | ENG | Visual | IFC drawings and revisions transmitted from theThiess Technical Services team and detailed in register | Prior to works | HP | WP | No |  |  | No |  |  | No |  |  | No |  |  | No
PC1.9 | Survey natural surface | SURV | Field | Survey pick up of work area and digital file saved in Construction Team Sharepoint and detailed in register. Surface area shape file created and uploaded to Qfield | Prior to works | HP | HP | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No
PC1.10 | Erosion and sediment control plan | ENV ENG | Visual | Approved Erosion and Sediment Control Plan saved in Construction Team Sharepoint and detailed in register | Prior to works | HP | HP | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No
PC1.11 | Approved stockpile locations | ENG | Visual | All stockpile locations to be nominated and approved prior to commencement of activity. Topsoil register to be maintained with information on topsoil volumes and stockpile locations. | Prior to works | HP | HP | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No
PC1.12 | Embankment fill materials | ENG | Visual | Embankment fill materials have been approved for use and in accordance with the requirements in the specification. General fill material as per Table A3-1 Cut/fill material properties in the specification: Less than 30% passing 0.075mm sieve Liquid limit 20% to 60% Soaked CBR = or >3% (STD compaction @ OMC) 1 test per 5,000 m3 Subgrade replacement material CBR10. Select Fill as per the details in Table A3-2 Select fill material properties & Table A3-3 Select fill grading envelope. | Prior to works | HP | WP | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No
PC1.13 | Fauna Spotter Catcher (FSC) Pre-Clearance Survey | ENV | Visual | FSC pre-clearance survey completed only if within 2 weeks of construction saved in Construction Team Sharepoint and detailed in register | Prior to works | HP | HP | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No
PC1.14 | Cultural Heritage(CH) Clearance Survey | CH | Visual | Approved CH Clearance Survey saved in Construction Team Sharepoint and detailed in register Areas of CH clearly demarcated | Prior to works | HP | HP | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No
PC1.15 | Ground Disturbance Permit (GDP) | ENV ENG | Visual | Approved GDP saved in Construction Team Sharepoint and detailed in register | Prior to works | HP | HP | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No
PC1.16 | GDP survey set out | SURV | Field | Area of works pegged and clearly defined to GDP. Clearing pegs installed at nominal intervals to ensure no over-clearing . | Prior to works | HP | HP | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No
PC1.17 | Survey of pegs to confirm correct GDP survey set out | ENV | Visual | Pegs to be surveyed and sent back to the engineer. This is then to be confirmed by the environmental team | Prior to works | HP | WP | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No
PC1.18 | Mandatory GDP Pre-Clearing walk | SUP OP ENG ENV | Field | Walkthrough with FSC, Supervisor, Surveyor, PM or Senior Engineer, operations that will be undertaking the clearing | Prior to works | HP | WP | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No
PC1.19 | QA close out | ENG | Visual | Works completed and update ITP/Lot register/MDR and close out of GDP | As required | HP | HP | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No
[11 empty] | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No

## ITP1-C&G
THIESS HARMONY Alliance - QA Register-ITP1 Clear & Grub
| Project |  | EVA Copper Mine Project | [5 empty] | Total Hold Points |  | #REF! | Total Witness Points |  | #REF!
| ITP Folder |  | EVAMP001-THS-QA-ITP-0001 | [5 empty] | Remaining | #REF! |  | Remaining | #REF!
| Client |  | Harmony | [5 empty] | Complete | #REF! | #REF! | Complete | 0 | #REF!
| Contract Number |  | EVAMP001 | [5 empty] | Incomplete | #REF! |  | Incomplete | #REF!
Master Tracker Code | Inspection / Test Point | Responsibility | Test Method | Conformance Criteria | Freguency | Link to ITP | Thiess HP/WP Check | Inspector HP/WP Sign Off | MAR001 |  |  | MAR002 |  |  | MAR003 |  |  | MAR004 |  |  | MAR005 |  |  | MAR006 |  |  | MAR007 |  |  | MAR008 |  |  | MAR009 |  |  | MAR010 |  |  | MAR011 |  |  | MAR012 |  |  | MAR013 |  |  | MAR014 |  |  | MAR015 |  |  | MAR016 |  |  | MAR017 |  |  | VAR001 |  |  | VAR002 |  |  | TN001 |  |  | VP001 |  |  | PP001 |  |  | PP002 |  |  | PP003 |  |  | PP004 |  |  | PP005 |  |  | PP006
[9 empty] | Complete | Date | Folder Link | Complete | Date | Folder Link | Complete | Date | Folder Link | Complete | Date | Folder Link | Complete | Date | Folder Link | Complete | Date | Folder Link | Complete | Date | Folder Link | Complete | Date | Folder Link | Complete | Date | Folder Link | Complete | Date | Folder Link | Complete | Date | Folder Link | Complete | Date | Folder Link | Complete | Date | Folder Link | Complete | Date | Folder Link | Complete | Date | Folder Link | Complete | Date | Folder Link | Complete | Date | Folder Link | Complete | Date | Folder Link | Complete | Date | Folder Link | Complete | Date | Folder Link | Complete | Date | Folder Link | Complete | Date | Folder Link | Complete | Date | Folder Link | Complete | Date | Folder Link | Complete | Date | Folder Link | Complete | Date | Folder Link | Complete | Date | Folder Link
GC1.1 | Underlying lot & ITP signed off and conforming | ENG | Visual | Pre-construction lots closed out | As required | PC1.19 |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No
GC1.2 | Ground Disturbance Permit (GDP) | ENV ENG | Visual | Approved GDP saved in Construction Team Sharepoint and detailed in register | Prior to works (Check if this has already been completed at ITP Pre-construction stage) | PC1.15 | HP | HP | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No
GC1.3 | Cultural Heritage(CH) Clearance Survey | CH | Visual | Approved CH Clearance Survey saved in Construction Team Sharepoint and detailed in register Areas of CH clearly demarcated | Prior to works (Check if this has already been completed at ITP Pre-construction stage) | PC1.14 | HP | HP | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No
GC1.4 | GDP survey set out | SURV | Field | Area of works pegged and clearly defined to GDP. Clearing pegs installed at nominal intervals to ensure no over-clearing . | Prior to works (Check if this has already been completed at ITP Pre-construction stage) | PC1.16 | HP | WP | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No
GC1.5 | Survey of pegs to confirm correct GDP survey set out | ENV | Visual | Pegs to be surveyed and sent back to the engineer. This is then to be confirmed by the environmental team | Prior to works (Check if this has already been completed at ITP Pre-construction stage) | PC1.17 | HP | WP | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No
GC1.6 | Survey natural surface | SURV | Field | Check survey pick up of work area and digital file saved in Construction Team Sharepoint and detailed in register. Surface area shape file created and uploaded to Qfield | Prior to works (Check if this has already been completed at ITP Pre-construction stage) | PC1.9 | HP | HP | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No
GC1.7 | Fauna Spotter Catcher (FSC) Pre-Clearance Survey | ENG | Visual | FSC pre-clearance survey completed within 2 weeks of construction. Habitat vegetation, threatened species demarcated. | Prior to works (Check if this has already been completed at ITP Pre-construction stage) | PC1.13 | HP | HP | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No
GC1.8 | Mandatory GDP Pre-Clearing walk | SUP OP ENG ENV | Field | Walkthrough with FSC, Supervisor, Surveyor, PM or Senior Engineer, operations that will be undertaking the clearing | Prior to works (Check if this has already been completed at ITP Pre-construction stage) | PC1.18 | HP | WP | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No
GC1.9 | Clearing of vegetation | SUP | Visual | FSC individual on site at works during clearing operations. Habitat vegetation, threatened species and cultural heritage areas demarcated | As required | - | HP | WP | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No
GC1.10 | Stockpile Cleared Vegetation | SUP | Visual | Cleared vegetation loaded and hauled to approved stockpile location | As required | PC1.11 | HP | WP | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No
GC1.11 | Erosion and sediment control | SUP | Visual | Erosion and sediment control measures to be implemented whereever possible after clearing has been completed. | After clearing | PC1.10 | HP | HP | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No
GC1.12 | QA close out | ENG | Visual | Works completed and update ITP/Lot register/MDR and close out of GDP | As required | - | HP | HP | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No

## ITP2-Top. Strip
THIESS HARMONY Alliance - QA Register-ITP2 Topsoil Stripping
| Project |  | EVA Copper Mine Project | [5 empty] | Total Hold Points |  | #REF! | Total Witness Points |  | #REF!
| ITP Folder |  | EVAMP001-THS-QA-ITP-0002 | [5 empty] | Remaining | #REF! |  | Remaining | #REF!
| Client |  | Harmony | [5 empty] | Complete | #REF! | #REF! | Complete | 0 | #REF!
| Contract Number |  | EVAMP001 | [5 empty] | Incomplete | #REF! |  | Incomplete | #REF!
Master Tracker Code | Inspection / Test Point | Responsibility | Test Method | Conformance Criteria | Freguency | Link to ITP | Thiess HP/WP Check | Inspector HP/WP Sign Off | MAR001 |  |  | MAR002 |  |  | MAR003 |  |  | MAR004 |  |  | MAR005 |  |  | MAR006 |  |  | MAR007 |  |  | MAR008 |  |  | MAR009 |  |  | MAR010 |  |  | MAR011 |  |  | MAR012 |  |  | MAR013 |  |  | MAR014 |  |  | MAR015 |  |  | MAR016 |  |  | MAR017 |  |  | VAR001 |  |  | VAR002 |  |  | TN001 |  |  | VP001 |  |  | PP001 |  |  | PP002 |  |  | PP003 |  |  | PP004 |  |  | PP005 |  |  | PP006
[9 empty] | Complete | Date | Folder Link | Complete | Date | Folder Link | Complete | Date | Folder Link | Complete | Date | Folder Link | Complete | Date | Folder Link | Complete | Date | Folder Link | Complete | Date | Folder Link | Complete | Date | Folder Link | Complete | Date | Folder Link | Complete | Date | Folder Link | Complete | Date | Folder Link | Complete | Date | Folder Link | Complete | Date | Folder Link | Complete | Date | Folder Link | Complete | Date | Folder Link | Complete | Date | Folder Link | Complete | Date | Folder Link | Complete | Date | Folder Link | Complete | Date | Folder Link | Complete | Date | Folder Link | Complete | Date | Folder Link | Complete | Date | Folder Link | Complete | Date | Folder Link | Complete | Date | Folder Link | Complete | Date | Folder Link | Complete | Date | Folder Link | Complete | Date | Folder Link
TS1.1 | Underlying lot & ITP signed off and conforming | ENG | Visual | Clear & Grubbing ITP closed out | Prior to works | GC1.12 |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No
TS1.2 | Survey Set out | Surv | Field | Areas of work to be set out by surveyor and/or models in plant | As required | - | HP | WP | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No
TS1.3 | Strip topsoil, load & haul to approved stockpile location | ENG | Visual | Provisional depth of topsoil strip shall be 100 mm unless shown otherwise on the drawings. Stripped topsoil loaded and hauled to approved stockpile location. Stockpile locations located minimum 40m from watercourses and not exceed 2m in height. Native seeding of topsoil stockpiles as agreed with Company. | As required | PC1.11 | HP | WP | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No
TS1.4 | Topsoil location, destination and quantity catalogued. | ENG | Visual | Topsoil register to be maintained with information on topsoil volumes and stockpile locations | As required | PC1.11 | HP | HP | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No
TS1.5 | Surface level check and survey pick-up | SURV | Survey / Field Test | Stripped surface level picked up as per Table 10 C15 (DXF file format, volume calculated and filr saved in Construction Team Sharepoint and detailed in register | As required | - | HP | HP | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No
TS1.6 | QA close out | ENG | Visual | GDP permits closed. ITP closed. Approved MDR. | As required | - | HP | HP | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No

## ITP3-Subgrade. FoundationPrep
THIESS HARMONY Alliance - QA Register-ITP3 Subgrade/Foundation Preparation
| Project |  | EVA Copper Mine Project | [5 empty] | Total Hold Points |  | #REF! | Total Witness Points |  | #REF!
| ITP Folder |  | EVAMP001-THS-QA-ITP-0003 | [5 empty] | Remaining | #REF! |  | Remaining | #REF!
| Client |  | Harmony | [5 empty] | Complete | #REF! | #REF! | Complete | 0 | #REF!
| Contract Number |  | EVAMP001 | [5 empty] | Incomplete | #REF! |  | Incomplete | #REF!
Master Tracker Code | Inspection / Test Point | Responsibility | Test Method | Conformance Criteria | Freguency | Link to ITP | Thiess HP/WP Check | Inspector HP/WP Sign Off | MAR001 |  |  | MAR002 |  |  | MAR003 |  |  | MAR004 |  |  | MAR005 |  |  | MAR006 |  |  | MAR007 |  |  | MAR008 |  |  | MAR009 |  |  | MAR010 |  |  | MAR011 |  |  | MAR012 |  |  | MAR013 |  |  | MAR014 |  |  | MAR015 |  |  | MAR016 |  |  | MAR017 |  |  | VAR001 |  |  | VAR002 |  |  | TN001 |  |  | VP001 |  |  | PP001 |  |  | PP002 |  |  | PP003 |  |  | PP004 |  |  | PP005 |  |  | PP006
[9 empty] | Complete | Date | Folder Link | Complete | Date | Folder Link | Complete | Date | Folder Link | Complete | Date | Folder Link | Complete | Date | Folder Link | Complete | Date | Folder Link | Complete | Date | Folder Link | Complete | Date | Folder Link | Complete | Date | Folder Link | Complete | Date | Folder Link | Complete | Date | Folder Link | Complete | Date | Folder Link | Complete | Date | Folder Link | Complete | Date | Folder Link | Complete | Date | Folder Link | Complete | Date | Folder Link | Complete | Date | Folder Link | Complete | Date | Folder Link | Complete | Date | Folder Link | Complete | Date | Folder Link | Complete | Date | Folder Link | Complete | Date | Folder Link | Complete | Date | Folder Link | Complete | Date | Folder Link | Complete | Date | Folder Link | Complete | Date | Folder Link | Complete | Date | Folder Link
SP.1.1 | Underlying lot & ITP signed off and conforming | ENG | Visual | Topsoil ITP closed out | Prior to Works | TS1.6 |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No
SP.1.2 | Embankment fill material | ENG | Visual | Ensure CBR10 subgrade replacement materials have been approved for use and within specification | Prior to works (Check if this has already been completed at ITP Pre-construction stage) | PC1.12 | HP | WP | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No
SP.1.3 | Survey Set out | Surv | Field | Areas of work to be set out by surveyor and/or models in plant | As required | - | HP | WP | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No
SP.1.4 | Removal and replacement of unsuitable material | SUP | Field | Determination of unsuitable material by the Level 1 GITA or Inspector (Sedgman) is required prior to the removal of any unsuitable material. Unsuitable material criteria is in the specification. | As required | PC1.12 | HP | HP | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No
SP.1.5 | Subgrade/Foundation preparation | SUP | Field | Foundations for embankments to be ripped 200m deep, moisture conditioned then compacted. Density requirements: < 300mm from finished level under roads & structures minimum RDD 97%, all other areas and depths RDD 95%, moisture content -1% to +2%, normal level of testing 1 test per 500m3, reduced level of testing 1 test per 1,000m3. All material exposed in cuttings at subgrade level minimum CBR 3 or DCP 150kpa. If CBR2: Remove & replace with CBR10 select fill 150mm deep. If CBR1: Remove & replace with CBR10 select fill 250mm deep | As required | PC1.12 | HP | HP | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No
SP.1.6 | Trim subgrade | SUP / SURV | Field | Trim all subgrade to the lines and levels shown on the drawings in accordance with the following tolerances: Top of bulk earthworks +/-50mm; Road subgrades & under buildings & structures +0mm to -25mm. | As required | - | HP | HP | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No
SP.1.7 | Proof rolling | SUP | Field | Proof-roll subgrade/foundation surface prior to placement of embankment fill. Proof roll under a standard 8 tonne axle load or 10,000L water cart or heavy self propellled smooth drum roller dynapac 620D or equivalent to confirm that, in the Inspector (Sedgman) s opinion, deflections are negligible | As required | - | HP | HP | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No
SP.1.8 | Surface level check and survey pick-up | SURV | Survey / Field Test | Surface level picked up as per Table 10 C15 (DXF file format, volume calculated and filr saved in Construction Team Sharepoint and detailed in register | As required | - | HP | HP | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No
SP.1.9 | QA close out | ENG | Visual | GDP permits closed. ITP closed. Approved MDR. | As required | - | HP | HP | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No

## ITP8-Emb. Con.
THIESS HARMONY Alliance - QA Register-ITP8 Embankment Construction
| Project |  | EVA Copper Mine Project | [5 empty] | Total Hold Points |  | 1 | Total Witness Points |  | 1
| ITP Folder |  | EVAMP001-THS-4000-QA-ITP-008 | [5 empty] | Remaining | #REF! |  | Remaining | 1
| Client |  | Harmony | [5 empty] | Complete | #REF! | #REF! | Complete | 0 | 0%
| Contract Number |  | EVAMP001 | [5 empty] | Incomplete | #REF! |  | Incomplete | #REF!
Master Tracker Code | Inspection / Test Point | Responsibility | Test Method | Conformance Criteria | Freguency | Link to ITP | Thiess HP/WP Check | Inspector HP/WP Sign Off | MAR001 |  |  | MAR002 |  |  | MAR003 |  |  | MAR004 |  |  | MAR005 |  |  | MAR006 |  |  | MAR007 |  |  | MAR008 |  |  | MAR009 |  |  | MAR010 |  |  | MAR011 |  |  | MAR012 |  |  | MAR013 |  |  | MAR014 |  |  | MAR015 |  |  | MAR016 |  |  | MAR017 |  |  | VAR001 |  |  | VAR002 |  |  | TN001 |  |  | VP001 |  |  | PP001 |  |  | PP002 |  |  | PP003 |  |  | PP004 |  |  | PP005 |  |  | PP006
[9 empty] | Complete | Date | Folder Link | Complete | Date | Folder Link | Complete | Date | Folder Link | Complete | Date | Folder Link | Complete | Date | Folder Link | Complete | Date | Folder Link | Complete | Date | Folder Link | Complete | Date | Folder Link | Complete | Date | Folder Link | Complete | Date | Folder Link | Complete | Date | Folder Link | Complete | Date | Folder Link | Complete | Date | Folder Link | Complete | Date | Folder Link | Complete | Date | Folder Link | Complete | Date | Folder Link | Complete | Date | Folder Link | Complete | Date | Folder Link | Complete | Date | Folder Link | Complete | Date | Folder Link | Complete | Date | Folder Link | Complete | Date | Folder Link | Complete | Date | Folder Link | Complete | Date | Folder Link | Complete | Date | Folder Link | Complete | Date | Folder Link | Complete | Date | Folder Link
EC1.1 | Underlying lot & ITP signed off and conforming | ENG | Visual | Subgrade/Foundation Preparation ITP signed off | Prior to works | SP.1.9 | HP | WP | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No
EC1.2 | Embankment fill material | ENG | Visual | Ensure embankment fill materials have been approved for use and within specification | Prior to works (Check if this has already been completed at ITP Pre-construction stage) | PC1.12 | HP | WP | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No
EC1.3 | Survey Set out | Surv | Field | Areas of work to be set out by surveyor and/or models in plant | As required | - | HP | WP | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No
EC1.4 | Place, moisture condition & compact embankment fill | SUP/GeoTech | Field Test | Layer thickness minimum 150mm maximum 300mm. Density requirements: < 300mm from finished level under roads & structures minimum RDD 97%, all other areas and depths RDD 95%, moisture content -1% to +2%, normal level of testing 1 test per 500m3, reduced level of testing 1 test per 1,000m3. Subject to client approval oversized material up to 500mm can be used in general fill at the following depths: 600mm or greater in depth below subgrade for stockpiles, road surfaces and embankments, or 2m or greater in depth below the footprints of structures. Rock fill may be used >600mm below subgrade level. Material containing a high proportion of large particles may be used in embankments using the Mechanical interlock method of construction.Maximum layer thickness 500mm. | As required | - | HP | WP | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No
EC1.5 | Trim embankment | SUP / SURV | Field | Trim all embankment to the lines and levels shown on the drawings in accordance with the following tolerances: Top of bulk earthworks +/-50mm; Road subgrades & under buildings & structures +0mm to -25mm. | As required | - | HP | HP | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No
EC1.6 | Proof rolling | ENG/SUP | Field Test | Proof-roll embankment finished surface under a standard 8 tonne axle load or 10,000L water cart or heavy self propellled smooth drum roller dynapac 620D or equivalent, to confirm that in the Inspector's opinion, deflections are negligible. | As required | - | HP | HP | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No
EC1.7 | Surface level check and survey pick-up | SURV | Survey / Field Test | Surface level picked up as per Table 10 C15 (DXF file format, volume calculated and filr saved in Construction Team Sharepoint and detailed in register | As required | - | HP | HP | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No
EC1.8 | QA close out | ENG | Visual | GDP permits closed. ITP closed. Approved MDR. | As required | - | HP | WP | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No

## ITP8-Sub.Grade
THIESS HARMONY Alliance - QA Register-ITP8 Subgrade
| Project |  | EVA Copper Mine Project | [5 empty] | Total Hold Points |  | 1 | Total Witness Points |  | 1
| ITP Folder |  | EVAMP001-THS-4000-QA-ITP-008 | [5 empty] | Remaining | #REF! |  | Remaining | 1
| Client |  | Harmony | [5 empty] | Complete | #REF! | #REF! | Complete | 0 | 0%
| Contract Number |  | EVAMP001 | [5 empty] | Incomplete | #REF! |  | Incomplete | #REF!
Master Tracker Code | Inspection / Test Point | Responsibility | Test Method | Conformance Criteria | Freguency | Link to ITP | Thiess HP/WP | Sedgman HP/WP | MAR001 |  |  | MAR002 |  |  | MAR003 |  |  | MAR004 |  |  | MAR005 |  |  | MAR006 |  |  | MAR007 |  |  | MAR008 |  |  | MAR009 |  |  | MAR010 |  |  | MAR011 |  |  | MAR012 |  |  | MAR013 |  |  | MAR014 |  |  | MAR015 |  |  | MAR016 |  |  | MAR017 |  |  | VAR001 |  |  | VAR002 |  |  | TN001 |  |  | VP001 |  |  | PP001 |  |  | PP002 |  |  | PP003 |  |  | PP004 |  |  | PP005 |  |  | PP006
[9 empty] | Complete | Date | Folder Link | Complete | Date | Folder Link | Complete | Date | Folder Link | Complete | Date | Folder Link | Complete | Date | Folder Link | Complete | Date | Folder Link | Complete | Date | Folder Link | Complete | Date | Folder Link | Complete | Date | Folder Link | Complete | Date | Folder Link | Complete | Date | Folder Link | Complete | Date | Folder Link | Complete | Date | Folder Link | Complete | Date | Folder Link | Complete | Date | Folder Link | Complete | Date | Folder Link | Complete | Date | Folder Link | Complete | Date | Folder Link | Complete | Date | Folder Link | Complete | Date | Folder Link | Complete | Date | Folder Link | Complete | Date | Folder Link | Complete | Date | Folder Link | Complete | Date | Folder Link | Complete | Date | Folder Link | Complete | Date | Folder Link | Complete | Date | Folder Link
EC1.1 | Underlying lot & ITP signed off and conforming | ENG | Visual | Embankment or Excavation ITP signed off | Prior to works |  | HP | WP | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No
EC1.2 | Place and compact general fill layer – Subgrade | SUP/GeoTech | Field Test | Material containing a high proportion of large particles may be used in embankments using the Mechanical interlock method of construction Field density standard minimum Dry density test to be 95%, OMC -1%, +2% with a minimum layer thickness of 150mm and maximum 300mm. Material greater than 600mm may be allowed to be used in the Embankment. | As required |  | HP | WP | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No
EC1.3 | Subgrade in cut | SUP/GeoTech | Survey/Field Test | For subgrades under road/rail pavements and buildings/structures, the materials exposed at the subgrade level of cuttings is to have a minimum CBR of 3. | As required |  | HP | WP | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No
EC1.4 | Proof rolling | ENG/SUP | Field Test | The embankment will be proof rolled with either Proof rolling shall be undertaken using a 10,000 L water cart or heavy, self-propelled, smooth drum vibrating roller capable of operating in variable frequency modes. | As required each lot |  | HP | WP | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No
EC1.5 | As-built of completed surface | ENG/SURV | Survey | Survey to be completed of the finished surface to confirm to the levels as shown on the drawings with deviations as per Top of earthworks other than the subgrade and pad level ± 50, Road subgrade & building / structure pads +0 -25 | Each Finished Surface |  | HP | WP | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No
EC1.6 | QA close out | ENG | Visual | GDP permits closed. ITP closed. Approved MDR. | As required |  | HP | WP | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No

## ITP4-RCP Ins.
THIESS HARMONY Alliance - QA Register-ITP4 RCP Installation
| Project |  | EVA Copper Mine Project |  |  |  | Total Hold Points |  | 6 | Total Witness Points |  | 6
| ITP Folder |  | EVAMP001-THS-QA-ITP-0004 |  |  |  | Remaining | #REF! |  | Remaining | 6
| Client |  | Harmony |  |  |  | Complete | #REF! | #REF! | Complete | 0 | 0%
| Contract Number |  | EVAMP001 |  |  |  | Incomplete | #REF! |  | Incomplete | #REF!
Master Tracker Code | Inspection / Test Point | Responsibility | Test Method | Conformance Criteria | Freguency | HP/WP | MAR001 |  |  | MAR002 |  |  | MAR003 |  |  | MAR004 |  |  | MAR005 |  |  | MAR006 |  |  | MAR007 |  |  | MAR008 |  |  | MAR009 |  |  | MAR010 |  |  | MAR011 |  |  | MAR012 |  |  | MAR013 |  |  | MAR014 |  |  | MAR015 |  |  | MAR016 |  |  | MAR017 |  |  | VAR001 |  |  | VAR002 |  |  | TN001 |  |  | VP001 |  |  | PP001 |  |  | PP002 |  |  | PP003 |  |  | PP004 |  |  | PP005 |  |  | PP006
[7 empty] | Complete | Date | Folder Link | Complete | Date | Folder Link | Complete | Date | Folder Link | Complete | Date | Folder Link | Complete | Date | Folder Link | Complete | Date | Folder Link | Complete | Date | Folder Link | Complete | Date | Folder Link | Complete | Date | Folder Link | Complete | Date | Folder Link | Complete | Date | Folder Link | Complete | Date | Folder Link | Complete | Date | Folder Link | Complete | Date | Folder Link | Complete | Date | Folder Link | Complete | Date | Folder Link | Complete | Date | Folder Link | Complete | Date | Folder Link | Complete | Date | Folder Link | Complete | Date | Folder Link | Complete | Date | Folder Link | Complete | Date | Folder Link | Complete | Date | Folder Link | Complete | Date | Folder Link | Complete | Date | Folder Link | Complete | Date | Folder Link | Complete | Date | Folder Link
1.0 Pre-Construction
RCP1.1 | Drawings supplied most current IFC | ENG | Visual | Reviewed drawing register | Prior to works | HP | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No
RCP1.2 | Define RCP ID | ENG | Visual | Inspection Register. Allocate ID for reinforced concrete pipe, define work area | Prior to works | HP | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No
RCP1.3 | Lot Register/ WBS submitted and approved | ENG | Visual | Approved WBS | Prior to works | WP | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No
RCP1.4 | Underlying lot & ITP signed off and conforming | ENG | Visual | Subgrade prep ITP Signed | Prior to works | HP | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No
RCP1.5 | Certificate of compliance for RCP Material | ENG | Written | Supplier to provide certificates indicating manufacturing processes, materials, thicknesses, classes, and diameters (Only culverts with materials & dimensions complying with the culvert schedule & specification to be used). | Per pipe | HP | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No
RCP1.6 | Inspect reinforced pipe culverts for damage | ENG/SV | Visual | Prior to installation, Pipes are checked for damages and accepted/rejected and documented on Incoming Goods Inspection form | Per pipe | HP | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No
2.0 Construction
RCP2.7 | Trench Excavation | SV/SC | Visual | Trenches should be excavated to the required width and grade indicated on the IFC Drawings, with allowance made for benching for excavations greater than 1.5 meters. Excavations must be kept free from water until work below ground level us adequately set or protected | As required | HP | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No
RCP2.8 | Bedding | SV/SC | Visual | Culverts shall be bedded as detailed on the Drawings. Proposed | As required | HP | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No
RCP2.9 | RCP Installation | SV/SC | Written/survey | Culverts are to be installed to the line, level, and grade shown on the IFC Drawings. Inlet and outlet invert levels shall be as shown in the Drawings plus or minus 10mm. Inverts shall be smooth and of uniform gradient throughout each culvert length. Tolerances: Vertical level: ± 10mm Horizontal Alignment: ± 25mm | As required | HP | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No
RCP2.10 | Backfilling of culvert | ENG/SV | Visual | Backfilling and compaction shall be carried out in horizontal layers of uniform thickness not exceeding 200 mm of uncompacted selected fill material for 300 mm all around the pipe or culvert. Compaction in this zone shall generally be by hand tampers to a minimum density of 95% of the standard maximum dry density at +/- 2% optimum moisture content. Compaction of backfill in the remainder of the trench to subgrade level shall be to a minimum 98% modified MDD at +/-2% OMC shall be advised | As required | HP | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No
RCP2.11 | End Treatment – Headwall & Wingwalls (Reinforcement) | ENG/SV | Visual | Reinforcement installed as per IFC design drawings | V | HP | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No
RCP2.12 | End Treatment – Headwall & Wingwalls (Formwork) | ENG/SV | Visual/Field Survey | Formwork installed as per IFC design drawings. Tolerances: Variation in cross-sectional Dimensions: + 5mm Variation in overall dimensions: + 10mm Variation in surface level: + 5mm | Each inlet/outlet | HP | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No
RCP2.13 | End Treatment – Headwall & Wingwalls (Concrete) | SC/SV | Visual | Concrete placed and compacted to specified strength (N40) and slump (max100mm). | Each inlet/outlet | HP | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No
RCP2.14 | Rock Protection | SC/SV | Visual | Dimensions and class of rock protection shall be as specified in the Culvert Schedule and supplied IFC Drawings. | Each inlet/outlet | HP | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No
3.0 Post Construction
RCP3.15 | Works completed and update ITP/ Lot Register/ MDR and close out of GDP | ENG | Visual | GDP permits closed. ITP closed. Approved MDR | As required | HP | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No

## ITP9 - Pavements
THIESS HARMONY Alliance - QA Register-ITP9 Unbound Gravel Pavements
| Project |  | EVA Copper Mine Project |  |  |  | Total Hold Points |  | 7 | Total Witness Points |  | 7
| ITP Folder |  | EVAMP001-THS-QA-ITP-009 |  |  |  | Remaining | #REF! |  | Remaining | 7
| Client |  | Harmony |  |  |  | Complete | #REF! | #REF! | Complete | 0 | 0%
| Contract Number |  | EVAMP001 |  |  |  | Incomplete | #REF! |  | Incomplete | #REF!
Master Tracker Code | Inspection / Test Point | Responsibility | Test Method | Conformance Criteria | Freguency | HP/WP | MAR001 |  |  | MAR002 |  |  | MAR003 |  |  | MAR004 |  |  | MAR005 |  |  | MAR006 |  |  | MAR007 |  |  | MAR008 |  |  | MAR009 |  |  | MAR010 |  |  | MAR011 |  |  | MAR012 |  |  | MAR013 |  |  | MAR014 |  |  | MAR015 |  |  | MAR016 |  |  | MAR017 |  |  | VAR001 |  |  | VAR002 |  |  | TN001 |  |  | VP001 |  |  | PP001 |  |  | PP002 |  |  | PP003 |  |  | PP004 |  |  | PP005 |  |  | PP006
[7 empty] | Complete | Date | Folder Link | Complete | Date | Folder Link | Complete | Date | Folder Link | Complete | Date | Folder Link | Complete | Date | Folder Link | Complete | Date | Folder Link | Complete | Date | Folder Link | Complete | Date | Folder Link | Complete | Date | Folder Link | Complete | Date | Folder Link | Complete | Date | Folder Link | Complete | Date | Folder Link | Complete | Date | Folder Link | Complete | Date | Folder Link | Complete | Date | Folder Link | Complete | Date | Folder Link | Complete | Date | Folder Link | Complete | Date | Folder Link | Complete | Date | Folder Link | Complete | Date | Folder Link | Complete | Date | Folder Link | Complete | Date | Folder Link | Complete | Date | Folder Link | Complete | Date | Folder Link | Complete | Date | Folder Link | Complete | Date | Folder Link | Complete | Date | Folder Link
1.0 Pre-Construction
GP1.1 | Drawings supplied most current IFC | ENG | Visual | Reviewed drawing register | Prior to works | HP | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No
GP1.2 | Management Plans submitted and approved as per PMP | ENG | Visual | Approved Package MP’s | Prior to works | HP | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No
GP1.3 | Inspection Test Plan (ITP) submitted and approved | ENG | Visual | Approved ITP revision | Prior to works | HP | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No
GP1.4 | Lot Register/ WBS submitted and approved | ENG | Visual | Approved WBS | Prior to works | WP | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No
GP1.5 | Pavement material compliance testing | ENG | Visual | Test results comply with the details on the drawings or where not specified the specification | Prior to works | HP | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No
GP1.6 | Stockpile locations | ENG | Visual | Stockpile locations shown on the drawings or approved by client’s rep | Prior to works | HP | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No
GP1.7 | Underlying lot & ITP signed off and conforming | ENG | Visual | Subgrade prep ITP Signed | Prior to works | HP | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No
2.0 Construction
GP2.8 | Subgrade preparation under pavements | ENG | Visual/Field Test | If subgrade material is less than CBR10, subgrade shall be boxed and replaced with 150 mm of CBR10 or greater material. Subgrades shall be trimmed and compacted to within 15 mm of the established grade or cross section. Compaction requirement: 98% modified maximum dry density at +/- 2% OMC. | As required | HP | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No
EC2.9 | Surface level check/ and survey pick-up | SURV | Survey/Field Test | Surface level pick-up submitted to company | As required | HP | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No
EC2.10 | Proof roll subgrade prior to placement of pavement materials | ENG | Visual | Subgrades under pavements shall be proofrolled under a 10,000L water cart or heavy, self-propelled, smooth drum vibrating roller capable of operating in variable frequency modes, to confirm that, in the principal’s opinion, deflections are negligible | As required | HP | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No
EC2.11 | Placement of pavement material layers | ENG | Visual/Field Test | All materials delivered to site shall be accompanied by test certificates. Each layer shall be free from sticks, organic matter, clay lumps and other deleterious material, and be spread and compacted in a uniform thickness minimum 75mm, maximum 250mm as per the details on the drawings. The deviation from a 3m long straight-edge placed anywhere on the surface of a layer shall not exceed 8mm. Pavement layer thickness tolerances: Base -0mm to +30mm; Sub Base -15mm to +30mm. Finished pavement surface level tolerance: Base -15mm to +25mm Horizontal tolerances: Base, centreline/crown -150mm to +50mm, edgeline/changepoint -100mm to +200mm; Sub Base, centreline/crown +/-200mm, change point -100mm to +400mm Compaction requirements: Base & Sub Base 100% standard relative dry density (RDD) maximum degree of saturation 70%. Compliance testing frequency as per table in Specification Annexure A clause 5. | As required | HP | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No
EC2.12 | Surface level check/ and survey pick-up | SURV | Survey/Field Test | Surface level as per the pavement layer details on the drawings, and all layers as per the tolerances listed in item 11 of this ITP. | As required | HP | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No
3.0 Post Construction
EC3.13 | Works completed and update ITP/ Lot Register/ MDR and close out of GDP | ENG | Visual | ITP closed. Approved MDR | As required | HP | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No

## ITPX-Road Signs
THIESS HARMONY Alliance - QA Register-ITPX Road Signs
| Project |  | EVA Copper Mine Project |  |  |  | Total Hold Points |  | 10 | Total Witness Points |  | 10
| ITP Folder |  | EVAMP001-THS-QA-ITP-0004 |  |  |  | Remaining | #REF! |  | Remaining | 10
| Client |  | Harmony |  |  |  | Complete | #REF! | #REF! | Complete | 0 | 0%
| Contract Number |  | EVAMP001 |  |  |  | Incomplete | #REF! |  | Incomplete | #REF!
Master Tracker Code | Inspection / Test Point | Responsibility | Test Method | Conformance Criteria | Freguency | HP/WP | MAR001 |  |  | MAR002 |  |  | MAR003 |  |  | MAR004 |  |  | MAR005 |  |  | MAR006 |  |  | MAR007 |  |  | MAR008 |  |  | MAR009 |  |  | MAR010 |  |  | MAR011 |  |  | MAR012 |  |  | MAR013 |  |  | MAR014 |  |  | MAR015 |  |  | MAR016 |  |  | MAR017 |  |  | VAR001 |  |  | VAR002 |  |  | TN001 |  |  | VP001 |  |  | PP001 |  |  | PP002 |  |  | PP003 |  |  | PP004 |  |  | PP005 |  |  | PP006
[7 empty] | Complete | Date | Folder Link | Complete | Date | Folder Link | Complete | Date | Folder Link | Complete | Date | Folder Link | Complete | Date | Folder Link | Complete | Date | Folder Link | Complete | Date | Folder Link | Complete | Date | Folder Link | Complete | Date | Folder Link | Complete | Date | Folder Link | Complete | Date | Folder Link | Complete | Date | Folder Link | Complete | Date | Folder Link | Complete | Date | Folder Link | Complete | Date | Folder Link | Complete | Date | Folder Link | Complete | Date | Folder Link | Complete | Date | Folder Link | Complete | Date | Folder Link | Complete | Date | Folder Link | Complete | Date | Folder Link | Complete | Date | Folder Link | Complete | Date | Folder Link | Complete | Date | Folder Link | Complete | Date | Folder Link | Complete | Date | Folder Link | Complete | Date | Folder Link
1.0 Pre-Construction
RS1.1 | Drawings supplied most current IFC | ENG | Visual | Reviewed drawing register | Prior to works | HP | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No
RS1.2 | Management Plans submitted and approved as per PMP | ENG | Visual | Approved Package MP’s | Prior to works | HP | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No
RS1.3 | Inspection Test Plan (ITP) submitted and approved | ENG | Visual | Approved ITP revision | Prior to works | HP | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No
RS1.4 | Lot Register/ WBS submitted and approved | ENG | Visual | Approved WBS | Prior to works | WP | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No
RS1.5 | Check existing services and dial before you dig | ENG | Visual | DBYD certificate and EP | Prior to works | HP | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No
RS1.6 | Ground Disturbance Procedure (GDP) obtained | ENG/ENV | Visual | GDP permit with work packs | Prior to works | HP | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No
RS1.7 | Materials for signs | ENG | Visual/ Manufacturer warranties and/or certificates | Signage panels fabricated from 2mm thick aluminium sheeting conforming to AS1742. Sign face shall be non-reflective (NR) with the vinyl film conforming to appendix B of AS1743. Post sections are to comply with AS1163 and be in accordance with the following: Steel circular hollow sections in accordance with grade C250L0; and Steel rectangular hollow sections in accordance with grade C350L0. Steel posts are to be hot-dipped galvanised with a minimum of 300g/m2 galvanised coating complying with AS1650. Post sizes will be as detailed on the drawings. Hot dipped galvanised caps are to be fitted to the top of posts. Steel or Aluminium Brackets are to be used on all sign posts | Prior to works | HP | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No
RS1.8 | Fabrication of signs | ENG | Visual/ Manufacturer warranties and/or certificates | MUTCD is to be used for compilation of the message, shape, size, layout and colour required for the facing of the sign. Signs are to be, cleaned, degreased and chemically etched or abraded in accordance with manufacturers specifications prior to application of non-reflective sheeting or paint. Non-reflective sheeting or paint shall be applied to the sign blank in accordance with the manufacturers specifications. All letters, arrows, symbols and borders shall be applied by: Silk screening before or after sign blank sheeting; and Pre-cut non-reflective material. | Prior to works | HP | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No
RS1.9 | Set out for sign locations | Surv | Survey | Locations of signage set out as per MUTCD or as shown on the design drawings | Prior to works | HP | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No
RS1.10 | Underlying lot & ITP signed off and conforming | ENG | Visual | Pavement and/or Bulk Earthworks ITPs signed off | Prior to works | HP | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No
2.0 Construction
RS2.11 | Installation of signs | ENG | Visual | Signage to be installed as per MUTCD or as shown on the design drawings | As required | HP | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No
RS2.12 | Removal or demolition of existing signs | SV | Visual | Any existing road signage to be removed or made redundant must be demolished including all signs, brackets, footing etc after the new signage in place. Voids left after post removal must be backfilled with approved pavement material to design surface level as shown on design drawings. | As required | HP | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No
RS2.13 | Sign installation location check and survey pick-up | Surv | Survey/Field Test | Locations of signage installed as per MUTCD or as shown on the design drawings | As required | HP | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No
3.0 Post Construction
RS3.14 | Works completed and update ITP/ Lot Register/ MDR and close out of GDP | ENG | Visual | ITP closed. Approved MDR | As required | HP | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No |  |  | No

## Camp Road
Lot 1 | Foundation Prep | Embankment
Lot 2 | Foundation Prep | Embankment
Lot 3 | Foundation Prep | Embankment
Lot 4 | Foundation Prep | Embankment
Lot 5 | Subgrade cut
Lot 6 | Foundation Prep | Embankment
Lot 7 | Foundation Prep | Embankment
Lot 8 | Subgrade cut | sent to worley
Lot 9 | Subgrade cut | sent to worley
Lot 10 | Subgrade cut
Lot 11 | Subgrade cut
Lot 12 | Foundation Prep | Embankment | sent embankment to worley
Lot 13 | Foundation Prep | Embankment | sent embankment to worley
Lot 14 | Subgrade cut
Lot 15 |  | Embankment
Lot 16 | Subgrade cut | Embankment
Lot 17 | Foundation Prep | Embankment
Lot 18 | Foundation Prep | Embankment
Lot 19 | Foundation Prep | Embankment

## List of ITPS
ITP No. | List of ITPS
ITP001 | Clearing and Grubbing
ITP002 | Topsoil stripping
ITP003 | Subgrade Preparation
ITP004 | RCP Installation
ITP005
ITP006
ITP007
ITP008 | Embankment Construction
ITP009 | Pavements
ITP010
ITP011
ITP012
ITP013
ITP014
ITP015
ITP016
ITP017
ITP018
ITP019
Road Furniture - Road Signs