## Master List Templates
Id | Type | Name | Values | Prompting Name
2dc61ceb-183d-4225-b0c2-fa3552a96601 | checklist | EVAMP001-THS-QA-ITP-0001 - Clear and Grubbing | itp | EVAMP001-THS-QA-ITP-0001 - Clear and Grubbing
123a04ed-8bcb-4000-a8aa-230a4e11ec20 | section | 1 - Pre-Construction
6e2dcbd0-c242-406b-b018-16ba73f9d1aa | checkpoint | Lot Map
11eae57a-9aa1-4e1c-b4ec-f791161f27ca | checkpoint | 8 - Area of works pegged and clearly defined to GDP. Pre- strip area survey pick-up
84e60977-bfdc-5517-ad85-f0586923788a | note | Responsibility - SURV
6cbcd8ed-57c3-56dd-88ce-69f7e3120a4e | note | Method - Visual
fa4f230b-0e1b-5e73-8a87-ede64e1fbe20 | note | Conformance Criteria - Clearing pegs installed at nominal intervals to ensure no over-clearing
687c79b2-6a31-5c1e-9b99-12925f6a716d | note | Specification Clause - EVAMP001-EVA- 7340-PE-PRM-0001 to ensure no over-clearing
59b28b6e-93f9-5334-9e70-8cb4e04ef116 | note | Frequency - Prior to works
d517d0fd-b955-55dc-8cb8-e8997d733c0d | note | Verification: THIESS (Initial) - HP
dd20d1be-cd4f-55a0-af99-ae37553e8bb7 | note | Verification: Client (Initial) - HP
6fa2d4d9-a8ca-47f0-b1fc-2526bdeb7071 | signoff | HOLD POINT
8411cd09-1ea4-446d-9e38-2cb45797cac8 | checkpoint | 10 - Survey of pegs to confirm correct setting out
ce5a3407-9d28-58ab-9b41-1260e4365bf5 | note | Responsibility - ENV
b6219998-181a-578b-b32d-5dd7ea1293d3 | note | Method - Visual
025efb29-7f71-5c03-90a9-c44839709b6b | note | Conformance Criteria - Pegs to be surveyed and sent back to the engineer. This is then to be confirmed by the environmental team
6b600084-5407-5e8c-b57c-2c2e4f390403 | note | Specification Clause - EVAMP001-EVA- EN-PLA-0001
59df7d40-4f28-5767-b422-f91d5c0b1fd9 | note | Frequency - Prior to clearing
66d95759-32e1-53a7-a1e6-92332f54c6e0 | note | Verification: THIESS (Initial) - HP
0c000f85-a88a-5dcf-a82c-15536a73ca9d | note | Verification: Client (Initial) - HP
c0e12c16-755b-4c27-8de8-09442ed0aec9 | signoff | HOLD POINT
ff7a217b-0bcd-4de5-9271-a69152d419b7 | section | 2 - Construction
d9230512-0cf7-4a06-bf29-9128c86f4267 | checkpoint | 11 - Clearing of vegetation and removal to nominated stockpile location
9ec30b2c-3ff1-5c99-865d-07970713d91b | note | Responsibility - ENG
7fa3fcd8-a832-5d1f-b1bd-6ce225a3c526 | note | Method - Visual
32e2292e-1958-577b-8377-3a816e7ce72e | note | Conformance Criteria - Spotter/ catcher in place during clearing operations
b297214d-7495-5c2b-80fa-3e59aa065521 | note | ○ Habitat vegetation, threatened species and cultural heritage areas demarcated
bdf0570a-f976-53fd-95af-ef5ef309997c | note | Specification Clause - EVAMP001- EVA-EN-PLA- 0001
3ad3a22d-70e1-5f7f-8ea3-d24beb2b7987 | note | — EVAMP001- EVA-7340-PE- PRM-1
b9b9f255-b459-5f31-9784-19ca8b8a37ad | note | — C22 of EVAMP001-QVT- PE-PRM-1
82915ec0-68ee-540d-befe-eed0e6b01e20 | note | Frequency - As required
5a314882-bae0-54d9-bb9f-1ac0b488e099 | note | Verification: THIESS (Initial) - HP
3d7df1b6-8547-57ab-bf06-c070114b5dd4 | note | Verification: Client (Initial) - W
cbd6e942-230b-4f6d-9160-4ed315f5e179 | signoff | HOLD POINT
76bb71da-ab3d-4566-9135-388e7b991e29 | checkpoint | 12 - All Erosion sediment control measures installed prior to construction
a2a6e786-2b3c-5b03-8747-9a0a7cb18be5 | note | Responsibility - ENV
a361c1d2-e070-5b83-a59f-4bf91144246b | note | Method - Visual
a044c74b-a994-57a1-9a2e-8d677c940176 | note | Conformance Criteria - All control measures for erosion sediment control need to be implemented after clearing has been completed.
1b0b6346-15bd-5577-bde4-719ab72b88e8 | note | Specification Clause - EVAMP001-EVA- 7340-PE-PRM-0001
c9cae457-809e-501c-8d72-5a1d8a082663 | note | — EVAMP001-EVA- EN-PLA-0001
f4adb0eb-c05c-5660-97df-33b6754d1da9 | note | Frequency - After clearing completed
6a43e62e-a28a-5943-b47f-b6503518ce43 | note | Verification: THIESS (Initial) - HP
526850d4-f9bd-5d88-8b76-4f0bafe64ec9 | note | Verification: Client (Initial) - HP
9c35f85c-f9d5-4a58-afdf-8034e09b8f98 | signoff | HOLD POINT
a0707b61-49da-4bd5-b575-b8dbce7822e6 | checkpoint | 13 - Inspection of foundation prior to next stage of construction
47868d81-6add-506a-8bac-fd579126a668 | note | Responsibility - ENG
df2c4744-04bc-5485-9dd4-e35fd801877e | note | Method - Field Test
9ade0960-8b5c-53b3-93d9-1795fe06bdd8 | note | Conformance Criteria - Proof roll where required
78e8e33d-80b1-5ab4-988c-649add1caa4e | note | Specification Clause - EVAMP001-EVA- EN-PLA-0001
8c857f8c-2ac3-5e35-aa49-89f3266a3183 | note | Frequency - As required
d526c092-75d9-50d1-b48f-fec9cc3ae138 | note | Verification: THIESS (Initial) - HP
3fffed97-1031-5786-a3ae-b96d385eaea6 | note | Verification: Client (Initial) - HP
d89cd23b-45b8-434b-abb2-615769c20cd2 | signoff | HOLD POINT
764d3fbe-e73a-4d41-9c7a-6b2be8c72319 | checkpoint | 14 - Surface level check/post-strip area survey pick-up
d22ebb01-29ca-5265-a9c2-def834422058 | note | Responsibility - SURV
4c5c041f-e914-53ed-8443-8123ced4718b | note | Method - Survey/ Field Test
8e4eb6d0-b885-57ac-9174-b41aa51e2dcc | note | Conformance Criteria - DXF file submitted to Company
8501955f-6740-564e-ace8-f9a169bfb96c | note | Specification Clause - EVAMP001-EVA- 7340-PE-PRM-0001
45b96e5e-b610-5342-9ef5-7dcb61476a47 | note | Frequency - As required
16e7afe2-2547-54bc-87e6-8a5cbf4d77d8 | note | Verification: THIESS (Initial) - HP
046d1947-1d28-54f1-af6b-91620e6d999e | note | Verification: Client (Initial) - W
88b881f2-8230-4629-80ca-373d0691aed6 | signoff | HOLD POINT
b84db826-2024-40ae-b014-85a11d280f9c | section | 3 - Post Construction
c9b3e20d-f6df-4a96-8888-a6f878eb8314 | checkpoint | 15 - Works completed and update ITP/ Lot Register/ MDR and close out of GDP
e72654fb-4530-5103-856f-865ea8cc5f7a | note | Responsibility - ENG
ab361d09-0b68-598d-ad35-808da90bb112 | note | Method - Visual
c6cf5d84-03ec-52cd-b7cb-6b6c5851b505 | note | Conformance Criteria - GDP permits closed.
707dcfc9-97c7-5e55-a00a-b4c568739a8a | note | ○ ITP closed. Approved MDR
4eb1ab5b-a384-5a13-853a-0dad02071d0c | note | Specification Clause - EVAMP001- EVA-7340-PE- PRM-0001
8b3ce8f9-5295-5411-802a-6fa30dfa5f24 | note | — EVA PMP
c92dd74d-89c5-5053-83a3-919e70cd25c9 | note | Frequency - As required
4d3f2e49-cbb3-5f78-88f5-ea3be5a55e43 | note | Verification: THIESS (Initial) - HP
66964e09-bc27-5029-aa6d-5ea0606b667d | note | Verification: Client (Initial) - HP
5e7c81bb-55ba-46df-ba4f-ae5cbc10b3d3 | signoff | HOLD POINT
fd4be270-e75a-4b8d-a474-4b812aed51e7 | checkpoint | Final Inspection
7b8b411d-e8c0-58dd-b3b0-2bfee1441f98 | tickbox | Conformance to Specification
009f4040-bb0b-5dfb-a33d-29d1cbf093f7 | tickbox | Requires Re-Work:
672f4c3c-dab1-5028-a2d3-155d3eb0b7b3 | textbox | (Provide Details):
34da4660-2088-555b-9ab1-984208295d5d | tickbox | Non-Conformance
6058c9e5-ea5a-5c6a-9f60-b6e0f8bcebb4 | textbox | NCR No:
8b898533-e533-4c29-8701-4bd49cca6d28 | signoff | Approved by THIESS QA Representative / THIESS Project Manager / Client
4b0abbcd-c699-4e90-a660-11e4e10f062b | checklist | EVAMP001-THS-QA-ITP-0001 - Clear and Grubbing - Global Lot | itp | EVAMP001-THS-QA-ITP-0001 - Clear and Grubbing (Global Lot)
99768ba4-d48b-4d7a-94e4-e6aa108e40db | section | 1 - Pre-Construction
7b1f87c1-b809-4777-8871-d467d0b9011c | checkpoint | 1 - Drawings supplied most current IFC
89111b25-423c-54c3-abbb-07da20d5360c | note | Responsibility - ENG
c20aaab4-8b74-5f0a-9400-77f0fd6e920d | note | Method - Visual
80e4f95e-ae72-54a1-9be4-9788b9919243 | note | Conformance Criteria - Reviewed drawing register
9bd2c39a-4312-5507-a3e7-a1143c307723 | note | Specification Clause - Reviewed drawing register
7c1b92b9-bd05-51b9-a977-a5cf38401438 | note | Frequency - Prior to works
7646f7f3-21ed-5e35-9aa4-e2e347c1cff9 | note | Verification: THIESS (Initial) - HP
fcce6462-5ff1-51b1-9f41-edd9c79597f7 | note | Verification: Client (Initial) - W
8d289e51-09dd-4a98-a3de-e832cc597d97 | signoff | HOLD POINT
c5a3dcd2-2ac8-4572-b21e-4632bd805cf7 | checkpoint | 2 - Management Plans submitted and approved as per PMP
1a340662-b554-585c-b6a5-891704592c46 | note | Responsibility - ENG
874c2a5f-7d6b-5f18-a0e3-36ba47716efe | note | Method - Visual
26abac50-e2c2-58bc-92a6-0b28e836b022 | note | Conformance Criteria - Approved Package MP’s
0a6252ee-3db2-5486-b391-778ac2bbb6a0 | note | Specification Clause - Approved Package MP’s
6b0a3bdf-9548-5200-b427-0f1e15950d84 | note | Frequency - Prior to works
04a9c812-264c-57e2-8727-a3be5ae54018 | note | Verification: THIESS (Initial) - HP
09312a57-0cfb-5c73-8f85-c95734617a85 | note | Verification: Client (Initial) - W
7df4b227-a7bc-4b95-894b-eab2b8f08308 | signoff | HOLD POINT
35e243cc-aaf4-429f-acdd-c08341905679 | checkpoint | 3 - Inspection Test Plan (ITP) submitted and approved
fd0e0c69-cfa1-5ec2-bd10-4cd2872258d5 | note | Responsibility - ENG
2fe9c0f6-ce56-5134-b856-625b5ae91d29 | note | Method - Visual
678f14c5-589a-57a8-a107-bc2e189993a1 | note | Conformance Criteria - Approved ITP revision
43a7cba5-af80-564a-b9e4-c9656b4c9eb2 | note | Specification Clause - Approved ITP revision
32301199-da66-5a36-b919-55deb71aec1c | note | Frequency - Prior to works
800992f3-d3f8-59a2-a989-0899f32ab6e0 | note | Verification: THIESS (Initial) - HP
f05ff70d-ac3f-55c9-a06f-0dd1b428be34 | note | Verification: Client (Initial) - W
33cf753c-5345-4b17-89eb-b4735421aae6 | signoff | HOLD POINT
3d7bf959-e14f-4cf8-85a8-58263e37a22c | checkpoint | 4 - Lot Register/ WBS submitted and approved
13e0807a-1dee-5c37-97a5-d98aadaeb00d | note | Responsibility - ENG
fc961a75-b911-535b-a0ae-a9a7176990bb | note | Method - Visual
9c590ad2-25eb-5e53-9177-251762869175 | note | Conformance Criteria - Approved WBS
28f44be7-447b-59f2-aa45-898e22561a1e | note | Specification Clause - Approved WBS
d62326e4-b14f-59ce-99c9-141f055f962f | note | Frequency - Prior to works
4bb66250-3077-59fb-91b9-b850b576a6c9 | note | Verification: THIESS (Initial) - WP
b919aae5-376c-5947-9b41-f824cbe79371 | note | Verification: Client (Initial) - W
71d7dca5-5087-4f38-9556-553e3ae0229c | signoff | WITNESS POINT
046638ad-3b34-43b4-a38d-f1107cb22e67 | checkpoint | 5 - Erosion and sediment control plan approved
32c84350-1ee7-515e-a7b5-d2e0924e911f | note | Responsibility - ENV
bd312d9e-2f42-5dcc-8e54-3afa8544b6aa | note | Method - Visual
6c4dd2f6-2b3b-5f5c-909f-8896f2cc089f | note | Conformance Criteria - Approved erosion and sediment control plan
eddbea88-e040-5cfb-ad50-dc76637466d2 | note | Specification Clause - EVAMP001-EVA- 7340-PE-PRM-0001
adee58bd-8509-57d0-a61c-960183409803 | note | Frequency - Prior to works
c6ec1f9f-bd5e-5d51-98cd-0cc328da704f | note | Verification: THIESS (Initial) - HP
59409af6-bd44-5c6e-aa87-56cd0e2bd525 | note | Verification: Client (Initial) - HP
1186d6fd-e8bb-430e-a217-7f6f96959387 | signoff | HOLD POINT
48298157-57de-48cf-998a-b5ca1758a8e9 | checkpoint | 6 - Check existing services and dial before you dig
80e195af-d4a7-55a7-91b6-2065a79213db | note | Responsibility - ENG
8256ec3e-1ef0-5884-8d75-dff8911649da | note | Method - Visual
dd7cba8d-be74-55ac-8ff0-d4be987d4eef | note | Conformance Criteria - DBYD certificate and EP
a7ae043d-432b-53cb-a6da-586a3cabdfbd | textbox | Specification Clause - Excavation Permit (EP) Doc no.
843816da-efe0-52c7-beb1-d4490acc221d | note | Frequency - Prior to works
e9d465ac-8f69-53bd-babf-9d11cd362e1b | note | Verification: THIESS (Initial) - HP
c858b134-ab80-5a5c-9489-768f83d3df38 | note | Verification: Client (Initial) - W
748eeac4-4328-4e92-94a7-3d09a2266a51 | signoff | HOLD POINT
c4acd5df-dc83-46b0-8c6f-29fa109b5b57 | checkpoint | 7 - Ground Disturbance Procedure (GDP) obtained
4a3aedeb-aa0f-54e4-820f-86c0aa92db8e | note | Responsibility - ENG
a6fb453d-ed71-58cd-b6b8-3df2e3cabfb3 | note | Method - Visual
c2521a66-52f7-54d4-8e19-fd2b77297b5b | note | Conformance Criteria - GDP permit with work packs
cb980b7a-21c7-5ff6-aafa-1b403c1d885d | note | Specification Clause - EVAMP001-EVA- 7340-PE-PRM-0001
69e83c88-ed42-5cfc-8402-15bf32996c3c | note | Frequency - Prior to works
4f93652f-2edf-5bb5-895c-34ffe67ff628 | note | Verification: THIESS (Initial) - HP
67a88537-b41d-5a28-8430-9e955ae47522 | note | Verification: Client (Initial) - HP
106e6800-5307-4392-9d84-be558e3602df | signoff | HOLD POINT
8d7b3140-1858-4d73-ab55-5f33a82f3559 | checkpoint-no-value | 8 - Area of works pegged and clearly defined to GDP. Pre- strip area survey pick-up (REFER TO SUBLOTS)
f42e2edd-fa1d-4df5-a60b-5fd448b7f8ac | checkpoint | 9 - Area of works been pre-cleared for Fauna/ Flora
4aabc1df-e839-591c-b386-d2813645b180 | note | Responsibility - ENV
6ccbc6e3-3dd4-567c-99d9-820ea9b0078d | note | Method - Visual
32568ccc-bcfb-53e8-adf2-d32c73a60b1e | note | Conformance Criteria - All areas to be pre-cleared prior to clearing operations.
fc438aef-6070-58b1-926a-ef87a5d9675e | note | Specification Clause - EVAMP001-EVA- EN-PLA-0001
504b47e0-913a-500a-bc6d-7c50a92e40ec | note | Frequency - Prior to works
4ad6444b-7fea-5fa8-ac4d-583a0aef7dfb | note | Verification: THIESS (Initial) - HP
399dbb51-ed64-5cf9-ad5f-7588ea90d442 | note | Verification: Client (Initial) - HP
68bc99ec-6f29-4ad8-9a7d-b62f872c8840 | signoff | HOLD POINT
bd5da62e-53e7-496f-aabe-8c5ab4f325cb | checkpoint-no-value | 10 - Survey of pegs to confirm correct setting out
e6b3ee28-3caa-4f17-9e89-421b2362a24d | checklist | EVAMP001-THS-QA-ITP-0002 - Topsoil Stripping | itp | EVAMP001-THS-QA-ITP-0002 - Topsoil Stripping
bb2e1762-4d0e-404b-8ed1-f392b37abd6a | section | 1 - Pre-Construction
1522be28-1cee-48d1-9f14-166524653872 | checkpoint | 1 - Underlying lot & ITP signed off and conforming
7012591b-baee-5565-a621-3d03742a9f88 | note | Responsibility - ENG
9a0d6136-566f-5289-976e-e0b46176625a | note | Verification: THIESS (Initial) - HP
20ba5b44-7991-5a84-b99f-d0fca388249a | note | Verification: Client (Initial) - W
3c43db1a-22b0-4826-8ef2-0e0274af5ab6 | signoff | WITNESS POINT
297a9d0e-098c-4818-b253-4865c7b786d4 | checkpoint-no-value | Documents already approved
e066ec26-aa7c-5c73-abf8-e79868f98c84 | note | 2 - Drawings supplied most current IFC
c6fbefed-71d3-5649-af6c-7bfd0fbc6bf2 | note | 3 - Check existing services and dial before you dig
ade025a4-c02f-527c-a867-73f61c66451d | note | 4 - Ground Disturbance Procedure (GDP) obtained
25c3d13c-0422-40c2-92e9-21d2a80ebc3a | checkpoint | 5 - Area of works pegged and clearly defined to GDP. Pre-strip area survey pick-up
eb97e363-e818-53eb-a7f5-514579cc3100 | note | Responsibility - ENG
91c06af4-96af-5f4e-b63e-f0c6f6b51613 | note | Method - Visual
f254e918-bf94-5358-9e33-f11bb65905e4 | note | Conformance Criteria - Boundary pegs installed at nominal intervals to ensure no over-stripping
557dc8bb-5dac-5302-a576-63c408aa81e1 | note | Specification Clause - EVAMP001-EVA- 7340-PE-PRM-0001
5eef00b2-78cf-5dde-896a-8073ec628850 | note | Frequency - Prior to works
d0249876-780e-5d21-b3d0-f9fba18d8d68 | note | Verification: THIESS (Initial) - HP
d8ffa544-2007-534d-9efe-1918efa03b82 | note | Verification: Client (Initial) - HP
84d273b0-6521-4f8f-99cd-4d27eb4bff2b | signoff | HOLD POINT
0134881a-cc2b-4495-8a4e-2a219e89cf09 | section | 2 - Construction
15d3a864-cd48-4fab-85fc-1a0b54d65f1b | checkpoint | 6 - Stripped topsoil load and hauled to nominated stockpile location
682c8e66-35ab-5982-bc62-30332bade47c | note | Responsibility - ENG
2be64ee8-dc2d-51f1-9c8f-b6d853b7c935 | note | Method - Visual
90cb55bf-6f0d-523b-8c86-838ba045220a | note | Conformance Criteria - Stockpile locations located 40m from watercourses and not exceed 2m in height.
0ffb2b90-2383-50d7-b6e5-81b1823f8486 | note | ○ Native seeding of topsoil stockpiles as agreed with Company.
152c1158-6847-5db7-8ff6-9420d732d0a0 | note | ○ The provisional depth of stripping shall be 150 mm unless shown otherwise on the drawings
b69bcd59-53bd-5606-8487-646f39a58001 | note | Specification Clause - C9 of EVAMP001-QVT-PE-PRM-1
a5ea82f0-eb8f-56e4-a07a-f6157d674465 | note | — EVAMP001-EVA-EN-DCR-0002
68024f57-8529-502f-97fb-e88347bebd79 | note | — EVAMP001-EVA- EN-PLA-0001
350f585c-97b0-5084-ae05-9f8ca7241d49 | note | — 107501-EB- 00000-27280-001 Rev A
70669dd5-9057-5285-9173-aa3d893e9efe | note | Frequency - As required
b2b7f49b-54dc-5f18-b99c-d23dd5bd19d3 | note | Verification: THIESS (Initial) - HP
6c2b69af-1ff1-5668-b4df-36691c8805fa | note | Verification: Client (Initial) - W
841c83d5-857c-4dbe-a647-12e60695f306 | signoff | WITNESS POINT
02f71ad7-e8a4-4585-83dc-b013eef0a969 | checkpoint | 7 - Topsoil location, destination and quantity catalogued.
068b036e-522a-5bfc-a0fd-67fe02503804 | note | Responsibility - ENG
894c69e0-4a6c-57cb-ac5d-0eceac6ccbf0 | note | Method - Field Test
c5fc7914-d3cf-5586-a1d6-87d309b46708 | note | Conformance Criteria - A topsoil inventory will be maintained with information on topsoil volumes and stockpile locations
b0bb0db9-4ec2-55af-b5b3-cc10585793e9 | note | Specification Clause - EVAMP001-EVA-EN-PLA-0001
c7ca3ae5-4222-5f25-afea-c94599e22349 | note | ○ EVAMP001-THS- CV-REG-0003
9db2f9e6-a958-51f6-9269-37ec894d2e4d | note | Frequency - As required
1d14ae1f-2398-5019-9ade-87b064dd8b81 | note | Verification: THIESS (Initial) - HP
b8ee2c11-d47c-56d2-8f65-e957799175f2 | note | Verification: Client (Initial) - HP
8650afee-cdd6-45cf-a6e8-83d631f09683 | signoff | HOLD POINT
5104befa-de89-4f28-b970-43f37f8f45b4 | checkpoint | 8 - Surface level check/post-strip area and volume survey pick-up
04f60c26-69e9-5995-88a5-f41fa9fe107d | note | Responsibility - SURV
3438c3e1-0d55-5d81-91a0-b12e9571e501 | note | Method - Survey/Field Test
fd8d767d-7dec-55b2-93b3-34e7fba9c304 | note | Conformance Criteria - DXF file submitted to Company and inventory updated
c78ee30b-8f70-5a49-9ab8-a8931ac9a6db | note | Specification Clause - EVAMP001-EVA-7340-PE-PRM-0001
befffdea-0cf5-50c3-8f41-749e87394115 | note | Frequency - As required
743a0459-1a6a-553d-a38d-b30a655a923a | note | Verification: THIESS (Initial) - HP
4792d11d-7842-5e50-9fbf-93420c852649 | note | Verification: Client (Initial) - W
80742484-eee7-4467-832e-ea20e49dbaf9 | signoff | WITNESS POINT
e06be554-ef9f-4c13-b6a9-8eadbc8aabae | section | 3 - Post Construction
9789f97b-8d3f-4c7d-bea7-0bada95ba9a2 | checkpoint | 9 - Works completed and update ITP/ Lot Register/ MDR and close out of GDP
e904e364-cd35-5909-8f55-da5ef86a8515 | note | Responsibility - ENG
3994174c-c988-5ed1-a4b6-0ed00b3d1cba | note | Method - Visual
3bc71412-bff9-5f51-8146-d2561552a3e9 | note | Conformance Criteria - GDP permits closed.
5c3c2402-b346-5c07-8ad0-af2662568473 | note | ○ ITP closed. Approved MDR
cfdee6fd-9a70-5883-9295-857e33bc5f96 | note | Specification Clause - EVAMP001- EVA-7340-PE- PRM-0001
3ceb5748-756a-59e8-bbf4-2aad50430fd3 | note | — EVA PMP
b5ea251e-f767-5c20-8af9-23453232a67f | note | Frequency - As required
b3abc8f0-5100-5a1d-a0ea-d570c9910c4e | note | Verification: THIESS (Initial) - HP
1720935b-24e5-5a70-ac1e-7951f54fad2d | note | Verification: Client (Initial) - HP
f3f6c0de-eb42-4415-8871-7a9e78f6961c | signoff | HOLD POINT
3fe6c12b-1b2e-4c38-b8d0-425f5f150f54 | checkpoint | Final Inspection
756030b9-dc70-5e21-9e75-e579e56ceff2 | tickbox | Conformance to Specification
b8651b46-c877-5252-ae40-b57f4790fb62 | tickbox | Requires Re-Work:
440e874b-3264-5107-8d30-24d0bb436dab | textbox | (Provide Details):
4b97aab6-16d2-5761-8954-f37fddeaadb9 | tickbox | Non-Conformance
cb69cc2f-b3f1-54c7-bfd3-ce0184bb27eb | textbox | NCR No:
99104eec-f7c4-4c6a-be14-9b7bc2d85c2f | signoff | Approved by THIESS QA Representative / THIESS Project Manager / Client
7a49fa02-b542-4f06-aed8-44a7c534570d | checklist | EVAMP001-THS-QA-ITP-0002 - Topsoil Stripping - Global Lot | itp | EVAMP001-THS-QA-ITP-0002 - Topsoil Stripping - (Global Rev. B)
da3138eb-09d1-4a92-8bc5-a424dc7885bf | section | 1 - Pre-Construction
2de2b913-4167-4e82-9432-efe8465bb73c | checkpoint-no-value | 1 - Underlying lot & ITP signed off and conforming (REFER TO SUBLOTS)
f34ac06a-1db1-4249-9cf5-07e0c272faaa | checkpoint | 2 - Drawings supplied most current IFC
63b1f38c-562b-5ca2-8c1d-a7313da24ba0 | note | Responsibility - ENG
eb37e7e7-74fa-562d-8d6f-3879b815da58 | note | Method - Visual
b9f2cb0f-adbe-5e51-8c97-bb55a0107499 | note | Conformance Criteria - Reviewed drawing register
d134f6e9-c969-5daa-bab7-37b4ae58adac | note | Specification Clause - Reviewed drawing register
6173ba04-a5bc-53dd-82f8-ae425f5f1b6b | note | Frequency - Prior to works
17505b77-582e-5058-b64f-dd4d779548a9 | note | Verification: THIESS (Initial) - HP
0436bee3-ca4b-5f2b-b62a-d67be88a3e03 | note | Verification: Client (Initial) - W
db1a1429-2735-40d4-8341-2ba7df8a32c8 | signoff | WITNESS POINT
1012d911-cf7c-4e0a-bbb1-a58fcfffdb56 | checkpoint | 3 - Check existing services and dial before you dig
5452ccf3-4e57-5a02-8ee0-f6d07413da2d | note | Responsibility - ENG
6bfcb91c-b304-5040-97ca-ae36fdb20a07 | note | Method - Visual
7f865b8a-5733-52f4-a1b4-95faa6767dcb | note | Conformance Criteria - DBYD certificate and EP
f5536559-4a6d-5893-8177-c7f3acc20572 | note | Specification Clause - Excavation Permit (EP) Doc no.
09109048-af2d-5302-bbaa-72cff50b2a21 | note | Frequency - Prior to works
829c87f9-9388-53bd-a234-d61107fa2bb0 | note | Verification: THIESS (Initial) - HP
b03dc187-9067-5cfd-8382-cdcfe0701793 | note | Verification: Client (Initial) - HP
758bc98c-8c92-4224-9155-0ebbaec9ad71 | signoff | HOLD POINT
4aedcde4-2e25-4347-ac5c-459806af1206 | checkpoint | 4 - Ground Disturbance Procedure (GDP) obtained
c6f2e774-f5d6-538d-83d1-a28480d971d8 | note | Responsibility - ENG
6f2412b4-ac28-51f3-a20a-d92e1e9e4643 | note | Method - Visual
dee5924a-22a6-5a77-9f4e-28495b57a214 | note | Conformance Criteria - GDP permit with work packs
dc2c797d-f141-52e4-bd10-6d0f5dbd7ee8 | note | Specification Clause - EVAMP001-EVA- 7340-PE-PRM-0001
aa587f56-d0d4-5497-9008-e4f1bd18851c | note | Frequency - Prior to works
9be8329d-58e4-549c-bb83-c9a0293ae1c5 | note | Verification: THIESS (Initial) - HP
0049b511-9bf9-54e5-b370-e297591e7362 | note | Verification: Client (Initial) - W
e98556d4-792f-4cf2-b067-aa155970e785 | signoff | WITNESS POINT
f661993a-da18-45ab-9d09-e35e50f5d9f0 | checkpoint-no-value | 5 - Area of works pegged and clearly defined to GDP. Pre-strip area survey pick-up (REFER TO SUBLOTS)
db980d36-b393-4cae-96a5-5d92d16fdff9 | checklist | EVAMP001-THS-QA-ITP-0003 - Subgrade Preparation | itp | EVAMP001-THS-QA-ITP-0003 - Subgrade Preparation
a3728f01-7949-462b-a069-9f4a9c5708f7 | section | 1 - Pre-Construction
e956ccaa-3b5c-4b88-b1bd-0c5a9fb602ad | checkpoint | Lot Map
ec7d65fc-9244-48e8-969f-84a7bea75889 | checkpoint | Test Results
64407864-774c-4fa9-b98f-dcc227a852b5 | section | 2 - Construction
919c395d-1f97-4282-9f28-f63691b5c18b | checkpoint | 6 - Underlying lot & ITP signed off and conforming
68624404-36f1-583e-92db-a98ff217b5e7 | note | Responsibility - ENG
03f189a1-adc1-537f-acb6-e78d1c74de16 | note | Method - Visual
cc753c97-023f-564e-908e-020a68ea60b2 | note | Conformance Criteria - Topsoil stripping ITP signed off
79d299d0-42b7-5176-8211-2afb0d143cd0 | note | Specification Clause - Approved QMP
e6c2d882-e1e0-5419-ab31-7243ae5fe949 | note | Frequency - Prior to works
83724454-bc64-504e-ba2e-48e89fc6209a | note | Verification: THIESS (Initial) - HP
a77f0315-4624-5ae3-bbe8-c5b952bd749f | note | Verification: Client (Initial) - W
762ece96-d03b-45c5-8a54-66dbae60b72c | signoff | WITNESS POINT
8e9dbe40-a5cf-4f64-9c0f-facab2d71738 | checkpoint | 7 - Removal and replacement of unsuitable material
f73d3e12-a1cd-5a8b-a064-b4fb73ba4089 | note | Responsibility - SV
03956dbd-a0ab-5499-858d-a9f37f12e7b3 | note | Method - Visual
914e75d9-b106-5473-a8e0-b45a58fbc487 | note | Conformance Criteria - Determination of unsuitable material by the Level 1 GITA or Principal is required prior to the removal of any unsuitable material.
81aa9528-8ffa-57bc-9d44-2191dcf68cf5 | note | ○ Unsuitable material shall be disposed as directed by the company or in areas specified in the annexure.
13f2b256-8293-54a0-9f89-0b99823a6f85 | note | Specification Clause - EVAMP001-THS- CV-SPE-0001
a43a01a3-b6b0-5a25-b85a-3ebdf20f7bb7 | note | Frequency - As required
b8c135cb-a494-5646-8ec8-e00b1b4757b9 | note | Verification: THIESS (Initial) - HP
5e9ef728-55b9-574b-8268-717bfa4b589f | note | Verification: Client (Initial) - W
00b55881-f2e3-4133-82eb-3496308d2180 | signoff | WITNESS POINT
00d679e7-d09d-429c-9998-09e7552b433a | checkpoint | 8 - Subgrade preparation – 200mm depth
e2eebd06-a2fc-5579-ad58-e628b49acc06 | note | Responsibility - SV
badfeb2f-8642-5752-acab-116aae4aa317 | note | Method - Visual
faa735b0-fdf1-5a15-98ba-85386707f954 | note | Conformance Criteria - Area to be ripped and conditioned to suit a minimum CBR value of 10.
1f4a78f8-82da-5928-a6cc-fff806c2495c | note | Specification Clause - C10 and C14 107501-EB-00000-27280-001 Rev A
233ea6ef-885c-5e8a-a670-e19478844992 | note | — EVAMP001-THS- CV-SPE-0001 clause 4.16
552ce3b6-ff77-560b-9257-72d3ae5ecd08 | note | Frequency - As required
2d46c621-efa4-5491-941f-985568789c8a | note | Verification: THIESS (Initial) - HP
e88c16c1-f089-5b5f-accc-88eb9c45a907 | note | Verification: Client (Initial) - HP
97ef884e-5d14-4529-a0da-cdb0fcd944bc | signoff | HOLD POINT
942e2cc5-650c-4b58-8b69-c00cb79a6050 | checkpoint | 9 - Proof-roll subgrade surface prior to placement of embankment fill
c7af55be-697b-5153-b670-3e84c2e96e63 | note | Responsibility - SV
09c73cf9-a7a2-5d82-8d4b-2c0bd829eb50 | note | Method - Field Test
36d3a400-5525-5bcb-b248-924fd46371fe | note | Conformance Criteria - All subgrades and foundations shall be proof rolled under a standard 8 tonne axle load to confirm that, in the principal’s opinion, deflections are negligible.
3d52e9d4-81c0-5505-af79-f9833db3ce7e | note | Specification Clause - EVAMP001-THS- CV-SPE-0001 clause 4.16
0a025c1b-81d5-5d4c-b1b7-523781061e80 | note | Frequency - As required
7a05aeab-7603-5bf5-8472-c2602289a658 | note | Verification: THIESS (Initial) - HP
d865f730-a19a-5340-a948-151678a800e0 | note | Verification: Client (Initial) - W
f75d0c6d-2faf-4078-b6a1-e197e60122be | signoff | WITNESS POINT
b6b366a3-5408-4251-8269-ce84604dde79 | checkpoint | 10 - Surface level check/ and survey pick-up
962c3e74-d737-5ce0-aa66-e97c533f2d08 | note | Responsibility - Surv
2155f7cb-ccf2-5077-adac-13a031e94003 | note | Method - Survey/ Field test
e3f84197-67d4-57fb-90e3-c12e9678be99 | note | Conformance Criteria - Surface level as per Table 10 C15
ad0ea4a5-91eb-5858-a6cf-7efcc1366f74 | note | ○ DXF file submitted to Company
13dd35fc-3a74-5da7-b24c-105cb34a9596 | note | Specification Clause - EVAMP001-THS- CV-SPE-0001 clause 4.16
42e75c73-ace3-5dc9-953d-589af7caf2c5 | note | Frequency - As required
7458c5d8-daac-50ef-8dce-e0ff8ba33721 | note | Verification: THIESS (Initial) - HP
61c52c2e-2aa1-5e4f-974b-f34672327276 | note | Verification: Client (Initial) - HP
443a13dc-9996-4492-b97e-0432ab2d6f51 | signoff | HOLD POINT
84f84b57-1479-4568-b984-83e8bc7c55ec | section | 3 - Post Construction
04029cd9-69f4-4343-bf5c-2685ca58e6be | checkpoint | 11 - Works completed and update ITP/ Lot Register/ MDR and close out of GDP
065e6724-8a6a-5899-aa74-4cfe5a626dee | note | Responsibility - ENG
fa3f9f99-31b4-526e-aa91-af724b07b376 | note | Method - Visual
c5ab272c-f0b4-51dc-a0d0-01597e939177 | note | Conformance Criteria - GDP permits closed.
a70d4651-6e27-52f3-bf91-c2fb5fe09beb | note | ○ ITP closed. Approved MDR
0ee368aa-f400-5806-bebb-44dde7021f20 | note | Specification Clause - EVAMP001- EVA-EN-PLA- 0001
e9788671-4d00-5a6e-a6ca-310b519c8e94 | note | — EVA PMP
8d16f1ec-84e6-5542-a08f-e7c15a3f7514 | note | Frequency - As required
4d529521-5b2c-5920-893f-4ec9baa2e25d | note | Verification: THIESS (Initial) - HP
d425ee3f-4815-5fa3-9fb0-cc42717f415f | note | Verification: Client (Initial) - HP
d2eddce9-014b-45d7-b02b-6fefccb5fc00 | signoff | HOLD POINT
16793a3e-90a6-495c-ab04-025bd238e148 | checkpoint | Final Inspection
bbf8c7f5-f960-5383-a263-b3f517e4a3d8 | tickbox | Conformance to Specification
33d3b783-7aad-53c2-a189-ae4041f36e8a | tickbox | Requires Re-Work:
e82b2fdf-244f-5c92-b0c4-b3d031f56bd4 | textbox | (Provide Details):
734a7b6b-d3bb-5845-b791-f3dc9c14a0f4 | tickbox | Non-Conformance
c2c5b5da-56ec-5488-84f9-980dea82d593 | textbox | NCR No:
c6ba9168-1177-4b63-846f-fac64b35ef93 | signoff | Approved by THIESS QA Representative / THIESS Project Manager / Client
6a11b2a7-3bb5-4f28-93bf-f9317191332e | checklist | EVAMP001-THS-QA-ITP-0003 - Subgrade Preparation - Global Lot | itp | EVAMP001-THS-QA-ITP-0003 - Subgrade Preparation (Global Lot)
5f51824f-f07f-4e9f-9eb1-8a2d83b62efb | section | 1 - Pre-Construction
590ffd40-44d5-4e78-82f2-8d59dfd1e37e | checkpoint | 1 - Drawings supplied most current IFC Retrieved from InEight
d2d3733c-2a44-5bda-afe6-6b8285577657 | note | Responsibility - ENG
21f9d1e0-2706-5f2e-9016-c5745a2796dc | note | Method - Visual
c843b7cf-9327-50cd-bafe-9c20a578ce12 | note | Conformance Criteria - Reviewed drawing register
1f36333d-d67f-5027-8688-aa9fafa3ca5c | note | Specification Clause - Reviewed drawing register
19ecbe90-45eb-58f7-b617-f6bd3a14a401 | note | Frequency - Prior to works
8cc0362e-03cd-5b32-8210-7e17c70ca2b3 | note | Verification: THIESS (Initial) - HP
9a8ea906-da82-54d6-9579-b9d14bfc9eb6 | note | Verification: Client (Initial) - W
094741de-c040-46fe-888c-2afbdb0144d5 | signoff | WITNESS POINT
c60240eb-a228-4088-ad42-41d14adb2165 | checkpoint | 2 - Management Plans submitted and approved as per PMP
0a0e9fc3-d274-5fc6-9f57-df74195c497e | note | Responsibility - ENG
e3cc226e-b094-5f75-bb74-6b4e74faeb83 | note | Method - Visual
4d2a8fa9-3ea7-512c-b94b-02d4fa30efd2 | note | Conformance Criteria - Approved Package MP’s
1eac4c94-2620-517f-89f3-a7740741edba | note | Specification Clause - Approved Package MP’s
9f182d1f-963e-51d9-a306-ecdfc73659a6 | note | Frequency - Prior to works
6f54bd9b-2c8f-513b-86dd-7d9d9178288d | note | Verification: THIESS (Initial) - HP
62b2cdc9-add1-51da-b433-a6c965ba8855 | note | Verification: Client (Initial) - W
630ed720-ebbb-4ca2-9030-52ce01538995 | signoff | WITNESS POINT
174aea8f-e4c6-4e03-8327-82eb08a4a694 | checkpoint | 3 - Inspection Test Plan (ITP) submitted and approved
e7ac2421-5425-5cae-b718-eb00bb14841d | note | Responsibility - ENG
ce9f71a5-862c-5de1-9844-a3723d632f7e | note | Method - Visual
40224ae5-65a5-5078-a48b-f5767c225e9c | note | Conformance Criteria - Approved ITP revision
c521a7d6-961f-5ccf-a157-525c2fb3c83c | note | Specification Clause - Approved ITP revision
1d309c8b-04a1-5df5-850c-8f0b09cc7ba1 | note | Frequency - Prior to works
e8891c51-94b9-5825-82d5-19558d35e4f9 | note | Verification: THIESS (Initial) - HP
5b1aa8bc-49f1-5387-8edb-755bd77ba34a | note | Verification: Client (Initial) - W
dc44237c-dac9-497d-8013-665d7724d8c9 | signoff | WITNESS POINT
4f2531ac-f5fc-4fcf-bf76-62ae27d1696f | checkpoint | 4 - Lot Register/ WBS submitted and approved
969e213c-905a-5887-9713-4d93107c396f | note | Responsibility - ENG
82a0ec28-d332-5001-8383-fa24436b4228 | note | Method - Visual
c040dfca-12c5-5bcb-9478-9a79b4f61011 | note | Conformance Criteria - Approved WBS
19252cdd-afd9-5e9f-baf6-4572b6242d69 | note | Specification Clause - Approved WBS
c97fc9b5-e770-53ce-b8fa-0125253812f3 | note | Frequency - Prior to works
1ebadab9-678c-5699-8aca-93c18813babd | note | Verification: THIESS (Initial) - WP
d2d72935-fb7d-5a3d-a2fc-6888d7565da9 | note | Verification: Client (Initial) - W
0b10c07c-6516-4d1b-8aee-16e0405d94ee | signoff | WITNESS POINT
845b0ced-fb75-4660-88ee-d5ee43d3e95a | checkpoint | 5 - Check existing services and dial before you dig
70ab0ed5-3679-585b-8552-574649778141 | note | Responsibility - ENV/ENG
e9239656-4c63-50d2-bb45-206bdbbde368 | note | Method - Visual
e468b8bc-cdbf-50c8-83f0-3053b66339a7 | note | Conformance Criteria - Approved erosion and sediment control plan
849a38a7-4a5f-5634-b77a-7c4327028029 | note | Specification Clause - EVAMP001-EVA- EN-PLA-0001
a3b7a595-9333-5296-a864-be9222ea8712 | note | Frequency - Prior to works
f8c992b6-9bea-5c19-96d2-ed73c1ee66c6 | note | Verification: THIESS (Initial) - HP
2b310fac-c2bc-5c76-b0d5-0033d4f33221 | note | Verification: Client (Initial) - HP
0b5c0738-e8a0-411b-941d-84b03a35ed5f | signoff | HOLD POINT
84c66102-7f0a-4d90-be3f-40506d45f252 | checklist | EVAMP001-THS-QA-ITP-008 - Embankment Construction | itp | EVAMP001-THS-QA-ITP-008 - Embankment Construction
d573f8aa-580e-4fe9-a11f-654a1f726426 | section | 1 - Pre-Construction
1041a7e1-2fa9-4185-95dd-18228d494083 | checkpoint | 1 - Drawings supplied most current IFC
4352b278-c32a-5914-bd8d-6881f33698f5 | note | Responsibility - ENG
e053e9ea-07bd-5b22-bd18-ee55ef18ccdd | note | Method - Visual
dd2722a6-73b8-584e-967d-6585390834f8 | note | Conformance Criteria - Reviewed drawing register
9fa9f463-eec2-5894-bbbb-0b3b524d0bcb | note | Specification Clause - Reviewed drawing register
2df548fb-fe8d-5dd0-a954-90858b0b154b | note | Frequency - Prior to works
3d219ae7-9e1b-5e92-9b4e-cb193a8b112d | note | Verification: THIESS (Initial) - HP
0848e2bf-b25a-5934-8b42-0e9e4aa6ef17 | note | Verification: Client (Initial) - W
50e61aea-384e-4e6b-b2d6-f7e0f831815f | signoff | HOLD POINT
fecd7c5d-8b39-42e2-bf2a-de1ab61f67a4 | checkpoint | 2 - Define Lot dimensions
be9a0d3e-1579-5700-9dfa-951cab705cb4 | note | Responsibility - ENG
fad3b30b-e912-5b37-870c-1fb928ab8b69 | note | Method - Visual
df9439d9-7a72-5a43-8648-71dfd3bc2b56 | note | Conformance Criteria - Allocate Lot No to ITP and update Lot register
4ee754de-5702-58f9-8040-3d88bd3aadc2 | note | Specification Clause - Lot register.
0b43bc80-10ff-505a-bb00-d871d26e3c83 | note | — EVAMP001-THS-CV-SPE-0001
d62576fe-2be8-52bd-ab9d-7b3f0e1a0161 | note | — EVAMP001-THS-CV-SPE-0002
710dc26c-bd18-56f7-9cb2-7f6c2437cf4a | note | Frequency - Prior to works
ad77617d-3971-519a-b954-a03aabad66b6 | note | Verification: THIESS (Initial) - HP
69e04f89-ae2a-52aa-84a4-6cfbc50a7900 | note | Verification: Client (Initial) - W
c4fe1aad-5f63-4d3b-b781-c3de9184ff7c | signoff | HOLD POINT
1541ff49-ccd8-4442-8e41-0a3786539f93 | checkpoint | 3 - Lot Register/ WBS submitted and approved
32ebdd98-d099-56f9-bc5b-d3411050ff50 | note | Responsibility - ENG
82a4eb77-535b-5c21-8ea1-062ae34ddeed | note | Method - Visual
2cf2f278-dbfb-525e-a36c-55461e734992 | note | Conformance Criteria - Approved WBS
e16ca92a-512a-5f04-a334-f5eccf633946 | note | Specification Clause - Approved WBS
91313960-c57c-55db-b7eb-7abb2673a027 | note | Frequency - Prior to works
6ebed981-5e80-5282-aba9-cb83a829aa7c | note | Verification: THIESS (Initial) - WP
2ac3141d-9d21-5cdf-a22a-cbd699e99c09 | note | Verification: Client (Initial) - W
3ca6ea58-5f28-4eda-ad69-ffbcef88b1bc | checkpoint | 4 - Underlying lot & ITP signed off and conforming
cf2ba22b-dde2-55e8-aa8c-05ea79a5bca8 | note | Responsibility - ENG
a6ee57e0-e80f-5ae9-8b05-9a9421bf3649 | note | Method - Visual
bae417f8-60b4-5f10-a89e-90d522ea8877 | note | Conformance Criteria - Topsoil stripping ITP signed off
0f36e061-625f-5501-b159-88eaaa6ca1fb | note | Specification Clause - Approved QMP. Approved ITP
2af79ea6-5c39-5012-b5f7-c29f55f80462 | note | Frequency - Prior to works
74696de6-7532-5af5-a60a-b9b6201839aa | note | Verification: THIESS (Initial) - HP
aa0903b1-55f9-55ae-9c93-e38408fdb190 | note | Verification: Client (Initial) - W
495b089c-d47e-48f6-bd24-0397161b986f | signoff | HOLD POINT
af8f03ff-aecd-4b72-ac0f-e0f17dffdaf2 | section | 2 - Construction
3e503bda-adf8-4a3d-b12d-844809a52fc5 | checkpoint | 5 - Ensure Embankment Construction materials have been approved for use and within specification
e97b1254-9480-5111-a1e4-7af59eb29eb4 | note | Responsibility - ENG
faf579b6-36dd-5a6a-9c5f-317bee137716 | note | Method - Visual
b511de5d-2359-54f1-9f47-02f56f9aebfb | note | Conformance Criteria - Embankments (general fill material)
c4792551-d1cd-5bad-bceb-d1f3770da6d3 | note | ○ Less than 30% passing 0.075mm sieve
71a3d2d6-e73e-506a-9638-7f51773a8194 | note | ○ Liquid limit 20% to 60%
7c22521d-cc79-549a-8dff-c3a5b225d1cb | note | ○ Soaked CBR = or >3% (STD compaction @ OMC), 1 test per 5,000 m3
9e54ac0e-1775-5d3c-9037-1a0ddf38a997 | note | Specification Clause - EVAMP001-THS-CV-SPE-0001
e83ba7f9-7619-53fc-b95d-996b939cc3d9 | note | Frequency - As required
f799b2f4-602b-542d-8cc9-860c66bab38e | note | Verification: THIESS (Initial) - HP
dbb2fba1-efbc-57bd-b306-010fe4c67f0f | note | Verification: Client (Initial) - W
0f5fdaa9-3d7e-4477-ae83-ed36d1c87e35 | signoff | HOLD POINT
aa5ee103-9d03-4083-8c0c-8a877f03e649 | checkpoint | 6 - Construction Layer Thickness (300mm)
52f80590-8372-51ba-9948-da746330c8f1 | note | Responsibility - SV
7a248c1a-0f37-517a-9620-d60f8c0442f0 | note | Method - Visual
7d8b8ef8-91e3-5f13-9124-1285b9aac584 | note | Conformance Criteria - Depths of such layers shall not exceed the capability of the proposed plant and in any case shall not exceed 300 mm uncompacted.
ea4c7b71-a997-5fee-ac6d-c0168054a42f | note | Specification Clause - EVAMP001-THS-CV-SPE-0001 clause 4.17
830c3dbd-e35b-5f70-86c2-b348d43f9938 | note | Frequency - As required
59cae5a5-3080-57af-8ebf-786c407434eb | note | Verification: THIESS (Initial) - HP
12b70be1-577a-5700-adf9-63497b78bd91 | note | Verification: Client (Initial) - HP
c1e21529-c268-5a8d-ad35-493bfdc915c6 | note | Records or Comments - On site verification sheet and survey
d300c5de-f0fb-4827-aea4-4b8d2364cc00 | signoff | HOLD POINT
2401d6ae-a888-4353-a36a-61edc1516728 | checkpoint | 7 - Place and compact general fill layer – Subgrade
e3e11055-289e-5bbc-b84e-19c20bf97d4a | note | Responsibility - ENG
31ff3671-c583-50c0-bbc9-5cead1fbd6f8 | note | Method - Field Test
363452a7-33a6-519d-bb28-a818d4673302 | note | Conformance Criteria - Material containing a high proportion of large particles may be used in embankments using the Mechanical interlock method of construction.
bbde3292-a54c-5505-8ba3-4cc7b2bd05ea | note | ○ Field density standard minimum Dry density test to be 95%, OMC -1%, +2% with a minimum layer thickness of 150mm and maximum 300mm. Material greater than 600mm may be allowed to be used in the Embankment.
3973bfc7-ae3d-5537-8255-57bf4baf24c9 | note | Specification Clause - EVAMP001-THS-CV-SPE-0001 clause 4.17
176b105e-efc4-5761-af91-1c5038b2e090 | note | Frequency - As required
c99f7572-11c9-55c9-9e03-2cbf0d277651 | note | Verification: THIESS (Initial) - HP
7754342d-3f15-5efd-a8cc-cb5505a2bd73 | note | Verification: Client (Initial) - W
543b9466-2dfe-5c6f-9f26-b457208202b2 | note | Records or Comments - On site verification sheet, NATA Test report
85d2740d-8b78-402d-8698-1b694ed34533 | signoff | HOLD POINT
d09041f1-5201-4ee0-8dc5-776936853523 | checkpoint | 8 - Subgrade in cut
54d5fc29-b4e4-5fcc-887a-46a1ffa76b0a | note | Responsibility - ENG
4f12ba52-2d81-5e23-a637-0b1658413f5e | note | Method - Survey/ Field test
dd19a455-ef3d-5341-9b55-7a7e63fdea97 | note | Conformance Criteria - For subgrades under road/rail pavements and buildings/structures, the materials exposed at the subgrade level of cuttings is to have a minimum CBR of 3.
3c3a14a0-4fa5-5155-9458-8d7b12b8b5b7 | note | Specification Clause - EVAMP001-THS-CV-SPE-0001 clause 4.16
1760669b-07ca-5e06-a6bc-ebd8f646b05e | note | Frequency - As required
bb15657c-a19c-5f2e-947b-d4e56c8a05cf | note | Verification: THIESS (Initial) - HP
9ed98f89-0710-581e-8810-446ca4dd070f | note | Verification: Client (Initial) - HP
1c20c79f-9eb0-4515-9501-35ef6daf37d5 | signoff | HOLD POINT
d636cc89-bd23-4641-aff5-dd4dde485208 | checkpoint | 9 - Proof rolling
91c09909-6ddf-51a3-8567-ae094b1ee899 | note | Responsibility - ENG/ SV
b9c6cefd-5a3a-590d-acd6-8ed06a64d5f5 | note | Method - Field test
f202b0b9-448f-56a3-89d2-e733fbd2b292 | note | Conformance Criteria - The embankment will be proof rolled with either Proof rolling shall be undertaken using a 10,000 L water cart or heavy, self-propelled, smooth drum vibrating roller capable of operating in variable frequency modes.
a89fee8c-f5ea-52d9-ab7b-a6d5cb45ea3a | note | Specification Clause - EVAMP001-THS-CV-SPE-0001 clause 4.26
7d94b44f-cc6a-5b87-a4f0-dff8efbc96c7 | note | Frequency - As required, Each lot
1f0d3aed-52fd-5d42-88fe-94783368cffd | note | Verification: THIESS (Initial) - HP
c14f4b90-5570-5ca5-9de2-470bb929b8bf | note | Verification: Client (Initial) - HP
7a964c0e-1194-5c52-91d9-480d35d86aec | note | Records or Comments - On site verification sheet
8f79d321-3968-40bb-99e6-5b831964878d | signoff | HOLD POINT
c4ee4fac-e992-41ce-978e-a6181be507f3 | checkpoint | 10 - As-built of completed surface
3e9f7865-da4d-537c-b9cd-247adf27801c | note | Responsibility - ENG/SURV
517ad2d9-d303-5ecc-a41a-a2f016574237 | note | Method - Survey
bacd9556-412a-51b9-b839-eebefee9c508 | note | Conformance Criteria - Survey to be completed of the finished surface to confirm to the levels as shown on the drawings with deviations as per Top of earthworks other than the subgrade and pad level ± 50,
e00c3626-2623-53c5-98d8-56d937ef5d8c | note | ○ Road subgrade & building / structure pads +0 -25
0c72d224-ff74-5e55-96bf-59a59112f48a | note | Specification Clause - EVAMP001-THS-CV-SPE-0001 Appendix A clause 6
54e4762a-c3ef-5175-a762-74b8248d8ba0 | note | Frequency - Each finished surface
c5e4cd03-79a9-59a5-a28e-4bb650d0167f | note | Verification: THIESS (Initial) - HP
d86ff281-0cad-5b0e-9e0f-d5d750e81694 | note | Verification: Client (Initial) - HP
606c3d68-2a26-533d-a94c-c7632c899bee | note | Records or Comments - Survey report
92710511-b8ab-4943-bac1-b94f69f5ab88 | signoff | HOLD POINT
0a9b25b3-1a80-4783-a610-0d0be47c2530 | section | 3 - Post Construction
8a9f2a88-875d-47f8-8a51-f078b6358a5f | checkpoint | 11 - Works completed and updated ITP/ Lot Register/ MDR and close out of GDP
a76e19d5-8702-5269-911a-270f117726a9 | note | Responsibility - ENG
30eda4e8-ff94-54d4-bba1-fbce9f37d07e | note | Method - Visual
bcaedf8f-218b-534f-87f7-0dc374245056 | note | Conformance Criteria - ITP closed. Approved MDR
35c57f97-7d59-56c0-a9dc-c69cb884e52f | note | Specification Clause - EVAMP001-EVA-7340-PE-PRM-0001
f04f4dc7-408b-5b38-9266-2bcd95d0358a | note | — EVA PMP
42d01794-e014-582b-ae64-339379c09db8 | note | Frequency - As required
6c3dc22c-f90d-5a97-895e-c014ea6fd319 | note | Verification: THIESS (Initial) - HP
363ee473-d748-544a-affc-4817b18c27d7 | note | Verification: Client (Initial) - HP
35fc172a-827b-4dee-967e-47d3f75aa99f | signoff | HOLD POINT
ae8011b7-9f2f-4c74-9e2c-520cdecf338c | checkpoint | Final Inspection
6e87df0e-8783-550f-a8ce-bef7ecc6ff27 | tickbox | Conformance to Specification
4503d9b4-447f-59b0-b666-b9cb688600f8 | tickbox | Requires Re-Work:
a0d2a9eb-d281-5edb-a487-5f154f089d3d | textbox | (Provide Details):
9e76af3a-b5f2-500a-b2f2-746b4a49c5d5 | tickbox | Non-Conformance
c15177d0-1957-5aca-8226-fb591475a16e | textbox | NCR No:
606cf50f-95ca-42d4-b068-758a15dd64d5 | signoff | Approved by THIESS QA Representative / THIESS Project Manager / Client