## Sheet1
- | Responsibility - | Test Method - | Conformance Criteria - | Frequency - | Link to ITP - | Thiess HP/WP Check - | Sedgman HP/WP - | - | RS1.1 | Drawings supplied most current IFC | ENG | Visual | Reviewed drawing register | Prior to works | HP | RS1.1 - Drawings supplied most current IFC | Responsibility - ENG | Test Method - Visual | Conformance Criteria - Reviewed drawing register | Frequency - Prior to works | HP/WP - HP | RS1.1 - Drawings supplied most current IFC
[8 empty] | Responsibility - | RS1.2 | Management Plans submitted and approved as per PMP | ENG | Visual | Approved Package MP’s | Prior to works | HP | RS1.2 - Management Plans submitted and approved as per PMP | Responsibility - ENG | Test Method - Visual | Conformance Criteria - Approved Package MP’s | Frequency - Prior to works | HP/WP - HP | Responsibility - ENG
[8 empty] | Test Method - | RS1.3 | Inspection Test Plan (ITP) submitted and approved | ENG | Visual | Approved ITP revision | Prior to works | HP | RS1.3 - Inspection Test Plan (ITP) submitted and approved | Responsibility - ENG | Test Method - Visual | Conformance Criteria - Approved ITP revision | Frequency - Prior to works | HP/WP - HP | Test Method - Visual
[8 empty] | Conformance Criteria - | RS1.4 | Lot Register/ WBS submitted and approved | ENG | Visual | Approved WBS | Prior to works | WP | RS1.4 - Lot Register/ WBS submitted and approved | Responsibility - ENG | Test Method - Visual | Conformance Criteria - Approved WBS | Frequency - Prior to works | HP/WP - WP | Conformance Criteria - Reviewed drawing register
[8 empty] | Frequency - | RS1.5 | Check existing services and dial before you dig | ENG | Visual | DBYD certificate and EP | Prior to works | HP | RS1.5 - Check existing services and dial before you dig | Responsibility - ENG | Test Method - Visual | Conformance Criteria - DBYD certificate and EP | Frequency - Prior to works | HP/WP - HP | Frequency - Prior to works
[8 empty] | Link to ITP - | RS1.6 | Ground Disturbance Procedure (GDP) obtained | ENG/ENV | Visual | GDP permit with work packs | Prior to works | HP | RS1.6 - Ground Disturbance Procedure (GDP) obtained | Responsibility - ENG/ENV | Test Method - Visual | Conformance Criteria - GDP permit with work packs | Frequency - Prior to works | HP/WP - HP | HP/WP - HP
[8 empty] | Thiess HP/WP Check - | RS1.7 | Materials for signs | ENG | Visual/ Manufacturer warranties and/or certificates | Signage panels fabricated from 2mm thick aluminium sheeting conforming to AS1742. Sign face shall be non-reflective (NR) with the vinyl film conforming to appendix B of AS1743. Post sections are to comply with AS1163 and be in accordance with the following: Steel circular hollow sections in accordance with grade C250L0; and Steel rectangular hollow sections in accordance with grade C350L0. Steel posts are to be hot-dipped galvanised with a minimum of 300g/m2 galvanised coating complying with AS1650. Post sizes will be as detailed on the drawings. Hot dipped galvanised caps are to be fitted to the top of posts. Steel or Aluminium Brackets are to be used on all sign posts | Prior to works | HP | RS1.7 - Materials for signs | Responsibility - ENG | Test Method - Visual/ Manufacturer warranties and/or certificates | Conformance Criteria - Signage panels fabricated from 2mm thick aluminium sheeting conforming to AS1742. Sign face shall be non-reflective (NR) with the vinyl film conforming to appendix B of AS1743. Post sections are to comply with AS1163 and be in accordance with the following: Steel circular hollow sections in accordance with grade C250L0; and Steel rectangular hollow sections in accordance with grade C350L0. Steel posts are to be hot-dipped galvanised with a minimum of 300g/m2 galvanised coating complying with AS1650. Post sizes will be as detailed on the drawings. Hot dipped galvanised caps are to be fitted to the top of posts. Steel or Aluminium Brackets are to be used on all sign posts | Frequency - Prior to works | HP/WP - HP | RS1.2 - Management Plans submitted and approved as per PMP
[8 empty] | Sedgman HP/WP - | RS1.8 | Fabrication of signs | ENG | Visual/ Manufacturer warranties and/or certificates | MUTCD is to be used for compilation of the message, shape, size, layout and colour required for the facing of the sign. Signs are to be, cleaned, degreased and chemically etched or abraded in accordance with manufacturers specifications prior to application of non-reflective sheeting or paint. Non-reflective sheeting or paint shall be applied to the sign blank in accordance with the manufacturers specifications. All letters, arrows, symbols and borders shall be applied by: Silk screening before or after sign blank sheeting; and Pre-cut non-reflective material. | Prior to works | HP | RS1.8 - Fabrication of signs | Responsibility - ENG | Test Method - Visual/ Manufacturer warranties and/or certificates | Conformance Criteria - MUTCD is to be used for compilation of the message, shape, size, layout and colour required for the facing of the sign. Signs are to be, cleaned, degreased and chemically etched or abraded in accordance with manufacturers specifications prior to application of non-reflective sheeting or paint. Non-reflective sheeting or paint shall be applied to the sign blank in accordance with the manufacturers specifications. All letters, arrows, symbols and borders shall be applied by: Silk screening before or after sign blank sheeting; and Pre-cut non-reflective material. | Frequency - Prior to works | HP/WP - HP | Responsibility - ENG
[9 empty] | RS1.9 | Set out for sign locations | Surv | Survey | Locations of signage set out as per MUTCD or as shown on the design drawings | Prior to works | HP | RS1.9 - Set out for sign locations | Responsibility - Surv | Test Method - Survey | Conformance Criteria - Locations of signage set out as per MUTCD or as shown on the design drawings | Frequency - Prior to works | HP/WP - HP | Test Method - Visual
[9 empty] | RS1.10 | Underlying lot CHAR(AMP) ITP signed off and conforming | ENG | Visual | Pavement and/or Bulk Earthworks ITPs signed off | Prior to works | HP | RS1.10 - Underlying lot CHAR(AMP) ITP signed off and conforming | Responsibility - ENG | Test Method - Visual | Conformance Criteria - Pavement and/or Bulk Earthworks ITPs signed off | Frequency - Prior to works | HP/WP - HP | Conformance Criteria - Approved Package MP’s
[9 empty] | RS2.11 | Installation of signs | ENG | Visual | Signage to be installed as per MUTCD or as shown on the design drawings | As required | HP | RS2.11 - Installation of signs | Responsibility - ENG | Test Method - Visual | Conformance Criteria - Signage to be installed as per MUTCD or as shown on the design drawings | Frequency - As required | HP/WP - HP | Frequency - Prior to works
[9 empty] | RS2.12 | Removal or demolition of existing signs | SV | Visual | Any existing road signage to be removed or made redundant must be demolished including all signs, brackets, footing etc after the new signage in place. Voids left after post removal must be backfilled with approved pavement material to design surface level as shown on design drawings. | As required | HP | RS2.12 - Removal or demolition of existing signs | Responsibility - SV | Test Method - Visual | Conformance Criteria - Any existing road signage to be removed or made redundant must be demolished including all signs, brackets, footing etc after the new signage in place. Voids left after post removal must be backfilled with approved pavement material to design surface level as shown on design drawings. | Frequency - As required | HP/WP - HP | HP/WP - HP
[9 empty] | RS2.13 | Sign installation location check and survey pick-up | Surv | Survey/Field Test | Locations of signage installed as per MUTCD or as shown on the design drawings | As required | HP | RS2.13 - Sign installation location check and survey pick-up | Responsibility - Surv | Test Method - Survey/Field Test | Conformance Criteria - Locations of signage installed as per MUTCD or as shown on the design drawings | Frequency - As required | HP/WP - HP | RS1.3 - Inspection Test Plan (ITP) submitted and approved
[9 empty] | RS3.14 | Works completed and update ITP/ Lot Register/ MDR and close out of GDP | ENG | Visual | ITP closed. Approved MDR | As required | HP | RS3.14 - Works completed and update ITP/ Lot Register/ MDR and close out of GDP | Responsibility - ENG | Test Method - Visual | Conformance Criteria - ITP closed. Approved MDR | Frequency - As required | HP/WP - HP | Responsibility - ENG
Test Method - Visual
Conformance Criteria - Approved ITP revision
Frequency - Prior to works
HP/WP - HP
RS1.4 - Lot Register/ WBS submitted and approved
Responsibility - ENG
Test Method - Visual
Conformance Criteria - Approved WBS
Frequency - Prior to works
HP/WP - WP
RS1.5 - Check existing services and dial before you dig
Responsibility - ENG
Test Method - Visual
Conformance Criteria - DBYD certificate and EP
Frequency - Prior to works
HP/WP - HP
RS1.6 - Ground Disturbance Procedure (GDP) obtained
Responsibility - ENG/ENV
Test Method - Visual
Conformance Criteria - GDP permit with work packs
Frequency - Prior to works
HP/WP - HP
RS1.7 - Materials for signs
Responsibility - ENG
Test Method - Visual/ Manufacturer warranties and/or certificates
Conformance Criteria - Signage panels fabricated from 2mm thick aluminium sheeting conforming to AS1742. Sign face shall be non-reflective (NR) with the vinyl film conforming to appendix B of AS1743. Post sections are to comply with AS1163 and be in accordance with the following: Steel circular hollow sections in accordance with grade C250L0; and Steel rectangular hollow sections in accordance with grade C350L0. Steel posts are to be hot-dipped galvanised with a minimum of 300g/m2 galvanised coating complying with AS1650. Post sizes will be as detailed on the drawings. Hot dipped galvanised caps are to be fitted to the top of posts. Steel or Aluminium Brackets are to be used on all sign posts
Frequency - Prior to works
HP/WP - HP
RS1.8 - Fabrication of signs
Responsibility - ENG
Test Method - Visual/ Manufacturer warranties and/or certificates
Conformance Criteria - MUTCD is to be used for compilation of the message, shape, size, layout and colour required for the facing of the sign. Signs are to be, cleaned, degreased and chemically etched or abraded in accordance with manufacturers specifications prior to application of non-reflective sheeting or paint. Non-reflective sheeting or paint shall be applied to the sign blank in accordance with the manufacturers specifications. All letters, arrows, symbols and borders shall be applied by: Silk screening before or after sign blank sheeting; and Pre-cut non-reflective material.
Frequency - Prior to works
HP/WP - HP
RS1.9 - Set out for sign locations
Responsibility - Surv
Test Method - Survey
Conformance Criteria - Locations of signage set out as per MUTCD or as shown on the design drawings
Frequency - Prior to works
HP/WP - HP
RS1.10 - Underlying lot CHAR(AMP) ITP signed off and conforming
Responsibility - ENG
Test Method - Visual
Conformance Criteria - Pavement and/or Bulk Earthworks ITPs signed off
Frequency - Prior to works
HP/WP - HP
RS2.11 - Installation of signs
Responsibility - ENG
Test Method - Visual
Conformance Criteria - Signage to be installed as per MUTCD or as shown on the design drawings
Frequency - As required
HP/WP - HP
RS2.12 - Removal or demolition of existing signs
Responsibility - SV
Test Method - Visual
Conformance Criteria - Any existing road signage to be removed or made redundant must be demolished including all signs, brackets, footing etc after the new signage in place. Voids left after post removal must be backfilled with approved pavement material to design surface level as shown on design drawings.
Frequency - As required
HP/WP - HP
RS2.13 - Sign installation location check and survey pick-up
Responsibility - Surv
Test Method - Survey/Field Test
Conformance Criteria - Locations of signage installed as per MUTCD or as shown on the design drawings
Frequency - As required
HP/WP - HP
RS3.14 - Works completed and update ITP/ Lot Register/ MDR and close out of GDP
Responsibility - ENG
Test Method - Visual
Conformance Criteria - ITP closed. Approved MDR
Frequency - As required
HP/WP - HP