## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource Id
checklist | EVAMP001-THS-QA-ITP-0001 Pre-construction | itp
section | Pre-construction
checkpoint | PC1.1 - Construction Management Plan
label | Responsibility - ENG
label | Test Method - Visual
label | Conformance Criteria - Approved Construction Management Plan saved in Construction Team Sharepoint and detailed in register
label | Frequency - Prior to works
label | Thiess HP/WP Check - HP
label | Inspector HP/WP Sign Off - WP
holdpoint | WITNESS POINT
checkpoint | PC1.2 - Lot Register/ WBS
label | Responsibility - ENG
label | Test Method - Visual
label | Conformance Criteria - Lot register saved in Construction Team Sharepoint and detailed in register
label | Frequency - Prior to works
label | Thiess HP/WP Check - WP
label | Inspector HP/WP Sign Off - WP
holdpoint | WITNESS POINT
checkpoint | PC1.3 - Construction procedures
label | Responsibility - ENG
label | Test Method - Visual
label | Conformance Criteria - Construction procedures saved in Construction Team Sharepoint and detailed in register
label | Frequency - Prior to works
label | Thiess HP/WP Check - HP
label | Inspector HP/WP Sign Off - WP
holdpoint | WITNESS POINT
checkpoint | PC1.4 - Excavation permit
label | Responsibility - ENG
label | Test Method - Visual
label | Conformance Criteria - Approved Excavation Permit saved in Construction Team Sharepoint and detailed in register
label | Frequency - Prior to works
label | Thiess HP/WP Check - HP
label | Inspector HP/WP Sign Off - WP
holdpoint | WITNESS POINT
checkpoint | PC1.5 - Dial before you dig check
label | Responsibility - ENG
label | Test Method - Visual
label | Conformance Criteria - In date DBYD certificate saved in Construction Team Sharepoint and detailed in register
label | Frequency - Prior to works
label | Thiess HP/WP Check - HP
label | Inspector HP/WP Sign Off - WP
holdpoint | WITNESS POINT
checkpoint | PC1.6 - Traffic control plan
label | Responsibility - ENG
label | Test Method - Visual
label | Conformance Criteria - Traffic control plansaved in Construction Team Sharepoint and detailed in register
label | Frequency - Prior to works
label | Thiess HP/WP Check - HP
label | Inspector HP/WP Sign Off - WP
holdpoint | WITNESS POINT
checkpoint | PC1.7 - Inspection Test Plan (ITP) submitted and approved
label | Responsibility - ENG
label | Test Method - Visual
label | Conformance Criteria - Approved ITPs relevant to the works saved in Construction Team Sharepoint and detailed in register
label | Frequency - Prior to works
label | Thiess HP/WP Check - HP
label | Inspector HP/WP Sign Off - WP
holdpoint | WITNESS POINT
checkpoint | PC1.8 - IFC drawings
label | Responsibility - ENG
label | Test Method - Visual
label | Conformance Criteria - IFC drawings and revisions transmitted from theThiess Technical Services team and detailed in register
label | Frequency - Prior to works
label | Thiess HP/WP Check - HP
label | Inspector HP/WP Sign Off - WP
holdpoint | WITNESS POINT
checkpoint | PC1.9 - Survey natural surface
label | Responsibility - SURV
label | Test Method - Field
label | Conformance Criteria - Survey pick up of work area and digital file saved in Construction Team Sharepoint and detailed in register.
label | ○ Surface area shape file created and uploaded to Qfield
label | Frequency - Prior to works
label | Thiess HP/WP Check - HP
label | Inspector HP/WP Sign Off - HP
holdpoint | HOLD POINT
checkpoint | PC1.10 - Erosion and sediment control plan
label | Responsibility - ENV ENG
label | Test Method - Visual
label | Conformance Criteria - Approved Erosion and Sediment Control Plan saved in Construction Team Sharepoint and detailed in register
label | Frequency - Prior to works
label | Thiess HP/WP Check - HP
label | Inspector HP/WP Sign Off - HP
holdpoint | HOLD POINT
checkpoint | PC1.11 - Approved stockpile locations
label | Responsibility - ENG
label | Test Method - Visual
label | Conformance Criteria - All stockpile locations to be nominated and approved prior to commencement of activity.
label | ○ Topsoil register to be maintained with information on topsoil volumes and stockpile locations.
label | Frequency - Prior to works
label | Thiess HP/WP Check - HP
label | Inspector HP/WP Sign Off - HP
holdpoint | HOLD POINT
checkpoint | PC1.12 - Embankment fill materials
label | Responsibility - ENG
label | Test Method - Visual
label | Conformance Criteria - Embankment fill materials have been approved for use and in accordance with the requirements in the specification.
label | ○ General fill material as per Table A3-1 Cut/fill material properties in the specification:
label | ○ Less than 30% passing 0.075mm sieve
label | ○ Liquid limit 20% to 60% Soaked CBR = or >3% (STD compaction @ OMC)
label | ○ 1 test per 5,000 m3
label | ○ Subgrade replacement material CBR10.
label | ○ Select Fill as per the details in Table A3-2 Select fill material properties & Table A3-3 Select fill grading envelope.
label | Frequency - Prior to works
label | Thiess HP/WP Check - HP
label | Inspector HP/WP Sign Off - WP
holdpoint | WITNESS POINT
checkpoint | PC1.13 - Fauna Spotter Catcher (FSC) Pre-Clearance Survey
label | Responsibility - ENV
label | Test Method - Visual
label | Conformance Criteria - FSC pre-clearance survey completed only if within 2 weeks of construction saved in Construction Team Sharepoint and detailed in register
label | Frequency - Prior to works
label | Thiess HP/WP Check - HP
label | Inspector HP/WP Sign Off - HP
holdpoint | HOLD POINT
checkpoint | PC1.14 - Cultural Heritage(CH) Clearance Survey
label | Responsibility - CH
label | Test Method - Visual
label | Conformance Criteria - Approved CH Clearance Survey saved in Construction Team Sharepoint and detailed in register
label | ○ Areas of CH clearly demarcated
label | Frequency - Prior to works
label | Thiess HP/WP Check - HP
label | Inspector HP/WP Sign Off - HP
holdpoint | HOLD POINT
checkpoint | PC1.15 - Ground Disturbance Permit (GDP)
label | Responsibility - ENV ENG
label | Test Method - Visual
label | Conformance Criteria - Approved GDP saved in Construction Team Sharepoint and detailed in register
label | Frequency - Prior to works
label | Thiess HP/WP Check - HP
label | Inspector HP/WP Sign Off - HP
holdpoint | HOLD POINT
checkpoint | PC1.16 - GDP survey set out
label | Responsibility - SURV
label | Test Method - Field
label | Conformance Criteria - Area of works pegged and clearly defined to GDP.
label | ○ Clearing pegs installed at nominal intervals to ensure no over-clearing.
label | Frequency - Prior to works
label | Thiess HP/WP Check - HP
label | Inspector HP/WP Sign Off - HP
holdpoint | HOLD POINT
checkpoint | PC1.17 - Survey of pegs to confirm correct GDP survey set out
label | Responsibility - ENV
label | Test Method - Visual
label | Conformance Criteria - Pegs to be surveyed and sent back to the engineer. This is then to be confirmed by the environmental team
label | Frequency - Prior to works
label | Thiess HP/WP Check - HP
label | Inspector HP/WP Sign Off - WP
holdpoint | WITNESS POINT
checkpoint | PC1.18 - Mandatory GDP Pre-Clearing walk
label | Responsibility - SUP OP ENG ENV
label | Test Method - Field
label | Conformance Criteria - Walkthrough with FSC, Supervisor, Surveyor, PM or Senior Engineer, operations that will be undertaking the clearing
label | Frequency - Prior to works
label | Thiess HP/WP Check - HP
label | Inspector HP/WP Sign Off - WP
holdpoint | WITNESS POINT
checkpoint | PC1.19 - QA close out
label | Responsibility - ENG
label | Test Method - Visual
label | Conformance Criteria - Works completed and update ITP/Lot register/MDR and close out of GDP
label | Frequency - As required
label | Thiess HP/WP Check - HP
label | Inspector HP/WP Sign Off - HP
holdpoint | HOLD POINT
checklist | EVAMP001-THS-QA-ITP-0001 Clear & Grub | itp
section | Clear & Grub
checkpoint | GC1.1 - Underlying lot & ITP signed off and conforming
label | Responsibility - ENG
label | Test Method - Visual
label | Conformance Criteria - Pre-construction lots closed out
label | Frequency - As required
label | Link to ITP - PC1.19
checkpoint | GC1.2 - Ground Disturbance Permit (GDP)
label | Responsibility - ENV ENG
label | Test Method - Visual
label | Conformance Criteria - Approved GDP saved in Construction Team Sharepoint and detailed in register
label | Frequency - Prior to works (Check if this has already been completed at ITP Pre-construction stage)
label | Link to ITP - PC1.15
label | Thiess HP/WP Check - HP
label | Inspector HP/WP Sign Off - HP
holdpoint | HOLD POINT
checkpoint | GC1.3 - Cultural Heritage(CH) Clearance Survey
label | Responsibility - CH
label | Test Method - Visual
label | Conformance Criteria - Approved CH Clearance Survey saved in Construction Team Sharepoint and detailed in register
label | ○ Areas of CH clearly demarcated
label | Frequency - Prior to works (Check if this has already been completed at ITP Pre-construction stage)
label | Link to ITP - PC1.14
label | Thiess HP/WP Check - HP
label | Inspector HP/WP Sign Off - HP
holdpoint | HOLD POINT
checkpoint | GC1.4 - GDP survey set out
label | Responsibility - SURV
label | Test Method - Field
label | Conformance Criteria - Area of works pegged and clearly defined to GDP.
label | ○ Clearing pegs installed at nominal intervals to ensure no over-clearing.
label | Frequency - Prior to works (Check if this has already been completed at ITP Pre-construction stage)
label | Link to ITP - PC1.16
label | Thiess HP/WP Check - HP
label | Inspector HP/WP Sign Off - WP
holdpoint | WITNESS POINT
checkpoint | GC1.5 - Survey of pegs to confirm correct GDP survey set out
label | Responsibility - ENV
label | Test Method - Visual
label | Conformance Criteria - Pegs to be surveyed and sent back to the engineer. This is then to be confirmed by the environmental team
label | Frequency - Prior to works (Check if this has already been completed at ITP Pre-construction stage)
label | Link to ITP - PC1.17
label | Thiess HP/WP Check - HP
label | Inspector HP/WP Sign Off - WP
holdpoint | WITNESS POINT
checkpoint | GC1.6 - Survey natural surface
label | Responsibility - SURV
label | Test Method - Field
label | Conformance Criteria - Check survey pick up of work area and digital file saved in Construction Team Sharepoint and detailed in register.
label | ○ Surface area shape file created and uploaded to Qfield
label | Frequency - Prior to works (Check if this has already been completed at ITP Pre-construction stage)
label | Link to ITP - PC1.9
label | Thiess HP/WP Check - HP
label | Inspector HP/WP Sign Off - HP
holdpoint | HOLD POINT
checkpoint | GC1.7 - Fauna Spotter Catcher (FSC) Pre-Clearance Survey
label | Responsibility - ENG
label | Test Method - Visual
label | Conformance Criteria - FSC pre-clearance survey completed within 2 weeks of construction.
label | ○ Habitat vegetation, threatened species demarcated.
label | Frequency - Prior to works (Check if this has already been completed at ITP Pre-construction stage)
label | Link to ITP - PC1.13
label | Thiess HP/WP Check - HP
label | Inspector HP/WP Sign Off - HP
holdpoint | HOLD POINT
checkpoint | GC1.8 - Mandatory GDP Pre-Clearing walk
label | Responsibility - SUP OP ENG ENV
label | Test Method - Field
label | Conformance Criteria - Walkthrough with FSC, Supervisor, Surveyor, PM or Senior Engineer, operations that will be undertaking the clearing
label | Frequency - Prior to works (Check if this has already been completed at ITP Pre-construction stage)
label | Link to ITP - PC1.18
label | Thiess HP/WP Check - HP
label | Inspector HP/WP Sign Off - WP
holdpoint | WITNESS POINT
checkpoint | GC1.9 - Clearing of vegetation
label | Responsibility - SUP
label | Test Method - Visual
label | Conformance Criteria - FSC individual on site at works during clearing operations.
label | ○ Habitat vegetation, threatened species and cultural heritage areas demarcated
label | Frequency - As required
label | Thiess HP/WP Check - HP
label | Inspector HP/WP Sign Off - WP
holdpoint | WITNESS POINT
checkpoint | GC1.10 - Stockpile Cleared Vegetation
label | Responsibility - SUP
label | Test Method - Visual
label | Conformance Criteria - Cleared vegetation loaded and hauled to approved stockpile location
label | Frequency - As required
label | Link to ITP - PC1.11
label | Thiess HP/WP Check - HP
label | Inspector HP/WP Sign Off - WP
holdpoint | WITNESS POINT
checkpoint | GC1.11 - Erosion and sediment control
label | Responsibility - SUP
label | Test Method - Visual
label | Conformance Criteria - Erosion and sediment control measures to be implemented whereever possible after clearing has been completed.
label | Frequency - After clearing
label | Link to ITP - PC1.10
label | Thiess HP/WP Check - HP
label | Inspector HP/WP Sign Off - HP
holdpoint | HOLD POINT
checkpoint | GC1.12 - QA close out
label | Responsibility - ENG
label | Test Method - Visual
label | Conformance Criteria - Works completed and update ITP/Lot register/MDR and close out of GDP
label | Frequency - As required
label | Thiess HP/WP Check - HP
label | Inspector HP/WP Sign Off - HP
holdpoint | HOLD POINT
checklist | EVAMP001-THS-QA-ITP-0002 Topsoil Stripping | itp
section | Topsoil Stripping
checkpoint | TS1.1 - Underlying lot & ITP signed off and conforming
label | Responsibility - ENG
label | Test Method - Visual
label | Conformance Criteria - Clear & Grubbing ITP closed out
label | Frequency - Prior to works
label | Link to ITP - GC1.12
checkpoint | TS1.2 - Survey Set out
label | Responsibility - Surv
label | Test Method - Field
label | Conformance Criteria - Areas of work to be set out by surveyor and/or models in plant
label | Frequency - As required
label | Thiess HP/WP Check - HP
label | Inspector HP/WP Sign Off - WP
holdpoint | WITNESS POINT
checkpoint | TS1.3 - Strip topsoil, load & haul to approved stockpile location
label | Responsibility - ENG
label | Test Method - Visual
label | Conformance Criteria - Provisional depth of topsoil strip shall be 100 mm unless shown otherwise on the drawings.
label | ○ Stripped topsoil loaded and hauled to approved stockpile location.
label | ○ Stockpile locations located minimum 40m from watercourses and not exceed 2m in height.
label | ○ Native seeding of topsoil stockpiles as agreed with Company.
label | Frequency - As required
label | Link to ITP - PC1.11
label | Thiess HP/WP Check - HP
label | Inspector HP/WP Sign Off - WP
holdpoint | WITNESS POINT
checkpoint | TS1.4 - Topsoil location, destination and quantity catalogued.
label | Responsibility - ENG
label | Test Method - Visual
label | Conformance Criteria - Topsoil register to be maintained with information on topsoil volumes and stockpile locations
label | Frequency - As required
label | Link to ITP - PC1.11
label | Thiess HP/WP Check - HP
label | Inspector HP/WP Sign Off - HP
holdpoint | HOLD POINT
checkpoint | TS1.5 - Surface level check and survey pick-up
label | Responsibility - SURV
label | Test Method - Survey / Field Test
label | Conformance Criteria - Stripped surface level picked up as per Table 10 C15 (DXF file format, volume calculated and filr saved in Construction Team Sharepoint and detailed in register
label | Frequency - As required
label | Thiess HP/WP Check - HP
label | Inspector HP/WP Sign Off - HP
holdpoint | HOLD POINT
checkpoint | TS1.6 - QA close out
label | Responsibility - ENG
label | Test Method - Visual
label | Conformance Criteria - GDP permits closed. ITP closed. Approved MDR.
label | Frequency - As required
label | Thiess HP/WP Check - HP
label | Inspector HP/WP Sign Off - HP
holdpoint | HOLD POINT
checklist | EVAMP001-THS-QA-ITP-0003 Subgrade/Foundation Preparation | itp
section | Subgrade/Foundation Preparation
checkpoint | SP.1.1 - Underlying lot & ITP signed off and conforming
label | Responsibility - ENG
label | Test Method - Visual
label | Conformance Criteria - Topsoil ITP closed out
label | Frequency - Prior to Works
label | Link to ITP - TS1.6
checkpoint | SP.1.2 - Embankment fill material
label | Responsibility - ENG
label | Test Method - Visual
label | Conformance Criteria - Ensure CBR10 subgrade replacement materials have been approved for use and within specification
label | Frequency - Prior to works (Check if this has already been completed at ITP Pre-construction stage)
label | Link to ITP - PC1.12
label | Thiess HP/WP Check - HP
label | Inspector HP/WP Sign Off - WP
holdpoint | WITNESS POINT
checkpoint | SP.1.3 - Survey Set out
label | Responsibility - Surv
label | Test Method - Field
label | Conformance Criteria - Areas of work to be set out by surveyor and/or models in plant
label | Frequency - As required
label | Thiess HP/WP Check - HP
label | Inspector HP/WP Sign Off - WP
holdpoint | WITNESS POINT
checkpoint | SP.1.4 - Removal and replacement of unsuitable material
label | Responsibility - SUP
label | Test Method - Field
label | Conformance Criteria - Determination of unsuitable material by the Level 1 GITA or Inspector (Sedgman) is required prior to the removal of any unsuitable material. Unsuitable material criteria is in the specification.
label | Frequency - As required
label | Link to ITP - PC1.12
label | Thiess HP/WP Check - HP
label | Inspector HP/WP Sign Off - HP
holdpoint | HOLD POINT
checkpoint | SP.1.5 - Subgrade/Foundation preparation
label | Responsibility - SUP
label | Test Method - Field
label | Conformance Criteria - Foundations for embankments to be ripped 200m deep, moisture conditioned then compacted. Density requirements: < 300mm from finished level under roads & structures minimum RDD 97%, all other areas and depths RDD 95%, moisture content -1% to +2%, normal level of testing 1 test per 500m3, reduced level of testing 1 test per 1,000m3.
label | ○ All material exposed in cuttings at subgrade level minimum CBR 3 or DCP 150kpa. If CBR2: Remove & replace with CBR10 select fill 150mm deep. If CBR1: Remove & replace with CBR10 select fill 250mm deep
label | Frequency - As required
label | Link to ITP - PC1.12
label | Thiess HP/WP Check - HP
label | Inspector HP/WP Sign Off - HP
holdpoint | HOLD POINT
checkpoint | SP.1.6 - Trim subgrade
label | Responsibility - SUP / SURV
label | Test Method - Field
label | Conformance Criteria - Trim all subgrade to the lines and levels shown on the drawings in accordance with the following tolerances: Top of bulk earthworks +/-50mm; Road subgrades & under buildings & structures +0mm to -25mm.
label | Frequency - As required
label | Thiess HP/WP Check - HP
label | Inspector HP/WP Sign Off - HP
holdpoint | HOLD POINT
checkpoint | SP.1.7 - Proof rolling
label | Responsibility - SUP
label | Test Method - Field
label | Conformance Criteria - Proof-roll subgrade/foundation surface prior to placement of embankment fill. Proof roll under a standard 8 tonne axle load or 10,000L water cart or heavy self propellled smooth drum roller dynapac 620D or equivalent to confirm that, in the Inspector (Sedgman) s opinion, deflections are negligible
label | Frequency - As required
label | Thiess HP/WP Check - HP
label | Inspector HP/WP Sign Off - HP
holdpoint | HOLD POINT
checkpoint | SP.1.8 - Surface level check and survey pick-up
label | Responsibility - SURV
label | Test Method - Survey / Field Test
label | Conformance Criteria - Surface level picked up as per Table 10 C15 (DXF file format, volume calculated and filr saved in Construction Team Sharepoint and detailed in register
label | Frequency - As required
label | Thiess HP/WP Check - HP
label | Inspector HP/WP Sign Off - HP
holdpoint | HOLD POINT
checkpoint | SP.1.9 - QA close out
label | Responsibility - ENG
label | Test Method - Visual
label | Conformance Criteria - GDP permits closed. ITP closed. Approved MDR.
label | Frequency - As required
label | Thiess HP/WP Check - HP
label | Inspector HP/WP Sign Off - HP
holdpoint | HOLD POINT
checklist | EVAMP001-THS-4000-QA-ITP-008 Embankment Construction | itp
section | Embankment Construction
checkpoint | EC1.1 - Underlying lot & ITP signed off and conforming
label | Responsibility - ENG
label | Test Method - Visual
label | Conformance Criteria - Subgrade/Foundation Preparation ITP signed off
label | Frequency - Prior to works
label | Link to ITP - SP.1.9
label | Thiess HP/WP Check - HP
label | Inspector HP/WP Sign Off - WP
holdpoint | WITNESS POINT
checkpoint | EC1.2 - Embankment fill material
label | Responsibility - ENG
label | Test Method - Visual
label | Conformance Criteria - Ensure embankment fill materials have been approved for use and within specification
label | Frequency - Prior to works (Check if this has already been completed at ITP Pre-construction stage)
label | Link to ITP - PC1.12
label | Thiess HP/WP Check - HP
label | Inspector HP/WP Sign Off - WP
holdpoint | WITNESS POINT
checkpoint | EC1.3 - Survey Set out
label | Responsibility - Surv
label | Test Method - Field
label | Conformance Criteria - Areas of work to be set out by surveyor and/or models in plant
label | Frequency - As required
label | Thiess HP/WP Check - HP
label | Inspector HP/WP Sign Off - WP
holdpoint | WITNESS POINT
checkpoint | EC1.4 - Place, moisture condition & compact embankment fill
label | Responsibility - SUP/GeoTech
label | Test Method - Field Test
label | Conformance Criteria - Layer thickness minimum 150mm maximum 300mm.
label | ○ Density requirements: < 300mm from finished level under roads & structures minimum RDD 97%, all other areas and depths RDD 95%, moisture content -1% to +2%, normal level of testing 1 test per 500m3, reduced level of testing 1 test per 1,000m3.
label | ○ Subject to client approval oversized material up to 500mm can be used in general fill at the following depths: 600mm or greater in depth below subgrade for stockpiles, road surfaces and embankments, or 2m or greater in depth below the footprints of structures.
label | ○ Rock fill may be used >600mm below subgrade level.
label | ○ Material containing a high proportion of large particles may be used in embankments using the Mechanical interlock method of construction.Maximum layer thickness 500mm.
label | Frequency - As required
label | Thiess HP/WP Check - HP
label | Inspector HP/WP Sign Off - WP
holdpoint | WITNESS POINT
checkpoint | EC1.5 - Trim embankment
label | Responsibility - SUP / SURV
label | Test Method - Field
label | Conformance Criteria - Trim all embankment to the lines and levels shown on the drawings in accordance with the following tolerances: Top of bulk earthworks +/-50mm; Road subgrades & under buildings & structures +0mm to -25mm.
label | Frequency - As required
label | Thiess HP/WP Check - HP
label | Inspector HP/WP Sign Off - HP
holdpoint | HOLD POINT
checkpoint | EC1.6 - Proof rolling
label | Responsibility - ENG/SUP
label | Test Method - Field Test
label | Conformance Criteria - Proof-roll embankment finished surface under a standard 8 tonne axle load or 10,000L water cart or heavy self propellled smooth drum roller dynapac 620D or equivalent, to confirm that in the Inspector's opinion, deflections are negligible.
label | Frequency - As required
label | Thiess HP/WP Check - HP
label | Inspector HP/WP Sign Off - HP
holdpoint | HOLD POINT
checkpoint | EC1.7 - Surface level check and survey pick-up
label | Responsibility - SURV
label | Test Method - Survey / Field Test
label | Conformance Criteria - Surface level picked up as per Table 10 C15 (DXF file format, volume calculated and filr saved in Construction Team Sharepoint and detailed in register
label | Frequency - As required
label | Thiess HP/WP Check - HP
label | Inspector HP/WP Sign Off - HP
holdpoint | HOLD POINT
checkpoint | EC1.8 - QA close out
label | Responsibility - ENG
label | Test Method - Visual
label | Conformance Criteria - GDP permits closed. ITP closed. Approved MDR.
label | Frequency - As required
label | Thiess HP/WP Check - HP
label | Inspector HP/WP Sign Off - WP
holdpoint | WITNESS POINT
checklist | EVAMP001-THS-4000-QA-ITP-008 Subgrade | itp
section | Subgrade
checkpoint | EC1.1 - Underlying lot & ITP signed off and conforming
label | Responsibility - ENG
label | Test Method - Visual
label | Conformance Criteria - Embankment or Excavation ITP signed off
label | Frequency - Prior to works
label | Thiess HP/WP Check - HP
label | Sedgman HP/WP - WP
holdpoint | WITNESS POINT
checkpoint | EC1.2 - Place and compact general fill layer – Subgrade
label | Responsibility - SUP/GeoTech
label | Test Method - Field Test
label | Conformance Criteria - Material containing a high proportion of large particles may be used in embankments using the Mechanical interlock method of construction Field density standard minimum Dry density test to be 95%, OMC -1%, +2% with a minimum layer thickness of 150mm and maximum 300mm. Material greater than 600mm may be allowed to be used in the Embankment.
label | Frequency - As required
label | Thiess HP/WP Check - HP
label | Sedgman HP/WP - WP
holdpoint | WITNESS POINT
checkpoint | EC1.3 - Subgrade in cut
label | Responsibility - SUP/GeoTech
label | Test Method - Survey/Field Test
label | Conformance Criteria - For subgrades under road/rail pavements and buildings/structures, the materials exposed at the subgrade level of cuttings is to have a minimum CBR of 3.
label | Frequency - As required
label | Thiess HP/WP Check - HP
label | Sedgman HP/WP - WP
holdpoint | WITNESS POINT
checkpoint | EC1.4 - Proof rolling
label | Responsibility - ENG/SUP
label | Test Method - Field Test
label | Conformance Criteria - The embankment will be proof rolled with either Proof rolling shall be undertaken using a 10,000 L water cart or heavy, self-propelled, smooth drum vibrating roller capable of operating in variable frequency modes.
label | Frequency - As required each lot
label | Thiess HP/WP Check - HP
label | Sedgman HP/WP - WP
holdpoint | WITNESS POINT
checkpoint | EC1.5 - As-built of completed surface
label | Responsibility - ENG/SURV
label | Test Method - Survey
label | Conformance Criteria - Survey to be completed of the finished surface to confirm to the levels as shown on the drawings with deviations as per Top of earthworks other than the subgrade and pad level ± 50, Road subgrade & building / structure pads +0 -25
label | Frequency - Each Finished Surface
label | Thiess HP/WP Check - HP
label | Sedgman HP/WP - WP
holdpoint | WITNESS POINT
checkpoint | EC1.6 - QA close out
label | Responsibility - ENG
label | Test Method - Visual
label | Conformance Criteria - GDP permits closed. ITP closed. Approved MDR.
label | Frequency - As required
label | Thiess HP/WP Check - HP
label | Sedgman HP/WP - WP
holdpoint | WITNESS POINT
checklist | EVAMP001-THS-QA-ITP-0004 RCP Installation | itp
section | 1.0 Pre-Construction
checkpoint | RCP1.1 - Drawings supplied most current IFC
label | Responsibility - ENG
label | Test Method - Visual
label | Conformance Criteria - Reviewed drawing register
label | Frequency - Prior to works
label | HP/WP - HP
holdpoint | HOLD POINT
checkpoint | RCP1.2 - Define RCP ID
label | Responsibility - ENG
label | Test Method - Visual
label | Conformance Criteria - Inspection Register. Allocate ID for reinforced concrete pipe, define work area
label | Frequency - Prior to works
label | HP/WP - HP
holdpoint | HOLD POINT
checkpoint | RCP1.3 - Lot Register/ WBS submitted and approved
label | Responsibility - ENG
label | Test Method - Visual
label | Conformance Criteria - Approved WBS
label | Frequency - Prior to works
label | HP/WP - WP
holdpoint | WITNESS POINT
checkpoint | RCP1.4 - Underlying lot & ITP signed off and conforming
label | Responsibility - ENG
label | Test Method - Visual
label | Conformance Criteria - Subgrade prep ITP Signed
label | Frequency - Prior to works
label | HP/WP - HP
holdpoint | HOLD POINT
checkpoint | RCP1.5 - Certificate of compliance for RCP Material
label | Responsibility - ENG
label | Test Method - Written
label | Conformance Criteria - Supplier to provide certificates indicating manufacturing processes, materials, thicknesses, classes, and diameters (Only culverts with materials & dimensions complying with the culvert schedule & specification to be used).
label | Frequency - Per pipe
label | HP/WP - HP
holdpoint | HOLD POINT
checkpoint | RCP1.6 - Inspect reinforced pipe culverts for damage
label | Responsibility - ENG/SV
label | Test Method - Visual
label | Conformance Criteria - Prior to installation, Pipes are checked for damages and accepted/rejected and documented on Incoming Goods Inspection form
label | Frequency - Per pipe
label | HP/WP - HP
holdpoint | HOLD POINT
section | 2.0 Construction
checkpoint | RCP2.7 - Trench Excavation
label | Responsibility - SV/SC
label | Test Method - Visual
label | Conformance Criteria - Trenches should be excavated to the required width and grade indicated on the IFC Drawings, with allowance made for benching for excavations greater than 1.5 meters.
label | ○ Excavations must be kept free from water until work below ground level us adequately set or protected
label | Frequency - As required
label | HP/WP - HP
holdpoint | HOLD POINT
checkpoint | RCP2.8 - Bedding
label | Responsibility - SV/SC
label | Test Method - Visual
label | Conformance Criteria - Culverts shall be bedded as detailed on the Drawings. Proposed
label | Frequency - As required
label | HP/WP - HP
holdpoint | HOLD POINT
checkpoint | RCP2.9 - RCP Installation
label | Responsibility - SV/SC
label | Test Method - Written/survey
label | Conformance Criteria - Culverts are to be installed to the line, level, and grade shown on the IFC Drawings. Inlet and outlet invert levels shall be as shown in the Drawings plus or minus 10mm. Inverts shall be smooth and of uniform gradient throughout each culvert length.
label | Tolerances:
label | ○ Vertical level: ± 10mm
label | ○ Horizontal Alignment: ± 25mm
label | Frequency - As required
label | HP/WP - HP
holdpoint | HOLD POINT
checkpoint | RCP2.10 - Backfilling of culvert
label | Responsibility - ENG/SV
label | Test Method - Visual
label | Conformance Criteria - Backfilling and compaction shall be carried out in horizontal layers of uniform thickness not exceeding 200 mm of uncompacted selected fill material for 300 mm all around the pipe or culvert. Compaction in this zone shall generally be by hand tampers to a minimum density of 95% of the standard maximum dry density at +/- 2% optimum moisture content. Compaction of backfill in the remainder of the trench to subgrade level shall be to a minimum 98% modified MDD at +/-2% OMC shall be advised
label | Frequency - As required
label | HP/WP - HP
holdpoint | HOLD POINT
checkpoint | RCP2.11 - End Treatment – Headwall & Wingwalls (Reinforcement)
label | Responsibility - ENG/SV
label | Test Method - Visual
label | Conformance Criteria - Reinforcement installed as per IFC design drawings
label | Frequency - V
label | HP/WP - HP
holdpoint | HOLD POINT
checkpoint | RCP2.12 - End Treatment – Headwall & Wingwalls (Formwork)
label | Responsibility - ENG/SV
label | Test Method - Visual/Field Survey
label | Conformance Criteria - Formwork installed as per IFC design drawings.
label | Tolerances:
label | ○ Variation in cross-sectional Dimensions: + 5mm
label | ○ Variation in overall dimensions: + 10mm
label | ○ Variation in surface level: + 5mm
label | Frequency - Each inlet/outlet
label | HP/WP - HP
holdpoint | HOLD POINT
checkpoint | RCP2.13 - End Treatment – Headwall & Wingwalls (Concrete)
label | Responsibility - SC/SV
label | Test Method - Visual
label | Conformance Criteria - Concrete placed and compacted to specified strength (N40) and slump (max100mm).
label | Frequency - Each inlet/outlet
label | HP/WP - HP
holdpoint | HOLD POINT
checkpoint | RCP2.14 - Rock Protection
label | Responsibility - SC/SV
label | Test Method - Visual
label | Conformance Criteria - Dimensions and class of rock protection shall be as specified in the Culvert Schedule and supplied IFC Drawings.
label | Frequency - Each inlet/outlet
label | HP/WP - HP
holdpoint | HOLD POINT
section | 3.0 Post Construction
checkpoint | RCP3.15 - Works completed and update ITP/ Lot Register/ MDR and close out of GDP
label | Responsibility - ENG
label | Test Method - Visual
label | Conformance Criteria - GDP permits closed.
label | ○ ITP closed.
label | ○ Approved MDR
label | Frequency - As required
label | HP/WP - HP
holdpoint | HOLD POINT
checklist | EVAMP001-THS-QA-ITP-009 Unbound Gravel Pavements | itp
section | 1.0 Pre-Construction
checkpoint | GP1.1 - Drawings supplied most current IFC
label | Responsibility - ENG
label | Test Method - Visual
label | Conformance Criteria - Reviewed drawing register
label | Frequency - Prior to works
label | HP/WP - HP
holdpoint | HOLD POINT
checkpoint | GP1.2 - Management Plans submitted and approved as per PMP
label | Responsibility - ENG
label | Test Method - Visual
label | Conformance Criteria - Approved Package MP’s
label | Frequency - Prior to works
label | HP/WP - HP
holdpoint | HOLD POINT
checkpoint | GP1.3 - Inspection Test Plan (ITP) submitted and approved
label | Responsibility - ENG
label | Test Method - Visual
label | Conformance Criteria - Approved ITP revision
label | Frequency - Prior to works
label | HP/WP - HP
holdpoint | HOLD POINT
checkpoint | GP1.4 - Lot Register/ WBS submitted and approved
label | Responsibility - ENG
label | Test Method - Visual
label | Conformance Criteria - Approved WBS
label | Frequency - Prior to works
label | HP/WP - WP
holdpoint | WITNESS POINT
checkpoint | GP1.5 - Pavement material compliance testing
label | Responsibility - ENG
label | Test Method - Visual
label | Conformance Criteria - Test results comply with the details on the drawings or where not specified the specification
label | Frequency - Prior to works
label | HP/WP - HP
holdpoint | HOLD POINT
checkpoint | GP1.6 - Stockpile locations
label | Responsibility - ENG
label | Test Method - Visual
label | Conformance Criteria - Stockpile locations shown on the drawings or approved by client’s rep
label | Frequency - Prior to works
label | HP/WP - HP
holdpoint | HOLD POINT
checkpoint | GP1.7 - Underlying lot & ITP signed off and conforming
label | Responsibility - ENG
label | Test Method - Visual
label | Conformance Criteria - Subgrade prep ITP Signed
label | Frequency - Prior to works
label | HP/WP - HP
holdpoint | HOLD POINT
section | 2.0 Construction
checkpoint | GP2.8 - Subgrade preparation under pavements
label | Responsibility - ENG
label | Test Method - Visual/Field Test
label | Conformance Criteria - If subgrade material is less than CBR10, subgrade shall be boxed and replaced with 150 mm of CBR10 or greater material. Subgrades shall be trimmed and compacted to within 15 mm of the established grade or cross section. Compaction requirement: 98% modified maximum dry density at +/- 2% OMC.
label | Frequency - As required
label | HP/WP - HP
holdpoint | HOLD POINT
checkpoint | EC2.9 - Surface level check/ and survey pick-up
label | Responsibility - SURV
label | Test Method - Survey/Field Test
label | Conformance Criteria - Surface level pick-up submitted to company
label | Frequency - As required
label | HP/WP - HP
holdpoint | HOLD POINT
checkpoint | EC2.10 - Proof roll subgrade prior to placement of pavement materials
label | Responsibility - ENG
label | Test Method - Visual
label | Conformance Criteria - Subgrades under pavements shall be proofrolled under a 10,000L water cart or heavy, self-propelled, smooth drum vibrating roller capable of operating in variable frequency modes, to confirm that, in the principal’s opinion, deflections are negligible
label | Frequency - As required
label | HP/WP - HP
holdpoint | HOLD POINT
checkpoint | EC2.11 - Placement of pavement material layers
label | Responsibility - ENG
label | Test Method - Visual/Field Test
label | Conformance Criteria - All materials delivered to site shall be accompanied by test certificates.
label | ○ Each layer shall be free from sticks, organic matter, clay lumps and other deleterious material, and be spread and compacted in a uniform thickness minimum 75mm, maximum 250mm as per the details on the drawings.
label | ○ The deviation from a 3m long straight-edge placed anywhere on the surface of a layer shall not exceed 8mm.
label | ○ Pavement layer thickness tolerances: Base -0mm to +30mm; Sub Base -15mm to +30mm.
label | ○ Finished pavement surface level tolerance: Base -15mm to +25mm
label | ○ Horizontal tolerances: Base, centreline/crown -150mm to +50mm, edgeline/changepoint -100mm to +200mm; Sub Base, centreline/crown +/-200mm, change point -100mm to +400mm
label | Compaction requirements:
label | ○ Base & Sub Base 100% standard relative dry density (RDD) maximum degree of saturation 70%.
label | ○ Compliance testing frequency as per table in Specification Annexure A clause 5.
label | Frequency - As required
label | HP/WP - HP
holdpoint | HOLD POINT
checkpoint | EC2.12 - Surface level check/ and survey pick-up
label | Responsibility - SURV
label | Test Method - Survey/Field Test
label | Conformance Criteria - Surface level as per the pavement layer details on the drawings, and all layers as per the tolerances listed in item 11 of this ITP.
label | Frequency - As required
label | HP/WP - HP
holdpoint | HOLD POINT
section | 3.0 Post Construction
checkpoint | EC3.13 - Works completed and update ITP/ Lot Register/ MDR and close out of GDP
label | Responsibility - ENG
label | Test Method - Visual
label | Conformance Criteria - ITP closed.
label | ○ Approved MDR
label | Frequency - As required
label | HP/WP - HP
holdpoint | HOLD POINT
checklist | EVAMP001-THS-QA-ITP-0004 Road Signs | itp
section | 1.0 Pre-Construction
checkpoint | RS1.1 - Drawings supplied most current IFC
label | Responsibility - ENG
label | Test Method - Visual
label | Conformance Criteria - Reviewed drawing register
label | Frequency - Prior to works
label | HP/WP - HP
holdpoint | HOLD POINT
checkpoint | RS1.2 - Management Plans submitted and approved as per PMP
label | Responsibility - ENG
label | Test Method - Visual
label | Conformance Criteria - Approved Package MP’s
label | Frequency - Prior to works
label | HP/WP - HP
holdpoint | HOLD POINT
checkpoint | RS1.3 - Inspection Test Plan (ITP) submitted and approved
label | Responsibility - ENG
label | Test Method - Visual
label | Conformance Criteria - Approved ITP revision
label | Frequency - Prior to works
label | HP/WP - HP
holdpoint | HOLD POINT
checkpoint | RS1.4 - Lot Register/ WBS submitted and approved
label | Responsibility - ENG
label | Test Method - Visual
label | Conformance Criteria - Approved WBS
label | Frequency - Prior to works
label | HP/WP - WP
holdpoint | WITNESS POINT
checkpoint | RS1.5 - Check existing services and dial before you dig
label | Responsibility - ENG
label | Test Method - Visual
label | Conformance Criteria - DBYD certificate and EP
label | Frequency - Prior to works
label | HP/WP - HP
holdpoint | HOLD POINT
checkpoint | RS1.6 - Ground Disturbance Procedure (GDP) obtained
label | Responsibility - ENG/ENV
label | Test Method - Visual
label | Conformance Criteria - GDP permit with work packs
label | Frequency - Prior to works
label | HP/WP - HP
holdpoint | HOLD POINT
checkpoint | RS1.7 - Materials for signs
label | Responsibility - ENG
label | Test Method - Visual/ Manufacturer warranties and/or certificates
label | Conformance Criteria - Signage panels fabricated from 2mm thick aluminium sheeting conforming to AS1742.
label | ○ Sign face shall be non-reflective (NR) with the vinyl film conforming to appendix B of AS1743.
label | ○ Post sections are to comply with AS1163 and be in accordance with the following:
label | ○ Steel circular hollow sections in accordance with grade C250L0; and
label | ○ Steel rectangular hollow sections in accordance with grade C350L0.
label | ○ Steel posts are to be hot-dipped galvanised with a minimum of 300g/m2 galvanised coating complying with AS1650.
label | ○ Post sizes will be as detailed on the drawings.
label | ○ Hot dipped galvanised caps are to be fitted to the top of posts.
label | ○ Steel or Aluminium Brackets are to be used on all sign posts
label | Frequency - Prior to works
label | HP/WP - HP
holdpoint | HOLD POINT
checkpoint | RS1.8 - Fabrication of signs
label | Responsibility - ENG
label | Test Method - Visual/ Manufacturer warranties and/or certificates
label | Conformance Criteria - MUTCD is to be used for compilation of the message, shape, size, layout and colour required for the facing of the sign.
label | ○ Signs are to be, cleaned, degreased and chemically etched or abraded in accordance with manufacturers specifications prior to application of non-reflective sheeting or paint.
label | ○ Non-reflective sheeting or paint shall be applied to the sign blank in accordance with the manufacturers specifications.
label | ○ All letters, arrows, symbols and borders shall be applied by:
label | ○ Silk screening before or after sign blank sheeting; and
label | ○ Pre-cut non-reflective material.
label | Frequency - Prior to works
label | HP/WP - HP
holdpoint | HOLD POINT
checkpoint | RS1.9 - Set out for sign locations
label | Responsibility - Surv
label | Test Method - Survey
label | Conformance Criteria - Locations of signage set out as per MUTCD or as shown on the design drawings
label | Frequency - Prior to works
label | HP/WP - HP
holdpoint | HOLD POINT
checkpoint | RS1.10 - Underlying lot & ITP signed off and conforming
label | Responsibility - ENG
label | Test Method - Visual
label | Conformance Criteria - Pavement and/or Bulk Earthworks ITPs signed off
label | Frequency - Prior to works
label | HP/WP - HP
holdpoint | HOLD POINT
section | 2.0 Construction
checkpoint | RS2.11 - Installation of signs
label | Responsibility - ENG
label | Test Method - Visual
label | Conformance Criteria - Signage to be installed as per MUTCD or as shown on the design drawings
label | Frequency - As required
label | HP/WP - HP
holdpoint | HOLD POINT
checkpoint | RS2.12 - Removal or demolition of existing signs
label | Responsibility - SV
label | Test Method - Visual
label | Conformance Criteria - Any existing road signage to be removed or made redundant must be demolished including all signs, brackets, footing etc after the new signage in place.
label | ○ Voids left after post removal must be backfilled with approved pavement material to design surface level as shown on design drawings.
label | Frequency - As required
label | HP/WP - HP
holdpoint | HOLD POINT
checkpoint | RS2.13 - Sign installation location check and survey pick-up
label | Responsibility - Surv
label | Test Method - Survey/Field Test
label | Conformance Criteria - Locations of signage installed as per MUTCD or as shown on the design drawings
label | Frequency - As required
label | HP/WP - HP
holdpoint | HOLD POINT
section | 3.0 Post Construction
checkpoint | RS3.14 - Works completed and update ITP/ Lot Register/ MDR and close out of GDP
label | Responsibility - ENG
label | Test Method - Visual
label | Conformance Criteria - ITP closed.
label | ○ Approved MDR
label | Frequency - As required
label | HP/WP - HP
holdpoint | HOLD POINT