## Retaining Wall
INSPECTION & TEST PLAN
|  | Contract Name: 7063- Whainui Matari- Remediation Works | [8 empty] | Rev: | Originator | Date | Approved | Date
|  | Retaining Wall |  |  | Hold Point (H) | Verify (V) |  |  |  |  | 0 | Cameron Hinge | 2025-05-21
ITP001- Whainui Matari- Remediation Works |  |  |  |  | Submit (S) | Review (R) |  |  |  |  | 1
[5 empty] | Approve(A) | Witness (W)
Surveillance (SU)
TASK | SPECIFICATION REFERENCE | TEST REQUIRED | INSPECTION BY | TASK TIMING OR TASK FREQUENCY | ACCEPTANCE CRITERIA | UCCL Signature | Client Signature | SBC Signature | UCCL | Client | SBC | DATE | COMMENTS
Piling Works
Reinforcing Cage - Procurement | DWG No. SPEC-01. | Detail sheets. Mill certificates. Engineers inspection. | UCCL, HGK, HW | Prior delivery to site | Engineers Approval |  |  |  | R, V, S | R, V, A | S
Concrete - Procurement | DWG No. SPEC 01. DWG No. SPEC 02. DWG No. SPEC 03. | Concrete mix design | UCCL, HGK, HW | Following Award | Engineers Approval |  |  |  | R, V, S | R, A | S
Retaining Wall Location | DWG No. SPEC 02. ROP-03 | Engineers inspection. | UCCL, HGK, HW | Prior delivery to site | Engineers Approval |  |  |  | R, S | V, A | S, H
Pile Drill Records - Ground conditions/Drilled excavation | DWG No. SPEC 02. | Drill records - Final excavation depth to road level. - Depth and nature of groundwater encountered. - Depth of any notable change in piling conditions (ground conditions, colour, or change in material). Engineers inspection | UCCL, HGK, HW | Drill logs - each pile. Engineers inspection - As required | Engineers Approval |  |  |  | R, S | R, A, V | H
Reinforcing Cage - Placement | DRW No. SPEC 02. | Engineers inspection. | UCCL, HGK, HW | Each pile / as required | Engineers Approval |  |  |  | R, S | R, A, V | H
Concrete - Placement | DWG No. SPEC 01. SESOC / NZGS Bored and Driven Pile Construction Specifications. Haigh Workman Technical Specfications. | Engineers inspection. | UCCL, HGK, HW | Each pile / as required | Engineers Approval |  |  |  | W | W | H
Capping Beam |  |  | UCCL, HGK, HW
Reinforcing Cage - Procurement | DWG No. SPEC-01. | Detail sheets. Mill certificates. Engineers inspection. | UCCL, HGK, HW | Following delivery to site | Engineers Approval |  |  |  | R, S | R, A | R, S, H
Concrete - Procurement | DWG No. SPEC 01. DWG No. SPEC 02. DWG No. SPEC 03. | Concrete mix design | UCCL, HGK, HW | Following Award | Engineers Approval |  |  |  | W | R, A | H
Reinforcing - Placement | DRW No. SPEC 02. | Engineers inspection | UCCL, HGK, HW | Prior to Concrete Placement | Engineers Approval |  |  |  | R, S | R, A, V | H