## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource Id
checklist | ITP002 - 7063 - Whainui Matari - Remediation Works Retaining Wall | itp |  |  |  |  | ITP002 - 7063 - Whainui Matari - Remediation Works Retaining Wall Rev 1
section | Piling Works
checkpoint | Reinforcing Cage - Procurement
label | SPECIFICATION REFERENCE - DWG No. SPEC-01.
label | TEST REQUIRED - Detail sheets.
label | ○ Mill certificates.
label | ○ Engineers inspection.
label | INSPECTION BY - UCCL, HGK, HW
label | TASK TIMING OR TASK FREQUENCY - Prior delivery to site
label | ACCEPTANCE CRITERIA - Engineers Approval
label | UCCL - R, V, S
label | Client - R, V, A
label | SBC - S
checkpoint | Concrete - Procurement
label | SPECIFICATION REFERENCE - DWG No. SPEC 01.
label | ○ DWG No. SPEC 02.
label | ○ DWG No. SPEC 03.
label | TEST REQUIRED - Concrete mix design
label | INSPECTION BY - UCCL, HGK, HW
label | TASK TIMING OR TASK FREQUENCY - Following Award
label | ACCEPTANCE CRITERIA - Engineers Approval
label | UCCL - R, V, S
label | Client - R, A
label | SBC - S
checkpoint | Retaining Wall Location
label | SPECIFICATION REFERENCE - DWG No. SPEC 02. ROP-03
label | TEST REQUIRED - Engineers inspection.
label | INSPECTION BY - UCCL, HGK, HW
label | TASK TIMING OR TASK FREQUENCY - Prior delivery to site
label | ACCEPTANCE CRITERIA - Engineers Approval
label | UCCL - R, S
label | Client - V, A
label | SBC - S, H
checkpoint | Pile Drill Records - Ground conditions/Drilled excavation
label | SPECIFICATION REFERENCE - DWG No. SPEC 02.
label | TEST REQUIRED - Drill records
label | — Final excavation depth to road level.
label | — Depth and nature of groundwater encountered.
label | — Depth of any notable change in piling conditions (ground conditions, colour, or change in material).
label | ○ Engineers inspection
label | INSPECTION BY - UCCL, HGK, HW
label | TASK TIMING OR TASK FREQUENCY - Drill logs - each pile.
label | ○ Engineers inspection - As required
label | ACCEPTANCE CRITERIA - Engineers Approval
label | UCCL - R, S
label | Client - R, A, V
label | SBC - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | Reinforcing Cage - Placement
label | SPECIFICATION REFERENCE - DRW No. SPEC 02.
label | TEST REQUIRED - Engineers inspection.
label | INSPECTION BY - UCCL, HGK, HW
label | TASK TIMING OR TASK FREQUENCY - Each pile / as required
label | ACCEPTANCE CRITERIA - Engineers Approval
label | UCCL - R, S
label | Client - R, A, V
label | SBC - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | Concrete - Placement
label | SPECIFICATION REFERENCE - DWG No. SPEC 01.
label | ○ SESOC / NZGS Bored and Driven Pile
label | ○ Construction Specifications.
label | ○ Haigh Workman Technical Specfications.
label | TEST REQUIRED - Engineers inspection.
label | INSPECTION BY - UCCL, HGK, HW
label | TASK TIMING OR TASK FREQUENCY - Each pile / as required
label | ACCEPTANCE CRITERIA - Engineers Approval
label | UCCL - W
label | Client - W
label | SBC - H
holdpoint | AUTHORITY HOLDPOINT
section | Capping Beam
checkpoint | Reinforcing Cage - Procurement
label | SPECIFICATION REFERENCE - DWG No. SPEC-01.
label | TEST REQUIRED - Detail sheets.
label | ○ Mill certificates.
label | ○ Engineers inspection.
label | INSPECTION BY - UCCL, HGK, HW
label | TASK TIMING OR TASK FREQUENCY - Following delivery to site
label | ACCEPTANCE CRITERIA - Engineers Approval
label | UCCL - R, S
label | Client - R, A
label | SBC - R, S, H
checkpoint | Concrete - Procurement
label | SPECIFICATION REFERENCE - DWG No. SPEC 01.
label | ○ DWG No. SPEC 02.
label | ○ DWG No. SPEC 03.
label | TEST REQUIRED - Concrete mix design
label | INSPECTION BY - UCCL, HGK, HW
label | TASK TIMING OR TASK FREQUENCY - Following Award
label | ACCEPTANCE CRITERIA - Engineers Approval
label | UCCL - W
label | Client - R, A
label | SBC - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | Reinforcing - Placement
label | SPECIFICATION REFERENCE - DRW No. SPEC 02.
label | TEST REQUIRED - Engineers inspection
label | INSPECTION BY - UCCL, HGK, HW
label | TASK TIMING OR TASK FREQUENCY - Prior to Concrete Placement
label | ACCEPTANCE CRITERIA - Engineers Approval
label | UCCL - R, S
label | Client - R, A, V
label | SBC - H
holdpoint | AUTHORITY HOLDPOINT