## Sheet1
5.1 | Red Line Mark Up Drawings | As-built drawings to capture any deviation from the IFC drawings. |  | Submit | At Completion | H | R |  | Red Line Mark Up Drawings | 5.1 - Red Line Mark Up Drawings | Description - As-built drawings to capture any deviation from the IFC drawings. | Specifications and Standards - | Method/Description - Submit | Test frequency - At Completion | Conformance Criteria - | Constructor - H | CPS - R | Lab - | IOM - | Verifying Records - Red Line Mark Up Drawings | 5.1 - Red Line Mark Up Drawings
5.2 | As-built Drawings | As-built drawings to capture any deviation from the IFC drawings. | Quality Management Plan | Submit | At Completion | H | R |  |  | 5.2 - As-built Drawings | Description - As-built drawings to capture any deviation from the IFC drawings. | Specifications and Standards - Quality Management Plan | Method/Description - Submit | Test frequency - At Completion | Conformance Criteria - | Constructor - H | CPS - R | Lab - | IOM - | Verifying Records - | Description - As-built drawings to capture any deviation from the IFC drawings.
5.3 | Tunnel Operation and maintenance report | Tunnel Operation and maintenance report to detail the maintenance frequency and maintenance procedures. |  | Submit | At Completion | H | R | R | Tunnel operation and maintenance report | 5.3 - Tunnel Operation and maintenance report | Description - Tunnel Operation and maintenance report to detail the maintenance frequency and maintenance procedures. | Specifications and Standards - | Method/Description - Submit | Test frequency - At Completion | Conformance Criteria - | Constructor - H | CPS - R | Lab - | IOM - R | Verifying Records - Tunnel operation and maintenance report | Specifications and Standards -
5.4 | Final Handover Package | Collation of all QA, as-built drawings,as-built records, installation records, PTT, testing and monitoring documentation. Provision of asset management operation and maintenance report to NZTA, including Producer Statements. | Quality Management Plan | Submit | At Completion | H | R | R | As-built drawings, installation record, as built records, PTT, testing results, monitoring documentation, operation and maintenance report, Producer Statements | 5.4 - Final Handover Package | Description - Collation of all QA, as-built drawings,as-built records, installation records, PTT, testing and monitoring documentation. Provision of asset management operation and maintenance report to NZTA, including Producer Statements. | Specifications and Standards - Quality Management Plan | Method/Description - Submit | Test frequency - At Completion | Conformance Criteria - | Constructor - H | CPS - R | Lab - | IOM - R | Verifying Records - As-built drawings, installation record, as built records, PTT, testing results, monitoring documentation, operation and maintenance report, Producer Statements | Method/Description - Submit
Test frequency - At Completion
Conformance Criteria -
Constructor - H
CPS - R
Lab -
IOM -
Verifying Records - Red Line Mark Up Drawings
5.2 - As-built Drawings
Description - As-built drawings to capture any deviation from the IFC drawings.
Specifications and Standards - Quality Management Plan
Method/Description - Submit
Test frequency - At Completion
Conformance Criteria -
Constructor - H
CPS - R
Lab -
IOM -
Verifying Records -
5.3 - Tunnel Operation and maintenance report
Description - Tunnel Operation and maintenance report to detail the maintenance frequency and maintenance procedures.
Specifications and Standards -
Method/Description - Submit
Test frequency - At Completion
Conformance Criteria -
Constructor - H
CPS - R
Lab -
IOM - R
Verifying Records - Tunnel operation and maintenance report
5.4 - Final Handover Package
Description - Collation of all QA, as-built drawings,as-built records, installation records, PTT, testing and monitoring documentation. Provision of asset management operation and maintenance report to NZTA, including Producer Statements.
Specifications and Standards - Quality Management Plan
Method/Description - Submit
Test frequency - At Completion
Conformance Criteria -
Constructor - H
CPS - R
Lab -
IOM - R
Verifying Records - As-built drawings, installation record, as built records, PTT, testing results, monitoring documentation, operation and maintenance report, Producer Statements