## zres_siteapp_NEW
Id | Type | Name | Values | Prompting Name | Postfix | Resource Id
b1129ed0-8fae-40db-9161-44217223b6d2 | checklist | 03.41 - Rock Protection | itp | 03.41 - Rock Protection
3cd09632-e18b-4e45-85db-146dd0ccd4a3 | section | Details
bd077679-8a76-438d-bfe6-8470a5b595c8 | checkpoint | Rock complies with size requirements specified on drawings and shall have the following grading. D10 = 0.5m, D50 = 0.65m, D90 = 1.0m
f8a0de25-0e7e-5910-b943-9f9071071cf0 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
7e83db44-f325-50ec-8745-6f42fbfca493 | note | Check Item - Check Item
f6dbba65-89ec-5f39-ad4d-62eab26eb7f4 | note | Reference - MRTS03 Cl. 35 and Project Drawings
c95e0151-3951-40e6-9794-b468956c1a4b | checkpoint | Rock shall be clean, hard, dense and durable igneous or metamorphic rocks. It shall be resistant to weathering, free from overburden, spoil, shale and organic matter.
8622933d-cfba-5061-a4d8-cb02b809fb42 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
3f0dabe2-f6f8-5661-b155-bee066b13507 | note | Check Item - Check Item
c3a2af08-73d7-5afe-8c6a-1f403bdf9013 | note | Reference - MRTS03 Cl. 35.2
df099ca4-7e9c-4510-8b47-bf41e1f2efd3 | checkpoint | Rock Protection constructed in the locations and in accordance with the drawings
b555c07a-3094-5cac-9397-d7f0a2f7cdaf | note | Acceptance Criteria and Frequency (Project Specific) - Visual
b76bbec1-b437-5c34-ad17-97b055c5bcb4 | note | Check Item - Check Item
d04c6c04-0e74-5961-aef0-8459259763d2 | note | Reference - MRTS03 Cl. 35.3
85730f3e-d9ba-4ec5-aa88-d7034a08bf38 | checkpoint | Rock Protection is uniform in appearance and does not have noticeable veritical or horizontal irregularities
b75ed5aa-f215-5d19-a7ac-9d942f267d99 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
4d44fad5-76e9-56a4-bd9c-d39ff43454ea | note | Check Item - Check Item
20c39408-d61e-5402-a0ba-28702272602c | note | Reference - MRTS03 Cl. 35.3
3ef1d4b8-0284-48a9-aa48-16d10e2b76a4 | checkpoint | Rock material shall be placed such that larger rocks are uniformly distributed throughout the rockwork layer with smaller rocks filling the voids.
d99c03d1-1206-5b7d-806b-e2129ff878e2 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
b515c9aa-c5e3-5b6f-9339-fdcc1e990f9e | note | Check Item - Check Item
8fee6002-4dfd-566d-86ab-f8d41bcade92 | note | Reference - MRTS03 Cl. 35.3
8284bbd2-ba97-4a30-8447-89d244c51c1d | checkpoint | Where constructed on an embankment, rock protection is constructed concurrent with the embankment with no more than 1m vertical height of open embankment above the completed rock protection
a069d796-cb64-5050-997d-f4523baeacdc | note | Acceptance Criteria and Frequency (Project Specific) - Visual
8131191c-c210-58c0-9f20-1723dd7d11f6 | note | Check Item - Check Item
dd649b77-add1-5ae2-9e30-a213367439c2 | note | Reference - MRTS03 Cl. 35.3
8fc82d45-57db-4cde-8c5e-c711138adc97 | checkpoint | Cement mortar shall consist of one part Type GP cement to three parts fine sand. Materials shall coply with MRTS70
d7e9fe5f-bdc3-5cbb-b9a5-2131a563926b | note | Acceptance Criteria and Frequency (Project Specific) - Visual
be8d8647-b7c8-5f9e-b4d7-053e11bdcf0c | note | Check Item - Check Item
e5446081-d264-5251-8847-a0cd52009391 | note | Reference - MRTS03 Cl. 35.3
c9b5ea6c-3ab2-4acc-ad63-21523f6b9ae0 | checkpoint | Final Verification
ac16e7d4-3eb1-5eb5-bc62-807ef93a348f | note | Project Manager Verify that the Above has been Constructed according to Specification
563e6757-89ed-5887-8e3c-4256440ab3d4 | textbox | Print Name:
3fdfeabe-16a7-5f78-b0c3-5cc2495f697a | date | Date:
c2a5ba59-6ef5-576a-832b-65dcd4d2a78e | note | Client Verify that the Above has been Constructed according to Specification
ee369afd-55fc-58fb-8111-851cbedf4b16 | textbox | Print Name:
a540780c-f6ce-5f91-b4e3-a11c8d3be91d | date | Date:
821a9d5f-a6b6-4198-a5ff-f716c4092498 | signoff | Signature