## ITP Summary
Project\Job | 2025-22 - Upper Orara Culverts | values | Check list | options
checklist-sectioned | Precast Components ITP
section | Job Approval Documents/Construction Documents
checkpoint | Received Construction drawing from Client |  | Pass/Fail/NA | attachments/photos
checkpoint | Shop drawings Prepared, reviewed and updated. Issued "As For Construction" |  | Pass/Fail/NA | attachments/photos
All approvals, certificates, data warranties, guarantees, manuals, as-built drawings collected.
section | Pre-Pour Check Approvals
checkpoint | Formwork |  |  | attachments/photos/Sign
checkpoint | Reinforcement (Reo) |  |  | attachments/photos/Sign
checkpoint | Embedded Items and their placement |  |  | attachments/photos/Sign
checkpoint | Lift Procedure
checkpoint | Concreting (mix design) |  |  | attachments/photos/Sign
section | Test on Concrete (requests and approvals)
checkpoint | Request From Client |  |  | attachments/photos/Sign
checkpoint | Test schedule and Test Results |  |  | attachments/photos/Sign
section | Transport
Sub section 01 | Transport 01
| Any Lifting, Loading, Transport Instructions from Client |  | Pass/Fail/NA | attachments/photos/Sign
| Transport Vehicle Approvals |  | Pass/Fail/NA | attachments/photos/Sign
| Ensure loads are glutted correctly and chains are over gluts. |  | Pass/Fail/NA | attachments/photos/Sign
Sub section 02 | Transport 02
| Any Lifting, Loading, Transport Instructions from Client |  | Pass/Fail/NA | attachments/photos/Sign
| Transport Vehicle Approvals |  | Pass/Fail/NA | attachments/photos/Sign
| Ensure loads are glutted correctly and chains are over gluts. |  | Pass/Fail/NA | attachments/photos/Sign
Sub section 03 | Transport 03
| Any Lifting, Loading, Transport Instructions from Client |  | Pass/Fail/NA | attachments/photos/Sign
| Transport Vehicle Approvals |  | Pass/Fail/NA | attachments/photos/Sign
| Ensure loads are glutted correctly and chains are over gluts. |  | Pass/Fail/NA | attachments/photos/Sign
Sub section 04 | Transport 04
| Any Lifting, Loading, Transport Instructions from Client |  | Pass/Fail/NA | attachments/photos/Sign
| Transport Vehicle Approvals |  | Pass/Fail/NA | attachments/photos/Sign
| Ensure loads are glutted correctly and chains are over gluts. |  | Pass/Fail/NA | attachments/photos/Sign
section | Other Documentations
checkpoint | Special Instructions |  |  | attachments/photos/Sign
checkpoint | Other |  |  | attachments/photos/Sign
section | Installation
checkpoint | All PPE and safety requirements in place. Machinery inspections complete. |  | Pass/Fail/NA | attachments/photos/Sign
checkpoint | Notification of Inspection - all in accordance with approved shop drawings, correct size and location |  | Pass/Fail/NA | attachments/photos/Sign
tick box | Set out
tick box | Core Holes
tick box | Install dowels
checkpoint | Pre approvals for the cast insitu concrete |  | Pass/Fail/NA | attachments/photos/Sign
checkpoint | Installation of precast panels including back propping. Correct location, connections, finish confirmed against shop drawings. |  | Pass/Fail/NA | attachments/photos/Sign
checkpoint | Grouting and sealing |  | Pass/Fail/NA | attachments/photos/Sign
checkpoint | Remove back propping when instructed by consulting Engineers. |  | Pass/Fail/NA | attachments/photos/Sign
section | Final Inspection
tick box | Wall + Wall+ Roof |  | Pass/Fail/NA | attachments/photos/Sign
tick box | Wall + Wall+ Roof |  | Pass/Fail/NA | attachments/photos/Sign
tick box | Wall + Wall+ Roof |  | Pass/Fail/NA | attachments/photos/Sign
tick box | Wall + Wall+ Roof |  | Pass/Fail/NA | attachments/photos/Sign | Repeating items
checkpoint | All approvals, certificates, data warranties, guarantees, manuals, as-built drawings collected. |  | Pass/Fail/NA | attachments/photos/Sign
No Repeating Items

## Culvert 1
Project | 2025-22 - Upper Orara Culverts
checklist | Checkers Checklist
section | Culvert Wall - C1-W1
checkpoint | Availability of updated shop drawing | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Site Safety / Workers Safety | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Overall Measurements of construction Element | Pass/Fail/NA | attachments/photos/Comments
tick box | Formwork Check - Magnets are 100% Secure, All supports,Ties,Bracing
tick box | Formwork Check - Flatness, Levelness, Panel is clean
tick box | Formwork Check - Double check the measurement with Diagonal check
tick box | Apply Debonding agents -bond breaker or wax (1/2/3/ Coats)
checkpoint | Reinforcement (Reo) placed, cleaned, tightened | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Embedded Item -Placement, position, alignment | Pass/Fail/NA | attachments/photos/Comments
tick box | Concrete cover- 30mm
tick box | Lifters - 2 x Foot Anchor - 10t x 340mm
tick box | ID Plate
checkpoint | Curing Procedure arranged | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Shape the concrete up to pipe invert level | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Final Check, Photo Taken | Pass/Fail/NA | attachments/photos/Comments
section | Culvert Wall - C1-W2
checkpoint | Availability of updated shop drawing | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Site Safety / Workers Safety | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Overall Measurements of construction Element | Pass/Fail/NA | attachments/photos/Comments
tick box | Formwork Check - Magnets are 100% Secure, All supports,Ties,Bracing
tick box | Formwork Check - Flatness, Levelness, Panel is clean
tick box | Formwork Check - Double check the measurement with Diagonal check
tick box | Apply Debonding agents -bond breaker or wax (1/2/3/ Coats)
checkpoint | Reinforcement (Reo) placed, cleaned, tightened | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Embedded Item -Placement, position, alignment | Pass/Fail/NA | attachments/photos/Comments
tick box | Concrete cover- 30mm
tick box | Lifters - 2 x Foot Anchor - 10t x 340mm
tick box | ID Plate
checkpoint | Curing Procedure arranged | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Shape the concrete up to pipe invert level | Pass/Fail/NA | attachments/photos/Comments
Final Check, Photo Taken
section | Culvert Roof - C1-R
checkpoint | Availability of updated shop drawing | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Site Safety / Workers Safety | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Overall Measurements of construction Element | Pass/Fail/NA | attachments/photos/Comments
tick box | Formwork Check - Magnets are 100% Secure, All supports,Ties,Bracing
tick box | Formwork Check - Flatness, Levelness, Panel is clean
tick box | Formwork Check - Double check the measurement with Diagonal check
tick box | Apply Debonding agents -bond breaker or wax (1/2/3/ Coats)
checkpoint | Reinforcement (Reo) placed, cleaned, tightened | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Embedded Item -Placement, position, alignment | Pass/Fail/NA | attachments/photos/Comments
tick box | Concrete cover- 30mm
tick box | Lifters - 4 x Foot Anchor - 10t x 340mm
tick box | ID Plate
checkpoint | Curing Procedure arranged | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Shape the concrete up to pipe invert level | Pass/Fail/NA | attachments/photos/Comments
Final Check, Photo Taken
checklist | Installers Checklist
section | Culvert Wall - C1-W1
checkpoint | Availability of updated shop drawing | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Site Safety / Workers Safety | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Overall Measurements of construction Element (Attach Photos) | Pass/Fail/NA | attachments/photos/Comments
tick box | Formwork Check - Magnets are 100% Secure, All supports,Ties,Bracing
tick box | Formwork Check - Flatness, Levelness, Panel is clean
tick box | Formwork Check - Double check the measurement with Diagonal check
tick box | Apply Debonding agents -bond breaker or wax (1/2/3/ Coats)
checkpoint | Reinforcement (Reo) placed, cleaned, tightened | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Embedded Item -Placement, position, alignment | Pass/Fail/NA | attachments/photos/Comments
tick box | Concrete cover- 30mm
tick box | Lifters - 2 x Foot Anchor - 10t x 340mm
tick box | ID Plate
checkpoint | Curing Procedure arranged | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Shape the concrete up to pipe invert level | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Final Check, Photo Taken | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Curing Procedure arranged | Pass/Fail/NA | attachments/photos/Comments
date | Pour Date
section | Quality Assurance - C1-W1
checkpoint | QA - All requirement to do Concreting -DOUBLE CHECK | Pass/Fail/NA | attachments/photos/Comments
tick box | QA - Concrete NS502PAN2 - Special Adjustments | Pass/Fail/NA | attachments/photos/Comments
checkpoint | QA - Concrete mix design ,variations%, adjustments%, mix time | Pass/Fail/NA | attachments/photos/Comments
checkpoint | CONCRETE TEST Procedure | Pass/Fail/NA | attachments/photos/Comments
checkpoint | APPROVAL FROM ENGINEER | Pass/Fail/NA | attachments/photos/Comments
section | Culvert Wall - C1-W2
checkpoint | Availability of updated shop drawing | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Site Safety / Workers Safety | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Overall Measurements of construction Element (Attach Photos) | Pass/Fail/NA | attachments/photos/Comments
tick box | Formwork Check - Magnets are 100% Secure, All supports,Ties,Bracing
tick box | Formwork Check - Flatness, Levelness, Panel is clean
tick box | Formwork Check - Double check the measurement with Diagonal check |  |  | Repeating items
tick box | Apply Debonding agents -bond breaker or wax (1/2/3/ Coats)
checkpoint | Reinforcement (Reo) placed, cleaned, tightened | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Embedded Item -Placement, position, alignment | Pass/Fail/NA | attachments/photos/Comments
tick box | Concrete cover- 30mm
tick box | Lifters - 2 x Foot Anchor - 10t x 340mm
tick box | ID Plate
checkpoint | Curing Procedure arranged | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Final Check, Photo Taken | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Curing Procedure arranged | Pass/Fail/NA | attachments/photos/Comments
date | Pour Date
section | Quality Assurance - C1-W2
checkpoint | QA - All requirement to do Concreting -DOUBLE CHECK | Pass/Fail/NA | attachments/photos/Comments
tick box | QA - Concrete NS502PAN2 - Special Adjustments | Pass/Fail/NA | attachments/photos/Comments
checkpoint | QA - Concrete mix design ,variations%, adjustments%, mix time | Pass/Fail/NA | attachments/photos/Comments
checkpoint | CONCRETE TEST Procedure | Pass/Fail/NA | attachments/photos/Comments
checkpoint | APPROVAL FROM ENGINEER | Pass/Fail/NA | attachments/photos/Comments
section | Culvert Roof - C1-R
checkpoint | Availability of updated shop drawing | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Site Safety / Workers Safety | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Overall Measurements of construction Element (Attach Photos) | Pass/Fail/NA | attachments/photos/Comments
tick box | Formwork Check - Magnets are 100% Secure, All supports,Ties,Bracing
tick box | Formwork Check - Flatness, Levelness, Panel is clean
tick box | Formwork Check - Double check the measurement with Diagonal check
tick box | Apply Debonding agents -bond breaker or wax (1/2/3/ Coats)
checkpoint | Reinforcement (Reo) placed, cleaned, tightened | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Embedded Item -Placement, position, alignment | Pass/Fail/NA | attachments/photos/Comments
tick box | Concrete cover- 30mm
tick box | Lifters - 4 x Foot Anchor - 10t x 340mm
tick box | ID Plate
checkpoint | Curing Procedure arranged | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Final Check, Photo Taken | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Curing Procedure arranged | Pass/Fail/NA | attachments/photos/Comments
date | Pour Date
section | Quality Assurance - C1-R
checkpoint | QA - All requirement to do Concreting -DOUBLE CHECK | Pass/Fail/NA | attachments/photos/Comments
tick box | QA - Concrete NS502PAN2 - Special Adjustments | Pass/Fail/NA | attachments/photos/Comments
checkpoint | QA - Concrete mix design ,variations%, adjustments%, mix time | Pass/Fail/NA | attachments/photos/Comments
checkpoint | CONCRETE TEST Procedure | Pass/Fail/NA | attachments/photos/Comments
checkpoint | APPROVAL FROM ENGINEER | Pass/Fail/NA | attachments/photos/Comments
No Repeating Items

## Culvert 2
Project | 2025-22 - Upper Orara Culverts
checklist | Checkers Checklist
section | Culvert Wall - C1-W1
checkpoint | Availability of updated shop drawing | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Site Safety / Workers Safety | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Overall Measurements of construction Element | Pass/Fail/NA | attachments/photos/Comments
tick box | Formwork Check - Magnets are 100% Secure, All supports,Ties,Bracing
tick box | Formwork Check - Flatness, Levelness, Panel is clean
tick box | Formwork Check - Double check the measurement with Diagonal check
tick box | Apply Debonding agents -bond breaker or wax (1/2/3/ Coats)
checkpoint | Reinforcement (Reo) placed, cleaned, tightened | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Embedded Item -Placement, position, alignment | Pass/Fail/NA | attachments/photos/Comments
tick box | Concrete cover- 30mm
tick box | Lifters - 2 x Foot Anchor - 10t x 340mm
tick box | ID Plate
checkpoint | Curing Procedure arranged | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Shape the concrete up to pipe invert level | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Final Check, Photo Taken | Pass/Fail/NA | attachments/photos/Comments
section | Culvert Wall - C2-W2
checkpoint | Availability of updated shop drawing | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Site Safety / Workers Safety | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Overall Measurements of construction Element | Pass/Fail/NA | attachments/photos/Comments
tick box | Formwork Check - Magnets are 100% Secure, All supports,Ties,Bracing
tick box | Formwork Check - Flatness, Levelness, Panel is clean
tick box | Formwork Check - Double check the measurement with Diagonal check
tick box | Apply Debonding agents -bond breaker or wax (1/2/3/ Coats)
checkpoint | Reinforcement (Reo) placed, cleaned, tightened | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Embedded Item -Placement, position, alignment | Pass/Fail/NA | attachments/photos/Comments
tick box | Concrete cover- 30mm
tick box | Lifters - 2 x Foot Anchor - 10t x 340mm
tick box | ID Plate
checkpoint | Curing Procedure arranged | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Shape the concrete up to pipe invert level | Pass/Fail/NA | attachments/photos/Comments
Final Check, Photo Taken
section | Culvert Roof - C2-R
checkpoint | Availability of updated shop drawing | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Site Safety / Workers Safety | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Overall Measurements of construction Element | Pass/Fail/NA | attachments/photos/Comments
tick box | Formwork Check - Magnets are 100% Secure, All supports,Ties,Bracing
tick box | Formwork Check - Flatness, Levelness, Panel is clean
tick box | Formwork Check - Double check the measurement with Diagonal check
tick box | Apply Debonding agents -bond breaker or wax (1/2/3/ Coats)
checkpoint | Reinforcement (Reo) placed, cleaned, tightened | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Embedded Item -Placement, position, alignment | Pass/Fail/NA | attachments/photos/Comments
tick box | Concrete cover- 30mm
tick box | Lifters - 4 x Foot Anchor - 10t x 340mm
tick box | ID Plate
checkpoint | Curing Procedure arranged | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Shape the concrete up to pipe invert level | Pass/Fail/NA | attachments/photos/Comments
Final Check, Photo Taken
checklist | Installers Checklist
section | Culvert Wall - C2-W1
checkpoint | Availability of updated shop drawing | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Site Safety / Workers Safety | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Overall Measurements of construction Element (Attach Photos) | Pass/Fail/NA | attachments/photos/Comments
tick box | Formwork Check - Magnets are 100% Secure, All supports,Ties,Bracing
tick box | Formwork Check - Flatness, Levelness, Panel is clean
tick box | Formwork Check - Double check the measurement with Diagonal check
tick box | Apply Debonding agents -bond breaker or wax (1/2/3/ Coats)
checkpoint | Reinforcement (Reo) placed, cleaned, tightened | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Embedded Item -Placement, position, alignment | Pass/Fail/NA | attachments/photos/Comments
tick box | Concrete cover- 30mm
tick box | Lifters - 2 x Foot Anchor - 10t x 340mm
tick box | ID Plate
checkpoint | Curing Procedure arranged | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Shape the concrete up to pipe invert level | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Final Check, Photo Taken | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Curing Procedure arranged | Pass/Fail/NA | attachments/photos/Comments
date | Pour Date
section | Quality Assurance - C2-W1
checkpoint | QA - All requirement to do Concreting -DOUBLE CHECK | Pass/Fail/NA | attachments/photos/Comments
tick box | QA - Concrete NS502PAN2 - Special Adjustments | Pass/Fail/NA | attachments/photos/Comments
checkpoint | QA - Concrete mix design ,variations%, adjustments%, mix time | Pass/Fail/NA | attachments/photos/Comments
checkpoint | CONCRETE TEST Procedure | Pass/Fail/NA | attachments/photos/Comments
checkpoint | APPROVAL FROM ENGINEER | Pass/Fail/NA | attachments/photos/Comments
section | Culvert Wall - C2-W2
checkpoint | Availability of updated shop drawing | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Site Safety / Workers Safety | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Overall Measurements of construction Element (Attach Photos) | Pass/Fail/NA | attachments/photos/Comments
tick box | Formwork Check - Magnets are 100% Secure, All supports,Ties,Bracing
tick box | Formwork Check - Flatness, Levelness, Panel is clean
tick box | Formwork Check - Double check the measurement with Diagonal check |  |  | Repeating items
tick box | Apply Debonding agents -bond breaker or wax (1/2/3/ Coats)
checkpoint | Reinforcement (Reo) placed, cleaned, tightened | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Embedded Item -Placement, position, alignment | Pass/Fail/NA | attachments/photos/Comments
tick box | Concrete cover- 30mm
tick box | Lifters - 2 x Foot Anchor - 10t x 340mm
tick box | ID Plate
checkpoint | Curing Procedure arranged | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Final Check, Photo Taken | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Curing Procedure arranged | Pass/Fail/NA | attachments/photos/Comments
date | Pour Date
section | Quality Assurance - C2-W2
checkpoint | QA - All requirement to do Concreting -DOUBLE CHECK | Pass/Fail/NA | attachments/photos/Comments
tick box | QA - Concrete NS502PAN2 - Special Adjustments | Pass/Fail/NA | attachments/photos/Comments
checkpoint | QA - Concrete mix design ,variations%, adjustments%, mix time | Pass/Fail/NA | attachments/photos/Comments
checkpoint | CONCRETE TEST Procedure | Pass/Fail/NA | attachments/photos/Comments
checkpoint | APPROVAL FROM ENGINEER | Pass/Fail/NA | attachments/photos/Comments
section | Culvert Roof - C2-R
checkpoint | Availability of updated shop drawing | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Site Safety / Workers Safety | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Overall Measurements of construction Element (Attach Photos) | Pass/Fail/NA | attachments/photos/Comments
tick box | Formwork Check - Magnets are 100% Secure, All supports,Ties,Bracing
tick box | Formwork Check - Flatness, Levelness, Panel is clean
tick box | Formwork Check - Double check the measurement with Diagonal check
tick box | Apply Debonding agents -bond breaker or wax (1/2/3/ Coats)
checkpoint | Reinforcement (Reo) placed, cleaned, tightened | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Embedded Item -Placement, position, alignment | Pass/Fail/NA | attachments/photos/Comments
tick box | Concrete cover- 30mm
tick box | Lifters - 4 x Foot Anchor - 10t x 340mm
tick box | ID Plate
checkpoint | Curing Procedure arranged | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Final Check, Photo Taken | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Curing Procedure arranged | Pass/Fail/NA | attachments/photos/Comments
date | Pour Date
section | Quality Assurance - C2-R
checkpoint | QA - All requirement to do Concreting -DOUBLE CHECK | Pass/Fail/NA | attachments/photos/Comments
tick box | QA - Concrete NS502PAN2 - Special Adjustments | Pass/Fail/NA | attachments/photos/Comments
checkpoint | QA - Concrete mix design ,variations%, adjustments%, mix time | Pass/Fail/NA | attachments/photos/Comments
checkpoint | CONCRETE TEST Procedure | Pass/Fail/NA | attachments/photos/Comments
checkpoint | APPROVAL FROM ENGINEER | Pass/Fail/NA | attachments/photos/Comments
No Repeating Items

## Culvert 3
Project | 2025-22 - Upper Orara Culverts
checklist | Checkers Checklist
section | Culvert Wall - C1-W1
checkpoint | Availability of updated shop drawing | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Site Safety / Workers Safety | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Overall Measurements of construction Element | Pass/Fail/NA | attachments/photos/Comments
tick box | Formwork Check - Magnets are 100% Secure, All supports,Ties,Bracing
tick box | Formwork Check - Flatness, Levelness, Panel is clean
tick box | Formwork Check - Double check the measurement with Diagonal check
tick box | Apply Debonding agents -bond breaker or wax (1/2/3/ Coats)
checkpoint | Reinforcement (Reo) placed, cleaned, tightened | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Embedded Item -Placement, position, alignment | Pass/Fail/NA | attachments/photos/Comments
tick box | Concrete cover- 30mm
tick box | Lifters - 2 x Foot Anchor - 10t x 340mm
tick box | ID Plate
checkpoint | Curing Procedure arranged | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Shape the concrete up to pipe invert level | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Final Check, Photo Taken | Pass/Fail/NA | attachments/photos/Comments
section | Culvert Wall - C3-W2
checkpoint | Availability of updated shop drawing | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Site Safety / Workers Safety | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Overall Measurements of construction Element | Pass/Fail/NA | attachments/photos/Comments
tick box | Formwork Check - Magnets are 100% Secure, All supports,Ties,Bracing
tick box | Formwork Check - Flatness, Levelness, Panel is clean
tick box | Formwork Check - Double check the measurement with Diagonal check
tick box | Apply Debonding agents -bond breaker or wax (1/2/3/ Coats)
checkpoint | Reinforcement (Reo) placed, cleaned, tightened | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Embedded Item -Placement, position, alignment | Pass/Fail/NA | attachments/photos/Comments
tick box | Concrete cover- 30mm
tick box | Lifters - 2 x Foot Anchor - 10t x 340mm
tick box | ID Plate
checkpoint | Curing Procedure arranged | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Shape the concrete up to pipe invert level | Pass/Fail/NA | attachments/photos/Comments
Final Check, Photo Taken
section | Culvert Roof - C3-R
checkpoint | Availability of updated shop drawing | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Site Safety / Workers Safety | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Overall Measurements of construction Element | Pass/Fail/NA | attachments/photos/Comments
tick box | Formwork Check - Magnets are 100% Secure, All supports,Ties,Bracing
tick box | Formwork Check - Flatness, Levelness, Panel is clean
tick box | Formwork Check - Double check the measurement with Diagonal check
tick box | Apply Debonding agents -bond breaker or wax (1/2/3/ Coats)
checkpoint | Reinforcement (Reo) placed, cleaned, tightened | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Embedded Item -Placement, position, alignment | Pass/Fail/NA | attachments/photos/Comments
tick box | Concrete cover- 30mm
tick box | Lifters - 4 x Foot Anchor - 10t x 340mm
tick box | ID Plate
checkpoint | Curing Procedure arranged | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Shape the concrete up to pipe invert level | Pass/Fail/NA | attachments/photos/Comments
Final Check, Photo Taken
checklist | Installers Checklist
section | Culvert Wall - C3-W1
checkpoint | Availability of updated shop drawing | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Site Safety / Workers Safety | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Overall Measurements of construction Element (Attach Photos) | Pass/Fail/NA | attachments/photos/Comments
tick box | Formwork Check - Magnets are 100% Secure, All supports,Ties,Bracing
tick box | Formwork Check - Flatness, Levelness, Panel is clean
tick box | Formwork Check - Double check the measurement with Diagonal check
tick box | Apply Debonding agents -bond breaker or wax (1/2/3/ Coats)
checkpoint | Reinforcement (Reo) placed, cleaned, tightened | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Embedded Item -Placement, position, alignment | Pass/Fail/NA | attachments/photos/Comments
tick box | Concrete cover- 30mm
tick box | Lifters - 2 x Foot Anchor - 10t x 340mm
tick box | ID Plate
checkpoint | Curing Procedure arranged | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Shape the concrete up to pipe invert level | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Final Check, Photo Taken | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Curing Procedure arranged | Pass/Fail/NA | attachments/photos/Comments
date | Pour Date
section | Quality Assurance - C3-W1
checkpoint | QA - All requirement to do Concreting -DOUBLE CHECK | Pass/Fail/NA | attachments/photos/Comments
tick box | QA - Concrete NS502PAN2 - Special Adjustments | Pass/Fail/NA | attachments/photos/Comments
checkpoint | QA - Concrete mix design ,variations%, adjustments%, mix time | Pass/Fail/NA | attachments/photos/Comments
checkpoint | CONCRETE TEST Procedure | Pass/Fail/NA | attachments/photos/Comments
checkpoint | APPROVAL FROM ENGINEER | Pass/Fail/NA | attachments/photos/Comments
section | Culvert Wall - C3-W2
checkpoint | Availability of updated shop drawing | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Site Safety / Workers Safety | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Overall Measurements of construction Element (Attach Photos) | Pass/Fail/NA | attachments/photos/Comments
tick box | Formwork Check - Magnets are 100% Secure, All supports,Ties,Bracing
tick box | Formwork Check - Flatness, Levelness, Panel is clean
tick box | Formwork Check - Double check the measurement with Diagonal check |  |  | Repeating items
tick box | Apply Debonding agents -bond breaker or wax (1/2/3/ Coats)
checkpoint | Reinforcement (Reo) placed, cleaned, tightened | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Embedded Item -Placement, position, alignment | Pass/Fail/NA | attachments/photos/Comments
tick box | Concrete cover- 30mm
tick box | Lifters - 2 x Foot Anchor - 10t x 340mm
tick box | ID Plate
checkpoint | Curing Procedure arranged | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Final Check, Photo Taken | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Curing Procedure arranged | Pass/Fail/NA | attachments/photos/Comments
date | Pour Date
section | Quality Assurance - C3-W2
checkpoint | QA - All requirement to do Concreting -DOUBLE CHECK | Pass/Fail/NA | attachments/photos/Comments
tick box | QA - Concrete NS502PAN2 - Special Adjustments | Pass/Fail/NA | attachments/photos/Comments
checkpoint | QA - Concrete mix design ,variations%, adjustments%, mix time | Pass/Fail/NA | attachments/photos/Comments
checkpoint | CONCRETE TEST Procedure | Pass/Fail/NA | attachments/photos/Comments
checkpoint | APPROVAL FROM ENGINEER | Pass/Fail/NA | attachments/photos/Comments
section | Culvert Roof - C3-R
checkpoint | Availability of updated shop drawing | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Site Safety / Workers Safety | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Overall Measurements of construction Element (Attach Photos) | Pass/Fail/NA | attachments/photos/Comments
tick box | Formwork Check - Magnets are 100% Secure, All supports,Ties,Bracing
tick box | Formwork Check - Flatness, Levelness, Panel is clean
tick box | Formwork Check - Double check the measurement with Diagonal check
tick box | Apply Debonding agents -bond breaker or wax (1/2/3/ Coats)
checkpoint | Reinforcement (Reo) placed, cleaned, tightened | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Embedded Item -Placement, position, alignment | Pass/Fail/NA | attachments/photos/Comments
tick box | Concrete cover- 30mm
tick box | Lifters - 4 x Foot Anchor - 10t x 340mm
tick box | ID Plate
checkpoint | Curing Procedure arranged | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Final Check, Photo Taken | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Curing Procedure arranged | Pass/Fail/NA | attachments/photos/Comments
date | Pour Date
section | Quality Assurance - C3-R
checkpoint | QA - All requirement to do Concreting -DOUBLE CHECK | Pass/Fail/NA | attachments/photos/Comments
tick box | QA - Concrete NS502PAN2 - Special Adjustments | Pass/Fail/NA | attachments/photos/Comments
checkpoint | QA - Concrete mix design ,variations%, adjustments%, mix time | Pass/Fail/NA | attachments/photos/Comments
checkpoint | CONCRETE TEST Procedure | Pass/Fail/NA | attachments/photos/Comments
checkpoint | APPROVAL FROM ENGINEER | Pass/Fail/NA | attachments/photos/Comments
No Repeating Items

## Culvert 4
Project | 2025-22 - Upper Orara Culverts
checklist | Checkers Checklist
section | Culvert Wall - C4-W1
checkpoint | Availability of updated shop drawing | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Site Safety / Workers Safety | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Overall Measurements of construction Element | Pass/Fail/NA | attachments/photos/Comments
tick box | Formwork Check - Magnets are 100% Secure, All supports,Ties,Bracing
tick box | Formwork Check - Flatness, Levelness, Panel is clean
tick box | Formwork Check - Double check the measurement with Diagonal check
tick box | Apply Debonding agents -bond breaker or wax (1/2/3/ Coats)
checkpoint | Reinforcement (Reo) placed, cleaned, tightened | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Embedded Item -Placement, position, alignment | Pass/Fail/NA | attachments/photos/Comments
tick box | Concrete cover- 30mm
tick box | Lifters - 2 x Foot Anchor - 10t x 340mm
tick box | ID Plate
checkpoint | Curing Procedure arranged | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Shape the concrete up to pipe invert level | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Final Check, Photo Taken | Pass/Fail/NA | attachments/photos/Comments
section | Culvert Wall - C4-W2
checkpoint | Availability of updated shop drawing | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Site Safety / Workers Safety | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Overall Measurements of construction Element | Pass/Fail/NA | attachments/photos/Comments
tick box | Formwork Check - Magnets are 100% Secure, All supports,Ties,Bracing
tick box | Formwork Check - Flatness, Levelness, Panel is clean
tick box | Formwork Check - Double check the measurement with Diagonal check
tick box | Apply Debonding agents -bond breaker or wax (1/2/3/ Coats)
checkpoint | Reinforcement (Reo) placed, cleaned, tightened | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Embedded Item -Placement, position, alignment | Pass/Fail/NA | attachments/photos/Comments
tick box | Concrete cover- 30mm
tick box | Lifters - 2 x Foot Anchor - 10t x 340mm
tick box | ID Plate
checkpoint | Curing Procedure arranged | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Shape the concrete up to pipe invert level | Pass/Fail/NA | attachments/photos/Comments
Final Check, Photo Taken
section | Culvert Roof - C4-R
checkpoint | Availability of updated shop drawing | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Site Safety / Workers Safety | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Overall Measurements of construction Element | Pass/Fail/NA | attachments/photos/Comments
tick box | Formwork Check - Magnets are 100% Secure, All supports,Ties,Bracing
tick box | Formwork Check - Flatness, Levelness, Panel is clean
tick box | Formwork Check - Double check the measurement with Diagonal check
tick box | Apply Debonding agents -bond breaker or wax (1/2/3/ Coats)
checkpoint | Reinforcement (Reo) placed, cleaned, tightened | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Embedded Item -Placement, position, alignment | Pass/Fail/NA | attachments/photos/Comments
tick box | Concrete cover- 30mm
tick box | Lifters - 4 x Foot Anchor - 10t x 340mm
tick box | ID Plate
checkpoint | Curing Procedure arranged | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Shape the concrete up to pipe invert level | Pass/Fail/NA | attachments/photos/Comments
Final Check, Photo Taken
checklist | Installers Checklist
section | Culvert Wall - C4-W1
checkpoint | Availability of updated shop drawing | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Site Safety / Workers Safety | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Overall Measurements of construction Element (Attach Photos) | Pass/Fail/NA | attachments/photos/Comments
tick box | Formwork Check - Magnets are 100% Secure, All supports,Ties,Bracing
tick box | Formwork Check - Flatness, Levelness, Panel is clean
tick box | Formwork Check - Double check the measurement with Diagonal check
tick box | Apply Debonding agents -bond breaker or wax (1/2/3/ Coats)
checkpoint | Reinforcement (Reo) placed, cleaned, tightened | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Embedded Item -Placement, position, alignment | Pass/Fail/NA | attachments/photos/Comments
tick box | Concrete cover- 30mm
tick box | Lifters - 2 x Foot Anchor - 10t x 340mm
tick box | ID Plate
checkpoint | Curing Procedure arranged | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Shape the concrete up to pipe invert level | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Final Check, Photo Taken | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Curing Procedure arranged | Pass/Fail/NA | attachments/photos/Comments
date | Pour Date
section | Quality Assurance - C4-W1
checkpoint | QA - All requirement to do Concreting -DOUBLE CHECK | Pass/Fail/NA | attachments/photos/Comments
tick box | QA - Concrete NS502PAN2 - Special Adjustments | Pass/Fail/NA | attachments/photos/Comments
checkpoint | QA - Concrete mix design ,variations%, adjustments%, mix time | Pass/Fail/NA | attachments/photos/Comments
checkpoint | CONCRETE TEST Procedure | Pass/Fail/NA | attachments/photos/Comments
checkpoint | APPROVAL FROM ENGINEER | Pass/Fail/NA | attachments/photos/Comments
section | Culvert Wall - C4-W2
checkpoint | Availability of updated shop drawing | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Site Safety / Workers Safety | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Overall Measurements of construction Element (Attach Photos) | Pass/Fail/NA | attachments/photos/Comments
tick box | Formwork Check - Magnets are 100% Secure, All supports,Ties,Bracing
tick box | Formwork Check - Flatness, Levelness, Panel is clean
tick box | Formwork Check - Double check the measurement with Diagonal check |  |  | Repeating items
tick box | Apply Debonding agents -bond breaker or wax (1/2/3/ Coats)
checkpoint | Reinforcement (Reo) placed, cleaned, tightened | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Embedded Item -Placement, position, alignment | Pass/Fail/NA | attachments/photos/Comments
tick box | Concrete cover- 30mm
tick box | Lifters - 2 x Foot Anchor - 10t x 340mm
tick box | ID Plate
checkpoint | Curing Procedure arranged | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Final Check, Photo Taken | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Curing Procedure arranged | Pass/Fail/NA | attachments/photos/Comments
date | Pour Date
section | Quality Assurance - C4-W2
checkpoint | QA - All requirement to do Concreting -DOUBLE CHECK | Pass/Fail/NA | attachments/photos/Comments
tick box | QA - Concrete NS502PAN2 - Special Adjustments | Pass/Fail/NA | attachments/photos/Comments
checkpoint | QA - Concrete mix design ,variations%, adjustments%, mix time | Pass/Fail/NA | attachments/photos/Comments
checkpoint | CONCRETE TEST Procedure | Pass/Fail/NA | attachments/photos/Comments
checkpoint | APPROVAL FROM ENGINEER | Pass/Fail/NA | attachments/photos/Comments
section | Culvert Roof - C4-R
checkpoint | Availability of updated shop drawing | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Site Safety / Workers Safety | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Overall Measurements of construction Element (Attach Photos) | Pass/Fail/NA | attachments/photos/Comments
tick box | Formwork Check - Magnets are 100% Secure, All supports,Ties,Bracing
tick box | Formwork Check - Flatness, Levelness, Panel is clean
tick box | Formwork Check - Double check the measurement with Diagonal check
tick box | Apply Debonding agents -bond breaker or wax (1/2/3/ Coats)
checkpoint | Reinforcement (Reo) placed, cleaned, tightened | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Embedded Item -Placement, position, alignment | Pass/Fail/NA | attachments/photos/Comments
tick box | Concrete cover- 30mm
tick box | Lifters - 4 x Foot Anchor - 10t x 340mm
tick box | ID Plate
checkpoint | Curing Procedure arranged | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Final Check, Photo Taken | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Curing Procedure arranged | Pass/Fail/NA | attachments/photos/Comments
date | Pour Date
section | Quality Assurance - C4-R
checkpoint | QA - All requirement to do Concreting -DOUBLE CHECK | Pass/Fail/NA | attachments/photos/Comments
tick box | QA - Concrete NS502PAN2 - Special Adjustments | Pass/Fail/NA | attachments/photos/Comments
checkpoint | QA - Concrete mix design ,variations%, adjustments%, mix time | Pass/Fail/NA | attachments/photos/Comments
checkpoint | CONCRETE TEST Procedure | Pass/Fail/NA | attachments/photos/Comments
checkpoint | APPROVAL FROM ENGINEER | Pass/Fail/NA | attachments/photos/Comments
No Repeating Items

## Instaler CheckList PL Panels (hidden)
checklist | Checkers Checklist
checkpoint | Site Safety / Workers Safety |  | Pass/Fail/NA | attachments/photoes/Coments
checkpoint | Availability of updated shop drawing |  | Pass/Fail/NA | attachments/photoes/Coments
checkpoint | Overall Measurements of construction Eliment |  | Pass/Fail/NA | attachments/photoes/Coments
checkpoint | Embeded Item - Void - Position,Size,Orientation |  | Pass/Fail/NA | attachments/photoes/Coments
checkpoint | Embeded Item - Ferrules - - Position,Size,Orientation - NS / FS |  | Pass/Fail/NA | attachments/photoes/Coments
checkpoint | Embeded Item - Lifters Correct - Position,Size,Orientation |  | Pass/Fail/NA | attachments/photoes/Coments
checkpoint | Embeded Item - Fillet / Chamfer instasllation |  | Pass/Fail/NA | attachments/photoes/Coments
checkpoint | Concrete cover check minimum 30mm |  | Pass/Fail/NA | attachments/photoes/Coments
checkpoint | Panel Thickness check |  | Pass/Fail/NA | attachments/photoes/Coments
dropdown |  | 150mm
dropdown |  | 200mm
checkpoint | Panel length check |  | Pass/Fail/NA | attachments/photoes/Coments
dropdown |  | 15m
dropdown |  | 16m
checkpoint | Formwork Check - Magnets are 100% Secure,All supports,Ties |  | Pass/Fail/NA | attachments/photoes/Coments
checkpoint | Formwork Check - Panel is clean |  | Pass/Fail/NA | attachments/photoes/Coments
checkpoint | Reinforcment (Reo) arrangmnet |  | Pass/Fail/NA | attachments/photoes/Coments
checkpoint | Curing Procedure arranged |  | Pass/Fail/NA | attachments/photoes/Coments
checkpoint | Photo Taken |  | Pass/Fail/NA | attachments/photoes/Coments
Kempsey Sale Yard
checklist | Installers Checklist
section | Job Aproval Documents/Construction Documents
checkpoint | Complete Material "Bucket List" |  | Pass/Fail/NA | attachments/photoes/Coments
checkpoint | Eye Anchor - Pinhead Lifter Galvanised 5Ton x 180mm (LA05180) |  | Pass/Fail/NA | attachments/photoes/Coments
checkpoint | Embeded Item - Void - Position,Size,Orientation |  | Pass/Fail/NA | attachments/photoes
dropdown |  | 0
dropdown |  | 4
dropdown |  | 6
dropdown |  | 7
dropdown |  | 8
dropdown |  | 9
dropdown |  | other
checkpoint | Embeded Item - Ferrules -M16x96 - Position,Size,Orientation - NS / FS |  | Pass/Fail/NA | attachments/photoes
dropdown |  | 2
dropdown |  | 6
dropdown |  | 8
dropdown |  | 9
dropdown |  | 10
dropdown |  | 12
dropdown |  | other
checkpoint | ID Plate |  |  | attachments/photoes/Coments
text box
section | Pre-Pour Check Approvals
checkpoint | Formwork Check -Panel Dimensions & DOUBLE CHECK |  | Pass/Fail/NA | attachments/photoes/Coments
checkpoint | Apply Debonding agents -bond breaker or wax (1/2/3/ Coats) |  | Pass/Fail/NA | attachments/photoes/Coments
checkpoint | Temporary Fix ID Plate to Formwork |  | Pass/Fail/NA | attachments/photoes/Coments
checkpoint | Use Required Mould,Supports,Ties - Bridge Plank Mould |  | Pass/Fail/NA | attachments/photoes/Coments
checkpoint | Reinforcment Check - Reo as-per Shop Drawing |  | Pass/Fail/NA | attachments/photoes/Coments
checkpoint | Lifters, Ferrules, Tubes Fixed Firm & alligned -Check |  | Pass/Fail/NA | attachments/photoes/Coments
checkpoint | Concrete cover Check - (top min cov30mm, Bottom Min Cov 25mm) |  | Pass/Fail/NA | attachments/photoes/Coments
section | Quality Assuarance
checkpoint | QA - Final Check of ALL measurerments & Diaganals |  | Pass/Fail/NA | attachments/photoes/Coments
checkpoint | QA - Concrete N40 Panel Mix - Special Adjustments |  | Pass/Fail/NA | attachments/photoes/Coments
checkpoint | QA - Concrete mixdesign ,veriations%, adjustments%,mix time |  | Pass/Fail/NA | attachments/photoes/Coments
checkpoint | QA - All main & other requirment to do Concreting -DOUBLE CHECK |  | Pass/Fail/NA | attachments/photoes/Coments
date | Pour Date
checkpoint | CONCRETE TEST Procedure |  | Pass/Fail/NA | attachments/photoes/Coments
checkpoint | APPROVAL FROM ENGINEER
section | Other Arangments
checkpoint | Concrete surface Finish Requirment arranged (Fine Finish) |  | Pass/Fail/NA | attachments/photoes/Coments
checkpoint | Curing Procedure arranged |  | Pass/Fail/NA | attachments/photoes/Coments
[5 empty] | Repeating items | SP1
SP2
SP3
SP4
SP5
SP6
SP7
SP8
SP9
SP10
SP11
SP12
SP13
SP14

## Instaler CheckList ST(steps) (hidden)
checklist | Checkers Checklist
checkpoint | Site Safety / Workers Safety |  | Pass/Fail/NA | attachments/photoes/Coments
checkpoint | Availability of updated shop drawing |  | Pass/Fail/NA | attachments/photoes/Coments
checkpoint | Overall Measurements of construction Eliment |  | Pass/Fail/NA | attachments/photoes/Coments
checkpoint | Embeded Item - Void - Position,Size,Orientation |  | Pass/Fail/NA | attachments/photoes/Coments
checkpoint | Embeded Item - Ferrules - - Position,Size,Orientation - NS / FS |  | Pass/Fail/NA | attachments/photoes/Coments
checkpoint | Embeded Item - Lifters Correct - Position,Size,Orientation |  | Pass/Fail/NA | attachments/photoes/Coments
checkpoint | Embeded Item - Fillet / Chamfer instasllation |  | Pass/Fail/NA | attachments/photoes/Coments
checkpoint | Concrete cover check minimum 30mm |  | Pass/Fail/NA | attachments/photoes/Coments
checkpoint | Panel Thickness check |  | Pass/Fail/NA | attachments/photoes/Coments
dropdown |  | 150mm
dropdown |  | 200mm
checkpoint | Panel length check |  | Pass/Fail/NA | attachments/photoes/Coments
dropdown |  | 15m
dropdown |  | 16m
checkpoint | Formwork Check - Magnets are 100% Secure,All supports,Ties |  | Pass/Fail/NA | attachments/photoes/Coments
checkpoint | Formwork Check - Panel is clean |  | Pass/Fail/NA | attachments/photoes/Coments
checkpoint | Reinforcment (Reo) arrangmnet |  | Pass/Fail/NA | attachments/photoes/Coments
checkpoint | Curing Procedure arranged |  | Pass/Fail/NA | attachments/photoes/Coments
checkpoint | Photo Taken |  | Pass/Fail/NA | attachments/photoes/Coments
Kempsey Sale Yard
checklist | Installers Checklist
section | Job Aproval Documents/Constrction Documents
checkpoint | Complete Material "Bucket List" |  | Pass/Fail/NA | attachments/photoes/Coments
checkpoint | Embeded Item -Lifters -XXXXXX - Position,Size,Orientation - NS / FS |  | Pass/Fail/NA | attachments/photoes/Coments
checkpoint | Embeded Item - Ferrules -M12x50 - Position,Size,Orientation - NS / FS |  | Pass/Fail/NA | attachments/photoes
checkpoint | ID Plate |  |  | attachments/photoes/Coments
text box
section | Pre-Pour Check Approvals
checkpoint | Formwork Check -Panel Dimensions & DOUBLE CHECK |  | Pass/Fail/NA | attachments/photoes/Coments
checkpoint | Apply Debonding agents -bond breaker or wax (1/2/3/ Coats) |  | Pass/Fail/NA | attachments/photoes/Coments
checkpoint | Temporary Fix ID Plate to Formwork |  | Pass/Fail/NA | attachments/photoes/Coments
checkpoint | Use Required Mould,Supports,Ties - Bridge Plank Mould |  | Pass/Fail/NA | attachments/photoes/Coments
checkpoint | Reinforcment Check - Reo as-per Shop Drawing |  | Pass/Fail/NA | attachments/photoes/Coments
checkpoint | Lifters, Ferrules, Tubes Fixed Firm & alligned -Check |  | Pass/Fail/NA | attachments/photoes/Coments
checkpoint | Concrete cover Check - (min cov XXmm) |  | Pass/Fail/NA | attachments/photoes/Coments
section | Quality Assuarance
checkpoint | QA - Final Check of ALL measurerments & Diaganals |  | Pass/Fail/NA | attachments/photoes/Coments
checkpoint | QA - Concrete N40 Panel Mix - Special Adjustments |  | Pass/Fail/NA | attachments/photoes/Coments
checkpoint | QA - Concrete mixdesign ,veriations%, adjustments%,mix time |  | Pass/Fail/NA | attachments/photoes/Coments
checkpoint | QA - All main & other requirment to do Concreting -DOUBLE CHECK |  | Pass/Fail/NA | attachments/photoes/Coments
date | Pour Date
checkpoint | CONCRETE TEST Procedure |  | Pass/Fail/NA | attachments/photoes/Coments
checkpoint | APPROVAL FROM ENGINEER
section | Other Arangments
checkpoint | Concrete surface Finish Requirment arranged (BROOM\SPONGE Finish) |  | Pass/Fail/NA | attachments/photoes/Coments
checkpoint | Curing Procedure arranged |  | Pass/Fail/NA | attachments/photoes/Coments
[5 empty] | Repeating items | STD1-1
STD1-2
STD1-3
STD1-4
STD1-5
STD1-6
STD1-7
STD1-8
STD1-9
STD1-10
STD1-11

## Sheet1 (hidden)
Repeating items | SP1 | STD1-1
| SP2 | STD1-2
| SP3 | STD1-3
| SP4 | STD1-4
| SP5 | STD1-5
| SP6 | STD1-6
| SP7 | STD1-7
| SP8 | STD1-8
| SP9 | STD1-9
| SP10 | STD1-10
| SP11 | STD1-11
SP12
SP13
SP14

## old doc (hidden)
BP-01 | Bridge Plank | values
checklist-sectioned | Precast Components ITP
section | Manufacturing Documents
checkpoint | Shop drawings reviewed and updated. Issued "As For Construction" |  | upload a copy to CONQA?
section | Pre-Pour Checks
checkpoint | Final Inspection - all placed in accordance with approved shop drawings
checkpoint | Upload sufficient number of photos pre pour
section | Concrete Testing
section | Transport
Checkpoint | Ensure loads are glutted correctly and chains are over gluts.
section | Final Inspection |  |  | 6.3 | 0.6 | 0.1 | 0.378 | 0.9072
checkpoint | All approvals, certificates, data warranties, guarantees, manuals, as-built drawings collected. |  |  | 6.3 | 0.6 | 0.1 | 0.378 | 0.9072
|  |  |  | 0.8 | 0.6 | 0.1 | 0.048 | 0.1152
checklist | Checkers Checklist
checkpoint | Overall Measurements | [5 empty] | 0.804 | 1.9296
checkpoint | Void Correct Position
checkpoint | Ferrules - Measurements & Size - NS / FS
checkpoint | Lifters Correct - Position, Size, Orientation
checkpoint | Fillet is Installed
checkpoint | Check Concrete cover around Reo 30mm
checkpoint | Panel Thickness confirmed
dropdown |  | 150mm
checkpoint | Magnets are 100% Secure
checkpoint | Panel is Clean
checkpoint | Photo Taken
checklist | Installers Checklist
checkpoint | Complete Material "Bucket List"
textbox | Eye Anchor - 2.5T | 4
textbox | Ferrules - M20 x 96mm | 10
textbox | ID Plate
checkpoint | Flick-out Panel Dimensions & DOUBLE CHECK
checkpoint | Apply bond breaker or wax 1 2 3
checkpoint | Temporary Fix ID Plate to Formwork
checkpoint | Use Bridge Plank Mould
checkpoint | Install Reo as-per Shop Drawing Plan
checkpoint | Lifters to be Firm & Square against Formwork
checkpoint | Check Concrete cover around reo 30mm
checkpoint | DOUBLE CHECK EVERYTHING
checkpoint | Finish Required - Broom
checkpoint | QA - Final Check of ALL measurerments & Photos
checkpoint | QA - Concrete Mix N40 Panel Mix
checkpoint | QA - Check Concrete mix % before accepting. Allow enough mix time.
checkpoint | CONCRETE TEST TAKEN |  | upload docket?
date | Pour Date
checkpoint | NOT TO BE POURED WITHOUT APPROVAL FROM ENGINEER |  | signoff?