## ITP Summary
Job | 2025-23 - Maclean High School Lift Shaft
checklist-sectioned | Precast Components ITP
section | Job Approval Documents/Construction Documents
checkpoint | Received Construction drawing from Client | Pass/Fail/NA | attachments/photos
checkpoint | Shop drawings repaired, reviewed and updated. Issued "As For Construction" | Pass/Fail/NA | attachments/photos
All approvals, certificates, data warranties, guarantees, manuals, as-built drawings collected.
section | Pre-Pour Check Approvals
checkpoint | Formwork |  | attachments/photos/Sign
checkpoint | Reinforcement(Reo) |  | attachments/photos/Sign
checkpoint | Embedded Items and their placement |  | attachments/photos/Sign
checkpoint | Lift Procedure
checkpoint | Concreting (mix design) |  | attachments/photos/Sign
section | Test on Concrete (requests and approvals)
checkpoint | Request From Client |  | attachments/photos/Sign
checkpoint | Test schedule and Test Results |  | attachments/photos/Sign
section | Transport
Sub section 01 | Transport 01
| Any Lifting, Loading, Transport Instructions from Client | Pass/Fail/NA | attachments/photos/Sign
| Transport Vehicle Approvals | Pass/Fail/NA | attachments/photos/Sign
| Ensure loads are glutted correctly and chains are over gluts. | Pass/Fail/NA | attachments/photos/Sign
Sub section 02 | Transport 02
| Any Lifting, Loading, Transport Instructions from Client | Pass/Fail/NA | attachments/photos/Sign
| Transport Vehicle Approvals | Pass/Fail/NA | attachments/photos/Sign
| Ensure loads are glutted correctly and chains are over gluts. | Pass/Fail/NA | attachments/photos/Sign
Sub section 03 | Transport 03
| Any Lifting, Loading, Transport Instructions from Client | Pass/Fail/NA | attachments/photos/Sign
| Transport Vehicle Approvals | Pass/Fail/NA | attachments/photos/Sign
| Ensure loads are glutted correctly and chains are over gluts. | Pass/Fail/NA | attachments/photos/Sign
section | Other Documentations
checkpoint | Special Instructions |  | attachments/photos/Sign
checkpoint | Other |  | attachments/photos/Sign
section | Installation
checkpoint | All PPE and safety requirements in place. Machinery inspections complete. | Pass/Fail/NA | attachments/photos/Sign
checkpoint | Notification of Inspection - all in accordance with approved shop drawings, correct size and location | Pass/Fail/NA | attachments/photos/Sign
tick box | Set out | Pass/Fail/NA | attachments/photos/Sign
tick box | Core Holes | Pass/Fail/NA | attachments/photos/Sign
tick box | Install dowels | Pass/Fail/NA | attachments/photos/Sign
checkpoint | Installation of precast panels including back propping. Correct location, connections, finish confirmed against shop drawings. | Pass/Fail/NA | attachments/photos/Sign
checkpoint | Grouting and sealing | Pass/Fail/NA | attachments/photos/Sign
checkpoint | Remove back propping when instructed by consulting Engineers. | Pass/Fail/NA | attachments/photos/Sign
section | Final Inspection | Pass/Fail/NA | attachments/photos/Sign
checkpoint | All approvals, certificates, data warranties, guarantees, manuals, as-built drawings collected. | Pass/Fail/NA | attachments/photos/Sign

## LL1
Job | 2025-23 - Maclean High School Lift Shaft
checklist | Checkers Checklist
checkpoint | Site Safety / Workers Safety | attachments/photos/comments | attachments/photos/comments
checkpoint | Availability of current for construction shop drawing | attachments/photos/comments | attachments/photos/comments
checkpoint | Overall Measurements of construction Element | attachments/photos/comments | attachments/photos/comments
tick box | Formwork Check - Magnets are 100% Secure, All supports,Ties,Bracing
tick box | Formwork Check - Flatness, Levelness, Panel is clean
tick box | Formwork Check - Double check the measurement with Diagonal check
tick box | Apply Debonding agents -bond breaker or wax (1/2/3/ Coats)
checkpoint | Reinforcement (Reo) placed, cleaned, tightened | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Embedded Item -Placement, position, alignment | Pass/Fail/NA | attachments/photos/Comments
tick box | Grout Tubes - 8 x ∅=50, L=200
tick box | Jacob HBL - 3
tick box | Lifters - 4 x T41 Face Lifters
checkpoint | Embedded Item - Fillet / Chamfer installation | Pass/Fail/NA | attachments/photos/comments
checkpoint | Concrete cover 30mm | Pass/Fail/NA | attachments/photos/comments
checkpoint | Panel Thickness check,allignment check - 175mm | Pass/Fail/NA | attachments/photos/comments
checkpoint | Formwork Check - Magnets are 100% Secure, All supports, Ties, Bracing | Pass/Fail/NA | attachments/photos/comments
checkpoint | Formwork Check - Flatness, Levelness, Panel is clean | Pass/Fail/NA | attachments/photos/comments
checkpoint | Formwork Check - Double check the measurement with Diagonal check | Pass/Fail/NA | attachments/photos/comments
checkpoint | Reinforcement (Reo) placed, cleaned, tightened | Pass/Fail/NA | attachments/photos/comments
checkpoint | Curing Procedure arranged | Pass/Fail/NA | attachments/photos/comments
checkpoint | Photo Taken | Pass/Fail/NA | attachments/photos/comments
checklist | Installers Checklist |  |  | Repeating items
section | Job Approval Documents/Construction Documents
checkpoint | Complete Material "Bucket List" | Pass/Fail/NA | attachments/photos/comments
checkpoint | Embedded Item -Placement, position, alignment | Pass/Fail/NA | attachments/photos/Comments
tick box | Grout Tubes - 8 x ∅=50, L=200
tick box | Jacob HBL - 3
tick box | Lifters - 4 x T41 Face Lifters
checkpoint | ID Plate |  | attachments/photos/comments
section | Pre-Pour Check Approvals
checkpoint | Formwork Check -Panel Dimensions & DOUBLE CHECK | Pass/Fail/NA | attachments/photos/comments
checkpoint | Apply Debonding agents -bond breaker or wax (1/2/3/ Coats) | Pass/Fail/NA | attachments/photos/comments
checkpoint | Temporary Fix ID Plate to Formwork | Pass/Fail/NA | attachments/photos/comments
checkpoint | Use Required Mould, Supports, Ties - Bridge Plank Mould | Pass/Fail/NA | attachments/photos/comments
checkpoint | Reinforcement Check - Reo as-per Shop Drawing | Pass/Fail/NA | attachments/photos/comments
checkpoint | Lifters, Ferrules, Tubes Fixed Firm & aligned -Check | Pass/Fail/NA | attachments/photos/comments
checkpoint | Concrete cover Check - 30mm | Pass/Fail/NA | attachments/photos/comments
section | Quality Assurance
checkpoint | QA - Final Check of ALL measurements & Diagonals | Pass/Fail/NA | attachments/photos/comments
checkpoint | QA - Concrete N40 Panel Mix - Special Adjustments | Pass/Fail/NA | attachments/photos/comments
checkpoint | QA - Concrete mix design ,variations%, adjustments%, mix time | Pass/Fail/NA | attachments/photos/comments
checkpoint | QA - All main & other requirement to do Concreting -DOUBLE CHECK | Pass/Fail/NA | attachments/photos/comments
date | Pour Date
checkpoint | CONCRETE TEST Procedure | Pass/Fail/NA | attachments/photos/comments
checkpoint | APPROVAL FROM ENGINEER
section | Other Arrangements
checkpoint | Concrete surface Finish Requirement arranged (Fine Finish) | Pass/Fail/NA | attachments/photos/comments
checkpoint | Curing Procedure arranged | Pass/Fail/NA | attachments/photos/comments

## LP1
Job | 2025-23 - Maclean High School Lift Shaft
checklist | Checkers Checklist
checkpoint | Site Safety / Workers Safety | attachments/photos/comments | attachments/photos/comments
checkpoint | Availability of current for construction shop drawing | attachments/photos/comments | attachments/photos/comments
checkpoint | Overall Measurements of construction Element | attachments/photos/comments | attachments/photos/comments
tick box | Formwork Check - Magnets are 100% Secure, All supports,Ties,Bracing
tick box | Formwork Check - Flatness, Levelness, Panel is clean
tick box | Formwork Check - Double check the measurement with Diagonal check
tick box | Apply Debonding agents -bond breaker or wax (1/2/3/ Coats)
checkpoint | Void for lift door openings - Dimensional and location check | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Reinforcement (Reo) placed, cleaned, tightened | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Embedded Item -Placement, position, alignment | Pass/Fail/NA | attachments/photos/Comments
tick box | Grout Tubes - 2 x ∅=50, L=1200
tick box | Lifters - 6 x 9T Edge Lifters
tick box | Brace Ferrules - 2 x M20x96mm
tick box | Ferrules - 8 x M20 - FS - 75-96mm
tick box | Reidbar Insert - 71 x RBA16 - NS
checkpoint | Embedded Item - 4 x Strongback inserts installed as per drawings | Pass/Fail/NA | attachments/photos/comments
checkpoint | Embedded Item - Fillet / Chamfer installation | Pass/Fail/NA | attachments/photos/comments
checkpoint | Concrete cover 30mm | Pass/Fail/NA | attachments/photos/comments
checkpoint | Panel Thickness check,allignment check - 175mm | Pass/Fail/NA | attachments/photos/comments
checkpoint | Formwork Check - Magnets are 100% Secure, All supports, Ties, Bracing | Pass/Fail/NA | attachments/photos/comments
checkpoint | Formwork Check - Flatness, Levelness, Panel is clean | Pass/Fail/NA | attachments/photos/comments
checkpoint | Formwork Check - Double check the measurement with Diagonal check | Pass/Fail/NA | attachments/photos/comments
checkpoint | Reinforcement (Reo) placed, cleaned, tightened | Pass/Fail/NA | attachments/photos/comments
checkpoint | Curing Procedure arranged | Pass/Fail/NA | attachments/photos/comments
checkpoint | Photo Taken | Pass/Fail/NA | attachments/photos/comments
checklist | Installers Checklist |  |  | Repeating items
section | Job Approval Documents/Construction Documents
checkpoint | Complete Material "Bucket List" | Pass/Fail/NA | attachments/photos/comments
checkpoint | Embedded Item -Placement, position, alignment | Pass/Fail/NA | attachments/photos/Comments
tick box | Grout Tubes - 2 x ∅=50, L=1200
tick box | Lifters - 6 x 9T Edge Lifters
tick box | Brace Ferrules - 2 x M20x96mm
tick box | Ferrules - 8 x M20 - FS - 75-96mm
tick box | Reidbar Insert - 71 x RBA16 - NS
checkpoint | ID Plate |  | attachments/photos/comments
section | Pre-Pour Check Approvals
checkpoint | Formwork Check -Panel Dimensions & DOUBLE CHECK | Pass/Fail/NA | attachments/photos/comments
checkpoint | Apply Debonding agents -bond breaker or wax (1/2/3/ Coats) | Pass/Fail/NA | attachments/photos/comments
checkpoint | Temporary Fix ID Plate to Formwork | Pass/Fail/NA | attachments/photos/comments
checkpoint | Use Required Mould, Supports, Ties - Bridge Plank Mould | Pass/Fail/NA | attachments/photos/comments
checkpoint | Reinforcement Check - Reo as-per Shop Drawing | Pass/Fail/NA | attachments/photos/comments
checkpoint | Lifters, Ferrules, Tubes Fixed Firm & aligned -Check | Pass/Fail/NA | attachments/photos/comments
checkpoint | Concrete cover Check - 30mm | Pass/Fail/NA | attachments/photos/comments
section | Quality Assurance
checkpoint | QA - Final Check of ALL measurements & Diagonals | Pass/Fail/NA | attachments/photos/comments
checkpoint | QA - Concrete N40 Panel Mix - Special Adjustments | Pass/Fail/NA | attachments/photos/comments
checkpoint | QA - Concrete mix design ,variations%, adjustments%, mix time | Pass/Fail/NA | attachments/photos/comments
checkpoint | QA - All main & other requirement to do Concreting -DOUBLE CHECK | Pass/Fail/NA | attachments/photos/comments
date | Pour Date
checkpoint | CONCRETE TEST Procedure | Pass/Fail/NA | attachments/photos/comments
checkpoint | APPROVAL FROM ENGINEER
section | Other Arrangements
checkpoint | Concrete surface Finish Requirement arranged (Fine Finish) | Pass/Fail/NA | attachments/photos/comments
checkpoint | Curing Procedure arranged | Pass/Fail/NA | attachments/photos/comments

## LP2
Job | 2025-23 - Maclean High School Lift Shaft
checklist | Checkers Checklist
checkpoint | Site Safety / Workers Safety | attachments/photos/comments | attachments/photos/comments
checkpoint | Availability of current for construction shop drawing | attachments/photos/comments | attachments/photos/comments
checkpoint | Overall Measurements of construction Element | attachments/photos/comments | attachments/photos/comments
tick box | Formwork Check - Magnets are 100% Secure, All supports,Ties,Bracing
tick box | Formwork Check - Flatness, Levelness, Panel is clean
tick box | Formwork Check - Double check the measurement with Diagonal check
tick box | Apply Debonding agents -bond breaker or wax (1/2/3/ Coats)
checkpoint | Void for lift door openings - Dimensional and location check | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Reinforcement (Reo) placed, cleaned, tightened | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Embedded Item -Placement, position, alignment | Pass/Fail/NA | attachments/photos/Comments
tick box | Grout Tubes - 2 x ∅=50, L=1200
tick box | Lifters - 6 x 9T Edge Lifters
tick box | Brace Ferrules - 2 x M20x96mm
tick box | Ferrules - 8 x M20 - FS - 75-96mm
checkpoint | Embedded Item - Fillet / Chamfer installation | Pass/Fail/NA | attachments/photos/comments
checkpoint | Concrete cover 30mm | Pass/Fail/NA | attachments/photos/comments
checkpoint | Panel Thickness check,allignment check - 175mm | Pass/Fail/NA | attachments/photos/comments
checkpoint | Formwork Check - Magnets are 100% Secure, All supports, Ties, Bracing | Pass/Fail/NA | attachments/photos/comments
checkpoint | Formwork Check - Flatness, Levelness, Panel is clean | Pass/Fail/NA | attachments/photos/comments
checkpoint | Formwork Check - Double check the measurement with Diagonal check | Pass/Fail/NA | attachments/photos/comments
checkpoint | Reinforcement (Reo) placed, cleaned, tightened | Pass/Fail/NA | attachments/photos/comments
checkpoint | Curing Procedure arranged | Pass/Fail/NA | attachments/photos/comments
checkpoint | Photo Taken | Pass/Fail/NA | attachments/photos/comments
checklist | Installers Checklist |  |  | Repeating items
section | Job Approval Documents/Construction Documents
checkpoint | Complete Material "Bucket List" | Pass/Fail/NA | attachments/photos/comments
checkpoint | Embedded Item -Placement, position, alignment | Pass/Fail/NA | attachments/photos/Comments
tick box | Grout Tubes - 2 x ∅=50, L=1200
tick box | Lifters - 6 x 9T Edge Lifters
tick box | Brace Ferrules - 2 x M20x96mm
tick box | Ferrules - 8 x M20 - FS - 75-96mm
checkpoint | ID Plate |  | attachments/photos/comments
section | Pre-Pour Check Approvals
checkpoint | Formwork Check -Panel Dimensions & DOUBLE CHECK | Pass/Fail/NA | attachments/photos/comments
checkpoint | Apply Debonding agents -bond breaker or wax (1/2/3/ Coats) | Pass/Fail/NA | attachments/photos/comments
checkpoint | Temporary Fix ID Plate to Formwork | Pass/Fail/NA | attachments/photos/comments
checkpoint | Use Required Mould, Supports, Ties - Bridge Plank Mould | Pass/Fail/NA | attachments/photos/comments
checkpoint | Reinforcement Check - Reo as-per Shop Drawing | Pass/Fail/NA | attachments/photos/comments
checkpoint | Lifters, Ferrules, Tubes Fixed Firm & aligned -Check | Pass/Fail/NA | attachments/photos/comments
checkpoint | Concrete cover Check - 30mm | Pass/Fail/NA | attachments/photos/comments
section | Quality Assurance
checkpoint | QA - Final Check of ALL measurements & Diagonals | Pass/Fail/NA | attachments/photos/comments
checkpoint | QA - Concrete N40 Panel Mix - Special Adjustments | Pass/Fail/NA | attachments/photos/comments
checkpoint | QA - Concrete mix design ,variations%, adjustments%, mix time | Pass/Fail/NA | attachments/photos/comments
checkpoint | QA - All main & other requirement to do Concreting -DOUBLE CHECK | Pass/Fail/NA | attachments/photos/comments
date | Pour Date
checkpoint | CONCRETE TEST Procedure | Pass/Fail/NA | attachments/photos/comments
checkpoint | APPROVAL FROM ENGINEER
section | Other Arrangements
checkpoint | Concrete surface Finish Requirement arranged (Fine Finish) | Pass/Fail/NA | attachments/photos/comments
checkpoint | Curing Procedure arranged | Pass/Fail/NA | attachments/photos/comments

## LP3
Job | 2025-23 - Maclean High School Lift Shaft
checklist | Checkers Checklist
checkpoint | Site Safety / Workers Safety | attachments/photos/comments | attachments/photos/comments
checkpoint | Availability of current for construction shop drawing | attachments/photos/comments | attachments/photos/comments
checkpoint | Overall Measurements of construction Element | attachments/photos/comments | attachments/photos/comments
tick box | Formwork Check - Magnets are 100% Secure, All supports,Ties,Bracing
tick box | Formwork Check - Flatness, Levelness, Panel is clean
tick box | Formwork Check - Double check the measurement with Diagonal check
tick box | Apply Debonding agents -bond breaker or wax (1/2/3/ Coats)
checkpoint | Void for lift door openings - Dimensional and location check | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Reinforcement (Reo) placed, cleaned, tightened | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Embedded Item -Placement, position, alignment | Pass/Fail/NA | attachments/photos/Comments
tick box | Grout Tubes - 2 x ∅=50, L=1200
tick box | Lifters - 6 x 9T Edge Lifters
tick box | Brace Ferrules - 2 x M20x96mm
tick box | Ferrules - 8 x M20 - FS - 75-96mm
checkpoint | Embedded Item - Fillet / Chamfer installation | Pass/Fail/NA | attachments/photos/comments
checkpoint | Concrete cover 30mm | Pass/Fail/NA | attachments/photos/comments
checkpoint | Panel Thickness check,allignment check - 175mm | Pass/Fail/NA | attachments/photos/comments
checkpoint | Formwork Check - Magnets are 100% Secure, All supports, Ties, Bracing | Pass/Fail/NA | attachments/photos/comments
checkpoint | Formwork Check - Flatness, Levelness, Panel is clean | Pass/Fail/NA | attachments/photos/comments
checkpoint | Formwork Check - Double check the measurement with Diagonal check | Pass/Fail/NA | attachments/photos/comments
checkpoint | Reinforcement (Reo) placed, cleaned, tightened | Pass/Fail/NA | attachments/photos/comments
checkpoint | Curing Procedure arranged | Pass/Fail/NA | attachments/photos/comments
checkpoint | Photo Taken | Pass/Fail/NA | attachments/photos/comments
checklist | Installers Checklist |  |  | Repeating items
section | Job Approval Documents/Construction Documents
checkpoint | Complete Material "Bucket List" | Pass/Fail/NA | attachments/photos/comments
checkpoint | Embedded Item -Placement, position, alignment | Pass/Fail/NA | attachments/photos/Comments
tick box | Grout Tubes - 2 x ∅=50, L=1200
tick box | Lifters - 6 x 9T Edge Lifters
tick box | Brace Ferrules - 2 x M20x96mm
tick box | Ferrules - 8 x M20 - FS - 75-96mm
checkpoint | ID Plate |  | attachments/photos/comments
section | Pre-Pour Check Approvals
checkpoint | Formwork Check -Panel Dimensions & DOUBLE CHECK | Pass/Fail/NA | attachments/photos/comments
checkpoint | Apply Debonding agents -bond breaker or wax (1/2/3/ Coats) | Pass/Fail/NA | attachments/photos/comments
checkpoint | Temporary Fix ID Plate to Formwork | Pass/Fail/NA | attachments/photos/comments
checkpoint | Use Required Mould, Supports, Ties - Bridge Plank Mould | Pass/Fail/NA | attachments/photos/comments
checkpoint | Reinforcement Check - Reo as-per Shop Drawing | Pass/Fail/NA | attachments/photos/comments
checkpoint | Lifters, Ferrules, Tubes Fixed Firm & aligned -Check | Pass/Fail/NA | attachments/photos/comments
checkpoint | Concrete cover Check - 30mm | Pass/Fail/NA | attachments/photos/comments
section | Quality Assurance
checkpoint | QA - Final Check of ALL measurements & Diagonals | Pass/Fail/NA | attachments/photos/comments
checkpoint | QA - Concrete N40 Panel Mix - Special Adjustments | Pass/Fail/NA | attachments/photos/comments
checkpoint | QA - Concrete mix design ,variations%, adjustments%, mix time | Pass/Fail/NA | attachments/photos/comments
checkpoint | QA - All main & other requirement to do Concreting -DOUBLE CHECK | Pass/Fail/NA | attachments/photos/comments
date | Pour Date
checkpoint | CONCRETE TEST Procedure | Pass/Fail/NA | attachments/photos/comments
checkpoint | APPROVAL FROM ENGINEER
section | Other Arrangements
checkpoint | Concrete surface Finish Requirement arranged (Fine Finish) | Pass/Fail/NA | attachments/photos/comments
checkpoint | Curing Procedure arranged | Pass/Fail/NA | attachments/photos/comments

## LP4
Job | 2025-23 - Maclean High School Lift Shaft
checklist | Checkers Checklist
checkpoint | Site Safety / Workers Safety | attachments/photos/comments | attachments/photos/comments
checkpoint | Availability of current for construction shop drawing | attachments/photos/comments | attachments/photos/comments
checkpoint | Overall Measurements of construction Element | attachments/photos/comments | attachments/photos/comments
tick box | Formwork Check - Magnets are 100% Secure, All supports,Ties,Bracing
tick box | Formwork Check - Flatness, Levelness, Panel is clean
tick box | Formwork Check - Double check the measurement with Diagonal check
tick box | Apply Debonding agents -bond breaker or wax (1/2/3/ Coats)
checkpoint | Void for lift door openings - Dimensional and location check | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Reinforcement (Reo) placed, cleaned, tightened | Pass/Fail/NA | attachments/photos/Comments
checkpoint | Embedded Item -Placement, position, alignment | Pass/Fail/NA | attachments/photos/Comments
tick box | Grout Tubes - 2 x ∅=50, L=1200
tick box | Lifters - 6 x 9T Edge Lifters
tick box | Brace Ferrules - 2 x M20x96mm
tick box | Ferrules - 8 x M20 - FS - 75-96mm
tick box | Reidbar Insert - 22 x RBA16 - NS
checkpoint | Embedded Item - Fillet / Chamfer installation | Pass/Fail/NA | attachments/photos/comments
checkpoint | Concrete cover 30mm | Pass/Fail/NA | attachments/photos/comments
checkpoint | Panel Thickness check,allignment check - 175mm | Pass/Fail/NA | attachments/photos/comments
checkpoint | Formwork Check - Magnets are 100% Secure, All supports, Ties, Bracing | Pass/Fail/NA | attachments/photos/comments
checkpoint | Formwork Check - Flatness, Levelness, Panel is clean | Pass/Fail/NA | attachments/photos/comments
checkpoint | Formwork Check - Double check the measurement with Diagonal check | Pass/Fail/NA | attachments/photos/comments
checkpoint | Reinforcement (Reo) placed, cleaned, tightened | Pass/Fail/NA | attachments/photos/comments
checkpoint | Curing Procedure arranged | Pass/Fail/NA | attachments/photos/comments
checkpoint | Photo Taken | Pass/Fail/NA | attachments/photos/comments
checklist | Installers Checklist |  |  | Repeating items
section | Job Approval Documents/Construction Documents
checkpoint | Complete Material "Bucket List" | Pass/Fail/NA | attachments/photos/comments
checkpoint | Embedded Item -Placement, position, alignment | Pass/Fail/NA | attachments/photos/Comments
tick box | Grout Tubes - 2 x ∅=50, L=1200
tick box | Lifters - 6 x 9T Edge Lifters
tick box | Brace Ferrules - 2 x M20x96mm
tick box | Ferrules - 8 x M20 - FS - 75-96mm
tick box | Reidbar Insert - 22 x RBA16 - NS
checkpoint | ID Plate |  | attachments/photos/comments
section | Pre-Pour Check Approvals
checkpoint | Formwork Check -Panel Dimensions & DOUBLE CHECK | Pass/Fail/NA | attachments/photos/comments
checkpoint | Apply Debonding agents -bond breaker or wax (1/2/3/ Coats) | Pass/Fail/NA | attachments/photos/comments
checkpoint | Temporary Fix ID Plate to Formwork | Pass/Fail/NA | attachments/photos/comments
checkpoint | Use Required Mould, Supports, Ties - Bridge Plank Mould | Pass/Fail/NA | attachments/photos/comments
checkpoint | Reinforcement Check - Reo as-per Shop Drawing | Pass/Fail/NA | attachments/photos/comments
checkpoint | Lifters, Ferrules, Tubes Fixed Firm & aligned -Check | Pass/Fail/NA | attachments/photos/comments
checkpoint | Concrete cover Check - 30mm | Pass/Fail/NA | attachments/photos/comments
section | Quality Assurance
checkpoint | QA - Final Check of ALL measurements & Diagonals | Pass/Fail/NA | attachments/photos/comments
checkpoint | QA - Concrete N40 Panel Mix - Special Adjustments | Pass/Fail/NA | attachments/photos/comments
checkpoint | QA - Concrete mix design ,variations%, adjustments%, mix time | Pass/Fail/NA | attachments/photos/comments
checkpoint | QA - All main & other requirement to do Concreting -DOUBLE CHECK | Pass/Fail/NA | attachments/photos/comments
date | Pour Date
checkpoint | CONCRETE TEST Procedure | Pass/Fail/NA | attachments/photos/comments
checkpoint | APPROVAL FROM ENGINEER
section | Other Arrangements
checkpoint | Concrete surface Finish Requirement arranged (Fine Finish) | Pass/Fail/NA | attachments/photos/comments
checkpoint | Curing Procedure arranged | Pass/Fail/NA | attachments/photos/comments

## Sheet1 (hidden)
Repeating items | SP1 | STD1-1
| SP2 | STD1-2
| SP3 | STD1-3
| SP4 | STD1-4
| SP5 | STD1-5
| SP6 | STD1-6
| SP7 | STD1-7
| SP8 | STD1-8
| SP9 | STD1-9
| SP10 | STD1-10
| SP11 | STD1-11
SP12
SP13
SP14

## old doc (hidden)
BP-01 | Bridge Plank | values
checklist-sectioned | Precast Components ITP
section | Manufacturing Documents
checkpoint | Shop drawings reviewed and updated. Issued "As For Construction" |  | upload a copy to CONQA?
section | Pre-Pour Checks
checkpoint | Final Inspection - all placed in accordance with approved shop drawings
checkpoint | Upload sufficient number of photos pre pour
section | Concrete Testing
section | Transport
Checkpoint | Ensure loads are glutted correctly and chains are over gluts.
section | Final Inspection |  |  | 6.3 | 0.6 | 0.1 | 0.378 | 0.9072
checkpoint | All approvals, certificates, data warranties, guarantees, manuals, as-built drawings collected. |  |  | 6.3 | 0.6 | 0.1 | 0.378 | 0.9072
|  |  |  | 0.8 | 0.6 | 0.1 | 0.048 | 0.1152
checklist | Checkers Checklist
checkpoint | Overall Measurements | [5 empty] | 0.804 | 1.9296
checkpoint | Void Correct Position
checkpoint | Ferrules - Measurements & Size - NS / FS
checkpoint | Lifters Correct - Position, Size, Orientation
checkpoint | Fillet is Installed
checkpoint | Check Concrete cover around Reo 30mm
checkpoint | Panel Thickness confirmed
dropdown |  | 150mm
checkpoint | Magnets are 100% Secure
checkpoint | Panel is Clean
checkpoint | Photo Taken
checklist | Installers Checklist
checkpoint | Complete Material "Bucket List"
textbox | Eye Anchor - 2.5T | 4
textbox | Ferrules - M20 x 96mm | 10
textbox | ID Plate
checkpoint | Flick-out Panel Dimensions & DOUBLE CHECK
checkpoint | Apply bond breaker or wax 1 2 3
checkpoint | Temporary Fix ID Plate to Formwork
checkpoint | Use Bridge Plank Mould
checkpoint | Install Reo as-per Shop Drawing Plan
checkpoint | Lifters to be Firm & Square against Formwork
checkpoint | Check Concrete cover around reo 30mm
checkpoint | DOUBLE CHECK EVERYTHING
checkpoint | Finish Required - Broom
checkpoint | QA - Final Check of ALL measurerments & Photos
checkpoint | QA - Concrete Mix N40 Panel Mix
checkpoint | QA - Check Concrete mix % before accepting. Allow enough mix time.
checkpoint | CONCRETE TEST TAKEN |  | upload docket?
date | Pour Date
checkpoint | NOT TO BE POURED WITHOUT APPROVAL FROM ENGINEER |  | signoff?