## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource Id
checklist | Precast Components ITP
section | Job Approval Documents/Construction Documents
checkpoint | Received Construction drawing from Client
checkpoint | Shop drawings repaired, reviewed and updated. Issued "As For Construction"
label | All approvals, certificates, data warranties, guarantees, manuals, as-built drawings collected.
section | Pre-Pour Check Approvals
checkpoint-no-status | Formwork
checkpoint-no-status | Reinforcement(Reo)
checkpoint-no-status | Embedded Items and their placement
checkpoint-no-status | Lift Procedure
checkpoint-no-status | Concreting (mix design)
section | Test on Concrete (requests and approvals)
checkpoint-no-status | Request From Client
checkpoint-no-status | Test schedule and Test Results
section | Transport 01
checkpoint | Any Lifting, Loading, Transport Instructions from Client
checkpoint | Transport Vehicle Approvals
checkpoint | Ensure loads are glutted correctly and chains are over gluts.
section | Transport 02
checkpoint | Any Lifting, Loading, Transport Instructions from Client
checkpoint | Transport Vehicle Approvals
checkpoint | Ensure loads are glutted correctly and chains are over gluts.
section | Transport 03
checkpoint | Any Lifting, Loading, Transport Instructions from Client
checkpoint | Transport Vehicle Approvals
checkpoint | Ensure loads are glutted correctly and chains are over gluts.
section | Other Documentations
checkpoint-no-status | Special Instructions
checkpoint-no-status | Other
section | Installation
checkpoint | All PPE and safety requirements in place. Machinery inspections complete.
checkpoint | Notification of Inspection - all in accordance with approved shop drawings, correct size and location
checkpoint | Set out
checkpoint | Core Holes
checkpoint | Install dowels
checkpoint | Installation of precast panels including back propping. Correct location, connections, finish confirmed against shop drawings.
checkpoint | Grouting and sealing
checkpoint | Remove back propping when instructed by consulting Engineers.
section | Final Inspection
checkpoint | All approvals, certificates, data warranties, guarantees, manuals, as-built drawings collected.
checklist | Checkers Checklist (LL1)
section | Details
checkpoint-no-status | Site Safety / Workers Safety
checkpoint-no-status | Availability of current for construction shop drawing
checkpoint-no-status | Overall Measurements of construction Element
bool | Formwork Check - Magnets are 100% Secure, All supports,Ties,Bracing
bool | Formwork Check - Flatness, Levelness, Panel is clean
bool | Formwork Check - Double check the measurement with Diagonal check
bool | Apply Debonding agents -bond breaker or wax (1/2/3/ Coats)
checkpoint | Reinforcement (Reo) placed, cleaned, tightened
checkpoint | Embedded Item -Placement, position, alignment
bool | Grout Tubes - 8 x ∅=50, L=200
bool | Jacob HBL - 3
bool | Lifters - 4 x T41 Face Lifters
checkpoint | Embedded Item - Fillet / Chamfer installation
checkpoint | Concrete cover 30mm
checkpoint | Panel Thickness check,allignment check - 175mm
checkpoint | Formwork Check - Magnets are 100% Secure, All supports, Ties, Bracing
checkpoint | Formwork Check - Flatness, Levelness, Panel is clean
checkpoint | Formwork Check - Double check the measurement with Diagonal check
checkpoint | Reinforcement (Reo) placed, cleaned, tightened
checkpoint | Curing Procedure arranged
checkpoint | Photo Taken
checklist | Installers Checklist (LL1)
section | Job Approval Documents/Construction Documents
checkpoint | Complete Material "Bucket List"
checkpoint | Embedded Item -Placement, position, alignment
bool | Grout Tubes - 8 x ∅=50, L=200
bool | Jacob HBL - 3
bool | Lifters - 4 x T41 Face Lifters
checkpoint-no-status | ID Plate
textbox | ID:
section | Pre-Pour Check Approvals
checkpoint | Formwork Check -Panel Dimensions & DOUBLE CHECK
checkpoint | Apply Debonding agents -bond breaker or wax (1/2/3/ Coats)
checkpoint | Temporary Fix ID Plate to Formwork
checkpoint | Use Required Mould, Supports, Ties - Bridge Plank Mould
checkpoint | Reinforcement Check - Reo as-per Shop Drawing
checkpoint | Lifters, Ferrules, Tubes Fixed Firm & aligned -Check
checkpoint | Concrete cover Check - 30mm
section | Quality Assurance
checkpoint | QA - Final Check of ALL measurements & Diagonals
checkpoint | QA - Concrete N40 Panel Mix - Special Adjustments
checkpoint | QA - Concrete mix design ,variations%, adjustments%, mix time
checkpoint | QA - All main & other requirement to do Concreting -DOUBLE CHECK
date | Pour Date
checkpoint | CONCRETE TEST Procedure
checkpoint | APPROVAL FROM ENGINEER
section | Other Arrangements
checkpoint | Concrete surface Finish Requirement arranged (Fine Finish)
checkpoint | Curing Procedure arranged
checklist | Checkers Checklist (LP1)
section | Details
checkpoint-no-status | Site Safety / Workers Safety
checkpoint-no-status | Availability of current for construction shop drawing
checkpoint-no-status | Overall Measurements of construction Element
bool | Formwork Check - Magnets are 100% Secure, All supports,Ties,Bracing
bool | Formwork Check - Flatness, Levelness, Panel is clean
bool | Formwork Check - Double check the measurement with Diagonal check
bool | Apply Debonding agents -bond breaker or wax (1/2/3/ Coats)
checkpoint | Void for lift door openings - Dimensional and location check
checkpoint | Reinforcement (Reo) placed, cleaned, tightened
checkpoint | Embedded Item -Placement, position, alignment
bool | Grout Tubes - 2 x ∅=50, L=1200
bool | Lifters - 6 x 9T Edge Lifters
bool | Brace Ferrules - 2 x M20x96mm
bool | Ferrules - 8 x M20 - FS - 75-96mm
bool | Reidbar Insert - 71 x RBA16 - NS
checkpoint | Embedded Item - 4 x Strongback inserts installed as per drawings
checkpoint | Embedded Item - Fillet / Chamfer installation
checkpoint | Concrete cover 30mm
checkpoint | Panel Thickness check,allignment check - 175mm
checkpoint | Formwork Check - Magnets are 100% Secure, All supports, Ties, Bracing
checkpoint | Formwork Check - Flatness, Levelness, Panel is clean
checkpoint | Formwork Check - Double check the measurement with Diagonal check
checkpoint | Reinforcement (Reo) placed, cleaned, tightened
checkpoint | Curing Procedure arranged
checkpoint | Photo Taken
checklist | Installers Checklist (LP1)
section | Job Approval Documents/Construction Documents
checkpoint | Complete Material "Bucket List"
checkpoint | Embedded Item -Placement, position, alignment
bool | Grout Tubes - 2 x ∅=50, L=1200
bool | Lifters - 6 x 9T Edge Lifters
bool | Brace Ferrules - 2 x M20x96mm
bool | Ferrules - 8 x M20 - FS - 75-96mm
bool | Reidbar Insert - 71 x RBA16 - NS
checkpoint-no-status | ID Plate
textbox | ID:
section | Pre-Pour Check Approvals
checkpoint | Formwork Check -Panel Dimensions & DOUBLE CHECK
checkpoint | Apply Debonding agents -bond breaker or wax (1/2/3/ Coats)
checkpoint | Temporary Fix ID Plate to Formwork
checkpoint | Use Required Mould, Supports, Ties - Bridge Plank Mould
checkpoint | Reinforcement Check - Reo as-per Shop Drawing
checkpoint | Lifters, Ferrules, Tubes Fixed Firm & aligned -Check
checkpoint | Concrete cover Check - 30mm
section | Quality Assurance
checkpoint | QA - Final Check of ALL measurements & Diagonals
checkpoint | QA - Concrete N40 Panel Mix - Special Adjustments
checkpoint | QA - Concrete mix design ,variations%, adjustments%, mix time
checkpoint | QA - All main & other requirement to do Concreting -DOUBLE CHECK
date | Pour Date
checkpoint | CONCRETE TEST Procedure
checkpoint-no-status | APPROVAL FROM ENGINEER
section | Other Arrangements
checkpoint | Concrete surface Finish Requirement arranged (Fine Finish)
checkpoint | Curing Procedure arranged
checklist | Checkers Checklist (LP2)
section | Details
checkpoint-no-status | Site Safety / Workers Safety
checkpoint-no-status | Availability of current for construction shop drawing
checkpoint-no-status | Overall Measurements of construction Element
bool | Formwork Check - Magnets are 100% Secure, All supports,Ties,Bracing
bool | Formwork Check - Flatness, Levelness, Panel is clean
bool | Formwork Check - Double check the measurement with Diagonal check
bool | Apply Debonding agents -bond breaker or wax (1/2/3/ Coats)
checkpoint | Void for lift door openings - Dimensional and location check
checkpoint | Reinforcement (Reo) placed, cleaned, tightened
checkpoint | Embedded Item -Placement, position, alignment
bool | Grout Tubes - 2 x ∅=50, L=1200
bool | Lifters - 6 x 9T Edge Lifters
bool | Brace Ferrules - 2 x M20x96mm
bool | Ferrules - 8 x M20 - FS - 75-96mm
checkpoint | Embedded Item - Fillet / Chamfer installation
checkpoint | Concrete cover 30mm
checkpoint | Panel Thickness check,allignment check - 175mm
checkpoint | Formwork Check - Magnets are 100% Secure, All supports, Ties, Bracing
checkpoint | Formwork Check - Flatness, Levelness, Panel is clean
checkpoint | Formwork Check - Double check the measurement with Diagonal check
checkpoint | Reinforcement (Reo) placed, cleaned, tightened
checkpoint | Curing Procedure arranged
checkpoint | Photo Taken
checklist | Installers Checklist (LP2)
section | Job Approval Documents/Construction Documents
checkpoint | Complete Material "Bucket List"
checkpoint | Embedded Item -Placement, position, alignment
bool | Grout Tubes - 2 x ∅=50, L=1200
bool | Lifters - 6 x 9T Edge Lifters
bool | Brace Ferrules - 2 x M20x96mm
bool | Ferrules - 8 x M20 - FS - 75-96mm
checkpoint-no-status | ID Plate
textbox | ID:
section | Pre-Pour Check Approvals
checkpoint | Formwork Check -Panel Dimensions & DOUBLE CHECK
checkpoint | Apply Debonding agents -bond breaker or wax (1/2/3/ Coats)
checkpoint | Temporary Fix ID Plate to Formwork
checkpoint | Use Required Mould, Supports, Ties - Bridge Plank Mould
checkpoint | Reinforcement Check - Reo as-per Shop Drawing
checkpoint | Lifters, Ferrules, Tubes Fixed Firm & aligned -Check
checkpoint | Concrete cover Check - 30mm
section | Quality Assurance
checkpoint | QA - Final Check of ALL measurements & Diagonals
checkpoint | QA - Concrete N40 Panel Mix - Special Adjustments
checkpoint | QA - Concrete mix design ,variations%, adjustments%, mix time
checkpoint | QA - All main & other requirement to do Concreting -DOUBLE CHECK
date | Pour Date
checkpoint | CONCRETE TEST Procedure
checkpoint-no-status | APPROVAL FROM ENGINEER
section | Other Arrangements
checkpoint | Concrete surface Finish Requirement arranged (Fine Finish)
checkpoint | Curing Procedure arranged
checklist | Checkers Checklist (LP3)
section | Details
checkpoint-no-status | Site Safety / Workers Safety
checkpoint-no-status | Availability of current for construction shop drawing
checkpoint-no-status | Overall Measurements of construction Element
bool | Formwork Check - Magnets are 100% Secure, All supports,Ties,Bracing
bool | Formwork Check - Flatness, Levelness, Panel is clean
bool | Formwork Check - Double check the measurement with Diagonal check
bool | Apply Debonding agents -bond breaker or wax (1/2/3/ Coats)
checkpoint | Void for lift door openings - Dimensional and location check
checkpoint | Reinforcement (Reo) placed, cleaned, tightened
checkpoint | Embedded Item -Placement, position, alignment
bool | Grout Tubes - 2 x ∅=50, L=1200
bool | Lifters - 6 x 9T Edge Lifters
bool | Brace Ferrules - 2 x M20x96mm
bool | Ferrules - 8 x M20 - FS - 75-96mm
checkpoint | Embedded Item - Fillet / Chamfer installation
checkpoint | Concrete cover 30mm
checkpoint | Panel Thickness check,allignment check - 175mm
checkpoint | Formwork Check - Magnets are 100% Secure, All supports, Ties, Bracing
checkpoint | Formwork Check - Flatness, Levelness, Panel is clean
checkpoint | Formwork Check - Double check the measurement with Diagonal check
checkpoint | Reinforcement (Reo) placed, cleaned, tightened
checkpoint | Curing Procedure arranged
checkpoint | Photo Taken
checklist | Installers Checklist (LP3)
section | Job Approval Documents/Construction Documents
checkpoint | Complete Material "Bucket List"
checkpoint | Embedded Item -Placement, position, alignment
bool | Grout Tubes - 2 x ∅=50, L=1200
bool | Lifters - 6 x 9T Edge Lifters
bool | Brace Ferrules - 2 x M20x96mm
bool | Ferrules - 8 x M20 - FS - 75-96mm
checkpoint-no-status | ID Plate
textbox | ID:
section | Pre-Pour Check Approvals
checkpoint | Formwork Check -Panel Dimensions & DOUBLE CHECK
checkpoint | Apply Debonding agents -bond breaker or wax (1/2/3/ Coats)
checkpoint | Temporary Fix ID Plate to Formwork
checkpoint | Use Required Mould, Supports, Ties - Bridge Plank Mould
checkpoint | Reinforcement Check - Reo as-per Shop Drawing
checkpoint | Lifters, Ferrules, Tubes Fixed Firm & aligned -Check
checkpoint | Concrete cover Check - 30mm
section | Quality Assurance
checkpoint | QA - Final Check of ALL measurements & Diagonals
checkpoint | QA - Concrete N40 Panel Mix - Special Adjustments
checkpoint | QA - Concrete mix design ,variations%, adjustments%, mix time
checkpoint | QA - All main & other requirement to do Concreting -DOUBLE CHECK
date | Pour Date
checkpoint | CONCRETE TEST Procedure
checkpoint-no-status | APPROVAL FROM ENGINEER
section | Other Arrangements
checkpoint | Concrete surface Finish Requirement arranged (Fine Finish)
checkpoint | Curing Procedure arranged
checklist | Checkers Checklist (LP4)
section | Details
checkpoint-no-status | Site Safety / Workers Safety
checkpoint-no-status | Availability of current for construction shop drawing
checkpoint-no-status | Overall Measurements of construction Element
bool | Formwork Check - Magnets are 100% Secure, All supports,Ties,Bracing
bool | Formwork Check - Flatness, Levelness, Panel is clean
bool | Formwork Check - Double check the measurement with Diagonal check
bool | Apply Debonding agents -bond breaker or wax (1/2/3/ Coats)
checkpoint | Void for lift door openings - Dimensional and location check
checkpoint | Reinforcement (Reo) placed, cleaned, tightened
checkpoint | Embedded Item -Placement, position, alignment
bool | Grout Tubes - 2 x ∅=50, L=1200
bool | Lifters - 6 x 9T Edge Lifters
bool | Brace Ferrules - 2 x M20x96mm
bool | Ferrules - 8 x M20 - FS - 75-96mm
bool | Reidbar Insert - 22 x RBA16 - NS
checkpoint | Embedded Item - Fillet / Chamfer installation
checkpoint | Concrete cover 30mm
checkpoint | Panel Thickness check,allignment check - 175mm
checkpoint | Formwork Check - Magnets are 100% Secure, All supports, Ties, Bracing
checkpoint | Formwork Check - Flatness, Levelness, Panel is clean
checkpoint | Formwork Check - Double check the measurement with Diagonal check
checkpoint | Reinforcement (Reo) placed, cleaned, tightened
checkpoint | Curing Procedure arranged
checkpoint | Photo Taken
checklist | Installers Checklist (LP4)
section | Job Approval Documents/Construction Documents
checkpoint | Complete Material "Bucket List"
checkpoint | Embedded Item -Placement, position, alignment
bool | Grout Tubes - 2 x ∅=50, L=1200
bool | Lifters - 6 x 9T Edge Lifters
bool | Brace Ferrules - 2 x M20x96mm
bool | Ferrules - 8 x M20 - FS - 75-96mm
bool | Reidbar Insert - 22 x RBA16 - NS
checkpoint-no-status | ID Plate
textbox | ID:
section | Pre-Pour Check Approvals
checkpoint | Formwork Check -Panel Dimensions & DOUBLE CHECK
checkpoint | Apply Debonding agents -bond breaker or wax (1/2/3/ Coats)
checkpoint | Temporary Fix ID Plate to Formwork
checkpoint | Use Required Mould, Supports, Ties - Bridge Plank Mould
checkpoint | Reinforcement Check - Reo as-per Shop Drawing
checkpoint | Lifters, Ferrules, Tubes Fixed Firm & aligned -Check
checkpoint | Concrete cover Check - 30mm
section | Quality Assurance
checkpoint | QA - Final Check of ALL measurements & Diagonals
checkpoint | QA - Concrete N40 Panel Mix - Special Adjustments
checkpoint | QA - Concrete mix design ,variations%, adjustments%, mix time
checkpoint | QA - All main & other requirement to do Concreting -DOUBLE CHECK
date | Pour Date
checkpoint | CONCRETE TEST Procedure
checkpoint-no-status | APPROVAL FROM ENGINEER
section | Other Arrangements
checkpoint | Concrete surface Finish Requirement arranged (Fine Finish)
checkpoint | Curing Procedure arranged