## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource Id
checklist | Testing & Commissioning - LIGHT/POWER Circuits | [5 empty] | Testing & Commissioning - LIGHT/POWER Circuits
section | Lighting/Power Circuits Field PRE ITC
checkpoint-no-status | Lighting/Power Circuits Field PRE ITC
textbox | Distribution Board
textbox | Cable Type
textbox | Submain Size
textbox | CB Size
textbox | Fed From
textbox | Tested By
date | Date ITC
section | ITC
checkpoint | LIGHT/POWER Circuits
textbox | C/B No.
textbox | C/B Size
textbox | Cable Size
textbox | Earth Resistance
textbox | Insulation Resistance
textbox | Polarity
textbox | Fault Loop
textbox | Safe to Energise
textbox | Tested By
date | Date
holdpoint | Checked By (Heyday):
checklist | Testing & Commissioning - MAINS AND SUBMAINS | [5 empty] | Testing & Commissioning - MAINS AND SUBMAINS
section | Submain Details
checkpoint-no-status | Submain Details
textbox | Area
textbox | Drawing No.
textbox | From
textbox | To
textbox | Cable No.
textbox | Cable Type
textbox | Cable Size
textbox | Length
textbox | Cores
textbox | MCCB Model
textbox | Rating (A)
textbox | Trip Unit
textbox | Trip Setting (A)
section | Visual Inspections (AS/NZS 3000)
checkpoint | Provided with adequate support, suspension and fixings?
checkpoint | Suited for the intended use?
checkpoint | Protected against mechanical damage, enviromental and other external influnece by enclosure?
checkpoint | Is the cable the correct type and size?
checkpoint | Is the cable terminated at both ends?
checkpoint | Are the connections tight, correct tension and marked?
checkpoint | Is the cable free of damaged?
checkpoint | Is the cable and terminations correctly labeled?
section | Pre Energisation Checks (AS/NZS 3000)
checkpoint | Bolt Tension Check/Bolt Lined and Tension noted?
textbox | NM
checkpoint | Earth Continuity (Value must be less than 0.5 ohms)
textbox | Earth Size
textbox | FROM
textbox | TO
textbox | Point to Point Reading |  |  | Ω
checkpoint | Insulation Resistance Test (AS/NZS 3000)
textbox | RED TO WHITE
textbox | RED TO BLACK
textbox | RED TO EARTH
textbox | WHITE TO BLUE
textbox | WHITE TO BLACK
textbox | WHITE TO EARTH
textbox | BLUE TO RED
textbox | BLUE TO BLACK
textbox | BLUE TO EARTH
checkpoint | Polarity Test
textbox | RED TO RED
textbox | WHITE TO WHITE
textbox | BLUE TO BLUE
textbox | BLACK TO BLACK
checkpoint | Fault Loop Impedance (If Applicable)
label | Cables have been installed as per design calculations.
label | Note, if FAIL seek design clarification to adjust circuit breaker tripping curve characteristics.
section | Post Engerisation Checks (AS/NZS 3000)
checkpoint-no-status | Phase Rotation
dropdown | Phase Rotation: | Clockwise →,Anti Clockwise ←
checkpoint | Voltage Checks (AS/NZS 3000)
textbox | RED TO WHITE
textbox | RED TO BLACK
textbox | RED TO EARTH
textbox | WHITE TO BLUE
textbox | WHITE TO BLACK
textbox | WHITE TO EARTH
textbox | BLUE TO RED
textbox | BLUE TO BLACK
textbox | BLUE TO EARTH
checkpoint-no-status | Test Equipment - Multimeter
textbox | Brand/Model
textbox | Serial No.
textbox | Calibration Due
textbox | Tester
date | Date
checkpoint-no-status | Test Equipment - Insulation Resistance Tester
textbox | Brand/Model
textbox | Serial No.
textbox | Calibration Due
textbox | Tester
date | Date
checkpoint-no-status | Test Equipment - Phase Rotation Meter
textbox | Brand/Model
textbox | Serial No.
textbox | Calibration Due
textbox | Tester
date | Date
checklist | Testing & Commissioning - MSB AND DB's | [5 empty] | Testing & Commissioning - MSB AND DB's
section | Submain Details as per ITC 4A
checkpoint-no-status | Submain Details as per ITC 4A
textbox | Area
textbox | Drawing No.
textbox | From
textbox | To
textbox | Cable No.
textbox | Cable Type
textbox | Cable Size
textbox | Length
textbox | Cores
textbox | MCCB Model
textbox | Rating (A)
textbox | Trip Unit
textbox | Trip Setting (A)
section | CHECKLIST
checkpoint | Approved Factory Acceptance Test completed?
checkpoint | Switchboard is secure and ready for Consumer Main/Submain Installation
checkpoint | Consumer Main/Submain Installed?
checkpoint | Verify C/B Trip Settings are Correct.
checkpoint | Consumer Main/Submain Test has been completed as per Heyday ITC-4A
checkpoint | Are the connections tight, correct tension and marked?
checkpoint | Switchboard is ready to be energised?
section | Pre Energisation Checks (AS/NZS 3000)
checkpoint | Earth Continuity (Value must be less than 0.5 ohms)
textbox | Earth Size
textbox | FROM
textbox | TO
textbox | Point to Point Reading |  |  | Ω
checkpoint | BUSBAR Insulation Resistance Test (AS/NZS 3000)
textbox | RED TO WHITE
textbox | RED TO BLACK
textbox | RED TO EARTH
textbox | WHITE TO BLUE
textbox | WHITE TO BLACK
textbox | WHITE TO EARTH
textbox | BLUE TO RED
textbox | BLUE TO BLACK
textbox | BLUE TO EARTH
section | Post Energisation Checks (AS/NZS 3000)
checkpoint-no-status | Phase Rotation
dropdown | Phase Rotation: | Clockwise →,Anti Clockwise ←
checkpoint | Voltage Checks (AS/NZS 3000)
textbox | RED TO WHITE
textbox | RED TO BLACK
textbox | RED TO EARTH
textbox | WHITE TO BLUE
textbox | WHITE TO BLACK
textbox | WHITE TO EARTH
textbox | BLUE TO RED
textbox | BLUE TO BLACK
textbox | BLUE TO EARTH
checkpoint-no-status | Test Equipment - Multimeter
textbox | Brand/Model
textbox | Serial No.
textbox | Calibration Due
textbox | Tester
date | Date
checkpoint-no-status | Test Equipment - Insulation Resistance Tester
textbox | Brand/Model
textbox | Serial No.
textbox | Calibration Due
textbox | Tester
date | Date
checkpoint-no-status | Test Equipment - Phase Rotation Meter
textbox | Brand/Model
textbox | Serial No.
textbox | Calibration Due
textbox | Tester
date | Date