## Master List Templates
Id | Type | Name | Values | Prompting Name
081ec648-9162-4735-99e5-f2638011f575 | checklist | Precast Element |  | Item -
8181493c-d147-4784-9adf-6b5dc0fd309a | section | Formwork
b4921539-4c30-4401-adfe-526239c57600 | checkpoint | IFC Drawing Revision
a75cef4a-761a-4b8e-a8e0-c05a34ad67d7 | checkpoint | Squareness
d19e0b5c-198e-419e-a118-0a5eef3f6c26 | checkpoint | Dimensions
5380a079-389e-456e-8b15-f4d7e719ec8d | checkpoint | Windows/Doors/voids
08bf0381-9a25-4092-904c-c229b914acd2 | checkpoint | Edge Form/ Fillets
a548b726-6868-4aa6-926e-f1662ad5a4b3 | checkpoint | ID Tag
feb5e0c6-4db0-4e77-bf12-b7a095314d74 | checkpoint | Weather joint
91cc7ded-ff84-59be-aad7-362909ff758b | tickbox | Top
7ec146d4-184b-5bbf-b3e0-e2acc9889e14 | tickbox | Bottom
ea88bad0-c587-518d-aa7a-0587329367c2 | tickbox | Return
b5a2ad14-b826-4891-8834-19c33dda10e5 | checkpoint | Dummy joints
16db2598-c54b-5d73-a7ad-58ae29b2d2be | tickbox | NF
42460099-8fd0-5639-a6f2-f9884e4bed4a | tickbox | FF
1e1943be-cd93-5911-b83a-83e6badc47fc | tickbox | Edge
8ec19fb1-5b5d-40b4-8974-51953a78a000 | checkpoint | Cleanliness
df9d3c34-44b5-549f-932a-109217c1632e | textbox | Notes/Changes
40de16d0-0be3-42ab-9266-14b96c9be569 | checkpoint-no-value | Drafting Non conformities
d99817be-19c3-5016-8bca-8b2ccab5ea23 | note | Missing information
5de3073c-d9ef-513a-b527-0afa2509f813 | note | Inconsistent information
ec912131-ce9c-55bc-a921-d0a36786fcd4 | note | Wrong information
272dd2a5-a459-5189-9458-70b456ed10b0 | note | Revision
5b599f67-d48d-429d-8627-63980d327271 | checkpoint-no-value | Formwork Non conformities
9d20060d-11c0-5601-b74d-9adc59ee4f05 | note | Squareness
2bffe084-9c89-5e79-9d1b-2d29407333f0 | note | Dimensions
70443246-85d5-50fc-96ba-2562f079c7eb | note | GT
11263174-f019-5826-a9bb-b7becb8a0f95 | note | Panel Orientation
bb444572-e310-530f-afa1-87f9fb9184fd | note | Fitments
2f0f408c-69be-59c6-9003-6a0a3c51df69 | note | Tag
db4a58c0-1a40-4f2f-8500-22c8c19b6e16 | section | Reinforcement & Embedded Items
d4d323ee-831f-45e8-9de7-c18c6a75b957 | checkpoint | Cover
e910b787-2556-4763-a996-b7fa19e333ef | checkpoint | Rebates
6c4c3de0-bcb7-5b91-a621-46f083fcffd0 | tickbox | NF
f274cfc0-2f70-50e5-8317-94bcbcb85c73 | tickbox | FF
1a951f60-0717-580e-bf23-573be3fb8792 | tickbox | Edge
ca8e9278-2d26-421f-90f6-e6461f231a09 | checkpoint | Grout tubes
b8e56c91-4e76-557c-934f-63d5486b8bc6 | tickbox | NF
afa91024-b5bb-5186-8054-08ce326fba2f | tickbox | FF
87214160-18de-51d4-bc33-5deda7156cf8 | tickbox | Edge
d8c258eb-d464-4850-a5cc-549f8f98fd05 | checkpoint | Cast in plates
b03cb126-24fd-59d5-bdd3-17385f8bb36a | tickbox | NF
c8df7840-8a56-58b7-a664-75a93528ea69 | tickbox | FF
66531348-ef2a-5ea0-9e8f-614939a7c656 | tickbox | Edge
3153b021-7c4e-4982-8f6f-344caa52de92 | checkpoint | Prop points
3c5070e4-eb02-5a96-80d1-892771be13b9 | tickbox | NF
fcaf0c99-e09c-5e8e-b16b-0cc52a963ea6 | tickbox | FF
e0b2c9e2-d5da-5859-9975-3cb3f3ba0b3b | tickbox | Edge
54a92e31-cdd0-443e-8b9b-f513858491c3 | checkpoint | Exposed edges
e81c94fe-6f0a-5624-b0c7-f1735eb1d6e5 | tickbox | LHS
6eaf42d2-b964-5a03-a039-b19d02cb04c1 | tickbox | RHS
dcbb78e8-5a4d-5d22-a9a2-949721720df0 | tickbox | Top
556ee3f5-8a80-55cc-93e1-82f12aee1555 | tickbox | Bottom
6e78e845-677a-4019-9b18-e4ee85589cb0 | checkpoint | Lifting devices securely/in place
cd893388-3e98-4d89-a150-7ab8edb0540a | checkpoint | Conduits
aececd53-382d-40e7-ae89-8a7e48003770 | checkpoint | Ready to pour- Take photo of QA drawing
2bb22c50-642e-4a6e-a818-e01274c889d4 | checkpoint | Ready to pour- Take photo of the approved panel meeting specs.
3a0bbd2a-00bd-4645-bce8-c55ad55c1200 | checkpoint-no-value | Steel Non conformities
29810c28-c440-56ba-b680-93b0ad7839ee | note | Cover
403eb9a5-9fc9-5a5e-ade3-b0772796e985 | note | Missing bars
dfdf3e2d-25b9-58fb-89c7-88627d38a6cf | note | Wrong bars
840cf6c1-020f-55d5-ad6d-cbda90e14da0 | note | Wrong configuration
03f35cc1-1d93-5f6e-a80a-fdce808e5c81 | note | Orientation
0750b50c-98fb-59ae-b3e9-fa4b71688cf7 | note | Wrong projection/ embedment
0120faeb-9e40-52d7-86cd-d5e3028bf1d5 | note | Rebate Reo
f4c88f9e-51fd-553c-bb0e-f95012cd46f5 | note | GT
6608d720-7f3a-5574-8b8f-b7e3bba5251e | note | Fitments
45c06fc9-a4f9-4251-9b58-1204c7fa9a0d | section | Concrete
4fe33f2e-aeee-4a48-99bc-b9ca95864527 | checkpoint-no-value | Enter "Pouring date" in the Update panel (Production tracking section)
6b8291d8-d8eb-457e-a726-6222a36d62a0 | checkpoint | Take a picture or attach copy of concrete doc
9f54d69b-835c-599a-b63f-5018172620d0 | dropdown | Concrete Supplier | Hy-Tec, Titan, Other
a25cfa32-f439-56fa-a99c-57235477fa69 | textbox | Other Concrete Supplier
c7c470c0-d94f-57c4-8372-a6ac54c2ba4c | dropdown | Type of concrete poured | VS502CPAN, VS504BKR3G, VS502WPAN, VS804BPAN, VS502W7PAN, VS654BPANLTE, VS504CPANLTE, VS504BPANLTE, VS507BPANLTE, VS507CPANLTE, VS657BPANLTE, VS804BPANLTE
6b2c7298-0193-5606-bbfb-e4fb8b64aae8 | textbox | Other Type of concrete
f6b3e2f7-179c-5e95-b432-b81a1b5ae590 | textbox | Concrete schedule docket #
7de76c66-f79c-5f2d-8743-687405795fbf | textbox | Concrete Requisition (m3)
b0f4be20-3fa2-4a27-ab51-ee8fb6df2506 | checkpoint | Correct mix being used
fd88375a-04b5-55e9-9ab9-129e448f96b1 | button | Concrete strength tested | Yes, No
b7de795a-a943-49a5-84f7-c722c2533542 | checkpoint-no-value | Concrete Non conformities
1d5ae7d9-43c0-53ad-9143-9cf7c4bc51a4 | note | Poured with lower Mpa
2e5d617e-7018-53b7-b9cd-333314be8d65 | note | Concrete Fails to Meet Specifications
3b2e42e7-2d5e-4e16-9817-1c089ff9194b | section | Post Production
8906b4ac-dab0-4a1e-b64a-b710639eba92 | checkpoint-no-value | Class
6785879e-d8ed-53f1-8194-bf05b5de14c7 | dropdown | Class | 1,2,3
17927173-3316-46d4-b1e2-45b3e588be2d | checkpoint | Dimensions
1a2347be-bbca-4813-add9-3f8aeaa40add | checkpoint | Voids cleared and serviceable
c1fe776a-c99f-40d5-9847-0cbb4df97f82 | checkpoint | Cast in plates Location
a22cbcee-39a7-4d6e-b3ad-b59e9531f830 | checkpoint | Rebates Location
7225d459-3033-4b76-8aa2-9fdb0914edd7 | checkpoint | ID Tag correct and clean
8f3ce744-b1db-4dba-ac41-b2a8811e4995 | checkpoint | Surface finish
ab7354d0-4ee3-4deb-bcf3-a390afad25ee | checkpoint | Exposed edges Sticker
43c1bb22-29ac-4991-a31d-41586a058fb5 | checkpoint | Fitments removed (GT Caps, fillets, Ferrule caps)
93c96090-1bd9-46a4-bc6d-518618f63d03 | checkpoint | Cracks within tolerances
8afc9b62-0422-4259-a8b6-bf093859a5a9 | checkpoint | Strong backs and bracings
508add87-25d0-417c-b3da-4d1de6d64b17 | checkpoint | Approved panel meeting specs - Take a photo
8c23c92a-f744-4f2a-bf9b-bad611b64697 | checkpoint-no-value | Post production Non conformities
eea94c99-a16a-5649-9414-b3172670d308 | note | Patching required
511b8ca4-1ea0-5a4a-8202-a36d1b2794bb | note | Fixing required