## Table 1
Abbreviations
Third Party |  | TP |  |  | RSA Contractors |  | RSA | Nominated Project Personnel |  |  |  |  | NPP | Principle Contractor |  |  |  | PC
Surveyor |  | SUR |  |  | RPEQ |  | RPEQ | Supervisor |  |  |  |  | SUP | Inspect |  |  |  | INS
Test |  | TST |  |  | Project Engineer |  | PE | Witness Point |  |  |  |  | WP | Hold Point |  |  |  | HP
Visual |  | VIS |  |  | Check |  | CHK | Written |  |  |  |  | WRI | Monitor |  |  |  | M
Milestone |  | MST |  |  | Review |  | R
Inspection and Test Plan Details | [13 empty] | Contractor |  |  |  | Client
Item | Inspection Activity |  | Work By |  | Standard / Spec |  | Criteria |  |  |  | Frequency |  | Record | Resp |  | Type | Signoff | Resp | Type | Signoff
1 | Site Clearing |  | Contractor |  | Technical Specification |  | All vegetation, roots, topsoil removed |  |  |  | 1/Lot |  | ITP Verification | RSA |  | CHK |  | ACC | CHK
2 | Foundation Stripping |  | Contractor |  | Technical Specification |  | Strip to firm, undisturbed soil (no organics) |  |  |  | 1/project |  | ITP Verification Checklist/Lot Map | RSA |  | CHK |  | ACC | CHK
3 | Soft Spot Removal |  | Contractor |  | Technical Specification |  | Soft areas removed and backfilled with clay |  |  |  | 1/Lot |  | ITP Verification Checklist/Lot Map | RSA |  | VIS |  | ACC | VIS
4 | Cutoff Trench Excavation |  | Contractor |  | Technical Specification |  | Depth to clay/impervious layer achieved Excavate down to clay or impervious layer (depth: 1–3 m typical). |  |  |  | 1/Lot |  | ITP Verification Checklist/Lot Map | RSA |  | WP |  | ACC | WP
5 | Cutoff Backfill Placement |  | Contractor |  | Technical Specification |  | Clay placed in 150–200 mm layers, OMC ±2% |  |  |  | 1/Lot |  | ITP Verification Checklist/Lot Map | RSA |  | WP |  | ACC | WP
6 | Compaction Testing |  | Contractor |  | Technical Specification |  | The foundation surface level shall be scarified, watered and compacted to a density ratio of no less than 96% |  |  |  | 1/Lot |  | Testing | RSA |  | WP |  | ACC | WP
7 | Proof Rolling |  | Contractor |  | Technical Specification |  | Prior to the placemat of construction materials, the subgrade shall be rolled using a smooth drum roller to form a hard-smooth surface and approved by the superintendent |  |  |  | 1/2500m2 |  | NATA certificate | RSA |  | HP |  | ACC | HP
8 | Foundation Approval |  | Contractor |  | Technical Specification |  | Engineer sign-off prior to embankment fill |  |  |  | 1/Lot |  | Survey as Built | RSA |  | HP |  | ACC | HP
Test Details | [6 empty] | Normal Testing Level | [6 empty] | Required Result(s)
Item | Test |  |  | Description |  |  | Max Lot Size |  | Min Test Frequency |  |  | Min No of tests |  | Criteria
1 | AS 1289 5.1.1 |  |  | Hilf Dry density ratio, Moisture Content | [9 empty] | -2% dry to +2% wet OMC DDR 96%
Contractor Construction Manager:
[6 empty] | (Print Name) |  |  |  | (Signature) |  |  |  |  | (Date)
Client Superintendent:
[6 empty] | (Print Name) |  |  |  | (Signature) |  |  |  |  | (Date)
Document Status
Revision Status |  | Responsible Person |  |  | Signed |  | Dated | Revision
Draft By: |  | Madhu Achana
Reviewed By:
Submitted By:
Approved By: