## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource Id
checklist | ITP001 - CLEAR GRUB & TOPSOIL STRIPPING | itp
section | CLEARING & GRUBBING
checkpoint | 01 - Survey Set Out
label | Work By - Contractor
label | Standard / Spec - Technical Specification
label | Criteria - The contractor shall be responsible for engaging a licensed surveyor of Australia approved by the Superintendent to set out all works in accordance with the design drawings prior to the commencement of the works
label | Frequency - Prior to commencement
label | Record - ITP Verification Checklist/Site Survey
label | Contractor: Resp - RSA
label | Contractor: Type - WP
label | Client: Resp - ACC
label | Client: Type - WP
checkpoint | 02 - Site Services
label | Work By - Contractor
label | Standard / Spec - Technical Specification
label | Criteria - Contractor shall take reasonable steps to locate all existing service on the site. Where existing services are identified they shall be clearly marked for the duration of the works.
label | Frequency - Prior to commencement
label | Record - Site general layout drawing
label | Contractor: Resp - RSA
label | Contractor: Type - HP
label | Client: Resp - ACC
label | Client: Type - HP
holdpoint | HOLD POINT
checkpoint | 03 - Lot Identification
label | Work By - Contractor
label | Standard / Spec - Technical Specification
label | Criteria - Location of works identified in accordance with the Project Technical Specifications.
label | Frequency - 1/Lot
label | Record - Attached Drawing
label | Contractor: Resp - RSA
label | Contractor: Type - CHK
label | Client: Resp - ACC
label | Client: Type - CHK
checkpoint | 04 - Clearing& Grubbing
label | Work By - Contractor
label | Standard / Spec - Technical Specification
label | Criteria - Clearing shall be performed within the limits of the works indicated on the drawings.
label | ○ Trees, shrubs, logs, debris, perishable material, organic matter, fallen trees, overhanging branches and surface obstructions shall be removed from the stripping area.
label | Frequency - 1/Lot
label | Record - ITP Verification Checklist
label | Contractor: Resp - RSA
label | Contractor: Type - HP
label | Client: Resp - ACC
label | Client: Type - HP
holdpoint | HOLD POINT
section | TOPSOIL STRIPPING
checkpoint | 05 - Topsoil Stripping
label | Work By - Contractor
label | Standard / Spec - Technical Specification
label | Criteria - Topsoil shall be stripped such that all organic rich soil and roots/rootlets has been removed from the foundation of the embankment and internal borrow areas
label | ○ Topsoil shall be stripped to the depth(s) 200mm. Any areas with depth greater than 200mm should be notified to the superintendent.
label | Frequency - Confirm with survey
label | Record - ITP Verification Checklist/Site Survey
label | Contractor: Resp - RSA
label | Contractor: Type - HP
label | Client: Resp - ACC
label | Client: Type - HP
holdpoint | HOLD POINT
checkpoint | 06 - Stockpile of Materials
label | Work By - Contractor
label | Standard / Spec - Technical Specification
label | Criteria - Stripped topsoil shall be stockpiled where directed by the Superintendent, for reuse.
label | ○ Topsoil is to be placed in a loose, non- compacted state, to a maximum height of 3 metres
label | Frequency - 1/lot
label | Record - ITP Verification Checklist/ Lot Map
label | Contractor: Resp - RSA
label | Contractor: Type - HP
label | Client: Resp - ACC
label | Client: Type - HP
holdpoint | HOLD POINT
checkpoint | 07 - Survey after topsoil removal
label | Work By - Contractor
label | Standard / Spec - Technical Specification
label | Criteria - As-constructed survey has been to be completed to record the surface levels on completion of topsoil stripping.
label | Frequency - As required
label | Record - ITP Verification Checklist/Lot Map
label | Contractor: Resp - RSA
label | Contractor: Type - HP
label | Client: Resp - ACC
label | Client: Type - HP
holdpoint | HOLD POINT
section | Contractor Construction Manager / Client Superintendent Signoff
checkpoint | Contractor Construction Manager / Client Superintendent Signoff
holdpoint | Add Signatures
checklist | ITP002 - FP - FOUNDATION PREPARATION | itp
section | Inspection and Test Plan Details
checkpoint | 01 - Site Clearing
label | Work By - Contractor
label | Standard / Spec - Technical Specification
label | Criteria - All vegetation, roots, topsoil removed
label | Frequency - 1/Lot
label | Record - ITP Verification
label | Contractor: Resp - RSA
label | Contractor: Type - CHK
label | Client: Resp - ACC
label | Client: Type - CHK
checkpoint | 02 - Foundation Stripping
label | Work By - Contractor
label | Standard / Spec - Technical Specification
label | Criteria - Strip to firm, undisturbed soil (no organics)
label | Frequency - 1/project
label | Record - ITP Verification Checklist/Lot Map
label | Contractor: Resp - RSA
label | Contractor: Type - CHK
label | Client: Resp - ACC
label | Client: Type - CHK
checkpoint | 03 - Soft Spot Removal
label | Work By - Contractor
label | Standard / Spec - Technical Specification
label | Criteria - Soft areas removed and backfilled with clay
label | Frequency - 1/Lot
label | Record - ITP Verification Checklist/Lot Map
label | Contractor: Resp - RSA
label | Contractor: Type - VIS
label | Client: Resp - ACC
label | Client: Type - VIS
checkpoint | 04 - Cutoff Trench Excavation
label | Work By - Contractor
label | Standard / Spec - Technical Specification
label | Criteria - Depth to clay/impervious layer achieved Excavate down to clay or impervious layer (depth: 1–3 m typical).
label | Frequency - 1/Lot
label | Record - ITP Verification Checklist/Lot Map
label | Contractor: Resp - RSA
label | Contractor: Type - WP
label | Client: Resp - ACC
label | Client: Type - WP
checkpoint | 05 - Cutoff Backfill Placement
label | Work By - Contractor
label | Standard / Spec - Technical Specification
label | Criteria - Clay placed in 150–200 mm layers, OMC ±2%
label | Frequency - 1/Lot
label | Record - ITP Verification Checklist/Lot Map
label | Contractor: Resp - RSA
label | Contractor: Type - WP
label | Client: Resp - ACC
label | Client: Type - WP
checkpoint | 06 - Compaction Testing
label | Work By - Contractor
label | Standard / Spec - Technical Specification
label | Criteria - The foundation surface level shall be scarified, watered and compacted to a density ratio of no less than 96%
label | Frequency - 1/Lot
label | Record - Testing
label | Contractor: Resp - RSA
label | Contractor: Type - WP
label | Client: Resp - ACC
label | Client: Type - WP
checkpoint | 07 - Proof Rolling
label | Work By - Contractor
label | Standard / Spec - Technical Specification
label | Criteria - Prior to the placemat of construction materials, the subgrade shall be rolled using a smooth drum roller to form a hard-smooth surface and approved by the superintendent
label | Frequency - 1/2500m2
label | Record - NATA certificate
label | Contractor: Resp - RSA
label | Contractor: Type - HP
label | Client: Resp - ACC
label | Client: Type - HP
holdpoint | HOLD POINT
checkpoint | 08 - Foundation Approval
label | Work By - Contractor
label | Standard / Spec - Technical Specification
label | Criteria - Engineer sign-off prior to embankment fill
label | Frequency - 1/Lot
label | Record - Survey as Built
label | Contractor: Resp - RSA
label | Contractor: Type - HP
label | Client: Resp - ACC
label | Client: Type - HP
holdpoint | HOLD POINT
section | Test Details
checkpoint | 01 - Site Clearing
label | Description - Hilf Dry density ratio, Moisture Content
checkpoint-no-status | 01 - Site Clearing - Normal Testing Level
textbox | Max Lot Size
textbox | Min Test Frequency
textbox | Min No of tests
checkpoint-no-status | 01 - Site Clearing - Required Result(s)
label | Criteria - -2% dry to +2% wet OMC DDR 96%
section | Contractor Construction Manager / Client Superintendent Signoff
checkpoint | Contractor Construction Manager / Client Superintendent Signoff
holdpoint | Add Signatures
checklist | ITP003 - EC - EMBANKMENT CONSTRUCTION | itp
section | Inspection and Test Plan Details
checkpoint | 01 - Lot Identification
label | Work By - Contractor
label | Standard / Spec - Technical Specification
label | Criteria - Location of Works identified in accordance with project technical specification
label | Frequency - 1/Lot
label | Record - ITP Verification Checklist/Lot Map
label | Contractor: Resp - RSA
label | Contractor: Type - CHK
label | Client: Resp - ACC
label | Client: Type - CHK
checkpoint | 02 - Underlying Lot Conforms
label | Work By - Contractor
label | Standard / Spec - Technical Specification
label | Criteria - Foundation preparation works are cleared, proof rolled, no soft spots or organics.
label | Frequency - 1/Lot
label | Record - ITP Verification Checklist/Lot Map
label | Contractor: Resp - RSA
label | Contractor: Type - CHK
label | Client: Resp - ACC
label | Client: Type - CHK
checkpoint | 03 - Fill placement
label | Work By - Contractor
label | Standard / Spec - Technical Specification
label | Criteria - General Fill
label | ○ Placed in continuous, approximately horizontal layers for the full width of the area, having a compacted thickness of not more than 300 mm or less than 75 mm. If the surface of any layer is smooth, it must be scarified to a depth of approximately 30 to 50 mm prior to the placement of the next layer.
label | ○ ≥ 96 % standard MDD. -2% to +2% of OMC
label | Frequency - Each Lot
label | Record - ITP Verification Checklist/Lot Map
label | Contractor: Resp - RSA
label | Contractor: Type - WP
label | Client: Resp - ACC
label | Client: Type - WP
checkpoint | 04 - Survey
label | Work By - Contractor
label | Standard / Spec - Technical Specification
label | Criteria - RSA shall submit 25%, 50%, 100% tank pad foundation fill placement completion.
label | Frequency - 1/Lot
label | Record - Survey
label | Contractor: Resp - RSA
label | Contractor: Type - HP
label | Client: Resp - ACC
label | Client: Type - HP
holdpoint | HOLD POINT
section | Test Details
checkpoint | 01 - AS 1289 5.7.1
label | Description - Hilf Dry density ratio, Moisture Content
checkpoint-no-status | 01 - AS 1289 5.7.1 - Normal Testing Level
textbox | Max Lot Size
textbox | Min Test Frequency
label | Min No of tests: 20
checkpoint-no-status | 01 - AS 1289 5.7.1 - Required Result(s)
label | Criteria - -2% dry to +2% wet OMC DDR 96%
checkpoint | 02 - AS1289
label | Description - PSD
label | ○ Atterberg Limits
label | ○ Emerson
checkpoint-no-status | 01 - AS 1289 5.7.1 - Normal Testing Level
textbox | Max Lot Size
textbox | Min Test Frequency
label | Min No of tests: 5
checkpoint-no-status | 01 - AS 1289 5.7.1 - Required Result(s)
section | Contractor Construction Manager / Client Superintendent Signoff
checkpoint | Contractor Construction Manager / Client Superintendent Signoff
holdpoint | Add Signatures