## matrix
Matrix Name | Dimension | Name | Type / Data Field | Tag 1 | Tag 2
Precast Beams - Overall Progress (869-B01 to 869-B37)
| Scope |  |  | Precast Manufacture | Precast Beams
Rows
|  | 864-P01 to 864-P19 | dynamic | 869-B01 to 869-B37 | Precast Beams
Columns
|  | Details |  | details
|  | Pre-pour QA |  | pre-pour qa
|  | Pour QA |  | pour qa
|  | Post pour/Pre delivery QA |  | post pour/pre delivery qa
Precast Beams - Detailed Progress (869-B01 to 869-B37)
| Scope |  |  | Precast Manufacture | Precast Beams
Rows
|  | 869-B01 to 869-B37 | dynamic | 869-B01 to 869-B37 | Precast Beams
Columns
|  | Photograph/Upload of latest drawing attached (Office PM) |  | photograph/upload of latest drawing attached (office pm)
|  | Drawing # | Drawing # | photograph/upload of latest drawing attached (office pm)
|  | Revision # | Revision # | photograph/upload of latest drawing attached (office pm)
|  | Formwork Fixed Correctly |  | formwork fixed correctly
|  | Mould clean |  | mould clean
|  | Release oil applied correctly |  | release oil applied correctly
|  | Primary dimensions checked |  | primary dimensions checked
|  | Length | Length | primary dimensions checked
|  | Width | Width | primary dimensions checked
|  | Thickness | Thickness | primary dimensions checked
|  | Diagonal dimensions checked |  | diagonal dimensions checked
|  | Openings Checked and Correct |  | openings checked and correct
|  | size | size | openings checked and correct
|  | location | location | openings checked and correct
|  | orientation | orientation | openings checked and correct
|  | Rebates Installed Correctly |  | rebates installed correctly
|  | Formwork chamfers installed correctly where required |  | formwork chamfers installed correctly where required
|  | Reinforcing placed correctly, checked and approved |  | reinforcing placed correctly, checked and approved
|  | Correct Size and Type | Correct Size and Type | reinforcing placed correctly, checked and approved
|  | Laps and Splices correct | Laps and Splices correct | reinforcing placed correctly, checked and approved
|  | Cover Checked | Cover Checked | reinforcing placed correctly, checked and approved
|  | Spacing Checked | Spacing Checked | reinforcing placed correctly, checked and approved
|  | Cast in items checked, correct (size and location |  | cast in items checked, correct (size and location
|  | Weld Plates | Weld Plates | cast in items checked, correct (size and location
|  | Drossbach | Drossbach | cast in items checked, correct (size and location
|  | PS Voids | PS Voids | cast in items checked, correct (size and location
|  | TIM Inserts | TIM Inserts | cast in items checked, correct (size and location
|  | RB Coupler(s) | RB Coupler(s) | cast in items checked, correct (size and location
|  | Other cast in items checked (if any) | Other cast in items checked (if any) | cast in items checked, correct (size and location
|  | Starter Bars inserted, checked and correct |  | starter bars inserted, checked and correct
|  | Size | Size | starter bars inserted, checked and correct
|  | Location | Location | starter bars inserted, checked and correct
|  | Spacing | Spacing | starter bars inserted, checked and correct
|  | Lifting Items inserted, checked and correct |  | lifting items inserted, checked and correct
|  | Size | Size | lifting items inserted, checked and correct
|  | Location | Location | lifting items inserted, checked and correct
|  | Check Minimum Cover |  | check minimum cover
|  | Pre-Pour checks completed and approval given to pour Item |  | pre-pour checks completed and approval given to pour item
|  | Concrete Strength correct as per design (Attach photo of concrete docket) |  | concrete strength correct as per design (attach photo of concrete docket)
|  | All Concrete Dockets Attached | All Concrete Dockets Attached | concrete strength correct as per design (attach photo of concrete docket)
|  | Placement method correct (Attach any relevant photos) |  | placement method correct (attach any relevant photos)
|  | Date item was cast | Date item was cast | placement method correct (attach any relevant photos)
|  | Lifters Location Checked and approved |  | lifters location checked and approved
|  | Visual Check - Specified finish achieved |  | visual check - specified finish achieved
|  | U3 | U3 | visual check - specified finish achieved
|  | F5 | F5 | visual check - specified finish achieved
|  | Broom | Broom | visual check - specified finish achieved
|  | Exposed | Exposed | visual check - specified finish achieved
|  | Other finish (if applicable) specified here | Other finish (if applicable) specified here | visual check - specified finish achieved
|  | Post Pour Works Completed |  | post pour works completed
|  | Chamfers | Chamfers | post pour works completed
|  | Openings (formwork removed) | Openings (formwork removed) | post pour works completed
|  | Nail Plates Removed | Nail Plates Removed | post pour works completed
|  | Lifter Recesses Removed | Lifter Recesses Removed | post pour works completed
|  | Starter Bars Checked and Correct | Starter Bars Checked and Correct | post pour works completed
|  | Weld Plates Cleaned | Weld Plates Cleaned | post pour works completed
|  | RB Couplers Cleaned | RB Couplers Cleaned | post pour works completed
|  | TIM Inserts Cleaned | TIM Inserts Cleaned | post pour works completed
|  | RB Grout Sleeves Cleaned | RB Grout Sleeves Cleaned | post pour works completed
|  | Dross Bach Holes Drilled | Dross Bach Holes Drilled | post pour works completed
|  | Any Strongbacks Installed where required |  | any strongbacks installed where required
|  | Defects identified and photographed and remedial work completed (if required) |  | defects identified and photographed and remedial work completed (if required)
|  | All Post Pour Works complete - Item Checked, Approved and Ready for stacking |  | all post pour works complete - item checked, approved and ready for stacking
Precast Stairs - Overall Progress (869-S01 to 869-S09)
| Scope |  |  | Precast Manufacture | Precast Stairs
Rows
|  | 869-S01 to 869-S09 | dynamic | 869-S01 to 869-S09 | Precast Stairs
Columns
|  | Details |  | Details
|  | Pre-pour QA |  | Pre-pour QA
|  | Pour QA |  | Pour QA
|  | Post pour/Pre delivery QA |  | Post pour/Pre delivery QA
|  | Rebound Hammer Readings/Product Damage Notification |  | Rebound Hammer Readings/Product Damage Notification
Precast Stairs - Detailed Progress (869-S01 to 869-S09)
| Scope |  |  | Precast Manufacture | Precast Stairs
Rows
|  | 869-S01 to 869-S09 | dynamic | 869-S01 to 869-S09 | Precast Stairs
Columns
|  | Photograph/Upload of latest drawing attached (Office PM) |  | Photograph/Upload of latest drawing attached (Office PM) | Details
|  | Drawing # | Drawing # | Photograph/Upload of latest drawing attached (Office PM) | Details
|  | Revision # | Revision # | Photograph/Upload of latest drawing attached (Office PM) | Details
|  | Formwork Fixed Correctly |  | Formwork Fixed Correctly | Pre-pour QA
|  | Mould clean |  | Mould clean | Pre-pour QA
|  | Release oil applied correctly |  | Release oil applied correctly | Pre-pour QA
|  | Primary dimensions checked |  | Primary dimensions checked | Pre-pour QA
|  | Length | Length | Primary dimensions checked | Pre-pour QA
|  | Width | Width | Primary dimensions checked | Pre-pour QA
|  | Thickness | Thickness | Primary dimensions checked | Pre-pour QA
|  | Diagonal dimensions checked |  | Diagonal dimensions checked | Pre-pour QA
|  | Openings Checked & Correct |  | Openings Checked and Correct | Pre-pour QA
|  | size | size | Openings Checked and Correct | Pre-pour QA
|  | location | location | Openings Checked and Correct | Pre-pour QA
|  | orientation | orientation | Openings Checked and Correct | Pre-pour QA
|  | Rebates Installed Correctly |  | Rebates Installed Correctly | Pre-pour QA
|  | Formwork chamfers installed correctly where required |  | Formwork chamfers installed correctly where required | Pre-pour QA
|  | Reinforcing placed correctly, checked & approved |  | Reinforcing placed correctly, checked and approved | Pre-pour QA
|  | Correct Size & Type | Correct Size and Type | Reinforcing placed correctly, checked and approved | Pre-pour QA
|  | Laps & Splices correct | Laps and Splices correct | Reinforcing placed correctly, checked and approved | Pre-pour QA
|  | Cover Checked | Cover Checked | Reinforcing placed correctly, checked and approved | Pre-pour QA
|  | Spacing Checked | Spacing Checked | Reinforcing placed correctly, checked and approved | Pre-pour QA
|  | Cast in items checked, correct (size & location |  | Cast in items checked, correct (size and location | Pre-pour QA
|  | Weld Plates | Weld Plates | Cast in items checked, correct (size and location | Pre-pour QA
|  | Drossbach | Drossbach | Cast in items checked, correct (size and location | Pre-pour QA
|  | PS Voids | PS Voids | Cast in items checked, correct (size and location | Pre-pour QA
|  | TIM Inserts | TIM Inserts | Cast in items checked, correct (size and location | Pre-pour QA
|  | RB Coupler(s) | RB Coupler(s) | Cast in items checked, correct (size and location | Pre-pour QA
|  | Other cast in items checked (if any) | Other cast in items checked (if any) | Cast in items checked, correct (size and location | Pre-pour QA
|  | Starter Bars inserted, checked & correct |  | Starter Bars inserted, checked and correct | Pre-pour QA
|  | Size | Size | Starter Bars inserted, checked and correct | Pre-pour QA
|  | Location | Location | Starter Bars inserted, checked and correct | Pre-pour QA
|  | Spacing | Spacing | Starter Bars inserted, checked and correct | Pre-pour QA
|  | Lifting Items inserted, checked & correct |  | Lifting Items inserted, checked and correct | Pre-pour QA
|  | Size | Size | Lifting Items inserted, checked and correct | Pre-pour QA
|  | Location | Location | Lifting Items inserted, checked and correct | Pre-pour QA
|  | Pre-Pour checks completed & approval given to pour stairs |  | Pre-Pour checks completed and approval given to pour stairs | Pre-pour QA
|  | Concrete Strength correct as per design |  | Concrete Strength correct as per design (Attach photo of concrete docket) | Pour QA
|  | All Concrete Dockets Attached | All Concrete Dockets Attached | Concrete Strength correct as per design (Attach photo of concrete docket) | Pour QA
|  | Placement method correct |  | Placement method correct (Attach any relevant photos) | Pour QA
|  | Date item was cast | Date item was cast | Placement method correct (Attach any relevant photos) | Pour QA
|  | Lifters Location Checked & approved |  | Lifters Location Checked and approved | Post pour/Pre delivery QA
|  | Visual Check - Specified finish achieved |  | Visual Check - Specified finish achieved | Post pour/Pre delivery QA
|  | U3 | U3 | Visual Check - Specified finish achieved | Post pour/Pre delivery QA
|  | F5 | F5 | Visual Check - Specified finish achieved | Post pour/Pre delivery QA
|  | Broom | Broom | Visual Check - Specified finish achieved | Post pour/Pre delivery QA
|  | Exposed | Exposed | Visual Check - Specified finish achieved | Post pour/Pre delivery QA
|  | Other finish (if applicable) specified here | Other finish (if applicable) specified here | Visual Check - Specified finish achieved | Post pour/Pre delivery QA
|  | Post Pour Works Completed |  | Post Pour Works Completed | Post pour/Pre delivery QA
|  | Chamfers | Chamfers | Post Pour Works Completed | Post pour/Pre delivery QA
|  | Openings (formwork removed) | Openings (formwork removed) | Post Pour Works Completed | Post pour/Pre delivery QA
|  | Nail Plates Removed | Nail Plates Removed | Post Pour Works Completed | Post pour/Pre delivery QA
|  | Lifter Recesses Removed | Lifter Recesses Removed | Post Pour Works Completed | Post pour/Pre delivery QA
|  | Starter Bars Checked & Correct | Starter Bars Checked and Correct | Post Pour Works Completed | Post pour/Pre delivery QA
|  | Weld Plates Cleaned | Weld Plates Cleaned | Post Pour Works Completed | Post pour/Pre delivery QA
|  | RB Couplers Cleaned | RB Couplers Cleaned | Post Pour Works Completed | Post pour/Pre delivery QA
|  | TIM Inserts Cleaned | TIM Inserts Cleaned | Post Pour Works Completed | Post pour/Pre delivery QA
|  | RB Grout Sleeves Cleaned | RB Grout Sleeves Cleaned | Post Pour Works Completed | Post pour/Pre delivery QA
|  | Dross Bach Holes Drilled | Dross Bach Holes Drilled | Post Pour Works Completed | Post pour/Pre delivery QA
|  | Any Strongbacks Installed where required |  | Any Strongbacks Installed where required | Post pour/Pre delivery QA
|  | Defects identified & photographed & remedial work completed |  | Defects identified and photographed and remedial work completed (if required) | Post pour/Pre delivery QA
|  | Rigging set up for demoulding followed as per drawing |  | Rigging set up for demoulding followed as per drawing | Post pour/Pre delivery QA
|  | REBOUND Hammer Readings: |  | REBOUND Hammer Readings: | Rebound Hammer Readings/Product Damage Notification
|  | 1 | 1 | REBOUND Hammer Readings: | Rebound Hammer Readings/Product Damage Notification
|  | 2 | 2 | REBOUND Hammer Readings: | Rebound Hammer Readings/Product Damage Notification
|  | 3 | 3 | REBOUND Hammer Readings: | Rebound Hammer Readings/Product Damage Notification
|  | 4 | 4 | REBOUND Hammer Readings: | Rebound Hammer Readings/Product Damage Notification
|  | 5 | 5 | REBOUND Hammer Readings: | Rebound Hammer Readings/Product Damage Notification
|  | 6 | 6 | REBOUND Hammer Readings: | Rebound Hammer Readings/Product Damage Notification
|  | 7 | 7 | REBOUND Hammer Readings: | Rebound Hammer Readings/Product Damage Notification
|  | 8 | 8 | REBOUND Hammer Readings: | Rebound Hammer Readings/Product Damage Notification
|  | 9 | 9 | REBOUND Hammer Readings: | Rebound Hammer Readings/Product Damage Notification
|  | 10 | 10 | REBOUND Hammer Readings: | Rebound Hammer Readings/Product Damage Notification
|  | Avg | Avg | REBOUND Hammer Readings: | Rebound Hammer Readings/Product Damage Notification
|  | Converted Strength: | Converted Strength: | REBOUND Hammer Readings: | Rebound Hammer Readings/Product Damage Notification
|  | Checked by: | Checked by: | REBOUND Hammer Readings: | Rebound Hammer Readings/Product Damage Notification
|  | Approved by: | Approved by: | REBOUND Hammer Readings: | Rebound Hammer Readings/Product Damage Notification
|  | Lifted by: | Lifted by: | REBOUND Hammer Readings: | Rebound Hammer Readings/Product Damage Notification
|  | Product Damage Notification |  | Product Damage Notification | Rebound Hammer Readings/Product Damage Notification
|  | Damage? | Damage? | Product Damage Notification | Rebound Hammer Readings/Product Damage Notification
|  | Damage Type: | Damage Type: | Product Damage Notification | Rebound Hammer Readings/Product Damage Notification
|  | Storage Location: | Storage Location: | Product Damage Notification | Rebound Hammer Readings/Product Damage Notification
|  | Notified by: | Notified by: | ILLUSTRATION: | Rebound Hammer Readings/Product Damage Notification
|  | Date: | Date: | ILLUSTRATION: | Rebound Hammer Readings/Product Damage Notification