## ITP-CIV-RSS Walls
ConQA Team Notes:
Document Title: |  | ITP-012STR-RSS Wall-Main
ITP Description: |  | RSS Wall-Main
Discipline (e.g. CIV/STR/RAIL: |  | STR
Revision Number: |  | 0
Revision Date: |  | 19/12/2022
ITP created by: |  | Victor Mira
ITP approved for use by: |  | Victor Mira
Special Notes to ConQA Team : |  | ITP to be available for Camms Road Project Only
Inspection & Test Plan - insert description here
[9 empty] | Revision: | 0
[9 empty] | Date: | 19/12/2022
Legend: HP: Hold Point, HP* Internal Hold Point, WP: Witness Point, IP: Inspection Point, SP: Surveillance Point
Item | Task/Activity Description | Reference | Acceptance Criteria | Inspection / Test |  |  | Responsibility | Verifying Documents | Date Completed | Sign-off
|  |  |  | Method | Frequency | Category
1 | Referenced Documentation
1.1 | Non Dependent | VicRoads Section 682 November 2018 | N/A | N/A | N/A | N/A | N/A | N/A | NA | N/A
1.2 | Non Dependent | VicRoads Section 204 December 2015 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
1.3 | Non Dependent | IFC drawings |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A
2 | Preliminaries-Materials
2.1 | Concrete-Leveling Pad | IFC drawings | CONCRETE COMPRESSIVE STRENGTH GRADE MUST NOT BE LESS THAN N25 FOR LEVELLING COURSE AND BACKING BLOCKS; [Free text]: Reference: Teambinder MA number: | Document Review | Each element | HP* | PE/Nominated Authority | Material approval
2.2 | Select fill | IFC Drawings | Select fill shall comply with the requirements of the RSS designer: UNIT WEIGHT: 22 ± 2 kN/m³ INTERNAL FRICTION ANGLE ≥ 34.5° Gradation: 150mm : 100% PASSING 37.5mm : 60 TO 100% PASSING 9.5mm : 25 TO 100% PASSING 2.36mm : 15 TO 100% PASSING 0.6mm : 10 TO 100% PASSING 0.075mm : 0 TO 15% PASSING Electrochemical Properties: RESISTIVITY >1000 Ω-cm CHLORIDES <200 mg/kg SULPHATES <200 mg/kg ORGANIC CONTENT 0% Structural Properties: COEFFICIENT OF UNIFORMITY ≥ 5 LIQUID LIMIT ≤ 30% PLASTICITY INDEX ≤ 12 The select backfill must meet the minimum requirements of Vicroads Type A filling [Free textx]: Reference: Material approval in Teambinder | Document Review | Each material specification | HP | Nominated Authority | Material approval
2.3 | General fill | IFC Drawings | Backfill behind the reinforced block shall be Vicroads Type B or better and: pH > 5.5 CHLORIDES < 2000 mg/kg SULPHATES < 1000 mg/kg Reference: Material approval in Teambinder | Document Review | Each material specification | HP | Nominated Authority | Material approval
2.4 | Perforated Pipe-material | IFC Drawings | Perforated plastic pipe perforations shall be a maximum width of 1.5mm and minimum length of 150mm per m2 Reference: Teambinder MA number: | Document review Measure | Each wall | HP | Nominated Authority | Material approval
3 | Preliminaries-Documents
3.1 | RSS Panels | IFC drawings | Precast supplier is required to provide the following Quality Assurance documentation for each element, typically this consists of: i. Certificate of Compliance / Birth Certificate - 1. Concrete strength; - 2.Date of manufacture; - 3.Unique Identification number; - 4.Mass; - 5.Confirmation of number, type and capacity of lifting inserts; - 6.Quality assurance sign-off. ii. Compressive strength test results iii. Precast Lifting Design iv. Pre-pour check sheet / ITP v. Post-pour check sheet / ITP vi. Covermeter check record vii. Record of dimensional measurements Collate: Precast Quality Assurance Documentation so it can be uploaded into Teambinder pre-cast supply Lot (don't attach it here) [Free text]: Reference: Precast panels MDR Lot in TeamBinder: | Document Review | Once for each type of panels | IP | PE | Precast panels Birth certificates and MDR Lot
4 | Pre-Construction Activities
4.1 | Foundation | IFC Drawings | The foundation material beneath the RSS fill shall be inspected on site by a qualified geotechnical Engineerto ensure that the soil conditions meet the assumed material properties: Description: Stiff Clay or better Unit Weight: 18 kN/m3 Effective friction angle: 28° Effective Cohession: 5 kPa Undrained cohesion: 80 kPa | Test Document Review Visual | Each retaining Wall | HP* | PE/Geotechnical Engineer | This ITP Test results
4.2 | Foundation | IFC Drawings MRO-052-C-SME-DRG-32-MPK-CSW-2053 | Where the foundation material does not meet the assumed material parameters, the existing ground shall be replaced with VR Type A fill Compacted in accordance with VR 204 - Ground improvement works shall be keyed into surrounding material at minimum 200mm Bench width - Ground improvement works shall extend beyond either side of bridge approach to detail show in IFC drawing | Visual | Each retaining wall | IP | PE/Geotechnical Engineer | This ITP
4.3 | Foundation | IFC Drawings | It is the rsponsibility of the Geotech engineer to determine that the bearing bearing capacity is adequate | Visual | Each retaining Wall | HP | Geotechnical Engineer | Geotechnical Engineer Sign off this ITP
4.4 | Foundation | VR 204.12 VR 204.11 | areas upon which fills are to be constructed shall be test rolled in accordance with VR 173 No Fill shall be placed against or within 3 meters of a structure until the foundation for the fill has been reviewed by the superintendant | Visual | Each retaining Wall | HP | PE/Niminated Authority | This ITP
4.5 | Levelling Pad-Survey Set out | IFC Drawings VR 682.20 MRP-052-C-RFL-DRG-33-CBE-CSW-1201 MRP-052-C-RFL-DRG-33-CBE-CSW-1202 MRP-052-C-RFL-DRG-33-CBE-CSW-1203 MRP-052-C-RFL-DRG-33-CBE-CSW-1204 | Survey activities to be undertaken to ensure and validate that all Works meet level and location requirements within the tolerances as per the tables in IFC Drawings and Vicroads Specification | Measure Visual | Each retaining Wall | IP | Surveyor SE/PE | This ITP
5 | Construction / Installation Activities
5.1 | Form Levelling pad | IFC Drawings MRP-052-C-RFL-DRG-33-CBE-CSW-1201 MRP-052-C-RFL-DRG-33-CBE-CSW-1202 MRP-052-C-RFL-DRG-33-CBE-CSW-1203 MRP-052-C-RFL-DRG-33-CBE-CSW-1204 | Form timber shutters to edge of levelling pad - Levelling pad is a 500mm wide by 150mm thick unreinforced concrete footing - The leveling course level shall NOT deviate from the specified level by mor than ±3mm. - 20mm Nominal gap between levelling pad and adjacent ground beam is to be maintained | Measure Visual | Each Lot | IP | SE/Site Supervisor | This ITP
5.2 | Leveling Pad Concrete Pour | IFC Drawings | Concrete to be placed in accordance with 610. Attach: Concrete Delivery Docket | Visual | Each Lot | IP | SE/Site Supervisor | Concrete Pour record
5.3 | Leveling Pad Concrete Testing | IFC Drawings | Concrete testing for compressive strength shall be undertaken at the testing frequency specified in VicRoads Section 610.16 (b) Attache: Concrete test report | Document Review | Each Lot | IP | PE | Attach Concrete Test Report
5.4 | Levelling Pad-Post Pour Survey-Levelling Course | IFC Drawings MRP-052-C-RFL-DRG-33-CBE-CSW-1201 MRP-052-C-RFL-DRG-33-CBE-CSW-1202 MRP-052-C-RFL-DRG-33-CBE-CSW-1203 MRP-052-C-RFL-DRG-33-CBE-CSW-1204 | - Levelling course level shall not deviate from the specified level by more than ±3mm - Plan position shown on the drawings at the base of the wall shall not exceed ±15mm (refer to drawings for WP locations) | Measure Visual | Each retaining Wall | IP | PE/Surveyor | Attach Survey Report
5.5 | Levelling Pad-Backfill commencement | VR 204.11 | No material shall be placed against concrete within 14 days of casting | Document review | Each retaining Wall | HP | Nominated Authority | This ITP
5.6 | Wall Panels Installation | 682.17 | The level and alignment of each course of facing panels shall be checked progressively after placement of each course and prior to placement of the next course to ensure compliance with the dimensional and positional tolerances stated in the design. The Contractor shall record the results of this checking together with details of any non-conformances and the associated corrective actions Refer to checklist for each course of panels Attach: Lot map | Visual Measure | Each course of facing panel | HP* | PE/SE | Inspection record checklist: CHK-CIV-RSS Pre-cast panel installation
5.7 | Drainage-Wall | IFC Drawings MRP-052-C-SME-DRG-32-MPK-CSW-2053 | 300mmx300mmGranular backfill in Geotextile BIDIM A64 around 100mm Dia. Perforted plastic pipewith 0.5%min fall to 50mm Dia weepholesin RSS panels. | Visual | Each wall | IP | PE/SE | This ITP
5.8 | Fill | 682.16 | The Contractor shall submit compaction test results for each layer of fill placement to the Superintendent for review and acceptance. No further fill placement shall be allowed if the total thickness of fill placement is greater than 1 m measured from the last layer that has been accepted. If any layer is found to be not in compliance with the compaction requirement, that layer and the layers above it shall be removed. Refer to checklist for each fill layer - Attach: Lot map | Visual Test Measure | Each layaer of fill | HP* | PE/SE | Inspection record checklist: CHK-CIV-RSS Fill installation
6 | Post-construction / Post-installation Activities
6.1 | As-built Survey | MRPA Quality Management Plan | Provide record of dimensional measurements to demonstrate that all Works meet level and location requirements within the tolerances Attach: Survey As-built / Survey Report | Document Review | Each element | IP | Surveyor SE/PE/SPE | Survey Report
6.2 | Wall Post construction monitoring | VR 682.20 VR 682.21 | . The Contractor shall take measurements of the position of the RSS at the points defined in clause 682.20(a) to (f) at intervals not exceeding one month for the first six months immediately following completion of the RSS and at intervals not exceeding six months thereafter until the end of the Defects Liability Period. a) plan position shown on the drawings, at base of wall shall not exceed 15 mm; (b) relative displacement of adjoining smooth panel faces shall not exceed 15 mm measured normal to face of wall; (c) local deviation of the wall face measured at any location with a 3 m straight edge shall not exceed 15 mm; (d) the tolerance on position measured at the top of the wall face shall not exceed 5 mm per 1 metre of wall height; (e) the wall level shall not deviate from the specified level by more than 20 mm; (f) variation in gap width between facing panels shall not exceed 5 mm per metre length and 10 mm over the full length of the gap. The measurements shall be recorded in writing and reported to the Superintendent within two weeks of the survey. | Measure Survey | Each wall | IP
6.3 | Non-conformance Report (NCR) Closure | MRPA Quality Management Plan | Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed. | Document Review | Once, prior to closure of this lot / element / Work area | HP* | SE/PE/SPE | This ITP
Final Inspection
On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
Print Name: Position: Signature: Date: / /