## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | ITP-012-STR-RSS Wall-Main | itp |  |  |  |  | ITP-012-STR-RSS Wall-Main Rev 0
section | Referenced Documentation
checkpoint | Referenced Documentation
note | Document Title: ITP-012-STR-RSS Wall-Main
note | ITP Description: RSS Wall-Main
note | Document Number (in Teambinder): MRP-0000-MRPA-ALT-ITP-00XX
note | Discipline (e.g. CIV/STR/RAIL): STR
note | Revision Number: 0
note | Revision Date: 19/12/2022
note | ITP created by: Victor Mira
note | ITP approved for use by: Victor Mira
note | 1.1 Non Dependent
note | Reference: VicRoads Section 682 November 2018
note | 1.2 Non Dependent
note | Reference: VicRoads Section 204 December 2015
note | 1.3 Non Dependent
note | Reference: IFC drawings
section | Preliminaries-Materials
checkpoint | 2.1 Concrete-Leveling Pad
note | REFERENCE: IFC drawings
note | – – – – – – – – – – – – – – – – –
note | ACCEPTANCE CRITERIA:
note | CONCRETE COMPRESSIVE STRENGTH GRADE MUST NOT BE LESS THAN N25 FOR LEVELLING COURSE AND BACKING BLOCKS;
textbox | Reference: Teambinder MA number:
note | – – – – – – – – – – – – – – – – –
note | METHOD: Document Review
note | – – – – – – – – – – – – – – – – –
note | FREQUENCY: Each element
note | – – – – – – – – – – – – – – – – –
note | CATEGORY: HP*
note | – – – – – – – – – – – – – – – – –
note | RESPONSIBILITY: PE/Nominated Authority
note | – – – – – – – – – – – – – – – – –
note | VERIFYING DOCUMENTS: Material approval
textbox | Date Completed:
checkpoint | 2.2 Select fill
note | REFERENCE: IFC Drawings
note | – – – – – – – – – – – – – – – – –
note | ACCEPTANCE CRITERIA:
note | Select fill shall comply with the requirements of the RSS designer:
note | UNIT WEIGHT: 22 ± 2 kN/m³
note | INTERNAL FRICTION ANGLE ≥ 34.5°
note | ○ Gradation:
note | • 150mm : 100% PASSING
note | • 37.5mm : 60 TO 100% PASSING
note | • 9.5mm : 25 TO 100% PASSING
note | • 2.36mm : 15 TO 100% PASSING
note | • 0.6mm : 10 TO 100% PASSING
note | • 0.075mm : 0 TO 15% PASSING
note | ○ Electrochemical Properties:
note | • RESISTIVITY >1000 Ω-cm
note | • CHLORIDES <200 mg/kg
note | • SULPHATES <200 mg/kg
note | • ORGANIC CONTENT 0%
note | ○ Structural Properties:
note | • COEFFICIENT OF UNIFORMITY ≥ 5
note | • LIQUID LIMIT ≤ 30%
note | • PLASTICITY INDEX ≤ 12
note | ○ The select backfill must meet the minimum requirements of Vicroads Type A filling
textbox | Reference: Material approval in Teambinder
note | – – – – – – – – – – – – – – – – –
note | METHOD: Document Review
note | – – – – – – – – – – – – – – – – –
note | FREQUENCY: Each material specification
note | – – – – – – – – – – – – – – – – –
note | CATEGORY: HP
note | – – – – – – – – – – – – – – – – –
note | RESPONSIBILITY: Nominated Authority
note | – – – – – – – – – – – – – – – – –
note | VERIFYING DOCUMENTS: Material approval
textbox | Date Completed:
holdpoint | NOMINATED AUTHORITY HOLDPOINT
checkpoint | 2.3 General fill
note | REFERENCE: IFC Drawings
note | – – – – – – – – – – – – – – – – –
note | ACCEPTANCE CRITERIA:
note | Backfill behind the reinforced block shall be Vicroads Type B or better and:
note | • pH > 5.5
note | • CHLORIDES < 2000 mg/kg
note | • SULPHATES < 1000 mg/kg
textbox | Reference: Material approval in Teambinder
note | – – – – – – – – – – – – – – – – –
note | METHOD: Document Review
note | – – – – – – – – – – – – – – – – –
note | FREQUENCY: Each material specification
note | – – – – – – – – – – – – – – – – –
note | CATEGORY: HP
note | – – – – – – – – – – – – – – – – –
note | RESPONSIBILITY: Nominated Authority
note | – – – – – – – – – – – – – – – – –
note | VERIFYING DOCUMENTS: Material approval
textbox | Date Completed:
holdpoint | NOMINATED AUTHORITY HOLDPOINT
checkpoint | 2.4 Perforated Pipe-material
note | REFERENCE: IFC Drawings
note | – – – – – – – – – – – – – – – – –
note | ACCEPTANCE CRITERIA:
note | Perforated plastic pipe perforations shall be a maximum width of 1.5mm and minimum length of 150mm per m2
textbox | Reference: Teambinder MA number:
note | – – – – – – – – – – – – – – – – –
note | METHOD: Document review, Measure
note | – – – – – – – – – – – – – – – – –
note | FREQUENCY: Each wall
note | – – – – – – – – – – – – – – – – –
note | CATEGORY: HP
note | – – – – – – – – – – – – – – – – –
note | RESPONSIBILITY: Nominated Authority
note | – – – – – – – – – – – – – – – – –
note | VERIFYING DOCUMENTS: Material approval
textbox | Date Completed:
holdpoint | NOMINATED AUTHORITY HOLDPOINT
section | Preliminaries-Documents
checkpoint | 3.1 RSS Panels
note | REFERENCE: IFC drawings
note | – – – – – – – – – – – – – – – – –
note | ACCEPTANCE CRITERIA:
note | Precast supplier is required to provide the following Quality Assurance documentation for each element, typically this consists of:
note | i. Certificate of Compliance / Birth Certificate
note | – 1. Concrete strength;
note | – 2.Date of manufacture;
note | – 3.Unique Identification number;
note | – 4.Mass;
note | – 5.Confirmation of number, type and capacity of lifting inserts;
note | – 6.Quality assurance sign-off.
note | ii. Compressive strength test results
note | iii. Precast Lifting Design
note | iv. Pre-pour check sheet / ITP
note | v. Post-pour check sheet / ITP
note | vi. Covermeter check record
note | vii. Record of dimensional measurements
note | Collate: Precast Quality Assurance Documentation so it can be uploaded into Teambinder pre-cast supply Lot (don't attach it here)
textbox | Reference: Precast panels MDR Lot in TeamBinder:
note | – – – – – – – – – – – – – – – – –
note | METHOD: Document Review
note | – – – – – – – – – – – – – – – – –
note | FREQUENCY: Once for each type of panels
note | – – – – – – – – – – – – – – – – –
note | CATEGORY: IP
note | – – – – – – – – – – – – – – – – –
note | RESPONSIBILITY: PE
note | – – – – – – – – – – – – – – – – –
note | VERIFYING DOCUMENTS: Precast panels Birth certificates and MDR Lot
textbox | Date Completed:
section | Pre-Construction Activities
checkpoint | 4.1 Foundation
note | REFERENCE: IFC Drawings
note | – – – – – – – – – – – – – – – – –
note | ACCEPTANCE CRITERIA:
note | The foundation material beneath the RSS fill shall be inspected on site by a qualified geotechnical Engineerto ensure that the soil conditions meet the assumed material properties:
note | • Description: Stiff Clay or better
note | • Unit Weight: 18 kN/m3
note | • Effective friction angle: 28°
note | • Effective Cohession: 5 kPa
note | • Undrained cohesion: 80 kPa
note | – – – – – – – – – – – – – – – – –
note | METHOD: Test, Document Review, Visual
note | – – – – – – – – – – – – – – – – –
note | FREQUENCY: Each retaining Wall
note | – – – – – – – – – – – – – – – – –
note | CATEGORY: HP*
note | – – – – – – – – – – – – – – – – –
note | RESPONSIBILITY: PE/Geotechnical Engineer
note | – – – – – – – – – – – – – – – – –
note | VERIFYING DOCUMENTS: This ITP, Test results
textbox | Date Completed:
checkpoint | 4.2 Foundation
note | REFERENCE:
note | • IFC Drawings
note | • MRO-052-C-SME-DRG-32-MPK-CSW-2053
note | – – – – – – – – – – – – – – – – –
note | ACCEPTANCE CRITERIA:
note | Where the foundation material does not meet the assumed material parameters, the existing ground shall be replaced with VR Type A fill Compacted in accordance with VR 204
note | – Ground improvement works shall be keyed into surrounding material at minimum 200mm Bench width
note | – Ground improvement works shall extend beyond either side of bridge approach to detail show in IFC drawing
note | – – – – – – – – – – – – – – – – –
note | METHOD: Visual
note | – – – – – – – – – – – – – – – – –
note | FREQUENCY: Each retaining wall
note | – – – – – – – – – – – – – – – – –
note | CATEGORY: IP
note | – – – – – – – – – – – – – – – – –
note | RESPONSIBILITY: PE/Geotechnical Engineer
note | – – – – – – – – – – – – – – – – –
note | VERIFYING DOCUMENTS: This ITP
textbox | Date Completed:
checkpoint | 4.3 Foundation
note | REFERENCE: IFC Drawings
note | – – – – – – – – – – – – – – – – –
note | ACCEPTANCE CRITERIA: It is the rsponsibility of the Geotech engineer to determine that the bearing bearing capacity is adequate
note | – – – – – – – – – – – – – – – – –
note | METHOD: Visual
note | – – – – – – – – – – – – – – – – –
note | FREQUENCY: Each retaining Wall
note | – – – – – – – – – – – – – – – – –
note | CATEGORY: HP
note | – – – – – – – – – – – – – – – – –
note | RESPONSIBILITY: Geotechnical Engineer
note | – – – – – – – – – – – – – – – – –
note | VERIFYING DOCUMENTS: Geotechnical Engineer Sign off this ITP
textbox | Date Completed:
holdpoint | NOMINATED AUTHORITY HOLDPOINT
checkpoint | 4.4 Foundation
note | REFERENCE:
note | • VR 204.12
note | • VR 204.11
note | – – – – – – – – – – – – – – – – –
note | ACCEPTANCE CRITERIA:
note | • Areas upon which fills are to be constructed shall be test rolled in accordance with VR 173
note | • No Fill shall be placed against or within 3 meters of a structure until the foundation for the fill has been reviewed by the superintendant
note | – – – – – – – – – – – – – – – – –
note | METHOD: Visual
note | – – – – – – – – – – – – – – – – –
note | FREQUENCY: Each retaining Wall
note | – – – – – – – – – – – – – – – – –
note | CATEGORY: HP
note | – – – – – – – – – – – – – – – – –
note | RESPONSIBILITY: PE/Nominated Authority
note | – – – – – – – – – – – – – – – – –
note | VERIFYING DOCUMENTS: This ITP
textbox | Date Completed:
holdpoint | NOMINATED AUTHORITY HOLDPOINT
checkpoint | 4.5 Levelling Pad-Survey Set out
note | REFERENCE:
note | • IFC Drawings
note | • VR 682.20
note | • MRP-052-C-RFL-DRG-33-CBE-CSW-1201
note | • MRP-052-C-RFL-DRG-33-CBE-CSW-1202
note | • MRP-052-C-RFL-DRG-33-CBE-CSW-1203
note | • MRP-052-C-RFL-DRG-33-CBE-CSW-1204
note | – – – – – – – – – – – – – – – – –
note | ACCEPTANCE CRITERIA: Survey activities to be undertaken to ensure and validate that all Works meet level and location requirements within the tolerances as per the tables in IFC Drawings and Vicroads Specification
note | – – – – – – – – – – – – – – – – –
note | METHOD: Measure, Visual
note | – – – – – – – – – – – – – – – – –
note | FREQUENCY: Each retaining Wall
note | – – – – – – – – – – – – – – – – –
note | CATEGORY: IP
note | – – – – – – – – – – – – – – – – –
note | RESPONSIBILITY: Surveyor, SE/PE
note | – – – – – – – – – – – – – – – – –
note | VERIFYING DOCUMENTS: This ITP
textbox | Date Completed:
section | Construction / Installation Activities
checkpoint | 5.1 Form Levelling pad
note | REFERENCE:
note | • IFC Drawings
note | • MRP-052-C-RFL-DRG-33-CBE-CSW-1201
note | • MRP-052-C-RFL-DRG-33-CBE-CSW-1202
note | • MRP-052-C-RFL-DRG-33-CBE-CSW-1203
note | • MRP-052-C-RFL-DRG-33-CBE-CSW-1204
note | – – – – – – – – – – – – – – – – –
note | ACCEPTANCE CRITERIA:
note | Form timber shutters to edge of levelling pad
note | – Levelling pad is a 500mm wide by 150mm thick unreinforced concrete footing
note | – The leveling course level shall NOT deviate from the specified level by mor than ±3mm.
note | – 20mm Nominal gap between levelling pad and adjacent ground beam is to be maintained
note | – – – – – – – – – – – – – – – – –
note | METHOD: Measure, Visual
note | – – – – – – – – – – – – – – – – –
note | FREQUENCY: Each Lot
note | – – – – – – – – – – – – – – – – –
note | CATEGORY: IP
note | – – – – – – – – – – – – – – – – –
note | RESPONSIBILITY: SE/Site Supervisor
note | – – – – – – – – – – – – – – – – –
note | VERIFYING DOCUMENTS: This ITP
textbox | Date Completed:
checkpoint | 5.2 Leveling Pad Concrete Pour
note | REFERENCE: IFC Drawings
note | – – – – – – – – – – – – – – – – –
note | ACCEPTANCE CRITERIA:
note | Concrete to be placed in accordance with 610.
note | Attach: Concrete Delivery Docket
note | – – – – – – – – – – – – – – – – –
note | METHOD: Visual
note | – – – – – – – – – – – – – – – – –
note | FREQUENCY: Each Lot
note | – – – – – – – – – – – – – – – – –
note | CATEGORY: IP
note | – – – – – – – – – – – – – – – – –
note | RESPONSIBILITY: SE/Site Supervisor
note | – – – – – – – – – – – – – – – – –
note | VERIFYING DOCUMENTS: Concrete Pour record
textbox | Date Completed:
checkpoint | 5.3 Leveling Pad Concrete Testing
note | REFERENCE: IFC Drawings
note | – – – – – – – – – – – – – – – – –
note | ACCEPTANCE CRITERIA:
note | Concrete testing for compressive strength shall be undertaken at the testing frequency specified in VicRoads Section 610.16 (b)
note | Attach: Concrete test report
note | – – – – – – – – – – – – – – – – –
note | METHOD: Document Review
note | – – – – – – – – – – – – – – – – –
note | FREQUENCY: Each Lot
note | – – – – – – – – – – – – – – – – –
note | CATEGORY: IP
note | – – – – – – – – – – – – – – – – –
note | RESPONSIBILITY: PE
note | – – – – – – – – – – – – – – – – –
note | VERIFYING DOCUMENTS: Attach Concrete Test Report
textbox | Date Completed:
checkpoint | 5.4 Levelling Pad-Post Pour Survey-Levelling Course
note | REFERENCE:
note | • IFC Drawings
note | • MRP-052-C-RFL-DRG-33-CBE-CSW-1201
note | • MRP-052-C-RFL-DRG-33-CBE-CSW-1202
note | • MRP-052-C-RFL-DRG-33-CBE-CSW-1203
note | • MRP-052-C-RFL-DRG-33-CBE-CSW-1204
note | – – – – – – – – – – – – – – – – –
note | ACCEPTANCE CRITERIA:
note | – Levelling course level shall not deviate from the specified level by more than ±3mm
note | – Plan position shown on the drawings at the base of the wall shall not exceed ±15mm (refer to drawings for WP locations)
note | – – – – – – – – – – – – – – – – –
note | METHOD: Measure, Visual
note | – – – – – – – – – – – – – – – – –
note | FREQUENCY: Each retaining Wall
note | – – – – – – – – – – – – – – – – –
note | CATEGORY: IP
note | – – – – – – – – – – – – – – – – –
note | RESPONSIBILITY: PE/Surveyor
note | – – – – – – – – – – – – – – – – –
note | VERIFYING DOCUMENTS: Attach Survey Report
textbox | Date Completed:
checkpoint | 5.5 Levelling Pad-Backfill commencement
note | REFERENCE: VR 204.11
note | – – – – – – – – – – – – – – – – –
note | ACCEPTANCE CRITERIA: No material shall be placed against concrete within 14 days of casting
note | – – – – – – – – – – – – – – – – –
note | METHOD: Document review
note | – – – – – – – – – – – – – – – – –
note | FREQUENCY: Each retaining Wall
note | – – – – – – – – – – – – – – – – –
note | CATEGORY: HP
note | – – – – – – – – – – – – – – – – –
note | RESPONSIBILITY: Nominated Authority
note | – – – – – – – – – – – – – – – – –
note | VERIFYING DOCUMENTS: This ITP
textbox | Date Completed:
holdpoint | NOMINATED AUTHORITY HOLDPOINT
checkpoint | 5.6 Wall Panels Installation
note | REFERENCE: 682.17
note | – – – – – – – – – – – – – – – – –
note | ACCEPTANCE CRITERIA:
note | • The level and alignment of each course of facing panels shall be checked progressively after placement of each course and prior to placement of the next course to ensure compliance with the dimensional and positional tolerances stated in the design.
note | • The Contractor shall record the results of this checking together with details of any non-conformances and the associated corrective actions
note | • Refer to checklist for each course of panels
note | Attach: Lot map
note | – – – – – – – – – – – – – – – – –
note | METHOD: Visual, Measure
note | – – – – – – – – – – – – – – – – –
note | FREQUENCY: Each course of facing panel
note | – – – – – – – – – – – – – – – – –
note | CATEGORY: HP*
note | – – – – – – – – – – – – – – – – –
note | RESPONSIBILITY: PE/SE
note | – – – – – – – – – – – – – – – – –
note | VERIFYING DOCUMENTS: Inspection record checklist: CHK-CIV-RSS Pre-cast panel installation
textbox | Date Completed:
checkpoint | 5.7 Drainage-Wall
note | REFERENCE:
note | • IFC Drawings
note | • MRP-052-C-SME-DRG-32-MPK-CSW-2053
note | – – – – – – – – – – – – – – – – –
note | ACCEPTANCE CRITERIA: 300mmx300mmGranular backfill in Geotextile BIDIM A64 around 100mm Dia. Perforted plastic pipewith 0.5%min fall to 50mm Dia weepholesin RSS panels.
note | – – – – – – – – – – – – – – – – –
note | METHOD: Visual
note | – – – – – – – – – – – – – – – – –
note | FREQUENCY: Each wall
note | – – – – – – – – – – – – – – – – –
note | CATEGORY: IP
note | – – – – – – – – – – – – – – – – –
note | RESPONSIBILITY: PE/SE
note | – – – – – – – – – – – – – – – – –
note | VERIFYING DOCUMENTS: This ITP
textbox | Date Completed:
checkpoint | 5.8 Fill
note | REFERENCE: 682.16
note | – – – – – – – – – – – – – – – – –
note | ACCEPTANCE CRITERIA:
note | • The Contractor shall submit compaction test results for each layer of fill placement to the Superintendent for review and acceptance. No further fill placement shall be allowed if the total thickness of fill placement is greater than 1 m measured from the last layer that has been accepted.
note | • If any layer is found to be not in compliance with the compaction requirement, that layer and the layers above it shall be removed.
note | • Refer to checklist for each fill layer
note | Attach: Lot map
note | – – – – – – – – – – – – – – – – –
note | METHOD: Visual, Test, Measure
note | – – – – – – – – – – – – – – – – –
note | FREQUENCY: Each layer of fill
note | – – – – – – – – – – – – – – – – –
note | CATEGORY: HP*
note | – – – – – – – – – – – – – – – – –
note | RESPONSIBILITY: PE/SE
note | – – – – – – – – – – – – – – – – –
note | VERIFYING DOCUMENTS: Inspection record checklist: CHK-CIV-RSS Fill installation
textbox | Date Completed:
section | Post-construction / Post-installation Activities
checkpoint | 6.1 As-built Survey
note | REFERENCE: MRPA Quality Management Plan
note | – – – – – – – – – – – – – – – – –
note | ACCEPTANCE CRITERIA:
note | Provide record of dimensional measurements to demonstrate that all Works meet level and location requirements within the tolerances
note | Attach: Survey As-built / Survey Report
note | – – – – – – – – – – – – – – – – –
note | METHOD: Document Review
note | – – – – – – – – – – – – – – – – –
note | FREQUENCY: Each element
note | – – – – – – – – – – – – – – – – –
note | CATEGORY: IP
note | – – – – – – – – – – – – – – – – –
note | RESPONSIBILITY: Surveyor, SE/PE/SPE
note | – – – – – – – – – – – – – – – – –
note | VERIFYING DOCUMENTS: Survey Report
textbox | Date Completed:
checkpoint | 6.2 Wall Post construction monitoring
note | REFERENCE:
note | • VR 682.20
note | • VR 682.21
note | – – – – – – – – – – – – – – – – –
note | ACCEPTANCE CRITERIA:
note | The Contractor shall take measurements of the position of the RSS at the points defined in clause 682.20(a) to (f) at intervals not exceeding one month for the first six months immediately following completion of the RSS and at intervals not exceeding six months thereafter until the end of the Defects Liability Period.
note | (a) plan position shown on the drawings, at base of wall shall not exceed ⊕15 mm;
note | (b) relative displacement of adjoining smooth panel faces shall not exceed 15 mm measured normal to face of wall;
note | (c) local deviation of the wall face measured at any location with a 3 m straight edge shall not exceed 15 mm;
note | (d) the tolerance on position measured at the top of the wall face shall not exceed 5 mm per 1 metre of wall height;
note | (e) the wall level shall not deviate from the specified level by more than ⊕20 mm;
note | (f) variation in gap width between facing panels shall not exceed 5 mm per metre length and 10 mm over the full length of the gap.
note | The measurements shall be recorded in writing and reported to the Superintendent within two weeks of the survey.
note | – – – – – – – – – – – – – – – – –
note | METHOD: Measure, Survey
note | – – – – – – – – – – – – – – – – –
note | FREQUENCY: Each wall
note | – – – – – – – – – – – – – – – – –
note | CATEGORY: IP
textbox | Date Completed:
checkpoint | 6.3 Non-conformance Report (NCR) Closure
note | REFERENCE: MRPA Quality Management Plan
note | – – – – – – – – – – – – – – – – –
note | ACCEPTANCE CRITERIA: Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed.
note | – – – – – – – – – – – – – – – – –
note | METHOD: Document Review
note | – – – – – – – – – – – – – – – – –
note | FREQUENCY: Once, prior to closure of this lot / element / Work area
note | – – – – – – – – – – – – – – – – –
note | CATEGORY: HP*
note | – – – – – – – – – – – – – – – – –
note | RESPONSIBILITY: SE/PE/SPE
note | – – – – – – – – – – – – – – – – –
note | VERIFYING DOCUMENTS: This ITP
textbox | Date Completed:
checkpoint | Final Inspection
note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
textbox | Name:
textbox | Position:
textbox | Date Completed:
signoff | Sign ITP