## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-sectioned |  |  | checklist | ITP-CIV-CAMMS-Subgrade Preparation-Road-Rev 0 | itp |  |  |  | Yes | ITP-CIV-CAMMS-Subgrade Preparation-Road-Rev 0 | 056f96e2-dc65-47fe-b608-8999badde738
checkpoint-group |  |  | section | 1 - Referenced Documentation
checkpoint-status |  |  | checkpoint | Referenced Documentation
label | fdd34b50-5bee-5c94-9914-df7b370d3641 |  | note | Document Title: ITP-CIV-CAMMS-Subgrade Preparation - Road
label | ab267e6c-7650-5e93-9dbf-96f5e0bbcc51 |  | note | ITP Description: CAMMS-Subgrade Preparation - Road
label | 764f618d-938d-58f0-99b0-1ca1e9a31b2c |  | note | Discipline (e.g. CIV/STR/RAIL: CIV
label | df31e635-9d41-589d-9265-71b3e6459160 |  | note | Revision Number: 0
label | 2f8fe6df-e5e4-5680-9069-a4cb4de5ada1 |  | note | Revision Date: 18/08/22
label | 6a71a6a5-00a0-5172-9236-b2060d717c38 |  | note | ITP created by: Victor Mira
label | c30e8323-5eef-5d01-92b9-41ad9e8c2443 |  | note | ITP approved for use by: Aldrin Guinchoma
checkpoint-status |  |  | checkpoint | 1.1 - Non Dependent
label | 572cb9d4-49e6-5a9b-a096-1198ec098c1f |  | note | Reference - VicRoads Section 204
checkpoint-status |  |  | checkpoint | 1.2 - Non Dependent
label | d3c18019-2bd6-547b-9265-3b4e03e27f38 |  | note | Reference - VicRoads Section 173
checkpoint-group |  |  | section | 2 - Preliminaries-Materials
checkpoint-status |  |  | checkpoint | 2.1 - Non Dependent
checkpoint-group |  |  | section | 3 - Preliminaries-Documentations
checkpoint-status |  |  | checkpoint | 3.1 - Non Dependent
checkpoint-group |  |  | section | 4 - Pre-construction / Pre-installation Activities
checkpoint-status |  |  | checkpoint | 4.1 - Survey Set-Out
label | 81d017f2-83e0-50ac-8697-820dc8e11a3b |  | note | Reference - IFC Drawings
label | 094d26e4-b1f2-5bc9-a834-dd3bd3011609 |  | note | Acceptance Criteria - Area has been set out in accordance with the drawings
label | a84eb765-f230-59f5-8a8b-c14c3cf72b4c |  | note | ATTACH: LOT MARKED UP LOCATION ON THE IFC DRAWING (LOT MAP):
label | 1c19ea32-8c09-5d3a-8cb0-a152b6fd1d04 |  | note | Method - Verify
label | 9f77a5ca-5bd6-5ff5-a9c3-0c06aa317d44 |  | note | Frequency - Prior to commencement of excavation
label | a04909b2-0a2e-53c3-bdb6-96be987a5234 |  | note | Category - IP
label | 0ac88d0b-9f5b-5473-ba22-909cba1bf212 |  | note | Responsibility - SE/Surveyor
label | 8bcee0a5-9891-55b4-9a27-fb2ae9150c8e |  | note | Verifying Documents - This ITP
text | 708c77af-8ce2-556d-8132-2ea1c35c1356 |  | textbox | Date Completed:
checkpoint-group |  |  | section | 5 - Construction / Installation Activities
checkpoint-status |  |  | checkpoint | 5.1 - Inspection of Subgrade Material-Subgrade Material Properties
label | b6dcd196-318f-5e9e-95f6-528d4e10ebf6 |  | note | Reference - Section 204.06 ( c) Section 204.06 ( e) IFC Drawings
label | 83aae0a6-6b9d-5fec-9da1-d405f9dc08e6 |  | note | Acceptance Criteria - Prior to commencing excavation in any area and during excavation work, the Nominated Authority and the Contractor shall inspect each type of material encountered and subject to verification by appropriate laboratory testing, agree on the category of the material in accordance with Clause 204.04
label | 5441e849-479c-5468-9fc5-7f2571b2728c |  | note | In situ material within 400mm of cut floor level to be consistent with IFC Drawings
label | 47245560-ba28-5f1d-849c-221aa56de566 |  | note | Assigned CBR ≥ 2.5%
label | b53f8812-ed83-5133-9370-65e49b464bf3 |  | note | If parameters are met, rip and recompact to a depth of 150mm.
label | b79a242f-8dfc-5d88-b7cf-86ce8e7b4d3b |  | note | If assumed design parameters not met, remove 400mm of material and replace with conforming Type A fill.
label | cc2a3a72-70dd-5922-95c1-53083222d9d1 |  | note | If existing material needs to be removed and replaced with Type A Fill, ITP-CIV Type A Fill - Road is to be utilised.
label | bcfa0011-b1bb-501d-907f-2907772b26d6 |  | note | Attach: Laboratory testing Verification:
text | da42f828-f9b9-568f-a12e-809a15e7e728 |  | textbox | Enter: Type A fill Lot Number:
label | 4a550785-31e2-56cf-aeed-b4d18c534e5c |  | note | Method - Verify-Document Review
label | c69312be-39c4-5c49-ae2c-6dd6f7608d1b |  | note | Frequency - Each lot
label | 09d988db-9b1e-5185-8957-8711101b590c |  | note | Category - HP
label | e0ba499a-eb1c-52d3-b789-58616ecf0d2b |  | note | Responsibility - PE/Nominated Authority
label | 7bc4a220-0ec9-5e67-a9b8-aa53d01460d5 |  | note | Verifying Documents - This ITP/Test Report/Referenced Lot number
text | 27c5e308-63d8-510d-8939-a0d47a3fa6ad |  | textbox | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 5.2 - Material classified as silt
label | 5f7f50f0-3b75-5b21-97f4-efd508481491 |  | note | Reference - Section 204.04 b)
label | 469c2365-6ac9-5e80-8681-473ff9c3ccd2 |  | note | Acceptance Criteria - Material classified as silt, either before or after compaction, is not acceptable as Type A material without stabilization to the satisfaction of the Nominated Authority
label | 56adb619-49e2-5c15-99c7-ad29bbc13538 |  | note | Method - Document Review
label | 265d3519-2b6e-5b10-b5aa-1d97c830b2f9 |  | note | Frequency - Prior to commencing
label | d77edc05-21a8-5d90-8e00-923e689a1ee7 |  | note | Category - HP
label | 65ed1060-76dd-538c-9910-dea9036a3729 |  | note | Responsibility - SE/Nominated Authority
label | 554f3a84-aafa-53fe-a12d-ac4b7a534425 |  | note | Verifying Documents - Superintendent satisfied with Stabilisation
label | bb5187bd-8536-5c0c-878f-b74c686d7edf |  | note | Signed ITP/ records
text | 0b706f09-71ac-50a9-8393-8258e89b4355 |  | textbox | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 5.3 - Acceptance of Rock Subgrade (where applicable)
label | dee7a647-b8a8-5c46-a2a2-53512bd56c4c |  | note | Reference - Section 204.06 f)
label | 0e5faf74-19ff-55d7-9f44-1361a0039134 |  | note | Acceptance Criteria - Prior to construction of the regulating layer, the areas of rock subgrade shall be presented to the Superintendent for acceptance.
label | a6045b83-144e-539d-bb05-39c30462286b |  | note | Any necessary amendments to the subsurface drainage design including transverse subsurface drainage at the interfaces shall be presented to Superintendent for review.
label | da9e087e-80ac-55b9-a791-2176fd2e8e9c |  | note | Method - Site Inspection/ Document Review
label | 8d9e4cb0-89d7-5d3b-9839-e5064017dfed |  | note | Frequency - Prior construction of the regulating layer
label | e9ff3405-2bef-510e-9d06-503be0fa2255 |  | note | Category - HP
label | f15bba90-6677-549a-9fa8-736c4681bbf5 |  | note | Responsibility - SE/Nominated Authority
label | ca74c18e-6ce5-51ab-b25a-b214115d432a |  | note | Verifying Documents - This ITP
text | b76e13ba-472e-58eb-8f8e-051ade86f4cb |  | textbox | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 5.4 - Unsuitable Material
label | f5762e6a-252d-5eea-a2db-f91ce8194480 |  | note | Reference - Section 204.07 d)
label | 2d8c7b7b-5242-51ec-bc74-810eb899b011 |  | note | Acceptance Criteria - Where Unsuitable material is encountered, proposed in-situ treatment must be submitted to the Nominated Authority for review.
label | 2e55e64a-0592-58f2-90ef-d880e3357df7 |  | note | Method - Visual inspection
label | ba3acae5-437e-5c7a-823d-bf7fe454fca4 |  | note | Frequency - Each lot
label | e805fba9-b73c-5889-93dc-7873391449ef |  | note | Category - HP
label | a93032c6-432f-5120-9c4d-bd14ee36fead |  | note | Responsibility - SE/Nominated Authority
label | 7847bd56-52d8-5851-8856-1e86bf5ae369 |  | note | Verifying Documents - This ITP
text | 867ba0a7-b5dd-5983-9ce9-638ef9fd7653 |  | textbox | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 5.5 - Groundwater
label | cbd39376-812f-5ad9-88ab-cf40dd2e2f80 |  | note | Reference - Section 204.06 h)
label | 16826619-2e9e-5a6b-94e2-2ca05cb27231 |  | note | Acceptance Criteria - Where groundwater is encountered the contractor shall notify the superintendent and submit proposed action for review.
label | c313b280-406a-503c-a5ca-aa6c1d9d5e2f |  | note | The Contractor shall submit any necessary approvals from relevant authorities for the treatment and disposal of this groundwater.
label | fecb422e-a636-55b9-b651-7bbf22db4632 |  | note | Method - Visual inspection
label | ecc65a18-98c4-5a57-87f3-f39c1cb0dcae |  | note | Frequency - Each lot
label | 03637807-2b0f-5112-b385-7a6901407618 |  | note | Category - HP
label | 732134d2-8b75-516d-9042-69013f68a0d4 |  | note | Responsibility - SE/Nominated Authority
label | 75cc0c13-1248-5a6f-8d2f-86ea12b1c56f |  | note | Verifying Documents - This ITP
text | 87ed565d-5667-5fc8-82e6-ab7d02efaad6 |  | textbox | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 5.6 - Cut to Fill Zones
label | bf6b3ac1-5281-5ac0-9228-b30e7bf5c304 |  | note | Reference - Section 204.06 g)
label | cfe6cad4-7059-5ac7-b604-54d8e36e2b40 |  | note | Acceptance Criteria - All pavement and verge areas at cut to fill zones shall be excavated to a minimum depth of 600mm below the cut floor level or top of the type A material, for a distance of not less than 15m into the cut and 30m under the fill from the cut-fill line at the upper surface of the Type A material.
label | e202154c-b981-54b6-82de-9c3127b9d306 |  | note | Method - Site Inspection
label | d7e538e8-3e4d-540a-9e2c-b2312586febd |  | note | Frequency - Each lot
label | a869b10c-6b40-53f9-a38e-ea74afe250ee |  | note | Category - IP
label | 2fcddaa5-9edd-50a9-8d49-66c0d8e6db66 |  | note | Responsibility - SE/Site Supervisor
label | edebc9fb-77dd-56d6-9f4e-fd14a0ab6555 |  | note | Verifying Documents - Sign ITP
text | da315dfc-0586-5ba8-8d2a-88d31f806972 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.7 - Proof Roll
label | abf33bb9-5fdb-52cd-a325-38f69546d39a |  | note | Reference - Section 173
label | edcf178a-e26a-505e-bdb6-04d483689d17 |  | note | Acceptance Criteria - Proof rolls to be conducted in accordance with Section 173 of the VicRoads Standard Specification
label | bb3f8019-1054-5077-9023-b6bea4ca4eda |  | note | Method - Visual inspection
label | ab015910-2658-5966-9f78-9430a0c9002a |  | note | Frequency - Each lot
label | 9197be12-d19f-5ca4-8c0b-2793d62b017a |  | note | Category - HP
label | 721ce0dd-a573-58ba-b3a7-0bed70e49167 |  | note | Responsibility - Site Engineer/Superintendent
label | 858d2eaf-723f-58f9-88bd-a8e7d31c6607 |  | note | Verifying Documents - This ITP
text | 15334f87-3bba-57ce-9354-d62f7906da93 |  | textbox | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 5.8 - Compaction Testing
label | c4ad0127-7c06-58ed-9b14-e0966936395a |  | note | Reference - Table 204.131
label | 7817aa3c-2b86-53af-ac52-86202633a9fb |  | note | Acceptance Criteria - All Type A Material, Type B Material placed within 400 mm of top of Type B Material and Ripped and re-compacted material below Cut Floor Level
label | 486ff726-b40e-50bf-8c26-d3f03704efdc |  | note | Scale A: Characteristic Density Ratio 99%.
label | bed677cd-45bc-5d6e-8fea-9e8a4c22eea9 |  | note | Scale B: Characteristic Density Ratio 98%.
label | 0a20e21f-53bf-50fc-99c8-1b6e1e4daced |  | note | Scale C: Mean Value of Density Ratio: 100%
label | 7d019dd5-e702-55dd-b40d-7e17bffd6b51 |  | note | Attach: Compaction Test Result:
label | 2e93ad84-53e8-5395-8579-329be8a6989f |  | note | Method - Document Review
label | bb4d8816-26e3-5ece-92dd-da1fc2d82908 |  | note | Frequency - Each lot
label | 5cb56ada-7525-5db0-86d6-7347774ae057 |  | note | Category - IP
label | 5981f34e-1749-5d76-87e7-cc4a156c0b3a |  | note | Responsibility - PE/SE
label | 1069cd4b-e880-5d80-b897-b497b1058913 |  | note | Verifying Documents - Test Records
label | 5d4c9c17-7ed4-5b58-863c-a36b0fe3280f |  | note | Lot Register
text | abfb48e2-30ee-5ce5-8a15-4643e493bc4d |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.9 - Post Compaction Material Property Testing
label | b45cb912-a745-50f0-99f9-419966923399 |  | note | Reference - Table 204,041
label | 7efff24c-2cbb-5003-a4d4-00ec772d2ddb |  | note | Table 204.141
label | c6e90238-95e2-52c1-8e53-3332287cc525 |  | note | Section 204.14 a) or b)
label | 4a5626d9-7a29-5a06-822a-9b047b44bb93 |  | note | Acceptance Criteria - Material Properties (Not Applicable for Scale C):
label | 59d8ebfe-d528-58fe-9ba1-ff374ef887b1 |  | note | CBR ≥ 3% and Swell ≤ 1.5%
label | 4a121581-1950-5778-963c-7afc9c8aa41e |  | note | Max Permeability = 5X10-9 m/s
label | 16e87b2a-5606-59fc-9f9e-0bc80ee6742c |  | note | Grading: 75.0mm 100%
label | 2a79fc1b-91bc-51e9-b37b-8e7654657f75 |  | note | 4.75mm 40-80%
label | 5c5e41ac-ab43-50ce-a834-098fba7aec4d |  | note | 0.075mm 10-40%
label | e0e04acd-d21b-5da0-8422-001f1bcfb05a |  | note | Max. PI x%Passing 0.425mm = 1000 , PI = 6 to 25
label | 54f43dc4-d61e-5deb-b7a1-2c88a6da3da7 |  | note | Scale A:
label | bb54881f-31a6-560a-b137-e07ee16258a9 |  | note | CBR & Swell
label | 2bbef769-31e0-5dbe-841b-2e5c100e1105 |  | note | Initial - 1 Lot Test to determine Assigned CBR and swell
label | 220cf4e9-6b0c-5f86-b531-aaba0e96a20c |  | note | Reduced - 1 Single CBR test to confirm Assigned CBR and swell per every 2 lots
label | 43c95da2-2ab1-5629-96b4-7e150a56f278 |  | note | Max Permeability
label | b54215d6-d076-5363-bf89-bf15189da42a |  | note | Initial - 1 test per 2 lots
label | da86e7a7-8756-592f-8491-b2c2c39ecf7f |  | note | Reduced - 1 test per 4 lots
label | e90f33ae-e6e8-57f9-95f9-392dd261aeb3 |  | note | Grading:
label | 2794d8c7-c096-5fbf-b622-2b7f263e3583 |  | note | Initial - 1 test for each lot tested for compaction
label | 2a49c024-6491-505b-8902-d67ee2ae748f |  | note | Reduced - 1 test for every second lot tested for compaction
label | aac3a73a-8baa-54c4-ab24-985caf32c94c |  | note | Max. PI x%Passing 0.425mm & PI
label | c75076a8-2a1b-5088-9607-58ef54990484 |  | note | Initial - 1 test per 2 lots
label | 9d3065a2-ce4c-520e-87dd-e7b82cee1119 |  | note | Reduced - 1 test per 4 lots
label | 909b5e97-a84c-5b1e-b54d-b7eaa1019676 |  | note | Scale B:
label | f866ab87-ba8a-5b2e-bedd-531a910c9e04 |  | note | 1 Lot Test to determine: Assigned CBR and swell, Grading & Max. Particle Dimension, PI and PIx%Passing 0.425mm and permeability.
label | 97a335c2-6d17-51d2-81c4-9e8ef2384e54 |  | note | Where the first lot passes, no further testing required except where changes to the physical properties of the material are observed.
label | 0b3bc9b4-2ca1-56c3-8eac-f13a5829ef26 |  | note | Attach: Post compaction test results
label | f9aaf5f2-5dba-5f0e-85d9-3486c0edce20 |  | note | Method - Review Document
label | 678fc9c9-eab9-5093-8bae-f6c8b14e7b62 |  | note | Frequency - Refer to Section 204
label | 848d26ab-608d-5759-994b-4dae07155655 |  | note | Category - IP
label | 82e17378-040f-592b-96df-64c2d608cc51 |  | note | Responsibility - PE/SE
label | e0408a22-efe3-572c-a576-03e026050efb |  | note | Verifying Documents - Sign ITP
label | 57a1a3a5-c322-5ff0-9fd0-90b260e39b68 |  | note | Attach Material Property Test Report
text | abb08515-506d-5c6e-8edd-ac2c7b5b5c9e |  | textbox | Date Completed:
checkpoint-group |  |  | section | 6 - Post Construction Activities
checkpoint-status |  |  | checkpoint | 6.1 - Survey Conformance
label | 464c3684-c41d-5314-a509-a757a3761280 |  | note | Reference - VicRoads 204.03f,g and h
label | 0f2f5917-a610-5d09-b8e6-652c2d1ada58 |  | note | Acceptance Criteria - The level at any point on the subgrade shall not lie more than 20 mm below a 3 m straightedge laid in any direction, except across a crown and water shall not pond at any point.
label | e8c67308-c717-5ae7-81dd-0d5688013dc1 |  | note | Level tolerances (Scale A):
label | d4d13d9c-0b54-5d2d-bf9a-7e684c277185 |  | note | Range x = +5, -15mm
label | 2908c60a-5f2a-524a-962e-c5cceb4e5f73 |  | note | Max S = 12 mm
label | 390b3bde-dde7-5445-8bdd-fff98e2f3a7f |  | note | 80 measurements per lot
label | f1dc11f8-6efc-50d4-b559-1f2dfb7d1489 |  | note | Level tolerances (Scale B):
label | d0460f13-2049-55ef-a39a-2ffaa261f1ba |  | note | Range x = +5, -25mm
label | 1209f24a-70be-539e-b723-5dae8eeb6c76 |  | note | Max S = 15 mm
label | 198a14e2-b0de-5204-8733-cb99dc3cf5d1 |  | note | 40 measurements per lot
label | a4b6d4ba-ffc1-509e-b0c2-dd6cfa2c1c5e |  | note | Level tolerances (Scale C):
label | d7ca8de2-9be4-53d4-90df-4ad3cecba1bc |  | note | Where Scale C is nominated, random levelling is not required; however no point on the subgrade surface shall be more than 10 mm above or 30 mm below the specified level.
label | a1d616de-d64a-50b2-9875-8dc0bd2caa9e |  | note | Method - Review Document
label | c1da78a0-f4e4-56ad-8dd3-c72b1f7eec71 |  | note | Frequency - Each lot
label | 2e8ad31e-a545-5118-8035-b6f4f41f050d |  | note | Category - SCP
label | 870df477-1571-52a4-af26-deb4d2c3421e |  | note | Responsibility - SE/Surveyor
label | 60635c4a-7dc2-5a58-bc8d-8a3d0ad7f781 |  | note | Verifying Documents - Sign ITP
label | 5852b3d7-7d40-5f69-a650-fcb00a90e866 |  | note | Attach Survey Report
text | 5d76aa78-6e65-5d90-9109-175b99668729 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | Final Inspection
label | e398a81e-d8ce-5518-90b1-dfa0ba52d31d |  | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
text | 86040a30-b8ac-5ca2-8179-61fe3a18a4a2 |  | textbox | Print Name:
text | e359971c-b909-5749-88fe-75b132d667e1 |  | textbox | Position:
text | 552a64ae-cf55-5aa0-ac73-f1082b1c619d |  | textbox | Date:
checklist-sectioned |  |  | checklist | ITP-014-CIV-CAMMS-Footpaths & Shared User Paths | itp |  |  |  | Yes | ITP-014-CIV-CAMMS-Footpaths & Shared User Paths Rev 0 | 1c60bfb1-c3f7-4777-be91-a1f4d1093838
checkpoint-group |  |  | section | Referenced Documentation
checkpoint-status |  |  | checkpoint | Referenced Documentation
label | fc64aecb-8ca8-5aab-a86c-0bcf339cac52 |  | note | Document Title: ITP-014-CIV-CAMMS-Footpaths & Shared User Paths
label | 2f108b87-5f93-534b-9c9f-cf7319931abe |  | note | ITP Description: CAMMS-Footpaths & Shared User Paths Scale C- 1 (Set-out & Bedding)
label | e25af5ad-7cf9-5d1b-97da-e20ee9463669 |  | note | Document Number (in Teambinder): MRP-0000-MRPA-ALT-ITP-00XX
label | 2cdf6b43-9bfc-5af2-b19d-a7fd09f982f9 |  | note | Discipline (e.g. CIV/STR/RAIL): CIV
label | 924e088d-1fee-5dbe-b5fe-a42ff9b53af9 |  | note | Revision Number: 0
label | 1638855d-f9e7-50c4-857b-e143ef552111 |  | note | Revision Date:
label | b89d024e-7ab5-5a38-9ae8-1fd27002a672 |  | note | ITP created by: Victor Mira
label | ac6c96bc-7dff-5f22-827f-34a7e5332d1a |  | note | ITP approved for use by: Victor Mira
label | 2cf64137-1eee-51a4-bc41-88d45ce79308 |  | note | 1.1 Non Dependent
label | 8032ab5b-1907-5f89-a73c-0e2e0d37f108 |  | note | Reference: VicRoads Section 304 August 2013
label | 8b41f279-4a2d-5f90-869b-aca9513c68e5 |  | note | 1.2 Non Dependent
label | 323fc24c-aa3f-5062-91ca-a10e50674e80 |  | note | Reference: VicRoads Section 703 April 2019
label | 4e5f658e-010a-5521-a3d5-66e0cedd0b35 |  | note | 1.3 Non Dependent
label | 9d447e82-9f7a-54c5-8e5a-d398f9437e7e |  | note | Reference: Council EDCM 401
label | e1c12051-86be-5c9a-a3e7-7b50ac01cd14 |  | note | 1.4 Non Dependent
label | 7776f39b-37ab-5ad9-b8ee-ac53d1b0b8ba |  | note | Reference: Council EDCM 501
label | f6c7412d-07d5-5454-9456-b01a0237a513 |  | note | 1.5 Non Dependent
label | cb2dad1f-d6bb-556e-b9b5-5821014183f0 |  | note | Reference: Council EDCM 502
label | d09b53ed-dfe0-50c2-a6b3-71fd028d10b5 |  | note | 1.6 Non Dependent
label | 5981a5fc-fb1f-56af-9084-6797a86b5042 |  | note | Reference: Council EDCM 503
label | f53ea9e0-ffd6-5962-8ba2-a27b026777bc |  | note | 1.7 Non Dependent
label | f726b3c8-e5d0-51de-9c35-7de645e9fb42 |  | note | Reference: AS 1379-2007
label | bfe9837b-08f2-5d4f-804e-86308772b95c |  | note | 1.8 Non Dependent
label | 9b088160-60d9-5331-97f7-703458a58170 |  | note | Reference: VicRoads Section 812 July 2016
checkpoint-group |  |  | section | Preliminaries - Materials
checkpoint-status |  |  | checkpoint | 2.1 Bedding Material Placement & Compaction
label | 6cf8d671-6ddd-5bce-b60b-f09f7076dfec |  | note | REFERENCE: IFC Drawings:
label | a8b59300-f6a4-52f8-beba-dbc00c90f7b4 |  | note | • MRP-052-C-SME-DRG-13-MPK-CPT-0101 & MRP-052-C-SME-DRG-13-MPK-CPT-0102
label | 2a32b19b-7aad-501b-9250-f92ee8ae0496 |  | note | • 812.04, 703.21
label | e2f59b3f-bb9c-5cd0-ae82-34c8724a5e46 |  | note | – – – – – – – – – – – – – – – – –
label | cf5d6f2e-b5a1-52cb-bc97-7bab6bbe7abc |  | note | ACCEPTANCE CRITERIA: Footpaths: SIZE 20mm CLASS 3 CRUSHED ROCK
label | 393da40f-56c4-54bf-bf90-9486498bdc6f |  | note | • SUP: SIZE 40mm CLASS 3 CRUSHED ROCK
label | a5d1becf-25ab-501c-be61-4f74627dc1d1 |  | note | • Material is registered with VicRoads in accordance with Code of Practice RC500.02.
text | dbf8a31b-6095-5666-b183-be3865024f62 |  | textbox | • Enter: Teambinder Material Approval number
label | fefa6539-9f89-5b4d-a8dc-0df05f115982 |  | note | – – – – – – – – – – – – – – – – –
label | 818891b5-3c35-56dc-afa6-a8c13f520af4 |  | note | METHOD: Document Review
label | f967724c-47bd-53a1-a795-deb18644b185 |  | note | – – – – – – – – – – – – – – – – –
label | 6df591d4-3915-5799-a8bf-f60a9f2f85a3 |  | note | FREQUENCY: Each Lot
label | d0f19106-ce40-5274-9d12-b5b242ebc1f4 |  | note | – – – – – – – – – – – – – – – – –
label | a1742d23-e519-524b-82b7-1152a6556947 |  | note | CATEGORY: HP
label | 69d9da30-205c-5159-aad3-7979fbf3d027 |  | note | – – – – – – – – – – – – – – – – –
label | b2db3095-9308-5f9d-8cc1-bd59b87ebc94 |  | note | RESPONSIBILITY: Nominated Authority
label | aa7d586f-08bb-5287-aa99-c1c09c01471a |  | note | – – – – – – – – – – – – – – – – –
label | 6cd0fb2a-ed0f-5ccf-8455-e8743f6eb0ac |  | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
text | 384a9d06-810f-5757-8470-6f8a3584a4a8 |  | textbox | Date Completed:
holdpoint |  |  | signoff | NOMINATED HOLDPOINT AUTHORITY
checkpoint-status |  |  | checkpoint | 2.2 Concrete Mix
label | 587e2ff5-3377-5c6a-9737-4662297424d0 |  | note | REFERENCE: IFC Drawings:
label | 54bf0276-8bde-596f-aafc-1ec40c7aae86 |  | note | • MRP-052-C-SME-DRG-13-MPK-CPT-0101 & MRP-052-C-SME-DRG-13-MPK-CPT-0102
label | d5fcfdd2-85d4-5191-ab69-86de8db6352a |  | note | • 703.05 (a), 703.07
label | 616ab5e2-336d-5d0b-ad9f-543d68ab435c |  | note | – – – – – – – – – – – – – – – – –
label | af8047e4-6c5d-5dd6-8d6e-d79ede21ccf6 |  | note | ACCEPTANCE CRITERIA: Concrete mix meets strength, grade, and maximum aggregate size as detailed on the drawings:
label | e8400f84-b5d2-5e60-9cac-44e3b22add24 |  | note | — Footpaths, Residential driveways and Median islands infills: 25Mpa
label | f29e11f9-5561-5033-a571-5c8f907d7d24 |  | note | — Industrial Crossovers: VR330/32 to be registered by Vicroads
label | b6835f34-a063-5fd0-ae49-fd07d2f7c65b |  | note | — Traffic Islands: 32 Mpa
label | 2d137bee-d452-526d-8d5e-58d61bd69bf0 |  | note | — SUP: VR330/32
label | bb853c93-83a4-5c92-a9e3-6850b99a782c |  | note | • No air entraining chemical admixtures shall be used without approval from the Nominated Authority.
text | d61b1f52-8ca1-5188-8b5c-0fb2632ae7b5 |  | textbox | • Enter: Teambinder Material Approval number
label | 4e27f9c2-e402-5dce-b678-e1874439392c |  | note | – – – – – – – – – – – – – – – – –
label | 3bfcad8f-fb00-5f83-a945-6c172e4c82cb |  | note | METHOD: Document Review
label | dc1fe9ed-9993-5f6a-ad71-04c7ab615499 |  | note | – – – – – – – – – – – – – – – – –
label | 877e5c40-37f3-5a4f-8280-92d362453608 |  | note | FREQUENCY: Each Lot
label | 38a5c72e-c740-514e-8392-f3fb5e4d7964 |  | note | – – – – – – – – – – – – – – – – –
label | ffe9236b-204e-5616-a520-81e6378005f3 |  | note | CATEGORY: HP
label | 7fd05cbe-28b5-5f78-834e-5608846c7585 |  | note | – – – – – – – – – – – – – – – – –
label | 526fd435-6585-5b79-a2e4-ec1fd714a64b |  | note | RESPONSIBILITY: Nominated Authority
label | 793465d6-aa44-55fa-b046-652549626e49 |  | note | – – – – – – – – – – – – – – – – –
label | 80cf2e8e-4081-5caa-9563-0579fa646202 |  | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
text | ec114962-159a-5efa-84d8-cd5135115557 |  | textbox | Date Completed:
holdpoint |  |  | signoff | NOMINATED HOLDPOINT AUTHORITY
checkpoint-status |  |  | checkpoint | 2.3 Reinforcement
label | 58016811-3a75-5396-be51-73931674fd14 |  | note | REFERENCE: IFC Drawings:
label | 28907ad9-ab70-577c-bb73-c7c959718427 |  | note | • MRP-052-C-SME-DRG-13-MPK-CPT-0101 & MRP-052-C-SME-DRG-13-MPK-CPT-0102
label | c4b981cb-e2e0-5d1f-8f61-728aeeb29c37 |  | note | • 703.16
label | a493c16b-6c95-526b-8842-959191ef116d |  | note | – – – – – – – – – – – – – – – – –
label | e371dd15-ee30-527c-a68c-bb8fd40b5a26 |  | note | ACCEPTANCE CRITERIA: Reinforcement shall comply with AS4671.
label | 01601efe-52fd-5c63-b8c9-235c68bbad09 |  | note | • Alternatively, provide a current ACRS certification for materials and for bar processing (as this covers a higher certification)
label | eb6919a1-269d-521a-b1f7-08341dce94fe |  | note | • Following steel mesh requirements shall apply as per IFC Drawings:
label | 2f9cb185-9017-5b6d-8752-b562bacc9683 |  | note | — Footpaths, Residential driveways and Median islands infills: SL72
label | 2e33393c-5671-59f7-b034-d87a7f737c52 |  | note | — Industrial Crossovers: SL82
label | 01b616dc-9be4-5e7b-aa56-ec8649077a25 |  | note | — Traffic Islands: SL72
label | bec4b9b9-353d-5a23-8c15-95d037ce9f0b |  | note | — SUP: SL82
text | 929ddc98-2c7d-5487-9fe1-a7599db645c9 |  | textbox | • Enter: Teambinder Material Approval number
label | 2b1da527-f5a8-516c-b41e-c1bb1e0792c9 |  | note | – – – – – – – – – – – – – – – – –
label | 8a1d722a-1809-509b-9050-5daf6acc6099 |  | note | METHOD: Document Review
label | d0a53be3-365c-57a3-a827-3372719be2a9 |  | note | – – – – – – – – – – – – – – – – –
label | f093e72d-922d-56df-a060-ddf83d74ee8d |  | note | FREQUENCY: Each Lot
label | 17292696-9d23-579a-8beb-1e31eefe5f8f |  | note | – – – – – – – – – – – – – – – – –
label | 3a885809-8d07-5e0f-b665-7a31f3000068 |  | note | CATEGORY: HP
label | 4f5be39a-1f7d-5312-a339-15c9ab87cdda |  | note | – – – – – – – – – – – – – – – – –
label | 4366c40c-eb38-5645-bec9-0d804921f217 |  | note | RESPONSIBILITY: Nominated Authority
label | b029ecc8-4e93-51c9-809b-c72892d51a5a |  | note | – – – – – – – – – – – – – – – – –
label | bf0d9fa3-4114-5169-a144-ad88827d18fd |  | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
text | 486a3b30-f057-57a5-ad5f-38505467e521 |  | textbox | Date Completed:
holdpoint |  |  | signoff | NOMINATED HOLDPOINT AUTHORITY
checkpoint-status |  |  | checkpoint | 2.4 Evaporative Retardant
label | 4269db9d-733d-555b-a67e-ad91612d6ef6 |  | note | REFERENCE: 703.09
label | 0fb45cd7-f885-578c-b37f-fa9e3bab7969 |  | note | 610.17 (f)
label | 58739c78-a1f0-576f-ac11-50fd592c6434 |  | note | – – – – – – – – – – – – – – – – –
label | 35068d34-51d6-5753-832a-b62f558d2f30 |  | note | ACCEPTANCE CRITERIA: Details of evaporative retardant, application procedure (including application rates) to be submitted for review to the Nominated Authority.
text | 0bee3d49-44e5-5d30-8e6b-b8539c0ed88a |  | textbox | • Enter: Teambinder Material Approval number
label | d7b37cf8-5428-5532-b0db-b075abf4c0d8 |  | note | – – – – – – – – – – – – – – – – –
label | a614a7cb-5e5b-5c05-94d1-3e04ee7b1b66 |  | note | METHOD: Document Review
label | 479eba6d-fc0d-5fb0-98df-1d3172f62f08 |  | note | – – – – – – – – – – – – – – – – –
label | a95cd09d-c87f-5918-9a6b-d5be65639d5f |  | note | FREQUENCY: Once, for each product, prior to placement of concrete
label | 33587df1-4faa-5f3d-9ccb-7fa75c56cb08 |  | note | – – – – – – – – – – – – – – – – –
label | 190380f8-7e93-5e80-bc65-3d582e2d9634 |  | note | CATEGORY: HP
label | 71e339ce-3f02-5a61-a0a4-e3b60a34402e |  | note | – – – – – – – – – – – – – – – – –
label | 24939bdd-7a7f-53c1-85e5-b5cdf9ab4883 |  | note | RESPONSIBILITY: Nominated Authority
label | d6b91cfe-28a1-5a23-b0ee-b10469d27317 |  | note | – – – – – – – – – – – – – – – – –
label | 5deee1ac-d733-5a87-99a9-7a7a4e85461c |  | note | VERIFYING DOCUMENTS: This ITP
text | 164a9300-3aa8-505b-8abc-8bc3be714a06 |  | textbox | Date Completed:
holdpoint |  |  | signoff | NOMINATED HOLDPOINT AUTHORITY
checkpoint-status |  |  | checkpoint | 2.5 Curing Compound
label | 0220c777-3102-5b5f-844d-d8033d201edc |  | note | REFERENCE: 703.10 (a)
label | 161dc935-85b3-57d4-9d8c-4ef604edef43 |  | note | 610.23 (d)
label | aaeefc51-d650-5e2d-8c79-eb1fb666f5dd |  | note | – – – – – – – – – – – – – – – – –
label | 2e4289d6-4992-5cde-9ca3-222a479fd965 |  | note | ACCEPTANCE CRITERIA: Details of curing compound and NATA test certificate stating compliance with AS3799 no more than 3 years from issue, to be submitted for review to the Nominated Authority.
label | 5fd56e48-ed02-5830-b2cd-78401458c285 |  | note | • Enter: Teambinder Material Approval number
label | fc00595b-33d3-5c08-820a-284e9b47faf0 |  | note | – – – – – – – – – – – – – – – – –
label | 79727f00-b6d9-5573-8006-f013ae3e0992 |  | note | METHOD: Document Review
label | c75b9a19-ddd7-515f-b697-b9d4a8171ac8 |  | note | – – – – – – – – – – – – – – – – –
label | 09dd4130-df4e-5546-8971-fd956d4755d6 |  | note | FREQUENCY: Once, for each product, prior to placement of concrete
label | 3344a181-9168-5215-b4bf-39585e28b58e |  | note | – – – – – – – – – – – – – – – – –
label | c0a43d9e-6f4c-501f-8fe2-9c6b18fa19af |  | note | CATEGORY: HP
label | 939d6627-5960-5e9b-a72f-8b8da1082031 |  | note | – – – – – – – – – – – – – – – – –
label | 293663ea-782a-5a3b-b5b3-6592b0498ef4 |  | note | RESPONSIBILITY: Nominated Authority
label | 0b0ef9ac-0fe3-54f4-9956-4b127650cac8 |  | note | – – – – – – – – – – – – – – – – –
label | a0fef5ca-81b6-5182-ae84-c75159d2f570 |  | note | VERIFYING DOCUMENTS: This ITP
text | bcdb33cf-4204-5d39-a4c2-6506e0de92a5 |  | textbox | Date Completed:
holdpoint |  |  | signoff | NOMINATED HOLDPOINT AUTHORITY
checkpoint-group |  |  | section | Preliminaries - Documents
checkpoint-status |  |  | checkpoint | 3.1 Survey Set-out
label | 9d10619c-bfbf-5e79-ac43-05fe6457591d |  | note | REFERENCE: IFC Drawings
label | 8fdb9dc2-0788-53fb-888c-df916fd7d54f |  | note | 703.17
label | d1e1efc6-2cf0-58a5-8612-0019fe71d8ac |  | note | – – – – – – – – – – – – – – – – –
label | 2e50890d-6661-568a-af96-6fb6c6892468 |  | note | ACCEPTANCE CRITERIA: The work shall be constructed in accordance with the confirmed set out to the line and level and cross-sectional profiles as shown on the drawings.
label | 72e27fed-7f33-5565-b571-ca4e653efcfd |  | note | • The Nominated Authority will review and confirm the set out.
label | a3618167-790a-525b-befd-2b57748c2c33 |  | note | Attach: Survey Report
label | 10d33d3b-410c-5c4f-b226-c702ebef23be |  | note | – – – – – – – – – – – – – – – – –
label | 40a07f72-38c7-565b-9431-261b310a95d8 |  | note | METHOD: Document Review, Measure, Visual
label | da6443c3-60c3-501c-8c81-4681760fbe75 |  | note | – – – – – – – – – – – – – – – – –
label | 601f1a56-7564-5bdc-84f0-362ef92923b0 |  | note | FREQUENCY: Each lot
label | 572fac93-01c2-5a55-8d16-fc1f50fed54f |  | note | – – – – – – – – – – – – – – – – –
label | b2145ba2-74b2-5c10-9176-6ed4097edb84 |  | note | CATEGORY: HP
label | afabbe7f-7619-5b7b-a6d4-f1fa3e661805 |  | note | – – – – – – – – – – – – – – – – –
label | 3ef1a0a3-83b2-5e4b-a972-f0830164bbf0 |  | note | RESPONSIBILITY: Nominated Authority
label | dabf51d8-a119-5599-b2b9-59bb919e7712 |  | note | – – – – – – – – – – – – – – – – –
label | 1b57014e-42ac-562f-b038-766ad0a4e0e7 |  | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
text | 933863a6-e1a9-57d3-880a-3a71510e2b63 |  | textbox | Date Completed:
holdpoint |  |  | signoff | NOMINATED HOLDPOINT AUTHORITY
checkpoint-status |  |  | checkpoint | 3.2 Lot Map
label | dffd64ad-5df5-520c-bf8d-369836e87256 |  | note | REFERENCE: MRPA Lot Management Plan
label | 6958710a-48b0-5e85-8b30-f4ea6745366a |  | note | – – – – – – – – – – – – – – – – –
label | 38156042-48fb-516a-9654-9480f42f93b3 |  | note | ACCEPTANCE CRITERIA: Attach Marked drawing indicating the location of this Lot
label | f6950ec2-6676-54da-ab65-4ccf9fe7463d |  | note | Attach: Lot Map
label | 9232d1c8-0608-5613-9a64-b287e742c2f4 |  | note | – – – – – – – – – – – – – – – – –
label | 061c9dcd-f887-55fc-a307-cad4e52820bc |  | note | METHOD: Document
label | f94b2ae7-de4f-50c1-9cf8-834a5c19e8a5 |  | note | – – – – – – – – – – – – – – – – –
label | 4b03d937-79ee-5ab3-a3c5-e0142f595345 |  | note | FREQUENCY: Each Lot
label | 161feabf-050a-5a62-a3bd-dec18600246d |  | note | – – – – – – – – – – – – – – – – –
label | d9d3a16f-5b2b-5808-b8d1-5078a4d7aded |  | note | CATEGORY: HP*
label | c54e9f94-3b4c-520e-bc8a-f512cd474425 |  | note | – – – – – – – – – – – – – – – – –
label | a84586a9-75ca-5c02-9e0a-e9edf28d0472 |  | note | RESPONSIBILITY: SE/PE
label | e55e9821-10f2-5396-a934-7783b839a833 |  | note | – – – – – – – – – – – – – – – – –
label | aa0d9e8f-c45b-5bfb-ba33-c100fc92fa5e |  | note | VERIFYING DOCUMENTS: Attached Lot Map
text | 9a3b2bb2-b018-5fce-bf4c-45a2c30f013b |  | textbox | Date Completed:
checkpoint-group |  |  | section | Pre-Construction Activities
checkpoint-status |  |  | checkpoint | 4.1 Site Clearing & Grubbing
label | 824f16b7-5504-5520-89af-63539b4131a5 |  | note | REFERENCE: IFC Drawings
label | 63cff46f-6793-52d5-b712-48ee2b886e81 |  | note | – – – – – – – – – – – – – – – – –
label | 1a01a863-4283-5b9e-950d-dc7c7e0f2e9f |  | note | ACCEPTANCE CRITERIA: If not completed during the site establishment, the work area needs to be cleared and grubbed.
label | bcb002ed-c54a-5c84-ba1c-ae74f287f356 |  | note | • Complete: Site Clearing & Grubbing ITP before proceeding with this ITP.2
label | d2cbf0de-8864-5800-8cfa-d0da2605145f |  | note | – – – – – – – – – – – – – – – – –
label | 325530fb-4c85-5b6e-91dd-bac4b82ef227 |  | note | METHOD: Visual
label | 7002e901-a768-54e9-9c1a-bb3f62283e06 |  | note | – – – – – – – – – – – – – – – – –
label | 7d6439a6-0f5d-5fc3-a506-9e57b63b5fc7 |  | note | FREQUENCY: Where applicable
label | 5c66bde4-7c46-59ac-994f-f2b2b63bffa8 |  | note | – – – – – – – – – – – – – – – – –
label | 28960d9a-a260-549e-9ebb-d595488aba07 |  | note | CATEGORY: IP
label | e3c7a306-b7ab-5549-bbf1-a80cd1d7437a |  | note | – – – – – – – – – – – – – – – – –
label | 02d8697d-cacb-5548-b81d-2777002d7adb |  | note | RESPONSIBILITY: SE/PE/SPE
label | e17cdc57-5b41-5b00-a925-96891b510103 |  | note | – – – – – – – – – – – – – – – – –
label | 2689933c-9bfb-5199-b9c2-12f97092ec55 |  | note | VERIFYING DOCUMENTS: This ITP
text | 826ffebb-c0fd-5db7-a0e3-8725b1187b50 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 4.2 IFC Drawings
label | d2040f26-1129-585d-a04e-9e4dd0594ab8 |  | note | REFERENCE: MRPA Quality Management Plan
label | 4cbad991-90c9-5787-ab7c-75c19e01a2cf |  | note | – – – – – – – – – – – – – – – – –
label | 0a3ab6ec-b0f9-56de-a23d-619705a56626 |  | note | ACCEPTANCE CRITERIA: Ensure that all employee and sub contractors are:
label | c4a77406-3caf-5ed8-b646-cee3b83bdb22 |  | note | — Using the correct and complete set of drawings
label | f70b89ea-ccfa-5440-a222-c9984d0796d8 |  | note | – – – – – – – – – – – – – – – – –
label | bc6149ad-289a-5733-8710-1aa6faaf94fc |  | note | METHOD: Document Review
label | ccfec7d7-5cc3-5f1b-ba23-2f0ddb86dc42 |  | note | – – – – – – – – – – – – – – – – –
label | 06955dc2-3976-53ea-b905-a67fa5ffe86f |  | note | FREQUENCY: Prior to starting Works and at regular intervals
label | 35a316b2-84d9-5bfd-a0f2-35bf0b5e74bb |  | note | – – – – – – – – – – – – – – – – –
label | 67dd9aa3-3220-5c84-bf2f-d6dc5b8d7f49 |  | note | CATEGORY: HP*
label | 4997436b-32c9-50c6-b91d-8186a61d0be7 |  | note | – – – – – – – – – – – – – – – – –
label | 261831e2-e762-5b8c-ae0d-81bb37a96507 |  | note | RESPONSIBILITY: SE/PE/SPE
label | 538f1659-0dc1-517d-840c-4265d827e3a4 |  | note | – – – – – – – – – – – – – – – – –
label | 03c82516-a256-55bb-ba2a-98ecac5d95ee |  | note | VERIFYING DOCUMENTS: This ITP
text | 3f46b628-6fdd-53b2-8f15-ca12b72bfa76 |  | textbox | Date Completed:
checkpoint-group |  |  | section | Construction Activities
checkpoint-status |  |  | checkpoint | 5.1 Excavation
label | 2edd880e-25ca-5df8-8906-725de4e202d6 |  | note | REFERENCE: 703.20
label | ef11e3cc-53ab-5b4c-84f5-ca004fe87580 |  | note | IFC Drawings
label | de34e989-22f1-57b1-8409-bda932089800 |  | note | – – – – – – – – – – – – – – – – –
label | 1d68071d-3414-598f-906b-930f7ab82ab1 |  | note | ACCEPTANCE CRITERIA: Excavation shall be to a sufficient depth to allow for the required compacted thickness of bedding material under the full width of concrete paving.
label | 761171c7-1d45-56ed-9071-3f79e15be6e9 |  | note | • Where it is necessary to excavate existing pavement, the excavation shall not extend more than 150 mm from the edge of the adjacent face.
label | 7f7101e3-7a79-580e-9aad-884f457a3134 |  | note | • Existing asphalt or bituminous surfacing shall be saw cut for a sufficient depth to produce a neat vertical face.
label | d6a070d6-b3f8-591d-89b6-dd126c4206d1 |  | note | – – – – – – – – – – – – – – – – –
label | e71dbdd9-2ed0-5221-99d3-2755ba7dec77 |  | note | METHOD: Visual, Measure
label | c2171d5e-0bb8-527c-8efa-fe2d0e7b32f3 |  | note | – – – – – – – – – – – – – – – – –
label | 386d59cc-3935-569d-b4e1-2798cc0d7b5d |  | note | FREQUENCY: Each lot
label | 9fb51219-7d7f-5498-a508-b7e5faafe97b |  | note | – – – – – – – – – – – – – – – – –
label | 1db71cdc-7d19-553a-92b5-47448b584e77 |  | note | CATEGORY: IP
label | 41b1ebda-2f2b-5a07-ac5d-715a749d1496 |  | note | – – – – – – – – – – – – – – – – –
label | 283a0864-daeb-5716-939d-a1344e5c3e65 |  | note | RESPONSIBILITY: SE/PE/SPE
label | e4ec1cb6-47e0-5675-9873-b9bb345accec |  | note | – – – – – – – – – – – – – – – – –
label | e7bb1a59-94a6-5690-ac04-feec752df8ad |  | note | VERIFYING DOCUMENTS: This ITP
text | ad0f3720-ca06-5243-827f-5f736248e98c |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.2 Excavation-Pavement Thickness Increases for Crossings
label | 91b7ce80-fdca-5f48-a518-516c8215b2d9 |  | note | REFERENCE: IFC Drawings:
label | f4606c2e-2225-5251-8d36-453041801df1 |  | note | MRP-052-C-SME-DRG-13-MPK-CPT-0101 & MRP-052-C-SME-DRG-13-MPK-CPT-0102
label | 1f5a4bd2-383e-5cba-992a-c8788ac64964 |  | note | Relevant Council drawings:
label | 4fed62d2-4a73-52a9-b5f9-10349528996b |  | note | • EDCM 501
label | feffdea7-0b1b-56f7-bd06-a4cb8cd683bd |  | note | • EDCM 502
label | 42146818-3f06-5882-9145-39fbf9bda4a4 |  | note | • EDCM 503
label | e9aa9d49-09d3-5a53-a516-5154db08a05e |  | note | – – – – – – – – – – – – – – – – –
label | b0ecc7d8-25a1-5430-bb43-9bc6403af567 |  | note | ACCEPTANCE CRITERIA: Where applicable, excavation to allow for increase in the bedding and slab thicknesses at crossing.
label | 3752e101-f1a7-5be3-b163-7d15d5e0ce95 |  | note | • Consult the Relevant Council drawings for dimensional tolerances for thicknesses, grades and ramp lengths.
label | a99040e7-9699-52f1-b33c-5ec216697087 |  | note | – – – – – – – – – – – – – – – – –
label | d4d308d7-2001-5df6-ae5c-1aa908b710dd |  | note | METHOD: Visual, Measure
label | a91f635e-07e6-57c4-9b7a-58399b857594 |  | note | – – – – – – – – – – – – – – – – –
label | c88c405f-7ee1-58cd-b55e-3536ff7d7f22 |  | note | FREQUENCY: Where applicable, each lot
label | 139cdefe-7068-5093-b7c3-b9b0cd76b890 |  | note | – – – – – – – – – – – – – – – – –
label | 448bb1da-2769-5074-be70-06b4995343e5 |  | note | CATEGORY: IP
label | b7d27708-9ee7-5edb-84c0-8683c5e88f4b |  | note | – – – – – – – – – – – – – – – – –
label | 10f7aedf-5638-5131-9d94-3912623aa1d2 |  | note | RESPONSIBILITY: SE/PE/SPE
label | 9ad9e947-e11e-5353-8d50-b67c84f51cd0 |  | note | – – – – – – – – – – – – – – – – –
label | d1e724cf-258d-5383-8b82-4324d3983d07 |  | note | VERIFYING DOCUMENTS: This ITP
text | ab0bed56-a63f-53e0-85d9-3c3768853af1 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.3 Bedding Material Placement & Compaction
label | a62ad7f9-4418-5ca1-928f-c49c2d027057 |  | note | REFERENCE: 703.21 IFC Drawings
label | c3ce64b6-83a1-50c2-be61-8a81eb8c9f1d |  | note | IFC Drawings:
label | d8b5e32f-7954-53db-a0fc-0111652fa431 |  | note | MRP-052-C-SME-DRG-13-MPK-CPT-0101 & MRP-052-C-SME-DRG-13-MPK-CPT-0102
label | 8044e6f6-006c-588b-9ed5-fc2371e95a55 |  | note | Relevant Council drawings:
label | 51233942-2fcd-5e19-b11a-d7587c69d5dd |  | note | • EDCM 501
label | 3b8c50c7-dffe-516e-8e4f-a01a931f8610 |  | note | • EDCM 502
label | c4f3086d-2b93-5627-9ee4-37ca76b0d740 |  | note | • EDCM 503
label | 0b6eb486-2761-52c8-abe2-33fdf99a07b2 |  | note | – – – – – – – – – – – – – – – – –
label | 9331c19a-ffa3-5aca-9edf-2d6a5857675e |  | note | ACCEPTANCE CRITERIA: Place bedding material to the minimum thicknesses (post-compaction) as per the IFC drawings:
label | fc507a4b-5a4a-536f-896c-1311fca9232c |  | note | • Footpath: Bedding shall 100 mm compacted thickness
label | 2597f2c8-1a7c-55a9-8b5b-a7c03c86cada |  | note | • SUP: Bedding shall be 150 mm compacted thickness
label | 81060463-04f4-53e8-9507-3e2d267ef39e |  | note | • Bedding shall be trimmed to the appropriate levels, moistened as necessary, and firmly compacted.
label | 5bb277d5-6e48-5913-b873-3adfe7cd528c |  | note | • The foundation shall be true to grade and cross section as shown on the drawings by filling and excavating as necessary.
label | f0ce2970-0397-5155-b208-b8cf476225ac |  | note | • All soft wet or unstable material shall be removed to a depth of not less than 100 mm below the design level of the underside of bedding and filled with bedding material moistened and compacted to form a stable foundation.
label | d24c54bf-92ec-54c7-84bf-f9ba8f875019 |  | note | Attach: Bedding Material Delivery Dockets
label | ef5f332c-6d2d-5256-b629-050829a7fa98 |  | note | – – – – – – – – – – – – – – – – –
label | 056d5136-8b52-508c-a956-08dc29cdb080 |  | note | METHOD: Visual, Measure
label | 1986796f-5434-5afe-9f19-cf7ab9afbc46 |  | note | – – – – – – – – – – – – – – – – –
label | db77ab9a-f487-5703-aefa-2ba189dc8e55 |  | note | FREQUENCY: Each lot
label | e34b33c7-6cdc-5080-a18a-d1aa3c7e4c67 |  | note | – – – – – – – – – – – – – – – – –
label | 96d63fab-922d-5a1a-a212-3029f6484d53 |  | note | CATEGORY: IP
label | 24451a31-0f6e-5db8-b3fb-ca2af48243da |  | note | – – – – – – – – – – – – – – – – –
label | 5b2d9421-39ec-5824-afb4-2081fb005df9 |  | note | RESPONSIBILITY: SE/PE/SPE
label | 307a4c9e-4a7e-566f-a689-ce8232778445 |  | note | – – – – – – – – – – – – – – – – –
label | 70781a26-aee0-5b2d-9d75-644c0c15ad45 |  | note | VERIFYING DOCUMENTS: This ITP
text | 307c4ad5-0114-5da5-968f-2d4cbba7549f |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.4 Shared User Path - Compaction Testing
label | f7055046-1704-54b5-892c-a9790d05e412 |  | note | REFERENCE: 703.21
label | 96ff219a-a485-5220-8a92-23859ed2009c |  | note | 304.08 (a) & (b)
label | c276e749-4663-5803-804f-0a94cc0e7ba8 |  | note | 304.11 (a)
label | 02036880-2462-5910-b34c-cd6ba4720664 |  | note | – – – – – – – – – – – – – – – – –
label | 44906deb-d2c4-57c8-8deb-e0fc1e814f35 |  | note | ACCEPTANCE CRITERIA: Compaction shall meet the following requirements:
label | 770e0c5d-745f-5624-81f1-3442f2f170c3 |  | note | • Scale of Surface Level Measurement = Scale C
label | 54baf202-4778-50d9-b87b-a0d7c3f2e867 |  | note | • Material during compaction shall have a moisture content of not less than 85% of optimum. (1 test)
label | faf5aed2-cd01-5c3c-a671-fcaed180ee50 |  | note | • Mean Value of Density Ratio % (3 tests) not less than 100%
label | 7c93a7d5-1084-57ca-8617-236331b593f4 |  | note | Attach: Moisture Content Test Results
label | 4ac60631-d0f6-59c9-ad38-372fec2c0910 |  | note | Attach: Mean Value of Density Ratio
label | 29c08839-6bcf-58c0-89bc-dd6e0e7d3fb6 |  | note | – – – – – – – – – – – – – – – – –
label | d7be9aca-0344-5215-9fa5-7d0d9283761a |  | note | METHOD: Document Review, Visual
label | f8145038-161c-5a4c-b352-5b95231d43a8 |  | note | – – – – – – – – – – – – – – – – –
label | a787436c-eebd-5b64-8478-bd927394682e |  | note | FREQUENCY: Where applicable, each lot
label | 06fce67f-78d3-5d75-9e81-3975290504e2 |  | note | – – – – – – – – – – – – – – – – –
label | deef7d98-5542-562f-934c-a3ee2c166610 |  | note | CATEGORY: IP
label | 86c6b7f3-19f7-5292-9280-638677a471a5 |  | note | – – – – – – – – – – – – – – – – –
label | 1763033f-cf33-517a-81ea-c88315d7f593 |  | note | RESPONSIBILITY: SE/PE/SPE
label | ccb9236b-9562-56af-8265-51ab8af71073 |  | note | – – – – – – – – – – – – – – – – –
label | dcc98a4a-7d76-5b58-8efa-fdd69b6f75df |  | note | VERIFYING DOCUMENTS: This ITP
text | d3289d79-b4a5-5819-9eb6-258c58ca6b2f |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.5 Shared User Path - Proof-rolling
label | edfb8fc4-2108-5a60-a01c-21c09d6104f6 |  | note | REFERENCE: 703.21
label | 5f335392-563a-545a-8778-97331790766e |  | note | 304.08 (b)
label | eb13201b-147f-590f-9e17-4e79c1f33f98 |  | note | – – – – – – – – – – – – – – – – –
label | b28025f0-967f-5862-879b-dd2774a67dcd |  | note | ACCEPTANCE CRITERIA: Bedding material to be compacted and proof rolled before any construction.
label | 9d3e24d4-1acd-550d-9ac0-b6ee857a1a73 |  | note | • Withstands Test rolling without visible deformation or springing.
label | 54916573-a0bd-582f-bc5b-67d34080e7fc |  | note | – – – – – – – – – – – – – – – – –
label | b8dac25b-d8af-59b9-b7a1-07ad7300fc4f |  | note | METHOD: Visual
label | b5a190da-76a1-5235-b98d-53f5334de64d |  | note | – – – – – – – – – – – – – – – – –
label | 433ddf4c-d15a-53c8-ba66-c8461794edd1 |  | note | FREQUENCY: Where applicable, each lot
label | e6b52f9f-f1a9-5b54-a588-70579cb482db |  | note | – – – – – – – – – – – – – – – – –
label | efc08a40-9130-56fe-a353-b68995f3b27e |  | note | CATEGORY: HP
label | e8cb9039-bfc2-5db4-b3f9-ae985db55988 |  | note | – – – – – – – – – – – – – – – – –
label | 76a14fb2-a069-531a-a665-43fe2b564cb3 |  | note | RESPONSIBILITY: Nominated Authority
label | 64f5b852-408c-5a4f-a488-3b2afc35e65c |  | note | – – – – – – – – – – – – – – – – –
label | 877c355f-6981-5c62-b084-8ac07c6e820f |  | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
text | e3057b95-07bc-529e-9957-5c43f9c05d52 |  | textbox | Date Completed:
holdpoint |  |  | signoff | NOMINATED HOLDPOINT AUTHORITY
checkpoint-status |  |  | checkpoint | 5.6 Formwork Construction & Placement
label | 26993c83-77fc-5452-8e1a-0fe1c08ed83a |  | note | REFERENCE: IFC Drawings
label | 176c8234-27de-5842-9b43-29b711c3d8af |  | note | 703.12
label | a3cf90c9-2709-5c47-82bd-92973de9b538 |  | note | – – – – – – – – – – – – – – – – –
label | 56e04314-8522-59cd-927b-a73f48d7f9a4 |  | note | ACCEPTANCE CRITERIA: Formwork is designed and constructed in such a manner so it can be removed without damage to the concrete.
label | f7576f40-d753-5b74-9237-9680a8cea8f2 |  | note | • Formwork to be rigid, braced, full depth of the concrete & tied together to restrict movement during concreting operations to maintain dimensional conformance.
label | 5ecaa007-bce1-5504-8046-6185c3bb17c3 |  | note | • Joints in formwork shall be constructed such that loss of mortar is prevented.
label | bb8b3b60-d586-5a14-8d46-a7f4462b789a |  | note | • Prior to placing concrete in an earth excavation, formwork shall be erected so that fresh concrete is not placed directly against the sides of the excavation.
label | a3ae53be-c8e2-5cea-993a-e9577be979dd |  | note | – – – – – – – – – – – – – – – – –
label | 9057814d-e7c3-5cec-8464-3e7ba6035cdc |  | note | METHOD: Visual, Measure
label | ca6c84c9-6ac3-5462-96b4-df1a7112cc32 |  | note | – – – – – – – – – – – – – – – – –
label | 17cd11c0-7da2-5968-a241-c0f7e86327ea |  | note | FREQUENCY: Each lot
label | 23afed9a-5191-54b6-ba5f-5510d7732b8e |  | note | – – – – – – – – – – – – – – – – –
label | 0fe5d45f-2f94-5a3d-bbf1-dea90642ced8 |  | note | CATEGORY: IP
label | 9ea62e38-f7e2-51c8-9d16-1fe3cc3c9234 |  | note | – – – – – – – – – – – – – – – – –
label | 25a0c60d-b1ef-5c94-8a59-79e073928626 |  | note | RESPONSIBILITY: SE/PE/SPE
label | d0f3fd76-b833-59b5-b5be-8c374d804bff |  | note | – – – – – – – – – – – – – – – – –
label | e21a9ccb-2647-50cf-9e2e-96cf4d0e2a60 |  | note | VERIFYING DOCUMENTS: This ITP
text | 220abcae-6cd3-5548-9a28-9b5a6bb2c4d7 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.7 Construction Joints & Matching Existing Surfaces
label | 8a8b09d1-8f99-5a05-8c18-ec315f846fea |  | note | REFERENCE: IFC Drawings 703.24
label | 7bc5cf52-36a7-5147-9915-e99bccb1655e |  | note | Relevant Council Standard DrawingsRelevant Council drawings:
label | 82e2f162-32f6-5c1f-a31e-ec8227919785 |  | note | • EDSM 401
label | 6f380e73-1b6c-52a5-8626-f12122f896bf |  | note | • EDCM 501
label | 83e2cab0-1f9e-5e3a-982b-04ff2763c3d5 |  | note | • EDCM 502
label | cf05ebfc-deae-546d-b4d6-6ce32c749274 |  | note | • EDCM 503
label | 8ceaf1cc-cb2b-5339-87e4-3fe1f9af42b7 |  | note | – – – – – – – – – – – – – – – – –
label | 49ca563f-72af-5937-9861-5bd3d540851a |  | note | ACCEPTANCE CRITERIA: Where applicable, construction joints shall be placed where the new construction ties into existing structures.
label | 22e95ed1-1dcd-58e9-b520-f6695f7e16bb |  | note | • Consult the relevant Council Standard drawings for the joint detail, these may require:
label | 53202686-541b-5971-8d5b-fbc109adac5c |  | note | i. Concrete cutting of a shear-key
label | c046e412-fc46-5ef5-b891-71594fd70def |  | note | ii. Surface roughening
label | b7e24e42-85c7-54a3-bc1e-1b0c4378bc54 |  | note | iii. Drilling and insertion of dowel bars (may also be galvanised)
label | b28ac9a4-c874-5c17-af71-1bc7c414ab3f |  | note | iv. Cutting a groove for sealant
label | 7e98867c-fe98-5410-937f-c6bdbf8bd84a |  | note | • Where it is necessary to join to an existing section of profile different from that being constructed, the change of profile shall be made at a constant rate between 10 and 20 mm per metre.
label | 1de8c9e7-8d37-51fe-82f8-c08e0983fde2 |  | note | • Transitions between different profiles shall be made in accordance with the drawings.
label | a09cefe6-aa97-5882-b0ab-07edaf7829ab |  | note | • Matching of new to existing concrete paving shall be such that it appears identical to the existing section.
label | 974eddfe-bd5c-519c-b238-3eb13a0df08d |  | note | – – – – – – – – – – – – – – – – –
label | 934846c8-17fb-5a9f-902b-a7d0f1065e4c |  | note | METHOD: Visual, Measure
label | 76e4d39a-eafd-5933-bcd5-e715c2716b39 |  | note | – – – – – – – – – – – – – – – – –
label | f0620072-cafd-5a1d-adb6-de05d497fc22 |  | note | FREQUENCY: Where applicable, each lot
label | 05fd7679-1671-5d50-9d64-fec32a1f18d0 |  | note | – – – – – – – – – – – – – – – – –
label | 3736cd6d-deda-57b1-84d4-1204146bbc34 |  | note | CATEGORY: IP
label | 49edea88-bfdc-5bce-85de-ae2a58d1abbb |  | note | – – – – – – – – – – – – – – – – –
label | 5814f3a5-c87e-52db-8fd4-f9ae51338a49 |  | note | RESPONSIBILITY: SE/PE/SPE
label | cb657ea5-7766-59ca-8a3f-b78283f9f4b7 |  | note | – – – – – – – – – – – – – – – – –
label | 2deca750-4fcc-5eee-8732-55d48f5865a4 |  | note | VERIFYING DOCUMENTS: This ITP
text | 8fd72735-aa04-5f2e-ab73-40223899798e |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.8 Isolation Joints
label | ed4496cf-c91c-5951-b62c-9a41cd3a6ddc |  | note | REFERENCE: IFC Drawings 703.26 (c)
label | 39db067e-43e5-5c21-87c6-ab703339097d |  | note | Relevant Council Standard Drawings
label | 67a05e49-8378-5c62-ada5-98b4567e9938 |  | note | • EDSM 401
label | 4ad4478b-5e22-565c-91a5-0784b162e000 |  | note | • EDCM 501
label | 2a4eb86a-7a25-5d06-bde4-65d63509b4ef |  | note | • EDCM 502
label | c9e6b669-f2fe-5154-868e-72e558d1b2e6 |  | note | • EDCM 503
label | 6d6bbb6e-e00c-5f78-89de-e3ee3c6d28ed |  | note | – – – – – – – – – – – – – – – – –
label | c1b0b43c-a59a-51cf-b1e8-ccb4f5ae7377 |  | note | ACCEPTANCE CRITERIA: Where applicable, isolation joints shall be placed:
label | c06e86d1-9774-5ed5-9a86-f67e131f4672 |  | note | i. around all abutting structures such as pits, utility services, power poles, kerbs and other such features
label | 8d8ea595-abf7-5898-87dc-9db659df9000 |  | note | ii. at any location marked on the drawings
label | 76b68988-7455-5c86-bf1b-a0280ac3710a |  | note | • The joint shall be made with a compressible material extending for the full width and full depth of the paving and secured into position prior to concrete operations.
label | 4b9c7047-bd7e-5374-81e3-17076ca26e13 |  | note | – – – – – – – – – – – – – – – – –
label | 5725d20f-eb56-5da3-89fd-b103f9b76d5a |  | note | METHOD: Visual, Measure
label | bc6ad154-0982-5f98-b925-ef473be442b0 |  | note | – – – – – – – – – – – – – – – – –
label | b0f0c8e4-7346-543c-8a17-88b31e565c78 |  | note | FREQUENCY: Where applicable, each lot
label | 2c52a4d4-df1c-5910-8931-714633f28a70 |  | note | – – – – – – – – – – – – – – – – –
label | a37b60a8-181e-55b2-b63c-c7870c73c765 |  | note | CATEGORY: IP
label | a4da6d0f-bbfa-528b-b7f9-ee5180db5c46 |  | note | – – – – – – – – – – – – – – – – –
label | 2d210148-6b06-5456-88c8-d072ae3c7cd1 |  | note | RESPONSIBILITY: SE/PE/SPE
label | efd0419a-3dbc-5aed-86d2-d81832aa773b |  | note | – – – – – – – – – – – – – – – – –
label | 536a1900-70a2-5bb9-b492-7898a36303fb |  | note | VERIFYING DOCUMENTS: This ITP
text | 869c6d21-7a72-5d3c-8f77-d3ca7e640ae0 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.9 Expansion Joints
label | ed79a288-24ac-5453-9387-19dc13db620e |  | note | REFERENCE: IFC Drawings 703.26 (a) (ii) & (b) (i)
label | 9b72ee9a-8ece-5ca6-a335-8ab6251491e4 |  | note | Relevant Council Standard Drawings
label | 27c17791-0b8c-5a3d-9c8b-1dc0f7a925f2 |  | note | • EDSM 401
label | af2bf872-7619-59f1-bb20-7f554ad26982 |  | note | • EDCM 501
label | 5d4646a9-f835-5898-ac0c-7d72d39d9684 |  | note | • EDCM 502
label | 9c2d9834-d306-51ee-9884-e44373b75bfa |  | note | • EDCM 503
label | 8d581f1c-d71e-5d7d-8787-bb0aad048d3c |  | note | – – – – – – – – – – – – – – – – –
label | ffb5831e-9f60-51c2-8e04-55ff2df34c33 |  | note | ACCEPTANCE CRITERIA: Where applicable, expansion joints shall be placed:
label | 31c85add-85c2-5ca6-9b77-5ac273cfa3cd |  | note | i. on either side of vehicle crossings
label | baca2adc-be89-51a0-b16f-9178e023d57a |  | note | ii. at junctions with existing footpaths and shared use paths
label | 8f5cddeb-abad-5d21-82d4-6cc6cd8c6942 |  | note | iii. at junctions with bridges
label | 586e2018-eb41-592c-a8b5-e406fe3a2d6b |  | note | iv. at intervals not exceeding the Council maximum spacings (typically 12m).
label | fa9462c5-061c-58ee-804b-c3988f8c791b |  | note | • The joint shall be made with a compressible material extending for the full width and full depth of the paving and secured into position prior to concrete operations.
label | 99e5eeaa-19a6-5b6d-bbfb-0bf2163dc61e |  | note | • Dowels shall be installed in accordance with the details and locations as shown on the relevant Council Drawings.
label | 5c54e5c4-37d7-5e22-96eb-ba972ebc7b8c |  | note | • Alternatively, a proprietary joint system may be used, but ensure that the top of the system is flush with the formwork at each side to prevent future trip-hazards.
label | 2ca08b03-fce5-58e7-b32e-5f96c7081831 |  | note | – – – – – – – – – – – – – – – – –
label | 5ed258a8-e6cd-5ce3-8cea-e16937398347 |  | note | METHOD: Visual, Measure
label | 12ac50c8-93f1-56f8-9661-93733a5d7cad |  | note | – – – – – – – – – – – – – – – – –
label | 123431c6-9920-5476-b5d7-75062c113e7d |  | note | FREQUENCY: Where applicable, each lot
label | 99a146e8-819a-5f04-a537-d4299f502010 |  | note | – – – – – – – – – – – – – – – – –
label | c9cc577f-50ad-5571-93ab-8bf39a003bf2 |  | note | CATEGORY: IP
label | 1f952491-d27c-5f18-9d8f-f8877939399f |  | note | – – – – – – – – – – – – – – – – –
label | da859022-8219-5fd5-bba7-87b4efd334c2 |  | note | RESPONSIBILITY: SE/PE/SPE
label | 527c57f6-18c2-5ccc-945a-be344114838e |  | note | – – – – – – – – – – – – – – – – –
label | 5c62ce19-9ddf-58cf-b0cc-ce2509fa0239 |  | note | VERIFYING DOCUMENTS: This ITP
text | 77c40173-c4c7-58f7-88f1-6518aef8818c |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.10 Reinforcement Placement
label | 8a2a3b92-b378-5656-89d7-0b07556c8194 |  | note | REFERENCE: IFC Drawings 703.13
label | 4133543a-597b-5e10-8f18-e85659481f77 |  | note | • EDSM 401
label | 600f415f-c2b0-5437-a58d-3ff9dbf0b719 |  | note | • EDCM 501
label | 784ef684-668f-5601-b7d5-7e71c3645616 |  | note | • EDCM 502
label | bb3affb7-c3de-5e7d-aedf-8bf458a69e60 |  | note | • EDCM 503
label | 803b0eb8-9dd4-5e60-b2ef-a6e5480dffde |  | note | – – – – – – – – – – – – – – – – –
label | 853353b2-1699-591f-8f75-4f6a86e3f2fb |  | note | ACCEPTANCE CRITERIA: The correct mesh type and location as shown on the IFC drawings.
label | e9a52d0f-d019-5352-b57a-f802f4ae1ab7 |  | note | — Footpaths, Residential driveways and Median islands infills: SL72
label | 90252b38-9017-5414-8802-9cd9eed087be |  | note | — Industrial Crossovers: SL82
label | a9c2518a-496b-522e-b370-ff1573272d16 |  | note | — Traffic Islands: SL72
label | 09868269-99ea-5a3e-956c-f7054f1ae906 |  | note | — SUP: SL82
label | 8389ccc1-ef23-5bd9-8861-661ee4ca2f9e |  | note | • Minimum cover of 50mm at edges has been achieved (including tie wire locations).
label | c2a5e258-0806-51cc-9341-d14bbf14426d |  | note | • Any splice lengths achieve the minimum length and are in contact for this length.
label | 6e8366ab-ac86-58ec-a127-8efc167d7031 |  | note | • The reinforcement surface condition is free from dirt, debris and damage.
label | dcee12c7-5570-56d6-afe6-1d01e1144607 |  | note | • The resulting cage securely held with sufficient ties and/or bar chairs to limit displacement or deformation during the concrete pour (typically 900mm crs maximum).
label | 3d2437c5-bdd5-517c-890a-2d1a495c4c13 |  | note | • Wire chairs with or without plastic tips, bricks or pieces of timber or coarse aggregate shall NOT be used to support steel reinforcement.
label | 3ac8e3e5-fb71-5785-895f-ff6807a165e2 |  | note | – – – – – – – – – – – – – – – – –
label | 99791648-1a85-5aae-a056-bebea5652979 |  | note | METHOD: Measure, Visual
label | 25e7940e-4f80-5fe9-84d4-d92b4ff34543 |  | note | – – – – – – – – – – – – – – – – –
label | 66429bad-dd09-53c8-bb0a-d27cf41ed5ca |  | note | FREQUENCY: Each element
label | bd172e1a-a229-50c0-bf92-99ec507cf49d |  | note | – – – – – – – – – – – – – – – – –
label | 37e4d7f7-4e03-5932-881a-943657e10666 |  | note | CATEGORY: IP
label | 8936e843-2ee4-5060-9811-d27925a7ab59 |  | note | – – – – – – – – – – – – – – – – –
label | e496d13b-8e06-5e21-9bbf-c274a7c889f4 |  | note | RESPONSIBILITY: Foreman, SE/PE/SPE
label | 72d36f5a-88e3-5cfe-a573-ac4bdfd84a2e |  | note | – – – – – – – – – – – – – – – – –
label | 43cdaaa8-a2e9-5e9f-b49c-323af5c775a4 |  | note | VERIFYING DOCUMENTS: This ITP
text | 8a4feb4a-8138-5b9b-af2e-708ded5bd9bc |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.11 Pre-pour Survey
label | f8cc220e-eae7-5846-9416-914b6d86c92d |  | note | REFERENCE: IFC Drawings 703.15
label | c6bfddcb-49c5-50aa-a343-0db2093ca429 |  | note | – – – – – – – – – – – – – – – – –
label | 7c09b625-1c95-5c42-96e9-51138736d5a8 |  | note | ACCEPTANCE CRITERIA: A pre-pour survey carried out by a surveyor.
label | 461d5096-1466-5b37-810c-c5406c480094 |  | note | Erected formwork and base layer within the tolerances below:
label | 5d0c15cb-1c3e-564f-b9a1-75dc6facdc02 |  | note | • Departure from RL = ±10mm
label | d13e71e1-48f1-5b6c-93cb-776e6529f309 |  | note | • Departure from alignment = ±10mm
label | fc8bac5e-9566-554b-bdfe-5a69479ead9d |  | note | • Rate of change of deviation from RL or alignment = 10mm in 10m
label | f3585ed9-c477-5ac6-8c8a-cb5e2d32013a |  | note | • Irregularities in alignment = 5mm in 3m
label | d1929f03-1641-508c-9697-bd1798cd059c |  | note | • Section dimensions = ±5mm
label | d36b17d3-b832-547b-892b-2ae83733fb4d |  | note | • Section dimensions (less than 25mm) = ±3mm
label | b3be4eb2-75a7-5cc6-b5e9-7f3e98421aea |  | note | • Width of pavement = -5mm, +15mm
label | 84d8ac3b-9ef7-5c63-8b6a-51ebded9a883 |  | note | – – – – – – – – – – – – – – – – –
label | c0bbfe2e-592d-52a3-9d62-4e1e0df3d75f |  | note | METHOD: Measure, Visual
label | a1ef62a1-cef3-5bb0-b8f9-473bedb5b30a |  | note | – – – – – – – – – – – – – – – – –
label | 925ed43a-4f3e-5336-96ed-0ac681acf360 |  | note | FREQUENCY: Each lot
label | ab9287f0-47fe-5598-948d-744127c1963f |  | note | – – – – – – – – – – – – – – – – –
label | b970d517-01db-557b-b406-d9300a8e230c |  | note | CATEGORY: HP*
label | 04d1b7db-fc98-5975-a28b-32845b025555 |  | note | – – – – – – – – – – – – – – – – –
label | 8a53c71f-25d2-526d-8301-5c104418755a |  | note | RESPONSIBILITY: Surveyor, SE/PE/SPE
label | fbf98017-68fe-509e-bbec-ba83d65d8d4c |  | note | – – – – – – – – – – – – – – – – –
label | 5544992c-10aa-5128-9ab2-f5ccc28effb5 |  | note | VERIFYING DOCUMENTS: This ITP
text | 8fb8774a-36a2-51d4-9595-bf9d0b58643a |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.12 Pre-pour Inspection
label | 9cb9973d-b01c-5c67-af8d-a952ccf78e7b |  | note | REFERENCE: Section 703.09
label | 1712d846-26eb-59dd-9378-1c60bc5ba38e |  | note | Section 703.21
label | dfff3cce-d9bd-510c-a5ef-75d2697f5a8f |  | note | Section 610.17a), b) & c)
label | 00a462d1-dee7-5210-960d-301a7168beb8 |  | note | – – – – – – – – – – – – – – – – –
label | a127eb97-b110-5ce7-a351-e8c599a69da0 |  | note | ACCEPTANCE CRITERIA: Inspection to ensure that forms, reinforcement, joints, dowels and other embedments conform to the requirements of the specifications and drawings.
label | d57a7c34-5f20-5f74-8302-140263ac9b4d |  | note | • Immediately before concrete is placed, the bedding shall be moist but shall have no free water on the surface.
label | 241ad0ed-7147-50cd-9642-65e3fbe1ebd9 |  | note | – – – – – – – – – – – – – – – – –
label | ec710015-5f2d-57a2-bae8-3f9521421c4c |  | note | METHOD: Measure, Visual
label | d7626c04-d88c-5a85-ac66-26117d060a11 |  | note | – – – – – – – – – – – – – – – – –
label | 3569d93b-5045-56a8-870a-a230c394a659 |  | note | FREQUENCY: Each lot
label | 161bd7f7-da24-5eb1-86a1-dfa4f99433e0 |  | note | – – – – – – – – – – – – – – – – –
label | ab718df3-7cfb-5511-80eb-32fd7b3d7ae5 |  | note | CATEGORY: HP*
label | 45cccfb2-500a-5825-811c-b351d99358d4 |  | note | – – – – – – – – – – – – – – – – –
label | 6daf87e7-2071-5717-8a36-34f91b4d565a |  | note | RESPONSIBILITY: SE/PE/SPE
label | 698830a0-e138-588e-a3a9-ec8b5156d616 |  | note | – – – – – – – – – – – – – – – – –
label | 7d802580-3d4b-54d8-a857-968bb3a7dd6d |  | note | VERIFYING DOCUMENTS: This ITP
text | da944a5c-0008-5681-9259-22ae8a98b0c3 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.13 Weather Conditions & Evaporation Limits
label | 1b7ce114-5047-579b-95f7-909e4ff65cb1 |  | note | REFERENCE: 703.09
label | 49ee9f3d-43be-5d74-b6f6-5747f31faf7d |  | note | 610.17 (a - f)
label | d7b70446-c046-5ea3-bbf3-a7c1eef585ee |  | note | Table 610.171
label | 9f0c2c67-0acd-5117-a9da-11411fe77061 |  | note | – – – – – – – – – – – – – – – – –
label | bba4e4f2-c3da-5a1a-9260-5c93f4def278 |  | note | ACCEPTANCE CRITERIA: Concrete shall not be placed when the air temperature at the point of placement is less than 5°C or greater than 35°C.
label | 1b66151b-5f6e-56f6-8033-74005a865b17 |  | note | • The temperature of concrete, measured immediately prior to placing, shall not be less than 10°C or greater than 32°C.
label | b89ca60e-bad1-5827-b3b2-4799aa5028bb |  | note | • The air temperature, relative humidity, concrete temperature and wind velocity are measured to determine the evaporation rate of water from the concrete.
label | 601874fd-8b64-5e8a-a13f-d3c025c4c068 |  | note | • When the evaporation rate exceeds 0.50 kg/m²/hr apply evaporation retardant at the rates specified on the manufacturer’s TDS.
label | c378cc48-e507-5c26-80e9-6aae670ee0a8 |  | note | • Record: Required information on the Concrete Pour Record.
label | 6962cdcc-0355-5e2a-acdb-f56a5c52a8a6 |  | note | – – – – – – – – – – – – – – – – –
label | b02e77ed-c43f-5229-8b36-0ae1eccc18cf |  | note | METHOD: Measure, Visual
label | a2a8d1fd-e690-5e89-ba61-3a834496da73 |  | note | – – – – – – – – – – – – – – – – –
label | b7c3252f-6a6f-5f13-a520-a01cf480c309 |  | note | FREQUENCY: Each lot
label | 2f8208e7-6d5c-5c83-a49e-94e97bee422b |  | note | – – – – – – – – – – – – – – – – –
label | 137db7ff-93ac-5108-a63e-31cf6762676b |  | note | CATEGORY: IP
label | cf61b922-48eb-5357-83dd-323e756c8a51 |  | note | – – – – – – – – – – – – – – – – –
label | 224f61ea-70ee-5096-a915-aa4c8a36cf19 |  | note | RESPONSIBILITY: Foreman, SE/PE/SPE
label | 87f28a89-c99b-5e09-a325-12551bd26f08 |  | note | – – – – – – – – – – – – – – – – –
label | de5bd5f2-476d-5d11-8546-92eff40b9acb |  | note | VERIFYING DOCUMENTS: This ITP
text | e9ddba16-afab-5a8b-ab39-658e26363e18 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.14 Concrete Testing - Sampling Frequencies-Footpath
label | 7c822308-28d3-5d9f-8e1d-153738695dab |  | note | REFERENCE: 703.11
label | 91a6eb39-79d4-5589-bb42-68e89b032363 |  | note | AS 1379-2007 Clause 6.2
label | 38ce9c3a-d571-5e7a-ae84-06ec2350f0eb |  | note | – – – – – – – – – – – – – – – – –
label | 38a4dba2-422c-5d00-9a5a-41e416ace718 |  | note | ACCEPTANCE CRITERIA: The frequency of sampling and testing shall provide at least one sample at the point of discharge to be tested of each 50 m3 or part thereof of each strength grade placed on any one day. Where less than 50 m³ is provided for any one day then one sample shall be tested of each strength grade
label | 2273e34e-7685-5ad4-aea3-7647243663b3 |  | note | • Correct quantity of cylinders manufactured per sample.
label | d6bca5d7-78c1-530c-8960-18c3d5262582 |  | note | • Record: Required information on the Concrete Pour Record.
label | c3801267-b369-5782-8cac-ef093809ed59 |  | note | – – – – – – – – – – – – – – – – –
label | b565ab4f-6af5-5ea5-a807-81bf5a4ad375 |  | note | METHOD: Test
label | b608fc54-639f-564a-b3b4-e30bda05c8fc |  | note | – – – – – – – – – – – – – – – – –
label | e9b8da59-52f7-57d3-8cf1-f356fd19689b |  | note | FREQUENCY: Each lot
label | dbc4fbe7-9ac9-5dfb-a441-aabb3d60436b |  | note | – – – – – – – – – – – – – – – – –
label | d9469718-0e8f-5d03-90fc-02c82c40e31a |  | note | CATEGORY: IP
label | d9db5702-8281-585b-9b29-e7dd42fe129c |  | note | – – – – – – – – – – – – – – – – –
label | 27edf007-e425-5fdd-b5ec-0c32d2455a68 |  | note | RESPONSIBILITY: Concrete Tester, Foreman, SE/PE/SPE
label | 6b12c881-92e8-5c15-933f-bf15ab1efb33 |  | note | – – – – – – – – – – – – – – – – –
label | 9893d0a2-171a-5de9-9526-41fab35c8993 |  | note | VERIFYING DOCUMENTS: This ITP
text | cb7bfef7-d9a0-5c81-bc56-81d62a5435da |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.15 Concrete Testing - Sampling Frequencies-SUP
label | cfc2b2c7-e269-599e-a57c-d31045c0afff |  | note | REFERENCE: 703.11
label | fef7fa7f-c7ed-5034-9891-815ce8a3dca0 |  | note | 610.16 (b)
label | a5738060-fe3b-526a-acd5-83b3c6df7ec3 |  | note | – – – – – – – – – – – – – – – – –
label | 42bb920f-aac9-5fcc-938e-fdedcf3e6d5c |  | note | ACCEPTANCE CRITERIA: Concrete cast in one continuous operation to be tested at a frequency as shown below:
label | 925fc771-c0e7-51ff-8df2-147775ff2690 |  | note | Shared User Path:
label | 275b4465-e869-5264-b055-0968251bf5ed |  | note | • 0m3 to 10m3 = 1 sample
label | ab9ebe12-612f-5b8c-9252-8199e0a6862b |  | note | • 10m3 to 25m3 = 2 samples
label | fa5a4c9b-bd38-5a07-91f5-55c332768b7f |  | note | • 25m3 to 50m3 = 3 samples
label | c097be04-cbe6-5a39-a000-aef6c5392cfa |  | note | • 50m3 to 100m3 = 4 samples + 2 no. VPV cylinders.
label | ea27dd71-266a-5d40-99d1-40a5c6e16d55 |  | note | • For each additional 50m3 and additional sample shall be taken.
label | 20a8183e-d0c6-5563-a7f0-570924c2d74c |  | note | • Each sample shall consist of 1 no. slump test and 3 no. compressive strength cylinders minimum.
label | 8a0685f2-4d88-5fd3-8248-8be283f61f1d |  | note | • Compressive strength cylinders = 1 no. 7 day strength, 2 no. 28 day strength.
label | d8fba83e-7470-5ffe-9424-fa04132b37dd |  | note | Footpaths:
label | 85354775-fe96-5eef-a58d-5d1bbab2eb8d |  | note | • 0m3 to 50m3 = 1 sample
label | 3f8e2105-ea7b-5838-899f-2d9bda23418c |  | note | • Each sample shall consist of 1 no. slump test and 2 no. compressive strength cylinders minimum.
label | be1bd30c-788e-53e8-bcfd-259df13f51a8 |  | note | • Compressive strength cylinders = 2 no. 28 day strength.
label | a0add223-7449-5303-aa7c-6ce3b1039823 |  | note | • Correct quantity of cylinders manufactured per sample.
label | 92c3fdd3-21a2-5fd9-bfc0-882d33da3a3f |  | note | Record: Required information on the Concrete Pour Record.
label | 44ea6652-ae05-55ec-bde4-28dc2b88f0f1 |  | note | – – – – – – – – – – – – – – – – –
label | 638979f1-2c74-5154-a632-cc1458c6f578 |  | note | METHOD: Test
label | d4d842e8-9007-55df-8058-731e1d3d13fc |  | note | – – – – – – – – – – – – – – – – –
label | a3919df6-a94f-56a7-9a15-a23ed450c7eb |  | note | FREQUENCY: Each lot
label | f8195f6e-8dd4-54e3-9fe2-a1131157f1e1 |  | note | – – – – – – – – – – – – – – – – –
label | 523a6119-f186-597a-a542-0e567780eb58 |  | note | CATEGORY: IP
label | b85f56b2-1047-57d4-ac46-2395059f1542 |  | note | – – – – – – – – – – – – – – – – –
label | df488a7d-a1b4-582c-ab29-b50b37190b58 |  | note | RESPONSIBILITY: Concrete Tester, Foreman, SE/PE/SPE
label | cb830b48-5ea8-517f-9e25-4d7a9d092b03 |  | note | – – – – – – – – – – – – – – – – –
label | 442369a9-855a-50cc-82db-4bdc7b45d9fb |  | note | VERIFYING DOCUMENTS: This ITP
text | 34c3ce19-2868-56fb-80f2-93fcfe8ed2d0 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.16 Concrete Testing - Slump
label | c7b3a0f5-40eb-5729-a3ee-c2e0402a9987 |  | note | REFERENCE: 703.11
label | 6aa2443b-18f6-5c2f-a9e7-d59fb8f43649 |  | note | 610.16 (c)
label | 2370b6bd-d597-517a-86de-f200074407e3 |  | note | – – – – – – – – – – – – – – – – –
label | 29d847ee-aca0-5632-8b2d-a9fe0141a6a2 |  | note | ACCEPTANCE CRITERIA: Slump testing tolerances =
label | ed2570ce-9f86-51f3-953d-dfd12d768aab |  | note | <60mm = ±10mm
label | 7a94d04a-f5b2-5105-a5f2-54a12272c14b |  | note | ≥60mm to ≤80mm = ±15mm
label | 76f1cc61-1391-5fc2-8459-7cf6343fee1a |  | note | >80mm to ≤110mm = ±20mm
label | adacdba2-65c8-5d76-ba68-2d30448208c8 |  | note | >110mm to ≤150mm = ±30mm
label | 1be0b479-c11c-5355-a1be-508f3ed21167 |  | note | >150mm = ±40mm
label | 38ea3944-7620-52fc-aec0-ee27bdca55f5 |  | note | Record: Required information on the Concrete Pour Record.
label | 02b4bfc4-9900-54d0-a9ad-226d679b13c8 |  | note | – – – – – – – – – – – – – – – – –
label | 4942f767-ca98-5cb3-8fd2-b99c14ae65f1 |  | note | METHOD: Test
label | 15ba736c-06dd-54ce-9dd3-e0fe9c01c07d |  | note | – – – – – – – – – – – – – – – – –
label | a5771780-07f5-597a-b89c-7544dc1faee9 |  | note | FREQUENCY: Each sample
label | 8097f330-cb66-5fc5-861f-2d139480fc77 |  | note | – – – – – – – – – – – – – – – – –
label | 575155e4-fc2a-5af5-86c6-9e625084e46a |  | note | CATEGORY: IP
label | f50227fd-c87b-5573-a8fa-cbdeedb46541 |  | note | – – – – – – – – – – – – – – – – –
label | dbbe2384-288a-5638-850e-f6903c1b6f2a |  | note | RESPONSIBILITY: Concrete Tester
label | ad395592-948f-527e-a59f-f6017760f493 |  | note | – – – – – – – – – – – – – – – – –
label | 6c121bd3-bab7-5473-9aa0-88544b350642 |  | note | VERIFYING DOCUMENTS: This ITP
text | 09d8e152-4bfd-5111-949a-5783a927533f |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.17 Placement & Compaction
label | 46f369b1-f154-503c-ad9c-e913308877b2 |  | note | REFERENCE: 703.08
label | 2f1fc36f-0246-5de5-8fed-bbc0de2dbb9f |  | note | – – – – – – – – – – – – – – – – –
label | 87a1de1d-74af-5bb9-925e-650f6691971e |  | note | ACCEPTANCE CRITERIA:
label | f337802c-1557-54d9-a214-7e9096d8b776 |  | note | • All concrete batches are traceable.
label | a84247b3-3c2c-5287-9397-4197644eaba3 |  | note | • Concrete shall be transported, handled and placed to prevent segregation, loss or leakage of materials.
label | 35c7ba17-569f-5fe8-869a-86418054d78e |  | note | • Where concrete pumps are used, the initial discharge is pumped to waste until a consistent workable mix is discharged.
label | 5e4ed095-8e1c-5137-9fd4-23da37fb0d0a |  | note | • Fresh concrete shall not be placed against concrete which has taken its initial set, except at properly formed construction joints.
label | 9e5e4642-08d8-5982-9dbd-1f10b12bdb95 |  | note | • Concrete shall be thoroughly compacted by means of continuous tamping and internal vibration and shall be worked around any embedments and into corners of formwork or excavations to produce a dense concrete free from voids, honeycombing, segregation or surface defects.
label | a7edb8d1-24b1-54ca-a561-bbe76adc9b6b |  | note | • Vibration continued at each point until air bubbles cease to emerge from the concrete.
label | dc1076f0-45a0-5969-8e2f-323cb04e172e |  | note | • Unformed surfaces shall be hand tamped to ensure a smooth surface with a uniform colour and appearance, and screeded to achieve the specified level, dimensions, falls and tolerances.
label | 07d583f6-ab9f-5286-b5d8-2cd1c2b66eeb |  | note | Record: Required information on the Concrete Pour Record.
label | b14bc880-71e7-5c5c-b42c-1b76994422e4 |  | note | Attach: Concrete Pour Record
label | b4ad7267-2427-52e2-ac54-7bd17ecbf6dd |  | note | Attach: Concrete Dockets
label | 20564637-3210-5da4-8048-81f158bbc10c |  | note | – – – – – – – – – – – – – – – – –
label | 572086ba-60f8-5027-8546-35bb30baa9f7 |  | note | METHOD: Visual
label | a96cac2b-db13-5046-b253-119ae7ddcc0e |  | note | – – – – – – – – – – – – – – – – –
label | 7205747a-d00c-5ab6-8eee-78a518ae065c |  | note | FREQUENCY: Each load
label | 21ae167a-b087-5559-bcfc-3e424222878f |  | note | – – – – – – – – – – – – – – – – –
label | 3a068867-be89-5044-b557-cf208d2a8436 |  | note | CATEGORY: SP
label | 86963b1d-5dd7-52f8-bda6-71c6b044ebe9 |  | note | – – – – – – – – – – – – – – – – –
label | 8c28668f-23a4-5579-97e0-e3843fd8090f |  | note | RESPONSIBILITY: Foreman, SE/PE/SPE
label | 1effec2d-1027-5bf0-bedc-64141642acb7 |  | note | – – – – – – – – – – – – – – – – –
text | 6c76c8ef-6094-5616-b509-6d3559a299be |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.18 Surface Finishes
label | d305f8e0-120b-5791-8b38-a6f7af72f6eb |  | note | REFERENCE: IFC Drawings
label | 133a62fb-ee34-5a44-b770-9800f86993ed |  | note | Relevant Council Drawings
label | 43a22e9f-1284-5128-9939-e20b617ae9c1 |  | note | 703.25
label | f4a604ec-ab96-5615-95e6-9075e852beb5 |  | note | – – – – – – – – – – – – – – – – –
label | a570ee28-5449-5221-84d6-d9962a015a9f |  | note | ACCEPTANCE CRITERIA: Fresh concrete shall be compacted with internal vibration and worked until all the coarse aggregate is below the surface and the mortar comes to the top.
label | b95725c2-405f-5323-ac67-ab15a0cffd26 |  | note | • It shall then be struck off and finished to grade and cross section with a wooden float to produce a lightly textured non skid surface. All outside edges of slabs and all joints shall be finished with a suitable edging tool.
label | 2e46d909-00b1-537b-8ecf-e08ac0cb9093 |  | note | • After finishing, all work shall present a consistently neat appearance of uniform colour. All edges shall be sharp and clean and bullnoses shall be regular and of uniform radius. All discoloured concrete shall be cleaned or replaced by the Contractor.
label | 79c1f51b-967a-51e0-9c2d-ace9428f18c0 |  | note | • Permanently hidden concrete surfaces of concrete paving including footpaths, edgings, other concrete surfacing, and shared use paths shall have a Class 4 surface finish in accordance with AS 3610.
label | e9edaef6-7e39-5b19-9ea0-dcff9ab69a6d |  | note | • All other concrete elements constructed with reference to Section 703 shall have a Class 3 surface finish for external surfaces and a Class 4 surface finish for permanently hidden surfaces
label | 11a7d353-5255-5be0-a49c-59f3db64d5e4 |  | note | – – – – – – – – – – – – – – – – –
label | eeaa27b9-bec0-5113-95e8-7ec8cd1fba08 |  | note | METHOD: Visual
label | 297417e1-eec2-5891-acb7-0c740a1c1fbe |  | note | – – – – – – – – – – – – – – – – –
label | 0cef983c-8056-5a4d-9074-050959db394c |  | note | FREQUENCY: Each lot
label | 4145afa3-b1e3-597f-9959-3406daa9b236 |  | note | – – – – – – – – – – – – – – – – –
label | 6998986a-ea71-58df-89d1-5b06881f2de4 |  | note | CATEGORY: IP
label | db4a68ae-6594-56a1-9549-8eaf969bb2df |  | note | – – – – – – – – – – – – – – – – –
label | 41a8abbe-569c-577b-96b3-d7192956d877 |  | note | RESPONSIBILITY: Foreman, SE/PE/SPE
label | 7de01627-a8f6-5edb-8e4b-2cbcd5941c45 |  | note | – – – – – – – – – – – – – – – – –
label | a7ddc907-2e82-5c81-903c-91783938cc32 |  | note | VERIFYING DOCUMENTS: This ITP
text | 354ee154-1167-53a6-83e1-2ea782690584 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.19 Footpaths - Crack-control Joints / Weaken Plane Joints
label | 5cf3fab7-d224-5f58-b3e0-b08ec89fbe5c |  | note | REFERENCE: IFC Drawings
label | 90830ed8-5405-5b86-a1e8-7d570b7dd3d1 |  | note | Relevant Council Drawings
label | 91b199b3-b9a2-5b9b-b182-c7cdb3bdcd7f |  | note | 703.26 (b) (ii)
label | ee62d189-d4b4-50b4-8a51-700980847ed8 |  | note | – – – – – – – – – – – – – – – – –
label | 826ce92d-caf1-56ca-8068-795b04256c46 |  | note | ACCEPTANCE CRITERIA: Crack-control joints shall be finished with a suitable edging tool, full-width of the pavement to the required depth and locations and/or longitudinal spacings as shown on the drawings.
label | d44a59a3-966c-5621-8cb0-065abb7d2fa5 |  | note | – – – – – – – – – – – – – – – – –
label | 22be39fd-fd35-58fc-9611-2cca6fc64f49 |  | note | METHOD: Visual
label | f9be2ba4-04c1-57a2-bbff-bfd42451eb78 |  | note | – – – – – – – – – – – – – – – – –
label | 038f31dc-f99d-5d95-8850-396888698423 |  | note | FREQUENCY: Where applicable, each lot
label | bd1243d3-296e-5e5e-8b90-61bb6e12b2cc |  | note | – – – – – – – – – – – – – – – – –
label | a31b7a81-f4bc-5e54-b70b-951855a9eee2 |  | note | CATEGORY: IP
label | c8337e70-b4e6-53dc-9b1e-fb0684437676 |  | note | – – – – – – – – – – – – – – – – –
label | 566ba001-b394-553e-bd1d-d7ec2a5a02bb |  | note | RESPONSIBILITY: Foreman, SE/PE/SPE
label | 67310f25-d900-563c-8f05-aa588ab65080 |  | note | – – – – – – – – – – – – – – – – –
label | 996e1616-713d-53a8-a8d6-b1b5efb959e1 |  | note | VERIFYING DOCUMENTS: This ITP
text | 7f41f349-1542-536e-b48a-b3425cc6f6fc |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.20 Curing
label | dd804e12-e8f9-5f14-94c3-8bb9e9bd45f9 |  | note | REFERENCE: 703.10
label | c7d5da92-988e-5f8c-851d-e0aeff4f08d3 |  | note | – – – – – – – – – – – – – – – – –
label | 2e16ec37-3cb6-593b-b8d9-5c2ffd620e76 |  | note | ACCEPTANCE CRITERIA: The curing of exposed concrete surfaces shall commence immediately after finishing operations are progressively completed either by water curing, wet hessian, polyethylene sheeting which is adequately sealed, curing compound or a combination of these.
label | 2ca0f17f-903f-5d28-ab4b-654f9bfccf0a |  | note | • The curing of exposed concrete surfaces shall commence immediately after finishing operations are progressively completed either by water curing, wet hessian, polyethylene sheeting which is adequately sealed, curing compound or a combination of these.
label | 0a53e1f9-0503-568c-8006-7e027474b69e |  | note | • Where curing compounds are used, 2 coats of the shall be applied in accordance with the manufacturer's TDS.
label | c3d9d294-ccba-5804-96cb-f1be78887f35 |  | note | • The curing membrane shall be maintained intact for not less than the specified period of curing. Any damage to the curing membrane during the period of curing shall be repaired immediately at the original rate of application
label | 45ef870c-5415-5a80-af70-95ed5b8ca5a8 |  | note | • Curing shall continue uninterrupted for a period of not less than 7 days after placing the concrete, or 3 days for concrete edgings.
label | 5cbd600f-3569-5c6a-9614-1122a7b569be |  | note | • Freshly finished exposed concrete surfaces shall be effectively protected from rain or damage from other sources, until hard set has occurred.
label | 0a56bb5e-8884-5a3f-a620-86f35e93519a |  | note | – – – – – – – – – – – – – – – – –
label | 43593746-c9a0-5340-bbaa-b447774d4ddf |  | note | METHOD: Visual
label | 72c23070-e181-5609-a1ae-d87de1b7fd3a |  | note | – – – – – – – – – – – – – – – – –
label | bbcdfd17-5b42-5a13-8db9-9280a405c0da |  | note | FREQUENCY: Each lot
label | 7036eba4-e94c-5ca1-9564-65cd2ff3abed |  | note | – – – – – – – – – – – – – – – – –
label | c8ccd703-3ae5-532c-9d88-ddc93e2c0d3e |  | note | CATEGORY: IP
label | 78c72fbc-3a56-5b26-bda5-eb58eeaf4a4e |  | note | – – – – – – – – – – – – – – – – –
label | a4c68d98-130f-58df-8381-91f84bda3884 |  | note | RESPONSIBILITY: Foreman, SE/PE/SPE
label | be38fb10-20e0-5a6d-99c1-0c3b7e8f632e |  | note | – – – – – – – – – – – – – – – – –
label | adad98d8-b5d6-51de-9a47-402665c6b9e1 |  | note | VERIFYING DOCUMENTS: This ITP
text | 7bef9f79-b85b-5d87-8e6d-9e7f64db7cf5 |  | textbox | Date Completed:
checkpoint-group |  |  | section | Post-construction Activities
checkpoint-status |  |  | checkpoint | 6.1 Shared User Paths - Crack-control Joints / Weaken Plane Joints
label | a793e873-9a4c-51ab-be4d-0beae395eb45 |  | note | REFERENCE: IFC Drawings
label | 6f456919-ded4-5d34-ac81-f082f54b049d |  | note | Relevant Council Drawings
label | 10ab3a2f-b313-5265-a6bd-e312e6fd3446 |  | note | 703.26 (b) (ii)
label | c3a4477d-5230-500a-b5ad-29e1e02f1b81 |  | note | – – – – – – – – – – – – – – – – –
label | 2a8564f9-9eb9-5eaa-ba83-ccd099a19fca |  | note | ACCEPTANCE CRITERIA: Crack-control joints shall be saw cut full-width of the pavement to the required depth and locations and/or longitudinal spacings as shown on the drawings within the following time-frames and air temperatures:
label | f86d15df-96ad-5fa1-a514-23158d8800a1 |  | note | <20°C = within 24 hours of finishing operations
label | eb4e598c-bd4e-5716-a1c5-2468982b6840 |  | note | ≥20°C - 35°C = within 4 hours of finishing operations
label | ac73e02c-daab-5d12-a7c5-6c9df337787c |  | note | – – – – – – – – – – – – – – – – –
label | 7b6c9f4f-fbde-5393-a1fc-1df2602a257a |  | note | METHOD: Visual
label | 0f075842-9b55-54a3-8ff6-867fa6e28235 |  | note | – – – – – – – – – – – – – – – – –
label | 9418cd10-b914-5b7f-8155-17cd8e7a4c33 |  | note | FREQUENCY: Where applicable, each lot
label | a0890c7c-b945-59ca-8c0d-84d59b11f299 |  | note | – – – – – – – – – – – – – – – – –
label | 277a12ef-7fe6-589b-80eb-8effd69013d4 |  | note | CATEGORY: IP
label | a42b8a6a-7dd9-5bcb-a14c-c65c64249dfa |  | note | – – – – – – – – – – – – – – – – –
label | c6b54b69-6e26-53b6-a0bb-42271fe92d58 |  | note | RESPONSIBILITY: Foreman, SE/PE/SPE
label | 6dcac43a-3b09-589e-a394-7da571f5a09c |  | note | – – – – – – – – – – – – – – – – –
label | 4e0d7e43-f19a-57d1-bb4f-713f84fb69fe |  | note | VERIFYING DOCUMENTS: This ITP
text | 0ab4bc8c-b4d4-5809-a9ce-791215d5850d |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 6.2 Protection of Newly Poured Concrete
label | 30eec13f-faa1-5bbf-95a7-e7e2b9ce7caa |  | note | REFERENCE: 703.27
label | 0c73c963-36d0-5e0f-a454-cf6161a3243c |  | note | – – – – – – – – – – – – – – – – –
label | a3a2601c-8250-5096-83b2-37c0bfdb43ac |  | note | ACCEPTANCE CRITERIA: All concrete shall be protected from damage from early loading by pedestrians, animals, vehicles and from rain or any other cause.
label | bd8c1698-1f5f-5d0d-98a4-cc72acc2472f |  | note | • Suitable flagging, signage or bunding shall be erected to prevent vehicles from crossing over residential and/or commercial vehicle crossings a minimum of four days after completion of casting of the concrete. Vehicles greater than 1.5 tonnes may be permitted to cross after 7 days.
label | 388fe6e0-9755-5259-a980-d0d25ac33307 |  | note | – – – – – – – – – – – – – – – – –
label | 7fe9ffde-44cd-5fb1-82a1-bdd71f555b51 |  | note | METHOD: Visual
label | 75401d34-ea5c-5f96-872d-ac78dc20a220 |  | note | – – – – – – – – – – – – – – – – –
label | f87e895c-9bec-5931-8baf-88a6667ce067 |  | note | FREQUENCY: Where applicable, each lot
label | f4b68b52-1594-526f-9fe5-0161755cfb38 |  | note | – – – – – – – – – – – – – – – – –
label | a49a3f74-baa5-5253-9410-18bac69af7c0 |  | note | CATEGORY: IP
label | 0b4a2367-ab8e-5de4-ba5b-360c844f3b60 |  | note | – – – – – – – – – – – – – – – – –
label | 7e62c314-4a4f-5052-8c8d-a087cd55befc |  | note | RESPONSIBILITY: Foreman, SE/PE/SPE
label | 7a973b66-5149-52ac-a631-ceafcc97b674 |  | note | – – – – – – – – – – – – – – – – –
label | 45dbfaca-372d-5757-9fea-c4135735a0ce |  | note | VERIFYING DOCUMENTS: This ITP
text | facab81c-b5b9-5779-9042-8ece8c673d88 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 6.3 Stripping Formwork
label | 5b58007b-839a-573b-8c61-fb7e84ce13d0 |  | note | REFERENCE: 703.12 AS3610 Table C2
label | c21b67ae-f9d7-5022-92b6-967b279ea1b9 |  | note | – – – – – – – – – – – – – – – – –
label | 7a3267cb-c42a-5f3c-a816-933ed82ddf64 |  | note | ACCEPTANCE CRITERIA: Formwork shall not be stripped until the minimum times have elapsed from the time of completion of the placing of concrete:
label | fc5d575f-344f-5885-baff-ff9b54630dde |  | note | i. 2 days for vertical formwork on external surfaces; and
label | dfc72c9c-0019-5b08-bf02-fbef57829939 |  | note | ii. 1 day for vertical forms on permanently hidden surfaces
label | f487b3fa-166d-5673-9af8-987361cc803c |  | note | – – – – – – – – – – – – – – – – –
label | de7406d1-7d70-5e0f-a995-d5bc18900ebd |  | note | METHOD: Visual
label | 573c1feb-67d0-52f0-94e8-e81af959524b |  | note | – – – – – – – – – – – – – – – – –
label | 84137e56-bdde-5b74-9df2-60edcc42cefc |  | note | FREQUENCY: Each lot
label | 9c8a6f63-d187-5622-a1a3-6f0de56f31c3 |  | note | – – – – – – – – – – – – – – – – –
label | eb5dfad9-64de-5b61-b2f0-fc1c9145977f |  | note | CATEGORY: IP
label | c825ccfb-dcc9-5646-bfa0-2ce51babdb0c |  | note | – – – – – – – – – – – – – – – – –
label | 39fb8dbc-2060-5f12-81bf-8f114e70f850 |  | note | RESPONSIBILITY: Foreman, SE/PE/SPE
label | 048af16e-1566-5012-813a-4fbf46272637 |  | note | – – – – – – – – – – – – – – – – –
label | 78899bc3-d310-5aa2-b20d-bb1b68052547 |  | note | VERIFYING DOCUMENTS: This ITP
text | 538a9a89-d598-57a9-bd29-b4d156c20739 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 6.4 Backfilling & Pavement Restoration
label | f022c7bf-af20-5318-98a5-4bcd4c57fc04 |  | note | REFERENCE: 703.29
label | d6dc4644-b203-510c-9651-4eb1e6ced30c |  | note | – – – – – – – – – – – – – – – – –
label | ffa58ac7-f5d1-5c0f-8d78-2f5929376823 |  | note | ACCEPTANCE CRITERIA: At no earlier than 3 days after concrete placement, topsoil material shall be placed and firmly compacted in layers not exceeding 150 mm in thickness and to a width not less than 300 mm behind the edging to the top of the edging.
label | 17bb3bae-b9dd-5fdc-b168-87fcc3632451 |  | note | – – – – – – – – – – – – – – – – –
label | d8109c98-d2ee-5328-8cc2-6aeebaeddf55 |  | note | METHOD: Visual, Measure
label | 7e35b5de-efa2-527a-a011-7b46c023795f |  | note | – – – – – – – – – – – – – – – – –
label | 93deeab7-9abc-540e-af9b-eae25dfc18fe |  | note | FREQUENCY: Each lot
label | 38522e5d-3281-5ca2-a33e-429e0da8dc7f |  | note | – – – – – – – – – – – – – – – – –
label | 6a754b11-aac2-5e7b-9862-f26347c0baf7 |  | note | CATEGORY: IP
label | 833599a6-2f7d-54e3-9e48-1623e9f34a88 |  | note | – – – – – – – – – – – – – – – – –
label | 74fc8989-7835-5829-a971-cfe3e9d398bd |  | note | RESPONSIBILITY: Foreman, SE/PE/SPE
label | d4e4c4c0-56fa-56c6-bbcc-1442efdcf61e |  | note | – – – – – – – – – – – – – – – – –
label | c0347f91-19f8-5e82-97fb-ee59d54b7960 |  | note | VERIFYING DOCUMENTS: This ITP
text | dbfb98f0-02e3-53d2-a620-e013ff678769 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 6.5 Surface Inspection - Cracks
label | 7ead2397-0adf-50af-bc19-558e3ab8a801 |  | note | REFERENCE: 703.3
label | 8d7e1631-8cc6-5a4b-a2c0-52c967ca46d8 |  | note | – – – – – – – – – – – – – – – – –
label | 0be78d8f-77ea-5c7f-b26c-7d6f9c3e1f2b |  | note | ACCEPTANCE CRITERIA: No cracks greater than 0.2mm.
label | e5f43aee-d5ec-54c6-9c55-71c5393fbc69 |  | note | • If cracking greater than this is observed follow Structural Concrete Crack Repair ITP for investigation and repair.
label | 7d5df0b4-8ab3-5117-8421-879397814129 |  | note | – – – – – – – – – – – – – – – – –
label | 2f088fb5-38e0-5e2e-ad07-8195f841ba1a |  | note | METHOD: Visual, Measure
label | 2747096f-a7ae-5a8d-ad93-5d45713a027a |  | note | – – – – – – – – – – – – – – – – –
label | 3c037d7c-3e14-5c5c-8176-28a255f315ca |  | note | FREQUENCY: Where applicable, each lot
label | 4a37f61c-1909-572c-b006-8879fba2abfd |  | note | – – – – – – – – – – – – – – – – –
label | 5d72d5c1-4050-5fe0-87f9-50a1341b1c81 |  | note | CATEGORY: IP
label | 90f7ea5f-a2d1-51cb-b62c-41eab2703f70 |  | note | – – – – – – – – – – – – – – – – –
label | 84f60089-b222-5e70-91c8-6a3d007fbf3b |  | note | RESPONSIBILITY: SE/PE/SPE
label | 3f41cca3-13e3-5ade-bfcf-557fe129d1d1 |  | note | – – – – – – – – – – – – – – – – –
label | bae3beb4-7ae8-5a71-a6f0-64eaf8ba07aa |  | note | VERIFYING DOCUMENTS: This ITP
text | 696b55b8-689a-55cf-9e0f-54febfbde79d |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 6.6 Surface Inspection - Surface Finish
label | 499fbfb4-3ea4-5ad5-af52-87c4d794e6a9 |  | note | REFERENCE: IFC Drawings
label | e662fd3e-fb7c-5152-b9b6-e0abc34986d2 |  | note | Relevant Council Drawings
label | f8db1b73-bc19-5819-8811-4f9fcb9b3828 |  | note | 703.25
label | 695b57e3-6916-5d81-b938-51f441243a69 |  | note | 703.10 (a)
label | 6cc4c7fc-f831-5edf-9378-9794bcb86930 |  | note | AS3610 Clause 3.2
label | d1ff99ea-b0e9-523b-97b2-622de337439a |  | note | – – – – – – – – – – – – – – – – –
label | b2fbffbf-7060-58a6-afad-f7321a0dc19e |  | note | ACCEPTANCE CRITERIA: After finishing, all work shall present a consistently neat appearance of uniform colour.
label | 6203a806-4ad7-560c-8992-67a11dc567b7 |  | note | • All edges shall be sharp and clean and bullnoses shall be regular and of uniform radius.
label | eeda3e2f-7ec1-5ea3-801e-80ded35789c6 |  | note | Class of finish:
label | 1363d064-c007-5467-85fd-5e6a29f7fc64 |  | note | • Permanently hidden surfaces = Class 4
label | f5eb1c57-7bd6-5e1d-bfb5-81eb6d7c7254 |  | note | • All other surfaces = Class 3
label | adedacf5-d648-507c-806c-e84896ffa913 |  | note | • At the end of the curing period, concrete paving and shared user paths shall provide a dense, hard wearing surface
label | 29b77ed9-4632-5ba4-bed4-08738ea01de6 |  | note | • Where surface finishes are non-conforming follow Structural Concrete Patch Repair ITP for investigation and repair.
label | d70d1d1d-af42-5e2e-986f-34085b23dffe |  | note | – – – – – – – – – – – – – – – – –
label | afd53f5d-e2c4-50da-93c0-3e97ef8828e5 |  | note | METHOD: Visual
label | 24f2b796-8f75-5071-9d23-201bb26cc6ef |  | note | – – – – – – – – – – – – – – – – –
label | d9d87fc2-c6e7-5b24-a90a-abcfaea9168e |  | note | FREQUENCY: Each lot
label | a0b74965-2716-5220-8fd6-92313ece6377 |  | note | – – – – – – – – – – – – – – – – –
label | e1c1a68d-3ec1-5b9f-bb83-3f16187e6049 |  | note | CATEGORY: IP
label | 1cbc2db2-a684-50cb-a08f-05594bb59c5f |  | note | – – – – – – – – – – – – – – – – –
label | a2a8d6c9-9dd9-5ef3-b510-5df9d24c9ed7 |  | note | RESPONSIBILITY: SE/PE/SPE
label | 1ec6f1c1-5789-561e-8451-67b1eb9f0c6f |  | note | – – – – – – – – – – – – – – – – –
label | d1991529-e664-521c-b396-a8b658527ecd |  | note | VERIFYING DOCUMENTS: This ITP
text | af1156b8-a9be-551d-86bb-ae9778cba67b |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 6.7 Compressive Strength Test Results
label | 1979e0c8-0727-56b7-bb53-1f1187b5f5b2 |  | note | REFERENCE: IFC Drawings
label | d73a5c1c-1dd3-5119-9501-ad99bcfcb94f |  | note | Relevant Council Drawings
label | f7a6acee-5381-5d8c-8066-28b307a9c6ba |  | note | 703.11
label | 0b13d961-da4f-5c37-9538-0b5985421643 |  | note | Table 703.111
label | f9a86df8-d46f-5dc4-a8bc-6804cf69f8cd |  | note | Table 610.05.051
label | 83394bf0-9461-5fe2-a0d2-4b940806e33c |  | note | 610.16 (g)
label | 0913f9d9-c49d-5a6b-a6ab-7b954c7c790e |  | note | – – – – – – – – – – – – – – – – –
label | b85d8dbf-cf18-5e60-8630-f763ebb5f128 |  | note | ACCEPTANCE CRITERIA: 7 day compressive strength to comply with table 610.051 for early indication that the strength is tracking correctly.
label | 1f9df7a6-4808-5162-ad4a-535f33ad2685 |  | note | • 28 day compressive strength (average of the 2 no. cylinders) per sample comply with the design strength.
label | d0c45902-c465-50d8-8b9d-6a3b57e09385 |  | note | • Note: 1 of the 2 no. 28 day cylinders per sample may be as low as 90% of the required strength, so long as the average meets the required strength.
label | 2dc67c0b-7f54-5caa-a437-978b7b3bb8e4 |  | note | Attach: Compressive Strength Test Results
label | ff837007-3a0a-5f08-9127-318668a2a6d1 |  | note | – – – – – – – – – – – – – – – – –
label | 81bd8b61-a389-57a4-9eb9-316f0749bf28 |  | note | METHOD: Document Review
label | 6f2e8efc-b499-5eba-adea-c5fb12ccaea0 |  | note | – – – – – – – – – – – – – – – – –
label | 15707c39-2459-5e86-a8d4-600614ab2fc1 |  | note | FREQUENCY: Each cylinder
label | 9b532fc2-7747-5e00-9d6c-66a22cf8ba52 |  | note | – – – – – – – – – – – – – – – – –
label | 96fbf21e-3eaf-5ddb-8b62-5942ffdca4bf |  | note | CATEGORY: IP
label | 5a548fc2-546d-570f-ac5d-34838c38f876 |  | note | – – – – – – – – – – – – – – – – –
label | cc96b10f-107a-56c2-bfdf-787d287ccd0b |  | note | RESPONSIBILITY: SE/PE/SPE
label | 4a7546c4-62d9-54ba-b8aa-631bdda85de2 |  | note | – – – – – – – – – – – – – – – – –
label | 9e82bbc2-0fe0-55a7-8019-6a71c9727cf2 |  | note | VERIFYING DOCUMENTS: This ITP
text | 85a55408-7c5e-5c71-b371-7dc6a28fee1b |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 6.8 As-built Survey
label | 3b1785c8-6b05-5be7-ab8d-7e8739a47dec |  | note | REFERENCE: IFC Drawings 703.15
label | 072c2520-d478-5aee-af51-8501c4806181 |  | note | – – – – – – – – – – – – – – – – –
label | e01ef259-5788-5b24-879e-fe247388baaf |  | note | ACCEPTANCE CRITERIA: Provide record of dimensional measurements to demonstrate that all Works meet level and location requirements within the tolerances below:
label | 20bd3619-dd3e-5c9e-b6f0-370d0ac6de21 |  | note | • Departure from RL = ±10mm
label | 93523ff4-7ee8-5fa7-8223-84feaf58e107 |  | note | • Departure from alignment = ±10mm
label | 9e7d132d-56bc-5989-beb7-60fd18eb1505 |  | note | • Rate of change of deviation from RL or alignment = 10mm in 10m
label | 73722970-6ecf-536f-8a7e-20ae512ae358 |  | note | • Irregularities in alignment = 5mm in 3m
label | 6f2d9bef-c95c-5965-8ed5-c6fab42a4cd3 |  | note | • Section dimensions = ±5mm
label | 04c3aabc-9e3a-59d5-a915-221024efc4f7 |  | note | • Section dimensions (less than 25mm) = ±3mm
label | f11a0f53-42e5-5b15-86f3-404a70a4b74f |  | note | • Width of pavement = -5mm, +15mm
label | 02962a01-7d0d-592d-b5e4-f77fab612757 |  | note | • Where median surfacings are to be constructed between edge sections of the same level, paving shall be crowned to produce a cross fall between 1% and 3% towards the edges.
label | 3d5f971d-a39d-5518-ba27-26ae2a304087 |  | note | Attach: Survey As-builts / Survey Report
label | d2b46dfc-2aeb-52bb-8131-016a6a09a48c |  | note | – – – – – – – – – – – – – – – – –
label | 528efafb-302c-5469-9fb5-2aa827ce21fe |  | note | METHOD: Document Review
label | 26373794-cb24-5462-afe6-4bdcadea9001 |  | note | – – – – – – – – – – – – – – – – –
label | f663d835-f7b7-537e-8002-b91f18f59698 |  | note | FREQUENCY: Each lot
label | bcaa0868-0f71-548a-b0ee-558810c1acae |  | note | – – – – – – – – – – – – – – – – –
label | 35d86f22-684f-58a8-a0a7-31617d809b96 |  | note | CATEGORY: IP
label | dbdfa7d4-05ad-54f5-b1b0-f838a00e3b75 |  | note | – – – – – – – – – – – – – – – – –
label | 9d169127-f349-5524-9b55-f375c6d2088a |  | note | RESPONSIBILITY: Surveyor, SE/PE/SPE
label | e16ca35f-0bed-58ab-b2a6-fc9e16f2551c |  | note | – – – – – – – – – – – – – – – – –
label | e43a7615-e588-59de-a3ae-b4efcc962982 |  | note | VERIFYING DOCUMENTS: This ITP
text | fc7e7174-a872-5d75-ba69-d258f3026f82 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 6.9 Non-conformance Report (NCR) Closure
label | 0a20346a-b826-5f8d-ba87-5e07547dd142 |  | note | REFERENCE: MRPA Quality Management Plan
label | 8e75ba50-1f69-5d8d-bd0f-3d568cc41644 |  | note | – – – – – – – – – – – – – – – – –
label | ff8fe093-e8be-515c-a5ae-91cb0e1ff260 |  | note | ACCEPTANCE CRITERIA: Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed in CAMs.
label | b0989557-e6af-5d1a-b841-19a742bf065e |  | note | – – – – – – – – – – – – – – – – –
label | 372eaa1a-2aa7-5a49-bf60-d681e0beef63 |  | note | METHOD: Document Review
label | 82c2c511-aa87-5440-a672-a24bd9c29413 |  | note | – – – – – – – – – – – – – – – – –
label | a145d24f-0212-5fb3-9c8a-6cdd9cc6fd8c |  | note | FREQUENCY: Once, prior to closure of this lot / element / Work area
label | e08d8faf-c589-5ceb-a3f1-6f3fee477a76 |  | note | – – – – – – – – – – – – – – – – –
label | adbec5ba-69be-5c1d-b52b-16be4559f46c |  | note | CATEGORY: HP*
label | c3b1e79a-1221-5df5-b8de-35c5d5508a05 |  | note | – – – – – – – – – – – – – – – – –
label | 0f22f408-48c5-54e8-bb22-69390f219322 |  | note | RESPONSIBILITY: SE/PE/SPE
label | 23f152b6-0fc5-5ac4-a670-f4dab71d5e2e |  | note | – – – – – – – – – – – – – – – – –
label | ebdcf9da-7219-533d-bdfd-7da02b9faea8 |  | note | VERIFYING DOCUMENTS: This ITP
text | 1739ab08-21bd-5f2f-9fe1-07f6eca7e62e |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | Final Inspection
label | 40eeb546-a214-598d-8c67-2b2ba2bcd5f5 |  | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed above have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
text | 0c1f8dd2-6636-54a9-9036-417480c206f1 |  | textbox | Name:
text | 3838d519-6712-5bed-9623-c063aa840e77 |  | textbox | Position:
text | 741215e0-d9ae-5b0d-bc9b-3af2ecbf0546 |  | textbox | Date Completed:
holdpoint |  |  | signoff | Sign ITP
checklist-flat |  |  | checklist | CHK-002-CIV-Stormwater Drainage Pits Installation | itp |  |  |  | Yes | CHK-002-CIV-Stormwater Drainage Pits Installation | 1cd84ae7-48dd-4ca8-b587-550af6137787
checkpoint-status |  |  | checkpoint | CHK-002-CIV-Stormwater Drainage Pits Installation
label | 30c9e816-8b1e-5da5-8cee-6431e25224f8 |  | note | Document Title: CHK-002-CIV-Stormwater Drainage Pits Installation
label | 30e45402-24d3-5c32-bff6-06576ea5f814 |  | note | Check list Description: Stormwater Drainage Pits Installation
label | 8ab47a37-3455-58e0-9331-3d53a33589cc |  | note | Discipline (e.g. CIV/STR/RAIL): CIV
label | 934bb054-a166-5f8a-b390-c0d39e4a83a8 |  | note | Revision Number: 0
label | cc2670cb-be5d-5859-bb83-b7413f039d37 |  | note | Revision Date: [Date of Approval]
label | 44901902-92a4-59ee-ae8c-16c93abfe245 |  | note | ITP created by: Jon De Castro
label | d2e6e39f-970d-5ad2-b5cd-687b84348a87 |  | note | ITP approved for use by: Aldrin Guinchoma
checkpoint-status |  |  | checkpoint | 1 - Pits - Survey Set-out
label | 364aa61b-e1df-584e-91d4-d6aefd2f5a71 |  | note | REFERENCE:
label | 5e056dec-3d5f-5e61-ad10-889477a1ea3b |  | note | • Section 701.10
label | 4ce74228-2338-54c0-af42-f116acdab156 |  | note | • IFC Drawings
label | 9adf138a-3d16-51dd-815d-a2f50ed9fcc5 |  | note | • ITP-008-CIV-Stormwater Drainage Supply & Installation - Item 4.1
label | ab189ac6-906a-5174-ad72-e0632788d5f6 |  | note | ---------------------------------
label | 63c6b143-8945-5682-82f0-e405b3302a56 |  | note | ACCEPTANCE CRITERIA:
label | 1a78cbcc-59dd-5ca3-8d41-12e94c252d36 |  | note | 1. Pits are set-out in accordance to IFC Drawings and Section 701.10 with the following tolerances below.
label | 3f87f44c-5fe4-5832-88f6-832fc7c0aad4 |  | note | (a) offset of entry pits required to match lines of kerbs or barriers ±20 mm
label | f6126ccf-101f-5dab-92f6-5abad2446828 |  | note | (b) plan location of pits other than offsets to kerb lines or barriers ±100 mm
label | ecd2ac7a-008d-5357-924d-99aeab4ed0fd |  | note | (c) invert level of Pits at pits ±50 mm
label | dd7e382e-9a2e-5ea3-a1fd-4b7391e2a6f1 |  | note | (d) departure from design grade of pipe runs ±10 mm in 10 m provided minimum grade is not less than 1:250
label | fe913ae4-e5c6-5ac0-8049-45a89da2d90b |  | note | ---------------------------------
label | 393006ff-e752-5ca9-9c97-cf03e909e55f |  | note | METHOD: Survey
label | c19a6989-60df-5fab-aaf2-8e31619bbb08 |  | note | ---------------------------------
label | 3509534b-d6a7-58e8-896a-db0370e15186 |  | note | FREQUENCY: Each Lot
label | 6ecffd8b-bfd4-527c-bb4f-0e399c33c13d |  | note | ---------------------------------
label | e2f218e9-29e8-5e8a-b7f6-1578db29648c |  | note | CATEGORY: HP
label | 564b21d1-76ec-54d0-af83-af3d583bbb0e |  | note | ---------------------------------
label | 9eba681f-f9e8-5327-972c-12300bb61c13 |  | note | RESPONSIBILITY: SE
label | d23b03d5-3cc1-5754-836b-d3820147e113 |  | note | ---------------------------------
label | 9930173d-c574-5a8d-bbea-2e07a0159c67 |  | note | VERIFYING DOCUMENTS:
label | 47188cf2-2fe5-5a56-b672-b89845bd579f |  | note | • This Checklist
label | 57ae0f4a-d55b-5b3d-85e1-0318cde2dc32 |  | note | • Survey Report
label | 929e24a1-8224-5139-9062-d41ead4f94c9 |  | note | ---------------------------------
text | 545e53c1-04b7-5e82-b629-469f0e71f7b2 |  | textbox | Date Completed:
holdpoint |  |  | signoff | HOLDPOINT
checkpoint-status |  |  | checkpoint | 2 - Pits - Excavation
label | 8e589cfc-99f7-5d02-955a-80101c87450e |  | note | REFERENCE:
label | 574494c1-0a5f-513e-99ea-4592d6cfdeec |  | note | • IFC Drawings
label | 184814e1-55bf-5cf2-ae43-e58386a2507b |  | note | • Section 705.05
label | 142f784f-cb28-5820-bdb2-eb6edcc7c95a |  | note | • ITP-008-CIV-Stormwater Drainage Supply & Installation - Item 5.1
label | d7d690cf-436b-5ce3-a24a-3f2e7d2a9c37 |  | note | ---------------------------------
label | e0af2b03-cfa5-5d93-b045-38842bdbc335 |  | note | ACCEPTANCE CRITERIA:
label | 5e67ea48-4d26-5383-bd66-201537ac1c5f |  | note | 1. Excavation depth as indicated on the IFC Drawings
text | 063f7065-0fdc-5b3e-be25-aa62fbc437ea |  | textbox | Excavation depth:
text | 0232803e-a4ab-510e-adb1-d2ca3faf54ce |  | textbox | Drawing Reference No:
label | fe05cf53-378b-5b81-9ac7-55c4dbf16196 |  | note | 2. For precast pits the excavation to have minimum clearance of 400mm from face of the excavation
text | ec433622-4abf-510e-a2b1-6c1fb69e487d |  | textbox | Excavation depth:
text | 868d2fff-ccf5-5046-af83-e72c61affb8f |  | textbox | Minimum clearance from all faces of pit to face of excavation:
text | ff787d16-b03b-5f27-8434-59c65003bd97 |  | textbox | Drawing Reference No:
label | 313ce243-fc9b-5676-8b58-6657cca01212 |  | note | ---------------------------------
label | 97b87cc8-d944-5f27-849c-b903629ddd36 |  | note | METHOD:
label | 16b9f23e-8556-55df-9794-4691ad5ab453 |  | note | • Visual inspection
label | 047f0653-56d5-5240-b793-4bd20814bb9b |  | note | • Measure
label | b3b3c102-4101-5db8-a8da-e080204a9b57 |  | note | ---------------------------------
label | eeb9a657-2913-5c95-81a2-1f888e4565b6 |  | note | FREQUENCY: Each Lot
label | 5c4fc7a1-1396-5e96-a8e4-4b9511e1ff12 |  | note | ---------------------------------
label | 2f8dbe7d-06b0-5ff1-a643-007a98aa0bfa |  | note | CATEGORY: IP
label | c62776a2-ec52-5d48-a88b-8b20f3bdc2cb |  | note | ---------------------------------
label | 66aec079-ae4b-5dd4-adad-ddb5709b6f34 |  | note | RESPONSIBILITY: SE
label | e88141a4-8f21-5dde-9902-f07b8689c924 |  | note | ---------------------------------
label | 270c335c-1caf-56f1-9172-75acdfc052cb |  | note | VERIFYING DOCUMENTS: This Checklist
label | 0ed20853-43bb-5619-b7a9-db9c86ce5b2b |  | note | ---------------------------------
text | 991384ea-47c9-5766-8fab-ca91dd6132a0 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 3 - Pits - Placement of Bedding Material
label | 68cb2efc-4c1a-51bf-8615-ea6542a3a2b6 |  | note | REFERENCE:
label | 0dc9dfaf-5f26-5cf8-92b5-663b2ede9339 |  | note | • IFC Drawings
label | 6eba62d7-cb8e-5c2f-823a-dafc7d8adb44 |  | note | • Section 705.05
label | 8f586b9f-ec41-519c-ace8-a58c64926d32 |  | note | • ITP-008-CIV-Stormwater Drainage Suppy & Installation - Item 5.2
label | 619e51de-74b9-596d-8b86-ad37f000c497 |  | note | ---------------------------------
label | b0b078f7-dc7b-5ee4-84b2-9d7207b438a2 |  | note | ACCEPTANCE CRITERIA:
label | 2d0a3835-78cf-5101-bdad-1dde9e7d784b |  | note | Bedding conforming to to 701.09 shall be supplied, placed and compacted to a thickness:
label | 17257880-14c5-5832-a4a1-3e5db77c190c |  | note | > 80mm for clay foundations
label | 30a3cd86-43c5-58d7-b4fa-f36985eacacb |  | note | > 150mm for rock foundations
label | ef5b22e4-f5c7-5d7d-9965-fd29962d614c |  | note | ---------------------------------
label | c66c6e76-0629-58f4-8995-050e2fe99ee5 |  | note | METHOD:
label | 57acff42-006a-5a73-aa57-ef5b254e6d2b |  | note | • Visual inspection
label | dded4e63-7fc7-5f79-b308-05f3366cac6a |  | note | • Measure
label | 374d2a78-6d7c-5796-81f9-f860160a114d |  | note | ---------------------------------
label | 0e3fdfc0-4c7b-50b3-9f70-293c85d79c1d |  | note | FREQUENCY: Each Lot
label | d19029b5-345e-519c-90ae-961aa3424ec9 |  | note | ---------------------------------
label | 709bab63-3842-51c4-8ad0-373a81a5ad01 |  | note | CATEGORY: IP
label | 5492a649-8c58-50ad-91f5-ea2ed039f653 |  | note | ---------------------------------
label | b29e6e58-162c-56ab-800d-08bbd001899c |  | note | RESPONSIBILITY: SE
label | 71ae9a8f-55b2-59e6-a2e6-72e5ced38757 |  | note | ---------------------------------
label | f6cb76e2-1764-5556-81d3-4b8d9f9e28d5 |  | note | VERIFYING DOCUMENTS:
label | 4ecf8fd7-3362-522a-9fe0-d0dea618c39c |  | note | • This Checklist
label | fd0421a6-03c6-5282-a6b5-bdd4dfa72dff |  | note | • Material Delivery Docket
label | 3d0d5b06-f169-52ed-baf4-9f961da4e508 |  | note | ---------------------------------
text | 675a0ec9-617b-519b-9129-afaccb4da0c5 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 4 - Pits - Bedding Testting
label | 076436fc-27a8-5fcd-8b26-0aa1fb5b1e3c |  | note | REFERENCE:
label | 5b7eccc7-bce0-5903-bac1-c1c02c654561 |  | note | • IFC Drawings
label | f31e5a30-2acf-5dc3-8d69-9f18f693f274 |  | note | • Section 701.20
label | f84d9f20-3ada-58af-ab3c-b38f888a474c |  | note | • ITP-008-CIV-Stormwater Drainage Supply & Installation - Item 5.3
label | 3d2e0599-6c86-54aa-9cc6-0c34cf226a83 |  | note | ---------------------------------
label | 3bf0c7b8-e216-5a8d-bb40-50fe1e0db2be |  | note | ACCEPTANCE CRITERIA:
label | cbbdde7f-03cc-5369-9b06-4a989a72c2f1 |  | note | 1. Tested minimum of 20% of all lots for each culvert. (Lot = 1 layer of bedding).
label | d842de2c-4788-50c9-a000-6301db761ce9 |  | note | 2. Three (3) tests done per lot.
label | 8ea32daa-7604-5c7b-ba07-ba207a8e2bb5 |  | note | 2. Bedding compacted to refusal by hand held mechanical equipment & material (Swell ≥ 2.5%) mean moisture ratio of 92% between the completion of rolling and the placement of overlaying laye.
label | d67a11f0-91e1-595b-a1e2-3eea59ba75b3 |  | note | Responsible Engineer to confirm if the bedding testing is required for this lot.
label | f794f788-3661-554f-8fb9-c446f5a46d52 |  | note | ---------------------------------
label | 4309b11b-92ab-58a9-b927-f19bb452c75f |  | note | METHOD: Compaction Test
label | 5475226b-ec9e-55ea-9de2-3b326ec8be17 |  | note | ---------------------------------
label | d0a7d03a-5f6b-56af-b367-e020f5f3e019 |  | note | FREQUENCY: Each Lot
label | dde0083e-510d-5368-9f52-8449e8e0e462 |  | note | ---------------------------------
label | 4697e48c-f533-588c-94fa-795d71c957df |  | note | CATEGORY: IP
label | 80a4ea40-8fd9-5856-b5b2-8abcd2d74ec1 |  | note | ---------------------------------
label | bfac5106-4417-5b07-8b4a-d10ebf23baf0 |  | note | RESPONSIBILITY: SE
label | 9fee5af3-cfe4-5708-896c-8d5fabe33eaf |  | note | ---------------------------------
label | 97796678-a2ba-591d-902f-e5524aa1078a |  | note | VERIFYING DOCUMENTS:
label | 4d5633af-bb62-5375-8e2a-3029c8967949 |  | note | • This Checklist
label | 4b776c51-b44c-537f-a6aa-b6cd545464f2 |  | note | • Test Reports
label | 891cb70a-f183-5f00-9c32-eba9dfac8d58 |  | note | ---------------------------------
text | 4f8e9538-a867-5f2a-be09-ea54d56f02f5 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5 - Pits - Placement of Precast Drainage Pit
label | f1445d82-3b89-5a33-8af1-31cf3505e6af |  | note | REFERENCE:
label | 0a71b4ad-e41d-5362-b7ef-cd41ce77422d |  | note | • IFC Drawings
label | 99f95208-5f1c-55bf-a582-11665929d3ce |  | note | • Section 701.10
label | 1e3a24ba-6444-51ee-aa83-54bf9f22f66b |  | note | • ITP-008-CIV-Stormwater Drainage Supply & Installation - Item 5.4
label | a43ba1b8-8b5f-5fc0-ac63-869a0dd6ca56 |  | note | ---------------------------------
label | b3cd4a2c-6b69-5c2f-a484-7466dc1aa910 |  | note | ACCEPTANCE CRITERIA:
label | 36285b28-89ad-51cf-9f27-959e38430a71 |  | note | 1. Pits phycially checked and confirmed No Damage prior to install
label | bdd60993-a84d-5343-9aa4-cae70302801a |  | note | 2. Survey pick-up to verify:
label | 27fb3d87-bfac-58c0-a194-0c3f65a0dcda |  | note | – Plan location of pits, other than offsets to kerb line or barriers, to be +/- 100mm
label | c4ab9db6-9566-57fa-8e70-7d8dab1b3e0f |  | note | – Offset of entry pits required to match lines of kerbs or barriers ±20 mm
label | c3a01ce2-4daf-5ab6-8702-6bc2c852df03 |  | note | ---------------------------------
label | e26a49d3-d31a-58ca-b8d4-f8a4a1d65afa |  | note | METHOD:
label | 65fbaf8c-62de-5d1d-a91e-6d5169ab342d |  | note | • Visual inspection
label | fbff43b4-e094-587d-9764-6080d1f22165 |  | note | • Measure
label | e5b48f1a-5488-5ef0-969e-f75b2c2214e8 |  | note | ---------------------------------
label | 9d6f3937-0565-5500-ba3e-181eb46446d8 |  | note | FREQUENCY: Each Lot
label | 6823e393-dcef-5b25-b207-a2e8542e933c |  | note | ---------------------------------
label | 4c67be3d-c933-5f21-9fe5-09f2db6d0a23 |  | note | CATEGORY: IP
label | 9e088a93-8419-598e-827b-f38d80b29c16 |  | note | ---------------------------------
label | 9dc7f3c4-9835-5061-82f2-3ab3ce192632 |  | note | RESPONSIBILITY: SE
label | 0890b094-e394-5db9-b7e2-a6bb634209c8 |  | note | ---------------------------------
label | 36174503-9267-5972-a964-4b3f975f2540 |  | note | VERIFYING DOCUMENTS:
label | 6eaf8bc0-2d82-5dd1-90cf-9bed130f4c60 |  | note | • This Checklist
label | df2609cb-b5e2-5e33-ad4e-4ec8738c2dae |  | note | • Material Delivery Docket
label | cd69970b-7ed7-5734-8a08-63fecd70a78c |  | note | ---------------------------------
text | f9333993-a1d6-547d-a17d-1d2e1995d0e0 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 6 - Pits - Cast in Place Drainage Pit
label | 0b6e19be-11b8-5461-a1ff-22b8fc039214 |  | note | REFERENCE:
label | c7affa1c-710f-52f4-8933-8c2e8a125660 |  | note | • IFC Drawings
label | 275f13b9-0362-5dec-bac6-2cdc3185e064 |  | note | • Section 705.06
label | a27dc350-b379-52d8-9c03-f8047904ecc6 |  | note | • Section 610
label | 20257ad6-31e6-5ee3-b92e-f6715fa68af8 |  | note | • Section 611
label | c70e65d3-cc0d-57d0-8799-9b719728ffef |  | note | • ITP-008-CIV-Stormwater Drainage Supply & Installation - Item 5.5
label | 70513f17-1497-5e71-9d26-c59d49edee92 |  | note | ---------------------------------
label | 2950444e-3467-5014-93ca-94d925597e73 |  | note | ACCEPTANCE CRITERIA:
label | e15941d0-4d7a-5fe6-901f-4b7ce1e72ecb |  | note | 1. Cast in place drainage pits shall be constructed at locations and to the dimensions shown on the IFC Drawings and in accordance with Sections 610 and 611.
text | 9484c1fd-1794-503a-a66e-9d227102b730 |  | textbox | – Concrete Mix Design:
text | 46f9344a-fbc2-5224-bfee-d22b9216c6e8 |  | textbox | – Reinforcement & Formwork Checks:
text | fd8134d1-90c0-5a2b-af78-432f5fe8c832 |  | textbox | – Min Cover:
text | 61da7d9f-f07c-5bd2-91d8-ad5005ad5217 |  | textbox | – Drawing Ref No.
label | 58a9e722-7e2e-5d2b-bfe7-58354316e2c8 |  | note | 2. Cast in place drainage pits shall not be constructed with fibre reinforced concrete (FRC).
label | eaa162ea-e400-5ab6-8a20-4e5b13d5f0b2 |  | note | ---------------------------------
label | 30f7b3fe-cfaf-5689-a09d-e321fb75d861 |  | note | METHOD:
label | 5255a506-5403-5582-b263-07a86c78dbf8 |  | note | • Visual inspection
label | 2f2dda92-b5fc-5ced-bded-89e1701a6c06 |  | note | • Measure
label | bb9810e6-0439-55b6-aba7-c296512d6325 |  | note | ---------------------------------
label | b66a196e-05de-5b04-aa87-2c871ec2199d |  | note | FREQUENCY: Each Lot
label | 82c05857-f4e9-59a3-b352-237d466a4746 |  | note | ---------------------------------
label | 44e1189a-d836-5ad6-a3b3-4a042d18a334 |  | note | CATEGORY: IP
label | 3134f130-a88d-5ecd-b457-14e71903e22c |  | note | ---------------------------------
label | a5675d6c-7837-5e16-8d80-c74157e1379c |  | note | RESPONSIBILITY: SE
label | 59fed345-b4d8-517b-b3b5-819f452a1dd8 |  | note | ---------------------------------
label | 3a0fe1e6-5f95-5932-93c1-5f0c6e5de14d |  | note | VERIFYING DOCUMENTS:
label | ff388d1d-db01-5b68-bdee-7286d1b3168d |  | note | • This Checklist
label | 2b02dfd0-1e95-58d4-96e8-61fd9b0e1d5a |  | note | • Material Delivery Docket
label | 74dac6d7-ef48-5d2e-b331-f51a73299946 |  | note | ---------------------------------
text | 5cc004b5-6f2d-5ef0-9510-a9d21073f721 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 7 - Pits - Jointing & Drainage Connections
label | 6c32ed3e-af38-5f8b-b830-c0879b2e978e |  | note | REFERENCE:
label | e32c7987-452c-5c86-b4b1-49171737e868 |  | note | • IFC Drawings
label | 6d2e2734-dc59-5165-9087-6988dd7b16d8 |  | note | • Section 705.11
label | 1a85aba0-7820-5abe-95c7-a0832f423eba |  | note | • ITP-008-CIV-Stormwater Drainage Supply & Installation - Item 5.6
label | 8d73822f-6bd4-5221-9f7e-cf9acd907da8 |  | note | ---------------------------------
label | f11ad155-399f-5207-8e24-f7ae36c015b0 |  | note | ACCEPTANCE CRITERIA:
label | 8d88d998-ebc7-5f7d-a649-a1fb1af02a1d |  | note | 1. All connections to drainage pits neatly made in accordance with Section 705.11.
label | 9ac747fa-a50d-52dd-b17f-85287111ddfe |  | note | 2. Openings into drainage pit walls neatly saw cut to the required size not more than 50mm greater than pipe diameter.
label | 51daa0b9-0fa3-5c5a-bb17-1e2c1e9f6bb7 |  | note | 3. Breaking out of holes is not permitted.
label | ad6b4748-9878-5e8e-97bb-38b3316c2e47 |  | note | 4. Drainage pits to be replaced if cracking occurs as a result of installing holes or if the hole exceeds the pipe diameter by more than 50 mm.
label | 7e961d90-1c45-50c4-a11f-b8efda54a519 |  | note | 5. Exposed reinforcement to be coated with an approved epoxy treatment to prevent corrosion prior to rendering around the pipes.
label | 2926e5e7-c5b7-5ae2-857c-633bb90ebee6 |  | note | ---------------------------------
label | 300ace84-2871-5b5e-aaef-9f16aa48bf37 |  | note | METHOD:
label | bbb45c09-2b73-54df-807d-0bfcceb1b679 |  | note | • Visual inspection
label | 7a78234d-812a-5757-9e00-9876c1ee2756 |  | note | • Measure
label | 49aaeb0e-3474-57a3-a9cd-36aa8e661a16 |  | note | ---------------------------------
label | c2c1adbe-e046-5746-9e81-153408752e8d |  | note | FREQUENCY: Each Lot
label | fa54321b-0054-53aa-bcab-92f03eb17b4e |  | note | ---------------------------------
label | fac41546-7eb2-5b7a-b91b-a9633a14b371 |  | note | CATEGORY: IP
label | c670b8d3-f183-538a-b86c-1290283fe859 |  | note | ---------------------------------
label | 8a6ed3c8-8433-5c05-b78c-0dd07abddad7 |  | note | RESPONSIBILITY: SE
label | 7fddd01c-4ced-5047-af58-6f26059a6f43 |  | note | ---------------------------------
label | 1807016f-6525-5c03-ae6c-5860ee1b4b4b |  | note | VERIFYING DOCUMENTS: This Checklist
label | 25b56ff6-a9b4-5e1c-a9a2-ef3f8a4ce5cb |  | note | ---------------------------------
text | 6a6225ee-acc5-5d83-b968-26fda021340d |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 8 - Pits - Shaping of Floor
label | 4c039e29-38b2-5b1f-89c1-429bc46870c9 |  | note | REFERENCE:
label | 6636d6da-f22d-5e3b-bcef-dfa0d3f64124 |  | note | • Section 705.13
label | b6f36c93-6c1e-5cff-8206-32c5ba3b06ba |  | note | • ITP-008-CIV-Stormwater Drainage Supply & Installation - Section 5.7
label | 76c3a6d9-7929-59fb-ac53-0198e0d191ca |  | note | ---------------------------------
label | 736a63b1-5b22-5216-a678-fb55c7741ee5 |  | note | ACCEPTANCE CRITERIA:
label | fc1f161b-048f-56c8-95cc-80bea35805ce |  | note | 1. Drainage pit floors smoothly shaped from the inlets to the outlet for a height of one‑third of the diameter of the outlet pipe with cementitious mortar in accordance with Section 705.13.
label | c852c816-4334-518b-9693-eb664279d81f |  | note | ---------------------------------
label | f0774edb-a598-59cf-bd1c-20cfa35d3798 |  | note | METHOD:
label | 6ebfdcde-c3f6-5fa2-8cee-9c72310e40dd |  | note | • Visual inspection
label | 5e271432-013a-56f8-aea7-7a799b30ec96 |  | note | • Measure
label | e7a15b14-0902-5458-8aaf-cfd59e99b887 |  | note | ---------------------------------
label | 2e9c45e9-533e-5a5d-8d91-21cc59bbf329 |  | note | FREQUENCY: Each Lot
label | cee992bd-7766-5104-bb3a-9bda6e69c8ba |  | note | ---------------------------------
label | 883cad0c-19d7-5ccb-8e6f-aaafa76300b3 |  | note | CATEGORY: IP
label | 64fd4d39-1af5-5b39-b0d3-f60568a8ad5d |  | note | ---------------------------------
label | e1dd2c2d-5571-5806-ae17-c56cfb05888d |  | note | RESPONSIBILITY: SE
label | 2b370c32-f40c-5a14-a071-10669fcaedd4 |  | note | ---------------------------------
label | 59f24159-5299-5a0f-96e5-fbbdc836941f |  | note | VERIFYING DOCUMENTS:
label | 86bb8fde-d1bc-5d92-961c-c4cc171d46dd |  | note | • This Checklist
label | 0a0a94a6-9007-5300-bf77-dd83c270cdd4 |  | note | • Survey Report
label | 3dbb1376-10f2-5e9c-8052-00a869760ed8 |  | note | ---------------------------------
text | 4f26131b-b535-525f-be28-6d55b3e52e63 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 9 - Pits - Step Irons
label | 3eb04032-51db-5bef-a6f2-90e16cfb3a4e |  | note | REFERENCE:
label | b11c2203-64d4-5567-a0a2-10c39148dfdc |  | note | • IFC Drawings
label | 4c2b5404-a1d6-585c-9a62-7d128fa60202 |  | note | • Section 705.12
label | f0ed12c2-a474-5948-b9d9-d8e14af20d5e |  | note | • ITP-008-CIV-Stormwater Drainage Supply & Installation - Section 5.8
label | a8b14b48-7067-508b-8699-11ec1041a7fe |  | note | ---------------------------------
label | 930b946a-2235-5a82-84be-1b37345705ed |  | note | ACCEPTANCE CRITERIA:
label | f17b13c4-6a16-582d-8aa1-b5306c561fa7 |  | note | 1. Drainage pits greater than 1.0m deep fitted with step irons in accordance with 705.12.
label | 84e78289-9085-5f3c-89ed-2267920ba7d2 |  | note | 2. Ladder rungs to not obstruct openings and that water does not discharge on them.
label | e27d589c-92fa-5932-aa48-e95b730680b4 |  | note | 3. Step rungs do not come within 50mm of the top of the riser.
label | 8597bc44-9b5a-577b-ab96-323a17ce97f2 |  | note | 4. Step irons of an approved proprietary type shall be installed in accordance with the manufacturer's instructions.
label | f26ada7a-5858-5b57-9d5b-7d99ef9e044d |  | note | ---------------------------------
label | fcd920d2-c418-5ec7-8071-4809e72ee048 |  | note | METHOD:
label | 7002d7da-c627-5654-93a7-ae1528e7a852 |  | note | Visual inspection
label | bc307c6a-3f69-5763-aa0c-8d1a396a60f2 |  | note | Measure
label | 630ebaff-0527-500c-88bd-a81236d29be9 |  | note | ---------------------------------
label | a9980369-416e-5767-a4a8-87ec57ac73d6 |  | note | FREQUENCY: Each Lot
label | 17ee8c8d-2169-53a6-8565-22a6b79d390b |  | note | ---------------------------------
label | 45524b7f-5ba2-5b59-9aab-1bb984aec560 |  | note | CATEGORY: IP
label | ad0f3e65-298b-5fa2-a151-3f2ae8fcd465 |  | note | ---------------------------------
label | c24e4c04-b22f-5a62-a852-7a36506566cc |  | note | RESPONSIBILITY: SE
label | ae3f78d8-f382-5c03-8588-6242070ac84d |  | note | ---------------------------------
label | b821450c-27ef-518f-8fce-5bc77fd5e527 |  | note | VERIFYING DOCUMENTS: This Checklist
label | 0c6ca840-7bef-5fef-89ca-47e9790741bc |  | note | ---------------------------------
text | 4c21d7df-6dd6-52ae-9120-90df0bbab1c0 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 10 - Pits - Fitting of Covers
label | 0ad0a693-c1dc-558b-9c32-4a9bfe5d56a1 |  | note | REFERENCE:
label | 69826d87-909e-5f50-8262-94d2d626b57d |  | note | • IFC Drawings
label | 091e7d46-0733-5539-886d-ba21729c482b |  | note | • Section 705.17
label | 28abdcad-b1c5-5740-b837-3315fa0dfa68 |  | note | • ITP-008-CIV-Stormwater Drainage Supply & Installation - Section 5.9
label | 40be2ab1-c0b5-5b3b-a331-1afe2f89e6f6 |  | note | ---------------------------------
label | 02f4361c-3fec-5e1a-b18a-f6c55c9322f9 |  | note | ACCEPTANCE CRITERIA:
label | a6bb0303-5439-52fc-bca7-87645053108c |  | note | 1. Frames for drainage pit covers to be cast into the top of the drainage pit or bedded on fresh mortar, 5 mm thick, consisting of two parts of sand, one part of cement.
label | fc5491eb-ba29-5ba5-88e4-c7f9f77efe0b |  | note | 2. Height within 10mm of the design level.
label | 7bcbe5f7-ceb0-50fc-b857-077b009d068c |  | note | ---------------------------------
label | c02b2a6e-468b-5127-a39a-55677d89b9d3 |  | note | METHOD:
label | a182ca33-2609-5769-a6ce-155a60fe5c2b |  | note | • Visual inspection
label | 399cdbd7-3652-5f55-8e3e-b552da8e2701 |  | note | • Measure
label | 1d40f5e5-b067-50e5-9c8f-228538ff7fbb |  | note | ---------------------------------
label | 0e45197e-0991-5dbd-8667-8e8c78e73e0a |  | note | FREQUENCY: Each Lot
label | 916bb89c-31b9-5868-ad1c-97c78e357ee5 |  | note | ---------------------------------
label | b162e5cb-cd4e-5104-bba2-af0ea0b208c8 |  | note | CATEGORY: IP
label | b32a9b46-bdd6-5703-8124-c281f1d261bd |  | note | ---------------------------------
label | 845dd459-4c87-5ed7-8347-21a391fae070 |  | note | RESPONSIBILITY: SE
label | 38768ae6-33d2-5c47-965a-0945d6e7b05b |  | note | ---------------------------------
label | 0046fb59-239a-5b69-800a-f662092e4e54 |  | note | VERIFYING DOCUMENTS: This Checklist
label | 17b4e28a-b8a7-554c-9b8c-d23a1130d74e |  | note | ---------------------------------
text | 19fbe447-a152-5079-98da-3485edba97a8 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 11 - Pits - Pit Lids
label | df1de599-d46b-56f3-bee5-6461d85a4079 |  | note | REFERENCE:
label | d7bc0dc7-322e-5744-b36f-61f8135a521e |  | note | • IFC Drawings
label | 84c3a4fa-a12e-5b96-9d7b-94f2adcbce03 |  | note | • ITP-008-CIV-Stormwater Drainage Supply & Installation - Section 5.10
label | 52e3b067-39db-5cd6-897f-32016f305a87 |  | note | ---------------------------------
label | 92582495-a000-5f01-9222-51eeed162864 |  | note | ACCEPTANCE CRITERIA:
label | a5daa3f7-fd8a-5714-bbcf-b04c8971924b |  | note | 1. All stormwater pits to be provided with locakable pit lid minimum Class D with in-fill material or fibre glass Terra Firm Enduro or similar.
label | df481b6f-46d0-526d-8996-4e2524fecc98 |  | note | ---------------------------------
label | 6c1a28aa-e84a-5f26-a9ac-c9c422b1aee1 |  | note | METHOD: Visual inspection
label | 32370ad8-2c99-55ee-aa7f-53ee4c6160fd |  | note | ---------------------------------
label | 313625e0-4bc8-5c87-8a00-b12842e3cf8c |  | note | FREQUENCY: Each Lot
label | b86172e1-5a22-5a72-afea-be59a0bc712e |  | note | ---------------------------------
label | bbde57fc-5338-5ea0-8f64-61d16e3a5436 |  | note | CATEGORY: IP
label | f71b61f1-088f-5712-bc44-765035cc45c0 |  | note | ---------------------------------
label | 533ac7bc-b752-5691-a0f6-ae523efeb1f5 |  | note | RESPONSIBILITY: SE
label | 5b09ffa0-188c-5be2-b063-76751c518d08 |  | note | ---------------------------------
label | 669eed30-e351-50dd-a429-8a07061d9252 |  | note | VERIFYING DOCUMENTS: This Checklist
label | 9db406fe-d984-506d-8fc4-5dc72a2e1a31 |  | note | ---------------------------------
text | 87416cce-c65a-5b68-949e-30dd388e650c |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 12 - Pits - Backfilling Around Drainage Pits
label | da557e6b-8a8b-5a43-ad4e-4c381a6b87ea |  | note | REFERENCE:
label | 3308df2f-036f-5fb1-91ee-76ee4bfcff59 |  | note | • Section 705.18
label | a50330b3-547b-59e3-bd13-d65acfd5c5cf |  | note | • ITP-008-CIV-Stormwater Drainage Supply & Installation - Section 5.11
label | e8e41f08-e5f3-5616-9d9d-bd30a4967b01 |  | note | ---------------------------------
label | 13931d24-abc5-561a-87a2-92ba854677f1 |  | note | ACCEPTANCE CRITERIA:
label | df26af65-625f-5639-bb18-4fb5f29d03e9 |  | note | 1. Backfilling around drainage pits placed in layers not exceeding 300 mm loose thickness and compacted to refusal using hand held mechanical equipment.
label | 0ae568e7-bea1-5dcc-abb2-5938f12fa4b9 |  | note | ---------------------------------
label | 9dd23b52-55da-5b23-8927-04693ac312ea |  | note | METHOD:
label | ddbeb7e0-90ba-5841-a158-f6a024433568 |  | note | • Visual inspection
label | 5c279b66-aa8a-5a46-92b7-f57d9df7b9f9 |  | note | • Measure
label | 35a2865e-0cf3-576f-b519-f09945fb8717 |  | note | ---------------------------------
label | e2916034-5da0-5ee8-93b4-4269fdea4f25 |  | note | FREQUENCY: Each Lot
label | 77bed48c-980f-5f2e-8b5d-67eebb2ee4f4 |  | note | ---------------------------------
label | d605084a-f1c2-59ff-9eaa-cafb26a90598 |  | note | CATEGORY: IP
label | cbde8acf-2f0f-5dd6-8b40-93ff052a6343 |  | note | ---------------------------------
label | ef7dfb0a-5c55-55e7-b73d-f6a58b53b22d |  | note | RESPONSIBILITY: SE
label | f1b69732-ffc8-51d1-9fb6-a09e6f62984c |  | note | ---------------------------------
label | 71be012a-dd8a-5eec-9901-ce30df0d4a4a |  | note | VERIFYING DOCUMENTS: This Checklist
label | 495cba22-b4e9-5a4b-a605-bd0d4e544487 |  | note | ---------------------------------
text | 9c55294c-edba-5b98-898b-5e7cae97dead |  | textbox | Date Completed:
checklist-sectioned |  |  | checklist | ITP-015-CIV-Kerb and Channel | itp |  |  |  | Yes | ITP-015-CIV-Kerb and Channel Rev 0 | 22fcf66c-a0ad-449a-92df-cae9fe300731
checkpoint-group |  |  | section | Referenced Documentation
checkpoint-status |  |  | checkpoint | Referenced Documentation
label | 009b0b85-9846-5614-af5c-6da2e07d8d4e |  | note | Document Title: ITP-015-CIV-Kerb and Channel
label | 8e4cd3d1-5f7b-5ac9-a1c9-34ed64a1f4a0 |  | note | ITP Description: Kerb and Channel
label | 279ed2e7-32d4-5936-b07f-d48e25ef4dc0 |  | note | Document Number (in Teambinder): MRP-0000-MRPA-ALT-ITP-00XX
label | 08edf004-81e7-53e8-97c4-7c9660c80106 |  | note | Discipline (e.g. CIV/STR/RAIL): CIV
label | 30041052-cbf3-55ed-b6ae-b7fbd92a47a0 |  | note | Revision Number: 0
label | 81f54f9a-eabf-51c6-a1b5-0ca5c5f6facc |  | note | Revision Date: 16/12/22
label | b27efb9b-eaec-5d39-8e5d-0f1c68d107b9 |  | note | ITP created by: Isaac El Zayat
label | 85cb20cc-9585-5124-9f83-14abb38e8d07 |  | note | ITP approved for use by: Victor Mira
label | 4da3ae0b-4114-51e6-97b5-785a8ac619f5 |  | note | 1.1 Non Dependent
label | 6a6bfb6c-7aaa-53c0-b742-bc335d701a13 |  | note | Reference: VicRoads Section 703, VR SD2001, VR SD2102, AS 2876, AS1379
checkpoint-group |  |  | section | Preliminary Works - Materials
checkpoint-status |  |  | checkpoint | 2.2 Mix design
label | 5a1e31d0-1433-5127-b719-bb224dbf4fed |  | note | REFERENCE: SD2001, AS1379, Section 703.05, 703.06, 703.07
label | 8793c194-1e10-554d-baba-46e1a2e2ce34 |  | note | – – – – – – – – – – – – – – – – –
label | 8eafa027-8be4-55b7-b9ab-3479bc59c5fa |  | note | ACCEPTANCE CRITERIA:
label | 43240ca2-6ae1-55ba-ab46-b290e6e97c36 |  | note | • Approved VR mix design to be used.
label | d209a6f0-4ea1-54c8-8082-85599a7c703a |  | note | • Concrete being placed via extrusion machines have minimum cement content of 320 kg kg/m3
label | 642f9ae3-9d5d-597a-875f-b277941b7f36 |  | note | • Where K&C is placed and compacted with internal vibration between previously placed formwork, concrete shall be: N32 portland cement–based concrete
text | ecb5dee0-693c-5ce4-8f99-6cb88b2f3f68 |  | textbox | TeamBinder Material approval number for the Concrete Mix:
label | 8b4e5bef-7cec-557f-b9c2-d28c26d32703 |  | note | – – – – – – – – – – – – – – – – –
label | 9566883c-5415-5899-b2bf-2f8528c0747a |  | note | METHOD: Verify
label | 0e1b9cd4-2298-54da-890d-a9da8a433df7 |  | note | – – – – – – – – – – – – – – – – –
label | 64406640-093c-5ab1-94ca-c198fdfbb48c |  | note | FREQUENCY: Prior to commencing any activity
label | 6b1bff78-a382-5d8f-941a-1c6bc7402bf3 |  | note | – – – – – – – – – – – – – – – – –
label | c277bca8-e2e2-5a74-81ef-03f2fc86fe65 |  | note | CATEGORY: HP*
label | d8b9718f-a502-51e9-bce0-52c48db7ea9a |  | note | – – – – – – – – – – – – – – – – –
label | 9a8b911c-3756-527c-866e-78af2271508f |  | note | RESPONSIBILITY: SE
label | dfc5ba5e-77c1-52a0-8d2e-ca67b450428e |  | note | – – – – – – – – – – – – – – – – –
label | 77d1c512-a251-5e45-871b-f47aa5375d9a |  | note | VERIFYING DOCUMENTS: TeamBinder Material approval, ITP signed
text | 8367bae0-fcd3-555a-b029-59899f8e8ac9 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 2.3 Bedding Material
label | 3f88161f-836e-5002-9fcc-7511fa33b95f |  | note | REFERENCE: Section 703.21, IFC Drawings
label | ac6f147d-5a1b-5c89-bc6f-c65b465810db |  | note | – – – – – – – – – – – – – – – – –
label | 3124cdba-0d58-517f-89ca-34c9d074f356 |  | note | ACCEPTANCE CRITERIA: Bedding shall be size 20 mm Class 3 or Class 4 crushed rock or Class 3 or Class 4 crushed concrete. Or as per IFC drawings.
text | c09a2139-8a75-5bf7-8534-5be27a59f2e3 |  | textbox | TeamBinder Material approval number for Bedding:
label | 700d8d35-3f8b-5a7e-b35f-189bfd952f57 |  | note | – – – – – – – – – – – – – – – – –
label | d5f75223-6290-56fc-95fa-04b3be68cef7 |  | note | METHOD: Verify
label | e0d1da42-71f6-5610-8941-4d3047319a28 |  | note | – – – – – – – – – – – – – – – – –
label | 8001c62e-9bd4-54d8-9425-fe4b2208f154 |  | note | FREQUENCY: Prior to commencing any activity
label | b5f9d8b5-41ab-53c1-8ce9-45f150c78daa |  | note | – – – – – – – – – – – – – – – – –
label | 08969635-ca1c-5832-aeef-12845160994a |  | note | CATEGORY: HP*
label | 75af38ea-b85d-5599-8705-40a8f42c1925 |  | note | – – – – – – – – – – – – – – – – –
label | 04bbaeb1-101e-5abf-a235-ce4040acd89f |  | note | RESPONSIBILITY: SE
label | 6fcd0518-73de-5aae-8f6a-9ba46514dbea |  | note | – – – – – – – – – – – – – – – – –
label | 0b5b12d4-df9a-591a-983c-dee10f7e9e4e |  | note | VERIFYING DOCUMENTS: TeamBinder Material approval, ITP signed
text | 3fb8d8af-92c0-50a5-8307-2461a9285eb2 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 2.4 Curing Compound
label | 61f038ff-a538-521d-802a-ec36cf4706e7 |  | note | REFERENCE: Section 703.10
label | b1da764f-27d6-5683-bc32-8d054e37b362 |  | note | – – – – – – – – – – – – – – – – –
label | 60becb14-06d5-51e9-a0cc-9d69b13cf074 |  | note | ACCEPTANCE CRITERIA: Curing compound shall comply with AS3799
text | 47ecf238-462b-5c39-9e08-94d6f71087b9 |  | textbox | TeamBinder Material approval number for Curing Compound:
label | 49538ff9-08ae-5200-b458-c42c5df4c5e5 |  | note | – – – – – – – – – – – – – – – – –
label | 0b46957e-ca8d-5bb2-ae28-a5de1b125aad |  | note | METHOD: Verify
label | 0df53f6b-5df3-5a27-8a2a-f5e07f13cf38 |  | note | – – – – – – – – – – – – – – – – –
label | 68fa5587-8371-50fd-a663-f9c3f51094aa |  | note | FREQUENCY: Prior to commencing any activity
label | ee31a341-1b6e-5a46-aae1-389ada6a2143 |  | note | – – – – – – – – – – – – – – – – –
label | ea3ab702-60eb-51ea-b466-f56ab6e095d1 |  | note | CATEGORY: HP*
label | a2471272-8939-5d84-bdbb-e3c68d5c0a56 |  | note | – – – – – – – – – – – – – – – – –
label | 2673e2a4-8c75-5d69-89af-008d801cbe18 |  | note | RESPONSIBILITY: SE
label | 74ade77c-72af-5f7e-a438-018e05965d50 |  | note | – – – – – – – – – – – – – – – – –
label | 8e18faf4-e444-501c-95eb-892c115520c2 |  | note | VERIFYING DOCUMENTS: TeamBinder Material approval, ITP signed
text | d7db750f-139c-51c3-95bc-b46d2f545483 |  | textbox | Date Completed:
checkpoint-group |  |  | section | Preliminary Works - Documents
checkpoint-status |  |  | checkpoint | 2.1 Check for correct documentation
label | b089b2dd-0ed3-556c-8452-7d7c711a1860 |  | note | REFERENCE: Drawing and Drawing Register
label | d310df17-1eac-59f8-ac80-664d3456deae |  | note | – – – – – – – – – – – – – – – – –
label | d30c3627-8542-574b-9f0c-1f9479c83b41 |  | note | ACCEPTANCE CRITERIA: Ensure that all employee and sub contractors are:
label | 15535d57-b1dc-5dc5-9f66-549d32c244b1 |  | note | — Using the correct and complete set of drawings
label | eab875e9-ed1e-5661-baf0-7cfddbf2497c |  | note | — All drawings are the latest version
label | 3496e985-cd51-5836-8ae8-25497a41bdba |  | note | – – – – – – – – – – – – – – – – –
label | 7bba940b-7573-583a-933b-eb54cce6fad2 |  | note | METHOD: Visual inspection
label | e1e5375f-d8e6-5217-ae9a-950206aa9d28 |  | note | – – – – – – – – – – – – – – – – –
label | ad6e408a-5f75-539f-8550-2d67e445564a |  | note | FREQUENCY: Prior to commencing any activity
label | 510557e8-898e-53e2-b0c3-cadcc5e69d7f |  | note | – – – – – – – – – – – – – – – – –
label | 560153af-ff1f-52c1-b6e4-1dd671530a5f |  | note | CATEGORY: HP*
label | b2221f28-849b-5ffe-9768-1f27cbe8fe6b |  | note | – – – – – – – – – – – – – – – – –
label | 6f409df5-9355-5653-9425-4fac4fa72f02 |  | note | RESPONSIBILITY: SE/PE
label | 9cc20667-ffea-5efe-a1fc-8b3c1a517a68 |  | note | – – – – – – – – – – – – – – – – –
label | d67c355f-b28b-5099-9fba-142a1921e2d5 |  | note | VERIFYING DOCUMENTS: ITP Signed
text | 4e1f5115-7a9f-527d-82e5-8baca0eeebf8 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | Lot Map
label | 25c6853a-ca66-59ac-8360-4b7b170c585a |  | note | REFERENCE: MRPA Lot Management Procedure
label | b07ac09c-3dd2-58f7-a691-f8769256a2a5 |  | note | – – – – – – – – – – – – – – – – –
label | 858ac52e-8b77-5071-a5c2-dcd7d5bb6a5b |  | note | ACCEPTANCE CRITERIA: Upload a Marked up drawing which indicates the Location of this Lot:
label | b91f64c7-b080-50fa-a9e6-0ad3fdb7777c |  | note | • Attach: Lot Map
label | 0b7343d5-a27c-5d06-a6f8-c456907956b4 |  | note | – – – – – – – – – – – – – – – – –
label | 8fd4a064-bc41-57c0-acb6-eecd748be9de |  | note | METHOD: Document Review
label | 4ba919f4-4429-52e1-a2ee-1af0e0854d36 |  | note | – – – – – – – – – – – – – – – – –
label | 00af3142-1828-5895-83e8-c4380681a228 |  | note | FREQUENCY: For Each Lot
label | 5f4369f2-e676-50d6-aa7b-61e4cc08ce04 |  | note | – – – – – – – – – – – – – – – – –
label | 0d75dd56-b586-5b30-8e04-fe641d01648b |  | note | CATEGORY: HP*
label | 494e161b-c42b-5e4b-b066-8f36ce71fbf4 |  | note | – – – – – – – – – – – – – – – – –
label | b4f2fbe0-c030-5e42-ad84-8daeeaee4cb5 |  | note | RESPONSIBILITY: SE/PE
label | 10acd828-c5a4-5eb5-9a2b-58a7ee12c6de |  | note | – – – – – – – – – – – – – – – – –
label | d9e1c5ea-fe89-574c-bb96-9c33c51277a1 |  | note | VERIFYING DOCUMENTS: Lot Map
text | 4af5d2c5-f998-52c1-b1dc-75ce709ac8e3 |  | textbox | Date Completed:
checkpoint-group |  |  | section | Pre-construction / Pre-installation Activities
checkpoint-status |  |  | checkpoint | 3.1 Setting out
label | ee1cd808-b1ab-5de7-abda-bd2942e76034 |  | note | REFERENCE: Section 703.17
label | 2ea82630-6349-5ace-a425-4dcff0016e85 |  | note | – – – – – – – – – – – – – – – – –
label | d4f58911-e05b-589c-bd08-c026cc414f5e |  | note | ACCEPTANCE CRITERIA: Set out work in accordance with drawing.
label | a527abec-1c47-59cf-aeea-f5f1a69bc8fe |  | note | • The superintendent will review and confirm set out.
label | 679a21c0-8e9a-5640-9198-1580ce2ef4b5 |  | note | • The work shall be constructed in accordance with the confirmed set out to the line and level and cross-sectional profiles as shown on the drawings.
label | b176c907-217d-5baa-96f1-2d0019832074 |  | note | • Attach: Survey Report
label | 272bffe1-98be-5648-b25b-5bca165b1ba6 |  | note | – – – – – – – – – – – – – – – – –
label | 61639091-b4f2-562e-a8f5-54c9b1b463c7 |  | note | METHOD: verify
label | b86a650d-92d2-5b1a-b7fb-50faafed41a6 |  | note | – – – – – – – – – – – – – – – – –
label | b9e12d7a-9283-59ae-80cc-efa2a9cd6bc2 |  | note | FREQUENCY: Prior to start
label | 04abb4cd-6f69-56d1-99d9-d0b016486091 |  | note | – – – – – – – – – – – – – – – – –
label | e75d6c7d-6bb8-5258-9767-4f3c7fc3f64e |  | note | CATEGORY: HP
label | 374fa501-585b-5ca6-972e-ff8bb40754c9 |  | note | – – – – – – – – – – – – – – – – –
label | cac21d97-d6fd-5507-bbde-174256a8e3d2 |  | note | RESPONSIBILITY: Surveyor
label | 423d1ee1-7568-5d97-a833-7c37985c2d19 |  | note | – – – – – – – – – – – – – – – – –
label | 5753d09d-593b-5b1a-891b-c6a460f8b7aa |  | note | VERIFYING DOCUMENTS: ITP signed, Survey Report
text | d9dd448a-3d30-5653-b413-63785620a962 |  | textbox | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.2 Temporary drainage provisions
label | afed759f-ef43-5f74-8ac8-91311cdc52c1 |  | note | REFERENCE: Section 703.18
label | 65195814-84d0-549b-b70d-5e131c58ac6b |  | note | – – – – – – – – – – – – – – – – –
label | a975d8a7-7105-567f-8f77-d94a0bf3f357 |  | note | ACCEPTANCE CRITERIA: If obstructing waterways ,culverts or channels, temporary diversion of discharge of drainage and storm water to be in place.
label | d4888a9b-eeda-5dfd-af28-4d99de92d99f |  | note | • Need to obtain prior written approval from the relevant waterway authority prior to diversion.
label | 5424461f-402e-5904-96db-e4f883d4d906 |  | note | – – – – – – – – – – – – – – – – –
label | 2877beca-e0d9-586e-aa4f-b49d5b5882c9 |  | note | METHOD: Visual inspection
label | 8dbd7bd2-0688-599c-bf9c-1954887680c6 |  | note | – – – – – – – – – – – – – – – – –
label | 56f1874b-5f7f-5f40-8f1b-5076edd78285 |  | note | FREQUENCY: If required
label | 21b1b06b-4f0b-5377-ae70-ef1f3e74d4cb |  | note | – – – – – – – – – – – – – – – – –
label | 29ee0ee9-f4ad-50b9-a28f-7082a28f0845 |  | note | CATEGORY: WP
label | 69e90580-b5aa-5466-b0fc-f385fd1951c5 |  | note | – – – – – – – – – – – – – – – – –
label | 9063ceec-b994-5c58-8421-7dcd9c192c72 |  | note | RESPONSIBILITY: SE
label | 56e94125-92c9-5603-8485-62bbfef69a7a |  | note | – – – – – – – – – – – – – – – – –
label | 57c5f410-d939-52e0-abce-b5467a1f79bc |  | note | VERIFYING DOCUMENTS: ITP signed
text | 409adc9c-44f0-578a-ae1a-fd192031a10c |  | textbox | Date Completed:
checkpoint-group |  |  | section | Construction / Installation Activities
checkpoint-status |  |  | checkpoint | 4.1 Bedding
label | 762e074b-09b0-5f70-a982-8d4196e3d2b5 |  | note | REFERENCE: Section 703.21
label | 1f432c39-c800-52ff-bf4c-d4b97bbfd710 |  | note | – – – – – – – – – – – – – – – – –
label | 6ac67939-de31-586d-be8b-460dfd4371d0 |  | note | ACCEPTANCE CRITERIA: Bedding to be compacted to a thickness of not less than 100mm.
label | 01c1d797-0791-5092-bc6f-914e4e57e1c2 |  | note | • Bedding shall be trimmed to appropriate levels, moistened as necessary, and be firmly compacted .
label | 779bf67d-5b60-573d-b0e8-2451582262c0 |  | note | – – – – – – – – – – – – – – – – –
label | c3ae9df2-6a9e-5018-919b-4e8e6e95dd9c |  | note | METHOD: Visual Measure
label | fee4b89c-7e7a-5571-8890-6f31e1ec0b20 |  | note | – – – – – – – – – – – – – – – – –
label | 31820287-2dc3-5455-a253-9d97f69214f9 |  | note | FREQUENCY: Each lot
label | 7b7702d2-f36a-5f06-b68c-431db18b357e |  | note | – – – – – – – – – – – – – – – – –
label | 974ffea1-9efe-5b12-b512-d85fbce3e7e8 |  | note | CATEGORY: WP
label | 82b47de5-51b5-56c2-a135-8b9ee01c830a |  | note | – – – – – – – – – – – – – – – – –
label | 51da41f6-443f-5562-b683-9583346140be |  | note | RESPONSIBILITY: SE
label | a5583990-b09f-52a0-b6b7-747a6adfa500 |  | note | – – – – – – – – – – – – – – – – –
label | c903959d-2fb7-5d21-84dc-7a480bf134ae |  | note | VERIFYING DOCUMENTS: ITP signed
text | e689c30f-096a-5f8a-8623-11f5f46932a9 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 4.2 Formwork
label | a4e581fb-eae2-5f2c-bf70-4f87f2deb2e8 |  | note | REFERENCE: Section 703.12 AS3610
label | c2426949-9386-5e76-bc89-2bc6ac81e3e5 |  | note | – – – – – – – – – – – – – – – – –
label | 7d811fad-11f6-53d6-86df-7dfb2435b51e |  | note | ACCEPTANCE CRITERIA: Joints in formwork shall be constructed such that loss of mortar is prevented.
label | 7b68ad43-b84e-525b-8869-e9dbd9dc1816 |  | note | • Prior to placing concrete in an earth excavation, formwork shall be erected so that fresh concrete is not placed directly against the sides of the excavation.
label | 00b4020f-da86-54e2-af50-77b58619d00e |  | note | – – – – – – – – – – – – – – – – –
label | f5a55a3a-da4e-568d-93ed-13a90b3a99d6 |  | note | METHOD: Visual Inspection
label | 4ac166ae-ef69-56fa-82d4-7f0018da575c |  | note | – – – – – – – – – – – – – – – – –
label | b5ba3980-e514-56db-be2b-55d96b4d4138 |  | note | FREQUENCY: Each lot
label | abdf5389-c925-5760-9865-a19dc1055804 |  | note | – – – – – – – – – – – – – – – – –
label | 6e6bf7d0-db77-54b6-8307-42dc1f64aafc |  | note | CATEGORY: WP
label | 2ae4c4dd-e6d6-5ceb-aae6-1f5416ddf467 |  | note | – – – – – – – – – – – – – – – – –
label | a9b399a3-bc6c-54b4-a5e6-be1c73b624d1 |  | note | RESPONSIBILITY: SE
label | 6bd8b126-7b3f-5121-9558-da2159121c06 |  | note | – – – – – – – – – – – – – – – – –
label | f3515dbd-2b91-5e81-8fab-6c8aa52dd635 |  | note | VERIFYING DOCUMENTS: ITP signed
text | 51a8bc98-68f9-5244-924e-72956176d9d9 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 4.3 Pre Pour Check
label | 30baf684-2e7d-56f1-a2b8-9be588dc0cda |  | note | REFERENCE: Section 703.09
label | 06524336-786d-53b0-a173-ee9cf1731a51 |  | note | • Section 703.21 Section 610.17a), b) & c)
label | ee0bc2c9-5437-57d9-921a-8494e634ed2e |  | note | – – – – – – – – – – – – – – – – –
label | c7eda2f9-47ca-50ba-9379-059346e9f733 |  | note | ACCEPTANCE CRITERIA: Bedding shall be moist but shall have no free water on the surface.
label | 0aff6cfe-7592-51d3-83c9-85c7f1e6d16e |  | note | • Concrete shall not be placed when the air temperature measured at the point of placement is > 35°C or < 5°C
label | 2ff43214-00af-59b5-91c8-34898d62a1e6 |  | note | – – – – – – – – – – – – – – – – –
label | a8d953e5-f3a7-522a-a210-b8e86066ccea |  | note | METHOD: Verify
label | 8cbb57f0-ed39-54bd-8bea-61334b0e011e |  | note | – – – – – – – – – – – – – – – – –
label | 96ca5d0f-f5e3-5c5a-9e20-504e0724dd38 |  | note | FREQUENCY: Each lot
label | 7a9e86f8-3c13-599f-9024-2fbbb50eae3b |  | note | – – – – – – – – – – – – – – – – –
label | 4d8723a7-d5aa-5a24-9347-8d6ea4fbe9e9 |  | note | CATEGORY: HP*
label | 923b0363-8d9f-5708-be9d-eb349fd8ef69 |  | note | – – – – – – – – – – – – – – – – –
label | 5d394e83-a893-5d69-a796-c04d06770e5d |  | note | RESPONSIBILITY: SE
label | 10ded6b2-7e61-5acf-afe3-c9e96d310eab |  | note | – – – – – – – – – – – – – – – – –
label | 3bac01d7-37e2-5b2c-a4bd-3c9587d247c2 |  | note | VERIFYING DOCUMENTS: ITP signed
text | 8857eb30-6500-5acd-a913-4cac7773ec65 |  | textbox | • Ambient temperature |  |  | °C
text | 84f4e73d-ae50-5a59-af17-95797e4a3c10 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 4.4 Concrete placement
label | 97d25d60-2d9d-5ff1-8cc5-2e15b5f49ed7 |  | note | REFERENCE: Section 703.08
label | 4c67b128-d675-561d-a7c0-d3676ab56b3b |  | note | • Section 703.23
label | d1976323-729e-5dee-85cc-402c6e0ad413 |  | note | – – – – – – – – – – – – – – – – –
label | a453678e-4d7f-5dbc-9dad-0662b61e443d |  | note | ACCEPTANCE CRITERIA: Temperature of concrete to be measured immediately prior to placing and shall not be less than 10°C or greater than 32°C.
label | e95107d3-55c3-52b6-84cc-ba60e1b7fdcf |  | note | • Concrete is to be satisfactorily compacted so that finished surface are free from surface pitting larger than 5mm diameter, honey combing or faulty patches.
label | d0dc435a-0cae-5269-8df4-80f8a96e1ff2 |  | note | • Fresh concrete shall not be placed against concrete which has taken its initial set, except at properly formed construction joints.
label | f187b065-aab8-53ac-a948-3ec22cdefd7d |  | note | • Machine Extrusion: Concrete is to be fed to extrusion machine at a uniform rate.
label | b573af53-3a28-56ec-b7e2-d722e97901cc |  | note | – – – – – – – – – – – – – – – – –
label | f93a55ea-918e-55bd-81ed-35ea57823e63 |  | note | METHOD: Visual Measure
label | ba191213-2c60-5fcf-9c45-44d431e1c5d2 |  | note | – – – – – – – – – – – – – – – – –
label | 87b8aa60-9242-59cf-a301-2d4468011640 |  | note | FREQUENCY: Each lot
label | 984a11bb-2358-5d8e-a9db-5ed68f0bfd86 |  | note | – – – – – – – – – – – – – – – – –
label | f8bff205-3d92-59fc-86ce-9b7c2833c3c7 |  | note | CATEGORY: IP
label | e4539e86-91bd-5b87-b94b-fece5a5107c8 |  | note | – – – – – – – – – – – – – – – – –
label | c06d336f-eada-55e2-b7cb-e3d5b288119a |  | note | RESPONSIBILITY: SE
label | 2f978d3c-a969-57a9-934b-8b19da5f644d |  | note | – – – – – – – – – – – – – – – – –
label | c25bb7be-cb48-54cd-b3df-dbb2fc2ed6dd |  | note | VERIFYING DOCUMENTS: ITP signed
text | 389eac80-4b90-5616-876b-c820306bfb6f |  | textbox | • Ambient temperature |  |  | °C
text | 0b9815e2-e554-5505-8d8b-ea8888151527 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 4.5 Transitions
label | a70f7862-7afc-5d27-ba2e-647af3c7d687 |  | note | REFERENCE: Section 703.24
label | 367a3d26-bba8-512d-bd98-d9e047429ba0 |  | note | – – – – – – – – – – – – – – – – –
label | 868b422b-89f5-55f5-86a5-ba6231419071 |  | note | ACCEPTANCE CRITERIA: Where it is necessary to join to an existing section of profile different from that being constructed, the change of profile shall be made at a constant rate between 10 and 20 mm per metre.
label | 2f9f3818-52c1-53a7-8221-c187f9ba2be2 |  | note | – – – – – – – – – – – – – – – – –
label | 82cd302e-1025-5a7a-9621-ceb66d2596da |  | note | METHOD: Site inspection
label | ec0bbbcc-b596-5bf1-ae78-e3b904b260ab |  | note | – – – – – – – – – – – – – – – – –
label | 1cb8a997-e4d1-53f2-8868-a15389d32d4f |  | note | FREQUENCY: Each lot
label | 3b2a7db5-adee-56da-aa6a-761d60a940c9 |  | note | – – – – – – – – – – – – – – – – –
label | 5ec20c83-e723-504c-a18c-753aed4171b8 |  | note | CATEGORY: IP
label | 9dec7131-157d-569c-8402-f29e888c4ca8 |  | note | – – – – – – – – – – – – – – – – –
label | e0b9855f-608a-54a8-a74e-7c39e96e565b |  | note | RESPONSIBILITY: SE
label | 81464237-b855-5d07-94ec-e0471f379bed |  | note | – – – – – – – – – – – – – – – – –
label | a8b1c20c-e129-523c-a859-bafaae70a86f |  | note | VERIFYING DOCUMENTS: ITP Signed
text | e5af150d-2872-50b6-b682-ee01631f183c |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 4.6 Surface Finish
label | e2cce273-6889-56f8-92f4-43029d8a655f |  | note | REFERENCE: Section 703.25
label | c12925be-f6df-56ab-819b-1cc8f57e9413 |  | note | – – – – – – – – – – – – – – – – –
label | cb06741a-4c72-5ca6-98f6-44a2872c45fd |  | note | ACCEPTANCE CRITERIA: All edgings shall be rendered to a thickness not exceeding 3mm and trowel finished.
label | 3e8792a9-8cc4-5727-a16b-de3bdf4a939c |  | note | • Renderings shall be applied within 30 minutes of extrusion.
label | 5c7d8232-bf6d-5d6d-85af-cc03fc7d668d |  | note | • Concrete to have a neat appearance and uniform colour.
label | 036b6852-8bda-556f-8d52-c4817df800e6 |  | note | • Class 3 finish required for external surfaces.
label | 00d6088d-768a-570d-b615-b38b0ce8d6e8 |  | note | • Class 4 finish required for permanently hidden surfaces.
label | a4410fd8-ad28-59c3-afb0-1d43fff233c7 |  | note | – – – – – – – – – – – – – – – – –
label | 9ddc50e0-a96b-5e66-82c8-3ff0d3f34d9b |  | note | METHOD: Visual inspection
label | 2611502c-2341-515c-a0aa-6b11e45502fd |  | note | – – – – – – – – – – – – – – – – –
label | ffd3fe30-e166-5cf8-a4bf-0f630ec2fcba |  | note | FREQUENCY: Each lot
label | 2b3a7f2b-058c-5e13-9a21-9ba982f9487f |  | note | – – – – – – – – – – – – – – – – –
label | 48bb5cdd-285e-53b0-95d7-f864b0c32b55 |  | note | CATEGORY: IP
label | f2c9f1bd-38ca-5e8c-a59d-57149dedb2fd |  | note | – – – – – – – – – – – – – – – – –
label | 58e1083f-f1de-5594-b66c-4a5a153f3888 |  | note | RESPONSIBILITY: SE
label | e6c3818a-96a1-58be-9efd-c611bf72c2e7 |  | note | – – – – – – – – – – – – – – – – –
label | 62733df5-2d7d-5b44-9d4e-bffe563d43ab |  | note | VERIFYING DOCUMENTS: ITP signed
text | d8fbc71d-57e8-5743-b75f-91ae1931c025 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 4.7 Formwork Stripping
label | 8cd16c0f-d64d-5c27-8ae0-d0160eab4ff5 |  | note | REFERENCE: Section 703.12 AS3610
label | 079c25a5-2ae6-5a6c-9794-4eeac559f2a0 |  | note | – – – – – – – – – – – – – – – – –
label | f7f521c0-29ba-5a76-b77f-90f959d7d1d4 |  | note | ACCEPTANCE CRITERIA: Formwork shall not be stripped before the minimum time of:
label | 96cf3f77-42fe-5c67-a270-7655b15cae76 |  | note | — External faces 2 days
label | 8b9e71cb-7e14-54ab-bb38-f93f4db82125 |  | note | — Permanently hidden faces 1 day
label | 3f317d8c-103e-5dc8-950d-5385adae7a95 |  | note | – – – – – – – – – – – – – – – – –
label | 21d4e2cc-50f2-5ec7-b5d9-c95bdae1d5e8 |  | note | METHOD: Visual inspection
label | 944faf6c-248b-5a69-a353-daddbb58d855 |  | note | – – – – – – – – – – – – – – – – –
label | 0d415d2c-e161-55e6-aad2-2e77c447ed7f |  | note | FREQUENCY: Each lot
label | 183e9d0f-ce7e-5c2f-a36d-89b67df6f380 |  | note | – – – – – – – – – – – – – – – – –
label | 0745439a-7834-5775-b7c0-2bdb3733ad4a |  | note | CATEGORY: IP
label | d5296fb9-c7c4-5f08-8dd0-45d96dd871a5 |  | note | – – – – – – – – – – – – – – – – –
label | cb36f7ab-8c72-5f1f-8deb-94e3a66f943c |  | note | RESPONSIBILITY: SE
label | bb5c6b2f-aace-5248-adf3-0dee630eef34 |  | note | – – – – – – – – – – – – – – – – –
label | 5d455bf4-5b35-5107-97b0-d426561cb69b |  | note | VERIFYING DOCUMENTS: ITP signed
text | dcd2f75e-2a2e-5cb0-ba78-c18d5e249eaf |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 4.8 Tolerance
label | c3853922-80f3-5e00-9cd6-b5988d626edd |  | note | REFERENCE: Section 703.15
label | 435638de-3348-5ab4-b3e0-d5c88a3f63a0 |  | note | – – – – – – – – – – – – – – – – –
label | 2beebf03-c889-5f59-a2ff-29a5980200b6 |  | note | ACCEPTANCE CRITERIA: Match existing surfaces to within 5 mm from dimensions shown on drawings. Section dimensions to be with in 5mm and 15 mm for width , for dimension less than 25mm tolerance to be ±3mm.
label | cfb08aa2-049b-5afa-941a-c22764935765 |  | note | • Kerb and channel shall be constructed to the level of the adjoining pavement with a tolerance 0 to +10mm.
label | 466c0f4a-0b8f-5f7d-ab92-0a3778d61095 |  | note | • Except on curves or sharped areas, the deviation of the finished work from a 3m straight edge shall not exceed 5mm at any point.
label | 5cb1ab23-4d07-54a5-b346-0e1f1eb6800a |  | note | – – – – – – – – – – – – – – – – –
label | 4665ba93-f357-5753-aeac-607934073db6 |  | note | METHOD: verify
label | 156e4141-c22f-530e-b78c-a1c41913bb8f |  | note | – – – – – – – – – – – – – – – – –
label | 6d26b9a2-93bb-5759-9eb4-a5161e397e75 |  | note | FREQUENCY: Each lot
label | b84af3ed-c98e-5353-bf3d-7a2ebbdd0bb0 |  | note | – – – – – – – – – – – – – – – – –
label | 6e794285-36a2-5f20-9b85-02abb4f31faa |  | note | CATEGORY: IP
label | 9afed74c-c3c6-5085-9d38-096420c8f94a |  | note | – – – – – – – – – – – – – – – – –
label | f58a24d7-8e1c-58d4-b035-179f723eb92c |  | note | RESPONSIBILITY: SE/surveyor
label | 02ffc599-1b03-5f7a-a91b-bf46c9e3bc51 |  | note | – – – – – – – – – – – – – – – – –
label | 4333273e-35e8-5f6a-a09d-dcc6cd31c61f |  | note | VERIFYING DOCUMENTS: ITP signed
text | 7791fecf-236f-55ff-a55e-a4c8df9734e9 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 4.9 Curing
label | ebf09df0-ad3f-5597-a52c-43e1019388ed |  | note | REFERENCE: Section 703.10
label | 2492748a-7e0d-5b62-8d28-1cabc397e541 |  | note | – – – – – – – – – – – – – – – – –
label | f9e58fc1-f6b7-5aa0-8425-eeb39c60903e |  | note | ACCEPTANCE CRITERIA: The curing of exposed concrete surfaces shall commence immediately after finishing operations are progressively completed.
label | 8afbe40c-fc27-5d42-b7cc-dce8872c3e0b |  | note | • Concrete edgings shall be cured for a period of not less than three days after placing the concrete
label | ce3bc838-3ec9-58f9-a212-3c24d645ec89 |  | note | – – – – – – – – – – – – – – – – –
label | 13152c2a-95dc-5719-ad53-d5c775880512 |  | note | METHOD: Visual inspection
label | e0fb99c3-8f0a-5412-90c4-67b2173c5bb4 |  | note | – – – – – – – – – – – – – – – – –
label | f3393bbd-b7df-566f-9856-60308bb611c6 |  | note | FREQUENCY: Each lot
label | 91c7a221-c076-527d-aa37-79f07284bc72 |  | note | – – – – – – – – – – – – – – – – –
label | cfed0bd8-d7e7-5b03-92f0-7eff30d5228e |  | note | CATEGORY: IP
label | a3a08ea3-dab5-5d11-a225-aaacb43aeb3c |  | note | – – – – – – – – – – – – – – – – –
label | 6c1f6035-dafd-588f-847b-15b524c96de3 |  | note | RESPONSIBILITY: SE
label | 22667bc1-31d9-569e-b1cc-64ebf92f49e5 |  | note | – – – – – – – – – – – – – – – – –
label | 76096f2b-7bf6-5d15-baee-06e1d0b98498 |  | note | VERIFYING DOCUMENTS: ITP signed
text | e8130cbf-f9a2-5e6d-b48f-5a502abcb9ef |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 4.10 Joints
label | a0bb2f58-3e6e-5873-82b9-ece37a5919ec |  | note | REFERENCE: Section 703.26
label | 733ef3cb-67c5-53a4-9163-3cd517af738a |  | note | – – – – – – – – – – – – – – – – –
label | 3cae0f6d-fd4c-51f7-858c-9b204c83c23c |  | note | ACCEPTANCE CRITERIA: Transverse joints constructed at intervals not exceeding 2.5m.
label | c4d87c0b-8d92-5891-97ee-807cc6942e16 |  | note | • Groove cut 20mm deep and > 5mm wide on exposed surfaces, following with a vertical cut made through the base of the groove (depth >50mm from surface of section).
label | b09d8351-574c-57f9-97ad-ebd336252a82 |  | note | • Bonding between the concrete paving or shared use path and the edging shall be prevented by painting the back of the edging with bitumen, or by using a strip of bituminous felt material between the edging and the concrete paving or shared use path.
label | b6b1a498-fa86-5232-90a6-264b6686b6c9 |  | note | – – – – – – – – – – – – – – – – –
label | 9e5fce19-5968-5463-b362-bb9ed55ec795 |  | note | METHOD: Verify
label | 402318eb-1302-549b-9d71-19a3f2241917 |  | note | – – – – – – – – – – – – – – – – –
label | e7ee3b1f-4df6-540f-9bf7-70bd3868d8c0 |  | note | FREQUENCY: Each joint
label | e437408c-86c4-5ae2-8384-5158916c265e |  | note | – – – – – – – – – – – – – – – – –
label | 6eb3f885-598e-5e4c-8955-87e2846583cc |  | note | CATEGORY: IP
label | c7408ffa-65c4-50f0-a968-5d899d018740 |  | note | – – – – – – – – – – – – – – – – –
label | 70192751-eef3-50b7-8c6a-98769cc33366 |  | note | RESPONSIBILITY: SE
label | cad2f531-1933-55ef-957b-dd25accb966c |  | note | – – – – – – – – – – – – – – – – –
label | 552756b1-ed02-5e65-9269-6ce88839e38e |  | note | VERIFYING DOCUMENTS: ITP signed
text | bc8abcd0-a917-5ff6-aeac-b5fbdf9e0e1a |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 4.12 Protection of Concrete
label | 959b6dbc-f3ac-5e35-b527-d1c30c3c4747 |  | note | REFERENCE: Section 703.27
label | c9b79e65-4a4c-5850-b30e-84a22c2f51ef |  | note | – – – – – – – – – – – – – – – – –
label | 468cb98b-54ec-5912-9d10-26c0853e8de0 |  | note | ACCEPTANCE CRITERIA: All concrete shall be protected from damage from early loading.
label | bdca8787-9673-5e89-8a50-1d3cf111d014 |  | note | – – – – – – – – – – – – – – – – –
label | 5fdeaf08-9073-5f52-95ab-cc8655c64907 |  | note | METHOD: Visual inspection
label | c4406c1f-c0dd-5c42-ae38-cfba8dc04016 |  | note | – – – – – – – – – – – – – – – – –
label | 9333eb06-61aa-51a1-8574-cec5ae75005a |  | note | FREQUENCY: Each lot
label | 2c8121c8-2c15-5571-a3ad-26e9c6527689 |  | note | – – – – – – – – – – – – – – – – –
label | 813d5c6a-c556-5dd7-ad1b-326453b38415 |  | note | CATEGORY: IP
label | 10f83bf2-0a18-52a8-9732-08d4bf8f5cbe |  | note | – – – – – – – – – – – – – – – – –
label | 4639477c-bab4-5c56-8abd-3cdf300aadd0 |  | note | RESPONSIBILITY: SE
label | 892f4fde-4c58-572c-8b17-5ae44c42e64c |  | note | – – – – – – – – – – – – – – – – –
label | ba13e856-cf09-52ce-8787-9ab380eb47fd |  | note | VERIFYING DOCUMENTS: ITP signed
text | e5559e0c-3b1d-5a35-bdbc-35a34941301c |  | textbox | Date Completed:
checkpoint-group |  |  | section | Post-construction / Post-installation Activities
checkpoint-status |  |  | checkpoint | 4.11 Backfilling
label | 96243620-d8af-5026-a3e8-22c684be9021 |  | note | REFERENCE: Vic Road spec 703.29
label | 87daaec3-edc4-5729-9749-0eb9764c1536 |  | note | – – – – – – – – – – – – – – – – –
label | 34f01fde-79a6-534c-9559-5e7721172357 |  | note | ACCEPTANCE CRITERIA: No earlier than 3 days after casting, top soil material free from perishable matter, lumps or balls of clay, shall be placed and firmly compacted behind the edging in layers not > 150m thick and to a width not < 300mm behind the edging to the top of the edging.
label | a30e9da3-66c6-5efa-82e6-04f1f436e86f |  | note | – – – – – – – – – – – – – – – – –
label | 3d7d27cc-9ca0-52cb-a5b5-2b38f8375dae |  | note | METHOD: Verify
label | 825441a6-079b-57b9-8f77-bfdc38243bed |  | note | – – – – – – – – – – – – – – – – –
label | 1e040e0b-44e5-58a7-b526-7223c1235c20 |  | note | FREQUENCY: Each lot
label | e2a56c45-b0ed-5131-8be4-ad1e817cd65a |  | note | – – – – – – – – – – – – – – – – –
label | 0be29f85-517c-5697-8f89-d331516ad9d4 |  | note | CATEGORY: IP
label | 20522701-70c6-58dc-8023-62df75a7b42f |  | note | – – – – – – – – – – – – – – – – –
label | b41aff00-9f7b-598e-8c53-cc55fb738205 |  | note | RESPONSIBILITY: SE
label | aa3cce91-cd4b-5f43-9baa-c8c262ce4727 |  | note | – – – – – – – – – – – – – – – – –
label | 568072ef-cab2-5f0f-91a5-3b4c710c92ae |  | note | VERIFYING DOCUMENTS: ITP signed
text | d2738909-f493-500c-a210-74278be6cffb |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 4.13 Cracking of Concrete
label | ce3b039c-fe3d-5b3f-85f7-b57327933b5b |  | note | REFERENCE: Section 703.30
label | d8fb20ce-e6af-5768-8b5d-bfa7e8d41021 |  | note | – – – – – – – – – – – – – – – – –
label | 9df8d181-a87a-5a65-9249-ebf76de0209e |  | note | ACCEPTANCE CRITERIA: The concrete shall have no surface cracks at any stage after construction of width greater than 0.2 mm.
label | 0291f27c-6ea3-5ee2-a774-89232d96b77a |  | note | • Cracked sections of concrete shall be either removed and replaced, or repaired in accordance with Section 687
label | f0d337ed-50b3-5a80-883f-0345054f5252 |  | note | – – – – – – – – – – – – – – – – –
label | 5081422d-1071-5bd6-a9a0-fcff59140841 |  | note | METHOD: Visual inspection
label | 99719de9-a20b-5ed0-88c4-21c82daa072d |  | note | – – – – – – – – – – – – – – – – –
label | e328e7db-4e24-5365-be0d-dd2c8d17f3e3 |  | note | FREQUENCY: Each lot
label | 92ac3266-6315-5b82-ac74-55e0d8041f9a |  | note | – – – – – – – – – – – – – – – – –
label | 38d32c31-22d9-5f71-bf6c-5625fef12e71 |  | note | CATEGORY: IP
label | 3d2abd5d-dbfc-50e0-8325-1ed0614c3ce9 |  | note | – – – – – – – – – – – – – – – – –
label | 1dd766f1-84be-58d8-b010-628f6a212902 |  | note | RESPONSIBILITY: SE
label | 9ef08ed0-ad3d-572f-8726-f8cf71523b99 |  | note | – – – – – – – – – – – – – – – – –
label | fb690325-b569-5f74-9e9f-0006cdf26706 |  | note | VERIFYING DOCUMENTS: ITP signed
text | d3debc66-acac-5800-a133-342282f4112f |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.1 Survey Conformance
label | 48f386d9-e891-56b0-b48a-4130ebef8ea8 |  | note | REFERENCE: Section 703.15
label | d0cde9ff-d7eb-577a-8c81-2389fe200a56 |  | note | – – – – – – – – – – – – – – – – –
label | 212fa810-0edb-56b0-9be4-d673b80d497f |  | note | ACCEPTANCE CRITERIA: Survey to as built the works and to confirm the works are within the specified tolerances.
label | 908eff10-dc74-5615-bc30-e9e067eaa990 |  | note | • The departure of the finished work from line or level shall not exceed 10 mm at any point, and the rate of change of deviation from line or level shall not exceed 10 mm in 10 m.
label | a66b95da-ba89-5b84-bcf9-03285b16f05b |  | note | • Attach: Survey Report
label | 82a7a7df-3920-5950-b4d4-691a6e87a490 |  | note | – – – – – – – – – – – – – – – – –
label | b76f4d81-6966-5877-a4ea-4ce052ba65b5 |  | note | METHOD: Document Review
label | 97cf5121-552e-50aa-9217-6ed19b1e8d82 |  | note | – – – – – – – – – – – – – – – – –
label | 7529e5f3-71c8-5887-a7a1-b39569f9fefd |  | note | FREQUENCY: Completion of each lot
label | 8828a3cd-5602-550a-92fd-d30f144630a4 |  | note | – – – – – – – – – – – – – – – – –
label | b5df1611-b2a5-5d8c-a802-db7e2fb4291c |  | note | CATEGORY: WP
label | 2e8947d8-87e1-51be-908c-0efc3f9dc70d |  | note | – – – – – – – – – – – – – – – – –
label | 413e8387-5863-5a84-a547-8eb44eb11754 |  | note | RESPONSIBILITY: PE/Surveyor
label | 55e01e22-2108-5570-aaf6-e70f1496463d |  | note | – – – – – – – – – – – – – – – – –
label | 21217774-bc07-5336-a4c7-76a8dddd62cb |  | note | VERIFYING DOCUMENTS: As-built survey records
text | 8738316f-9035-5a07-aa07-353b4ac60f8b |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.2 Non-conformance Report (NCR) Closure
label | e63f7585-6d92-5e3b-8e04-0743155b9476 |  | note | REFERENCE: MRPA Quality Management Plan
label | 32fd29ee-3e7d-5842-8022-711df6208df5 |  | note | – – – – – – – – – – – – – – – – –
label | b8fd2f27-dc9e-57da-ab25-d90874e511f6 |  | note | ACCEPTANCE CRITERIA: Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed.
label | 2dfad744-b8f5-5f37-a717-1bc72c3239f9 |  | note | – – – – – – – – – – – – – – – – –
label | 2f2539de-9689-5dc2-990a-dffd492ddb64 |  | note | METHOD: Document Review
label | 8640e715-861a-545f-95ff-4df95d71dae8 |  | note | – – – – – – – – – – – – – – – – –
label | 9af60c05-0e22-5b15-9ebc-d8cc63ad5a9d |  | note | FREQUENCY: Once, prior to closure of this lot / element / Work area
label | 8e47ec21-3b6b-50e1-8e3b-199a1965be49 |  | note | – – – – – – – – – – – – – – – – –
label | f6aee78f-c149-521d-b195-e1a5010f7292 |  | note | CATEGORY: HP*
label | 34cf2938-d5e6-535f-afc1-0477abb95559 |  | note | – – – – – – – – – – – – – – – – –
label | 752bddc7-82f6-5f35-9ce7-10e7ae754737 |  | note | RESPONSIBILITY: PE/SPE
label | abbf31a0-f7f9-5da1-91bf-ddbb7deb2b8f |  | note | – – – – – – – – – – – – – – – – –
label | 3627b31b-b6cc-5936-bfd0-ff5e60a2f675 |  | note | VERIFYING DOCUMENTS: This ITP
text | ddce8c90-b6a9-58fd-acc6-7797f8635757 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | Final Inspection
label | 0927ae82-0d62-5e42-887e-da772c788e52 |  | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
text | 46f07742-a894-558c-9d53-37f89eb49b2a |  | textbox | Name:
text | 03fd852b-f6d1-5d0b-a5ba-1082c30f747e |  | textbox | Position:
text | 2302becd-6551-58f6-8a4d-cb3b25790f67 |  | textbox | Date Completed:
holdpoint |  |  | signoff | Sign ITP
checklist-sectioned |  |  | checklist | ITP-011-CIV-Horizontal Directional Drilling-SEW | itp |  |  |  | Yes | ITP-011-CIV-Horizontal Directional Drilling-SEW Rev 0 | 332c00dd-19de-4c57-9867-94146d38bbaf
checkpoint-group |  |  | section | Referenced Documentation
checkpoint-status |  |  | checkpoint | Referenced Documentation
label | 594202cd-753b-5596-9863-0bb6960a7a4a |  | note | Document Title: ITP-011-CIV-Horizontal Directional Drilling-SEW
label | 2537f71b-7e3e-5e8d-a6e0-93f79e7123e1 |  | note | ITP Description: Camms Road Horizontal Directional Drilling-SEW
label | 358409e2-c10a-5728-8883-367fdc6c2812 |  | note | Document Number (in Teambinder): MRP-0000-MRPA-ALT-ITP-00XX
label | cbc62f4b-5f42-5e2d-9d34-5b9698fad27f |  | note | Discipline (e.g. CIV/STR/RAIL): CIV
label | 3a41fccd-d231-5c59-9b6c-ec0c0db376f4 |  | note | Revision Number: 0
label | 1710aec5-d79a-5e7f-9061-daa68fcf2e60 |  | note | Revision Date: 19/10/2022
label | 9a819ced-bfee-5246-bcf0-69b23a06da50 |  | note | ITP created by: Michelle Lim
label | 907cfa7d-9421-5a51-ac4b-60be5b3eefef |  | note | ITP approved for use by: Victor Mira
label | cec8e546-510d-5b0a-b8e6-e54fdb5f9916 |  | note | 1.1 - Non Dependent
label | 066a2041-b978-5836-8f65-fee1884afee9 |  | note | Reference Documents:
label | 8b1b0b6d-bc9f-597a-8506-a0052467461c |  | note | • IFC Drawings:
label | 4d2e2828-35ae-51c3-989f-9c51209fdfad |  | note | • MRP-052-C-SME-DRG-64-MPK-CUT-1041
checkpoint-group |  |  | section | Preliminary Works-Materials
checkpoint-status |  |  | checkpoint | 2.1 Encasing Pipe
label | f27dc97a-465d-5b65-a8da-19527d9695d9 |  | note | REFERENCE:
label | b486b0c9-74ff-5f55-b5bc-9bd16b25e384 |  | note | IFC Drawings:
label | b19a9169-897d-582b-9778-3042552d041b |  | note | MRP-052-C-SME-DRG-64-MPK-CUT-1041
label | 27c4b792-9f0f-5d71-bf1a-07683f75c575 |  | note | – – – – – – – – – – – – – – – – –
label | b76027bd-55e5-5357-8acd-47c83f7db264 |  | note | ACCEPTANCE CRITERIA:
label | d6d94163-4bae-523b-9f00-ec49b7141974 |  | note | • All pipes must meet project specification
label | 56654f91-6d06-529e-ae8e-aefbc6e964cf |  | note | • DN 450 PE100 WSA PS-207 PN12.5
text | c57dc0d5-1125-5a3a-a5a3-705d2dedd498 |  | textbox | Reference: Material approval in Teambinder:
label | c950936d-3493-5bab-bbde-8d09a6b63c95 |  | note | – – – – – – – – – – – – – – – – –
label | bfe08a55-643a-5ed7-b201-bd7399e5be76 |  | note | METHOD: Document Review
label | 25c39180-e0e5-5ed3-90f3-1737363a6611 |  | note | – – – – – – – – – – – – – – – – –
label | c241a703-6b7d-522e-961a-cc8074b13bb4 |  | note | FREQUENCY: Prior to commencement
label | 66ada1ad-bb0a-5a02-9b6e-9c9f0dc98dbf |  | note | – – – – – – – – – – – – – – – – –
label | 050e52a4-bf5d-5b88-b4fa-513111892406 |  | note | CATEGORY: HP
label | 4492e1c4-8444-51b5-bf5d-01ef722f318d |  | note | – – – – – – – – – – – – – – – – –
label | 27119c0f-84d9-5ec9-a6c2-12197698058b |  | note | RESPONSIBILITY: PE/SPE
label | 459a4dd1-1897-53e7-8c60-528c3bf8dad2 |  | note | – – – – – – – – – – – – – – – – –
label | 04cd85f5-2208-5a1b-a35a-c785aca3ae48 |  | note | VERIFYING DOCUMENTS: Material compliance certificate
text | 54a5aea3-436c-5136-a598-2f35c70dbf5a |  | textbox | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.2 Carrier Pipe
label | 1befb960-40e0-5a6f-961e-950186c996a6 |  | note | REFERENCE:
label | 151e937b-135f-5287-955a-b84df52fbaee |  | note | • IFC Drawings:
label | 32560fc8-68e9-5585-9b77-d30362285386 |  | note | • MRP-052-C-SME-DRG-64-MPK-CUT-1041
label | 5f819ae6-a6c1-50ad-aee7-5ffe8e42381f |  | note | – – – – – – – – – – – – – – – – –
label | f3fdbe16-a13b-58c7-b017-9d897adc293e |  | note | ACCEPTANCE CRITERIA:
label | b69e4949-6e95-53a4-a9d1-6bc6f5aee3a6 |  | note | • All pipes must meet project specification
label | ff93fea9-fe21-539e-8d4b-f9c8ac214d88 |  | note | • DN 280 PE100 WSA PS-207 PN16
text | 0323cfe3-26a0-5fe9-b628-d9d905bd9034 |  | textbox | Reference: Material approval in Teambinder:
label | 48266a9d-6afe-54c3-b966-7375908dd36c |  | note | – – – – – – – – – – – – – – – – –
label | 2e43a314-dbfd-5648-99a5-a492a1b328bb |  | note | METHOD: Document Review
label | a06c9042-ebc1-553c-93bc-7bb08afaed5b |  | note | – – – – – – – – – – – – – – – – –
label | 70cfe2b6-2cde-5805-adcb-590602de46bc |  | note | FREQUENCY: Prior to commencement
label | 0529d6e3-42d0-5d92-9ae6-d2c61577df36 |  | note | – – – – – – – – – – – – – – – – –
label | 921353ea-dfb3-553c-832d-5fb0ec2c6491 |  | note | CATEGORY: HP
label | 099b39ea-6e82-50ba-9d2c-01c49a76cac8 |  | note | – – – – – – – – – – – – – – – – –
label | d375b4b5-8ace-54ed-988a-08fec1ec6aa3 |  | note | RESPONSIBILITY: PE/SPE
label | a4983a64-1d80-5a81-9ea3-34ceb4263daa |  | note | – – – – – – – – – – – – – – – – –
label | a455e8c3-85b5-563d-bf2e-6435789c9b08 |  | note | VERIFYING DOCUMENTS: Material compliance certificate
text | 3202d9ea-7455-59fb-b1d8-e938d8004196 |  | textbox | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.3 Grout
label | b33d0c7f-eb01-571b-a0d1-e6b1a37f54e4 |  | note | REFERENCE:
label | 5f6db095-9b25-5e0a-8fb5-3b1b31a0eb5e |  | note | IFC Drawings:
label | 61b41ca6-6a3f-53fb-a2bd-bccb7f4dbc39 |  | note | MRP-052-C-SME-DRG-64-MPK-CUT-1041
label | f283cd0a-2839-5ae7-b556-489704b68ebd |  | note | – – – – – – – – – – – – – – – – –
label | 8243181f-4881-54f3-8490-0d89348de683 |  | note | ACCEPTANCE CRITERIA:
label | ba33b3d8-e3bd-561b-b286-592c1dbdbe8b |  | note | • Review and approval of grout specification
text | f8855979-fd96-5d59-9465-347a0d126231 |  | textbox | Reference: Material approval in Teambinder:
label | a15b09d7-f3b6-5560-a9d4-a30991d85e27 |  | note | – – – – – – – – – – – – – – – – –
label | 679923e0-6864-5b1b-9656-3ebe4d5f1a94 |  | note | METHOD: Document review
label | 5d0d09e3-434a-575e-8647-25ce08e29ad7 |  | note | – – – – – – – – – – – – – – – – –
label | bb7c7d6d-7a37-58da-af0f-8f55c65844ad |  | note | FREQUENCY: Prior to commencement
label | 0e2df113-2403-5876-91df-1255b3184622 |  | note | – – – – – – – – – – – – – – – – –
label | 493d73e8-f734-52f5-8b4a-f412e63844ca |  | note | CATEGORY: HP
label | 569850e2-5b71-5509-a27e-afe14c4802ca |  | note | – – – – – – – – – – – – – – – – –
label | c6acce66-962a-5155-98ec-aee29c1cad0f |  | note | RESPONSIBILITY: PE/SPE
label | 83553e16-22b1-5108-a805-da18d00e7084 |  | note | – – – – – – – – – – – – – – – – –
label | 65242605-46e1-57e5-a395-fadbfe79329d |  | note | VERIFYING DOCUMENTS: Material compliance certificate
text | 188bf3ba-6aaa-5f75-acbd-253e9680efde |  | textbox | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | Preliminary Works-Procedures and Documents
checkpoint-status |  |  | checkpoint | 3.1 PE Welders Qualifications
label | 4dca9fd7-06a2-5b53-8fdb-f53c08b41f6f |  | note | ACCEPTANCE CRITERIA:
label | 20508239-a87b-540c-afb4-5cc94e642a43 |  | note | • PE welders are to be pre-Qualified
text | f476c1d9-de59-54c3-9675-8af1987005e6 |  | textbox | Reference:Teambinder Hold point release number:
label | 7a5153b8-f8bc-5ddb-abb3-17097886d42b |  | note | – – – – – – – – – – – – – – – – –
label | 099925fb-2e79-537a-ac63-1815dd43b745 |  | note | METHOD: Document review
label | 340bcbb0-1389-5a51-bf48-43dba8a3c2f9 |  | note | – – – – – – – – – – – – – – – – –
label | 7cd5c0dc-8acb-5452-a007-b93b81cf6d31 |  | note | FREQUENCY: Prior to commencement
label | b13657b8-46e6-5496-8802-3fbeb0669420 |  | note | – – – – – – – – – – – – – – – – –
label | 2fad386f-d2ae-59b9-9427-747d0d16d3d3 |  | note | CATEGORY: HP
label | 9921bff7-ee10-5131-97cb-b23cc064f546 |  | note | – – – – – – – – – – – – – – – – –
label | e69dd4fb-4ffd-5993-9c7c-4573d38b16b8 |  | note | RESPONSIBILITY: SE/PE
label | 217af1d9-6cdd-5c23-8476-22126784da54 |  | note | – – – – – – – – – – – – – – – – –
label | 3036a08e-ad90-59e4-854f-9a952dde079e |  | note | VERIFYING DOCUMENTS: Teambinder approval number
label | 762d2bc4-3eec-5229-a318-21678d7198fc |  | note | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.2 Check that current revision drawings are being used
label | a2f8ea2b-f915-51bc-8c54-95b47552e3a4 |  | note | REFERENCE:
label | 15272c7b-21a2-5841-8b56-152a2316890e |  | note | • IFC Drawings:
label | 2e68038a-f333-5898-b1f6-95aaa2272272 |  | note | • MRP-052-C-SME-DRG-64-MPK-CUT-1041
label | b696da9a-fc28-506e-b419-124b462943d4 |  | note | – – – – – – – – – – – – – – – – –
label | c960b9c4-3a63-5067-bb6c-efd67aea9544 |  | note | ACCEPTANCE CRITERIA:
label | 7b2e62a2-832a-5d50-b751-e3d3f510b822 |  | note | • Drawing revison must be confirmed with the design manager
label | 2ae58921-ccc6-56d8-88c5-d2cbb64f68dd |  | note | – – – – – – – – – – – – – – – – –
label | f5d65023-22d8-56c1-8600-d4f4eb78e2d1 |  | note | METHOD: Document review
label | ad9a53e2-a247-5941-ba94-87b96ba54eb3 |  | note | – – – – – – – – – – – – – – – – –
label | 07e5c8b8-3a61-5406-ab9e-6c213dedc8e2 |  | note | FREQUENCY: Prior to commencement
label | 813bf685-3cde-5084-99f7-4b914cdc101d |  | note | – – – – – – – – – – – – – – – – –
label | bc3dab5a-82e9-55af-ab68-d0734f00f6db |  | note | CATEGORY: HP*
label | 59ce0d43-3347-5490-b36a-8e8838ea3cd1 |  | note | – – – – – – – – – – – – – – – – –
label | c5118c6d-bb92-5304-bbd8-c4d7f0bf2190 |  | note | RESPONSIBILITY: SE/PE/SPE
label | 5ca3e899-c508-5dfa-aade-4983e80c56fa |  | note | – – – – – – – – – – – – – – – – –
label | b8ee6e6e-f40c-57ee-8684-aec9f07f680c |  | note | VERIFYING DOCUMENTS: Design drawings.
label | 7b0e5ab9-120f-5125-852d-ed7449d9109f |  | note | Date Completed:
checkpoint-group |  |  | section | Pre-construction / Pre-installation Activities
checkpoint-status |  |  | checkpoint | 4.1 Survey Set-out
label | 81925f84-9ba5-5f88-a0c6-b74cb1a4ccfe |  | note | REFERENCE:
label | 0bf5c138-a201-509b-89be-4c58a7420892 |  | note | • AS 4799-2000
label | e092658d-b826-5e1d-81bd-a09fe6789493 |  | note | • IFC Drawings:MRP-052-C-SME-DRG-64-MPK-CUT-1041
label | 1774d723-a28d-5b99-8e3f-532d534d02c8 |  | note | • DBYD Asset owners responses and requirements.
label | f29c9fbc-7713-58d6-81bb-c9b8de68184f |  | note | • MTM: L1-INF-PRO-001
label | c654265b-d5f2-5575-9074-1e13f26a7b6c |  | note | – – – – – – – – – – – – – – – – –
label | d31496d5-e439-51b7-aaef-327d19dd519a |  | note | ACCEPTANCE CRITERIA:
label | 3ee7f4f1-cba9-5634-8b7c-5ac47f82a871 |  | note | • Set out line and level of drilling works.
label | e0f58ae4-711f-53d2-a5bd-f274cdb34f9d |  | note | • Survey to mark out existing services.
label | caf47d9d-c3ce-54e8-b607-443aa84b8a15 |  | note | • Must maintain a min. of 600mm clearance to any existing service and a min. 3m clearance to any Railway Structure UON.
label | a92d5347-fa6e-506d-b3f1-705c78890d4e |  | note | – – – – – – – – – – – – – – – – –
label | dcb28227-6ea2-510e-aa11-f0185c0772d5 |  | note | METHOD:
label | 9752359e-ddc6-5ed8-9741-d29d57e54a9c |  | note | • Measure
label | 9212176d-caa3-5cde-87a1-13832d3099a7 |  | note | • Visual
label | 5bcea817-c8b2-5c79-9b13-a2d492a7c9db |  | note | – – – – – – – – – – – – – – – – –
label | baa7f63c-fd53-5f59-9040-a08e6e2cc135 |  | note | FREQUENCY: Each element
label | d5a8f3d6-0eb9-5073-ad2a-33f6f11d3afc |  | note | – – – – – – – – – – – – – – – – –
label | 8964c69e-45fa-51a2-84ec-6c43533aa9fb |  | note | CATEGORY: IP
label | 5df1efbf-f06d-5092-bd98-9c4fcb0fea20 |  | note | – – – – – – – – – – – – – – – – –
label | 6d3fae94-420f-5c8c-ab85-ce12ce06c24a |  | note | RESPONSIBILITY:
label | 559f05e3-d9e7-5d52-ad30-1aa96a062b83 |  | note | • Surveyor
label | 4395640e-1a6a-55c1-8ec8-6dc4aed86598 |  | note | • SE/PE/SPE
label | 2da80737-a1cf-572d-8dd9-f4b8a69468f0 |  | note | – – – – – – – – – – – – – – – – –
label | c97655ee-d80a-57c7-8323-1c2f244a2333 |  | note | VERIFYING DOCUMENTS: This ITP
label | bb0842ff-47e2-5849-b34c-b8c22fd32749 |  | note | Date Completed:
checkpoint-status |  |  | checkpoint | 4.2 Pipe welding
label | c5164130-de0b-573d-a552-3531e28ff7a7 |  | note | REFERENCE:
label | d65f2cfb-6c62-551e-8a42-066984948d96 |  | note | • IFC Drawings:
label | 3b5f76ab-e32d-5151-bd93-83c1ff53c2e5 |  | note | • MRP-052-C-SME-DRG-64-MPK-CUT-1041
label | a183cc98-ed38-5778-93ba-37fa453e79df |  | note | – – – – – – – – – – – – – – – – –
label | 310f2324-8e13-57fa-9429-3aa08e8c06b2 |  | note | ACCEPTANCE CRITERIA:
label | 21d85847-ef00-54c1-bdf2-59e6f64fe114 |  | note | • Joints are to be butt welded.
label | 8b39d3b3-f145-553a-b0db-662fb44a0c03 |  | note | • Butt Welding records to be supplied.
label | 012b21c2-61a8-54c9-9b6d-26bff825a234 |  | note | • ATTACH: Welding Record
label | c023b849-3929-58c4-b307-500653759347 |  | note | – – – – – – – – – – – – – – – – –
label | 17d940c2-19c1-53d4-a496-171ca31958b5 |  | note | METHOD: Document review
label | 192f0664-f681-55ae-bbf8-c1bdd9f3145a |  | note | – – – – – – – – – – – – – – – – –
label | caf3a73a-2018-53b0-bda4-7d39632c5acd |  | note | FREQUENCY: All Joints
label | ccc8031d-70fc-5226-8eb4-5783fe90c8cf |  | note | – – – – – – – – – – – – – – – – –
label | 275d49de-5e01-55a0-872f-86eb4fd41bee |  | note | CATEGORY: IP
label | 4605fea5-392e-53f0-85ac-3b4f142f7202 |  | note | – – – – – – – – – – – – – – – – –
label | 58d53df4-1132-51ea-a706-ccd917ceba6c |  | note | RESPONSIBILITY: SE/Site Supervisor/Survey
label | 5fe30491-e7e5-52da-a9fd-8dddad89f2fa |  | note | – – – – – – – – – – – – – – – – –
label | 2b6bf1a6-e473-5c80-8997-e8ebf47594a7 |  | note | VERIFYING DOCUMENTS:
label | e02a3cee-0d06-58b6-b138-f395756b5e63 |  | note | • Sign ITP
label | 2b57f5b0-472f-5588-b51b-59568a30a01a |  | note | • Butt Welding Records
label | c0dc88e9-8abb-5487-b9d3-8ab0e0a6978e |  | note | Date Completed:
checkpoint-group |  |  | section | Construction / Installation Activities
checkpoint-status |  |  | checkpoint | 5.1 Drill rig setout
label | ca198b3e-3330-5b0b-b320-90f3255af96a |  | note | REFERENCE: Drill Shot Plan
label | 60af4ff3-5c69-5695-9fc9-bc1dc490b178 |  | note | – – – – – – – – – – – – – – – – –
label | 54d1e2ce-7b8a-5589-a84f-0e521bc37d44 |  | note | ACCEPTANCE CRITERIA: Location as per current Drill shot plans
label | e6a944cf-9ca9-53ba-80c3-65278f770130 |  | note | – – – – – – – – – – – – – – – – –
label | f8bef584-428e-50bb-91fd-dfb633ada44a |  | note | METHOD: Visual
label | dbdc74eb-3579-5ab1-a2d8-ec9450dcf256 |  | note | – – – – – – – – – – – – – – – – –
label | 79d91c7f-8379-549a-a6c6-1cb9f1b0ae26 |  | note | FREQUENCY: Prior to commencement
label | 4fc8711d-287c-52c3-9f99-52f05e41becc |  | note | – – – – – – – – – – – – – – – – –
label | df60d1cb-3b0d-5852-99f7-f76b123f520e |  | note | CATEGORY: SP
label | 78a1ae66-9d5f-5948-aef1-40fa65841bc3 |  | note | – – – – – – – – – – – – – – – – –
label | d1bff473-ff49-5fc9-9d61-d05ffb7a907f |  | note | RESPONSIBILITY: SE
label | e65f3255-2dcf-5b87-b34b-95770fd2dbb2 |  | note | – – – – – – – – – – – – – – – – –
label | b608fe5b-8da0-56e9-ae69-153ed02e09c0 |  | note | VERIFYING DOCUMENTS: This ITP
label | dcd32bde-6d11-5b1a-b901-a8d003fa744a |  | note | Date Completed:
checkpoint-status |  |  | checkpoint | 5.2 Installation of Pipeline (Trenchless method)
label | 950309da-42a1-51eb-b977-9cd83a372479 |  | note | REFERENCE:
label | 6e6985fe-e114-57b6-a5a2-aed7c3719971 |  | note | • IFC Drawings:
label | 4961e4ae-53ec-5b96-9a3e-72bf8c9eec05 |  | note | • MRP-052-C-SME-DRG-64-MPK-CUT-1041
label | 530c2be0-9ea9-553e-8af1-b07a7d584c6f |  | note | – – – – – – – – – – – – – – – – –
label | 92391f99-98cd-58f5-8ae0-19956661e8a5 |  | note | ACCEPTANCE CRITERIA:
label | 12545a48-5452-51ac-aadb-bfb771509473 |  | note | • Drill to be installed as per the survey setout.
label | 7d87cbc3-099e-536c-bf46-45759bdc8b49 |  | note | • Bore longs to be supplied.
label | 5d810578-ffc3-5d6e-b448-d998d40163c4 |  | note | • ATTACH: Bore Logs
label | f16c687f-383a-5058-850c-30542aae41a6 |  | note | – – – – – – – – – – – – – – – – –
label | 8c75a063-3dad-560c-b065-41b00bfb0ffa |  | note | METHOD: Document review
label | adec6c1b-d466-51fe-aabb-b52e60634a9c |  | note | – – – – – – – – – – – – – – – – –
label | 3e97917a-28d8-5ce5-84cb-476d6ee71c91 |  | note | FREQUENCY: During pilot bore
label | 495438da-b8e5-59d1-8ad0-56aa9f6b219e |  | note | – – – – – – – – – – – – – – – – –
label | 3cc63faa-5eca-5b6c-a820-be8d6e753db7 |  | note | CATEGORY: IP
label | ecd706a2-c73c-5959-b0d3-7efd9621e588 |  | note | – – – – – – – – – – – – – – – – –
label | 90e46edd-2f1a-51a1-bda7-2415219e449b |  | note | RESPONSIBILITY: SE
label | 787a3658-a0f8-57a1-b20b-9b8ac932e321 |  | note | – – – – – – – – – – – – – – – – –
label | 310bfe9f-9a4a-5a0f-98ba-ad38519c244c |  | note | VERIFYING DOCUMENTS: Bore logs
label | 996d0d75-1331-5096-a06b-91a765fb64a0 |  | note | Date Completed:
checkpoint-status |  |  | checkpoint | 5.3 Mixing of grout
label | 9db30508-fbdd-501c-8b31-31997af9d048 |  | note | REFERENCE: Grout Manufacturer Technical Data Sheet
label | e871a985-fc21-51b2-b3f7-ea99d87dfc18 |  | note | – – – – – – – – – – – – – – – – –
label | 4f11ec8a-9173-5c6f-9ef1-4aa2750f9d3a |  | note | ACCEPTANCE CRITERIA:
label | 67bf306f-7779-5984-8172-50a3fa7cc3f1 |  | note | • Mixing and proportioning of grouting to take place as per Technical Data Sheet provided with product.
label | 0ce1f4c9-4d9d-5d8a-8de3-51b064b625ac |  | note | • Only whole bags of product shall be used.
label | 4398a09b-e9a2-5e02-8488-f726dc78f233 |  | note | • Grouting shall not commence when temperature is below 5 degrees Celsius or above 35 degrees Celsius
label | 917677a6-eda8-5256-8830-1d9b0e8c53b7 |  | note | • Grout mixture should be mixed adequately and free from lumps
text | f20e1f01-55a4-5146-a78c-766f9fa3b8e4 |  | textbox | Grout Volume Used
label | b41212d3-ebba-5f2e-acd0-16bd3a8ef3f2 |  | note | – – – – – – – – – – – – – – – – –
label | 5e2a00de-8b51-52e3-9463-0f3da076c80f |  | note | METHOD: Document review/Measure
label | bc72fbb7-a47a-5f7e-898a-0343db585e60 |  | note | – – – – – – – – – – – – – – – – –
label | 8b8eff9c-275e-5e5c-b10c-056e025d09f6 |  | note | FREQUENCY: During grouting process
label | 6dc8c19a-1550-5dd2-9693-c5c891c895e5 |  | note | – – – – – – – – – – – – – – – – –
label | 74b3cb0a-c274-51af-acb2-5b0940d23559 |  | note | CATEGORY: IP
label | 1cb31917-2400-56a7-9997-9e66330e9b9d |  | note | – – – – – – – – – – – – – – – – –
label | bb622d29-b2a9-5c9e-820d-2518042753c3 |  | note | RESPONSIBILITY: SE
label | 787bf020-a954-5c22-85a1-f0894baf39de |  | note | – – – – – – – – – – – – – – – – –
label | d30200d0-7115-5fc2-bba7-ec59afbe9df8 |  | note | VERIFYING DOCUMENTS: Sign ITP.
label | 17579022-ba7e-5997-8674-375212647634 |  | note | Date Completed:
checkpoint-status |  |  | checkpoint | 5.4 Clean surrounding faces and remove excess grout
label | 04eb82ed-13c5-5a2e-9089-49cee7e9825d |  | note | ACCEPTANCE CRITERIA: Area free of excess grout and spillage
label | 4562dc7d-e3ad-5653-84fb-9d8fda7ed60c |  | note | – – – – – – – – – – – – – – – – –
label | 071a445b-c6b6-5f4a-99eb-fff9176a0e2a |  | note | METHOD: Visual
label | 9ded60c8-3fce-581b-b677-13e93657b89a |  | note | – – – – – – – – – – – – – – – – –
label | ecd7ab3f-b4f2-5acc-b79c-1301a43f444a |  | note | FREQUENCY: Each shaft
label | 375bb4d9-0a0b-5b3d-b3b7-2b0293f4ad78 |  | note | – – – – – – – – – – – – – – – – –
label | 5d1c7ef9-b6be-5c9c-b509-91cedcb284cd |  | note | CATEGORY: WP
label | 6d9da102-e3fb-5edd-be82-dbbb9489735b |  | note | – – – – – – – – – – – – – – – – –
label | 63230b97-da5c-5b7f-bf82-c78e1155bd56 |  | note | RESPONSIBILITY: SE
label | 4b4fbb0a-8cc1-5b44-bd3e-9cbf4a58cf69 |  | note | – – – – – – – – – – – – – – – – –
label | 7f212852-d647-5967-af5b-69616eb4d24f |  | note | VERIFYING DOCUMENTS: Sign ITP
label | 3e014d06-1ac5-5edc-9912-a5f5be29d3cb |  | note | Date Completed:
checkpoint-status |  |  | checkpoint | 5.5 Curing
label | 1107e5f5-1375-5f6f-92e8-58e32cf98391 |  | note | REFERENCE: Grout Manufacturer Technical Data Sheet
label | 3808c881-0830-54a9-b345-ac38fe09909c |  | note | – – – – – – – – – – – – – – – – –
label | d45c4e82-ca6a-5e57-9c2e-2a6183738939 |  | note | ACCEPTANCE CRITERIA: Curing in accordance with TDS
label | 5843d4bb-1eed-5ea8-970e-c428e365a78d |  | note | – – – – – – – – – – – – – – – – –
label | cc9df75e-d5b0-5d51-b72a-ff9554716f58 |  | note | METHOD: Document review
label | 209215c5-14a2-5b78-a232-f49ba4e8839e |  | note | – – – – – – – – – – – – – – – – –
label | bb7ffd13-5804-5fc5-a997-675917adf21d |  | note | FREQUENCY: All pipe
label | 245a2d41-b64f-5b61-b79d-096992745599 |  | note | – – – – – – – – – – – – – – – – –
label | 800d86d8-f6ce-519c-ac99-94ff3389c9c6 |  | note | CATEGORY: IP
label | ca7f872d-d36f-501f-a27d-31e3bd827ba5 |  | note | – – – – – – – – – – – – – – – – –
label | 7755aad7-613a-5478-8549-532ded782ae2 |  | note | RESPONSIBILITY: SE
label | 5e3baa93-cf75-5edd-b4da-e07763680a27 |  | note | – – – – – – – – – – – – – – – – –
label | c6d8845d-af86-52f7-bf37-4bc929e82920 |  | note | VERIFYING DOCUMENTS: Sign ITP
label | beadbb23-fcb9-5317-bad4-50a04f6ddd6e |  | note | Date Completed:
checkpoint-status |  |  | checkpoint | 5.6 Auditing
label | 8d17e61a-9357-59e3-9139-3a4a8a726247 |  | note | REFERENCE: IFC Drawings
label | 45b2b9f8-95a5-50e7-a2e3-ce29f401f7b6 |  | note | – – – – – – – – – – – – – – – – –
label | f4fa4e4c-2e52-5d6d-9d57-fae1f57a3332 |  | note | ACCEPTANCE CRITERIA:
label | 04c8a3c4-47d6-56b4-aedd-3633316dc4a4 |  | note | • Auditing to be completed on conduit ends prior to backfilling of entry and exit shafts.
label | 2bc29c96-73af-5ae8-8870-d0c05c41e5fd |  | note | • ATTACH: Audit report
label | 42cd9895-37c9-5503-b72d-d0ea2e234637 |  | note | – – – – – – – – – – – – – – – – –
label | 018758f4-14be-59ec-8df2-ee94405b3edf |  | note | METHOD: Record and Review
label | ef21f3fc-9457-52e4-a615-2f5de08199c1 |  | note | – – – – – – – – – – – – – – – – –
label | 0e79791b-4844-515f-9d12-6196a38a4ee6 |  | note | FREQUENCY: Prior to backfill of exit/entry shafts
label | 6c8c069f-2118-58ff-a0be-336d337a8e74 |  | note | – – – – – – – – – – – – – – – – –
label | 3a5deebe-7807-5c01-9649-11371dfe5f65 |  | note | CATEGORY: HP
label | b08e8626-8b05-583c-a42d-b1afd2ab319a |  | note | – – – – – – – – – – – – – – – – –
label | 8407faad-fe99-5281-a6c2-6b1665e1d4af |  | note | RESPONSIBILITY: Nominated Authority (SEW)
label | b86b6029-0104-5c87-bdee-506a682270cc |  | note | – – – – – – – – – – – – – – – – –
label | 9b96fb1b-b13e-56b0-9f62-c04ab2a2ab04 |  | note | VERIFYING DOCUMENTS:
label | 9841058c-4bd9-580e-b5fd-b23d3543fbbc |  | note | • Sign ITP
label | 622ac85f-99cc-5ace-bdcf-38e43929c27a |  | note | • Auditing Report
label | f82c2662-dadb-5541-9fab-46f8ae5fd1b4 |  | note | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 5.7 Reinstatement
label | 28935bf7-2072-54a5-ab66-7e476edc5924 |  | note | REFERENCE:
label | 5fbfcd2b-25fc-5f99-bfcc-1fe697c80964 |  | note | • IFC Drawings:
label | 1b6ed5ce-a905-531a-a01a-400bec0d4b31 |  | note | • MRP-052-C-SME-DRG-64-MPK-CUT-1041
label | 8eca3a04-fd0f-5729-9fc9-66224c1ad0f2 |  | note | • MRWA-W-201 Table 201-A & 201-B
label | 0c7e7815-f49f-5912-9209-0a94b69be761 |  | note | – – – – – – – – – – – – – – – – –
label | 514c1f69-f0b8-5127-8376-a2cdde16db83 |  | note | ACCEPTANCE CRITERIA:
label | fd3395ca-0356-5a00-bc66-4417970535a4 |  | note | • REINSTATEMENT OF BORE SHAFTS SHALL FOLLOW MRWA BACKFILL SPECIFICATION MRWA-W-201 Table 201-A & 201-B;
label | 87dd418b-347b-581c-91ef-417f9ea89b2a |  | note | • Entry pits, exit pits and trenches to be backfilled with Type A or crushed rock. Backfill material shall be compacted to the same density as adjacent material or as specified.
label | 98fa1ce4-82c4-5420-bda6-f756834c9943 |  | note | – – – – – – – – – – – – – – – – –
label | a88b8de7-041d-5a18-aa6e-46cd501a6ea1 |  | note | METHOD: Visual
label | e47897ea-47ce-5152-83e2-979b2adb7721 |  | note | – – – – – – – – – – – – – – – – –
label | 500a549a-417d-56bb-bae9-8a392b8703a3 |  | note | FREQUENCY: Each shaft
label | 4c5c3e00-a888-5484-b5b8-7fae6b0bc3d4 |  | note | – – – – – – – – – – – – – – – – –
label | ca78556b-8d05-504b-ba9a-871f1b1dd6d9 |  | note | CATEGORY: IP
label | aed93e4e-811d-57af-9162-463ec7d025c1 |  | note | – – – – – – – – – – – – – – – – –
label | 36fb1be4-a0d8-5f1c-b969-a40b749c1787 |  | note | RESPONSIBILITY: SE/Site Supervisor
label | b8eb4b2d-3ddc-5f5b-99a5-d54cddd03e6c |  | note | – – – – – – – – – – – – – – – – –
label | 5fc0f876-6de0-5c97-a5d1-f320325e3822 |  | note | VERIFYING DOCUMENTS: Sign ITP
label | 6ba38a78-7ad4-5c98-9af1-1232279b1de8 |  | note | Date Completed:
checkpoint-status |  |  | checkpoint | 5.8 Subcontractor ITP
label | 3d0474ca-8ede-5c05-970e-ca004062474d |  | note | REFERENCE: N/A
label | ec8532ac-08f7-52fb-970f-911028415f17 |  | note | – – – – – – – – – – – – – – – – –
label | 20fb4c92-dcd3-5736-aa0c-c7573e70a22f |  | note | ACCEPTANCE CRITERIA:
label | 6d65d288-049f-5e16-b5c0-0bb4ab8c5db7 |  | note | • Acceptance and closeout of subcontractor ITP
label | 9ab9bdac-ffc7-5044-a3ec-96682ee8e6f3 |  | note | • ATTACHED: Completed and Signed Subcontractor ITP
label | 22a5af48-4e6f-59e4-95cc-8d2bc8e8b29c |  | note | – – – – – – – – – – – – – – – – –
label | e2a050ff-67b9-55d0-8cea-fec89c02b3d7 |  | note | METHOD: Document review
label | bf789d76-144b-5b36-829b-884be41d08bc |  | note | – – – – – – – – – – – – – – – – –
label | c2c33ad5-2f00-52c7-8aa1-7df2459d020a |  | note | FREQUENCY: Each element
label | 5cee562f-4791-54e5-847c-97f2f9d4e71a |  | note | – – – – – – – – – – – – – – – – –
label | d6bb1a7a-eaf4-5054-9a6f-676656a41923 |  | note | CATEGORY: HP*
label | ea807eb1-ba9c-5582-a443-d770b5561c4d |  | note | – – – – – – – – – – – – – – – – –
label | 37c12ab1-16df-5bb9-a301-c6c251804a6e |  | note | RESPONSIBILITY: SE/SPE
label | 63928657-0fa0-5095-b054-018573ff975e |  | note | – – – – – – – – – – – – – – – – –
label | 9419710d-e3d7-5546-bc4c-1ad473700bdd |  | note | VERIFYING DOCUMENTS:
label | d9b02aa1-eee4-5be3-809b-c53d8fb8f900 |  | note | • Subcontractor Signed ITP
label | 34cbcacf-28db-5604-a03b-4e3dd0d39893 |  | note | • Completed
label | 5f4797c7-3fe1-5756-8303-6a2ee26b7a5a |  | note | Date Completed:
checkpoint-group |  |  | section | Post-construction / Post-installation Activities
checkpoint-status |  |  | checkpoint | 6.1 Non-conformance Report (NCR) Closure
label | ed77b383-9afd-5445-a88a-59b2f6dde804 |  | note | REFERENCE: MRPA Quality Management Plan
label | 9b372559-fa82-537a-97dd-d64605787674 |  | note | – – – – – – – – – – – – – – – – –
label | 843dc03b-4666-5bca-a546-7909e4b53078 |  | note | ACCEPTANCE CRITERIA: Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed.
label | da01ccb1-acbc-5435-a925-3b014c6602a0 |  | note | – – – – – – – – – – – – – – – – –
label | 2729d196-9e8e-5ce4-9275-5cc6dec3d6df |  | note | METHOD: Document Review
label | 5be44998-113e-59f2-a297-f4163a911d8f |  | note | – – – – – – – – – – – – – – – – –
label | 7eba0c3b-9830-5232-9dde-d86a08ffc15a |  | note | FREQUENCY: Once, prior to closure of this lot / element / Work area
label | 2fe01a24-ce75-5f79-891f-7b8ffbbd83de |  | note | – – – – – – – – – – – – – – – – –
label | b17d3002-c15d-5443-996d-aacbcbbe4142 |  | note | CATEGORY: HP*
label | 47d15316-bd32-5b79-a481-ebbfe4c2acb7 |  | note | – – – – – – – – – – – – – – – – –
label | f3380249-61f3-570a-ab24-9e2ce44b4a2d |  | note | RESPONSIBILITY: SE/PE/SPE
label | 9ebb0d7e-f9e6-5a8b-b9e5-b9f9740e18f1 |  | note | – – – – – – – – – – – – – – – – –
label | a703bc0c-bdde-50fb-9fdd-30c7f49a4455 |  | note | VERIFYING DOCUMENTS: This ITP
label | 9841c41d-4989-5458-9a94-9fa7eceb349c |  | note | Date Completed:
checkpoint-status |  |  | checkpoint | 6.2 As-built Survey
label | 171690da-27ab-5517-9c0c-0c02446418f0 |  | note | REFERENCE:
label | d0a60653-ae5a-5b2c-9c04-5a5541c7195a |  | note | • IFC Drawings:
label | a465dd06-ce20-511d-bfd6-6ad378a7df18 |  | note | • MRP-052-C-SME-DRG-64-MPK-CUT-1041
label | 767dc9f4-696f-5e47-bf77-54eb5707e92c |  | note | – – – – – – – – – – – – – – – – –
label | 860d64d9-d4fa-5ad1-81ec-65eae70bbd37 |  | note | ACCEPTANCE CRITERIA:
label | adb3440a-82a7-5332-a9a0-9b2dd76ac5d7 |  | note | • Survey as built report to be compiled.
label | 32c1f56f-2213-5cc9-935c-d0d6e4dc8f0f |  | note | • Borelog obtained from subcontractor
label | cc0787b3-7748-5ed9-8a55-fec486ecf974 |  | note | • Autocad and PDF reports are to be supplied.
label | dd8ef055-31e8-5215-a9a4-466ae6398084 |  | note | • ATTACH: Survey As-Built Report
label | 5b12c7f5-f902-586a-9e12-11e060115c8b |  | note | – – – – – – – – – – – – – – – – –
label | 12b78f14-494c-53db-bf18-35e142b7deac |  | note | METHOD: Document Review
label | 90ccf9ed-b0d3-5b66-9f8c-47b7a02fa60b |  | note | – – – – – – – – – – – – – – – – –
label | 31e60aee-da0b-52d6-b109-6fab7ede0034 |  | note | FREQUENCY: Each element
label | 81963a14-10e8-55c5-aeae-b110b6452aaf |  | note | – – – – – – – – – – – – – – – – –
label | 5ddc6d32-4b47-57cd-92ff-8a63ad420c00 |  | note | CATEGORY: IP
label | b86633a4-a74b-51e4-a32f-735f93a43ca2 |  | note | – – – – – – – – – – – – – – – – –
label | 818307c3-8d34-5068-bccd-f27af1ff7434 |  | note | RESPONSIBILITY:
label | 5ea08cbb-4dc1-5bc7-8794-3a63d2b446ee |  | note | • Surveyor
label | 45f02f97-a58a-5b67-9584-3adda4258ec7 |  | note | • SE/PE/SPE
label | c92cffe6-c983-5067-bfa3-0c64a2d442f2 |  | note | – – – – – – – – – – – – – – – – –
label | d150ff4a-5bc2-5ed5-9d7a-fe8bb378e54c |  | note | VERIFYING DOCUMENTS: Survey As Report
label | 4d02fd2d-5f0d-5791-a4de-62d3da29cf66 |  | note | Date Completed:
checkpoint-status |  |  | checkpoint | 6.3 Red-line / As-constructed IFC Drawings
label | 7e25e6b8-03e9-5213-8703-527758880c03 |  | note | REFERENCE: MRPA Quality Management Plan
label | 30138de3-d288-5cbb-a1d6-ba24bdc823f4 |  | note | – – – – – – – – – – – – – – – – –
label | 3ecf4149-407c-5bd6-bb50-a016298caea5 |  | note | ACCEPTANCE CRITERIA:
label | 93140037-d863-5865-a497-d1553c245f7b |  | note | • All RFIs, NCRs and changes to the IFC drawings are captured on a controlled drawing set marked "Red-line", "As-built" or similar.
label | 7e97ed1b-5e72-5e0e-afc0-494b6621f3c8 |  | note | – – – – – – – – – – – – – – – – –
label | 1aaa41cf-a026-552b-b5bf-8a7e2d293099 |  | note | METHOD: Document Review
label | 03471765-4b60-5a0a-9f29-6712b725cb65 |  | note | – – – – – – – – – – – – – – – – –
label | f0d925e8-5c37-5989-aa95-78e3915beffd |  | note | FREQUENCY: Once, after construction of the design package
label | 69fa3425-e8aa-5c63-ba21-cd44a911d260 |  | note | – – – – – – – – – – – – – – – – –
label | 30007985-af9f-5d99-85b7-aab60723f2e2 |  | note | CATEGORY: WP
label | df3398b8-7d79-51d2-b0c1-ad4ee0d9cf40 |  | note | – – – – – – – – – – – – – – – – –
label | b3878b90-29d0-52e4-92cd-45df7df196de |  | note | RESPONSIBILITY: SE/PE/SPE
label | 55d502f7-7bfc-5d4f-83fd-32139500bad0 |  | note | – – – – – – – – – – – – – – – – –
label | 68cdcb72-8070-5353-8bcd-f7e46afe6726 |  | note | VERIFYING DOCUMENTS: This ITP
label | 7cdb9fe5-aba4-5a35-9d81-d49e9d4d8dfa |  | note | Date Completed:
checkpoint-status |  |  | checkpoint | Metropolitan Roads Program Alliance Final Inspection
label | 48cd75a8-1d9c-5b4a-bcad-2add2460a467 |  | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
text | 0e2c2a88-5eee-5aa9-99e0-fbf6553b2cd4 |  | textbox | Name:
text | 55b01236-1702-5672-8bd0-b183ccfec4b1 |  | textbox | Position:
text | 92c17c32-0d4c-5a7b-bb58-7ed6b3f94864 |  | textbox | Date Completed:
holdpoint |  |  | signoff | Sign ITP
checklist-sectioned |  |  | checklist | ITP-009-STR-Bored Piling | itp |  |  |  | Yes | ITP-009-STR-Bored Piling Rev 0 | 4b9003f8-8151-4362-b039-66f19e04c449
checkpoint-group |  |  | section | Referenced Documentation
checkpoint-status |  |  | checkpoint | Referenced Documentation
label | 52fa5381-7f92-5400-8bb4-c481246ece1b |  | note | Document Title: ITP-009-STR-Bored Piling
label | 2c2d6ba4-28ff-5076-a45a-fc0c47d69bd2 |  | note | ITP Description: Bored Piling
label | 77c717b2-e162-59c0-bf4d-a77a8dd9890c |  | note | Document Number (in Teambinder): MRP-0000-MRPA-ALT-ITP-00XX
label | 212aef7c-d24e-5d6b-9a39-d5f01812b080 |  | note | Discipline (e.g. CIV/STR/RAIL): 009-STR
label | ad7bfeee-8a64-5903-b907-0feec7fec2e1 |  | note | Revision Number: 0
label | edc909c4-fc3c-553b-8537-14f3aba04e62 |  | note | Revision Date: 11/10/2022
label | 8a5b7355-f54e-543d-a7e4-226209c7c883 |  | note | ITP created by:
label | 23af4e33-d6aa-54a6-9d2b-1711eefd90f6 |  | note | ITP approved for use by:
label | 718adae9-f64d-536f-92ba-1652c207c1ae |  | note | 1.1 - Non Dependent
label | 0631f35f-66c7-597d-8183-07b7471efa09 |  | note | Reference Documents:
label | 575cff68-dc4e-5649-a878-f9e5f0ecf925 |  | note | • VicRoads Section 606 July 2017
label | 67083365-e0a9-5f1e-b3a8-874277c2df0a |  | note | 1.2 - Non Dependent
label | c8bf7e37-ab26-5aa6-ae0a-42f9985b02b3 |  | note | Reference Documents:
label | d639850f-b897-5bde-9f50-7c295372c345 |  | note | • VicRoads Section 610 Feb 2020
label | 9cc3e9c1-75cf-51bb-a7bf-ce607728c2f8 |  | note | 1.3 - Non Dependent
label | 518986af-874e-552f-a608-00d1f86d359e |  | note | Reference Documents:
label | 919e322e-ef2f-5ce2-a4e9-93bb2f88fb9d |  | note | • VicRoads Section 611 November 2018
label | c0451440-8b56-5621-82f4-43e48354165f |  | note | 1.4 - Non Dependent
label | cab47aea-ad32-5f28-a5cf-a62be25952ea |  | note | Reference Documents:
label | 8f7ef28f-6a38-583f-8a36-171b9231c81f |  | note | • AS2159-2009
label | b07381a8-e3fa-5378-a29d-d34fe583c33d |  | note | 1.5 - Non Dependent
label | 4350757c-864a-57a9-8d5a-f089b4625da6 |  | note | Reference Documents:
label | 5407deb2-665b-5435-a4b3-f0520ed3e10c |  | note | • AS3810.1 2018
label | c7480114-60c6-585a-9bc7-cfa268204117 |  | note | 1.6 - Non Dependent
label | 7989f8de-ed7e-50c7-8bae-fb46ecc70ba6 |  | note | Reference Documents:
label | 33fd1675-48d2-5a36-bf5d-0a1b7082c2cc |  | note | • AS5100.3-2017
checkpoint-group |  |  | section | Preliminaries - Materials
checkpoint-status |  |  | checkpoint | 2.1 Concrete Mix
label | f9ec52d7-6720-55bb-84fe-3df33308254e |  | note | REFERENCE:
label | bc1d6b24-9ed7-5e78-885f-5c6906aeec78 |  | note | 610.07
label | d5f9ba87-c25d-5a0d-9d3a-0bf2a9e56902 |  | note | Table 610.071
label | 5cc1974a-89ac-50de-a22c-9e997d95f708 |  | note | – – – – – – – – – – – – – – – – –
label | 4b367dd5-7fd4-579d-be68-7cf5f43be6bd |  | note | ACCEPTANCE CRITERIA:
label | d2966f00-9e6c-5176-8791-0162a375ccac |  | note | • Concrete Mix is Registered with VicRoads.
label | f3dccb5b-632e-59da-90c8-6046af1fe44b |  | note | • Concrete mix meets strength, grade, and maximum aggregate size as detailed on drawings.
text | 3ec1d9a1-482e-5f18-a417-4772bb8a96b7 |  | textbox | Enter: Teambinder Material Approval number
label | f9a27263-c218-5491-90c4-414147c419c3 |  | note | – – – – – – – – – – – – – – – – –
label | 94b11045-40ce-512a-a7e2-3ae694fc84d5 |  | note | METHOD: Document Review
label | 2e927562-6c57-554b-aec9-e3f97f8feb09 |  | note | – – – – – – – – – – – – – – – – –
label | ef74f23c-255d-5a34-8508-733bf9614ad4 |  | note | FREQUENCY: Once, for each mix design, 4 weeks prior to placement of concrete
label | 097f1e5f-7c08-52e6-9e98-e5f40280abc0 |  | note | – – – – – – – – – – – – – – – – –
label | 726d6a41-cd0c-5581-8b45-ad8c45db4106 |  | note | CATEGORY: HP
label | 8567a3c6-ff1d-530c-893c-b185657990d5 |  | note | – – – – – – – – – – – – – – – – –
label | c3685c7e-02c6-5789-a7de-f3b87a5bde25 |  | note | RESPONSIBILITY: Nominated Authority
label | 1df1af45-6b20-5bb8-a996-bdc8c24b506b |  | note | – – – – – – – – – – – – – – – – –
label | eda71dd0-47f9-52cc-8905-0264cb5ff5f0 |  | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
text | d5f28fdb-0736-55ce-af0d-cd5e94e71eea |  | textbox | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.2 ACRS Certification (for Reinforcement)
label | b7b645b3-b7e7-5152-9940-259c96e79482 |  | note | REFERENCE: 611.05 (a)
label | ff285166-ba8f-5825-b52f-b6360968bf45 |  | note | – – – – – – – – – – – – – – – – –
label | 0d385491-a8e7-536b-a73d-b029e6425a66 |  | note | ACCEPTANCE CRITERIA:
label | ae7df377-9991-53d8-8a25-ced6a531d247 |  | note | • Current ACRS certification for materials and for bar processing.
label | 46010d56-c566-59a1-9858-089bd6178f46 |  | note | • Note: ACRS certificate may cover both aspects or be for each separate portion (e.g 1 for the material supplier and another for the bar processor (bending, cropping and delivery)
text | dfffbb20-5088-5def-ba55-934af8647721 |  | textbox | Enter: Teambinder Material Approval number
label | 442ea5fc-60da-5758-93b6-af84dc2f115c |  | note | – – – – – – – – – – – – – – – – –
label | 7ae33f1f-c621-5ee6-8d60-f61621b0a78d |  | note | METHOD: Document Review
label | b8095f3a-228f-5fc9-9ff4-dfb1450c45f8 |  | note | – – – – – – – – – – – – – – – – –
label | 48c4a90a-eb2a-5e72-8f33-f0fdd24b6fa7 |  | note | FREQUENCY: Once for each supplier, 14 days of award of contract
label | cfde858b-1517-5d88-afc1-5d649dbadf4e |  | note | – – – – – – – – – – – – – – – – –
label | 283bfbc9-07df-5a76-affc-c89f27e70428 |  | note | CATEGORY: HP
label | 88d87da6-b010-55e4-bb4d-593715776e9d |  | note | – – – – – – – – – – – – – – – – –
label | 32052a74-8e98-548a-aa1c-8a913f377fcc |  | note | RESPONSIBILITY: Nominated Authority
label | b8bee204-2f5d-52d8-b4c8-416f859e5b88 |  | note | – – – – – – – – – – – – – – – – –
label | f59a0a9a-ca38-533e-88a8-e55f8d7ecc3a |  | note | VERIFYING DOCUMENTS: This ITP
text | 0c7b12a2-1600-578a-9322-1f0e95e3191e |  | textbox | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.3 Bar Chairs/Aspros/wheels Certification
label | 32bbadad-28f5-50d2-a490-3dcd320ac940 |  | note | REFERENCE: 610.26 (a)
label | 7060c616-badc-5c47-98d2-703ef853a4e4 |  | note | – – – – – – – – – – – – – – – – –
label | 14e47d4f-c4d9-5d6e-a1c3-dacb68ae5d98 |  | note | ACCEPTANCE CRITERIA:
label | 1a9fc080-304c-55ff-a894-17423053f614 |  | note | • Plastic bar chairs, wheels, and spacers require bi-annual testing to demostrate suitablity to prevent excessive deformation under loads.
label | ec19b6d3-11cb-5e52-8ae7-95de4bcae11f |  | note | • Concrete aspros require annual compressive strength and soluble salt testing is required.
label | 113caa8c-c6d2-5dea-b154-47eb162b7fb6 |  | note | • Relevant test reports demonstrating compliance to this clause shall be submitted for review to the Nominated Authority.
text | 534a4b5c-4f95-5a44-9d89-2b6497937196 |  | textbox | Enter: Teambinder Material Approval number
label | 94afac09-2b06-5244-92cd-289d1a6b4d5f |  | note | – – – – – – – – – – – – – – – – –
label | af2fa23d-5fb8-524e-bc71-de17e9e6a3c7 |  | note | METHOD: Document Review
label | 0937d39c-0c3e-5f37-88f0-d7c46b26a16a |  | note | – – – – – – – – – – – – – – – – –
label | 1f5d6159-5a96-52b7-ae5a-1bb080f0273f |  | note | FREQUENCY: Once for each supplier, 14 days prior to placement of reinforcement
label | 54a88e2c-5f7e-5bb3-bcaa-12f26321c2d7 |  | note | – – – – – – – – – – – – – – – – –
label | d2850ffb-79e8-55ce-b986-1e2a64b4ea64 |  | note | CATEGORY: HP
label | 66a4e47c-d3dd-5665-a9c7-6ff3320041da |  | note | – – – – – – – – – – – – – – – – –
label | e9122874-018a-52b0-aeba-bc3d7e58ac97 |  | note | RESPONSIBILITY: Nominated Authority
label | 94283f24-ba4d-5d86-a8f2-55f4785487a0 |  | note | – – – – – – – – – – – – – – – – –
label | 6f7bc0e9-6f25-573d-9da7-5d97e74bea91 |  | note | VERIFYING DOCUMENTS: This ITP
text | f0f2c9ea-9da7-5c02-bd77-f2b2639e3703 |  | textbox | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | Preliminaries - Procedures & Documentation
checkpoint-status |  |  | checkpoint | 3.1 Working Platform certification
label | c9e4fb5c-4829-5061-a064-0a52b86c89aa |  | note | REFERENCE: -
label | 51b1090b-0474-59c2-aaf7-131e1bbc1fce |  | note | – – – – – – – – – – – – – – – – –
label | 60f8af1f-d74e-5c56-8ddd-73469eedfa30 |  | note | ACCEPTANCE CRITERIA: Satisfies minimum plant bearing pressures requirement
label | fecc628b-fddf-5eeb-a058-2c9a67fa8374 |  | note | – – – – – – – – – – – – – – – – –
label | 96fc436b-6d09-54d9-95ec-2dfae3171c60 |  | note | METHOD: Document Review
label | c66cd20b-5523-526a-aaf0-5b85b3c1fbe3 |  | note | – – – – – – – – – – – – – – – – –
label | 0f00208e-d935-5441-bbfc-514206980546 |  | note | FREQUENCY: Prior to works commencing & after rain event which there is >10mm in a 24hr period.
label | c8735659-aac2-5253-8d38-e94de6acc01d |  | note | – – – – – – – – – – – – – – – – –
label | a8f3fade-3d78-5549-98fc-4ee905da09be |  | note | CATEGORY: HP
label | bf0b0c4d-6034-5447-92d4-e1bceffb901b |  | note | – – – – – – – – – – – – – – – – –
label | 452d6077-ec8f-5fd5-9057-a0a04ed247a0 |  | note | RESPONSIBILITY: Piling Contractor/Geotechnical Engineer/Fulton Hogan Engineer
label | eb1bc9ac-1ab7-5ee4-8302-d69fde181891 |  | note | – – – – – – – – – – – – – – – – –
label | 0a968724-9d11-5cdb-beba-d5914832af2e |  | note | VERIFYING DOCUMENTS: This ITP
text | a19a7013-27b6-593e-8057-7fa4b759e953 |  | textbox | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.2 Piling Operations Work Procedure
label | 7e0a8aec-8c0d-5e82-a802-6c51c52758b6 |  | note | REFERENCE: 606.03 (a)
label | b654e747-4464-5618-8d4e-97f46135f2fd |  | note | – – – – – – – – – – – – – – – – –
label | 237272d8-7bac-5850-9bb4-0a559bb24df2 |  | note | ACCEPTANCE CRITERIA: Piling operations work procedure to be submitted for review to the Nominated Authority.
text | dba8e25f-02da-5316-a336-edce6a4cc564 |  | textbox | Enter: Teambinder Approval number
label | b43d955d-8809-5d56-876a-15520799e107 |  | note | – – – – – – – – – – – – – – – – –
label | 992ee446-b5f2-5adf-8b9b-62659a7cffc8 |  | note | METHOD: Document Review
label | 16f05ef8-045a-5684-a382-94b23f48f4e8 |  | note | – – – – – – – – – – – – – – – – –
label | 8ff5aed5-e4b7-5710-b054-d47b46c6785d |  | note | FREQUENCY: Once, 4 weeks prior to the commencement of piling
label | 2ffc20a8-fc6d-5ec9-95b2-3f6301b8cd90 |  | note | – – – – – – – – – – – – – – – – –
label | d016d519-254b-5051-969b-e6c840c7a8cb |  | note | CATEGORY: HP
label | a703042d-3146-5a80-9dfd-13565613045b |  | note | – – – – – – – – – – – – – – – – –
label | 2a800fe2-935c-563c-beed-5b51b71a2ac7 |  | note | RESPONSIBILITY: Nominated Authority
label | a8fd2277-c0a2-5dc1-9695-853a14ca90f7 |  | note | – – – – – – – – – – – – – – – – –
label | cd1e4829-73d9-5521-8942-c523e937f55d |  | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
text | 7122e299-8fbc-536a-811d-e84fa6a22b98 |  | textbox | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.3 Temporary Steel Casings
label | e456b16a-c8d7-5389-a6cf-babf89ce0824 |  | note | REFERENCE: 606.03 (b)
label | 15f7d266-1a3c-5a82-b4ab-7de09688bd26 |  | note | – – – – – – – – – – – – – – – – –
label | a3810d3e-de68-5ee8-be9b-4e03b846d72b |  | note | ACCEPTANCE CRITERIA:
label | ea95881e-68bd-51dd-800e-9676018bb233 |  | note | • Temporary steel casings shall be free from holes and distortion with a smooth internal surface without any projections.
label | 6816b67f-c68f-58c9-a6f4-f9c122148828 |  | note | • Any splices in the casings shall be able to withstand any stresses induced during installation & removal.
label | 98c193b3-cc16-5646-abe5-f506d745acd1 |  | note | • The casing shall be proof engineered by a proof engineer who is pre-qualified with VicRoads.
text | a3e0d1f4-e5e5-520a-91bf-262386541ce0 |  | textbox | Enter: Teambinder Approval number
label | 840f39f5-2ccb-5b6d-b116-c6cecabe12c3 |  | note | – – – – – – – – – – – – – – – – –
label | 8da83028-0f4c-5b66-97a8-424124829e68 |  | note | METHOD: Document Review
label | fd670178-9c0b-5d44-ba69-a92ba4a230f6 |  | note | – – – – – – – – – – – – – – – – –
label | a4d4bf0d-6890-5ad2-b75d-72b7f1badb39 |  | note | FREQUENCY: Where applicable, once, prior to use
label | ae147cdd-8a5f-578d-98fa-dfac104a3ebe |  | note | – – – – – – – – – – – – – – – – –
label | 50db6fdc-db64-5ea1-b605-fc7b6d2d7d98 |  | note | CATEGORY: HP
label | 910a22f3-f2d5-56a5-ac5f-01799149a16b |  | note | – – – – – – – – – – – – – – – – –
label | fb1bffe3-e28e-5275-a001-e6443bc8c0eb |  | note | RESPONSIBILITY: Nominated Authority
label | f113513b-2ee4-5f6b-8230-4c9344fa080f |  | note | – – – – – – – – – – – – – – – – –
label | 4225087c-1077-599d-9446-8f51535a0e72 |  | note | VERIFYING DOCUMENTS: This ITP
text | 81a88703-350a-52b7-aee3-8206ee4fddfa |  | textbox | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.4 Casting Under Water Procedure
label | 3904a830-e946-5547-ac51-4f3f42350611 |  | note | REFERENCE: 606.06 (a)
label | 1feb4396-f8ec-5887-8ebc-10aad9a808a5 |  | note | – – – – – – – – – – – – – – – – –
label | ddd424a8-bf09-5690-a6f4-fa40184de56d |  | note | ACCEPTANCE CRITERIA:
label | c4c19078-6ee8-5f5f-9a44-1a6790cdd662 |  | note | • Casting under water procedure and methodology for removing mud, loose rock and other debris to be submitted for review to the Nominated Authority.
text | d64fa74a-75ea-5e0d-859a-469bc5cc1a09 |  | textbox | Enter: Teambinder Approval number
label | b57fde01-cfd8-53e1-bd8b-300635f51798 |  | note | • Note: Piling Operations Work Procedure may cover this requirement - if so, use the same Teambinder Approval Number if this is the case.
label | d8bfe649-68f9-55e6-8de3-ef97007e4f82 |  | note | – – – – – – – – – – – – – – – – –
label | 72ad5a3a-213c-57cd-bc2c-6b437e11d4f9 |  | note | METHOD: Document Review
label | f505e575-d09e-5f2f-95a6-f2aed13d72ff |  | note | – – – – – – – – – – – – – – – – –
label | f03ced72-3ddc-592f-9882-f81dfee1e333 |  | note | FREQUENCY: Where applicable, once, prior to placement of concrete
label | 54d6169d-96ad-5c02-a41f-11729127d64b |  | note | – – – – – – – – – – – – – – – – –
label | b69d86b2-4034-586e-a7f2-58141432e7d4 |  | note | CATEGORY: HP
label | f030e221-75de-59f2-9fb5-59f5d926efbb |  | note | – – – – – – – – – – – – – – – – –
label | eaf51dec-df6e-54b4-b3b1-0cc51f498499 |  | note | RESPONSIBILITY: Nominated Authority
label | 283fa6bc-6a03-595f-8e85-ea52a0bab996 |  | note | – – – – – – – – – – – – – – – – –
label | 35dbb304-b0e8-5f41-96b9-39123e49f810 |  | note | VERIFYING DOCUMENTS: This ITP
text | 4c33449e-1b0c-532c-97f5-a8e4efafa85c |  | textbox | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.5 Boring With Bentonite or Polymer Fluids
label | 001dc125-dcd6-500c-b420-146886b3499d |  | note | REFERENCE: 606.03 (c)
label | cad15905-5e4c-5ac9-a64e-ce4ad1bf0ed3 |  | note | – – – – – – – – – – – – – – – – –
label | 3af5c556-d1f7-5e00-92b9-024c1e91c924 |  | note | ACCEPTANCE CRITERIA:
label | cb30b0de-6d9e-5046-80b5-1e8cb88fa2b9 |  | note | • Boring conditions under bentonite or polymer fluids alone or in combination with temporary casings to be submitted for approval to the Nominated Authority.
text | 47b75531-5066-5a4a-a26c-40dca3632c5c |  | textbox | Enter: Teambinder Approval number
label | 3a493e96-db69-5009-af28-a35957d3ef3b |  | note | • Note: Piling Operations Work Procedure may cover this requirement - if so, use the same Teambinder Approval Number if this is the case.
label | f643b916-514f-51e7-b97f-c24360263e2d |  | note | – – – – – – – – – – – – – – – – –
label | f4ff55eb-ba61-5634-b993-5dce25069366 |  | note | METHOD: Document Review
label | 5f2147e1-f783-5eb0-96c6-d117ac625072 |  | note | – – – – – – – – – – – – – – – – –
label | 28c8f4e8-f3ff-5124-a6a2-693f2a05e4cb |  | note | FREQUENCY: Where applicable, once, prior to commencement of boring
label | fd389d57-d3b3-53dd-aadf-41006fa174fb |  | note | – – – – – – – – – – – – – – – – –
label | b74a2502-8205-5a38-8f97-538c1ce29ef3 |  | note | CATEGORY: HP
label | 221f2711-fc8e-5269-a37a-625b1c929fca |  | note | – – – – – – – – – – – – – – – – –
label | 4e9ebe07-00b8-5e0d-82a6-84ef2b4cab31 |  | note | RESPONSIBILITY: Nominated Authority
label | 1967d4e7-4006-5266-8c12-b6d372fd00cb |  | note | – – – – – – – – – – – – – – – – –
label | 3a7be694-a908-507e-bcdb-43603b85c5cb |  | note | VERIFYING DOCUMENTS: This ITP
text | 0aba3beb-476d-506e-a983-e974ec4bfd94 |  | textbox | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.6 Dynamic Pile Testing Procedure
label | 5c07b1d6-dfab-55af-884a-b2ab6c762879 |  | note | REFERENCE: 606.07 (c)
label | 311bb4cc-d826-5393-9a1a-f113d584a08a |  | note | – – – – – – – – – – – – – – – – –
label | e52526ea-2d66-50d1-944a-a4f5f8df5910 |  | note | ACCEPTANCE CRITERIA:
label | 509d0494-64ae-580a-8da7-fd3d3182fb73 |  | note | • Details of the proposed pile driving rig, hammer size and drop heights to be submitted for review to the Nominated Authority.
text | b27127e5-91fb-5ecd-ae5f-ce5e6b4acb6f |  | textbox | Enter: Teambinder Approval number
label | ea01df4d-f709-5346-98a5-9ff262eae81b |  | note | – – – – – – – – – – – – – – – – –
label | 1e281150-2ed2-5815-b3c0-4fa6ddb382a4 |  | note | METHOD: Document Review
label | d511e08c-8e2b-53e7-9900-7ffbbd9265f7 |  | note | – – – – – – – – – – – – – – – – –
label | 1f6a6b1f-e44c-549a-8d1e-20988b13f84d |  | note | FREQUENCY: Once, prior to testing
label | dca58c95-8f65-5839-a3e1-c300cbace64c |  | note | – – – – – – – – – – – – – – – – –
label | 4ab1edfd-ba09-592c-b8d8-2b6f28654398 |  | note | CATEGORY: HP
label | 3a49772c-9aaf-5eb9-bb29-e80d4b9fac20 |  | note | – – – – – – – – – – – – – – – – –
label | a4811b54-06b9-5d26-917c-0552e93865a3 |  | note | RESPONSIBILITY: Nominated Authority
label | 6f4dfdbb-d5cb-5874-a4f8-b22a736f2017 |  | note | – – – – – – – – – – – – – – – – –
label | 12ee48f1-8ff3-5fa8-9f68-ac9cb5c79f6b |  | note | VERIFYING DOCUMENTS: This ITP
text | 36f2f781-e3f2-5f62-9061-df0e41067a62 |  | textbox | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.7 Pre-qualified Pile Testing Consultant
label | 949c090a-5f08-5478-9eb9-6b2fb2145728 |  | note | REFERENCE: 606.07
label | 09c15931-e4bb-58dd-836b-8b0b863c2717 |  | note | – – – – – – – – – – – – – – – – –
label | 3c834cca-0f6f-595c-b3de-63a23b889d32 |  | note | ACCEPTANCE CRITERIA:
label | b4fef640-36d5-5b6e-b6b6-9b672c17bf15 |  | note | • All testing shall be undertaken by a Vicroads pre-qualified consultant who is independent of the piling contractor.
label | f28bab00-9f1b-57f8-9958-581c59292a44 |  | note | • Details of the consultant to be submitted for review to the Nominated Authority.
text | 3c43dcb3-7d79-54f9-9ecb-03341fd36f83 |  | textbox | Enter: Teambinder Approval number
label | e0719f0f-37a7-547a-beb3-0ab744ba6858 |  | note | – – – – – – – – – – – – – – – – –
label | 84c6e1f6-b75f-5960-8675-c755ced3f94b |  | note | METHOD: Document Review
label | f8dcb74b-0736-5426-b6be-72a377d687b4 |  | note | – – – – – – – – – – – – – – – – –
label | 19e8dd95-773c-5617-95f5-b454f79d18f1 |  | note | FREQUENCY: Once, two weeks prior to testing
label | 6eb426a9-07a8-5571-b4b0-6512dacfaae8 |  | note | – – – – – – – – – – – – – – – – –
label | b47cbffb-8af6-5ebd-83da-13bb8b8f5687 |  | note | CATEGORY: HP
label | 80ea157a-988b-5387-b602-03c8da33540e |  | note | – – – – – – – – – – – – – – – – –
label | 59de6927-5da8-59a6-b9b9-a19d305d753c |  | note | RESPONSIBILITY: Nominated Authority
label | 6dc45cdb-bd59-54ee-ab9c-a05020fd66d9 |  | note | – – – – – – – – – – – – – – – – –
label | 3cd28b57-5c72-54d7-9e0e-d414e4b26e79 |  | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
text | 9cdf8e14-9488-5b38-8040-390d6ea14540 |  | textbox | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.8 Reinforcement Welding Specifications & Qualifications
label | 8cb2dcf2-d2e2-536e-8ec0-d6d35742729c |  | note | REFERENCE:
label | b1b97f39-2c31-5948-a5b4-ca0da3e2a3b9 |  | note | 611.13 (a)
label | 331e3d42-96b1-53f1-9875-c5a9aa890b7d |  | note | AS/NZS1554.3, Clauses 3.3.2 & 3.3.3
label | e2be3a92-7881-584e-bd7f-0d57324f1113 |  | note | 611.14 (b)
label | 0f60840c-ca66-585e-a265-e0df8930d415 |  | note | – – – – – – – – – – – – – – – – –
label | 8abf435e-7794-569b-a13e-fc285151a1ac |  | note | ACCEPTANCE CRITERIA:
label | 2a818cbe-8250-5e8c-89b8-2430bf6c9a07 |  | note | • Welding of splices in steel reinforcement, including to other steelwork and to continuity bar reinforcement, shall not commence until the welding specification & qualifications (including macro inspection) have been approved by Nominated Authority.
text | 586166c3-49ec-54bd-b857-cf46a11f2986 |  | textbox | Enter: Teambinder Approval number
label | 2e94e801-47c7-5274-bd39-b3b02a470390 |  | note | – – – – – – – – – – – – – – – – –
label | 17c3899e-091e-5d74-8d0d-4a92be387f37 |  | note | METHOD: Document Review
label | 271f5e56-1024-5b77-a684-6f28a9b9cdff |  | note | – – – – – – – – – – – – – – – – –
label | 0a7ada04-4fef-592c-949c-055aeb489e27 |  | note | FREQUENCY: Where applicable, once, prior to welding
label | a4446d8f-7149-5d79-8a9d-cb8e2e8d7778 |  | note | – – – – – – – – – – – – – – – – –
label | 713edab5-8dbe-5af2-99e6-c4858e002de9 |  | note | CATEGORY: HP
label | c5d29d56-b783-5749-8390-dc308aeb2eff |  | note | – – – – – – – – – – – – – – – – –
label | a04f2a76-5638-5d24-a37a-f52ea38a45e7 |  | note | RESPONSIBILITY: Nominated Authority
label | d8c3d317-3413-5bd8-a09c-1fb5868066eb |  | note | – – – – – – – – – – – – – – – – –
label | 64b8b438-ce43-5734-a700-b629b8637bf1 |  | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
text | 4d25c1c1-cab2-5c6f-b794-8a7657e7fffa |  | textbox | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | Pre-construction Activities
checkpoint-status |  |  | checkpoint | 4.1 IFC Drawings
label | 184b4294-9264-5d23-9241-a14978164234 |  | note | REFERENCE: MRPA Quality Management Plan
label | e34b3ec0-4605-580a-a874-a7333aefa49c |  | note | – – – – – – – – – – – – – – – – –
label | e708b842-f867-5ed4-987f-15f35eefddc0 |  | note | ACCEPTANCE CRITERIA: Check the revision of the IFC drawings are current as per the drawing register (on Teambinder)
label | eb7b3bf9-5f26-5bf0-a66d-200d2c199c98 |  | note | – – – – – – – – – – – – – – – – –
label | 9e098647-e160-51c4-a177-1ac024c58e85 |  | note | METHOD: Document Review
label | e55d27e2-ec5c-54c3-999f-60b054cf55a3 |  | note | – – – – – – – – – – – – – – – – –
label | 573758ee-451a-57e6-b043-5e7ed4a35c0f |  | note | FREQUENCY: Prior to starting Works and at regular intervals
label | 56994085-35d4-5b8c-acd9-7ba3150e9cca |  | note | – – – – – – – – – – – – – – – – –
label | baf905ab-df5d-58e4-b646-6523719ed01b |  | note | CATEGORY: HP*
label | 638c8d54-14fe-5022-849e-1a073f04efb8 |  | note | – – – – – – – – – – – – – – – – –
label | 05c42d70-6fd4-5c9d-bc4d-ba732ad6827a |  | note | RESPONSIBILITY: All
label | d2da4d9a-c9ec-5b36-936d-f211763c1e2f |  | note | – – – – – – – – – – – – – – – – –
label | 139bb36e-43d3-543d-9790-752c4c651087 |  | note | VERIFYING DOCUMENTS: This ITP
text | 71cdfdfe-aaca-5fa1-b02d-7047ed2cb65d |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 4.2 Survey Set-out
label | f3055229-ef38-52a4-b376-6c66da9578ca |  | note | REFERENCE:
label | 875064e2-333f-547b-bb63-cb4b507ce67b |  | note | IFC Drawings
label | d2ede88d-da9c-5a22-b693-614edca97541 |  | note | 606.08 (a - c)
label | 140794b2-b54a-5de4-9202-60f37206c7de |  | note | – – – – – – – – – – – – – – – – –
label | a799edfb-4eb8-5c88-945e-fa8d5878da16 |  | note | ACCEPTANCE CRITERIA:
label | 5ab8ccbe-6c44-53e0-ba6d-2a21b51ecb02 |  | note | • Survey activities undertaken to ensure and validate that all Works meet location requirements of ±75mm.
label | 82b057a4-0456-5261-a05d-e0a7886deacd |  | note | • Attach: Lot Map, Marked drawing to indicate the location of piles in the Lot
label | b4d5d1cc-5ffb-5f15-8079-50466a497e7c |  | note | – – – – – – – – – – – – – – – – –
label | 9ef45056-24a6-50fc-bf87-37e19594a74e |  | note | METHOD:
label | 56229457-b904-56fa-ab8b-f6bdd85cc5eb |  | note | • Measure
label | 945f6558-c0b2-50eb-ae6c-8e5eb5a0dce3 |  | note | • Visual
label | bc17366f-0a5d-54bb-85c0-00b1b5071f11 |  | note | – – – – – – – – – – – – – – – – –
label | 41a877a3-3719-5e42-9909-5531286b1a43 |  | note | FREQUENCY: Each pile
label | cd381719-59c7-5f86-b2bf-43c2fde0b344 |  | note | – – – – – – – – – – – – – – – – –
label | 202c6e27-3bdb-50ca-bc14-3f29091c8e8b |  | note | CATEGORY: IP
label | 4664b29c-57e1-5240-8f2a-3c1e692fe09d |  | note | – – – – – – – – – – – – – – – – –
label | d860bf65-5f60-59a5-a820-7ef21770edcb |  | note | RESPONSIBILITY:
label | 6ce8eade-cb1e-54df-9db5-919817011b5a |  | note | • Surveyor
label | 0a94276e-331f-514c-b770-0332d60bf15b |  | note | • SE
label | dc614ca9-eaa0-5f4b-8068-c83f7bc01a2d |  | note | – – – – – – – – – – – – – – – – –
label | f3c3d0be-9661-5e9e-9b51-084573630029 |  | note | VERIFYING DOCUMENTS: This ITP
text | a94efc2c-a997-50f9-8473-05e6d9530fde |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 4.3 Protection of Adjacent Piles
label | 5e338647-ed2d-57cd-8efb-e55936763916 |  | note | REFERENCE: 606.04
label | 46d1ace9-4e9a-5a2f-8375-6c7694d6c94b |  | note | – – – – – – – – – – – – – – – – –
label | 8415349c-8677-56ed-b1db-78971afeba43 |  | note | ACCEPTANCE CRITERIA:
label | d26b7935-1345-5298-a7a2-4b2f9299ad20 |  | note | • Pile construction shall not:
label | 6c1a4094-15a0-5b4e-a469-bffcd696d9f5 |  | note | i. result in damage to adjacent newly cast piles due to ground vibration.
label | 9b2b3aad-edb8-53b6-9a16-e79b4b73551a |  | note | ii. commence within 2.5m clear distace from newly cast piles if that pile concrete strength <15MPa
label | 256723e0-9f86-50e6-b97f-ba588e25efaf |  | note | iii. involve driving or create significant vibration within 9m until that pile strength ≥15MPa and set for a minimum of 24 hours
label | 805b535a-ed9b-5dea-a9a4-7b3d0e3c1225 |  | note | – – – – – – – – – – – – – – – – –
label | 981f3aab-68bd-5a49-951b-3c5148b18cf5 |  | note | METHOD:
label | dc17e302-2089-5633-85ca-c46ecbe2cb17 |  | note | • Measure
label | 9919623d-8707-5d8d-9483-a38fe79a16d5 |  | note | • Visual
label | 4c01efbb-bd0c-52ff-bfd5-4d319894697e |  | note | – – – – – – – – – – – – – – – – –
label | 5bb3c1e5-fc40-5e55-9b45-3348da745c30 |  | note | FREQUENCY: Each pile
label | 8f0650ad-4594-5447-9144-881d88ca72a7 |  | note | – – – – – – – – – – – – – – – – –
label | d9a81f05-ecf8-5479-8cd0-4ad55c62c049 |  | note | CATEGORY: HP*
label | 1123222d-0b36-5b39-a79b-7e328f0fe89b |  | note | – – – – – – – – – – – – – – – – –
label | ef2c4f50-59ab-54e5-98b9-86cd5787f04e |  | note | RESPONSIBILITY: SPE/PE
label | a862cc19-4139-59ea-af80-6df0d0cc65a1 |  | note | – – – – – – – – – – – – – – – – –
label | 985b2886-668e-5af2-a2ef-39931d3a9a89 |  | note | VERIFYING DOCUMENTS: This ITP
text | 4b241ed0-be67-5111-9d39-649aa1f480be |  | textbox | Date Completed:
checkpoint-group |  |  | section | Construction Activities
checkpoint-status |  |  | checkpoint | 5.1 Boring Operations
label | 5b8af99e-6c5d-59a3-9a34-31a3c89f19c2 |  | note | REFERENCE:
label | 6cb2092f-3bee-57f1-bfaa-ea142eada30b |  | note | IFC Drawings
label | 9e1d41b5-515e-5faf-80af-7ca645aae55d |  | note | 606.03 (a)
label | 0ebfafec-d047-55b8-8b9f-fb20a3d7b14c |  | note | – – – – – – – – – – – – – – – – –
label | 2c0095f2-2862-5410-8304-30fa06960bb1 |  | note | ACCEPTANCE CRITERIA:
label | 8f47e637-4c94-5d3f-8a53-d9444e603c9d |  | note | • Boring performed to the required diameter and depths shown on the IFC Drawings under the instruction of an experienced geotechnical engineer.
label | 45d3792e-2573-595f-98aa-4ded19451085 |  | note | • Where piles are founded on rock, they shall extend a minimum of 2 x pile diameter into the rock shown on the IFC Drawings.
label | 9a6812e1-fefd-57aa-93ee-489b4126985b |  | note | • Excavation clean and de-watered (where applicable) for inspection.
label | 2594c267-2586-5cc9-99bb-0dc569a2e9c3 |  | note | • Excavation made safe by appropriate means and to be protected from site run-off and loose materials falling in.
label | 2bdb2e0d-c713-592e-9607-df67e49431a1 |  | note | • Excavated material to be disposed of as appropriate to maintain a clean site.
label | 6c6206c5-872e-5527-bc8d-f4612a28aa8b |  | note | – – – – – – – – – – – – – – – – –
label | b30ccc7b-c7ea-5cd1-989c-60f3bab8602e |  | note | METHOD:
label | ff2424e6-d1a3-593c-9ceb-f8eba0c46367 |  | note | • Measure
label | c7afa41d-1be8-5cc2-b24f-f687ba6d9f01 |  | note | • Visual
label | 1b71b34d-9333-5ea6-9daa-44018cd4d030 |  | note | – – – – – – – – – – – – – – – – –
label | 267c3edc-82f0-5db2-b49a-f79abfc15457 |  | note | FREQUENCY: Each pile
label | cad0a253-f81a-5778-a573-a340303072a3 |  | note | – – – – – – – – – – – – – – – – –
label | 53757d1c-896a-5a95-930f-8ba012c46f85 |  | note | CATEGORY: IP
label | de9826b9-4550-53bd-b625-90c97b4a8360 |  | note | – – – – – – – – – – – – – – – – –
label | e2693023-ac06-53ce-9719-35dcea95b488 |  | note | RESPONSIBILITY:
label | 86d7c5d0-7977-5460-bfa9-155136dc450f |  | note | • Surveyor
label | 28ed8a7b-8426-5b58-ad05-260bc888747f |  | note | • SE/PE/SPE
label | f6056cfe-6072-530d-91c2-9c1903b24262 |  | note | – – – – – – – – – – – – – – – – –
label | 37247ee1-c7e7-5830-9005-f9318539760e |  | note | VERIFYING DOCUMENTS: This ITP
text | 0e630cdb-cc92-57ea-a7bf-7fb3249d973f |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.2 Formwork Extension
label | b6797db5-8f1a-5193-960d-6162774d4f57 |  | note | REFERENCE: IFC Drawings
label | 3a642acc-e973-5d2d-aa46-dd87c899619a |  | note | – – – – – – – – – – – – – – – – –
label | c64c778e-233b-5376-8d93-58cb46d78714 |  | note | ACCEPTANCE CRITERIA: Where applicable, formwork shall be used to ensure the top of the pile is at the required RL.
label | 537b60d5-be34-589b-80c6-8e505b721fb3 |  | note | – – – – – – – – – – – – – – – – –
label | f9d6c7d1-f73b-57a8-b17c-b1170d72b340 |  | note | METHOD:
label | f62c4634-93b5-5502-a923-081f923fa7e7 |  | note | • Measure
label | ef2e9789-c3e2-5ce9-b88b-193c4e2fa5bc |  | note | • Visual
label | 923f0a66-f885-54c3-8756-8ca88e3c4c04 |  | note | – – – – – – – – – – – – – – – – –
label | 2dd2653e-7e45-5caa-8540-fb632987de53 |  | note | FREQUENCY: Where applicable, each pile
label | f66a9886-1989-597a-8d65-4071e9baf443 |  | note | – – – – – – – – – – – – – – – – –
label | 1965134d-646e-5749-a673-1b742a458048 |  | note | CATEGORY: IP
label | 64a24485-efd7-560e-93bf-de8310b5e2c2 |  | note | – – – – – – – – – – – – – – – – –
label | 0f0c593e-22e2-5351-a7e5-b3981c0e8ed0 |  | note | RESPONSIBILITY:
label | 14f0ab65-6e6e-5ea9-a9f2-4904c8dfb1f5 |  | note | • Surveyor
label | 02c1340f-0d7a-54ae-96d7-fd6b22c44ab4 |  | note | • SE/PE/SPE
label | 1d028e00-25b3-5ae6-b554-cc6154120bd6 |  | note | – – – – – – – – – – – – – – – – –
label | 93cdbda8-4d09-504c-a9e8-cb72349e854e |  | note | VERIFYING DOCUMENTS: This ITP
text | a008f0c7-beb7-54d4-9e90-344c0e389b4c |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.3 Inspection of Pile Excavation
label | 908cf23f-a48f-5715-9380-6f6741f5c945 |  | note | REFERENCE: 606.05
label | 43730929-0469-5104-97d1-539ba8ddcfa4 |  | note | – – – – – – – – – – – – – – – – –
label | 22636935-6f74-555c-accb-83e50300849a |  | note | ACCEPTANCE CRITERIA:
label | 41772c49-c836-596d-beb4-93d795f80af2 |  | note | • Pile walls and base to be inspected by the geotechnical engineer to confirm that the geotechnical strength of the materials in the pile wall base have satisfied the design assumptions.
label | c4178880-fc19-50d1-8b1d-0d6d9e8c45c2 |  | note | • Attach: Geotechnical Field Sheet or Report
label | d77bd15a-2d42-5ba6-9692-9f5b46ef2821 |  | note | – – – – – – – – – – – – – – – – –
label | 4723d3fb-304b-594b-bfb0-38be12df114c |  | note | METHOD:
label | e5e7e527-9976-58be-99e5-40f80b5d7062 |  | note | • Measure
label | 27174d12-2b72-562b-ba02-e7d57e432b9c |  | note | • Visual
label | 9a1ebe36-dd48-5550-a665-28757e5893ec |  | note | – – – – – – – – – – – – – – – – –
label | e522095b-7525-594e-9fe0-59f394ebe085 |  | note | FREQUENCY: Each pile
label | 8a5c9aa4-19b2-59f6-9917-d0fb942dccc9 |  | note | – – – – – – – – – – – – – – – – –
label | b0d24629-e0bc-54ff-831f-c1a0770848d8 |  | note | CATEGORY: HP
label | 44fe9f1a-8592-538a-a376-a0e9b073f85b |  | note | – – – – – – – – – – – – – – – – –
label | e8f481f0-f047-5c74-b6e2-6062226d91d6 |  | note | RESPONSIBILITY: Geotechnical Engineer
label | f7ace0eb-22c6-5e2d-aa8e-24b52ae0251e |  | note | – – – – – – – – – – – – – – – – –
label | dc33544c-3543-547d-afae-15a5226c47d1 |  | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
text | e7a266df-097b-5cb4-9207-b97035b57229 |  | textbox | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 5.4 Reinforcement - Placement
label | fb41695d-4601-5774-8c57-71aebac387d8 |  | note | REFERENCE:
label | 5fc19c93-04b7-570b-887f-8eff9e08a652 |  | note | IFC Drawings
label | b9fdaf84-1330-5f0f-a850-b0b8367ccac2 |  | note | 611.06
label | 55106d6f-c2c8-527c-937f-a245e8a0f34f |  | note | 611.09
label | 8757a8ad-d9e6-59f3-9af0-8486e1160e0c |  | note | 611.10
label | 70741d57-6763-523f-9ce2-c2f7f8063189 |  | note | 611.11
label | 86d984d2-fa34-544c-bed1-7ea5c8f433ae |  | note | 611.12
label | 4c82e585-c868-5105-90bd-96812e916b48 |  | note | 606.06 (a)
label | 293bf9ab-dac9-542c-b580-d648291a88bf |  | note | – – – – – – – – – – – – – – – – –
label | f3c08f0f-9589-5fb6-bdb2-4d8a211963ac |  | note | ACCEPTANCE CRITERIA:
label | 0f567ff5-3e64-5b63-b122-32a19e365626 |  | note | • The correct reinforcement grade, quantity, size, orientation, location and spacing as shown on the structural drawings.
label | 1ef96832-5a55-551a-8ceb-38c496149828 |  | note | • Projecting reinforcement is the correct length and location.
label | 933c190b-94b3-52a5-a3cd-621be900be85 |  | note | • Splice lengths achieve the minimum length and are in contact for this length.
label | 28f3d39a-6ccb-58e8-98a4-3722bde1216f |  | note | • The reinforcement surface condition is free from dirt, debris and damage.
label | c9bb9db2-51c2-59bc-ab3b-4465f37f24c9 |  | note | • The resulting cage securely held with sufficient ties to limit displacement or deformation during the concrete pour.
label | 276cf8db-c4d6-5f63-8aa4-812b031c619f |  | note | • Bar chairs or wheels used at no greater than 2m centres so that the minimum cover as shown on the structural drawings all around and has been achieved (including tie wire locations).
label | 40728aff-b0dc-5831-8e20-31693cc312c5 |  | note | – – – – – – – – – – – – – – – – –
label | 7b68cae8-22fc-58a6-a69f-47637d29e8ad |  | note | METHOD:
label | 9c04c931-5e42-5e8b-af6d-27ad8ae3e1d6 |  | note | • Measure
label | fe4fa412-8332-552c-ba52-490cb7a8d57a |  | note | • Visual
label | 884ff9db-867f-5993-b8b2-330fe176e154 |  | note | – – – – – – – – – – – – – – – – –
label | 3bf54891-f033-51bf-853d-f113f73ffdf4 |  | note | FREQUENCY: Each pile
label | 0702d125-2bf3-5898-b54b-5178a030d226 |  | note | – – – – – – – – – – – – – – – – –
label | 6f92b7db-1bfe-51ee-a86f-fcb05d65cd30 |  | note | CATEGORY: IP
label | 113626d2-601d-5a41-8b35-fada598facba |  | note | – – – – – – – – – – – – – – – – –
label | 95bfc037-64d4-54af-be32-250046e6b1d6 |  | note | RESPONSIBILITY:
label | 4f38a872-d9c6-5602-a9cc-4bd5a9862d8d |  | note | • Foreman
label | 3c001345-f79d-52ce-b27e-1ffbfc5a8d41 |  | note | • SE/PE/SPE
label | ed0c5e4d-1b95-51b4-8f0b-b167ff730859 |  | note | – – – – – – – – – – – – – – – – –
label | 662074ae-ffc4-57bb-abeb-f06a9eadc7b1 |  | note | VERIFYING DOCUMENTS: This ITP
text | 2254d36e-4dd1-5b4b-8192-1cec69b60d7f |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.5 Reinforcement - Electrical Continuity
label | 6c2ffd54-2acf-5267-9f86-5164124cf2e5 |  | note | REFERENCE:
label | f4e76d9c-5430-5e17-881e-8dc644f4fe6a |  | note | IFC Drawings
label | 747e0529-ad44-597e-9684-d7f6c48e2fa4 |  | note | 610.29 (d)
label | c718903d-0cb8-55cb-9fc8-a469b2e8e2d2 |  | note | 610.43
label | b115b553-24b5-50f7-90ab-17aae259db3e |  | note | – – – – – – – – – – – – – – – – –
label | 979818ba-544d-540d-8bc4-d47010142c4c |  | note | ACCEPTANCE CRITERIA:
label | 78e47b44-8d11-5134-b149-710d33ff2d44 |  | note | • Pile reinforcement cage to be made electrically continuous by:
label | e7dd9145-1004-580b-be2f-b167866c6ce4 |  | note | i. tack welding 4 no. min. longitudinal bars to all intersections of the helix at 2.0m centres max. (at every intersection is preferable)
label | e16569dc-fcc6-5f73-a617-cadec8df7798 |  | note | ii. tack welding the selected longitudinal bars at all splices (2 tacks minimum per bar)
label | 16c0a444-c56a-57b2-ba60-695cccb5254c |  | note | iii. tack welding or fastening the grounding clamps to the longitudinal reinforcement
label | 47f22b2d-bd2d-54a4-9404-984ffdedaca8 |  | note | • Evidence that the resistance across the cage has a maximum value of 0.01Ω / 10,000µΩ is required.
label | 1a69d8df-d934-50ec-8225-2c4c33b0f9e8 |  | note | • Photograph or attach: Ohmmeter reading across the splice or end to end of the reinforcement cage
label | c4cb3727-fa70-573a-90ef-f1e56bc8e7eb |  | note | – – – – – – – – – – – – – – – – –
label | 50f3482d-792e-540b-bcce-475b3b72ace5 |  | note | METHOD:
label | 15a1905b-0ef8-5981-bf03-18dccba90531 |  | note | • Measure
label | 78d99041-3651-552e-a44d-13825c6226b3 |  | note | • Visual
label | c32ee306-a0c6-5276-9482-5e620c25f987 |  | note | – – – – – – – – – – – – – – – – –
label | 20f753cb-730b-5964-a754-baaee7889514 |  | note | FREQUENCY: Where applicable, each pile
label | 8981778c-3d94-5e45-95d1-35c111cda609 |  | note | – – – – – – – – – – – – – – – – –
label | 9a3bb6cd-5dd3-515d-8fc6-992495f38c71 |  | note | CATEGORY: IP
label | 6efb60c4-7dd4-582c-b5a7-73c8a77c852a |  | note | – – – – – – – – – – – – – – – – –
label | 30fc4f1e-3e2c-574e-9706-7169f65fbcc3 |  | note | RESPONSIBILITY:
label | 94d6596b-3067-5047-8928-feec3addb5d6 |  | note | • Earthing Engineer
label | 776b0787-d915-5d7c-a5d0-e435ab62b959 |  | note | • SE/PE/SPE
label | 0906dde0-2855-5f04-a52e-f5c041ba9f9d |  | note | – – – – – – – – – – – – – – – – –
label | 8731249b-b035-597a-a7ab-48e0c6b92d5e |  | note | VERIFYING DOCUMENTS: This ITP
text | c13d8d7a-518a-566c-8612-7513718b8798 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.6 Cast-in Items
label | f0a91598-6448-57bc-b8af-f38b277da2e3 |  | note | REFERENCE:
label | bc3857fb-626c-5787-a7a7-8dae8a1d7662 |  | note | IFC Drawings
label | 3700168f-c94a-5bbb-bc1e-501cbf60bae7 |  | note | 610.46 (a), Table 610.462
label | f1b455e0-5de8-5a2d-9901-2c92d942eb11 |  | note | 610.47 (a), Table 610.472
label | 585df82c-bc6d-5a4d-bd19-0d3ee9f4853a |  | note | AS3810.1 Table 3.3.6.2
label | 1a07fe37-4f67-5626-a373-85006a15b895 |  | note | – – – – – – – – – – – – – – – – –
label | 3221b025-b921-5202-94a8-270b087f1070 |  | note | ACCEPTANCE CRITERIA:
label | a4d9b194-d415-598c-9848-0bfaabb3cbe8 |  | note | • All cast-in items are the correct type, grade, quantity, size, orientation and location as shown on the structural drawings and are securely fastened or restrained to withstand impact and pressure during the concreting operations to prevent dislodgement.
label | c44d62cc-b033-51bc-aae0-4112ac8426e1 |  | note | • Any exposed threads, conduits, ducts or voids shall be protected by suitable means to prevent concrete or grout ingress.
label | 5456c545-8965-50fb-b79e-4f7c42629d45 |  | note | • Tack welding of any cast-in items shall be performed by someone pre-qualified to do so.
label | c5b6b0ff-9bc5-556d-8821-122d431eb926 |  | note | • Grout tubes shall be fastened at regular intervals to prevent kinking.
label | 6458a195-221c-5ee8-ac7b-68e3caeac690 |  | note | • Placement tolerances to comply with the IFC drawings, if not specified, use the following:
label | b75b63b6-12fb-558e-b0e6-931064d31e30 |  | note | i. Bolts, ferrules, projecting bars & couplers = ±3mm
label | 1fd5e36b-a5ee-5923-885d-d4efb50e25ee |  | note | ii. Running dimensions of a group of the above = ±6mm
label | 9c6ba492-b335-5918-a3d3-5aacabbbb3b5 |  | note | iii. Ducts and conduit location = ±12mm
label | d941cae4-0d08-5d92-837f-64b6f65ba284 |  | note | iv. Diameter of ducts and conduits = ±3mm
label | da8101df-b5c9-571c-9b80-e24e791e5547 |  | note | – – – – – – – – – – – – – – – – –
label | 4c678050-0bb9-5753-8227-4762d3b70fe2 |  | note | METHOD:
label | 5cbb054c-9bfe-5fc3-b45b-49fb4d73bea3 |  | note | • Measure
label | 36e075bc-4c5a-55f9-982f-23ccc72baa72 |  | note | • Visual
label | 8c534a50-b451-5ee6-83a4-0b21e571e45d |  | note | – – – – – – – – – – – – – – – – –
label | c24a57ef-338d-57b3-91da-d67e322098a9 |  | note | FREQUENCY: Where applicable, each pile
label | bc04cb35-4eaa-5514-ab3c-7c1106067e18 |  | note | – – – – – – – – – – – – – – – – –
label | 7b90119f-9bdd-5db5-900c-858d5fb5df06 |  | note | CATEGORY: IP
label | a1aec0ae-3db3-51cf-80af-e622c01e660d |  | note | – – – – – – – – – – – – – – – – –
label | b4d93bb1-6dc3-5085-8293-26f0bf2f5f5f |  | note | RESPONSIBILITY:
label | d37adf33-1060-5967-9655-8318ca04949b |  | note | • Foreman
label | e035e217-0090-540f-be1d-a9d97b8884bb |  | note | • SE/PE/SPE
label | 100b2ddc-6c43-5a86-8355-0eecdd95943d |  | note | – – – – – – – – – – – – – – – – –
label | e6290714-cee7-5643-865e-03ea3479b016 |  | note | VERIFYING DOCUMENTS: This ITP
text | 7fc1ead9-e925-51a7-b6a6-fce481acbdd8 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.7 Pre-pour Inspection
label | ccb1aea9-6ca7-53ea-b218-af9499528574 |  | note | REFERENCE:
label | a9891590-b6c8-55ff-b539-f439bddec7a0 |  | note | IFC Drawings
label | 683d2725-6d12-5768-802f-ee1f467d677c |  | note | 610.18 (a) (ii) & (iii)
label | 6ef80670-3582-5f72-be8b-5d527fcf7ad4 |  | note | – – – – – – – – – – – – – – – – –
label | e9b1522e-ac3a-5c3e-9c5b-9e907f9054a9 |  | note | ACCEPTANCE CRITERIA:
label | aaae04ef-c689-58c7-8f25-b5f5a6bcbe75 |  | note | • Evidence that the forms, reinforcement, electrical continuity and other cast-in items conforming to the requirements of this specification and the drawings has been reviewed by the Nominated Authority
label | de845f86-3434-50d1-9344-6a7005ed30c7 |  | note | • All foreign material has been completely removed from the excavation.
label | d56c7d52-e2c5-5907-b8ae-3c35c7f67c17 |  | note | – – – – – – – – – – – – – – – – –
label | 8a6aa75e-5d48-553d-b102-5e9ef49fbe8d |  | note | METHOD:
label | f0c3167d-6bd7-5381-8fe3-43d7b4e3421e |  | note | • Measure
label | 57e01dd4-ce13-5445-8f2b-de1e37be6e3f |  | note | • Visual
label | 6a0aea67-d1fa-5741-9e52-4e3d497105f2 |  | note | – – – – – – – – – – – – – – – – –
label | 34f8de60-219e-5434-9e08-fa22065fad92 |  | note | FREQUENCY: Each pile
label | 384dc97d-5246-5180-9fb8-db077d00cc5a |  | note | – – – – – – – – – – – – – – – – –
label | 20e89be9-7499-5664-aa4c-1aa6951ff23b |  | note | CATEGORY: HP
label | 3211e7f8-57ac-5a84-83f4-de7231dc18f5 |  | note | – – – – – – – – – – – – – – – – –
label | db64ed9b-83c2-5eac-992c-3375022d095d |  | note | RESPONSIBILITY: Nominated Authority
label | 43caab17-7a72-5fdc-b4b8-f9618f690fb9 |  | note | – – – – – – – – – – – – – – – – –
label | 8fd5b646-bab6-5104-9b39-44210d140ce2 |  | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
text | 2b0094f7-efa9-53b7-bee3-fe70277c95fa |  | textbox | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 5.8 Weather Conditions & Evaporation Limits
label | 4ae13755-0459-5a88-862b-b2ec265b2ad8 |  | note | REFERENCE:
label | da60b163-8e44-5513-b514-041d7e9b62b0 |  | note | Hot and/or Cold Weather Concreting Procedure
label | 837243e0-2032-5278-8fb0-18512655f7f8 |  | note | 610.17
label | 495dcee6-6065-53b4-ad86-a1f1d80c5a8e |  | note | 610.17 (a) & (e)
label | 75141da4-fffc-576e-bb8a-01e101f6b2cb |  | note | Table 610.171
label | 9326bd23-5b67-501e-97a9-1a0ec8271e7a |  | note | – – – – – – – – – – – – – – – – –
label | 98598ef7-ea29-5a29-8c7e-817e6935ad69 |  | note | ACCEPTANCE CRITERIA:
label | 799a343f-1b38-520f-8134-012a086119d7 |  | note | • All freshly finished concrete surfaces shall be protected where required from the sun, wind or rain, until curing is implemented.
label | 64ae8e62-55c5-531c-aa46-4e5f71532de5 |  | note | • The temperature of concrete, measured immediately prior to placing, shall not be less than 10°C or greater than 32°C.
label | 5da17b89-0d0a-52e3-b0eb-b801f7d7e379 |  | note | • The air temperature, relative humidity, concrete temperature and wind velocity are measured to determine the evaporation rate of water from the concrete.
label | d7ac17e7-4e97-508e-92c1-41f7111e4535 |  | note | • When the evaporation rate exceeds 0.50 kg/m²/hr apply evaporation retardant at the rates specified on the manufacturer’s TDS.
label | bb4f1306-aa0b-5670-8bfa-7d031abdf776 |  | note | • Record: Required information on the Concrete Pour Record.
label | 0138f79c-efa8-585c-ba68-e0f6b976b926 |  | note | – – – – – – – – – – – – – – – – –
label | d5d7887b-04d7-5c7c-afb9-274f49cace75 |  | note | METHOD:
label | efe53f2c-74c1-5899-a49b-aff7568f3d0e |  | note | • Measure
label | 231c83f2-f1ad-5fb4-822b-101796f8338f |  | note | • Visual
label | e6785d06-da06-5be5-8b13-6bf2cfabebce |  | note | – – – – – – – – – – – – – – – – –
label | c074d7ed-b147-52f8-b849-9e371c8153bd |  | note | FREQUENCY: Each pile
label | 047b7264-e22b-54bb-830a-ea13e5a8b523 |  | note | – – – – – – – – – – – – – – – – –
label | a85730ce-ef27-534f-a464-29cbd462dbdd |  | note | CATEGORY: IP
label | 2b776525-4e6a-5dcd-8047-ccad2afa9bef |  | note | – – – – – – – – – – – – – – – – –
label | 9360dad6-667a-57fb-8e03-754531855cea |  | note | RESPONSIBILITY:
label | 5c07b353-4e98-57f7-9b89-bef30c66c002 |  | note | • Foreman
label | d743607e-3c9e-5708-baed-7068ffc1e981 |  | note | • SE/PE/SPE
label | 6379ad95-c7c8-55cd-ba97-952e5fe11a8d |  | note | – – – – – – – – – – – – – – – – –
label | 70a3e1f6-79b8-5651-b3d7-d0cd19ebfab9 |  | note | VERIFYING DOCUMENTS: This ITP
text | 07515d90-b409-51b8-8ea3-8837206546ec |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.9 Concrete Testing - Sampling Frequency
label | 1382ce67-6442-5c1b-aa61-e326e19ff602 |  | note | REFERENCE:
label | 74328e2d-331e-5997-8f59-d5f4444882d4 |  | note | Site Sampling & Testing Procedure
label | 75e52dc4-202a-54e7-96e5-815be23ee4b6 |  | note | 610.16 (b), Table 610.161
label | bc6492e5-c756-5ead-b454-83a7111cd4e8 |  | note | – – – – – – – – – – – – – – – – –
label | 92a280e0-b343-54c8-91e3-9fb087904179 |  | note | ACCEPTANCE CRITERIA:
label | 1a785b38-c52c-59d5-8af6-a64fd799bd23 |  | note | • Concrete cast in one continuous operation to be tested at a frequency as shown below:
label | 5199c201-07bc-5da1-ad6c-88c62a209bd1 |  | note | 0m3 to 10m3 = 1 sample
label | a689f10f-4bda-582c-9ebb-f7c6c1482eba |  | note | 10m3 to 25m3 = 2 samples
label | 92602b1d-849b-58e9-a91b-013dbed21be8 |  | note | 25m3 to 50m3 = 3 samples
label | cefcecbd-49b9-53dd-a4c4-abc29209cade |  | note | 50m3 to 100m3 = 4 samples + 2 no. VPV cylinders.
label | b9a12f12-b1cb-5d49-a7fa-ddb24c17f29b |  | note | • For each additional 50m3 and additional sample shall be taken.
label | 7dede268-4ff3-5730-b6b5-0ef669c80fac |  | note | • Where the time interval between the end of discharge of one truckload of concrete and the beginning of discharge of the next truckload exceeds 45 minutes, the minimum number of test samples shall be one (1) per truckload of concrete
label | db88e327-3a66-582f-a5d5-a459573de9d9 |  | note | • Each sample shall consist of 1 no. slump or spread test and 3 no. compressive strength cylinders minimum.
label | 6a0cfb67-553c-5fcc-a96c-082b9f5e0d37 |  | note | • Compressive strength cylinders = 1 no. 7 day strength, 2 no. 28 day strength.
label | 65517170-454d-51a7-8f81-2eef058f0aaa |  | note | • Note: Additional cylinders may be required for other purposes such as early strength determination of adjacent piles.
label | 4ce33dbc-6d13-5020-b3fb-1e5e0101db82 |  | note | • Record: Required information on the Concrete Pour Record.
label | bdf0bd54-13af-50a9-a5af-4007b5bf58ef |  | note | – – – – – – – – – – – – – – – – –
label | 87be18f7-a81b-557d-b277-4780894811c1 |  | note | METHOD: Test
label | 3b2f5893-e05f-582d-8c0b-7b5e76629253 |  | note | – – – – – – – – – – – – – – – – –
label | 852eca50-5c93-555b-ab86-258795766bed |  | note | FREQUENCY: Each pile
label | ea8f2c30-c385-5d66-b8f2-9edb55226947 |  | note | – – – – – – – – – – – – – – – – –
label | 54bfc334-b141-5188-81d2-565f61d5c802 |  | note | CATEGORY: IP
label | b5fcb9e3-0d7d-5cde-a2bf-2ff2be3fc568 |  | note | – – – – – – – – – – – – – – – – –
label | 710cdc76-9746-5928-9675-c5180ca05cb4 |  | note | RESPONSIBILITY:
label | 26214e97-442a-57fc-9baf-ba2a926a479e |  | note | • Concrete Tester
label | 67d349a6-8821-5e46-a034-05c84a206983 |  | note | • Foreman
label | 1d8c52c9-e16c-599a-a750-8ebaf021dc8a |  | note | • SE/PE/SPE
label | 6d7f106c-999d-5491-ae16-d0a98809ccf8 |  | note | – – – – – – – – – – – – – – – – –
label | f7732eda-68e9-5186-bbb9-90f1c44c1244 |  | note | VERIFYING DOCUMENTS: This ITP
text | c82d4c33-ea30-5911-8c68-d1709c6646dc |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.10 Concrete Testing - Spread, Passability & Viscosity
label | 303c18a3-aafc-555c-aedf-dcdb9165d8c4 |  | note | REFERENCE: 610.13 (b)
label | 0f5311cd-fc2d-5270-8aaf-fcd70e91fc97 |  | note | – – – – – – – – – – – – – – – – –
label | e6692335-b494-5984-8e42-3a1b7b6ece48 |  | note | ACCEPTANCE CRITERIA:
label | eed3bb58-905c-5e0d-a1c9-6a52bc81abb6 |  | note | • Spread range = 550mm to 750mm
label | 000e0527-af76-584b-86b1-9aab605d80cf |  | note | • T500 = 2 seconds to 5 seconds (to reach a spread of 500mm)
label | 5e9bde99-95f2-5f34-94b2-622908681825 |  | note | • Passability = ≤10mm (aggregate height differential)
label | d796fb8a-3094-541b-a455-03dc12782410 |  | note | • Record: Required information on the Concrete Pour Record.
label | 1bc37562-78b2-5cde-9d30-c02ac544979e |  | note | – – – – – – – – – – – – – – – – –
label | 1261a5c6-4c8b-56d8-b20d-e0af62150bc2 |  | note | METHOD: Test
label | aaa9aca6-cfcc-5ee1-a6ee-82e4af00af55 |  | note | – – – – – – – – – – – – – – – – –
label | 7d37e873-ecb8-5432-9dd1-8ecbf51e63b9 |  | note | FREQUENCY: Each sample of Self-compacting Concrete
label | b0d0dda2-d781-5ce1-8bcd-53504ca3b69e |  | note | – – – – – – – – – – – – – – – – –
label | cd78d7fe-d772-5aa3-a192-42b7cbf83d8a |  | note | CATEGORY: IP
label | 22e1bc46-81d8-575b-9ef3-ffb8ee076f2d |  | note | – – – – – – – – – – – – – – – – –
label | 3163e72a-fb4a-5c06-aa8d-6dd92d9e8314 |  | note | RESPONSIBILITY: Concrete Tester
label | 55964e68-9a0c-5e51-8ef4-3ddf844f409a |  | note | – – – – – – – – – – – – – – – – –
label | ef799eb4-9997-5cbf-99d6-c2fa1cc04a09 |  | note | VERIFYING DOCUMENTS: This ITP
text | c6719e76-32f8-5c24-a0c9-ed771379883c |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.11 Concrete Testing - Compressive Strength Cylinders
label | e22309a8-efd7-5d10-aedc-4165fdbaa8b9 |  | note | REFERENCE: Site Sampling & Testing Procedure 610.16
label | da1614cc-ff53-5d9a-82ff-11182e2a5948 |  | note | – – – – – – – – – – – – – – – – –
label | 3bdd4925-ad2d-556d-8427-df34ed6cd274 |  | note | ACCEPTANCE CRITERIA:
label | cae0acd7-cd78-57dd-a033-b2940e16e295 |  | note | • Correct quantity of cylinders manufactured per sample.
label | 6773aefc-1b63-5003-87b3-36acf215458e |  | note | • Record: Required information on the Concrete Pour Record.
label | 57942b8a-3d0f-5678-a346-19c5be20c6c6 |  | note | – – – – – – – – – – – – – – – – –
label | b8672514-f96e-507d-89fd-a5dd611aa725 |  | note | METHOD: Test
label | b7f6e96e-63a7-507f-91f5-cf308d9de5c6 |  | note | – – – – – – – – – – – – – – – – –
label | 20b7fbfe-7a6f-5c34-b3a1-371f5365e9ec |  | note | FREQUENCY: Each sample
label | 131c288a-3c39-5202-9266-69faf2868d85 |  | note | – – – – – – – – – – – – – – – – –
label | 4ca6b648-9d3a-54f8-b604-cc68911b68ca |  | note | CATEGORY: IP
label | 1f661a58-c6d8-5b27-a06e-338ded7b56a1 |  | note | – – – – – – – – – – – – – – – – –
label | 082603b4-a64b-5353-8469-684876be589a |  | note | RESPONSIBILITY: Concrete Tester
label | 90cc3038-3c79-5108-97b9-ccdf32aac757 |  | note | – – – – – – – – – – – – – – – – –
label | a30a2b2e-373f-538a-86bd-3fcb4dc6e6b0 |  | note | VERIFYING DOCUMENTS: This ITP
text | 6d71efc3-3367-5ed7-8143-c3dea5fed8a4 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.12 Placement & Compaction (Dry or Wet Excavation Conditions)
label | b9bde0a9-e2c0-56bb-a5c9-2f44083d3c51 |  | note | REFERENCE:
label | e920d1f1-481e-559c-9879-17320836f83f |  | note | Piling Quality Procedure
label | a10fdfb0-8200-5717-8b38-16d01aec4caa |  | note | 610.18 (a) & (b)
label | 80dc3c58-7689-56ab-bbce-7295add6fd7a |  | note | 610.18 (d) (i)
label | 9c399a3f-4ff3-5506-a2fa-618e96496364 |  | note | 606.06 (a & b)
label | 1baf149c-76c4-5d03-9720-4da2f518124c |  | note | – – – – – – – – – – – – – – – – –
label | cd5dca6d-abf6-5dbb-875f-c5231b3b35aa |  | note | ACCEPTANCE CRITERIA:
label | b8ed5be6-917f-55ed-8fd1-b2e0dbe69d83 |  | note | • Concrete shall be placed within 24 hours of excavation - where this has not been achieved, the internal wall & base of the excavation shall be cleaned to an additional depth of 25mm.
label | c1a383a0-40c3-5b1e-9b75-146387fd68ee |  | note | • All concrete batches are traceable.
label | 2a18c480-6373-51b0-972d-4f2573bb0310 |  | note | • Concrete shall be placed through either a tremie pipe or concrete pump and not dropped freely from a height exceeding 2m.
label | f9a1b51f-aa43-55c8-84bc-7427d2e4da2e |  | note | • The initial discharge is pumped to waste until a consistent workable mix is discharged.
label | dab8a50c-6537-54a6-8a51-c4201edeed08 |  | note | • The ends of the discharge pipe shall not be lifted off the base of the excavation until a 2m head is created, which shall be maintained until the completion of the pour.
label | 1eba0a67-f756-51a8-97f6-73138a96ebc7 |  | note | • Where a casing is used, it shall be withdrawn with care and at a rate to ensure that the free surface of the concrete is at least 1.5m above the bottom of the casing.
label | 9d39f2c6-377e-58ab-ad7c-65b3fb4e036e |  | note | • Pile height is to be 300mm above the cut-off level (or 400mm in wet piles) to allow for breaking back of sound concrete.
label | 6f866d9c-837c-5ced-b28d-461e43a6f045 |  | note | • Record: Required information on the Concrete Pour Record.
label | 4942db2c-94a3-5c5b-8f03-73d7d8423123 |  | note | • Attach: Concrete Pour Record
label | 0ed615ae-5db2-557c-8143-b152be104781 |  | note | • Attach: Concrete Dockets
label | 489b190e-963b-57fa-92b7-fdd3d627512a |  | note | – – – – – – – – – – – – – – – – –
label | 32b4b13e-3501-5f7c-86c8-5db8b0fac90a |  | note | METHOD: Visual
label | 75b35f67-d095-58a5-a983-ecf8f6a97074 |  | note | – – – – – – – – – – – – – – – – –
label | 5224947d-5a5d-5706-a32a-d30689777d16 |  | note | FREQUENCY: Each load
label | 2da807b5-69ef-5129-b0c4-ef29dac04bce |  | note | – – – – – – – – – – – – – – – – –
label | 5f33d5e9-a7c4-5016-a9c4-75ab44fcf37e |  | note | CATEGORY: SP
label | dc36632e-6146-51d7-9a8a-c93e70fb9c98 |  | note | – – – – – – – – – – – – – – – – –
label | 1aece2e7-4ee5-5058-af7a-7c3fc32a8bd9 |  | note | RESPONSIBILITY:
label | 9cc3dbd6-6995-5b02-9fe3-6d62f54d39ce |  | note | • Foreman
label | ea66409b-3b62-52da-9a48-e9162ebe1ce8 |  | note | • SE/PE/SPE
label | 95a280e8-1e05-5d86-999a-01f56e5d1d5a |  | note | – – – – – – – – – – – – – – – – –
label | f584ae30-c695-5e36-9405-42dc8fdfb163 |  | note | VERIFYING DOCUMENTS: -
text | 037ce166-0947-5186-b04f-ab15fa2cf586 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.13 Surface Finishes
label | 54b23332-f6d2-58c8-bdb8-2cfcd6d95ce9 |  | note | REFERENCE:
label | 28755c5a-1ab9-5660-a909-6ee2ece84536 |  | note | IFC Drawings
label | 2c6ab414-5ac8-521e-a7fa-9d648a772315 |  | note | 610.31
label | 61b45c5f-b92e-5289-ad93-00007c9f43eb |  | note | 610.20
label | 6024488d-5a47-52f7-924e-e50e5d6932b3 |  | note | – – – – – – – – – – – – – – – – –
label | a290f02e-9011-54c9-9e13-3687b5e78242 |  | note | ACCEPTANCE CRITERIA:
label | c4f963cc-0787-5bc2-84a7-53534be4b2d9 |  | note | • Surface finish as per IFC drawings.
label | cd9eb635-5653-5508-97c9-29ab62c51889 |  | note | • Where surface finish is not detailed, the VicRoads class finishes will apply as per 610.31.
label | 9e557e50-6e31-5351-90b3-a39aeb7319ab |  | note | • Construction joints shall be roughened in locations shown on the drawings - any proposed changes to construction joints shall be subject to approval from the Nominated Authority.
label | c1be53e4-f452-5051-823d-c98efdfcde57 |  | note | – – – – – – – – – – – – – – – – –
label | 4d56bedb-05c3-598d-88b0-d2f790f7a463 |  | note | METHOD: Visual
label | dcd67dd7-5c6f-52e2-aa14-6262c9d22380 |  | note | – – – – – – – – – – – – – – – – –
label | 5b42095c-06d5-5970-a086-c553e74a1c79 |  | note | FREQUENCY: Each pile
label | 58216b22-1f28-5631-8176-833e4537e0d3 |  | note | – – – – – – – – – – – – – – – – –
label | 64f6bf28-96df-56c2-bd8a-5c653cda82d5 |  | note | CATEGORY: IP
label | b29802c0-88a4-500f-80cb-6dc0068865ef |  | note | – – – – – – – – – – – – – – – – –
label | 5b7a1df3-5357-51e3-9629-095e3014d68a |  | note | RESPONSIBILITY:
label | 416d0cdc-a0fe-52f7-94d3-bcda9fc58b6b |  | note | • Foreman
label | 78ce9bba-778e-56dd-9af8-678555530bf7 |  | note | • SE/PE/SPE
label | be0914e2-d937-5f0d-8091-e7b52a85b66b |  | note | – – – – – – – – – – – – – – – – –
label | fe398dd9-dcca-5197-b23e-a27b7827af03 |  | note | VERIFYING DOCUMENTS: This ITP
text | d70f9596-c0f5-5d99-aa33-031038e5e544 |  | textbox | Date Completed:
checkpoint-group |  |  | section | Post-construction Activities
checkpoint-status |  |  | checkpoint | 6.1 Pile Trimming
label | 57ac4ef7-3180-5f93-a597-68aaf4004dd1 |  | note | REFERENCE:
label | 77cb3b31-38f0-511d-abe5-3886d87ac2e9 |  | note | IFC Drawings
label | 6328244c-0eb1-5887-9925-2e1a2e30562a |  | note | AS2159 Clause 7.2.2 - 3
label | 83400853-922c-580f-906d-09bc355cd34b |  | note | 606.06 (a & b)
label | f185fb5f-52cf-572f-97fc-da463f57c461 |  | note | – – – – – – – – – – – – – – – – –
label | 0967324a-56da-5304-bfa8-00fcfe3f4d42 |  | note | ACCEPTANCE CRITERIA:
label | eac07fbf-ad08-5c3b-aa7a-c7c5fb225336 |  | note | • Piles shall not be broken back until a minimum of 24 hours after completion of the placement of concrete.
label | ce62f0c3-820b-50f4-8157-a18511f8ad2b |  | note | • Care shall be taken to ensure that the full cross-sectional area of the pile is at the required RL without any cracking or damage
label | a6aad965-612a-5db0-b51d-360cb78121f9 |  | note | • Any weak or damaged concrete shall be removed back to sound concrete.
label | 151dce38-db41-55ae-9b07-eeb5f414e78d |  | note | – – – – – – – – – – – – – – – – –
label | d72d7461-58e5-5480-822a-23bf5b7f172b |  | note | METHOD:
label | 66f35c34-0d3a-568c-a1f9-a8bc96dd55b5 |  | note | • Measure
label | 43017313-852a-5c9f-bfb2-b0e19d9dba5b |  | note | • Visual
label | 621871e5-c198-5791-b7a6-c2a4fa792f51 |  | note | – – – – – – – – – – – – – – – – –
label | 19280a38-6c64-5a91-bb5b-42860b9bdb9a |  | note | FREQUENCY: Where applicable, each pile
label | 7a857f0e-001a-5013-ad5b-6fef219c49db |  | note | – – – – – – – – – – – – – – – – –
label | eb00e354-43c7-5564-b1e7-ef4c7061fd71 |  | note | CATEGORY: IP
label | 8e307f85-9399-57b1-99e4-f1a3cf1f901e |  | note | – – – – – – – – – – – – – – – – –
label | 12cce601-0234-5f90-94f1-5f5b110f2207 |  | note | RESPONSIBILITY: SE/PE/SPE
label | dbf961a5-1034-50a6-9e28-33eb80fee433 |  | note | – – – – – – – – – – – – – – – – –
label | 9f509c76-b16a-5cd3-a442-c444f76fbcbf |  | note | VERIFYING DOCUMENTS: This ITP
text | a6a5ec34-0f1c-5311-8404-f6a0870a2dd6 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 6.2 Compressive Strength Test Results
label | 018b039f-a339-5a07-a183-a13207ec9921 |  | note | REFERENCE:
label | 3d2f4a8a-f69c-5639-8981-e093765e1b2b |  | note | IFC Drawings
label | a55c7d51-a36b-5d5c-ae45-1e49a14cdded |  | note | Table 610.05.051
label | 20283e48-23f9-567c-8bd7-0f0db228e924 |  | note | 610.16 (g)
label | 19507a1e-2f45-57a6-aa9a-3bbc068ecf43 |  | note | – – – – – – – – – – – – – – – – –
label | 37e28c28-67b4-5e35-9ec2-e8e7d8199060 |  | note | ACCEPTANCE CRITERIA:
label | 9c9bc6bf-4609-5c13-8a10-9e82e8de1128 |  | note | • 7 day compressive strength to comply with table 610.051 for early indication that the strength is tracking correctly.
label | d404a19d-6b3b-5ec1-bd77-3a5f5e0acad5 |  | note | • 28 day compressive strength (average of the 2 no. cylinders) per sample comply with the design strength.
label | a2c58583-8ee6-5c47-9229-7452c82dd4ab |  | note | • Note: 1 of the 2 no. 28 day cylinders per sample may be as low as 90% of the required strength, so long as the average meets the required strength.
label | cab6a59d-97ec-5d00-a5fa-6a94b18cdce1 |  | note | • Attach: Compressive Strength Test Results
label | e8685b9d-b648-50b9-b42e-fdc9355d53a3 |  | note | – – – – – – – – – – – – – – – – –
label | 01e3c3c3-f425-5e44-a519-ad5c1be5ac29 |  | note | METHOD: Document Review
label | ee056bc5-698c-508f-b8f8-bb143bb50893 |  | note | – – – – – – – – – – – – – – – – –
label | 76a92605-10e7-523e-8544-32491ba28c3b |  | note | FREQUENCY: Each cylinder
label | 99e391c5-39f3-5821-8619-e30c9a210363 |  | note | – – – – – – – – – – – – – – – – –
label | 667fe7b3-1bb7-5a41-b5f0-7c45ca3d2ea1 |  | note | CATEGORY: IP
label | 47e69056-4475-58b5-826f-a024c7be5973 |  | note | – – – – – – – – – – – – – – – – –
label | 7b0c03d5-e352-579b-972b-12677865986c |  | note | RESPONSIBILITY: SE/PE/SPE
label | aa0536f2-da3f-5268-919b-deba77fb7345 |  | note | – – – – – – – – – – – – – – – – –
label | a212881b-6a5d-5d29-95bf-dc31525feb4e |  | note | VERIFYING DOCUMENTS: This ITP
text | 79778218-cdc8-514f-bdf9-8ec579ff9b34 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 6.3 Pile Integrity Testing
label | 826b09e2-5acf-5937-a427-c24c62581328 |  | note | REFERENCE:
label | 178fe60f-99d5-56a9-b9d5-f83fd0fa29c9 |  | note | 606.07 (a, d & e)
label | 0c80ff81-7c06-5070-9f44-426a57f98e41 |  | note | AS2159 Clause 8.8
label | a67840f8-85cb-5fa5-9c4f-48ecbbf35da3 |  | note | – – – – – – – – – – – – – – – – –
label | 2115b309-6921-533e-8e50-119400ae4b79 |  | note | ACCEPTANCE CRITERIA:
label | 363adf33-a47f-5e3b-a030-11f9370a51df |  | note | • Pile integrity testing shall be conducted after the concrete strength has reached 25MPa but not less than 7 days from casting.
label | b9c9f5b4-f236-57da-a7ad-2314cf5b9832 |  | note | • Cross-sectional area = ≥95%
label | ddd2fff0-5d55-55c6-b96d-9000b6c4341f |  | note | • If any test fails, all piles shall be tested.
label | 87cdf53a-6968-5dd8-ba4a-4d8a7663e5da |  | note | • Attach: Pile Integrity Test Report
label | 8675b9ca-caf4-5895-a256-0b760b0a4439 |  | note | – – – – – – – – – – – – – – – – –
label | 64b3f293-c8fe-5bd5-a181-9edfc2e05a97 |  | note | METHOD: Document Review
label | 31de156a-3c3b-5a8b-b97a-4d3000ca4ac3 |  | note | – – – – – – – – – – – – – – – – –
label | db5037ec-e767-5eac-85b6-34a9be1741c8 |  | note | FREQUENCY: Piles #1 - #6. Reduced to 1 test per 3 piles if the first 6 tests pass
label | 73e42e9a-f2d7-5a88-91e1-14a9a0a000d7 |  | note | – – – – – – – – – – – – – – – – –
label | 19353df2-86b2-5bed-b2ac-8053c33a33e3 |  | note | CATEGORY: IP
label | cdb4b066-07b3-5569-9554-29997dd48a90 |  | note | – – – – – – – – – – – – – – – – –
label | ec0086b0-eaf0-5608-bbe9-91f7f455c94e |  | note | RESPONSIBILITY:
label | 5feb6007-5c92-5779-ab27-ebfc1e5b1b4f |  | note | • Testing Consultant
label | 13aaad43-ab15-525d-b123-32132ce3b5de |  | note | • SE/PE/SPE
label | b201d981-87af-55cf-815e-97ac3b1b35c6 |  | note | – – – – – – – – – – – – – – – – –
label | 6d442335-0a49-5934-b136-8b5168f9c7a1 |  | note | VERIFYING DOCUMENTS: This ITP
text | 555c01ab-f524-5c8b-bf0b-91a8a97f5338 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 6.4 Static Load Testing
label | 50c78768-997f-5a34-ac91-dad527fa6f7a |  | note | REFERENCE:
label | f1f80288-9bfe-5312-978e-b251b1957cf5 |  | note | IFC Drawings
label | e5eb585e-983c-5c68-8052-3a36d4c639ae |  | note | 606.07 (b, d & e)
label | 917e537a-d454-5cc9-90ce-e9ca60034e51 |  | note | AS2159 Clause 8.4
label | 9ae5e0e0-ea3d-53ea-9e2f-bffaab8d4207 |  | note | – – – – – – – – – – – – – – – – –
label | bdd66bdc-3792-580b-a277-1a53b8381fb6 |  | note | ACCEPTANCE CRITERIA:
label | 823fe2c8-5b4c-5baf-90c0-bedfd7e38c0d |  | note | • Static load testing to be conducted on the designated piles as shown on the IFC drawings after the concrete strength has reached the 28 day compressive strength.
label | 314c269f-dabf-5cf5-9b63-e2dd09d9ea61 |  | note | i. Displacement vs Time Graph = linear or decreasing rate of creep
label | c4b9c380-5026-5aec-b94f-5d98d27a89e4 |  | note | ii. Creep rate = <2mm / log cycle of time at the test load
label | 3bc6b4a0-3194-5acb-abe1-df13493c0087 |  | note | iii. Maximum pile settlement and lateral displacement at the design load = < values on IFC drawings
label | 67b30180-469a-5906-b41f-72d0f1bd165c |  | note | • Attach: Static Load Test Report
label | bc37be61-31ba-5a2f-b31b-aa5718ae65a3 |  | note | – – – – – – – – – – – – – – – – –
label | 65789b53-aad5-5164-9b45-d54ef6d1e2c0 |  | note | METHOD: Document Review
label | a9b6920c-80c2-5a6a-b47b-77b857a83bb1 |  | note | – – – – – – – – – – – – – – – – –
label | 7e156a4b-7472-5860-8917-bf6eb08ac747 |  | note | FREQUENCY: Where applicable, as shown on the IFC Drawings
label | 4e2ed3f8-e41a-5271-84a7-2422fc5c123e |  | note | – – – – – – – – – – – – – – – – –
label | cc194558-c95d-56de-b720-fe593387e962 |  | note | CATEGORY: IP
label | ddba2631-47e9-5658-b192-21f95203141c |  | note | – – – – – – – – – – – – – – – – –
label | fb3931d0-472e-55e2-8048-3f98ebbecb71 |  | note | RESPONSIBILITY:
label | 031dbfbd-1a66-563b-b2c7-272075a743b1 |  | note | • Testing Consultant
label | be480f71-62d4-5fb8-b72c-86f87041d877 |  | note | • SE/PE/SPE
label | 8d0439c2-1728-5571-9f4b-730a69361077 |  | note | – – – – – – – – – – – – – – – – –
label | b77062a7-d772-5b49-9338-aa876453f6af |  | note | VERIFYING DOCUMENTS: This ITP
text | e2d5a759-2266-5135-9a5e-fbf28a44bd56 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 6.5 Dynamic Pile Testing
label | 6783e93d-db0e-5111-936d-89b29a4d5829 |  | note | REFERENCE:
label | 905a8cbc-70f9-5811-9e9e-7ed5be7eaa9a |  | note | 606.07 (c, d & e)
label | 4148c449-24e6-5f17-a91f-b0eb878cf391 |  | note | AS2159 Clause 8.7
label | 0b7523a3-9c64-57da-832d-544bbc8c08bf |  | note | – – – – – – – – – – – – – – – – –
label | 394320c4-7c38-5d87-8f40-ef68fbcbb160 |  | note | ACCEPTANCE CRITERIA:
label | 9eda13c5-cf5c-5df6-a846-73c3d13bccca |  | note | • Dynamic pile testing shall be conducted after the concrete strength has reached the 28 day compressive strength.
label | b77086dc-caf0-5267-9b9b-d4ae7270a282 |  | note | • Measured Ultimate capacity = ≥ values on IFC drawings
label | 57c1eab3-52bc-5978-b49f-8dcf05a90a01 |  | note | • Attach: Dynamic Pile Test Report
label | a85b13aa-9071-5e29-b755-b246f17f43d3 |  | note | – – – – – – – – – – – – – – – – –
label | f04bab84-378b-5a98-8e27-bd22a600df67 |  | note | METHOD: Document Review
label | a4f3cee2-08b8-56cd-a28b-6a3fe2502061 |  | note | – – – – – – – – – – – – – – – – –
label | 62a19c15-e109-5b71-a1aa-ec5bf030ef88 |  | note | FREQUENCY: Where applicable, 1 test per pile cap / abutment, where pile toe RL varies >2m from the test pile. At least 1 test per 10 piles
label | aa49f960-b032-55b4-9aa9-1b331b2e4908 |  | note | – – – – – – – – – – – – – – – – –
label | ad6add9a-f414-5a2f-9260-3ab51cc518c4 |  | note | CATEGORY: IP
label | 84f10c7a-a1e3-5614-bd8d-c31687d956d4 |  | note | – – – – – – – – – – – – – – – – –
label | 38fd1f3f-c3c2-5b65-86cb-9982681e33e2 |  | note | RESPONSIBILITY:
label | dd87504c-d29b-5ae8-958f-90adcfab9ebc |  | note | • Testing Consultant
label | 1de3a340-ac6b-5754-88b7-63568f37beed |  | note | • SE/PE/SPE
label | 7023f29d-8eff-5bff-b28d-b16cb2f1ccc5 |  | note | – – – – – – – – – – – – – – – – –
label | ac175a20-c97d-5d33-a317-d9165b551d22 |  | note | VERIFYING DOCUMENTS: This ITP
text | 642ad420-07a5-522f-99af-041b1cf7fc2f |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 6.6 As-built Survey
label | 4cdd0235-2ab6-53b4-b53d-619a25c432a4 |  | note | REFERENCE:
label | 004e708f-0dca-50ae-9204-6d57ec2fe97a |  | note | IFC Drawings
label | 0f4fbd8c-dfe2-5b38-911c-1da8a2113963 |  | note | 606.08 (a - c)
label | 0e1fe053-7f9c-52c6-93b2-dc4f0736c41a |  | note | AS2159 Clause 7.2.2
label | 4b8c1096-cc44-528e-bd6d-bfbc72fe463b |  | note | – – – – – – – – – – – – – – – – –
label | 8e9bf5c1-77d7-57a3-9578-81e60ddc3f1e |  | note | ACCEPTANCE CRITERIA:
label | 53e733e2-ca49-51c4-8994-e11c8a570709 |  | note | • The following tolerances apply to piles:
label | 3c90fde0-514c-5893-98c4-f20bfbc80bae |  | note | i. Pile head plan location = ±75mm
label | a50801ab-9431-5776-9a33-e09d2ad1b631 |  | note | ii. Variance from vertical or rake = 1:100
label | eed0d59e-fb38-53ae-854e-12c3eeab07e3 |  | note | iii. Irregularities in straightness = 1:100
label | c096ed3d-29c5-5737-b9af-98a634078ccc |  | note | iv. RL = ±25mm
label | d86e1be4-38a6-5ad0-a8ac-1f7566d930da |  | note | • Attach: Survey As-builts / Survey Report
label | 49801844-e8d1-5daa-b70f-26434b192901 |  | note | – – – – – – – – – – – – – – – – –
label | 7485bfdf-aeb8-5a92-8814-26c7fc371eaf |  | note | METHOD: Document Review
label | aa3b6c8e-4337-5778-9fb9-e0c752f9c3f0 |  | note | – – – – – – – – – – – – – – – – –
label | 83339143-0ed4-5ed2-b638-39feffd3cc13 |  | note | FREQUENCY: Each pile
label | 573e4047-7f15-588a-9ad8-8febb2ef9a6d |  | note | – – – – – – – – – – – – – – – – –
label | e11eff2c-70ee-5516-8cd9-21f16ab2e446 |  | note | CATEGORY: IP
label | 4db3adef-c0fb-5084-9ef9-6d1c8f868dce |  | note | – – – – – – – – – – – – – – – – –
label | 5df88f8a-aa8d-59b7-af48-74c9f5f5d606 |  | note | RESPONSIBILITY:
label | 02344539-6ddb-565d-8de2-0a04ea56130f |  | note | • Surveyor
label | 1e8695b6-e59d-509b-983b-2f53608e8330 |  | note | • SE/PE/SPE
label | 26d2248d-17a8-53dd-b8d9-fcbaaa58928b |  | note | – – – – – – – – – – – – – – – – –
label | 73b814fd-49c2-52f6-8c00-78dab99430b8 |  | note | VERIFYING DOCUMENTS: This ITP
text | 38988427-198f-59aa-a768-7fcf0b9be95e |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 6.7 Non-conformance Report (NCR) Closure
label | 172fefa4-2020-53c9-8a46-50f0eb5b4e2c |  | note | REFERENCE: MRPA Quality Management Plan
label | 5be0cf20-429d-52c2-b9a1-f4541d32a22e |  | note | – – – – – – – – – – – – – – – – –
label | bd862dc9-136c-5aeb-9240-c21a8fc96cc2 |  | note | ACCEPTANCE CRITERIA: Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed.
label | 9a714d65-ded6-50c6-853d-825813251398 |  | note | – – – – – – – – – – – – – – – – –
label | d8900b95-7084-5c47-9b22-1986774213d6 |  | note | METHOD: Document Review
label | f3f15852-56f3-5611-ac87-ac264dc08296 |  | note | – – – – – – – – – – – – – – – – –
label | 466ba696-9e22-51b5-b8af-458a049ceb5d |  | note | FREQUENCY: Once, prior to closure of this lot / element / Work area
label | b7c7420e-bc68-5ec6-bf80-966d3a395c88 |  | note | – – – – – – – – – – – – – – – – –
label | 56ac734d-7949-54c8-9d09-e8f6787b8047 |  | note | CATEGORY: HP*
label | 4adf119d-67f3-53a7-ac4d-d7b5ff5f396d |  | note | – – – – – – – – – – – – – – – – –
label | 34936249-80e7-5026-aaa8-30a4773fae3e |  | note | RESPONSIBILITY: SE/PE/SPE
label | 7a240b43-c51a-5c13-ba4f-fee782441a98 |  | note | – – – – – – – – – – – – – – – – –
label | 53b7aafe-c15b-51f4-b76b-3148a40fb715 |  | note | VERIFYING DOCUMENTS: This ITP
text | fb3248d7-dc7b-5bb9-ad86-f3d608eb7e36 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | Metropolitan Roads Program Alliance Final Inspection
label | 3c51eba2-4d52-5331-8f96-d11d9fd4b388 |  | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
text | 7cae7b1d-daad-5634-bab5-092af6643f14 |  | textbox | Name:
text | 6278deb0-64b7-5254-9809-24d46396795b |  | textbox | Position:
text | 9f617c41-f000-5ffc-a960-c0b823d39d37 |  | textbox | Date Completed:
holdpoint |  |  | signoff | Sign ITP
checklist-sectioned |  |  | checklist | ITP-CIV-CAMMS-Rail Delineation Temporary Fencing Rev 0 | itp |  |  |  | Yes | ITP-CIV-CAMMS-Rail Delineation Temporary Fencing Rev 0 | 5270c116-1c67-40b5-8e34-ca23d9c50e84
checkpoint-group |  |  | section | 1 - Referenced Documentation
checkpoint-status |  |  | checkpoint | 1.1 - Referenced Documentation
label | 0086e2b0-069c-589a-9be8-ffff175534b6 |  | note | Reference - IFC Drawings, L1-CHE-STD-005, L1-CHE-STD-025
checkpoint-group |  |  | section | 2 - Preliminaries-Materials
checkpoint-status |  |  | checkpoint | 2.1 - Concrete
label | 09c1327a-14b7-5d30-9e4f-2b0d44c01611 |  | note | Frequency - Each Mix
label | 7f42c11d-e549-5e8a-a2cb-3378f5b5ede6 |  | note | Acceptance Criteria - 32MPa concrete to be used as per IFC drawings.
label | 6f09df4d-6fd3-5751-97bf-b925c7b93f23 |  | note | Reference - IFC Drawings
label | e5584958-1795-500e-9983-0b92ba017ff7 |  | note | Inspection / Test Method - Document Review
label | 95c7e122-33b9-5aa5-bfe4-f33eaf68e18d |  | note | HP
label | ce5a7141-ae67-5066-9f75-d2ef4d9140c4 |  | note | Responsibility - SE/Site Supervisor
text | 412a98b8-2967-5cb4-8448-614ec314ab0e |  | textbox | Date Completed:
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.2 - Steel components
label | 163316ae-2a48-53f9-b716-a782f6800f6b |  | note | Frequency - All elements
label | f1df3b1d-11d2-564f-a653-a30d8522ab62 |  | note | Acceptance Criteria - All Steel must comply with Australian Standards. Steel section sizes must be checked on site. Steel posts to be CHS with a grade of C250
label | 7985a2e7-99a8-5554-89ad-a41ac7d1d649 |  | note | Reference - IFC Drawings, AS41000, AS1163
label | 4be22392-8002-5946-a48d-b249d02f57e3 |  | note | Inspection / Test Method - Document review, Visual and Measure
label | faaef798-13dd-51c1-806c-c750a31db5c5 |  | note | IP
label | 761fde72-2897-5272-81de-2495ff94b6eb |  | note | Responsibility - SE/Site Supervisor
text | f789bffb-9db8-5405-920f-4f533fe109ef |  | textbox | Date Completed:
checkpoint-group |  |  | section | 3 - Preliminaries-Documentations
checkpoint-status |  |  | checkpoint | 3.1 - Excavation works
label | 1b981071-dc0b-5dfc-b34f-ab4747cab6a6 |  | note | Frequency -
label | 2ba09585-1337-54bc-9213-e39f142c743b |  | note | Acceptance Criteria - Excavation for post foundation must not undermine track and comply with PTDT requirements.
label | 6d1c9ef3-ade0-56b3-92fa-f84b95bc3f18 |  | note | Follow asset owners guidelines for work around their service.
label | 75b96e0a-5c62-5791-af6f-273775b2e82f |  | note | Excavation must use Non Distructive Digging in the rail corridor
label | c8d3de30-4275-5c0c-ab66-126fe514dc82 |  | note | Reference - IFC Drawings, L1-CHE-STD-005
label | a092c613-d32b-5c58-b5a9-50661a135510 |  | note | Inspection / Test Method - Visual
label | 982b54c3-a0b9-5bd0-90cb-793f0f91d498 |  | note | IP
label | ba1447fe-e6b8-539a-b40d-50b7e737dab7 |  | note | Responsibility - SE/Site Supervisor
text | b9aa6b10-a341-5192-bc6a-e3b7422b8cdd |  | textbox | Date Completed:
checkpoint-group |  |  | section | 4 - Pre-construction / Pre-installation Activities
checkpoint-status |  |  | checkpoint | 4.1 - Survey Set-out
label | 33dfe856-f3c6-54c7-8e2f-daa109bb89c9 |  | note | Frequency - Each element
label | 55cd3fed-ec0f-5726-b22d-b0cc194c92b0 |  | note | Acceptance Criteria - Survey to set out the following but not limited to: existing services, post locations, refuge bays
label | fb87e010-88b1-5d95-b57d-13f4767e19fe |  | note | Offset checked against the running edge prior to installation of posts.
label | 978ea0ca-24e0-55d6-be9b-11f219218b76 |  | note | Up track: Minimum offset 2135mm from centreline of track. (1285mm outside edge of track - Engineer to verify with timber jig template)
label | 3aefea3a-379f-5ed7-8971-ea72c58219af |  | note | Down track: Minimum offset 3172mm from centreline of track. (Utilise existing posts - Engineer to verify with string line between posts)
label | 3111979b-40ac-58ff-98b3-41f2f0d792a0 |  | note | Reference - IFC Drawings
label | fd6b2e49-8a3f-51c0-8ea7-758c5a819481 |  | note | Inspection / Test Method - Measure,Visual inspect
label | 620d5139-ada9-50bb-ad4b-fb4c136d1dd0 |  | note | IP
label | e6bec084-f1d8-50e3-8a13-f38ee96e2352 |  | note | Responsibility - Surveyor, SE/PE/SPE
text | cc004d4b-f8da-52fd-a71b-87e846ba37a7 |  | textbox | Date Completed:
checkpoint-group |  |  | section | 5 - Construction / Installation Activities
checkpoint-status |  |  | checkpoint | 5.1 - Ground Conditions
label | 3b647908-ad1f-5138-97cb-9c07bf0f995a |  | note | Frequency - Each post
label | 014de3ca-70d5-5024-946d-e6b16d0dcf19 |  | note | Acceptance Criteria - All post foundations to be inspected by the site team prior to installing the posts. All foundations are to be free of water and loose material.
label | 5d503c7f-fe35-5418-b162-f7b4da3317cd |  | note | Reference - IFC Drawings
label | 015207d6-4103-5ace-86b5-2631625fe05d |  | note | Inspection / Test Method - Visual
label | 3d33ff62-2377-5851-afd9-6b4c45abdcbe |  | note | IP
label | f125ab25-a848-5ed7-8626-2a0e9a132c80 |  | note | Responsibility - SE/Site Supervisor
text | 2dca586f-780e-5a82-9464-3cd6e089f878 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.2 - Post Foundation
label | efbee789-59b3-5e81-be4e-b85286d6dbd2 |  | note | Frequency - Each footing
label | 758a26d3-3759-5fe7-90cc-914a2e714284 |  | note | Acceptance Criteria - Up track (Alongside central pier): - 300mm Dia, - 2000mm Depth, - 2700mm Typical Spacing
label | 8bf885f8-5906-5a7f-a69e-5d708a83cef6 |  | note | Up track (Outside central pier): - 300mm Dia, - 800mm Depth, - 2700mm Typical Spacing
label | 58d8f381-f8db-5729-acea-384d0deced60 |  | note | Down track: - 300mm Dia, - 800mm Depth, - 2700mm Typical Spacing
label | 6162211d-6853-5d34-b78d-cc140ade841f |  | note | Gates: - 350mm Dia, - 1400mm Depth, - 1350mm & 4000mm Spacing
label | 53d8b440-a441-5108-98b8-4216cc55b442 |  | note | Reference - IFC Drawings
label | 22c9d0ab-759a-5578-a4ad-f2471910d875 |  | note | Inspection / Test Method - Measure
label | 53160ea6-6be8-56ca-9108-9fda89a25a30 |  | note | IP
label | ef38cdb4-0a89-504c-a2a2-cf1885f81ee8 |  | note | Responsibility - SE/Site Supervisor
text | 1b827650-a385-5aae-945c-13bc5e4407f3 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.3 - Post Installation
label | 6879d564-32d7-537a-8c91-6a279cbbe56f |  | note | Frequency - Each post
label | ef9a6d0f-f836-5e7c-9a21-f85263fae68c |  | note | Acceptance Criteria - Up track: Minimum offset 2135mm from centreline of track. (1285mm outside edge of track - Engineer to verify with timber jig template)
label | b7ff9f17-187a-54de-bd12-ef5091eb8aa4 |  | note | Down track: Minimum offset 3172mm from centreline of track. (Utilise existing posts - Engineer to verify with string line between posts)
label | 34ce9ac0-b48f-5fa0-aa81-6d8261e4ec3a |  | note | Maximum post spacing to be 3.1m
label | 326cc269-9341-58b1-bcf5-de497b000c4a |  | note | Two spans at 1350CTRS at the end and at Refuge bays.
label | 6a8af9b1-34c1-5c24-acdd-7d87fdde5bc3 |  | note | Max. post height 1800mm above ground level.
label | ac562a8c-2048-56a3-b239-1621c82fc825 |  | note | Vertical Tolerance: ±20mm from the design line.
label | 0e784094-747c-52ec-b837-1a616ee0520d |  | note | Reference - IFC Drawings, L1-CHE-STD-005
label | cc6f6ece-ce87-5c13-a6e5-692d239898b3 |  | note | Inspection / Test Method - Measure
label | c36e509d-350e-5704-88f4-cb17721fb240 |  | note | IP
label | 30eaa3a9-5ca2-5698-bb46-48207b2da5a4 |  | note | Responsibility - SE/Site Supervisor
text | 963ae305-28be-5f09-b696-9e7a75d16deb |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.4 - Chain Wire Mesh Installation
label | 470ab7db-2b49-5b02-9fe4-02b3b333e558 |  | note | Frequency - Each element
label | 3f0a80b4-ec1a-5df5-9044-740d00b3628c |  | note | Acceptance Criteria - Chain-wire mesh 1800x50x2.50 to be fixed to fence post with tie wire.
label | 8315e12e-9191-575e-b5a7-7e120c08451f |  | note | Chain shall be tightened and securely fastened to posts at max. 400 crs and tension wires at max. 500 intervals with 2.5 dia. galv. tire wire.
label | a1963063-b220-58d8-af20-6354e3e91caa |  | note | Reference - IFC Drawings
label | 24e24fa4-1a60-5e7e-926f-e74dc01bb110 |  | note | Inspection / Test Method - Visual
label | b530c5ab-ff4f-5c1b-89b1-5f1de151cdeb |  | note | IP
label | 2f55e57f-79f9-501f-ad09-218d99a5bd74 |  | note | Responsibility - SE/Site Supervisor
text | d68013c9-1a71-5296-bd68-d22d2ea49c5a |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.5 - Bracing
label | 160a48ed-146e-5ede-88ad-dfb7d85c1a2b |  | note | Frequency - Each element
label | 72f490a6-fdc7-5a68-b6f7-1ad95fbc200e |  | note | Acceptance Criteria - 48.3 X 4 CHS brace at end bays and corners fixed each end via approved proprietary post and rail clamps.
label | 9a35470b-0d07-589d-be00-ee119a12c6c9 |  | note | Bracing to be installed on both sides of the fence at the fence corners
label | 823c0a41-ffb2-5b15-b081-f88bb856b31a |  | note | Reference - IFC Drawings
label | c60ae786-ae67-5b21-8088-200ff7d41fb5 |  | note | Inspection / Test Method - Visual
label | ebb5177b-7c2a-5174-9eeb-9c870a1c0e7e |  | note | IP
label | 77979268-1229-55a9-8d55-37d9cba713b6 |  | note | Responsibility - SE/Site Supervisor
text | b38a3644-2fd0-5ceb-88d0-6f08a87c8647 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.6 - Refuge Installation
label | 4ae06e8b-772b-52ef-8d69-3688e2b65f20 |  | note | Frequency - Each element
label | e76a52b9-fa80-58c4-8041-b854be1496c4 |  | note | Acceptance Criteria - Refuge Access to only open from track side.
label | b87f7d02-caa0-59a3-b292-4c783b9259aa |  | note | No chain wire mesh to be installed at refuge access.
label | 879f7031-7787-5232-8719-f1ec8b8582f9 |  | note | Refuge Access to be located maximum 10m along down track and staggered from up track refuge.
label | 70b41c8a-2abc-5a05-87a9-194eaa26edb3 |  | note | 50dia PVC pipe push out bars to be installed. PVC tubes to be pushed off from track side only.
label | 7179bcef-ccff-5ca7-8e87-f1ebeffce2f8 |  | note | Reference - IFC Drawings
label | 1288de59-4202-570b-961c-856e89717308 |  | note | Inspection / Test Method - Visual
label | 32b970e0-f7e5-5784-a288-b81d8a2f9d61 |  | note | IP
label | a654e461-afbf-5895-baa7-92e8a8ba9d2d |  | note | Responsibility - SE/Site Supervisor
text | 48369f25-0869-5c59-816e-c17790fc45c6 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.7 - Refuge Signage
label | 673c09e5-862e-5d2c-98ba-6413e340a8d9 |  | note | Frequency - Each element
label | e5000628-cad0-5684-9b91-87b70291c218 |  | note | Acceptance Criteria - Sign shall be installed on fence half way between refuges indicating distance to adjacent refuges. Max size of signage to be A3 or smaller (297mmx420mm MAX)
label | d9388aaa-5621-538a-ae34-b3ddcc1877fb |  | note | Reference - IFC Drawings
label | 79acefc3-1e3a-5e2d-996c-8ef68c740bd9 |  | note | Inspection / Test Method - Visual
label | 562ff33e-5c20-5f4e-8605-12fb6b095923 |  | note | IP
label | 447301e4-8c61-5df6-8d57-660875cfe6de |  | note | Responsibility - SE/Site Supervisor
text | 6fcb30fe-1d2e-54c2-a7ad-bef5aef2b176 |  | textbox | Date Completed:
checkpoint-group |  |  | section | 6 - Post-construction / Post-installation Activities
checkpoint-status |  |  | checkpoint | 6.1 - Fence Height and Track Clearance
label | 47a120ce-b7f4-5aeb-8dee-4e13d065602d |  | note | Frequency - Each lot
label | cc40d2a0-a501-50ac-99dd-416b2503904e |  | note | Acceptance Criteria - Posts are to be checked for verticality and ensure offset is not less than required from near face of post to centreline of track or as shown on alignment drawings.
label | 76338719-8d67-5316-924e-11c7d1e7978a |  | note | Reference - IFC Drawings
label | 47871499-9815-5917-8b1e-f62d11d6a238 |  | note | Inspection / Test Method - Measure
label | 2162d943-628c-57b2-b695-d9436c46ee02 |  | note | IP
label | 9e3e266f-0a95-59d9-9026-87dc8414f9de |  | note | Responsibility - SE/Site Supervisor
text | 0a653097-3e0f-5e7d-b7ac-f6f5fb3b3314 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | Final Inspection
label | 2d995c11-3f8d-511c-867e-e8a9a98b9228 |  | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
text | d5b9598d-5fe5-5e89-a571-b32eaa3c0aa3 |  | textbox | Print Name:
text | 33204aeb-f0cc-5abf-9a3a-03a18e6f926a |  | textbox | Position:
text | 1ef87d97-d9b6-544d-8671-f34297db17f9 |  | textbox | Work Completed On:
text | 354353d3-bfb4-5f39-87d2-c14a100016b6 |  | textbox | Date:
checklist-flat |  |  | checklist | CHK-003-CIV-Reinforced Concrete Pipe RCP-Material Inspection | itp |  |  |  | Yes | CHK-003-CIV-Precast Reinforced Concrete Pipes & Pits - Material Delivery Inspection | 68ba0c44-4839-4ace-8129-64d49bbb9e6a
checkpoint-status |  |  | checkpoint | CHK-003-CIV-Reinforced Concrete Pipe RCP-Material Inspection
label | 019b2fcb-282f-5c03-8510-431764122020 |  | note | Document Title: CHK-003-CIV-Precast Reinforced Concrete Pipes & Pits - Material Delivery Inspection
label | 2e985c30-43bc-5d1f-af5a-ef4b3c6d7b66 |  | note | Check list Description: Precast Reinforced Concrete Pipes & Pits - Material Delivery Inspection
label | 14dbd2be-5e2d-533b-9141-c209548ddeee |  | note | Discipline (e.g. CIV/STR/RAIL): CIV
label | 0408e18b-9ec2-530d-99a4-3f8dc49ded20 |  | note | Revision Number: 0
label | d57dfd10-cc6c-5046-8c38-83665359dcf2 |  | note | Revision Date: [Date of Approval]
label | ed9d2be5-138c-5841-84b7-05f0043e9d88 |  | note | ITP created by: Jon De Castro
label | b2cb522f-3dde-546a-b1ee-abc3ff3e45ae |  | note | ITP approved for use by: Aldrin Guinchoma
checkpoint-status |  |  | checkpoint | 1 - Materials - Fabrication
label | a31d80e0-9e92-56ca-bba7-ff75790fa978 |  | note | REFERENCE:
label | 037a6c07-3cb9-5657-b97f-181c52d18494 |  | note | • IFC Drawings
label | 1fe6dbb8-e520-586d-bb55-62d99625d0b3 |  | note | • Section 620
label | 35d3ed0e-43bf-5b2b-ba5e-27e31b2ec9b4 |  | note | • Section 701
label | d71c2ef3-7063-581b-9742-4776ddfaa98c |  | note | • Section 705
label | 14d20d00-a26d-535f-8f49-fdb852033cb8 |  | note | ---------------------------------
label | 44be64df-c925-5801-8cb5-5561d61b9000 |  | note | ACCEPTANCE CRITERIA:
label | 96778c0b-9592-58f7-932f-665ec11547e4 |  | note | (1) Precast items manufactured in accordnace with IFC Drawings
text | 53b71c7b-85d6-595c-9feb-7e7f231bf898 |  | textbox | - Drawing Ref No.
label | 5f66c1fc-9bb4-5fc4-9dfa-e1aa5eda178c |  | note | ---------------------------------
label | d9d585b2-96b1-5120-b997-d81bec3533fa |  | note | METHOD: Visual Inspection
label | a8615e53-b4b9-5079-ba5c-a2789afb27db |  | note | ---------------------------------
label | 0ae9e1e1-876b-5ffe-a598-2ac5ea35bd2d |  | note | FREQUENCY: Each Lot
label | f2e5db36-0a4f-518e-b1d8-dd07387f53aa |  | note | ---------------------------------
label | 48a2a278-3c84-5831-88ab-eb30a62cc44e |  | note | CATEGORY: IP
label | 16c2965d-c577-5190-8e0f-565e9e4259ab |  | note | ---------------------------------
label | 980af84b-e4da-542b-a3cd-8f34e8e87de0 |  | note | RESPONSIBILITY: SE
label | 3a17464d-f6cc-5453-a034-f1a0e8c1a264 |  | note | ---------------------------------
label | 6a8760dc-a643-5df4-ba94-997d0593c3ff |  | note | VERIFYING DOCUMENTS: Material Delivery Docket
label | 0372291c-020f-581d-a98e-7d2db3a921c5 |  | note | ---------------------------------
text | 101e42e4-3f6f-5b0e-8e35-9484ffdfe762 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 2 - Materials - Delivery
label | df8ecff6-40cd-5898-968f-f3d5615a8f4e |  | note | REFERENCE:
label | 1c89a5bd-8e5b-5145-8db3-bb6817e267ec |  | note | • IFC Drawings
label | 00dcc04c-df1d-5694-98c9-50bf90199517 |  | note | • Section 620
label | e36ae1bc-2cee-5516-b266-2c3b07c39ea4 |  | note | • Section 701
label | 46867914-f07f-5e53-bd41-ea570f0bcc41 |  | note | • Section 705
label | 8ca3d48d-c6bd-5cf0-b47e-3ed8458e9f5c |  | note | ---------------------------------
label | f9b0e62e-4560-5b96-8fb5-dcaa56ffa01d |  | note | ACCEPTANCE CRITERIA:
label | 58da26b8-caf0-574c-8c47-a3a67145807d |  | note | (1) Purchase Order and Material Description and Qtys matches
label | 8a3784fe-cf53-538f-a363-9cfd9c137025 |  | note | (2) Ensure precast concrete elements are as per IFC Drawings upon delivery and no damage evident.
label | 8a28b79a-c7af-555f-8b6d-b8440dfedd0f |  | note | (3) Lifting and Manufacture compliance certification provided
text | 8e0ed233-d02a-5c32-b320-e1483b893281 |  | textbox | - Purchase Order No.
label | c3872f8d-536b-5c19-a82d-8a35e4744197 |  | note | ---------------------------------
label | 46df0f86-5f7c-508c-b062-b794526e0990 |  | note | METHOD: Visual Inspection
label | b722609d-8305-571b-b3d3-06b6e045193b |  | note | ---------------------------------
label | daebe469-96b1-50e0-a603-239db95b7f45 |  | note | FREQUENCY: Each Lot
label | e30a5e47-bf68-5d59-ae52-6aae23cca778 |  | note | ---------------------------------
label | 503fc436-3ce7-57fc-a5d4-1c2e13c36622 |  | note | CATEGORY: IP
label | d67fdcf2-6170-5fdb-8872-affd95041ca3 |  | note | ---------------------------------
label | 7c27e44b-c16e-5563-92d5-66f0222aa4b1 |  | note | RESPONSIBILITY: SE
label | ef0aa3f1-61cb-503d-ae67-03e866d59025 |  | note | ---------------------------------
label | 8cf4a1be-1988-5874-8193-661c552774cc |  | note | VERIFYING DOCUMENTS:
label | 74fd841c-dd64-54ba-b810-24188d33b8c7 |  | note | • Material Delivery Docket
label | c323c157-8d44-52ed-9928-d4cd15766eb6 |  | note | • Purchase Order
label | 5163ea7e-abfd-500e-955d-aff06cee0d4d |  | note | ---------------------------------
text | 4e8776ab-e1cf-5116-87a6-346f4e2e6e36 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 3 - Materials - Manufacture's Certificate of Compliance
label | 8be78c5e-1f83-512c-b66c-3e80b63419fc |  | note | REFERENCE:
label | 142180f1-b30e-5a59-a162-6a1a88cab887 |  | note | • IFC Drawings
label | c12f060c-e2fd-5649-afcc-b0b79f950497 |  | note | • Section 620
label | cb8ad936-1a02-50ff-a1d1-bcd7db2d5188 |  | note | • Section 701
label | 1d684104-4992-5794-b8c1-3459fab12d4e |  | note | • Section 705
label | 27358ced-61e7-5e93-8c42-0f2f07a4a990 |  | note | ---------------------------------
label | 409c2c7c-a228-5b05-a42a-39e7cbfd9c50 |  | note | ACCEPTANCE CRITERIA:
label | 5b8f8a8b-48ad-5cff-93dc-ae0628bb2c0c |  | note | (1) Ensure Manufacturer’s certificates of compliance are received for precast RCP during delivery on site and min required strength is achieved prior to transporting.
label | e3a7be83-fc13-5eba-9344-a5903a61cc84 |  | note | ---------------------------------
label | 2b9ef523-10b8-5958-9841-0ef79d407c9c |  | note | METHOD: Visual Inspection
label | 92bfcef3-ce66-59f2-b945-08917f3f1b26 |  | note | ---------------------------------
label | 4ec5241a-87ca-58ba-8353-1493262c5e85 |  | note | FREQUENCY: Each Lot
label | dd536b47-d716-5f0c-a6de-87cdcf079a41 |  | note | ---------------------------------
label | c1afbc9d-668a-5d31-a055-791c969dc70a |  | note | CATEGORY: IP
label | 6b2f63a1-41d5-5e5c-af92-7893daaaa1a1 |  | note | ---------------------------------
label | d01c84e1-6e63-5748-ba62-b573715d2054 |  | note | RESPONSIBILITY: SE
label | 46d181a5-fba8-5abd-822f-bec41d47ed52 |  | note | ---------------------------------
label | dbc6a4e0-2688-51d8-9591-351cf9fd8366 |  | note | VERIFYING DOCUMENTS:
label | b4a335c0-7256-5ab6-afbd-dea24cf63dd2 |  | note | • Material Delivery Docket
label | 92808e45-ad04-5857-b09d-4e0736045f4c |  | note | • Compliance Certificate
label | 016dd470-72e9-5c87-b17e-298a7d55716a |  | note | ---------------------------------
text | d8d11084-342e-58a0-a041-66781c1842c1 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 4 - Materials - Delivery to site & Storage
label | c273c18d-9d18-5a08-ae99-2bb21dc955de |  | note | REFERENCE:
label | 5f8aee41-7970-55fd-a421-9b1db3336337 |  | note | • IFC Drawings
label | 9ece20c0-c8f8-55ee-8263-648d3da2e947 |  | note | • Section 620
label | 279812cb-d761-585f-ace9-5703d8a81e26 |  | note | • Section 701
label | f62075c6-da2e-5421-b9c5-9dc1c4ccd367 |  | note | • Section 705
label | 3e176a84-b1c4-52f5-a4b2-fbf8e649d340 |  | note | ---------------------------------
label | 47e6d5a1-cc7c-5b82-b84c-e4952d840d9c |  | note | ACCEPTANCE CRITERIA:
label | c2e51c54-506b-557c-898e-8f1e13cd3375 |  | note | (1) Identification of product is legible (Stamp, Label, Etc) and should be marked on every precast element.
label | f6a5263f-4ff9-5149-a107-eda9b040687e |  | note | (2) Precast elements are unloaded and stored properly on site as per manufacturer's instructions.
label | c3ec9166-6bd4-5fc6-9049-38e20bf4b00d |  | note | ---------------------------------
label | 2b8cf4a5-5dfc-5d69-85d6-fadf78b7e987 |  | note | METHOD: Visual Inspection
label | c4da6700-7522-5aa5-930d-2ef07287d37d |  | note | ---------------------------------
label | a4ffb242-686a-56d3-8463-65ba0e2b8e42 |  | note | FREQUENCY: Each Lot
label | fc8ebf0b-29c2-535b-a58c-36c07ab499dc |  | note | ---------------------------------
label | a2f3ddc4-af3d-5ce6-a61d-86ecd3152613 |  | note | CATEGORY: IP
label | 4f73a631-a0dd-5159-b12e-059426b152c8 |  | note | ---------------------------------
label | 65188cce-f55c-5483-ac42-2577350a7015 |  | note | RESPONSIBILITY: SE
label | e32c9e73-fdf9-5e1b-a394-5d51cc585406 |  | note | ---------------------------------
label | 6757f880-f5b6-51b0-b688-0940bad0ba65 |  | note | VERIFYING DOCUMENTS: Material Delivery Docket
label | 00750c6f-bed8-56bd-a67d-fb5864bcbb3b |  | note | ---------------------------------
text | ec97f1a7-cfa4-5dff-8c9e-fd14476f086b |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5 - Materials - Others
label | a5a52d65-933f-58a9-a0a2-5594403bf23d |  | note | REFERENCE:
label | 2da5bd4d-dc1f-5546-86c2-ae827027ec0c |  | note | • IFC Drawings
label | 231ec838-2e6a-5127-a238-be357e3034b6 |  | note | • Section 620
label | e1eda32d-9ef7-53fe-b645-0bca6fda293c |  | note | • Section 701
label | 729aee64-fbfb-51ca-9614-4ba01e4f7217 |  | note | • Section 705
label | a8f7a54f-0f32-5f90-9d32-d14c66a1d713 |  | note | ---------------------------------
label | 1fec4b7c-9e67-5197-8166-cdabea260a0d |  | note | ACCEPTANCE CRITERIA:
text | 60fe8f50-335a-5ab3-a4bc-3efb0c5d9753 |  | textbox | (For Additional Comments)
label | d19c29b2-2d3c-50fa-9133-9518edbccebe |  | note | ---------------------------------
label | 4ffd4269-e5dd-577d-8a52-8f922be7dbc5 |  | note | METHOD: Visual Inspection
label | 981c522a-e5b5-5cee-af7e-c5b906ab684a |  | note | ---------------------------------
label | 50ce190d-cf5f-5145-8b4f-e85c35653a5c |  | note | FREQUENCY: Each Lot
label | 6737c280-9192-5a0d-9ce4-867420b5503e |  | note | ---------------------------------
label | 3d0ae120-cb81-5ca1-b131-7ddde0554d4e |  | note | CATEGORY: IP
label | 7527edea-95c9-5e4b-869a-b4cc2fc033e0 |  | note | ---------------------------------
label | a335d91a-7ea0-5af1-8287-b1e7bbfdeca9 |  | note | RESPONSIBILITY: SE
label | aa0635d2-b4ce-5565-9e18-8b2dc5eb80df |  | note | ---------------------------------
label | a49f0d90-7151-5d75-9c4c-99ac18e20957 |  | note | VERIFYING DOCUMENTS: Material Delivery Docket
label | 1151319a-4aa3-5c59-888c-131653459a07 |  | note | ---------------------------------
text | 779385c1-ffce-5ad0-bd63-f7e231414293 |  | textbox | Date Completed:
checklist-sectioned |  |  | checklist | ITP-RAIL-CAMMS-MTM-Stormwater Drainage Rev 0 | itp |  |  |  | Yes | ITP-RAIL-CAMMS-MTM-Stormwater Drainage Rev 0 | 858657f8-8819-4b23-8bb8-ae41a661d944
checkpoint-group |  |  | section | Referenced Documentation
checkpoint-status |  |  | checkpoint | Referenced Documentation
label | ee0f1665-f439-5778-8996-b6b588da05c3 |  | note | Document Title: ITP-RAIL-CAMMS-MTM-Stormwater Drainage
label | ca9d17f2-29ba-56a6-a100-99b7c3187e72 |  | note | ITP Description: Stormwater Drainage
label | c5036338-012b-5962-8959-6240580c8e7c |  | note | Document Number (in Teambinder): MRP-0000-MRPA-ALT-ITP-00XX
label | c12a1f08-325d-5c32-acf2-8dc238f4ab10 |  | note | Discipline (e.g. CIV/STR/RAIL): RAIL
label | 48cf106b-6259-51fe-8fec-09db1dc83b3a |  | note | Revision Number: 0
label | 43da4b3d-8fbc-5482-b586-7fdb3f1f0b43 |  | note | Revision Date: 12/08/2022
label | 125a0c32-8fd8-56e0-b84e-de1a002abd97 |  | note | ITP created by: Justin Kreinberg
label | e7f9fa0f-e51e-5b46-a0a1-6b9a6c6236aa |  | note | ITP approved for use by: Victor Mira
label | f873287d-6fc9-5473-9110-18a97e28102b |  | note | 1.1 - Non Dependent
label | 57c32a93-f63f-5b4d-a0cc-15b9afb69fb6 |  | note | Reference Documents: VicRoads Section 701 (May 2020)
label | 181c8fbc-13f1-5609-9e3b-0db7f720adde |  | note | 1.2 -
label | f0a42740-6b31-5210-aebe-63d601c37320 |  | note | Reference Documents: VicRoads Section 705 (June 2021)
label | 617ebc07-b510-5c91-8547-37f7078a7d94 |  | note | 1.3 -
label | f075b407-a6ec-589d-b9f1-9f66f76e49f6 |  | note | Reference Documents: MTM Track Drainage L1-CHE-STD-030 (July 2018)
checkpoint-group |  |  | section | Preliminaries-Materials
checkpoint-status |  |  | checkpoint | 2.1 Drainage Pit - Supply
label | d35fb691-3fff-53db-bea9-7884543395ba |  | note | REFERENCE: Section 705.07
label | 0d0b8b81-2930-578b-b868-619f2eba9ee2 |  | note | ---------------------------------
label | 176605a4-5f4b-5859-9a35-d8e6e0ed4581 |  | note | ACCEPTANCE CRITERIA:
label | 93903a24-2529-53a1-bd19-468e350abb02 |  | note | Precast steel reinforced concrete drainage pits shall be manufactured, supplied and installed in accordance with 705.07.
text | a1e4191c-14c8-5dce-aea0-2fbad92fe53a |  | textbox | Enter: Teambinder Material Approval number
label | 82f90c8e-c567-5de1-ba48-4262e22fa9df |  | note | ---------------------------------
label | eb02dd27-63d7-5270-a7b6-f5ee8f7b19ce |  | note | METHOD: Document Review
label | 2467cf1c-b48f-5939-9b2f-b2a6394163a6 |  | note | ---------------------------------
label | 4e22e45d-48b0-5f66-acc2-818538980ba3 |  | note | FREQUENCY: Each lot
label | 8f21f7a0-2955-5c26-b397-a13c1b32fd73 |  | note | ---------------------------------
label | 95b4b310-4a1f-5600-ba35-a3c69b7ab9cc |  | note | CATEGORY: HP
label | 53d0674a-f8e0-5f54-a473-cbaaf411c3dd |  | note | ---------------------------------
label | 45241d70-f4c6-513a-944c-4f344a98db8a |  | note | RESPONSIBILITY: SE
label | 83d6435d-017d-5d4a-b7d9-2d4a96b60086 |  | note | ---------------------------------
label | 117db91e-b88f-5232-8a54-6c7ec96ad22b |  | note | VERIFYING DOCUMENTS: Teambinder Material Approval
text | 61929c14-d409-58f7-9a6b-737fc273c74f |  | textbox | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.2 Drainage Pit - Step Irons
label | 249617d1-8ef7-5e60-9cb8-786b6e630206 |  | note | REFERENCE: Section 705.04
label | 50de1a42-c0a7-544a-988b-47e155dd8a5c |  | note | ---------------------------------
label | 58f05bb9-1346-598c-b5f0-a9a271765eca |  | note | ACCEPTANCE CRITERIA:
label | fb82c56e-b483-54f9-95b1-aa0c3c207379 |  | note | Step irons shall be manufactured by 13mm steel bar covered with polypropylene plastic in accordance with 705.04
text | ee380b23-2ffd-56ff-b927-3f5a5ceb6b5e |  | textbox | Enter: Teambinder Material Approval number
label | 6f39f51a-2563-5c52-8e0b-80b6c3fdf3cf |  | note | ---------------------------------
label | 4cf0af88-3aec-52c1-b44a-dabb111e76aa |  | note | METHOD: Document Review
label | b6b5dbc6-ad1c-572b-9ea8-601dedd3c4ff |  | note | ---------------------------------
label | 15e8221b-1426-552b-8499-1aa47a1a10cc |  | note | FREQUENCY: Each lot
label | fd0f4f98-4cb3-53ac-9e46-6dfdeec68874 |  | note | ---------------------------------
label | f5e6a3f1-c94b-5f3e-a29e-7395861221c2 |  | note | CATEGORY: HP
label | 1750a881-a46c-5f65-a02f-381ab14f87dc |  | note | ---------------------------------
label | 236066b6-fe84-5df8-9a9a-77f69e3afeb7 |  | note | RESPONSIBILITY: SE
label | 4aa57b68-c1c0-5bef-9f86-05416b63f0a0 |  | note | ---------------------------------
label | ad922f16-3afb-51f0-9abd-10cf7c77830c |  | note | VERIFYING DOCUMENTS: Teambinder Material Approval
text | aceccb1a-01ce-576b-89c4-934f5b503190 |  | textbox | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.3 Drainage RCP Pipes - Supply
label | 02b426b2-6280-5138-9d31-1d974aa874b2 |  | note | REFERENCE: Section 701.05
label | 6ae553c2-ca7d-510e-b4ef-086d45bae2f6 |  | note | ---------------------------------
label | f1562463-519f-5771-a3b9-65cb871d0347 |  | note | ACCEPTANCE CRITERIA:
label | 92522e6a-6e3d-5093-908b-743a712a1467 |  | note | Precast reinforced concrete pipes shall be manufactured, supplied and installed in accordance with 701.05.
text | a39ffbe1-ed9d-5949-814b-5da898b8f444 |  | textbox | Enter: Teambinder Material Approval number
label | df99abc4-b95d-5c54-906c-92750fdd3741 |  | note | ---------------------------------
label | 6207baf8-56e7-58e4-8184-cf14f9f86f08 |  | note | METHOD: Document Review
label | 2165d4de-eb5e-504f-83f9-ba1c14d7025b |  | note | ---------------------------------
label | 7e4aecaf-0a5c-54d6-b596-2c88a5dcacb6 |  | note | FREQUENCY: Each lot
label | 75aace53-45e7-527a-8583-a84a87ce555a |  | note | ---------------------------------
label | 990262ed-a1a5-55b4-b27a-63b5abdb9756 |  | note | CATEGORY: HP
label | 8b365e65-5dc1-541f-982f-5b9d4a4913d5 |  | note | ---------------------------------
label | ccaedc50-6ca6-53c2-9f35-a3b9a5a6cd5f |  | note | RESPONSIBILITY: SE
label | 1c412879-2448-52f8-baeb-1773e5bf0897 |  | note | ---------------------------------
label | 6c6d4f30-73be-574d-a8ca-59d8c2ac4a9f |  | note | VERIFYING DOCUMENTS: Teambinder Material Approval
text | ee1235ea-b652-558c-8f48-0b46ef5a2a1b |  | textbox | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.4 Drainage Flexible Pipes - Supply
label | 4b42108b-bf31-592b-8e17-97652c40353c |  | note | REFERENCE: Section 701.07
label | 4da5202c-e8ec-5532-bf70-65815c18aeac |  | note | ---------------------------------
label | fe25e9ab-1d57-5212-bad0-2f29a8538d68 |  | note | ACCEPTANCE CRITERIA:
label | f6a4e174-3ea4-53fa-8135-eab9b55f0220 |  | note | Flexible pipes shall be supplied in accordance with 701.07
text | 27aea3b7-46f8-527e-bcd3-f6c068614576 |  | textbox | Enter: Teambinder Material Approval number
label | 7569500f-bb36-507c-b721-b8f65c4cc06a |  | note | ---------------------------------
label | 38d7e840-2db4-542b-a60f-5ac5e9515f38 |  | note | METHOD: Document Review
label | 4661889e-d64c-5a1c-aa94-618eb16db1f1 |  | note | ---------------------------------
label | ea901287-1084-50a0-90a8-c8d234a1e1de |  | note | FREQUENCY: Each lot
label | a3b64976-3d0a-5777-8550-0dc9fd722961 |  | note | ---------------------------------
label | b898c484-87e5-5b6b-a547-2c638f7bf07c |  | note | CATEGORY: HP
label | 85f80947-c023-5afd-8ae8-d8df5e9cbc4b |  | note | ---------------------------------
label | 68fa8178-43a0-5486-91a8-27106d4d7277 |  | note | RESPONSIBILITY: SE
label | 7493a83d-224c-5e31-a842-6993245af300 |  | note | ---------------------------------
label | c3b6b87e-c570-5c8d-9a4a-861adf35a5dd |  | note | VERIFYING DOCUMENTS: Teambinder Material Approval
text | d9743002-2d19-5f48-b8f9-673ad851342f |  | textbox | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.5 Drainage Slotted Pipes - Supply
label | 33f95161-186c-5789-945f-6a336aa441cd |  | note | REFERENCE: Section 701.07
label | a3d00c9c-932a-5ecf-89cf-cc6de5e9d23f |  | note | ---------------------------------
label | cbe915e1-e354-5f93-9600-51573dc520af |  | note | ACCEPTANCE CRITERIA:
label | 6ac404e0-569a-5b26-9eff-af9938e8ba1c |  | note | Subsurface drainage shall be supplied in accordance with 702.04
text | 68f97cd9-cf0f-5f2e-90dd-9e22805cf0df |  | textbox | Enter: Teambinder Material Approval number
label | 1e40e83a-21c3-5125-932a-80e84b28a7c6 |  | note | ---------------------------------
label | 7aab155d-dcf6-590c-89e1-05ff82809c62 |  | note | METHOD: Document Review
label | e5bbb8ee-9fb1-55ae-8a2f-f16bb71dbddc |  | note | ---------------------------------
label | 2215b88b-a7b2-5ff4-987c-04e43d33ae87 |  | note | FREQUENCY: Each lot
label | c31a3c15-1553-51f0-ac9a-9c9a433a48d0 |  | note | ---------------------------------
label | 35808bbf-8f0d-5fcc-96b7-991a9b51cfa9 |  | note | CATEGORY: HP
label | faa83399-21e5-5737-a783-11282fbf7d17 |  | note | ---------------------------------
label | f86e29e1-66df-5dcb-93ac-16dd13751864 |  | note | RESPONSIBILITY: SE
label | c88050b2-66f1-5bde-8be6-763aa2ecb0b4 |  | note | ---------------------------------
label | 4d812e67-d6e2-571d-b67e-d80ff80df937 |  | note | VERIFYING DOCUMENTS: Teambinder Material Approval
text | b7b02ae6-ac82-5c96-83dc-9c8c2b7cdbd6 |  | textbox | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.6 Drainage Bedding Material - Supply
label | ace21155-794b-5bf1-893e-a81c478fe97b |  | note | REFERENCE: Section 701.09
label | a2527941-f1e5-5843-bfa3-3ab3baab3108 |  | note | ---------------------------------
label | d6275d7a-a541-5cc7-b70b-b21401af8d20 |  | note | ACCEPTANCE CRITERIA:
label | 2fbe0a1f-37c4-51ff-b0ad-a6be070f56fd |  | note | Bedding Material shall be free from perishable matter, lumps and conform with the requirements of Table 701.091 and Table 701.092.
text | 8ee0743c-1bc0-55c2-82dc-fb6f444ee84a |  | textbox | Enter: Teambinder Material Approval number
label | 086bc06d-0161-59ee-baaa-21c60b9ada33 |  | note | ---------------------------------
label | 3916bbf4-dcc8-529e-8c57-dba79f5145d0 |  | note | METHOD: Document Review
label | 66613016-5666-5f13-9f1a-d2b8ae07d07a |  | note | ---------------------------------
label | 5b49b9f8-8222-54e8-9f6d-5252fad10de7 |  | note | FREQUENCY: Each lot
label | 25680218-bc2a-5253-956f-4ecaa0300424 |  | note | ---------------------------------
label | b17266fb-2460-5520-abe9-87facb2125d0 |  | note | CATEGORY: HP
label | d51816a2-a478-5edf-985e-e709e8a26bff |  | note | ---------------------------------
label | 0508c454-3218-58b3-9042-e32078a99195 |  | note | RESPONSIBILITY: SE
label | 3aeb1c7c-d631-5d97-8819-d0c6223faff8 |  | note | ---------------------------------
label | 86c7f31c-68a8-5d1f-b194-15e3c47ebda0 |  | note | VERIFYING DOCUMENTS: Teambinder Material Approval
text | ff4507ed-bd7e-5e9c-90b6-3585d81b8ff1 |  | textbox | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.7 Drainage Backfill Material - Supply
label | 9bc5fe82-03f3-509a-940e-59dd44fb6f1d |  | note | REFERENCE: Section 701.09
label | 0b1eacdd-5010-5ebc-b453-47775a5d26e0 |  | note | ---------------------------------
label | 3f280de6-d595-5b24-a8ad-3f4c06f73281 |  | note | ACCEPTANCE CRITERIA:
label | d7a64c0d-1737-5fd9-89f3-966cf49b7dae |  | note | Ordinary and Selected Backfill Material shall be free from perishable matter, lumps and conform with the requirements of Table 701.091 and Table 701.092.
text | 0e0561bd-9ab2-5ea3-8c19-8d7d646d9f69 |  | textbox | Enter: Teambinder Material Approval number
label | 8372510e-f2c9-5039-8238-bee6df3270df |  | note | ---------------------------------
label | d5c9d286-69a6-5f1d-b649-ffa0c693d0b3 |  | note | METHOD: Document Review
label | 482b3714-4726-590a-99e9-4a357291a726 |  | note | ---------------------------------
label | f8a29500-fb49-5d1a-873e-bf098b0898fc |  | note | FREQUENCY: Each lot
label | 2b82f3f7-f1c5-594e-9f3b-9a11e86b4b39 |  | note | ---------------------------------
label | 9a6dcc54-9a09-5393-bf9d-456e6677edf4 |  | note | CATEGORY: HP
label | f7adff96-2203-5711-8ff5-0d8e2d374777 |  | note | ---------------------------------
label | f8fed124-ec9e-5a67-8eb6-dc99bbe46ce0 |  | note | RESPONSIBILITY: SE
label | eb8d0b49-4a13-58be-a048-40893a213697 |  | note | ---------------------------------
label | b3131080-e373-526a-bcf0-4a7d84758d6a |  | note | VERIFYING DOCUMENTS: Teambinder Material Approval
text | 25716d88-2f9d-54ae-85ff-d1b3c0c735af |  | textbox | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | Preliminaries-Procedures
checkpoint-group |  |  | section | Pre Construction
checkpoint-status |  |  | checkpoint | 4.1 Survey Set Out-Pits
label | 24c3045e-d0ac-57b8-a766-93517d9a185c |  | note | REFERENCE:
label | 65d723e9-0a55-590f-8403-ec2bef2392fa |  | note | IFC Drawings
label | 1a1702aa-0e12-5527-969e-cbb197217b4f |  | note | Section 701.10
label | 972eb1d6-5ba6-5344-b116-31fc8701d517 |  | note | ---------------------------------
label | b3497c5e-d2d4-539c-b2cf-9cbdcc2fe8e3 |  | note | ACCEPTANCE CRITERIA:
label | 86b592cf-7026-5649-93e7-a109bb02d17c |  | note | Survey activities undertaken to ensure and validate the plan location, height and line of pits and location, invert level, plan of pipes in accordance with design documentation and 701.10
label | 26739f1c-d4c3-542f-8c6b-826eac4aba81 |  | note | ATTACH: LOT MARKED UP LOCATION ON THE IFC DRAWING (LOT MAP):
label | 3a8068e6-602d-5de7-a37b-2002ed28a5da |  | note | ---------------------------------
label | de790a75-201c-5785-b08a-61cb339dc1b8 |  | note | METHOD: Visual inspection
label | 1c0e42e0-a1de-5b89-bbd6-7e38d9244bb2 |  | note | ---------------------------------
label | e7cde081-9fec-5d90-a631-f15c57a2a455 |  | note | FREQUENCY: Each Lot
label | fb5c90ef-eda4-50a1-8718-701b43112cfe |  | note | ---------------------------------
label | 3c601cb1-ffcd-5fd6-8864-dc8c0f262ce4 |  | note | CATEGORY: IP
label | b04c4f49-4a19-5339-9327-7e74a4a5a892 |  | note | ---------------------------------
label | c5eb69db-c61c-557b-9fb3-65272332d919 |  | note | RESPONSIBILITY: SE
label | e32fb930-0599-5bb6-bf4a-89eeba3aaf47 |  | note | ---------------------------------
label | cb6a4a70-c046-511f-866c-d58b7e2a288a |  | note | VERIFYING DOCUMENTS: This ITP
text | bd7c1d2e-4cab-5814-9769-e86786a0bedc |  | textbox | Date Completed:
checkpoint-group |  |  | section | Construction - Pit Installation
checkpoint-status |  |  | checkpoint | 5.1 Pits-Pit Excavation
label | ed6be0ec-1c62-5653-bbcc-1662170f51af |  | note | REFERENCE:
label | 0cbfd44d-6c41-5300-b71a-96023c18dfc7 |  | note | IFC Drawings
label | 6f91ef1f-02a9-57b7-b581-0d95886f6416 |  | note | Section 705.05
label | 7d59e0c7-9b46-54a6-ac3d-9dc92a483be2 |  | note | ---------------------------------
label | e70ee95c-cb83-5058-b40a-6a3b8819985f |  | note | ACCEPTANCE CRITERIA: Excavation shall be to the depth indicated on the design documentation. Precast pits must have a clearance of 400mm from excavation face and external face of pit.
label | 42e95654-e866-5d86-a256-b9f74968f0d4 |  | note | ---------------------------------
label | b870fb0e-5e69-53da-9f32-451622b18cdd |  | note | METHOD: Visual inspection
label | 1bca50be-53d2-515c-9341-618d0522dff2 |  | note | ---------------------------------
label | c3b3cee9-6dcc-5db6-86e8-501ec35f8b5b |  | note | FREQUENCY: Each Lot
label | d4e2409f-58b1-5728-81de-b04cf8c4e791 |  | note | ---------------------------------
label | 457a7cfe-1e7a-5bbb-a987-5b90b0f9edec |  | note | CATEGORY: IP
label | ea2f9a3b-1671-5a11-928e-3679e3b749de |  | note | ---------------------------------
label | ebf56e51-8b16-5aeb-9c59-9125185090d6 |  | note | RESPONSIBILITY: SE
label | 4396d11b-1fa4-51dd-bf52-4435d138f09a |  | note | ---------------------------------
label | 72dfbe1c-c464-5ab7-9e02-90cf517933dc |  | note | VERIFYING DOCUMENTS: This ITP
text | 878ddb73-2b4b-5b25-8136-39ac23718970 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.2 Pits-Excavation Foundation
label | 85a96a73-ff5e-51e5-8c04-498f12d75018 |  | note | REFERENCE:
label | 712033fb-a9b7-510d-9ba0-75a0e52eda74 |  | note | IFC Drawings
label | e6765f0a-69f6-584d-a891-c7b32d8a7835 |  | note | Section 705.05
label | 2b69a6b9-5616-54d2-ab00-43c5f4e5d281 |  | note | ---------------------------------
label | dea16ed0-fab9-5a25-bb8a-7e40653cea9d |  | note | ACCEPTANCE CRITERIA:
label | c99e3955-7a04-57af-9ab9-cdf9cf4a88c2 |  | note | Bedding conforming to to 710.09 shallbe supplied, placed and compacted to a thickness:
label | 51b30dbd-0035-5670-bc46-0c9616282dd0 |  | note | > 80mm for clay foundations
label | 719e2db2-7a1a-5398-ad81-3b41cb511144 |  | note | > 150mm for rock foundations
label | 2ad43ef5-6811-59e4-a206-00826d7ca5cc |  | note | ---------------------------------
label | 89a9f105-91c2-5b76-8323-6684834864ab |  | note | METHOD: Visual inspection
label | 7cbe07a9-35e0-5895-9ae3-68a79e444fea |  | note | ---------------------------------
label | bdb00c1e-53ad-5f91-b651-a54eb35e4a0d |  | note | FREQUENCY: Each Lot
label | 2cdd8b35-d087-5a06-b886-dbb32e26a1ce |  | note | ---------------------------------
label | 3785669a-ca78-5783-8fb8-442984a0560c |  | note | CATEGORY: IP
label | 39eca24b-03c2-55a6-a77e-5150b245fcc1 |  | note | ---------------------------------
label | 331db0ad-de57-5f25-b239-ca91df89bb31 |  | note | RESPONSIBILITY: SE
label | 67471aef-aea3-5b9b-88a8-4b42a8411f7c |  | note | ---------------------------------
label | 355aa3c4-e68c-539b-9811-c66713209352 |  | note | VERIFYING DOCUMENTS: This ITP
text | b1505cc4-d68f-55a6-a09e-3092e2a737f5 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.3 Pits-Placement of Pit
label | 85cd7ea1-f306-5598-baac-98e19da6f39a |  | note | REFERENCE:
label | 8aa840b6-632f-593e-8217-138ba93d99cc |  | note | IFC Drawings
label | 15f8f898-e5b4-5f0f-8798-27c8f6596079 |  | note | Section 701.10
label | c9979c2c-a4e0-5335-a8da-0af05f98f9fe |  | note | ---------------------------------
label | af86d084-4940-5c57-8623-80fe428b100d |  | note | ACCEPTANCE CRITERIA: Plan location of pits, other than offsets to kerb line or barriers, to be +/- 100mm
label | 1e58d8a6-83d4-5a2b-b4e3-dffdb3d9898d |  | note | ---------------------------------
label | 2ab17e29-3d9c-5b41-9d58-f28634d9964c |  | note | METHOD: Visual inspection
label | 6d05f5c1-cd99-5369-b491-e03f61afd2ac |  | note | ---------------------------------
label | 08dedde9-ec63-5ab7-b1d4-fc819660bb7c |  | note | FREQUENCY: Each Lot
label | da02ae8d-1a26-54ea-9ff9-e097cf8bbb47 |  | note | ---------------------------------
label | 190d5bee-c547-52a3-bc31-885d27c1879a |  | note | CATEGORY: IP
label | 011e21d4-2545-5df7-9300-2c1705557a55 |  | note | ---------------------------------
label | 8c8d14e0-9dfb-5f68-b0fd-61f51a4c514c |  | note | RESPONSIBILITY: SE
label | af6f3432-07ec-5cce-abab-6f6cf54b4e49 |  | note | ---------------------------------
label | e713689d-4c80-5de9-ab9f-fb2c8965a9f3 |  | note | VERIFYING DOCUMENTS: This ITP
text | ea4acdd0-36ab-519d-a1e9-f31c9c7dac40 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.4 Pits-Jointing
label | ee2d2e28-80eb-5773-b7ba-09baeb128dc1 |  | note | REFERENCE: Section 705.11
label | 45c67af3-d133-5e14-abfe-811500e85c84 |  | note | ---------------------------------
label | cab47e0d-ff4e-5bbb-b310-376ae61954f3 |  | note | ACCEPTANCE CRITERIA:
label | fc409264-d5e3-51d8-997c-d94ef0504e98 |  | note | All connections shall be finished to provide a smooth surface, uniform with the inner of the pit structure. Saw cut surrounding hole shall not exceed 50mm greater than the pipe diameter.
label | fc010168-a5d9-5b8b-bff5-45dce5f5b295 |  | note | Exposed reinforcement shall be coated with an approved epoxy treatment
label | ccac88dc-f7bc-540e-a702-01088c2b185f |  | note | ---------------------------------
label | 3405c58c-815c-5bab-bb1f-17b6565469e7 |  | note | METHOD: Visual inspection
label | cb4eeede-9b00-5493-8aa9-7d43160ef0f7 |  | note | ---------------------------------
label | 7f2b43c5-e363-589a-abf8-de0cfd7da6b1 |  | note | FREQUENCY: Each Lot
label | 36b96de6-5865-5abb-a344-73de24356c3a |  | note | ---------------------------------
label | eff48ed6-2fde-594d-ad41-beae05169333 |  | note | CATEGORY: IP
label | dfeeb822-af59-5341-ba42-82686d48fe10 |  | note | ---------------------------------
label | c17f67c3-a359-5294-ab6e-65228d6bd126 |  | note | RESPONSIBILITY: SE
label | 2939739c-59ea-56f6-9bba-3db4f00c14c1 |  | note | ---------------------------------
label | 0b681a28-75a2-567a-8dcb-ebbece4ad935 |  | note | VERIFYING DOCUMENTS: This ITP
text | c4624971-1b90-5473-9471-38530abe8fb2 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.5 Pits-Shaping of Floor
label | f10c35d8-65d7-5b92-b88f-2b0b8a889794 |  | note | REFERENCE: Section 705.13
label | 358daee2-973e-562b-b05c-9f7b337dc660 |  | note | ---------------------------------
label | 954953d3-5ae9-5175-a49a-3f037772fda4 |  | note | ACCEPTANCE CRITERIA: Pit floors are smoothly shaped from inlet to outlet for a height one third the diameter of the outlet pipe.
label | 6e0ff7b7-fa57-5e66-91b6-a7f54abac9eb |  | note | ---------------------------------
label | 2a2a9c4c-adb1-53c9-b956-fda8fc13d969 |  | note | METHOD: Visual inspection
label | 35f00cd6-2c35-54b0-8434-ba50d0b89b85 |  | note | ---------------------------------
label | 70f73234-7ee9-548e-b13a-3467d0a96f30 |  | note | FREQUENCY: Each Lot
label | f2776a16-304d-5cb5-8010-fcb8eb989cc2 |  | note | ---------------------------------
label | a0f88a33-6483-5989-8d00-9cf80aab2300 |  | note | CATEGORY: IP
label | 1e636efb-65f9-5a77-8a9f-6ac9eb8549f1 |  | note | ---------------------------------
label | 898d930f-4604-51a4-aa55-f1e249e12137 |  | note | RESPONSIBILITY: SE
label | 1436ae27-0d2a-5a7b-9331-c8d89e8aefa5 |  | note | ---------------------------------
label | df0b565a-c79a-5307-a078-e700c99d52a5 |  | note | VERIFYING DOCUMENTS: This ITP
text | f07c80ba-e492-54f0-9464-83e2043a7f85 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.6 Pits-Step Irons
label | 34ba0edb-b7fb-56f8-a7ef-92fccffc9f3e |  | note | REFERENCE:
label | 41cf660d-15e7-5d17-8e60-1df09ee8b895 |  | note | IFC Drawings
label | 75e0407d-f21c-57ad-bf13-1bbe6cf3ec81 |  | note | Section 705.12
label | 702f758b-25a9-58f8-b63f-ad7c542980f7 |  | note | L1-CHE-STD-030
label | 42e56a8d-e91d-5f9b-8948-5da4beccdd6f |  | note | ---------------------------------
label | eee614f4-ef23-5f0a-a8cc-d8197af6e1dc |  | note | ACCEPTANCE CRITERIA:
label | 12ccab27-0ecb-5273-8ed0-d8179133e26f |  | note | Drainage pits greater than 1.0m deep shall be fitted with step irons in accordance with 705.12. Ladder rungs shall not opbstruct openings and that water does not discharge on them.
label | 30bfe0b2-e752-51bc-b2ee-cf9444c83ab8 |  | note | Step rungs do not come within 50mm of the top of the riser
label | 85ee49ac-02a5-51fe-a1bb-ca12919d295d |  | note | ---------------------------------
label | 5aede39f-1bbb-5981-86c8-3a804a1193d2 |  | note | METHOD: Visual inspection
label | 28b12efd-242c-5c15-aab8-41dc5fd30cdc |  | note | ---------------------------------
label | eb92abd3-89cd-5b48-a02e-931929e290eb |  | note | FREQUENCY: Each Lot
label | 57ec8156-e8f3-515b-927f-684bc8bbc126 |  | note | ---------------------------------
label | e522f67c-fe93-5c71-9b6c-1c5a4749530e |  | note | CATEGORY: IP
label | 1f7f9f75-928d-5b58-8db6-9047f72f8d90 |  | note | ---------------------------------
label | ba6c9f5b-1945-56cc-afa1-66df031fb173 |  | note | RESPONSIBILITY: SE
label | 31584d5a-ad2b-5bc3-9e19-761b08481d97 |  | note | ---------------------------------
label | 8bc7e1eb-9f1e-546e-8d12-2fe9f503ddfd |  | note | VERIFYING DOCUMENTS: This ITP
text | f6913d58-b792-546f-af64-f18f2230fa76 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.7 Pits-Fitting of Covers
label | 4532c040-f590-5f96-af12-5b540a605a9d |  | note | REFERENCE:
label | 366c940a-d048-5408-bbc6-837fc95f0c06 |  | note | IFC Drawings
label | d94ee30b-c1b1-5c77-9dda-34bb847252d4 |  | note | Section 705.17
label | 7f92d463-5be4-5480-b2ad-bb74df9650c6 |  | note | ---------------------------------
label | 47fab317-27c7-5275-ad0f-498e03c331f7 |  | note | ACCEPTANCE CRITERIA:
label | 836d9c66-059c-5abd-bbda-3f0e3c925036 |  | note | Frames for drainage pit covers shall be cast in place or or bedded on fresh mortar, 5mm thick, consisting of 2 parts sand and 1 part cement.
label | 89b65fa6-f352-57a8-9245-9eda18f45109 |  | note | Height shall be within 10mm of the design level
label | 34425cb7-da15-58d5-8f7d-752c8d051cac |  | note | ---------------------------------
label | 0c3fb92c-39cd-5705-a401-12a03faf0a5f |  | note | METHOD: Visual inspection
label | bba49c76-c8b2-5080-bb06-1ba7274dc845 |  | note | ---------------------------------
label | 486668c4-a7ce-5cc0-93d4-6bf7f24a6b39 |  | note | FREQUENCY: Each Lot
label | 603c3a49-7425-522e-a769-21a0d5355fa6 |  | note | ---------------------------------
label | 0dc9b661-5484-5700-9448-3ce8129872b9 |  | note | CATEGORY: IP
label | 0fd4bc91-5731-59da-bc9d-e26c5517b637 |  | note | ---------------------------------
label | 1755cce9-0031-5ec6-b6d4-b69a8f8900e9 |  | note | RESPONSIBILITY: SE
label | 2ba28105-3498-5d96-9761-6c1306fa07e4 |  | note | ---------------------------------
label | b557e12e-f2c3-56ab-848b-c325265dcbb2 |  | note | VERIFYING DOCUMENTS: This ITP
text | 7bb8eef7-adcc-5cf5-95f5-b18967eba967 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.8 Pits-Pit Lids
label | bd1098e3-8d44-5559-82a0-3ea0df6e5e4f |  | note | REFERENCE:
label | 34e7359d-b39e-5e61-bf4d-a6e84d0a2ade |  | note | IFC Drawings
label | 3d45db80-cc4a-5f63-b168-bf574e032831 |  | note | L1-CHE-STD-030
label | b6f9e720-43e9-5f27-a46d-3f7489714922 |  | note | ---------------------------------
label | c0e13d23-1d07-5c68-a38b-219d2bdcbc65 |  | note | ACCEPTANCE CRITERIA: All stormwater pits shall be provided with a locakable minimum Class D piit lid, grate or ballast cage in accordance with MTM L1-CHE-STD-030
label | 63d8f780-100b-557c-b451-1bfbf517a8fc |  | note | ---------------------------------
label | 2ffea3f0-1976-5939-82f0-363b23084255 |  | note | METHOD: Visual inspection
label | 142000b6-0432-59f7-b6cd-1e23f6216688 |  | note | ---------------------------------
label | 862c5908-7066-5c0d-b26b-7f7e839a3cc3 |  | note | FREQUENCY: Each Lot
label | 0b97a811-e93a-5668-a4cb-006c0a1eee67 |  | note | ---------------------------------
label | 808d5a99-9137-5304-9622-7fc18112d8a1 |  | note | CATEGORY: IP
label | 5e3aaac2-ca5f-55cc-be6c-e04d04eb59c0 |  | note | ---------------------------------
label | d0478c26-032e-5d2f-bc7d-3af33fe815f2 |  | note | RESPONSIBILITY: SE
label | f06db88f-84e8-59ea-9ac8-fb1f1bcc2c93 |  | note | ---------------------------------
label | 4c902db5-4669-5f40-97a3-6943b1e2dbf5 |  | note | VERIFYING DOCUMENTS: This ITP
text | 2e61b87a-c2e7-5d5b-8d29-d3615917283b |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.9 Pits-Backfilling Around Drainage Pits
label | b06e7bd1-dede-5309-b6ee-6a1859ac5bf2 |  | note | REFERENCE: Section 705.18
label | 3a15db24-964f-57cf-b272-2571688601d9 |  | note | ---------------------------------
label | 699361dd-85cf-50e1-bc7e-fb2112dc57c9 |  | note | ACCEPTANCE CRITERIA: Backfilling around drainage pits shall be placed in layers not exceeding 300mm loose thickness and compacted to refusal
label | 86dcc65d-e469-5709-aef6-5f911079aa12 |  | note | ---------------------------------
label | eab1bfab-d8bf-5097-a482-588e7e1242fb |  | note | METHOD: Visual inspection
label | f7e471e8-eba0-5880-a3b7-45b8f10519d4 |  | note | ---------------------------------
label | fab3b738-ce7d-558d-80d5-aeac12f7ea36 |  | note | FREQUENCY: Each Lot
label | 326eb8ce-3168-58ff-8610-2bf2b173abca |  | note | ---------------------------------
label | dd63fe2f-f2a9-524d-8286-52d7894eb559 |  | note | CATEGORY: IP
label | 1869fd24-4964-5d0a-9e6d-f6028f91134d |  | note | ---------------------------------
label | ebd3f927-0fdc-594a-9c9c-56640fe49fea |  | note | RESPONSIBILITY: SE
label | 0f5dcba4-64be-5110-9284-b27ed2abe28f |  | note | ---------------------------------
label | 6321e96b-e970-5db7-8ec2-77404b531ef5 |  | note | VERIFYING DOCUMENTS: This ITP
text | bfe23dd3-021f-553f-8304-b4f985c23e3c |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.10 Pipes-Trench Excavation
label | 4d14f358-afa0-51c6-ac56-3ab0905bce8b |  | note | REFERENCE:
label | 5fd7bf4f-2ea0-53b4-bfe4-16091c76165e |  | note | IFC Drawings
label | 84365ac4-e233-573e-8080-3e5bd9fb58ac |  | note | Section 701.15
label | 949e2451-0807-555e-ae73-104ec26499fb |  | note | ---------------------------------
label | 37b6640e-54fa-507d-afdd-9cc6b18b13ab |  | note | ACCEPTANCE CRITERIA:
label | abd7a860-0881-524f-b8b9-f3c1ba0e51a6 |  | note | Excavation for pipe shall have a horizontal clearance between the pipe and the excavation wall of:
label | 56256ba5-a5a1-5e50-81d3-47b8a2e78e65 |  | note | > 300mm, < 600mm for RCP
label | c546965e-3e80-5d1f-967f-ac998f4dd9e5 |  | note | > 150mm for Flexible Pipe
label | f9e0d5ea-ad14-5832-90f3-aff6f02a6244 |  | note | The base of the trench shall be compacted to refusal using mechanical plant.
label | c1bf97ab-121a-5a78-bef7-a03183fb6ff4 |  | note | ---------------------------------
label | 8dd74a29-f481-5ce3-b6ba-96237fa35cfa |  | note | METHOD: Visual inspection
label | 82a0d95a-553a-5761-a6e5-59f0ad44375d |  | note | ---------------------------------
label | ee5aec51-0f4c-517d-84ef-ef67b4ccf78d |  | note | FREQUENCY: Each Lot
label | bb052810-abda-5583-b528-84c166b2818d |  | note | ---------------------------------
label | e249fb66-6291-5961-b80b-6836d48035a4 |  | note | CATEGORY: IP
label | 2d017219-2582-5d0e-8edc-3c9f44fe6e82 |  | note | ---------------------------------
label | f5a3d236-3c4c-5420-b1c7-c9966d87c7f9 |  | note | RESPONSIBILITY: SE
label | 5b9a58f2-e2be-51a4-a7ce-9c633db9f004 |  | note | ---------------------------------
label | 2e68f86a-1561-5d5b-b7ed-8a687cdeca7e |  | note | VERIFYING DOCUMENTS: This ITP
text | 479691f4-0a47-55b6-9e35-e3ae7e0cfa89 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.11 Pipes-Bedding Placement
label | b4e3f79d-f3d8-51d0-a352-f3a25736235a |  | note | REFERENCE:
label | 1f271d1e-9b55-532c-b7a8-4ac68366e507 |  | note | IFC Drawings
label | 08948b4d-71a5-5d7a-8d51-6cec79015c7b |  | note | Section 701.16
label | 293a7ef2-cb0a-51d2-8779-18da5a6f771f |  | note | ---------------------------------
label | 744abee5-8722-53c7-9751-32fa4d5be873 |  | note | ACCEPTANCE CRITERIA:
label | 06893c25-64c7-56f3-b8d4-02caec541940 |  | note | Bedding material shall be provided and placed in the full width of the trench to the below minimum:
label | a04833af-65d1-5772-8c0c-ffb40d41a80e |  | note | > 100mm where D<1500mm
label | 5f1d119f-42e0-5f45-a559-2d170dd2fa7b |  | note | > 200mmwhwere D≥1500mm
label | 00522a45-06d2-5053-a3ac-bae07e8398f3 |  | note | Bedding material shall be placed and compacted in layers <150mm loose thickness
label | e54a318c-cfd3-5a72-90e2-5ca0704b28eb |  | note | ---------------------------------
label | 0bd577d0-595f-5cfc-a9ec-44bfa92a6925 |  | note | METHOD: Visual inspection
label | 8660f428-3cd5-5e96-94b2-465452d8d5d5 |  | note | ---------------------------------
label | 2a0f0780-9f96-5589-b966-c29bd72f4e21 |  | note | FREQUENCY: Each Lot
label | d024a489-4f9e-51be-a76b-8056a91992fa |  | note | ---------------------------------
label | 4b17f5fb-4c37-5e7d-b702-345208d43042 |  | note | CATEGORY: IP
label | 2a3001f6-db6f-520a-96bb-88d22c1f1c16 |  | note | ---------------------------------
label | 32545f4b-a18e-5a92-9aab-913d6f8ba3ef |  | note | RESPONSIBILITY: SE
label | f2649f91-0bc4-5676-8240-f970d2f3c213 |  | note | ---------------------------------
label | 50d4adc4-dccf-5df1-8788-4c449f2aab26 |  | note | VERIFYING DOCUMENTS: This ITP
text | 03c6db59-6e3c-5036-890f-ad8c5710bb49 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.12 Pipes-Placement of Pipe - RCP
label | 06e15bf1-5e65-5e63-af80-b67d4271856d |  | note | REFERENCE:
label | 9f159d52-ee9d-5fbb-bbdc-4a54e1a9de36 |  | note | IFC Drawings
label | f44ba8d0-a385-56aa-8c85-de23bc159514 |  | note | Section 701.17
label | 8cf575bb-c238-56f0-908f-8a8c6994c51a |  | note | Section 701.20
label | 44662b7d-def0-5dfb-a7a9-ee492f6dd3b3 |  | note | ---------------------------------
label | a99ae201-8a98-5d54-addc-ead713eb9813 |  | note | ACCEPTANCE CRITERIA:
label | f4fd9ed9-024a-5a61-b0da-9543402805df |  | note | Rebate and socket ends of pipe segments shall be placed facing upstream and be fully entered.
label | 8654a0c8-b700-54c2-8edb-a8d2c66b3407 |  | note | Gaps between spigot and socket are in accordance with the manufacturers specifications
label | aee5635f-d0bf-59d2-83e9-ec4db47117eb |  | note | The lower portion of the pipe shall be in contact with the bedding layer and shaped to accomodate the joint collar along its full length
label | 480de007-bfcd-503b-9b7d-082368669b21 |  | note | ---------------------------------
label | 507f39b5-8b6c-5a78-bfd6-99116e59a4e0 |  | note | METHOD: Visual inspection
label | 9cb8386c-8df3-5a25-a701-9913139c7989 |  | note | ---------------------------------
label | 35149eb1-d841-5eea-85ec-c4b8892f168f |  | note | FREQUENCY: Each Lot
label | 536daa6b-9674-557c-a9ff-9269503e2375 |  | note | ---------------------------------
label | 3eb4e9b8-e95e-55ee-9d66-7f0b19ded748 |  | note | CATEGORY: IP
label | 33ba882c-5051-5202-95e8-c1bc814ba019 |  | note | ---------------------------------
label | 42178f99-3aa6-515e-b50d-a6be12f96044 |  | note | RESPONSIBILITY: SE
label | ed2fbf33-ebba-5c2c-b193-20212630fdc2 |  | note | ---------------------------------
label | cfe287d8-471f-53dd-8ef4-528b8197a0e4 |  | note | VERIFYING DOCUMENTS: This ITP
text | da98a8df-aba4-5824-8f36-5e3a62e3dead |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.13 Pipes-Placement of Pipe - Flexible Pipe
label | 49ebfbdf-ea86-5e48-97a9-7aa8e060cf8e |  | note | REFERENCE:
label | 0e7a30f9-403c-51fd-ae6a-20c2bed782cc |  | note | IFC Drawings
label | 1aee6f40-17f7-5e18-aec9-4cd3f532cc92 |  | note | Section 701.17
label | 5ff76d14-24aa-5a63-9055-57ec70219988 |  | note | Section 701.22
label | 8e1d5d5a-ed66-5524-9ea8-3433af1c11f0 |  | note | ---------------------------------
label | 6d6ef945-6f31-577e-83bb-7b39aa103c90 |  | note | ACCEPTANCE CRITERIA: All buried flexible pipe sections supplied shall be assembled in accordance with the manufacturers specifications
label | 37295e20-5c6f-5405-ac4f-a5355063dd7e |  | note | ---------------------------------
label | 0dcc0960-808e-5429-9466-a4731d1fc196 |  | note | METHOD: Visual inspection
label | 3328b9fd-3ec6-555f-b8c4-ae4d31393d18 |  | note | ---------------------------------
label | 75794902-c9cc-5dab-9027-0c8a077e46a5 |  | note | FREQUENCY: Each Lot
label | 66bd8ac2-2ccf-51d4-b6a3-80c3fc63d5d4 |  | note | ---------------------------------
label | 9a783f71-6ce5-5691-9119-639849057cfa |  | note | CATEGORY: IP
label | 318349bb-5ef0-5d7e-9c26-30ffaa446205 |  | note | ---------------------------------
label | 2b827bf6-0e65-5c73-abbd-a052d0bc6515 |  | note | RESPONSIBILITY: SE
label | 77e31f6b-35ff-59ef-9cbf-56e81a05b03c |  | note | ---------------------------------
label | 551188a0-ade0-541d-ba11-652b68c90708 |  | note | VERIFYING DOCUMENTS: This ITP
text | 2f6c5883-845b-51bf-8a12-104979a91f0b |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.14 Pipes-Lifting Holes
label | 2220f9af-ff2f-52ed-aac9-d03bf5ec5de4 |  | note | REFERENCE: Section 701.18
label | a7b56b7a-123e-51af-8618-145a8c5003af |  | note | ---------------------------------
label | 252e31c8-5dad-5401-be4f-3878c055a07c |  | note | ACCEPTANCE CRITERIA: Lifting holes shall be plugged off in accordance with the manufacturers specifications after the pipe is installed.
label | 3de0cf93-4362-593b-b593-93641fae2513 |  | note | ---------------------------------
label | ccc02da8-a08e-57c8-a380-56e37b105906 |  | note | METHOD: Visual inspection
label | 4a2ccdfd-6139-58a2-9999-485c8d456c07 |  | note | ---------------------------------
label | c14dadc0-c35a-5bcf-9759-eb06022489b0 |  | note | FREQUENCY: Each Lot
label | de0d2bf9-a228-5ac5-a8f2-d91cac94626d |  | note | ---------------------------------
label | ecbeb7b4-5103-5396-87c9-70597a14225e |  | note | CATEGORY: IP
label | 5432f01f-9e75-5a23-871a-a73fdf979b39 |  | note | ---------------------------------
label | bdec262d-f7e1-5339-9689-2f541b3202a3 |  | note | RESPONSIBILITY: SE
label | 2a8401d1-31fd-5ae0-9d26-640b92735419 |  | note | ---------------------------------
label | 1c6583f1-afdc-546b-a3fe-9aa045d97df5 |  | note | VERIFYING DOCUMENTS: This ITP
text | ccaff243-1589-576e-9b5b-c8026af8157b |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.15 Pipes-Survey Conformance
label | 4e3e046b-9436-548c-b924-18289542a040 |  | note | REFERENCE: Section 710.10
label | 66e43c9a-ccbe-50db-b93c-5bce25bea3f1 |  | note | ---------------------------------
label | 6efd62c1-a4a9-56c4-928e-aafe8e7826fc |  | note | ACCEPTANCE CRITERIA: Location of drainage shall be verified by a surveyor prior to backfilling
label | f03dd153-9848-5d65-914a-12f511503aba |  | note | ---------------------------------
label | 639ba107-f120-5a6e-b6ca-c4901be5343f |  | note | METHOD: Visual inspection
label | 113d97b7-2825-5408-baa4-aad946bbcdb5 |  | note | ---------------------------------
label | 27078ed7-3f69-5a5d-83f2-d33c83ceb0bc |  | note | FREQUENCY: Each Lot
label | b2d2ddd4-5524-54fa-9869-98e26432ebed |  | note | ---------------------------------
label | 23f4a3f7-ec1d-5e42-bc7a-f2852cdff7b9 |  | note | CATEGORY: IP
label | c7239f3a-7f1d-5f96-9ccc-563e86980d37 |  | note | ---------------------------------
label | 464423d7-c7c9-5c3c-8123-87285b55b87f |  | note | RESPONSIBILITY: SE
label | 7421cbae-8301-5726-a2aa-11518a8e3d5d |  | note | ---------------------------------
label | d9d24082-7013-5142-95f6-ee729c78e1b0 |  | note | VERIFYING DOCUMENTS: This ITP
text | 74f8c082-903e-5b1a-934c-b3a374e4df6f |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.16 Pipes-Backfill Placement
label | b42df311-ea17-527f-b087-0d83dacdab2d |  | note | REFERENCE:
label | a417b9ab-ba11-512c-8f07-b8698f65b36e |  | note | IFC Drawings
label | b6f41a02-56ef-5f18-a78c-90032e2cb2ce |  | note | Section 701.16
label | 5ea19ec1-2b5d-5e18-b1ab-d891f0b64fa7 |  | note | ---------------------------------
label | 78dadb77-571e-5445-bf05-ce68e99dbdfb |  | note | ACCEPTANCE CRITERIA:
label | b3969438-529e-55d4-9872-f0f309c4dd9e |  | note | Backfill material shall be placed the full width of the bedding material and compacted in layers <150mm loose thickness.
label | 7484e7e9-2e5a-5648-a6d9-5f8a2ac5b138 |  | note | Filling shall not be placed within 2.0m of the open end of the pipe.
label | 8b8831d1-3c7e-5642-8bd7-be573629f0f8 |  | note | ---------------------------------
label | 4bb396d3-abdd-5658-9469-79c799c859de |  | note | METHOD: Visual inspection
label | f9e52bcf-5c66-56db-a804-c6c3260e2faa |  | note | ---------------------------------
label | b09237b9-9ffd-527b-9055-065485aa1c14 |  | note | FREQUENCY: Each Lot
label | 01e7a8fa-d452-5f31-a726-a7a0cf827946 |  | note | ---------------------------------
label | 444c49b4-ab69-56ce-a048-ce28628d2e59 |  | note | CATEGORY: IP
label | e7eb91c9-a28b-53b9-b6e8-84d92d0c4f6c |  | note | ---------------------------------
label | 6e252302-43b3-54ed-bd18-a89a96c204ce |  | note | RESPONSIBILITY: SE
label | 3983c04c-edd6-5ca4-9757-8992ac6a5dd1 |  | note | ---------------------------------
label | f6c8524f-d310-5322-8cd9-cb22fa72eda9 |  | note | VERIFYING DOCUMENTS: This ITP
text | 8517bf81-afe8-53d9-82c9-c0607b82626f |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.17 Pipes-Backfill Testing
label | 820058d3-598a-5434-9968-d4b1f215cdf3 |  | note | REFERENCE:
label | 97677478-e79b-5693-8f53-be7efd687af8 |  | note | IFC Drawings
label | 42458fb1-8e5a-5c1e-8e51-a220620d46ac |  | note | Section 701.20
label | d0a75b39-c421-5666-88a2-1fa0ead6f58d |  | note | Section 701.29
label | 87b5e65d-95c0-5548-bdc0-1f77a9ad0de7 |  | note | ---------------------------------
label | 5569456e-310e-52db-a278-9d5a6e4466c2 |  | note | ACCEPTANCE CRITERIA:
label | 637dd737-3b4a-5793-9646-695f771a8954 |  | note | Test a minimum of 20% of all lots for each culvert. (Lot = 1 layer of bedding or backfill)
label | d9d2d235-8a02-51cd-9f31-5d84aa57d169 |  | note | Backfill material shall be compacted to a density ratio > 97%. Material which has a swell equal or greater than 2.5% shall be maintained at a mean moisture ratio of 92% between the completion of rolling and the placement of overlaying layer
label | 8d08768b-539d-51fa-a131-be2738015d1e |  | note | ---------------------------------
label | 62af36e5-d2a0-5361-b3a1-cbdb9449c428 |  | note | METHOD: Visual inspection
label | 2328ac16-5c30-5008-ba9e-9d8daaa8a648 |  | note | ---------------------------------
label | b506f5c2-df8a-5dc8-80c0-319a8c84eede |  | note | FREQUENCY: Each Lot
label | 0e0c2357-2bfd-543d-9023-e5e4bf97761f |  | note | ---------------------------------
label | 0c33bf99-cb2d-52ee-97b8-a1a8c1881168 |  | note | CATEGORY: HP*
label | 67ed0c34-517d-5ec5-a0d6-916fd1f3f499 |  | note | ---------------------------------
label | 3c8ae780-9e2c-55c3-a312-5b06b73e0638 |  | note | RESPONSIBILITY: Nominated Authority
label | f2ca7ecd-4d04-5125-a1aa-73f817a5fc55 |  | note | ---------------------------------
label | 6865ca43-0d59-516a-8ca4-27359b23bca1 |  | note | VERIFYING DOCUMENTS:
label | 2819332c-48d9-54c7-8b09-276e9dc4292a |  | note | This ITP
label | 7bd7c424-7165-5a55-be1a-337e02d2c2f3 |  | note | Attach record of test report
label | dd3786f4-0147-56bd-a8d5-d35a095fd7eb |  | note | Attach material delivery docket
text | b7040397-4b83-56c2-839a-a7ab5173d048 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.18 Slotted Pipes-Trench Excavation
label | b5b245ef-a343-5534-b357-d5751cb70886 |  | note | REFERENCE:
label | fd9c6005-9307-5731-bee3-cbcaf2424f03 |  | note | IFC Drawings
label | 00f15a06-c160-5044-80ec-793490fb78c6 |  | note | Section 702.08
label | 7849dc5e-af99-5882-8e28-fb7cc3e2d3a3 |  | note | ---------------------------------
label | 46eca9e7-2dfd-59f4-8eac-f80d30592d4f |  | note | ACCEPTANCE CRITERIA:
label | 78dd904f-e15c-5237-a785-a6682f9d34f8 |  | note | Excavation for pipe shall have a horizontal clearance between the pipe and the excavation wall of > 150mm for Flexible Pipe
label | 5cceb90b-6782-58c1-8c13-f6c38d7a8a3f |  | note | The base of the trench shall be compacted to refusal using mechanical plant and be <50mm below the specified level of the invert
label | 53574fcd-13a1-500f-b6cb-87955612b7e6 |  | note | ---------------------------------
label | d60d3d4c-f27e-5e4c-a57c-a77b58eb762f |  | note | METHOD: Visual inspection
label | 9eb1f72a-8b8a-5dbe-8ea2-23f9a13dd834 |  | note | ---------------------------------
label | 61a6f493-76e7-5758-b8f4-cc46820d6bfa |  | note | FREQUENCY: Each Lot
label | 6c8e0eb8-6fa8-5733-9f41-0f755974c27a |  | note | ---------------------------------
label | f2cc37ab-1376-5aff-9293-f31b6ad809b7 |  | note | CATEGORY: HP
label | c6884d8b-2da2-5951-b92d-662f96a4dba2 |  | note | ---------------------------------
label | c6ccdf9a-cd1f-5b08-8a2b-f32728e81ef6 |  | note | RESPONSIBILITY: SE
label | c7b18488-e8f2-5863-b340-30c60a8472c2 |  | note | ---------------------------------
label | 4203bdbb-7783-579a-90c7-093dd285340d |  | note | VERIFYING DOCUMENTS: This ITP
text | 38c7ce53-c0c4-5860-b190-eedfc9b24c89 |  | textbox | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 5.19 Slotted Pipes-Geotextile placement
label | 05c5ab3a-2513-5cc5-890d-0a6ab7a5057a |  | note | REFERENCE: IFC Drawings
label | dd2eced2-721d-5ac9-b794-d486f193e8e0 |  | note | ---------------------------------
label | 33ad62bd-d418-5d95-b9a5-4b5cbae0655b |  | note | ACCEPTANCE CRITERIA:
label | 84be3a73-e262-50ed-a59d-098fb71ab197 |  | note | Trench to be wrapped with geotextile in accordance with the manufacturers specifications.
label | e90bcdda-7b4d-50f6-98ec-823a0e01bbf2 |  | note | All laps are to have 150mm lapped at the top of the trench
label | 68796600-c8b9-5a1b-abb6-f95efb7e6f17 |  | note | ---------------------------------
label | f4b72f64-aa07-5175-83da-1d97b970feb7 |  | note | METHOD: Visual inspection
label | c1609c5e-f9a8-576d-a45d-e754cb049829 |  | note | ---------------------------------
label | eb35193d-0047-5825-b6ca-427df50a6b63 |  | note | FREQUENCY: Each Lot
label | a6c68a3b-952f-58dc-9774-c97958253321 |  | note | ---------------------------------
label | 37a2a97a-3c03-5cd4-9dba-0e4ed8a731f7 |  | note | CATEGORY: IP
label | ae432d08-f7e7-5787-ac6b-4879877a5213 |  | note | ---------------------------------
label | bc84a794-f8b8-5370-8112-fe4c0f8c5147 |  | note | RESPONSIBILITY: SE
label | 997a0894-e01c-50e9-ba90-0f12d6cd874d |  | note | ---------------------------------
label | 757b103a-4a58-58bd-a299-039a4e8a0fe1 |  | note | VERIFYING DOCUMENTS: This ITP
text | b6d580f2-adcb-5e0f-8253-379690996400 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.20 Slotted Pipes-Bedding Placement
label | eb16a4d1-0372-5539-8fd3-6ad01a7534a5 |  | note | REFERENCE:
label | ece36646-006a-597a-8478-ed4385431db2 |  | note | IFC Drawings
label | 6a3f3ccb-54b4-5749-857e-7875d0c15018 |  | note | Section 702.09
label | 32561caa-4556-5965-a497-6bac3b254dca |  | note | ---------------------------------
label | 0f09302e-7ca9-5d2e-a52d-b1bf7807ffc3 |  | note | ACCEPTANCE CRITERIA: Bedding of granular filter material of thickness between 25 mm and 50mm placed across bottom of trench and screeded or graded to level
label | aa71f248-538f-5d28-b394-9d2310b0c95b |  | note | ---------------------------------
label | 046e77e6-5b32-52de-9f5e-b45cd8a9aefe |  | note | METHOD: Visual inspection
label | d02a8581-bf3e-5a0b-aeea-1036deb8a464 |  | note | ---------------------------------
label | 0acd30a6-ed9a-516e-9290-df75fe125c05 |  | note | FREQUENCY: Each Lot
label | a0412db0-c9a3-517b-8881-d3a975d16584 |  | note | ---------------------------------
label | e5ac17ec-613e-5265-8e6e-03cf9a0b2e40 |  | note | CATEGORY: IP
label | 71a615d4-c89a-5fc5-8970-170e20e73ebb |  | note | ---------------------------------
label | 1c4cc3d2-78b1-554c-88b8-6c706f11e7f2 |  | note | RESPONSIBILITY: SE
label | e6dbfb76-1f8d-58b7-86e2-62848202eb70 |  | note | ---------------------------------
label | 0a363582-3953-5b1d-b756-362161b53dcb |  | note | VERIFYING DOCUMENTS: This ITP
text | e843858f-db7b-5e7b-a95a-6c8c6aa05377 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.21 Slotted Pipes- Placement
label | cdd94068-ed09-5ee3-bc60-0c686f48ad0a |  | note | REFERENCE:
label | d9876986-0981-5c73-a942-0c1097f3b275 |  | note | Section 702.03
label | 66891bda-c8cd-569e-b93b-a5a2b2d98338 |  | note | Section 702.09
label | 608b563c-e99f-58cf-ac03-c89085233dda |  | note | ---------------------------------
label | fcd85316-eb06-5036-ab23-ac1bb154d9ae |  | note | ACCEPTANCE CRITERIA: Pipe shall be placed centrally in the trench on the prepared bedding. Slotted pipes shall be laid with the opening in the lower half of the pipe.
label | d3e68be9-5e20-5774-81d8-4eadab521d5b |  | note | ---------------------------------
label | a9ebddb6-64a7-5337-bc82-9ad595313389 |  | note | METHOD: Visual inspection
label | 1eb6e129-a718-5c29-9169-52d7972bc473 |  | note | ---------------------------------
label | 98ee3056-7438-5ad5-95b7-e9b9134a51a7 |  | note | FREQUENCY: Each lot
label | 0601b374-12a9-5961-8a0d-004e0843e1a6 |  | note | ---------------------------------
label | e1aaba7a-b7b6-5c2a-b590-f958ff0a61fc |  | note | CATEGORY: IP
label | 3ab7e929-cce3-5e20-a89f-c8b07616abfd |  | note | ---------------------------------
label | 2bc8aa86-d197-59f6-a1e8-c6adf92bb499 |  | note | RESPONSIBILITY: SE/Site Supervisor
label | 58fc6651-3614-58e6-922a-a70bc3a2253c |  | note | ---------------------------------
label | 4addd832-5db7-57da-aa7c-e1224cb0aaac |  | note | VERIFYING DOCUMENTS: Sign ITP
text | a73b1f53-027f-564e-ada9-cdadb0bd57f9 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.22 Slotted Pipes-Backfill Installation (Granular Filter Material)
label | 044baaac-a67b-5053-a032-56198d64febb |  | note | REFERENCE: Section 702.09
label | 238f0ae0-adff-566b-8172-0a2435c65c39 |  | note | ---------------------------------
label | 2fb73e0f-b078-55ec-b25d-d7f7044a1f38 |  | note | ACCEPTANCE CRITERIA:
label | efb7ee9f-8379-5ed9-b495-8cbb21ad66a6 |  | note | Material shall be placed moist and compacted in layers not exceeding 300mm.
label | f19bae9b-57a4-5d1c-aeab-30aeff2e650a |  | note | The method of compaction shall be in accordance with the procedures and reviewed by the NA.
label | 3829893a-134e-5fed-b37a-4b7185ab8440 |  | note | ---------------------------------
label | b746ee56-d877-5035-a2e6-b6fb2054c643 |  | note | METHOD: Visual, Doc. Review
label | b830b5d3-68ef-5c1b-960f-59946746042b |  | note | ---------------------------------
label | 198de62d-2057-5272-97ea-d5910c89f6a5 |  | note | FREQUENCY: Each lot
label | 3ba3f732-fd4a-5b4d-afbc-8f7ec22206fc |  | note | ---------------------------------
label | d13d54dc-28ce-58b8-ac47-c70104268209 |  | note | CATEGORY: HP
label | 1c5331c0-4470-584a-9539-4552b03267b1 |  | note | ---------------------------------
label | 94bc40c1-5bf0-56d4-a5aa-3f08a275debe |  | note | RESPONSIBILITY: SE, NA
label | 676a91d2-4a40-5786-9e7e-17f1aaf61242 |  | note | ---------------------------------
label | 939c8c1d-47e7-5668-92ec-a1001062189b |  | note | VERIFYING DOCUMENTS:
label | 42892726-ebc9-582c-b412-95ef849188f4 |  | note | Sign ITP
label | f4fd2f82-6ff9-5cef-9a23-81cc94471173 |  | note | Attach Backfill Delivery Dockets
text | 7a22b10a-6610-5d63-8233-605a8a6ca72d |  | textbox | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 5.23 Slotted Pipes-Backfill Installation (No Fines)
label | 974522fc-aa36-5435-a088-ecf04e9e91ac |  | note | REFERENCE: Section 702.09
label | 5e5fce74-fb8b-527f-8335-ac8db46896d1 |  | note | ---------------------------------
label | e7186fd4-c6dd-5211-9416-c889bbe23286 |  | note | ACCEPTANCE CRITERIA: All subsurface drainage shall have no fines concrete filter medium. No-fines concrete placed and compacted within 1 hour of mixing
label | ae0dd1e7-3c62-596c-baf7-f8389fe2c0db |  | note | ---------------------------------
label | fda5e73b-5f11-5966-a540-fa5ce7b2dc08 |  | note | METHOD: Visual
label | a34c7f77-4614-5161-981d-804a502e7544 |  | note | ---------------------------------
label | 4eff83fc-9bb8-5066-8ce3-0821e1ccddb9 |  | note | FREQUENCY: Each lot
label | a97903e2-6362-591b-bf96-6d75e9ea9101 |  | note | ---------------------------------
label | 9cf93d9c-579c-56c7-8aa4-e624d5f230ed |  | note | CATEGORY: HP
label | b11b403b-e023-5d8e-aff7-00a60fe71cff |  | note | ---------------------------------
label | 304c56c3-f9cd-52bc-8f42-c73d22f08315 |  | note | RESPONSIBILITY: SE, NA
label | f7bc0362-c179-5e7c-9c7c-dce7873bb7fb |  | note | ---------------------------------
label | 20145e76-99ff-5337-906c-6e5a38042ed6 |  | note | VERIFYING DOCUMENTS:
label | 1900f08c-ba76-5f98-b5dc-384faed8a9f2 |  | note | Sign ITP
label | ad9d87d0-1611-58a7-bb3d-fb47f156b079 |  | note | Attach Backfill Delivery Dockets
text | 33adaa53-2897-5bb4-8338-fd1757b6eba6 |  | textbox | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | Post-construction / Post-installation Activities
checkpoint-status |  |  | checkpoint | 6.1 Flushing & CCTV
label | dc85a34b-ce40-57f4-bb58-ea98e113d82e |  | note | REFERENCE:
label | e702f4e6-55c7-5f80-aec2-51319c6a0ebe |  | note | Section 701.28
label | c6a499fb-665b-5a03-b480-1ad8a7e8278f |  | note | Section 701.30
label | c5217ef7-9f45-53c8-9a88-08d0db5345a1 |  | note | ---------------------------------
label | e43a0c02-be3c-5e1e-bd59-90b00d6ea889 |  | note | ACCEPTANCE CRITERIA:
label | b0a45514-25a0-5c0f-adca-0f449a05deb6 |  | note | All pipes shall be flushed clean from end to end on completion
label | 72ec1625-98ba-545b-9717-2be8a5c37679 |  | note | All drainage lines shall be inspected after completion of earthworks to subgrade level and prior to construction of the pavement layer by an independent testing organisation using CCTV
label | e4a53ddc-8a69-5e84-b2a2-4684abfa30ab |  | note | ---------------------------------
label | 5e895991-d071-5988-b5be-69fb39ec04ec |  | note | METHOD: Record Review
label | d1903101-56a4-5b73-a0e2-fe65df214dee |  | note | ---------------------------------
label | 90686740-0360-5e95-86a3-95d728fb5b7b |  | note | FREQUENCY: Each lot
label | ecd1f3bb-6f66-5caa-97cb-a63f63d6952f |  | note | ---------------------------------
label | 935734cb-3dfd-5130-be07-3b53c19c6589 |  | note | CATEGORY: HP*
label | 46ef9af9-cc1f-593b-a252-930f1d5f95a6 |  | note | ---------------------------------
label | c430aab2-af78-51d2-9a07-167000ee2e39 |  | note | RESPONSIBILITY: Nominated Authority
label | 249354c1-6db3-5e14-aff6-d033594a6a1f |  | note | ---------------------------------
label | 20e2c0c6-fec4-5643-9a2a-2d07330bbaec |  | note | VERIFYING DOCUMENTS:
label | a429cdb7-91ac-5952-bf05-eee6a2bac67d |  | note | This ITP
label | 3fcb9b40-a31b-56bc-adb5-036189305105 |  | note | Attach Inspection record
text | 2f98c48e-6edc-59d2-a7ba-87898266fe4f |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 6.2 As Built Information
label | 48796809-da90-5ef8-b819-d095dab9c113 |  | note | REFERENCE: Section 701.10
label | 081ba7f1-0a9a-50e5-8e1b-cf589fbf98fc |  | note | ---------------------------------
label | 00141b82-678e-523e-8877-c7cc3efe2597 |  | note | ACCEPTANCE CRITERIA: Provide record of dimensional measurements to demonstrate the drainage is within the tolerances specified in 701.10
label | bd8d4df5-e55d-5a75-b525-8a4aecfba789 |  | note | ---------------------------------
label | 7cc3b521-5216-5d8a-b287-597d3ad9e499 |  | note | METHOD: Document Review
label | 1ce55bc9-0394-538d-871a-83ca85a6d174 |  | note | ---------------------------------
label | 22c7c124-c0d8-565b-b961-a7b01e77d2ad |  | note | FREQUENCY: Each lot
label | 05da4a4e-c905-58e1-9ec4-6d182e89e495 |  | note | ---------------------------------
label | a61c2355-dd35-57eb-b4b6-c747d2e38e58 |  | note | CATEGORY: IP
label | b8965b1c-d73c-5990-ac40-858c00230bfb |  | note | ---------------------------------
label | 47950599-6932-53d6-920f-0b306013bbc6 |  | note | RESPONSIBILITY: SE
label | 4494bc3d-d4c6-5769-99ed-dcdb10c19075 |  | note | ---------------------------------
label | dd0c8171-f023-5c45-aefe-8cafbdb8b81e |  | note | VERIFYING DOCUMENTS: Attach Survey Conformance Report
text | 8193a011-7cf0-54bc-a7d8-54084df7c2a7 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 6.3 Non-conformance Report (NCR) Closure
label | 7282d987-74e1-598c-b48a-ac8e0d0d9fa7 |  | note | REFERENCE: MRPA Quality Management Plan
label | a0aa31ed-567e-549b-b6a9-6c9db4f99509 |  | note | ---------------------------------
label | 58939b71-f09f-5147-9df1-c2b6fa7aae66 |  | note | ACCEPTANCE CRITERIA: Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed in Teambinder
label | bd757316-40c7-520f-b8b2-b538e23b49b3 |  | note | ---------------------------------
label | faeac183-b317-53b4-93ce-10fa785b2b8f |  | note | METHOD: Document Review
label | 5725ff7b-27f6-5efb-8770-958fc629bf06 |  | note | ---------------------------------
label | 5d2e5fed-b16d-5b89-8561-7957647bf728 |  | note | FREQUENCY: Once, prior to closure of this lot / element / Work area
label | 62d298c7-3a73-5a4d-8add-e422b03b5af9 |  | note | ---------------------------------
label | 08cc5676-d90d-55f0-ac31-4bdafac9b211 |  | note | CATEGORY: HP*
label | 7bc906e3-8b2d-5ba3-9575-90f35cbbe589 |  | note | ---------------------------------
label | 48846afc-24e4-56a9-8f11-99aae2179fd1 |  | note | RESPONSIBILITY: SE/PE/SPE
label | e8b09220-5dbf-53b0-a2ac-0a84d2cf6e69 |  | note | ---------------------------------
label | 7ff47de5-2b43-55ba-be2d-4a6c98c34d73 |  | note | VERIFYING DOCUMENTS: This ITP
text | d80159cb-e873-59e7-a5c6-d5c44bc799b7 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | Metropolitan Roads Program Alliance Final Inspection
label | aaa886a7-9224-551b-83ed-a507a443a674 |  | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
text | b6b1953f-c577-592c-95d2-7f1f15ea7bdf |  | textbox | Name:
text | 805d8c22-d1f8-5270-ac6a-526bd44ba46a |  | textbox | Position:
text | 1704ad4a-c42a-59f0-85a2-e5925c9d132c |  | textbox | Date Completed:
holdpoint |  |  | signoff | Sign ITP
checklist-sectioned |  |  | checklist | ITP-CIV-CAMMS-Ausnet Conduit Bore Rev 0 | itp |  |  |  | Yes | ITP-CIV-CAMMS-Ausnet Conduit Bore Rev 0 | ab7ef30d-9104-43f1-81a8-85781b69b393
checkpoint-group |  |  | section | Referenced Documentation
checkpoint-no-status |  |  | checkpoint | 1 - Referenced Documentation
label | a26e48ca-b62c-51ca-8723-7ab126cffe3e |  | note | Document Title: Ausnet Conduit Bore
label | 30c8b4d5-4fe9-5295-adc4-47450294b45c |  | note | ITP Description: Ausnet Conduit Bore
label | 9c308e30-e4b0-5a8d-b7af-3b006641a8d9 |  | note | Discipline (e.g. CIV/STR/RAIL: CIV
label | 91b37566-1552-5d58-8638-cde75f95933b |  | note | Revision Number: 0
label | e41ffb9f-bd40-5eaf-ba98-7acedefbf593 |  | note | Revision Date: 29/07/22
label | dda31d16-1b1e-5b22-85cc-2f96ce9ce57c |  | note | ITP created by: Michelle Lim
label | 99dbeb7e-3aeb-50ef-90d3-381b7810fa29 |  | note | ITP approved for use by: Aldrin Guinchoma
checkpoint-status |  |  | checkpoint | 1.1 - Non Dependent
label | bc9916e0-20c6-59a2-87b6-1615ffd8efdd |  | note | Reference - IFC Drawings
checkpoint-status |  |  | checkpoint | 1.2 - Non Dependant
label | 0b9f5de9-b824-5e8e-9daa-e5f959b24395 |  | note | Reference - AS 4799-2000
checkpoint-group |  |  | section | Preliminary Works/ Materials
checkpoint-status |  |  | checkpoint | 2.1 - Electrical Conduits
label | 2343d2fe-2fbf-58f3-a170-3631321a40fc |  | note | Reference - IFC drawings
label | da2bd1ba-c775-5868-a730-b8caf76a41de |  | note | Acceptance Criteria - Conduit crossing railway to be heavy duty PVC 150mm Id/180mm OD Grade PE100, SDR 13.6
text | 6964125a-a17b-57b2-84af-b8d4d02f7345 |  | textbox | Reference:TeamBinder Material Approval Number:
label | 29590f1f-f2bc-5bde-b12d-3a36f06a6472 |  | note | Method - Document Review
label | e6b2bc50-f99b-5912-8303-16252bef7a44 |  | note | Frequency - Prior to commencement
label | fd5d8759-b47e-5c94-b6f8-58e28e24d3ae |  | note | Category - HP
text | 92bc40ef-ca10-5d7b-b318-4b26bb007cf8 |  | textbox | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.2 - Grout
label | 75c1fa61-6377-5e69-8af8-4659f9163703 |  | note | Reference - IFC drawings
label | 91bc332c-dd2d-5b3d-8967-3b49547074e7 |  | note | Acceptance Criteria - Cement based grout shall be flowable, self leveling and non-shrink
label | 93c779a7-ea85-576e-a5d1-eb8db5984434 |  | note | Grout of the minimum UCS of 2Mpa at 28 days shall be used to fill the abandoned conduits
text | 850d6ace-d689-570b-91f9-ac9d9bd4cc53 |  | textbox | Reference:TeamBinder Material Approval Number:
label | 9b099fd6-ff6f-5cf4-ac7f-3055ee1d302a |  | note | Method - Document Review
label | 9c5d70ed-4d41-5f33-87ae-825287748566 |  | note | Frequency - Prior to commencement
label | 8735742d-2fa8-5080-81a5-f1777e90bbd3 |  | note | Category - HP
text | 05b7f63c-347b-567c-b685-c82a50a43146 |  | textbox | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | Preliminary Works/ Procedures
checkpoint-status |  |  | checkpoint | 3.1 - Check that current revision drawings are being used
label | 99777746-3b6b-54a3-bdbb-5ad15a4628cd |  | note | Reference - IFC drawings
label | 81a0fcc0-4396-5285-a79b-d6fa80110be2 |  | note | Acceptance Criteria - Drawing revison must be confirmed with the design manager
label | 2defc7ca-d5fc-5ab8-b41b-a9fcc8176091 |  | note | Method - Document review
label | 79e90360-dd08-530d-b5b5-c04977b7b082 |  | note | Frequency - Prior to commencement
label | f29d6c3c-0a33-56f9-9361-350e1492698a |  | note | Category - HP*
label | b2f0579c-60ad-59ca-ae41-4b2db75f9614 |  | note | Responsibility - SE/PE/SPE
label | d6e9d375-5f03-5a22-8960-ca2e2df1acb2 |  | note | Verifying Documents - Design drawings.
text | 3feb5f7a-9a2a-5c70-b6c8-79e073e96022 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 3.2 - Grouting Procedure
label | 9b1e0cd3-546d-596b-92b3-ba8e567ce26c |  | note | Reference - IFC Drawings
label | 05580c18-232e-55aa-9fe8-68ec00e9c65f |  | note | Acceptance Criteria - Volume of abandoned conduit to be calculated to determine amount of grout to be used. This should match the grout delivery volume.
label | 2db1fbcf-be2c-57bb-a754-95c08875e417 |  | note | Method - Measure
label | 211d07da-bd4a-5128-8ffd-82449ca17a82 |  | note | Frequency - Prior to commencement
label | 5056b12d-511a-53d5-a0d3-02a9bc9bbde4 |  | note | Category - HP*
label | 04bc4de1-a3b9-55ea-bd47-96122e0b65fd |  | note | Responsibility - SE
label | 9a1906bb-0cfa-587d-902c-5eb73958eb8b |  | note | Verifying Documents - Calculated grout volume used Grout Volume
text | d3faaeb5-1f84-5558-8a1f-3e8fa4fded80 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 3.3 - PE Welders Qualifications
label | 6b508fe2-235e-5971-97ab-47d23ec6882b |  | note | Acceptance Criteria - PE welders are to be pre-Qualified
text | ab0b19f9-77e8-539e-8e18-99440450cf9a |  | textbox | Reference:Teambinder Hold point release number:
label | 72bba6b6-e4c5-5670-b070-aaf34aa7ae41 |  | note | Method - Document review
label | c73974b3-ecba-5fa8-84e8-7b573c53de2a |  | note | Frequency - Prior to commencement
label | 9c03e138-3a75-5f29-a298-4095de4a49c0 |  | note | Category - HP
label | 23c5c349-ea8c-521d-9726-da87ebea809d |  | note | Responsibility - SE/PE
label | 8ed28ce6-9254-52a8-a0ba-cf3f32d5c972 |  | note | Verifying Documents - Teambinder approval number
text | b7e8583b-73e1-54a5-9da3-7b52dd9e2ac3 |  | textbox | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | Pre-construction / Pre-installation Activities
checkpoint-status |  |  | checkpoint | 4.1 - Survey Set-out
label | 4d6d00cd-1a01-5b44-9945-0dd8607a6d9f |  | note | Reference - IFC Drawings
label | f249b66e-5d8f-5788-8871-e67414f2d4f4 |  | note | Acceptance Criteria - Set out line and level of drilling works.
label | 02910dca-3067-5f70-82b2-0523a89d3633 |  | note | Survey to mark out existing services.
label | b0c5b90a-4c27-5b3c-9c43-b3d4694a941c |  | note | Must maintain a min. of 600mm clearance to any existing service and a min. 3m clearance to any Railway Structure UON.
label | 69deff03-f4a2-5285-bb54-5b86de012ee1 |  | note | Method - Measure
label | 91f73fa2-671d-5a44-82b3-485aa0e8f5f9 |  | note | Visual
label | c6f46eeb-67b1-53a0-a4c2-bcee233a7f9b |  | note | Frequency - Each element
label | 02905057-281d-566f-968f-1c7cae60bf66 |  | note | Category - IP
label | 3f05978f-76bb-58ed-95f9-27ac8619ab35 |  | note | Responsibility - Surveyor
label | 126ec3c0-349d-5607-9068-6df1851d725b |  | note | SE/PE/SPE
label | a1e9020e-a5bd-5fe8-966e-f984c6c8c817 |  | note | Verifying Documents - This ITP
text | d2086e41-55f3-534d-9576-c20ca3859822 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 4.2 - Draw ropes
label | 6d3e25d7-025e-560b-8480-0acf9a509a32 |  | note | Reference - IFC Drawings
label | 73bda0f5-5ae9-5693-806c-87416ccc126c |  | note | Acceptance Criteria - All conduits must have minimum of one 6mm polypropylene draw rope to AS4142.
label | cbd2af81-e826-5ba5-bbd5-3dbd8fcccabf |  | note | Method - Document review/ Visual
label | 26212195-c1d9-5fb1-9766-41f88c2dd09d |  | note | Frequency - Prior to commencement
label | 84b81427-ee06-5a10-8160-08eb8ee9e258 |  | note | Category - IP
label | a832c7b7-007a-5650-a43b-df369ddd79b7 |  | note | Responsibility - PE/SE
label | 49499d03-92e7-5ebb-9ee7-f9a5568bb9c6 |  | note | Verifying Documents - Material compliance certificate
text | bc6c886e-89fe-5bc1-b561-dcf84650d8e7 |  | textbox | Date Completed:
checkpoint-group |  |  | section | Construction / Installation Activities
checkpoint-status |  |  | checkpoint | 5.1 - Conduit welding
label | c3b66b0c-5a24-50d8-8f23-8ebaa0c35d91 |  | note | Reference - IFC Drawings
label | 671ee394-5dc3-5bf9-bfcd-965aca18d7c0 |  | note | Acceptance Criteria - Joints are to be butt welded.
label | fb84f130-03eb-534e-a955-20be59a268ae |  | note | Weld map to be supplied and identify unique joint numbers.
label | e87e08b8-b525-50f5-ada6-a48cd434f201 |  | note | Butt Welding records to be supplied.
label | db525af3-789a-5e09-9fc6-153329a1b2b1 |  | note | Method - Document review
label | e07eaae2-e233-56c0-94dd-fd703e7fb766 |  | note | Frequency - All Joints
label | 6e99f878-ca45-5faf-86f9-38cb9ddc036d |  | note | Category - IP
label | 2fb0f31f-5cc7-5864-81ba-78322019f59a |  | note | Responsibility - SE/Site Supervisor/Survey
label | bd29357b-b484-5b32-9454-870ce5308fb5 |  | note | Verifying Documents - Sign ITP
label | 40b1a6f4-32c8-53e9-a817-ab803ae438f2 |  | note | Butt Welding Records
text | 8dac538c-6b2c-5ba4-8720-d05d1aa50e01 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.2 - Drill rig setout
label | 4098c95a-3395-5fcc-a36c-9add0022ab74 |  | note | Reference - IFC Drawings
label | 7d7c5e7e-d616-55bc-84b1-2880e0694fed |  | note | Acceptance Criteria - Location as per current Drill shot plans
label | a64fceae-7330-5ca4-a8d6-953006539b35 |  | note | Method - Measure
label | 10cd76ca-f90f-559c-8ff9-d1449e4a1d18 |  | note | Visual
label | 90920f94-88c3-5b67-b189-480585af60f1 |  | note | Frequency - Prior to commencement
label | 80aeab88-0469-596e-8b7b-80f8b6387cba |  | note | Category - IP
label | 9ad8a52c-8435-5db3-8468-311ab2c10cdf |  | note | Responsibility - SE
label | d322de80-7236-5626-8d09-1e7422253894 |  | note | Verifying Documents - This ITP
text | 28999c4f-5db2-544d-b7f4-aae8207efa5d |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.3 - Installation of Pipeline (Trenchless method)
label | 11a7b036-bbee-544c-9b00-139e1d0ae2f4 |  | note | Reference - IFC Drawings
label | b31777de-dcf3-56a0-9a19-cc38e40d8c7c |  | note | Acceptance Criteria - Drill to be installed as per the survey setout.
label | ab965dd5-897a-54ef-b784-0411f61a3288 |  | note | Bore longs to be supplied.
label | 72f20a54-b9fa-57b1-b2ac-e21047fc946b |  | note | Method - Document review
label | 7693b7d1-ef10-501c-a9c2-b3d4b3732e23 |  | note | Frequency - During pilot bore
label | 2e3312e3-9d41-5849-a95c-1fea3b9a483a |  | note | Category - WP
label | c6b0fb06-fddc-5358-a26f-d59a948ad16d |  | note | Responsibility - SE/Site Supervisor
label | 73e9d0e3-4f5c-5763-af0e-984a32dbe654 |  | note | Verifying Documents - Bore logs
text | fa82014c-5479-5938-8afa-e3e877e461d0 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.4 - Plug pulling
label | 67f5321e-e58b-521d-8eae-2c9c05f05f90 |  | note | Reference - IFC Drawings
label | 448d2c5c-314a-5475-97d7-1c648eae780a |  | note | Acceptance Criteria - Mandrel with 90% of the pipe diameter to be pulled thrugh each conduit to ensure the conduit hasent been compressed.
label | d10307e6-3b31-5cf0-b366-e5858a6bb272 |  | note | Method - Record and Review
label | 5560ebe8-4de2-5e36-b15b-e252a20519f2 |  | note | Frequency - All Pipe
label | a6fbabd7-bf5e-580b-af0a-a01135cc6b9f |  | note | Category - HP*
label | 7bf43e90-98df-527b-9154-fb601e10256d |  | note | Responsibility - SE/SPE
label | 890a60bf-8cfb-5fb1-87c3-8f9df3b7072b |  | note | Verifying Documents - Sign ITP
label | 53c6dd31-ef14-518d-8464-fdf775628d66 |  | note | Visual of pipe pull pictures.
label | 1640019e-6d9b-5d24-bd9e-a90b077ecb29 |  | note | Subcontractor Test Record
text | 58f5e790-4501-56e2-91cd-31f4a1756074 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.5 - Draw rope
label | b60f5da9-c484-5def-b9e9-bd848fc23ff7 |  | note | Reference - IFC Drawings
label | 2db17aed-df56-5901-97d3-0dc4ba4c5b44 |  | note | Acceptance Criteria - All draw ropes must be continious between shafts and have 2m slak in the shaft.
label | f77b750d-6503-5bf3-865f-93b0983ef0c8 |  | note | Method - Visual
label | 4703f643-d2f9-55fd-90ec-b0c366ce3931 |  | note | Frequency - All Pipe
label | 784f2e5a-bb8c-5386-bb57-682cbe52f1de |  | note | Category - IP
label | 4ddb5923-708a-52b8-bfd4-8e53553979be |  | note | Responsibility - SE
label | 2d192fba-4d1f-5c96-83fc-d926e03cb8fd |  | note | Verifying Documents - Sign ITP.
text | 017d9f02-16e0-5095-b649-7944757032b1 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.6 - Mixing of grout
label | 33bca5f9-8c19-548f-9c1e-0843ed57fa40 |  | note | Reference - Grout TDS
label | e3174267-d1d6-50f4-91ec-7ae1fe41da08 |  | note | Acceptance Criteria - Mixing and proportioning of grouting to take place as per Technical Data Sheet provided with product.
label | 7d017c6c-cd41-55ce-afff-3c833e68be01 |  | note | Only whole bags of product shall be used.
label | 3e7838de-f2b5-5102-9f72-a4bc59952aec |  | note | Grouting shall not commence when temperature is below 5 degrees Celsius or above 35 degrees Celsius
label | c57a6119-8002-5cc5-a4c7-775dedbc23a9 |  | note | Grout mixture should be mixed adequately and free from lumps
label | e0a4d736-3cd9-5744-b7af-61cab2096126 |  | note | Method - Document review/Visual
label | 02bf9f2f-4570-567d-afbe-28e330e303ee |  | note | Frequency - All pipe
label | 5dd592b3-4981-5454-8583-1f19572746b8 |  | note | Category - WP
label | 484bd8b6-481d-5b7c-b187-0b5bbad93164 |  | note | Responsibility - SE
label | c3407150-afe6-5fac-b05f-5a8fc72d052f |  | note | Verifying Documents - Sign ITP.
text | 467f5742-9aab-5f32-9a0d-fa8444800224 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.7 - Clean surrounding faces and remove excess grout
label | 7d159a76-5ccb-573b-bcf9-4e1fed385f2f |  | note | Acceptance Criteria - Area free of excess grout and spillage
label | 44756d61-da04-5d1f-a669-e3ccce601413 |  | note | Method - Visual
label | b95396d1-334c-51c4-8c10-58a34f14c510 |  | note | Frequency - Each shaft
label | 5eee597c-182d-519f-a626-f06a1ec9c7c7 |  | note | Category - IP
label | 4b3167c9-cf1d-50d3-879a-e5d03bc233ef |  | note | Responsibility - SE
label | b848cd5f-223a-5d60-bbec-97cb8482ae19 |  | note | Verifying Documents - Sign ITP
text | 1baffb45-d45c-59ae-b08b-ebb98944ec4a |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.8 - Curing
label | c9e83b02-cda0-5a4f-8eae-22f910b11ffb |  | note | Reference - Grout TDS
label | 4751d2aa-1264-5796-94ae-f4db9f43bea6 |  | note | Acceptance Criteria - Curing in accordance with TDS
label | 8446b435-dca4-5569-b002-4dcc0731e346 |  | note | Method - Document review
label | 39b2d2fe-5f02-560e-a968-af210f08a29b |  | note | Frequency - All pipe
label | a4aca60f-2214-528e-bda0-47fe8d83ac1e |  | note | Category - IP
label | f39f19b0-54b1-574a-86e0-4aa03c6b0860 |  | note | Responsibility - SE
label | ba62e377-a91e-5c52-bbab-14dcdadffbaa |  | note | Verifying Documents - Sign ITP
text | 55a08de3-95ff-5a85-b1ba-0d433d677674 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.9 - Auditing
label | be960d36-283c-5a4c-be82-7c453f88155b |  | note | Reference - IFC Drawings
label | 38a2d4c6-15e3-5ab9-968f-ca7fa741f20a |  | note | Acceptance Criteria - Auditing to be completed on conduit ends prior to backfilling of entry and exit shafts.
label | 594c9a1e-da59-576f-ba81-8d3943958334 |  | note | Method - Record and Review
label | ea463cb6-db40-5926-9b78-5b93ff4a426a |  | note | Frequency - Alll Pipe
label | 224fa96f-e660-5c4e-b6c6-359ce014a9e3 |  | note | Category - HP*
label | e4c878c2-1584-591d-840c-7671f7965be9 |  | note | Responsibility - SE
label | 7b68420c-237e-5107-96d5-0b38fcbe484b |  | note | Verifying Documents - Sign ITP
label | 8c85c847-9d91-5aea-be5c-a1edfc54d0ad |  | note | Auditing Report
text | 70fa33c0-fa63-5290-b98b-e4e5d97d6902 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.10 - Reinstatement
label | 986a0bdc-25d6-5888-b53b-a702b80a2957 |  | note | Reference - IFC Drawings
label | e88720c5-dfa4-5968-b168-c01b060d14b0 |  | note | Acceptance Criteria - Entry pits, exit pits and trenches to be backfilled with Type A or crushed rock. Backfill material shall be compacted to the same density as adjacent material or as specified.
label | 40624830-4c05-5bc6-b15f-7dc3609c2e4f |  | note | Method - Visual
label | 3c18a4f0-5b03-56c6-82a0-a3fe6fc19287 |  | note | Frequency - Each shaft
label | 69948410-d81b-5fe9-85d5-35f6165c513f |  | note | Category - IP
label | 3e2bc950-50d9-567b-807f-ccb1b71b1aff |  | note | Responsibility - SE/Site Supervisor
label | 4b9b6efc-ac94-5535-a08e-1ef5750f70c6 |  | note | Verifying Documents - Sign ITP
text | aa62c1e9-16d8-587c-98f8-14aec683f009 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.11 - Subcontractor ITP
label | c1b762ff-1a2e-5df1-b4ec-fd671dd3729d |  | note | Reference - IFC Drawings
label | 564480c5-0d56-5cbe-ad97-ef798bde1201 |  | note | Acceptance Criteria - Acceptance and closeout of subcontractor ITP
label | c0389e95-f04f-55a5-bbc3-f47146a7810b |  | note | Method - Document review
label | 5dfead6d-e45f-5af8-9b3f-183e9ebaf84c |  | note | Frequency - Each element
label | 1146556a-28c6-5c6b-84e2-492fc57c0e6e |  | note | Category - IP
label | a298705d-17be-57ed-b2ef-afb11a8d12ef |  | note | Responsibility - SE/SPE
label | 1b9ec0e2-cac7-5c2b-b1b6-63b865f70fd5 |  | note | Verifying Documents - Sign ITP Completed
text | 96db5df5-7f33-588b-9ea1-e7c7872f41f6 |  | textbox | Date Completed:
checkpoint-group |  |  | section | Post-construction / Post-installation Activities
checkpoint-status |  |  | checkpoint | 6.1 - As-built Survey
label | 348b2a25-5039-597c-9699-2aa5d2a30ee0 |  | note | Reference - IFC Drawings
label | a9d7fa61-bb74-54fc-8231-537a2d4e9b34 |  | note | Acceptance Criteria - Survey as built report to be compiled.
label | 9a095dbc-ba18-5551-b2cc-0cd949ad2606 |  | note | Borelog obtained from subcontractor
text | cf4e5a54-ec7e-5fc5-a3fe-e1ab49731c18 |  | textbox | Autocad and PDF reports are to be supplied to:
label | 0f2c3fa9-23cc-57a7-b494-75aba86ea02d |  | note | Method - Document Review
label | 81fb97b8-995e-5363-8073-3a52cf383ab7 |  | note | Frequency - Each element
label | 9e9a1be8-4a74-5bad-befe-ee7280db1635 |  | note | Category - IP
label | a6c4ec19-0368-54f0-bbdd-1740c092f052 |  | note | Responsibility - Surveyor
label | 610ee70e-50a0-5857-8aad-8709b47697fb |  | note | SE/PE/SPE
label | 065d12b0-da05-5bfd-b234-981e87aa3ba9 |  | note | Verifying Documents - Survey As Report
text | 12c70a45-bb1f-5047-b37f-1f6748b6e3be |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 6.2 - Red-line / As-constructed IFC Drawings
label | c4e1e79c-55f6-56a0-aa00-3bfdd7afc265 |  | note | Reference - MRPA Quality Management Plan
label | 016e02f4-3aba-5a66-b2a6-169febb19de8 |  | note | Acceptance Criteria - All RFIs, NCRs and changes to the IFC drawings are captured on a controlled drawing set marked "Red-line", "As-built" or similar.
label | 65d9017c-bfda-5921-9b43-babf38628b85 |  | note | Method - Document Review
label | f5f691a9-f57d-5d5e-a9a1-5d7d7910b352 |  | note | Frequency - Once, after construction of the design package
label | 444930bf-552f-5370-aa75-2dea667f9582 |  | note | Category - WP
label | 34c105df-0c16-590b-a086-ae04a82ee1bf |  | note | Responsibility - SE/PE/SPE
label | 87844509-bd55-5f80-a132-2fe060fe870e |  | note | Verifying Documents - This ITP
text | fecc2c39-f85f-5f31-ba6d-773102a51b5e |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | Final Inspection
label | 709657aa-b366-535c-8439-714812c4f713 |  | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
text | cc5c7067-1a4e-5d4e-878c-c6a4c50777be |  | textbox | Print Name:
text | 2d9c35a5-327f-5d55-8ddf-e84f32b9c8b5 |  | textbox | Position:
text | e29a3a6e-769b-517a-a391-fbd26a88c279 |  | textbox | Date:
checklist-sectioned |  |  | checklist | ITP-012-STR-RSS Wall-Main | itp |  |  |  | Yes | ITP-012-STR-RSS Wall-Main Rev 0 | cff17963-117f-4710-9ec3-3daf3faa28a7
checkpoint-group |  |  | section | Referenced Documentation
checkpoint-status |  |  | checkpoint | Referenced Documentation
label | 5a3c858d-f28d-5a26-a500-cc3ccd289b49 |  | note | Document Title: ITP-012-STR-RSS Wall-Main
label | 81e6080e-17b6-50a5-9007-811886e5a1b0 |  | note | ITP Description: RSS Wall-Main
label | 10c7818b-bed6-5b3c-ae83-424d6ac42aee |  | note | Document Number (in Teambinder): MRP-0000-MRPA-ALT-ITP-00XX
label | ea799ef0-a113-59a5-8e54-c79b86433a9a |  | note | Discipline (e.g. CIV/STR/RAIL): STR
label | 498af1db-14e3-52ff-b944-57a29aa971ed |  | note | Revision Number: 0
label | 6242921e-876c-544e-9f2f-ac537052c48f |  | note | Revision Date: 19/12/2022
label | 79df7bf9-0549-59c1-ae10-a0131f8a60bf |  | note | ITP created by: Victor Mira
label | 2f2c2240-1f4b-5584-aea4-e76720b09432 |  | note | ITP approved for use by: Victor Mira
label | 147c6ce6-a448-540b-81b2-8b6396f4ed00 |  | note | 1.1 Non Dependent
label | 00a30657-d2d0-5182-9580-e3f1bf8c454d |  | note | Reference: VicRoads Section 682 November 2018
label | 48faceb2-6dcc-538c-93b4-9b862336b697 |  | note | 1.2 Non Dependent
label | 84d4e5dd-f2d2-5b91-9285-cc8ec4df3022 |  | note | Reference: VicRoads Section 204 December 2015
label | 8c45244a-453f-5f98-a4de-7c839e660b6a |  | note | 1.3 Non Dependent
label | 0003dad2-c909-5638-8e58-cc337f9b5d93 |  | note | Reference: IFC drawings
checkpoint-group |  |  | section | Preliminaries-Materials
checkpoint-status |  |  | checkpoint | 2.1 Concrete-Leveling Pad
label | ac6e6da8-dfc7-5fbd-a5c6-cd5ea2b452e2 |  | note | REFERENCE: IFC drawings
label | e52c053b-6646-56c9-871e-246989d9df76 |  | note | – – – – – – – – – – – – – – – – –
label | 2e3e43b6-0a5b-520d-86a6-ddf81de9207f |  | note | ACCEPTANCE CRITERIA:
label | e1d913ef-72e0-5001-b24e-90a1ad47f37b |  | note | CONCRETE COMPRESSIVE STRENGTH GRADE MUST NOT BE LESS THAN N25 FOR LEVELLING COURSE AND BACKING BLOCKS;
text | cf8e5207-4ebd-5eca-842f-ed0f7ed8716e |  | textbox | Reference: Teambinder MA number:
label | 17dbc5f6-89f3-5d41-b45c-2f473438863d |  | note | – – – – – – – – – – – – – – – – –
label | 3bd87415-233e-53e2-bf41-8c7984c80b71 |  | note | METHOD: Document Review
label | 1763229c-2a85-5470-b43f-b0326ad14288 |  | note | – – – – – – – – – – – – – – – – –
label | e4f72307-66d6-5faa-b854-22111c158f44 |  | note | FREQUENCY: Each element
label | dc07650c-b347-5554-b8fe-159901d40fee |  | note | – – – – – – – – – – – – – – – – –
label | eb483f7a-ba76-5f7e-8f68-50b77cd21337 |  | note | CATEGORY: HP*
label | dda970fc-b7d7-5411-8e43-aea331a03894 |  | note | – – – – – – – – – – – – – – – – –
label | 6ccf35c6-a5b8-580b-9c04-69e75857281d |  | note | RESPONSIBILITY: PE/Nominated Authority
label | 7d1711a2-562b-53f5-b318-f95c160839d7 |  | note | – – – – – – – – – – – – – – – – –
label | 839571de-373e-58e8-b39b-01735f0d9355 |  | note | VERIFYING DOCUMENTS: Material approval
text | abbfb767-34d4-544a-80d1-95daff0791dd |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 2.2 Select fill
label | a16c16e1-651e-5f63-aa99-33a4a8f863db |  | note | REFERENCE: IFC Drawings
label | b60f344e-a05f-57fe-a3cb-cfa5b801b74e |  | note | – – – – – – – – – – – – – – – – –
label | 9e6acb6b-967a-5087-a334-f1a4a9a055ec |  | note | ACCEPTANCE CRITERIA:
label | 1ce20ea9-aaa3-576b-9d14-db784fad7e0c |  | note | Select fill shall comply with the requirements of the RSS designer:
label | de3aada8-5ab9-5fd8-a6f0-906678e2834e |  | note | UNIT WEIGHT: 22 ± 2 kN/m³
label | 7c436b6a-d2d0-51df-8fb5-7cca9f406982 |  | note | INTERNAL FRICTION ANGLE ≥ 34.5°
label | 529f86fd-741c-5f05-bc70-5f1b4f17845f |  | note | ○ Gradation:
label | 1484a270-60e7-5e3f-9d3e-80064e9d0c35 |  | note | • 150mm : 100% PASSING
label | 4f7d50dd-4d92-5e18-b4d8-212213b5b50c |  | note | • 37.5mm : 60 TO 100% PASSING
label | e0f62b97-6261-59fb-af81-afda8d770742 |  | note | • 9.5mm : 25 TO 100% PASSING
label | 13475b85-6a63-59e0-9a6d-8d4ce6ae4371 |  | note | • 2.36mm : 15 TO 100% PASSING
label | 9951afd5-575d-56c8-b319-1afa017119fd |  | note | • 0.6mm : 10 TO 100% PASSING
label | baab5bfe-bfaa-5698-85db-1e831a6de5a7 |  | note | • 0.075mm : 0 TO 15% PASSING
label | d97e3a73-7176-5426-b13c-39562a7248cf |  | note | ○ Electrochemical Properties:
label | 057062b8-cab0-5792-9a75-375923fd3104 |  | note | • RESISTIVITY >1000 Ω-cm
label | d310a8ed-d230-5a05-b540-5ce5bfd7ae7e |  | note | • CHLORIDES <200 mg/kg
label | e0002a05-caf5-530a-8e87-e39ace8b8f70 |  | note | • SULPHATES <200 mg/kg
label | 24bf6a1f-9cb2-5048-9572-82a9466c9df1 |  | note | • ORGANIC CONTENT 0%
label | c446fcb9-2056-59c8-abe2-f2fbe4de6926 |  | note | ○ Structural Properties:
label | 2f69d07d-e8a3-5af6-a12c-da001c7a6597 |  | note | • COEFFICIENT OF UNIFORMITY ≥ 5
label | 395b2a51-bcf3-5c99-a950-b62a1738aca1 |  | note | • LIQUID LIMIT ≤ 30%
label | 10daa424-35a9-5070-bff5-47c50c6bc3c5 |  | note | • PLASTICITY INDEX ≤ 12
label | 5ff27ccd-6ed0-5f2b-9bbc-62043614a8cf |  | note | ○ The select backfill must meet the minimum requirements of Vicroads Type A filling
text | 76697044-1b1f-5854-9fb7-c6f3d398c50f |  | textbox | Reference: Material approval in Teambinder
label | 1848b70e-4d6f-5cc6-b353-5daaffb7ba0e |  | note | – – – – – – – – – – – – – – – – –
label | de263bd7-ecdf-54cd-a93b-6fcd7acc0782 |  | note | METHOD: Document Review
label | c59a7622-d7c7-5e60-8495-daacd4b9b9e1 |  | note | – – – – – – – – – – – – – – – – –
label | a6d902ba-0fb7-54a0-8b54-1d6890ce558f |  | note | FREQUENCY: Each material specification
label | 40bf56a7-78ac-589e-bc6f-e910b25059ec |  | note | – – – – – – – – – – – – – – – – –
label | 20e58292-a9a5-5365-80ef-32c028bf3631 |  | note | CATEGORY: HP
label | d5d9791c-fd78-50cb-b9ce-5b29c0abe554 |  | note | – – – – – – – – – – – – – – – – –
label | 33088e73-7560-5967-97af-115e80542c20 |  | note | RESPONSIBILITY: Nominated Authority
label | fc955469-8f6f-5597-8640-b930ec4ebbeb |  | note | – – – – – – – – – – – – – – – – –
label | d7c56057-a830-5666-ae5d-97c026ad739b |  | note | VERIFYING DOCUMENTS: Material approval
text | 073208f0-c097-5d8a-9f07-3f3c69abe4d0 |  | textbox | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.3 General fill
label | 8bd0d95d-de6d-557b-ae31-aa170b2bfb27 |  | note | REFERENCE: IFC Drawings
label | a2ffb24c-edc3-5382-83db-adedfff4ccb8 |  | note | – – – – – – – – – – – – – – – – –
label | 1619791e-09e6-5487-a4a3-e89a5c8c09b8 |  | note | ACCEPTANCE CRITERIA:
label | caee2742-4dac-5dc7-9e9b-13d254fa6b77 |  | note | Backfill behind the reinforced block shall be Vicroads Type B or better and:
label | 0369705b-3524-5854-9dac-30ebe695c128 |  | note | • pH > 5.5
label | 3f48facc-31ef-51cf-bfb2-7ad2cb2ea2c6 |  | note | • CHLORIDES < 2000 mg/kg
label | 9a98bb7b-fdc9-5d16-9297-da997a66f075 |  | note | • SULPHATES < 1000 mg/kg
text | 784da485-ce68-55b9-9cac-cf107e270242 |  | textbox | Reference: Material approval in Teambinder
label | 1918d7ee-963a-5ff3-92a6-b436b089037d |  | note | – – – – – – – – – – – – – – – – –
label | 7ad90829-ace8-591d-847e-ff9bc01f3f8e |  | note | METHOD: Document Review
label | f94a0441-5b95-5798-b7d9-1e402aa50895 |  | note | – – – – – – – – – – – – – – – – –
label | 6a2ed8ff-c4ad-5095-8575-e21352b65d93 |  | note | FREQUENCY: Each material specification
label | c5a24104-ab2b-501c-aadb-e0266ef2c4a7 |  | note | – – – – – – – – – – – – – – – – –
label | 11a077ff-d8c1-51c5-9084-d8cbd4fe0c4e |  | note | CATEGORY: HP
label | 3d762842-defc-5300-addf-f7d55e10149d |  | note | – – – – – – – – – – – – – – – – –
label | b70eb4ec-9d67-50b4-8581-63a1fcfd10cd |  | note | RESPONSIBILITY: Nominated Authority
label | a143be08-120f-538a-8312-ebee7a90059e |  | note | – – – – – – – – – – – – – – – – –
label | 9956eb0c-575e-566c-ae88-1416f3de1c6f |  | note | VERIFYING DOCUMENTS: Material approval
text | 09ba1b17-7cd6-5d79-93e4-159b5dd316aa |  | textbox | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.4 Perforated Pipe-material
label | 34745e42-9122-53c7-aba6-3ba3dae16027 |  | note | REFERENCE: IFC Drawings
label | 055b6ec5-b85a-5b32-a021-2ec8a6cbcd68 |  | note | – – – – – – – – – – – – – – – – –
label | 85875f8f-e864-50c5-b385-e7cb2c4028f9 |  | note | ACCEPTANCE CRITERIA:
label | aa570f89-96a0-5e8d-96bc-481c17d9d795 |  | note | Perforated plastic pipe perforations shall be a maximum width of 1.5mm and minimum length of 150mm per m2
text | a7981b7b-e1fd-5f92-8286-b7a6c77c9e3a |  | textbox | Reference: Teambinder MA number:
label | 07b63b0f-11b5-5d6a-ab6a-31d871f0fe81 |  | note | – – – – – – – – – – – – – – – – –
label | 84ae4048-9931-5224-92d4-f3dc050cafc3 |  | note | METHOD: Document review, Measure
label | ac56a61e-1e8b-56a1-a39e-495388e16b50 |  | note | – – – – – – – – – – – – – – – – –
label | 4412f8c2-1804-5c79-b964-f313d1f28a8f |  | note | FREQUENCY: Each wall
label | f3c92df9-6dfd-5063-83b1-30eac54119f5 |  | note | – – – – – – – – – – – – – – – – –
label | 128f450f-203a-51cc-9b25-427473450dbe |  | note | CATEGORY: HP
label | 73b7424b-105f-5004-955d-724f8ba6532b |  | note | – – – – – – – – – – – – – – – – –
label | f45aaa6e-707b-5946-a17d-2074f6bab417 |  | note | RESPONSIBILITY: Nominated Authority
label | 9d9da0c2-59bc-5230-9b5d-3575ae1c8922 |  | note | – – – – – – – – – – – – – – – – –
label | 8a6d41c9-c2a8-552f-baf0-b160bf4dbfbd |  | note | VERIFYING DOCUMENTS: Material approval
text | 80bc79e1-d190-5866-95dc-20078c657b0c |  | textbox | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | Preliminaries-Documents
checkpoint-status |  |  | checkpoint | 3.1 RSS Panels
label | 32247d12-6be9-5589-9cd7-84c7aae0906c |  | note | REFERENCE: IFC drawings
label | be4bfe9b-84f7-5a8a-a42f-ced2dd881ac9 |  | note | – – – – – – – – – – – – – – – – –
label | 3d3d1746-65c6-5b46-804e-e27bf32b419a |  | note | ACCEPTANCE CRITERIA:
label | 15f0200b-6a0e-571f-a552-80dae142aecf |  | note | Precast supplier is required to provide the following Quality Assurance documentation for each element, typically this consists of:
label | e8f0da02-ec27-5cd8-a702-d75be59cbc16 |  | note | i. Certificate of Compliance / Birth Certificate
label | b56f33a3-8b71-55c5-819b-ffe2a9d1e291 |  | note | – 1. Concrete strength;
label | 21f1bf95-5259-5cd4-8103-b29e59c67816 |  | note | – 2.Date of manufacture;
label | 40238426-c029-5689-8a7c-c429e543fe92 |  | note | – 3.Unique Identification number;
label | 79c9c8dc-ad1a-5800-a2ef-c680360a58c5 |  | note | – 4.Mass;
label | a8977833-4791-502f-9a3b-40d7ea05c71e |  | note | – 5.Confirmation of number, type and capacity of lifting inserts;
label | f55f1066-9d4f-5cd4-929b-bcdcfdb60178 |  | note | – 6.Quality assurance sign-off.
label | 2c2c9c90-6f5a-514c-bb9f-365642de7bca |  | note | ii. Compressive strength test results
label | bba556cf-3786-5bd5-b705-d85461031403 |  | note | iii. Precast Lifting Design
label | 0689a20a-e77e-55f9-a41b-5e304d8483c1 |  | note | iv. Pre-pour check sheet / ITP
label | af4e7666-ee88-5604-9925-b222b91612e8 |  | note | v. Post-pour check sheet / ITP
label | 551ed00c-228f-5d0f-9ac6-a56c70eb49e8 |  | note | vi. Covermeter check record
label | cc596442-105a-5107-a40b-bc7b5e38b50a |  | note | vii. Record of dimensional measurements
label | 7e7a0789-2525-523c-a951-d1b2aecbab77 |  | note | Collate: Precast Quality Assurance Documentation so it can be uploaded into Teambinder pre-cast supply Lot (don't attach it here)
text | 50a4513f-98de-5163-8848-106a86d43fbb |  | textbox | Reference: Precast panels MDR Lot in TeamBinder:
label | d9050164-57b0-53f3-87a6-5060e7cc2cd4 |  | note | – – – – – – – – – – – – – – – – –
label | bb13552e-f9a5-5e3d-b26d-433a2e085f03 |  | note | METHOD: Document Review
label | 176d88de-5335-567c-8408-dae1374d6788 |  | note | – – – – – – – – – – – – – – – – –
label | a2a02159-5c33-54e0-be53-0d42106781f8 |  | note | FREQUENCY: Once for each type of panels
label | 4fc2306f-7aa4-55c3-911d-87dcea54a83b |  | note | – – – – – – – – – – – – – – – – –
label | 2b794935-44fb-51c6-8fff-2d9535904f64 |  | note | CATEGORY: IP
label | 917b70dd-dbfd-526f-a24d-66d601dfbef5 |  | note | – – – – – – – – – – – – – – – – –
label | c1f25768-fe07-5207-91d7-0f03b3f5247e |  | note | RESPONSIBILITY: PE
label | 0c875e0c-c87d-5fc6-8978-240a71c0caf1 |  | note | – – – – – – – – – – – – – – – – –
label | 1fd39627-ef5c-5955-b8a1-8240a47782d8 |  | note | VERIFYING DOCUMENTS: Precast panels Birth certificates and MDR Lot
text | 7ccb88f3-5a66-5295-8e50-87e3c94de818 |  | textbox | Date Completed:
checkpoint-group |  |  | section | Pre-Construction Activities
checkpoint-status |  |  | checkpoint | 4.1 Foundation
label | a0116b19-efcf-5193-9f0b-674f6c6c9975 |  | note | REFERENCE: IFC Drawings
label | 0b8bbfc6-110f-57e9-aa97-51c6010d9241 |  | note | – – – – – – – – – – – – – – – – –
label | 90729cf3-3e42-54a2-92c1-69296a130c58 |  | note | ACCEPTANCE CRITERIA:
label | c9924684-2e56-5aac-8f6d-785b8036f286 |  | note | The foundation material beneath the RSS fill shall be inspected on site by a qualified geotechnical Engineerto ensure that the soil conditions meet the assumed material properties:
label | a3d2c97e-63cc-5b5c-8998-da70d2015ece |  | note | • Description: Stiff Clay or better
label | 327b9dbf-d987-50f1-99ad-2761b6ba3945 |  | note | • Unit Weight: 18 kN/m3
label | cadcbeb8-0849-5ead-8579-b8cff1010c40 |  | note | • Effective friction angle: 28°
label | 0f9bf4c9-71fa-5bff-a88d-3152eb10eeb1 |  | note | • Effective Cohession: 5 kPa
label | d3f838b6-3448-5ddd-99a8-56bf1c8bc011 |  | note | • Undrained cohesion: 80 kPa
label | 6963087f-69dc-5414-a611-5be62b59b877 |  | note | – – – – – – – – – – – – – – – – –
label | e5edea3c-6829-5319-afb3-990ad355647f |  | note | METHOD: Test, Document Review, Visual
label | b787244a-fc10-5992-8fd8-615da0224c05 |  | note | – – – – – – – – – – – – – – – – –
label | ec63b8b0-eef6-5141-a4c1-2b1651600bf0 |  | note | FREQUENCY: Each retaining Wall
label | 9bb756bb-a71a-54e2-8e2e-abb4addfc25c |  | note | – – – – – – – – – – – – – – – – –
label | dbcc25bb-09a0-52ec-9587-2cd37d354019 |  | note | CATEGORY: HP*
label | 7f12c942-89e2-5285-a7dc-5b446ab0a6dd |  | note | – – – – – – – – – – – – – – – – –
label | 0eb432e6-2d06-5809-973d-ef727e5a48ab |  | note | RESPONSIBILITY: PE/Geotechnical Engineer
label | 09401ba6-f5b6-5e74-a9a1-07a8cee9d635 |  | note | – – – – – – – – – – – – – – – – –
label | c402da48-1e79-52c4-8ad4-e034e4bf0126 |  | note | VERIFYING DOCUMENTS: This ITP, Test results
text | c49cd1e5-9f2e-5180-a59f-fc684f57cf95 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 4.2 Foundation
label | c2882d09-ab08-53ab-9cec-4d27b5a2ffe1 |  | note | REFERENCE:
label | e80b350f-e6fe-525d-bc51-1df4e8af971d |  | note | • IFC Drawings
label | 889bde63-e6f1-5442-a6f7-bb81b1814e43 |  | note | • MRO-052-C-SME-DRG-32-MPK-CSW-2053
label | fde2dcc0-0b73-5add-a2cd-2b36abce5dca |  | note | – – – – – – – – – – – – – – – – –
label | 07cb888d-c6d5-5f0a-a924-32ee9cef53da |  | note | ACCEPTANCE CRITERIA:
label | 25432280-bf9a-5154-9f4a-91e2a2af9e6e |  | note | Where the foundation material does not meet the assumed material parameters, the existing ground shall be replaced with VR Type A fill Compacted in accordance with VR 204
label | 97f29d86-0967-52f9-96bb-60f06153ceef |  | note | – Ground improvement works shall be keyed into surrounding material at minimum 200mm Bench width
label | c99a64c9-08fd-535a-b85c-797da0c5bbfc |  | note | – Ground improvement works shall extend beyond either side of bridge approach to detail show in IFC drawing
label | 685c0492-c679-59a6-a366-e4956e2296c3 |  | note | – – – – – – – – – – – – – – – – –
label | e2a1985a-3c98-5e55-900d-b3c8f7a196bf |  | note | METHOD: Visual
label | c569b4b3-075a-5874-b83d-351b53fadc00 |  | note | – – – – – – – – – – – – – – – – –
label | 448205d6-3368-51e4-a989-1cadee3ef3f0 |  | note | FREQUENCY: Each retaining wall
label | a96a9a70-e490-554a-bd2d-cd41f82874ff |  | note | – – – – – – – – – – – – – – – – –
label | 6e74f9cb-c918-55cc-ac52-af1ad8bfd33e |  | note | CATEGORY: IP
label | 61f422fe-2e0f-5baa-802e-e2507b0b678e |  | note | – – – – – – – – – – – – – – – – –
label | 695ee52a-e9a6-5c37-9d3f-69dd77791e70 |  | note | RESPONSIBILITY: PE/Geotechnical Engineer
label | b6aa5dcc-a326-5932-9616-3b68c945de63 |  | note | – – – – – – – – – – – – – – – – –
label | 9d9095af-5c5f-5e0a-9ef9-9fc3b4594ce2 |  | note | VERIFYING DOCUMENTS: This ITP
text | 6e398090-9897-56d5-bd36-6b11b6e1d215 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 4.3 Foundation
label | a640911d-32c8-558c-9a10-0b496616c3d3 |  | note | REFERENCE: IFC Drawings
label | ada6a7cb-a1cf-5ad0-af3e-1562470f82ec |  | note | – – – – – – – – – – – – – – – – –
label | 421593ff-bb51-56d6-a025-6ea89a603ced |  | note | ACCEPTANCE CRITERIA: It is the rsponsibility of the Geotech engineer to determine that the bearing bearing capacity is adequate
label | f87f56a2-9e16-5dd6-b0bb-351f5496eeab |  | note | – – – – – – – – – – – – – – – – –
label | 980b81b4-cf88-5706-914a-54d98bc5b0b0 |  | note | METHOD: Visual
label | 38a4faca-74c7-5c08-9913-c0bc694e6b00 |  | note | – – – – – – – – – – – – – – – – –
label | 6a9e4e1e-7438-5a9b-b7be-0a58bc639c33 |  | note | FREQUENCY: Each retaining Wall
label | 075201d1-cbe8-5e48-92c7-3dea21af538d |  | note | – – – – – – – – – – – – – – – – –
label | 3ce740a0-9d6e-53c5-9c37-e48158166573 |  | note | CATEGORY: HP
label | 5bf2a16a-2326-5fbd-968a-68c178b876c1 |  | note | – – – – – – – – – – – – – – – – –
label | 1216795e-0818-5d92-94f0-d8e92507756e |  | note | RESPONSIBILITY: Geotechnical Engineer
label | 7985e3e2-6b80-5ea0-a8ba-b3c16e485301 |  | note | – – – – – – – – – – – – – – – – –
label | c6c8f491-f6a0-5748-a82b-8b584242ddcc |  | note | VERIFYING DOCUMENTS: Geotechnical Engineer Sign off this ITP
text | 1447e74f-604a-5325-b99c-903353bb33b6 |  | textbox | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 4.4 Foundation
label | fa0a5fc6-09b3-5cbf-99c5-7a514c9ac2c5 |  | note | REFERENCE:
label | 374a8b6e-b695-535e-9bc0-ac9ae1e1fc97 |  | note | • VR 204.12
label | aeecf6bc-72c0-5134-8d0c-a2f6ff585c98 |  | note | • VR 204.11
label | 13560fd3-6c04-5b95-83b1-27cb13f2c73b |  | note | – – – – – – – – – – – – – – – – –
label | fe9f9ebb-3219-5f47-a7d8-c38aad92668c |  | note | ACCEPTANCE CRITERIA:
label | c5206c13-6690-51c9-b57b-75b03ff8c144 |  | note | • Areas upon which fills are to be constructed shall be test rolled in accordance with VR 173
label | b947a681-cd4d-59b0-8384-68a0ca404c20 |  | note | • No Fill shall be placed against or within 3 meters of a structure until the foundation for the fill has been reviewed by the superintendant
label | fe923ac7-d6bc-5344-82c7-d338178660cb |  | note | – – – – – – – – – – – – – – – – –
label | 6bfedb58-3733-54e0-8069-c9c018f43486 |  | note | METHOD: Visual
label | 06e1e88e-40f5-58cd-baef-ced02a9de161 |  | note | – – – – – – – – – – – – – – – – –
label | f5cd6d09-1606-5883-8087-37595bda66b7 |  | note | FREQUENCY: Each retaining Wall
label | 8438e244-b059-528b-b909-3f7567091c50 |  | note | – – – – – – – – – – – – – – – – –
label | 5ea2c970-54c3-5422-acd1-ad505d7dcb16 |  | note | CATEGORY: HP
label | bd3b15de-dd87-520c-a01e-198623a2ec80 |  | note | – – – – – – – – – – – – – – – – –
label | ab817e67-2d53-5513-805e-39cde127abaf |  | note | RESPONSIBILITY: PE/Nominated Authority
label | f074bb4e-1e08-5ad1-a4af-c99587baed7b |  | note | – – – – – – – – – – – – – – – – –
label | 76aa1f8f-852a-52d7-8b50-794788f40763 |  | note | VERIFYING DOCUMENTS: This ITP
text | baa4d394-b0c5-5ecd-9064-fbfcad8c2df8 |  | textbox | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 4.5 Levelling Pad-Survey Set out
label | f5a9651a-a6c2-500c-9829-5f83eead2644 |  | note | REFERENCE:
label | ec068df5-5204-5244-9a50-738ea688b2c7 |  | note | • IFC Drawings
label | 52155c31-e644-5d0f-a373-a841ac4bb1c2 |  | note | • VR 682.20
label | 68affa2d-a741-5cda-9277-34bea2c348ca |  | note | • MRP-052-C-RFL-DRG-33-CBE-CSW-1201
label | 8387b840-c8b6-586b-9910-6db91cadd5f6 |  | note | • MRP-052-C-RFL-DRG-33-CBE-CSW-1202
label | 3b495a7d-79ab-595f-8495-bb3244e96304 |  | note | • MRP-052-C-RFL-DRG-33-CBE-CSW-1203
label | c08d2336-af46-51e0-bcd0-c1b53c0f7fd4 |  | note | • MRP-052-C-RFL-DRG-33-CBE-CSW-1204
label | 29188adb-5dc1-5735-ab18-36992054d260 |  | note | – – – – – – – – – – – – – – – – –
label | aeba7a0a-ef27-51d0-8098-f7c176a021a0 |  | note | ACCEPTANCE CRITERIA: Survey activities to be undertaken to ensure and validate that all Works meet level and location requirements within the tolerances as per the tables in IFC Drawings and Vicroads Specification
label | a11a5f3e-8e02-5368-844d-fbb3a9253eb3 |  | note | – – – – – – – – – – – – – – – – –
label | 6a7f3c1a-ffad-5829-a37c-8ed0daacad6f |  | note | METHOD: Measure, Visual
label | 0177b48e-d449-519a-8b6a-f2a8e4d09bdb |  | note | – – – – – – – – – – – – – – – – –
label | b0f01367-92aa-593d-a880-0fa83c6bbfaf |  | note | FREQUENCY: Each retaining Wall
label | 406f2626-6d32-54f6-bb3d-9a7db5e7bb7c |  | note | – – – – – – – – – – – – – – – – –
label | 9dfe4abf-c369-5fdc-bb2f-1fedb47dc135 |  | note | CATEGORY: IP
label | 0b240a18-3b9d-5c74-977d-c2be3bd8b3bd |  | note | – – – – – – – – – – – – – – – – –
label | 27a6a8e1-56ee-5aef-a3d5-064454b3566e |  | note | RESPONSIBILITY: Surveyor, SE/PE
label | 5a132a02-9e55-5fe7-85bf-89c770e3bc7f |  | note | – – – – – – – – – – – – – – – – –
label | 738bc580-191e-5914-b651-56c0580a272d |  | note | VERIFYING DOCUMENTS: This ITP
text | 6cf40e4e-f91c-5a53-85c4-0a2739a5bcb3 |  | textbox | Date Completed:
checkpoint-group |  |  | section | Construction / Installation Activities
checkpoint-status |  |  | checkpoint | 5.1 Form Levelling pad
label | 7e641105-3464-5a1c-827e-b9894205c7ef |  | note | REFERENCE:
label | 6cabbf5f-bb96-5732-959c-8936ad0717cf |  | note | • IFC Drawings
label | 97579fea-1412-566c-b684-35e371f865e3 |  | note | • MRP-052-C-RFL-DRG-33-CBE-CSW-1201
label | a54055f3-47df-5470-ba51-212351af451d |  | note | • MRP-052-C-RFL-DRG-33-CBE-CSW-1202
label | 8dcabae1-db21-5434-8ba4-64d0c79f49b5 |  | note | • MRP-052-C-RFL-DRG-33-CBE-CSW-1203
label | d712c7b3-3490-5ec7-9015-508339083ce8 |  | note | • MRP-052-C-RFL-DRG-33-CBE-CSW-1204
label | 04ae5e2a-c425-5d70-b5db-64f9fb71e469 |  | note | – – – – – – – – – – – – – – – – –
label | 339841b0-c61a-5ff0-b731-dce35db3f202 |  | note | ACCEPTANCE CRITERIA:
label | 55ac77f5-fe6f-5eab-a846-1217983c8eef |  | note | Form timber shutters to edge of levelling pad
label | f71a9181-33c1-5fb3-a5c9-c416921ad48e |  | note | – Levelling pad is a 500mm wide by 150mm thick unreinforced concrete footing
label | 48493c3a-9ddc-5753-97d3-78eecd78c939 |  | note | – The leveling course level shall NOT deviate from the specified level by mor than ±3mm.
label | 9ecf6c46-9040-53f7-908c-2fa028d8cfc3 |  | note | – 20mm Nominal gap between levelling pad and adjacent ground beam is to be maintained
label | 48f071cf-3a9c-5d33-be73-538d8a44bd82 |  | note | – – – – – – – – – – – – – – – – –
label | 0b59787a-82b1-5ebd-b80f-a28077cc9e65 |  | note | METHOD: Measure, Visual
label | 4cda596e-30b0-57c5-9c2b-629cdd4208c8 |  | note | – – – – – – – – – – – – – – – – –
label | 9daf4cbf-659f-5af1-8a14-bc21e2517e5f |  | note | FREQUENCY: Each Lot
label | 5c541a1a-c1cc-57e6-a6ed-7cad5d7587d0 |  | note | – – – – – – – – – – – – – – – – –
label | 245af2d0-6c47-5a22-b821-dcd3608fcf14 |  | note | CATEGORY: IP
label | 5d9c6c54-7c1a-5b76-bfd4-8a71ed870153 |  | note | – – – – – – – – – – – – – – – – –
label | ee0a0ea0-d38b-5369-bedb-9eb0d23e2856 |  | note | RESPONSIBILITY: SE/Site Supervisor
label | 2e8cbf88-4a69-5850-affd-f0ff8f7f01e2 |  | note | – – – – – – – – – – – – – – – – –
label | 364a8614-6bea-5718-8f31-6402efee86e1 |  | note | VERIFYING DOCUMENTS: This ITP
text | 63689911-322a-5697-b544-6ba943d66f05 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.2 Leveling Pad Concrete Pour
label | 4ad6e7f0-6939-5c8a-a97d-6a2f0e69c832 |  | note | REFERENCE: IFC Drawings
label | ddd4b9a0-7b4e-5675-98eb-d6648889da21 |  | note | – – – – – – – – – – – – – – – – –
label | 30052cf0-7fb5-593e-a76f-354f6d9328ef |  | note | ACCEPTANCE CRITERIA:
label | e9f69702-1518-517f-935f-18c3a7c89364 |  | note | Concrete to be placed in accordance with 610.
label | 50242171-8918-5689-a34d-b9b4c91bae28 |  | note | Attach: Concrete Delivery Docket
label | 18858e5a-0c5b-58d0-9f5d-79d72cd99c8f |  | note | – – – – – – – – – – – – – – – – –
label | 0db85466-c697-5498-a8dd-5172848a613e |  | note | METHOD: Visual
label | c75f7239-ec12-5cde-bacb-ed1fe25148b0 |  | note | – – – – – – – – – – – – – – – – –
label | 4e0f21ab-ee4e-57df-879f-09ce0b9f9f47 |  | note | FREQUENCY: Each Lot
label | 807eb993-e420-5357-aaee-e8d956a46c09 |  | note | – – – – – – – – – – – – – – – – –
label | 1ebaf005-a5cd-5b25-9164-6b818b4aca2e |  | note | CATEGORY: IP
label | db108f6c-6da1-54f0-9968-485ea898db77 |  | note | – – – – – – – – – – – – – – – – –
label | c138ed25-d184-5e36-8ed0-207befefbd12 |  | note | RESPONSIBILITY: SE/Site Supervisor
label | 49078a7a-7594-5e47-8ab5-e9a9af83209d |  | note | – – – – – – – – – – – – – – – – –
label | 5a6bc732-33e4-5b38-a2dc-d7a99cc5402e |  | note | VERIFYING DOCUMENTS: Concrete Pour record
text | 0b09b08a-9231-5eef-8e67-1bc9d5d5d8d7 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.3 Leveling Pad Concrete Testing
label | 40835630-7066-508f-ae44-3657d2de9b5d |  | note | REFERENCE: IFC Drawings
label | 5f754176-89ec-57c0-89d2-8a51d9cd5dee |  | note | – – – – – – – – – – – – – – – – –
label | 7542ec66-472c-5d94-879d-964648cb4705 |  | note | ACCEPTANCE CRITERIA:
label | 09ab71a0-c7cf-5036-a148-8306153f5b07 |  | note | Concrete testing for compressive strength shall be undertaken at the testing frequency specified in VicRoads Section 610.16 (b)
label | 6bb78d82-069b-561e-92d6-a950d140d858 |  | note | Attach: Concrete test report
label | 62841cdf-66d9-5f82-a718-d0441a35a57a |  | note | – – – – – – – – – – – – – – – – –
label | eff81849-1ed3-5636-bc0d-9d3d4b0b15e6 |  | note | METHOD: Document Review
label | 4b3b08b6-08c0-5c56-82ca-cc2c21614dde |  | note | – – – – – – – – – – – – – – – – –
label | 203b1545-faee-5ec2-bf05-497c826998cf |  | note | FREQUENCY: Each Lot
label | 7bf2a98c-d573-5a15-9caf-276fc978e521 |  | note | – – – – – – – – – – – – – – – – –
label | b9be637a-a672-5491-aa4a-448394ba9097 |  | note | CATEGORY: IP
label | e997eda9-485c-5b0a-aef2-7e21d4f18e30 |  | note | – – – – – – – – – – – – – – – – –
label | a0eed67c-9c56-5e9c-854f-5916f292793d |  | note | RESPONSIBILITY: PE
label | dc691f4b-7dcb-5734-b6bf-0a27a4e4f49d |  | note | – – – – – – – – – – – – – – – – –
label | 5b1d8a29-e4cb-5d28-abfb-dd0a07fd8e51 |  | note | VERIFYING DOCUMENTS: Attach Concrete Test Report
text | 350ee018-fd4f-52cc-b3a0-3f3cdc6c142f |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.4 Levelling Pad-Post Pour Survey-Levelling Course
label | bc47cd65-126b-5bf8-af56-a6b2a3e606d1 |  | note | REFERENCE:
label | 178e5558-9471-56a4-ad21-66d0fa3094b6 |  | note | • IFC Drawings
label | 0b7130e7-d3bb-5ead-8187-17360f9de90e |  | note | • MRP-052-C-RFL-DRG-33-CBE-CSW-1201
label | 80e93925-d849-5ca0-8852-dfbd29201ef9 |  | note | • MRP-052-C-RFL-DRG-33-CBE-CSW-1202
label | bc154f4b-cbc1-57fc-862f-a1407b72ee98 |  | note | • MRP-052-C-RFL-DRG-33-CBE-CSW-1203
label | 6be26861-25bd-5ff8-aa39-1254121aea02 |  | note | • MRP-052-C-RFL-DRG-33-CBE-CSW-1204
label | 55c2f01e-6aeb-5518-813a-8c300dbbb433 |  | note | – – – – – – – – – – – – – – – – –
label | dd89458a-8a86-584c-b1ff-c894f3182bd0 |  | note | ACCEPTANCE CRITERIA:
label | 90f9e0e3-5c38-5971-837b-7c14f456f161 |  | note | – Levelling course level shall not deviate from the specified level by more than ±3mm
label | b77e9577-7573-5f47-9ce8-25f738c2b1ea |  | note | – Plan position shown on the drawings at the base of the wall shall not exceed ±15mm (refer to drawings for WP locations)
label | b24b6d71-9126-55fe-b392-5ac09947e8bb |  | note | – – – – – – – – – – – – – – – – –
label | fbb379d9-0f54-56e1-9179-c35e1c5dcc5f |  | note | METHOD: Measure, Visual
label | 626dc986-f16d-52a3-bd8a-71e664ad5dda |  | note | – – – – – – – – – – – – – – – – –
label | 24061947-9d5d-5705-b44f-c58fa5625f7b |  | note | FREQUENCY: Each retaining Wall
label | 5fc0959c-0b6a-527f-a95d-05dbfd8579eb |  | note | – – – – – – – – – – – – – – – – –
label | 355fffa2-45b9-5b02-b424-2cadced7b4b7 |  | note | CATEGORY: IP
label | 35a85de8-2c23-558d-9d6e-604a1f5e872f |  | note | – – – – – – – – – – – – – – – – –
label | 4f4a9085-14aa-56ca-97bc-5522e46f44c0 |  | note | RESPONSIBILITY: PE/Surveyor
label | 54bdddde-d885-5400-8b82-4d16cb73f187 |  | note | – – – – – – – – – – – – – – – – –
label | 65612319-51ba-5d43-a8a1-9c5266c5d5c3 |  | note | VERIFYING DOCUMENTS: Attach Survey Report
text | c3fb6a9c-e156-5eea-b2ba-b1115829a655 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.5 Levelling Pad-Backfill commencement
label | d9430ba7-885f-539d-b270-e9847d08f538 |  | note | REFERENCE: VR 204.11
label | 29f834ab-cade-5d88-98c1-da5295932b1c |  | note | – – – – – – – – – – – – – – – – –
label | 55da4019-4819-5c7d-9189-e1874c00f279 |  | note | ACCEPTANCE CRITERIA: No material shall be placed against concrete within 14 days of casting
label | ed24a67c-b1b0-5d23-83dc-d6510dfee4fb |  | note | – – – – – – – – – – – – – – – – –
label | 6ef96ee9-dab7-58eb-80df-71d5658a0c1b |  | note | METHOD: Document review
label | 5a9ffbba-f84c-5391-8318-e93f0ad4340d |  | note | – – – – – – – – – – – – – – – – –
label | e7782e90-bddc-50cc-867e-1ff3d29e791f |  | note | FREQUENCY: Each retaining Wall
label | 7597ab4d-e3a7-5f03-98aa-434b0e4b4595 |  | note | – – – – – – – – – – – – – – – – –
label | 84006bc2-141e-5f51-b37f-b42076a90d73 |  | note | CATEGORY: HP
label | cbdf47da-ba6e-5b4b-aa6c-e27cda7b59c9 |  | note | – – – – – – – – – – – – – – – – –
label | 85b88bb7-cc04-5134-b699-5f3d006af61b |  | note | RESPONSIBILITY: Nominated Authority
label | 963cc402-d37c-544a-b44d-01812c6bf8dc |  | note | – – – – – – – – – – – – – – – – –
label | b78ce687-534b-5e65-84f5-574b7f19168a |  | note | VERIFYING DOCUMENTS: This ITP
text | 49d7644e-b6cf-5b48-a03e-a4e4a8ee266a |  | textbox | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 5.6 Wall Panels Installation
label | a9f67426-017c-5cfe-991b-ca37f59149fa |  | note | REFERENCE: 682.17
label | 676d306b-8c88-5c29-bbd0-bdca0292e3fe |  | note | – – – – – – – – – – – – – – – – –
label | ffa1f531-7716-5121-b457-d0c079f3a6a2 |  | note | ACCEPTANCE CRITERIA:
label | 7e37173e-6c59-5fd7-bd38-076a3087fa01 |  | note | • The level and alignment of each course of facing panels shall be checked progressively after placement of each course and prior to placement of the next course to ensure compliance with the dimensional and positional tolerances stated in the design.
label | 83761097-6d35-55e8-b4bf-34c543f1c923 |  | note | • The Contractor shall record the results of this checking together with details of any non-conformances and the associated corrective actions
label | b22197c3-69d4-5415-a581-e1097f9165bb |  | note | • Refer to checklist for each course of panels
label | 68a4fca3-4152-5edc-9f48-5b37768561b3 |  | note | Attach: Lot map
label | 06a3ece2-31d4-52aa-85cd-21d3c16dd995 |  | note | – – – – – – – – – – – – – – – – –
label | 7397ad7b-58aa-565e-98dc-5b0185e152ae |  | note | METHOD: Visual, Measure
label | 9c916166-feb4-58e3-b2c2-1b9d1e11a2e9 |  | note | – – – – – – – – – – – – – – – – –
label | f7588021-a980-5947-b4b3-60986a9b74b4 |  | note | FREQUENCY: Each course of facing panel
label | b917d173-5bae-526b-8685-0662ec5b5183 |  | note | – – – – – – – – – – – – – – – – –
label | d842f95e-ef12-5c76-82dd-da783d56c3b2 |  | note | CATEGORY: HP*
label | e8171655-f4a4-5000-9c19-6182ed846395 |  | note | – – – – – – – – – – – – – – – – –
label | 60d2347d-610d-55c4-a671-4a8e459de077 |  | note | RESPONSIBILITY: PE/SE
label | bdcb89a3-679b-5e0b-adf1-5b7a73925208 |  | note | – – – – – – – – – – – – – – – – –
label | fb52f4ef-ad85-51ca-b89e-761be1bab63d |  | note | VERIFYING DOCUMENTS: Inspection record checklist: CHK-CIV-RSS Pre-cast panel installation
text | a2ed0717-c4d9-5b6b-857a-2b54e203b23d |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.7 Drainage-Wall
label | 62a62d9d-a43e-5f0b-8eaf-f26a6a565b42 |  | note | REFERENCE:
label | cfcc6013-5450-557a-a800-4b92ae353a39 |  | note | • IFC Drawings
label | 7873cbd7-4fb1-584e-bc36-1469fb2f81a5 |  | note | • MRP-052-C-SME-DRG-32-MPK-CSW-2053
label | b6f21b1b-c19b-57de-99eb-614bb37f3e4e |  | note | – – – – – – – – – – – – – – – – –
label | da899c96-65cb-52ae-bd0e-662ec6ef66d3 |  | note | ACCEPTANCE CRITERIA: 300mmx300mmGranular backfill in Geotextile BIDIM A64 around 100mm Dia. Perforted plastic pipewith 0.5%min fall to 50mm Dia weepholesin RSS panels.
label | a06f36a1-4e57-5511-a4bf-4f59189f7171 |  | note | – – – – – – – – – – – – – – – – –
label | 7770c051-0934-5439-9bb8-26c8f5499b91 |  | note | METHOD: Visual
label | 01f0f818-1c24-5d7f-af94-ec373d5883a8 |  | note | – – – – – – – – – – – – – – – – –
label | 4d583ce4-ad4f-5081-a55c-a2486f9c2cff |  | note | FREQUENCY: Each wall
label | 19a1c731-7e2e-5c7c-81fa-a4a1446a158e |  | note | – – – – – – – – – – – – – – – – –
label | 81e06d14-1fba-50a6-a552-e8750dc97ed3 |  | note | CATEGORY: IP
label | 297279d1-57ef-5521-b083-42139c61669c |  | note | – – – – – – – – – – – – – – – – –
label | 1cb477cd-eaf4-54cc-8bd5-2f702cb84048 |  | note | RESPONSIBILITY: PE/SE
label | 09047e11-9ee6-5d3a-bcfe-36cb451a38d4 |  | note | – – – – – – – – – – – – – – – – –
label | 4008c3e9-7e09-51fd-ba49-6d13196efda5 |  | note | VERIFYING DOCUMENTS: This ITP
text | 7f8805b4-5c53-5deb-89a3-4d0a48c0c470 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.8 Fill
label | f9c04b04-1d2d-56c3-bfc4-4d75b2620c82 |  | note | REFERENCE: 682.16
label | 629549e4-9795-550e-ac15-11034a00bafc |  | note | – – – – – – – – – – – – – – – – –
label | 9d87dcd0-f01a-5c33-8603-88925d8b026e |  | note | ACCEPTANCE CRITERIA:
label | 37869659-0bd3-5659-bd9a-94965172226e |  | note | • The Contractor shall submit compaction test results for each layer of fill placement to the Superintendent for review and acceptance. No further fill placement shall be allowed if the total thickness of fill placement is greater than 1 m measured from the last layer that has been accepted.
label | 289b4923-11ab-5adf-9730-366315107c2e |  | note | • If any layer is found to be not in compliance with the compaction requirement, that layer and the layers above it shall be removed.
label | a1bf154c-537a-5913-ae18-307951b7dee2 |  | note | • Refer to checklist for each fill layer
label | 80707539-7971-5018-945b-367c1db52c23 |  | note | Attach: Lot map
label | 6ebef5da-b349-5a9a-8fd4-94ea42ecb606 |  | note | – – – – – – – – – – – – – – – – –
label | 01df4da4-679a-5616-b42e-23bcdd096aad |  | note | METHOD: Visual, Test, Measure
label | ac822c5a-1655-55a2-a478-b8b4f1955b07 |  | note | – – – – – – – – – – – – – – – – –
label | ec1bce01-af13-5cce-bf08-a54cb4acbf20 |  | note | FREQUENCY: Each layer of fill
label | 9cfe9968-29fb-56cc-89af-8a5c6f9d0a60 |  | note | – – – – – – – – – – – – – – – – –
label | 0a593ecd-cc00-5251-a1ef-d2a97c55293a |  | note | CATEGORY: HP*
label | 1c1690c6-7f45-5305-aabb-25584a32c256 |  | note | – – – – – – – – – – – – – – – – –
label | a9fda449-0b49-574a-9cfb-62aa0f285a3d |  | note | RESPONSIBILITY: PE/SE
label | a7c41bce-2b5e-5ef1-a22a-cce7d62228a6 |  | note | – – – – – – – – – – – – – – – – –
label | 68cca033-233c-5b71-88fe-65d9897b2d9c |  | note | VERIFYING DOCUMENTS: Inspection record checklist: CHK-CIV-RSS Fill installation
text | 79d6f0ef-2558-5c6c-99e3-b0719c4b7a65 |  | textbox | Date Completed:
checkpoint-group |  |  | section | Post-construction / Post-installation Activities
checkpoint-status |  |  | checkpoint | 6.1 As-built Survey
label | f83ed84f-2e6a-531c-811f-b58c7563695f |  | note | REFERENCE: MRPA Quality Management Plan
label | 6208878e-cb65-58ff-a435-f36915a0f7f8 |  | note | – – – – – – – – – – – – – – – – –
label | c2071648-ce3e-51ca-a778-7f29bebe27d7 |  | note | ACCEPTANCE CRITERIA:
label | 1d26bd10-ed46-5430-9343-f01ba0b6b871 |  | note | Provide record of dimensional measurements to demonstrate that all Works meet level and location requirements within the tolerances
label | e24d4d9f-a889-5d65-87f8-d5be6da63b5a |  | note | Attach: Survey As-built / Survey Report
label | b38d854b-fb04-5726-bef6-3e29b153773a |  | note | – – – – – – – – – – – – – – – – –
label | 6fd74c38-bcc1-58a1-9829-5a8b1b69f46e |  | note | METHOD: Document Review
label | dea735bb-d47f-54b5-be90-758c58d1bd78 |  | note | – – – – – – – – – – – – – – – – –
label | 7497ce90-9022-53a7-82bd-cbd81a798ac7 |  | note | FREQUENCY: Each element
label | 6482d1e5-37c4-52b0-a586-b964d538d652 |  | note | – – – – – – – – – – – – – – – – –
label | 206fc87c-fae2-5769-8eba-ba8f95b57359 |  | note | CATEGORY: IP
label | 29405fa9-4ebb-5f18-b05d-12f9e34e6b18 |  | note | – – – – – – – – – – – – – – – – –
label | f14d97a9-1919-59cc-b931-7b7ecc3185c5 |  | note | RESPONSIBILITY: Surveyor, SE/PE/SPE
label | 8755cc80-2527-5762-877c-76d7530135b9 |  | note | – – – – – – – – – – – – – – – – –
label | 67d840cf-0a4f-5037-b7b7-6404a7de116d |  | note | VERIFYING DOCUMENTS: Survey Report
text | fbfad233-4376-5a54-b485-433a7705051c |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 6.2 Wall Post construction monitoring
label | a65625bf-aee8-5f6c-a0e8-16d5e7e37325 |  | note | REFERENCE:
label | 7605cae5-6cda-5f7f-87fc-7fab84685eb1 |  | note | • VR 682.20
label | 75ababa4-0ab2-595c-ab04-62800855845c |  | note | • VR 682.21
label | cb253744-4a57-5836-9c84-83d755130676 |  | note | – – – – – – – – – – – – – – – – –
label | 704a83af-c296-5167-8062-da057ef3b838 |  | note | ACCEPTANCE CRITERIA:
label | c25e087f-2af1-5ce3-853e-5b738c371d6f |  | note | The Contractor shall take measurements of the position of the RSS at the points defined in clause 682.20(a) to (f) at intervals not exceeding one month for the first six months immediately following completion of the RSS and at intervals not exceeding six months thereafter until the end of the Defects Liability Period.
label | 2096018b-5787-5109-a0fd-ad6c7b28c623 |  | note | (a) plan position shown on the drawings, at base of wall shall not exceed ⊕15 mm;
label | cd5ec6ec-2bd8-5f1f-b746-cf291d3f8d6f |  | note | (b) relative displacement of adjoining smooth panel faces shall not exceed 15 mm measured normal to face of wall;
label | 4c935e00-e4cc-503d-b65d-8e280e55fb59 |  | note | (c) local deviation of the wall face measured at any location with a 3 m straight edge shall not exceed 15 mm;
label | d0a1af76-3611-5e5a-9d72-805fd9450879 |  | note | (d) the tolerance on position measured at the top of the wall face shall not exceed 5 mm per 1 metre of wall height;
label | e5701a2e-f0b2-53f5-b38d-72c2dda9afb1 |  | note | (e) the wall level shall not deviate from the specified level by more than ⊕20 mm;
label | cdc88886-3d45-58d3-a007-0403ec48085b |  | note | (f) variation in gap width between facing panels shall not exceed 5 mm per metre length and 10 mm over the full length of the gap.
label | 131c124c-495f-5070-8986-712a6940380a |  | note | The measurements shall be recorded in writing and reported to the Superintendent within two weeks of the survey.
label | 644dc79a-c2d7-5ac5-84d7-79a0665127b8 |  | note | – – – – – – – – – – – – – – – – –
label | 378ba654-eac0-592f-a94d-427915658754 |  | note | METHOD: Measure, Survey
label | bb280a9b-d99f-59bc-8ac1-299a25015455 |  | note | – – – – – – – – – – – – – – – – –
label | 876e4f1f-b69f-540a-8f53-4f2f2c8ac740 |  | note | FREQUENCY: Each wall
label | 4680702c-039e-5cb6-b106-b94a82bc606c |  | note | – – – – – – – – – – – – – – – – –
label | 3892de0d-891a-59a7-aff2-950d1736d03d |  | note | CATEGORY: IP
text | 351a580b-137e-543a-99bf-7b5631a4cbd5 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 6.3 Non-conformance Report (NCR) Closure
label | d0d71591-0d61-57b5-8ad1-536ea2dadc8c |  | note | REFERENCE: MRPA Quality Management Plan
label | 47386c30-b6c4-56c2-be26-6e9285c64137 |  | note | – – – – – – – – – – – – – – – – –
label | 811205d1-d5e7-5956-bfb8-98186ab259d0 |  | note | ACCEPTANCE CRITERIA: Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed.
label | 1544313f-2e81-55c8-86d5-c43a9c69e0db |  | note | – – – – – – – – – – – – – – – – –
label | 1a33c899-2f58-5f5f-b30f-edaa774cbe8c |  | note | METHOD: Document Review
label | 3aac46f6-e882-5ca4-8171-06f61272cb63 |  | note | – – – – – – – – – – – – – – – – –
label | 8482e1d0-934e-53c5-b891-77cbd9c38e64 |  | note | FREQUENCY: Once, prior to closure of this lot / element / Work area
label | bd4b41cc-9927-51ea-bc53-f0a5ae629755 |  | note | – – – – – – – – – – – – – – – – –
label | bcc35338-726a-5bd0-8aa1-ddffdb0d0d43 |  | note | CATEGORY: HP*
label | c3526f81-803a-50ec-a41b-c47c8c8ad9c2 |  | note | – – – – – – – – – – – – – – – – –
label | 99aefe98-0b66-555e-87f1-d1318c0c8bef |  | note | RESPONSIBILITY: SE/PE/SPE
label | aafa504a-eb8c-5d3c-90b6-069bde4e1c72 |  | note | – – – – – – – – – – – – – – – – –
label | 7820860c-cafa-5691-99d5-73247d373abf |  | note | VERIFYING DOCUMENTS: This ITP
text | 9ee3d3d5-9fdb-5e2d-b3d1-54160afe7997 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | Final Inspection
label | 6b7e3044-01da-5c12-a8c8-1d03dd83d8d0 |  | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
text | 6bffcc49-da08-5266-a16c-bf686edaf980 |  | textbox | Name:
text | ee7ac50a-fa59-52bb-8199-cb595d7936b6 |  | textbox | Position:
text | 90ff8abf-e3d5-5df0-88a2-b4e3489783e4 |  | textbox | Date Completed:
holdpoint |  |  | signoff | Sign ITP
checklist-sectioned |  |  | checklist | ITP-010-STR-CFA Piling | itp |  |  |  | Yes | ITP-010-STR-CFA Piling Rev 0 | d8587987-3159-4ec7-9010-ae91619766bf
checkpoint-group |  |  | section | Referenced Documentation
checkpoint-status |  |  | checkpoint | Referenced Documentation
label | 7549e2a7-1046-5128-a10e-91343c2ab068 |  | note | Document Title: ITP-010-STR-CFA Piling
label | 829cd9ce-68b2-539f-bd23-7273ed749c30 |  | note | ITP Description: CFA Piling
label | a3e3891f-72ab-5dfc-b908-3fedcbcc4552 |  | note | Document Number (in Teambinder): MRP-0000-MRPA-ALT-ITP-00XX
label | 8e8590a4-c64b-5d15-bf0f-a420007c3b73 |  | note | Discipline (e.g. CIV/STR/RAIL): 010-STR
label | c5911cd5-c847-5547-958a-7e4825ce43a6 |  | note | Revision Number: 0
label | 78db8539-cc84-5649-873d-b352bad32f0e |  | note | Revision Date: 11/10/2022
label | abb17e33-687e-593d-b213-c4041b71f4bc |  | note | ITP created by: Victor Mira
label | c242f2c1-1528-5b71-a194-0bb14f860a5b |  | note | ITP approved for use by: Victor Mira
label | 77484c8e-bf5b-5b2c-b2bf-0c5b5ba8d1b8 |  | note | 1.1 - Non Dependent
label | 59903b61-657c-5520-86ad-4b5d8e5af298 |  | note | Reference Documents:
label | ca51b91d-f563-54b3-a14f-b6cee83fa8c4 |  | note | • VicRoads Section 607 March 2015
label | efcbe3d1-50ef-565b-b0b4-348dc112157e |  | note | 1.2 - Non Dependent
label | f4f5672e-d3fe-5b82-874c-ab470595ee4e |  | note | Reference Documents:
label | e3de9717-deca-5fe9-afd6-02f2ac36dbb2 |  | note | • VicRoads Section 610 June 2019
label | 09f1c815-3e13-5fbb-821d-1eada10827d0 |  | note | 1.3 - Non Dependent
label | fbff4bf4-31be-5584-b573-34de19f19bb5 |  | note | Reference Documents:
label | 31361a17-c6c3-55c9-8b0d-452eeb8f4114 |  | note | • VicRoads Section 611 November 2018
label | 773d1ca9-1320-5171-a5ba-71c18a413b25 |  | note | 1.4 - Non Dependent
label | d0e3994c-93c5-5748-ac34-2551e78da040 |  | note | Reference Documents:
label | 0df5e3fc-2b03-5075-beed-b6af53357e8c |  | note | • AS2159-2009
label | 951518e2-4968-5861-b015-7025143d9606 |  | note | 1.5 - Non Dependent
label | b56863f1-0ffd-51fd-9b92-94d63cd35dbb |  | note | Reference Documents:
label | 159afbb0-dea8-5732-8b69-92184f00a514 |  | note | • AS3810.1-2015
label | be4ee8f6-d48f-5d9b-b5c9-26cb5c187e4d |  | note | 1.6 - Non Dependent
label | 5b912002-b8dd-5e32-9cc2-27ae2f27caff |  | note | Reference Documents:
label | 3f031999-60a0-5bdb-a900-b6dba9a8ac1f |  | note | • AS5100.3-2017
checkpoint-group |  |  | section | Preliminaries - Materials
checkpoint-status |  |  | checkpoint | 2.1 Concrete Mix
label | e6b6fce8-8da4-5f27-9dac-7d581aebe422 |  | note | REFERENCE:
label | 02941778-7648-57a5-bad2-4cbd16e9b864 |  | note | 610.07
label | 42c5aa25-d29d-5f23-a7ed-da4bc9625e28 |  | note | Table 610.071
label | 64a869c8-35b2-58b9-bd99-0ff242dc7642 |  | note | – – – – – – – – – – – – – – – – –
label | 546cccf6-cdc6-5877-b01d-8314042ecf6a |  | note | ACCEPTANCE CRITERIA:
label | e2f9dcc9-f355-563f-b89a-d7db6a8fcfdd |  | note | • Concrete Mix is Registered with VicRoads.
label | aa449da5-e992-5a3c-b05c-0824be9fa509 |  | note | • Concrete mix meets strength, grade, and maximum aggregate size as detailed on drawings.
text | 40674fce-2247-529a-9d9b-d8ae2978d410 |  | textbox | Enter: Teambinder Material Approval number
label | c917990f-dcc3-5504-85d1-904b7f40480b |  | note | – – – – – – – – – – – – – – – – –
label | 34d4fda3-c9fc-51ad-b45e-ba78a947de10 |  | note | METHOD: Document Review
label | f4ca3ea2-1add-58b7-a6e1-10964205b9e1 |  | note | – – – – – – – – – – – – – – – – –
label | 1ab6d61e-9f1e-5719-8806-73d71c5d042b |  | note | FREQUENCY: Once, for each mix design, 4 weeks prior to placement of concrete
label | af7e8ea7-ab53-5f7d-bc9b-2ace8f41c185 |  | note | – – – – – – – – – – – – – – – – –
label | b8b10749-405d-5dbe-abf8-14c8f3557e03 |  | note | CATEGORY: HP
label | 7e7ff1a0-777d-5406-bb6d-0e7de37abe4b |  | note | – – – – – – – – – – – – – – – – –
label | 84431e09-2bde-555a-a438-a3015a221fba |  | note | RESPONSIBILITY: Nominated Authority
label | c93fcd6f-d5c3-5a6a-ad8a-1ddc7d21c29a |  | note | – – – – – – – – – – – – – – – – –
label | ee09559e-e1eb-5692-a710-921644c91d82 |  | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
text | 1497753e-057f-5c45-8e00-1932fab86c0d |  | textbox | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.2 ACRS Certification (for Reinforcement)
label | e00671e0-1948-5f86-9fcc-1f5ff19f0367 |  | note | REFERENCE: 611.05 (a)
label | e6173f55-4793-5248-a24f-81a30a57b07d |  | note | – – – – – – – – – – – – – – – – –
label | 5c2674fc-8ef2-5115-847f-65b682c56f16 |  | note | ACCEPTANCE CRITERIA:
label | 0af97f76-e186-58c3-8c66-78ecef6e71f2 |  | note | • Current ACRS certification for materials and for bar processing.
label | 0fb03936-aa0b-5e00-b8e3-c9ed45d7e5a0 |  | note | • Note: ACRS certificate may cover both aspects or be for each separate portion (e.g 1 for the material supplier and another for the bar processor (bending, cropping and delivery)
text | ef8d0620-11a0-5fc5-8489-df2e86b07120 |  | textbox | Enter: Teambinder Material Approval number
label | 414f97df-6ec3-539c-86b1-72c1571d7b18 |  | note | – – – – – – – – – – – – – – – – –
label | 06558eee-7b16-5813-894e-39e2c70a0598 |  | note | METHOD: Document Review
label | 9c5eb10c-8f34-5480-adb0-e11f2d19e0c1 |  | note | – – – – – – – – – – – – – – – – –
label | 6ea7afa9-8409-5ed6-849b-8eda0f7a1325 |  | note | FREQUENCY: Once for each supplier, 14 days of award of contract
label | 04faf56f-8c61-5ed4-a741-6c76f78a4866 |  | note | – – – – – – – – – – – – – – – – –
label | 48683286-273e-597b-9115-159b85f1de26 |  | note | CATEGORY: HP
label | 57dc0cb8-dc62-56bf-b862-93123f6e84a2 |  | note | – – – – – – – – – – – – – – – – –
label | 8d5ccd10-21c1-5512-9c77-c04ecc209be2 |  | note | RESPONSIBILITY: Nominated Authority
label | a10933ed-0e5b-55a9-9b82-c521805a1238 |  | note | – – – – – – – – – – – – – – – – –
label | 2ae4b7dd-05d2-56cd-81a3-b4959357545c |  | note | VERIFYING DOCUMENTS: This ITP
text | 7173f7db-60a6-53ca-86d6-1e6bf23f2c46 |  | textbox | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.3 Bar Chairs/Aspros Certification
label | 12f1996f-cb7a-589a-85e2-6c11ba309f94 |  | note | REFERENCE: 610.26 (a)
label | fdf85ddb-bfd8-5559-8ccb-94c1659fab56 |  | note | – – – – – – – – – – – – – – – – –
label | 5fbf9ae7-b5a1-5a89-9d0b-9c8b8a507392 |  | note | ACCEPTANCE CRITERIA: Wheels, and spacers require bi-annual testing to demonstrate suitability to prevent excessive deformation under loads.
text | d2b74115-73f5-5714-9e28-f69e32b28f92 |  | textbox | Enter: Teambinder Material Approval number
label | 0ead1d8b-fb44-5b4e-87fa-71f1d2c48685 |  | note | – – – – – – – – – – – – – – – – –
label | 14f684e5-883b-5588-9e3e-d7b358bfabf9 |  | note | METHOD: Document Review
label | 1d233384-d965-52a8-962f-47aea34b081e |  | note | – – – – – – – – – – – – – – – – –
label | 59a50cae-9b3c-542d-b223-a16f7f22e9ae |  | note | FREQUENCY: Once for each supplier, 14 days prior to placement of reinforcement
label | dedbac89-6650-5063-8daf-fdb2d546d721 |  | note | – – – – – – – – – – – – – – – – –
label | f16e7fd2-3ea4-5e06-b980-564138849cf8 |  | note | CATEGORY: HP
label | abee02ab-0f3a-5c21-ba1e-defa015e9e7f |  | note | – – – – – – – – – – – – – – – – –
label | bed15107-a396-51f6-829d-5c4b222f6b2b |  | note | RESPONSIBILITY: Nominated Authority
label | c612f2e9-85df-5798-811a-9b6dcc8f6148 |  | note | – – – – – – – – – – – – – – – – –
label | d19337af-80fd-58d3-b3cf-14c26487cba1 |  | note | VERIFYING DOCUMENTS: This ITP
text | 3edca008-bacf-5ee6-9060-52819c5b42e1 |  | textbox | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | Preliminaries - Procedures & Documentation
checkpoint-status |  |  | checkpoint | 3.1 Working Platform certification
label | e0b63556-ee4f-5dd1-909a-7fd4bd7b35bb |  | note | REFERENCE: Piling platform design
label | 5a106df2-c6f1-5174-88c8-32124664bc0d |  | note | – – – – – – – – – – – – – – – – –
label | 214ffec4-6820-5070-bc8e-e8267d1f572c |  | note | ACCEPTANCE CRITERIA:
label | 44fdf388-06b9-5e03-960b-4ec2dc59db2b |  | note | • Satisfies minimum plant bearing pressures requirement.
label | 792d43a4-53df-5de3-b108-4ec5cff74a39 |  | note | • ATTACH: Piling Platform Certificate
label | 6128419d-85ba-5d7e-87d5-aecae35a0797 |  | note | – – – – – – – – – – – – – – – – –
label | 961f24a5-0351-5da3-b38a-7f5a7c841b3f |  | note | METHOD: Document Review
label | 2bc93b80-e817-5206-b8ba-af4a731dc38d |  | note | – – – – – – – – – – – – – – – – –
label | 02e59985-2f1b-5776-a993-3fde57ee35f2 |  | note | FREQUENCY: Prior to works commencing & after rain event which there is >10mm in a 24hr period.
label | 7e764fb0-a55a-57cd-9907-5875431a9916 |  | note | – – – – – – – – – – – – – – – – –
label | e2f3d338-13da-5ce8-bd6a-6159cf530f26 |  | note | CATEGORY: HP
label | 1ad651c9-1d37-5668-acbc-5acb6784ddfe |  | note | – – – – – – – – – – – – – – – – –
label | a41a5ade-8cf5-5b25-80d2-ddfdfe82316b |  | note | RESPONSIBILITY: Piling Contractor/Geotechnical Engineer/Fulton Hogan Engineer
label | e5f9177b-58ee-5685-abe4-ab7963f606d9 |  | note | – – – – – – – – – – – – – – – – –
label | a3ce368e-59a0-5e28-ac94-d82a53627289 |  | note | VERIFYING DOCUMENTS:
label | 37ea9857-b872-5922-bc6e-de9ef7d376b5 |  | note | • This ITP
label | cc0ce12c-e583-5eb7-866b-f8905449b72e |  | note | • Platform Certification
text | 2fc8c7ef-5774-5379-9fe9-5e9e6b1f0711 |  | textbox | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.2 Concrete CFA Pile Design
label | 53a75d3d-f1c6-5dee-abc7-388e5d7bfdd2 |  | note | REFERENCE:
label | 00f1d1fe-3661-5068-9bd7-290d01f937d2 |  | note | 607.01
label | bb9f2e02-c05a-5a0d-9e7c-8009bd251bee |  | note | IFC Drawings
label | fc651d42-9301-57be-9427-3eaf45a39240 |  | note | – – – – – – – – – – – – – – – – –
label | ad95baa6-a171-58bc-93c8-1999e2fec21b |  | note | ACCEPTANCE CRITERIA: Concrete CFA piles shall not be used in foundations for bridges and other structures on or over roads without the approval of the Superintendent.
text | ddf46129-1132-5f78-a3f4-86b1812d5c46 |  | textbox | Enter: Teambinder Approval number
label | 28aefae1-8796-5f80-94c4-9228e921094a |  | note | – – – – – – – – – – – – – – – – –
label | 44a96bea-390d-5db1-a08d-45462ee47421 |  | note | METHOD: Document Review
label | 1876c45b-02ea-5f58-a12c-e8cab2baed4a |  | note | – – – – – – – – – – – – – – – – –
label | 8c14a288-abf9-5db1-9977-35fae1c122fa |  | note | FREQUENCY: Where applicable, once, 4 weeks prior to the commencement of piling
label | 12ae9c6d-a1f6-5277-9c87-540380c09663 |  | note | – – – – – – – – – – – – – – – – –
label | 41e1dfb2-1c62-515e-93fa-6c7feae7b993 |  | note | CATEGORY: HP
label | 6ca52adc-0c29-5097-ab25-005d7b5353ab |  | note | – – – – – – – – – – – – – – – – –
label | 8306cf6a-121d-523d-9eb7-f5e6338f9743 |  | note | RESPONSIBILITY: Nominated Authority
label | 8c9ed939-9394-5a54-8dd2-073b4c57ad4c |  | note | – – – – – – – – – – – – – – – – –
label | 8001036e-30b9-5f83-8487-9c09751669f4 |  | note | VERIFYING DOCUMENTS: This ITP
text | 1dcaeaa8-5cdd-5d26-a411-3deb430bf052 |  | textbox | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.3 Piling Operations Work Procedure
label | 8dd3e6f7-8991-5693-9b27-9c5f60863dde |  | note | REFERENCE: 606.03 (a)
label | c16a0ca2-612a-5133-b870-13cffb87b9ba |  | note | – – – – – – – – – – – – – – – – –
label | 4be58bac-163f-5738-aab5-9c94eb51b47c |  | note | ACCEPTANCE CRITERIA: Piling operations work procedure to be submitted for review to the Nominated Authority.
text | 5709bc97-c884-5e50-b3e9-7e084d6ee105 |  | textbox | Enter: Teambinder Approval number
label | 1fc6d3c0-f428-54a2-948e-a80423d7f794 |  | note | – – – – – – – – – – – – – – – – –
label | fe88073e-d76a-5107-b03d-a74ee544f63f |  | note | METHOD: Document Review
label | c770750d-a667-596a-9007-274f2670a892 |  | note | – – – – – – – – – – – – – – – – –
label | 0bb7a3fb-b6fd-58c7-adf9-bbac79d099ba |  | note | FREQUENCY: Once, 4 weeks prior to the commencement of piling
label | 6ef99a5f-23ad-5f4b-9644-f094ff3b551b |  | note | – – – – – – – – – – – – – – – – –
label | 3a3b6efc-b3c6-523c-96a6-2b763c4f21bc |  | note | CATEGORY: HP
label | e26958c6-d2c8-59c1-9d88-9fb9bacc4dbe |  | note | – – – – – – – – – – – – – – – – –
label | b6cbead7-f9c4-5b58-a3bc-9099571995e4 |  | note | RESPONSIBILITY: Nominated Authority
label | dc823df7-22ec-52aa-907f-1cb488d8a5f9 |  | note | – – – – – – – – – – – – – – – – –
label | 0bffaff7-8973-593e-b0e1-146d84be7c72 |  | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
text | 0585a0ad-e8c9-52f4-981e-4e9fe0c70729 |  | textbox | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.4 Casting Under Water Procedure
label | adaf1930-341c-5ca4-aa2a-6581b9aa7d42 |  | note | REFERENCE: 607.04
label | 9a1c2593-ebbb-5334-bf20-c452ff1806a1 |  | note | – – – – – – – – – – – – – – – – –
label | cbdadcf4-eb9c-5551-ab74-975a8c5405d3 |  | note | ACCEPTANCE CRITERIA:
label | f29f9d68-5cba-5430-a784-abe61fdfbe33 |  | note | • Where applicable, casting under water procedure using a temporary steel casing to be submitted for review to the Nominated Authority.
text | 3c12781b-39c1-5b38-ada5-b08d6ff04aa4 |  | textbox | Enter: Teambinder Approval number
label | 5dee6dcf-9002-5513-80de-8c2c2add1375 |  | note | • Note: Piling Operations Work Procedure may cover this requirement - if so, use the same Teambinder Approval Number if this is the case.
label | 450fd102-b4ce-52f4-b67f-b4f135ca325f |  | note | – – – – – – – – – – – – – – – – –
label | 0c81f093-6e12-5053-9bf4-4ee5b6385bb1 |  | note | METHOD: Document Review
label | ef53942d-a378-5beb-a227-a864254c0de1 |  | note | – – – – – – – – – – – – – – – – –
label | a1f18d49-71c4-51bc-aad4-5abbcf398daf |  | note | FREQUENCY: Where applicable, once, prior to placement of concrete
label | 4b38b0ac-45a7-5fa1-b0a0-2744f18a225b |  | note | – – – – – – – – – – – – – – – – –
label | 41647c13-2d4a-5b1f-9615-f939d2f9a73b |  | note | CATEGORY: HP
label | 3479660c-dbe8-5c79-83d2-2c93bd051e93 |  | note | – – – – – – – – – – – – – – – – –
label | 01acfe2e-152e-5878-a759-e3f95c7b014e |  | note | RESPONSIBILITY: Nominated Authority
label | a8e1112a-4101-5a9f-943a-4a604cc54f71 |  | note | – – – – – – – – – – – – – – – – –
label | 87275e00-5a93-5f2a-aa3f-a5a7ef3e324f |  | note | VERIFYING DOCUMENTS: This ITP
text | 32edc87a-f08a-5bbd-be24-918f3226e1a7 |  | textbox | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.5 Dynamic Pile Testing Procedure
label | fa11e898-2ae0-56cc-898a-46e23bac7d2e |  | note | REFERENCE: 607.07
label | 2236c0cb-63ea-5f63-8e20-39dd269e474b |  | note | – – – – – – – – – – – – – – – – –
label | 10b00ece-f10e-5d05-8500-dc8f8d6a3c53 |  | note | ACCEPTANCE CRITERIA: Details of the proposed pile driving rig, hammer size and drop heights to be submitted for review to the Nominated Authority.
text | e50c1d6b-7844-5e7d-8b7b-0b7d8ce03d80 |  | textbox | Enter: Teambinder Approval number
label | e5e8ed85-cb67-5e0b-9e00-dc079188247a |  | note | – – – – – – – – – – – – – – – – –
label | e53c48e9-5dda-5eee-a48f-7cfd31d41e26 |  | note | METHOD: Document Review
label | ab393b26-b5b4-52d5-adf0-e2c299fcc187 |  | note | – – – – – – – – – – – – – – – – –
label | a07d0533-3df3-5940-bc33-b1857116021d |  | note | FREQUENCY: Once, prior to testing
label | 5fc58fa0-0d79-5cc8-8909-903a5d73759a |  | note | – – – – – – – – – – – – – – – – –
label | 14024248-73a9-5b55-b1cc-b5a667484b3e |  | note | CATEGORY: HP
label | 956394d3-c147-58ba-bc49-157d15d17515 |  | note | – – – – – – – – – – – – – – – – –
label | 29f4143e-b62b-57c6-89f3-710b4e65ef32 |  | note | RESPONSIBILITY: Nominated Authority
label | 189d1a13-889c-5173-9e94-7808cd796671 |  | note | – – – – – – – – – – – – – – – – –
label | 1ddedc7c-9105-5a8d-9c60-fb26ae9aedee |  | note | VERIFYING DOCUMENTS: This ITP
text | 07522865-dbb1-5abf-aa9b-568ec56ec1a4 |  | textbox | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.6 Pre-qualified Pile Testing Consultant
label | 788ada95-27c5-50fa-80b8-be6b7e910288 |  | note | REFERENCE: 607.07
label | b611765d-7bc3-5e72-ae1b-938cea159663 |  | note | – – – – – – – – – – – – – – – – –
label | aadc1e89-c5d8-5cbe-b030-da7da2fa1db9 |  | note | ACCEPTANCE CRITERIA:
label | b994803f-5670-5693-85ef-f4201023b125 |  | note | • All testing shall be undertaken by a Vicroads pre-qualified consultant who is independent of the piling contractor.
label | 9c6e8a25-6619-5f8f-b2f3-d9b1a19d530a |  | note | • Details of the consultant to be submitted for review to the Nominated Authority.
text | c3f4bf77-9642-559d-8740-77dc39203aca |  | textbox | Enter: Teambinder Approval number
label | ec7c5367-0e11-5164-b8d7-215a69cc0561 |  | note | – – – – – – – – – – – – – – – – –
label | 6170bf87-b6b0-521e-8ccf-da8d3a5affe1 |  | note | METHOD: Document Review
label | 251bbea5-bd4e-577f-904e-a5c36f270897 |  | note | – – – – – – – – – – – – – – – – –
label | c00e152c-344c-55fd-91bc-59fa67316b4a |  | note | FREQUENCY: Once, 2 weeks prior to testing
label | 9c915265-5db8-57e4-8624-c93b1780917c |  | note | – – – – – – – – – – – – – – – – –
label | 4c3db164-5867-5277-896f-aae60d1ceab6 |  | note | CATEGORY: HP
label | 89877b47-2eb7-5b85-903d-d2f185984bc5 |  | note | – – – – – – – – – – – – – – – – –
label | 242621d7-0878-5ae4-a2b4-73570b82f38b |  | note | RESPONSIBILITY: Nominated Authority
label | 8f40897b-59cd-53a2-b7da-c5e8022fbc1a |  | note | – – – – – – – – – – – – – – – – –
label | afac3d60-ceaa-5b63-b3cc-8a1ef53b6eff |  | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
text | 38d8f895-c53f-5f3a-aa81-4b9217ab7be3 |  | textbox | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.7 Reinforcement Welding Specifications & Qualifications
label | c2a6103e-1117-54c3-bd3f-b8fe70b3435d |  | note | REFERENCE:
label | 06e7d05c-b184-5ead-8c0f-accc386321ad |  | note | 611.13 (a)
label | 2e171c67-7a17-5a87-b666-81a320090ee8 |  | note | AS/NZS1554.3, Clauses 3.3.2 & 3.3.3
label | 59a3a6f4-4409-5862-a5e3-99dadabe1cb1 |  | note | 611.14 (b)
label | 65848c5f-4b3a-5aaa-a9d9-c0c49122c2e6 |  | note | – – – – – – – – – – – – – – – – –
label | 0b58663d-6fef-51eb-a786-6471378d3894 |  | note | ACCEPTANCE CRITERIA: Where applicable, welded splices shall not commence until the welding specification & qualifications (including macro inspection) have been submitted for review to the Nominated Authority.
text | ccced383-60ec-5b49-adc4-f7d22c788287 |  | textbox | Enter: Teambinder Approval number
label | 873c70f6-c2dc-5a45-94a7-4137745aba81 |  | note | – – – – – – – – – – – – – – – – –
label | d2d3f91b-11db-5d4d-8658-7e2bdde03b51 |  | note | METHOD: Document Review
label | 835d64a5-8630-54a5-a85e-5855838d8f4d |  | note | – – – – – – – – – – – – – – – – –
label | 294fdc0e-1f51-59b2-a30d-1c25244e5e4a |  | note | FREQUENCY: Where applicable, once, prior to welding
label | 5a1e1f0b-94b0-5150-bee5-664e1d16b662 |  | note | – – – – – – – – – – – – – – – – –
label | 9b30ba64-c36a-5aab-b38d-54fe892a62c5 |  | note | CATEGORY: HP
label | d3b5a346-f8a8-50b7-a42c-3cb8db26281d |  | note | – – – – – – – – – – – – – – – – –
label | 36cc2f55-76c2-5cdc-b635-5fba2488c564 |  | note | RESPONSIBILITY: Nominated Authority
label | 4090a053-f7dc-5d42-be19-4df2dd34d1fc |  | note | – – – – – – – – – – – – – – – – –
label | f913e472-edbb-57fd-83d7-5b4b071516c4 |  | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
text | 879c350f-bd62-5d59-b298-8421f286ca8c |  | textbox | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | Pre-construction Activities
checkpoint-status |  |  | checkpoint | 4.1 IFC Drawings
label | 8302eeab-9c92-5ed5-aeb4-ad268bc74c40 |  | note | REFERENCE: MRPA Quality Management Plan
label | 599df973-8d56-5efb-8b4e-93ed11d1805e |  | note | – – – – – – – – – – – – – – – – –
label | 068d7f47-7473-59f2-b6de-8f3752d6e8d3 |  | note | ACCEPTANCE CRITERIA: Check the revision of the IFC drawings are current as per the drawing register (on Teambinder)
label | 15120bad-5da1-5e76-92ad-a7d1f16a8f3d |  | note | – – – – – – – – – – – – – – – – –
label | 3261dd6c-dfa0-5f52-9ae0-d7c20841c2c1 |  | note | METHOD: Document Review
label | 82f5eb63-6921-5d57-9e33-bb28552db41b |  | note | – – – – – – – – – – – – – – – – –
label | f6a7ebd8-2678-5bff-9e02-0f77d8003b96 |  | note | FREQUENCY: Prior to starting Works and at regular intervals
label | 046db6e5-928c-5627-84a5-933a82e81cf9 |  | note | – – – – – – – – – – – – – – – – –
label | f447ce0e-70f9-5e08-ae38-611530345a27 |  | note | CATEGORY: HP*
label | 669ad4e8-2bad-5c43-a00b-de0bed470544 |  | note | – – – – – – – – – – – – – – – – –
label | 58173127-3081-5a2e-bd67-e18abaec5173 |  | note | RESPONSIBILITY: All
label | 4cbd6afd-9620-5694-9999-65b06c0c08b9 |  | note | – – – – – – – – – – – – – – – – –
label | 780bb735-8028-5925-8d1a-150e92689f5b |  | note | VERIFYING DOCUMENTS: This ITP
text | 5bb6c783-3c40-5756-aeff-daeb30fc283c |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 4.2 Survey Set-out
label | b45bbb32-07c0-5931-bd7a-23f0a6bc9cc8 |  | note | REFERENCE:
label | 306f490f-d869-5a1a-aa5b-be8c803a2af3 |  | note | IFC Drawings
label | 6b1a2e93-114e-59b2-af65-affbf445eff4 |  | note | 607.06 (a )
label | e0d1a6dc-605a-560c-bf01-a2a5c851e5c1 |  | note | – – – – – – – – – – – – – – – – –
label | 3779384e-9434-5ed1-a5d6-a04890ff7c94 |  | note | ACCEPTANCE CRITERIA:
label | 576b9328-dc02-5d89-aa90-9cd579096680 |  | note | • Survey activities undertaken to ensure and validate that all Works meet location requirements of ±75mm.
label | 0624a16b-e9a8-573f-a295-3df8f000d1ad |  | note | • Attach: Lot Map, Marked drawing to indicate the location of piles in the Lot
label | 76cd3dde-d7d6-5cb2-8960-cef5e53d086a |  | note | – – – – – – – – – – – – – – – – –
label | f10a042e-df12-5d84-9eab-5a16fee74acb |  | note | METHOD:
label | 8292fd6f-1447-51a6-b7d6-ad5c4f65dc1e |  | note | • Measure
label | 96419738-7015-5f15-9c04-124beb25dc0c |  | note | • Visual
label | bd720192-a0ee-5a03-992b-2e9ccada0a51 |  | note | – – – – – – – – – – – – – – – – –
label | 5ed23c66-a65f-5365-9515-198c571bd089 |  | note | FREQUENCY: Each pile
label | e3d52180-e50e-55c6-bbf2-80a4198abf20 |  | note | – – – – – – – – – – – – – – – – –
label | 2c6ae7a2-1650-5df1-ba02-dede6b1839f7 |  | note | CATEGORY: IP
label | 4d5bf8c0-bcc6-5657-b4d7-da4c1b230ab7 |  | note | – – – – – – – – – – – – – – – – –
label | b16c38a4-292a-59fe-99c0-2d87190d771e |  | note | RESPONSIBILITY:
label | 3ed2cd5f-dc8a-51c5-84e6-bac46553656b |  | note | • Surveyor
label | 1ced7f52-19a7-5f2c-b0ce-283c39697543 |  | note | • SE/PE/SPE
label | 231182e8-6dd0-5ed5-8820-7b3ad7abb97a |  | note | – – – – – – – – – – – – – – – – –
label | d2581f63-3ecc-57b2-bb05-58b70c304167 |  | note | VERIFYING DOCUMENTS: This ITP
text | 01c03029-12ba-5faa-ae92-b7abf547f174 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 4.3 Protection of Adjacent Piles
label | 1d64cdb3-027e-58b8-9ce9-9e226690c2ee |  | note | REFERENCE: 607.05
label | 8c6ccfc8-8e6e-5505-9a10-3476eaa84cb3 |  | note | – – – – – – – – – – – – – – – – –
label | 6b6c829e-eac7-5762-b7c4-7f9c1a1da551 |  | note | ACCEPTANCE CRITERIA:
label | d2bd5f92-2320-54e4-98d2-aaff52067904 |  | note | • Pile construction shall not result in damage to adjacent newly cast piles due to ground vibration.
label | 677f2e83-3b76-53cd-9099-33464305d338 |  | note | • Pile excavation shall not commence within 2 metres or three pile diameters (whichever is the greater) of a newly cast pile until the concrete in the newly cast pile has attained a strength of 15 Mpa
label | 064456fb-daf5-52fd-833c-a040b008b4a1 |  | note | – – – – – – – – – – – – – – – – –
label | c45d1635-3ace-5877-9b23-229fbc11c967 |  | note | METHOD:
label | 960a68d3-c459-5044-871d-1f96e7a4ec79 |  | note | • Measure
label | 43cef934-a07d-5754-b6bd-a42cc10fe0ca |  | note | • Visual
label | 3ae0e3a7-4b22-5e8f-8f30-971ceca5f721 |  | note | – – – – – – – – – – – – – – – – –
label | 393ca6d8-87bf-5655-a8c2-b8da1ae9cf2e |  | note | FREQUENCY: Each pile
label | 44d5ac73-4fbd-5c64-a805-d7a44cf9b98d |  | note | – – – – – – – – – – – – – – – – –
label | af307444-7c0c-5039-8e7c-09f632fd1bd1 |  | note | CATEGORY: HP*
label | 7bc8e781-1b23-557b-9516-e7eb2c67357d |  | note | – – – – – – – – – – – – – – – – –
label | 52a498e0-b698-5458-9036-ad20ce22944f |  | note | RESPONSIBILITY: SPE/PE
label | 96a733bf-171d-532a-b4bb-ce1abb3391b0 |  | note | – – – – – – – – – – – – – – – – –
label | a9639976-9f8b-53cf-a4b2-3bb7df2d0c6e |  | note | VERIFYING DOCUMENTS: This ITP
text | 8b44bc78-4df6-52b8-b782-398c7a243648 |  | textbox | Date Completed:
checkpoint-group |  |  | section | Construction Activities
checkpoint-status |  |  | checkpoint | 5.1 Reinforcement - Inspection
label | a317cc07-4c31-5101-8a6a-a5bf585088a4 |  | note | REFERENCE:
label | 704ee794-d7ff-5e36-9047-aa68723ccd0f |  | note | IFC Drawings
label | 58d841e4-4b6f-5f48-9257-79151c34ecd3 |  | note | 611.06
label | c4679b0b-9d4a-5849-b149-3d9bbd61dc1b |  | note | 611.09
label | 7afb3a5f-68d7-52e8-b770-09dbc2127557 |  | note | 611.10
label | 75a4e45c-2be6-538f-9918-4788142c1743 |  | note | 611.11
label | 7969bbc6-e371-5872-b839-fa26491ca880 |  | note | 611.12
label | 434c010f-434f-5148-9805-51442ba596ff |  | note | – – – – – – – – – – – – – – – – –
label | 6cd9e403-507c-5074-b814-e99f2f197d60 |  | note | ACCEPTANCE CRITERIA:
label | d79f2ba9-c416-5fb8-b024-846142230387 |  | note | • The correct reinforcement grade, quantity, size, orientation, location and spacing as shown on the structural drawings.
label | b9e4b6c3-9cc5-5cf6-acd2-5f399feb3446 |  | note | • Projecting reinforcement is the correct length and location.
label | 4f0c5ec8-4a96-5a82-a970-17eee18de989 |  | note | • Splice lengths achieve the minimum length and are in contact for this length.
label | e4d48e21-acf3-5a3b-8cd7-d22e3e6184d5 |  | note | • The reinforcement surface condition is free from dirt, debris and damage.
label | e56cc545-3984-5dd1-bcc6-05bf2c76a436 |  | note | • Bar chairs or wheels used at no greater than 2m centres so that the minimum cover as shown on the structural drawings all around and has been achieved (including tie wire locations).
label | 85e20c21-4d32-59c6-be4c-a900970b705c |  | note | • The resulting reinforcement cage securely held with sufficient ties (or tacks) to limit displacement or deformation during handling.
label | 71c484d9-91c6-59a7-913d-e2492505d438 |  | note | – – – – – – – – – – – – – – – – –
label | 8ad2d9d0-9182-5e30-9dca-7617a26c82c7 |  | note | METHOD:
label | d8a382c7-449a-54c3-b8e2-6b0ba800754b |  | note | • Measure
label | 39976510-4255-5558-b19b-c465a462ab99 |  | note | • Visual
label | 6435c942-cd71-526b-bef7-536ec966e38b |  | note | – – – – – – – – – – – – – – – – –
label | 4c9ad975-cdfb-5d54-92cf-e9c1272483a2 |  | note | FREQUENCY: Each pile
label | 0388204d-35cc-57ef-a3bd-cd408d589426 |  | note | – – – – – – – – – – – – – – – – –
label | 15b82808-81d1-5dca-bb33-f661da694f3b |  | note | CATEGORY: IP
label | f355eb71-a635-50e0-9886-f2b44fa0e411 |  | note | – – – – – – – – – – – – – – – – –
label | 6259d671-7169-53d9-bc36-e3b3f4d14a76 |  | note | RESPONSIBILITY:
label | c8128fde-d471-5210-b1d6-e1be535beeb0 |  | note | • Foreman
label | ef2bec1b-521c-5a95-9e78-65802320f696 |  | note | • SE/PE/SPE
label | 63f5b36b-2022-591f-8b1d-48b692f03997 |  | note | – – – – – – – – – – – – – – – – –
label | 6e83879b-9c0c-520e-a16c-67c18f9dec3b |  | note | VERIFYING DOCUMENTS: This ITP
text | 68a3f965-218e-5569-98d1-8d302f04b79d |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.2 Reinforcement - Electrical Continuity
label | 4691d0bc-5b63-5918-af84-88b4ed8da2bd |  | note | REFERENCE:
label | 48bf9f5e-bb57-5865-910c-d744546060ff |  | note | IFC Drawings
label | 3a9b409f-899d-5f98-b589-3b6dd566fa11 |  | note | 610.29 (d)
label | 376d8ef0-ba56-5ce8-a22a-16608553e4f4 |  | note | 610.43
label | f34a45c0-afa9-5595-99bf-46a8991d7456 |  | note | – – – – – – – – – – – – – – – – –
label | d79e96bf-da9e-5e68-8d4e-e0373f384fc0 |  | note | ACCEPTANCE CRITERIA:
label | 5556b74b-3f04-5894-8679-d068339da059 |  | note | • Pile reinforcement cage to be made electrically continuous by:
label | 5e525698-dc16-5e9c-8dfa-ee118dc60d55 |  | note | i. tack welding 4 no. min. longitudinal bars to all intersections of the helix at 2.0m centres max. (at every intersection is preferable)
label | 3333ecbf-d145-5721-a4ca-ed5de17a6f6e |  | note | ii. tack welding the selected longitudinal bars at all splices (2 tacks minimum per bar)
label | c2762147-3a6a-5ce0-b476-04991b2763b2 |  | note | iii. tack welding or fastening the grounding clamps to the longitudinal reinforcement
label | bbcc0550-5479-52ad-92b7-1e8b6c9aa05e |  | note | • Evidence that the resistance across the cage has a maximum value of 0.01Ω / 10,000µΩ is required.
label | e25fa60c-b638-5ceb-82af-b03ff06aafaa |  | note | • Photograph or attach: Ohmmeter reading across the splice or end to end of the reinforcement cage
label | 23a77bff-413d-5b97-b49d-d40713df65b3 |  | note | – – – – – – – – – – – – – – – – –
label | 00c94f15-caf3-5996-8bb0-3960297a154f |  | note | METHOD:
label | 45c3bde8-cf59-5cee-b0f2-c34ff6a756e7 |  | note | • Measure
label | 993feaa7-7e0b-5897-86ea-d697c78de124 |  | note | • Visual
label | 866f4884-915d-50b8-83d6-ee331c6de02e |  | note | – – – – – – – – – – – – – – – – –
label | 901807b6-6971-5dfb-855f-236595a6cc2a |  | note | FREQUENCY: Where applicable, each pile
label | 263f00de-a20b-564c-9e6a-2b94f0f412f3 |  | note | – – – – – – – – – – – – – – – – –
label | d7ef6155-f64f-5c7c-9221-b8a91801b9b3 |  | note | CATEGORY: IP
label | 8fb3cbd3-6182-5e9c-bf1d-9259426dd22b |  | note | – – – – – – – – – – – – – – – – –
label | fbbb9d26-a6d1-5a45-a4fa-68c1e8467161 |  | note | RESPONSIBILITY:
label | 4e1235fa-bf8e-5dc7-9117-19db9b262676 |  | note | • Earthing Engineer
label | 7adb1e9c-23f0-53e4-ad9c-e1e001767198 |  | note | • SE/PE/SPE
label | f7809c77-b2b2-513b-a5b9-587ae7a08cbb |  | note | – – – – – – – – – – – – – – – – –
label | 5ab7dbbf-22cb-51f4-8512-c86672c88137 |  | note | VERIFYING DOCUMENTS: This ITP
text | 471af065-cc9f-5c03-8aed-2eeae4f6a89b |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.3 Augering Operations
label | a921fdb3-e9e5-5e9b-8398-c01208c3524c |  | note | REFERENCE:
label | ca7cb904-6bdd-5c31-bc20-cdea9c869343 |  | note | IFC Drawings
label | d7d5d020-c066-5f71-9e5b-905205b0aa8a |  | note | 607.04
label | 3ba9bdd2-0f8e-5d7d-944e-16cf846aa29b |  | note | – – – – – – – – – – – – – – – – –
label | 3d9f7769-4cd7-5513-8a3c-f450fada6116 |  | note | ACCEPTANCE CRITERIA:
label | 220d0c7e-4b01-50f1-acd5-3aa16e278270 |  | note | • Augering performed to the required diameter and depths shown on the IFC Drawings under the instruction of an experienced geotechnical engineer.
label | 56e19195-e209-53d7-a8b9-ac86e0f18c63 |  | note | • The augering shall be in once continuous operation with boring rate, penetration rate and torque monitored and recorded through-out the entire process.
label | 622069a3-6c0c-5d1a-85df-0517e8e464aa |  | note | • Where piles are founded on rock, they shall extend into the rock at a depth shown on the IFC Drawings.
label | f34c9a33-0137-5a77-bb87-3ffdaacbf6c9 |  | note | – – – – – – – – – – – – – – – – –
label | 027f3f2f-861e-5a69-a282-bba3f7459a62 |  | note | METHOD:
label | aedfa89c-77ea-5dcd-80c0-464606d812c4 |  | note | • Measure
label | 7e15b893-83dc-51e4-bb02-961a2a6af3e9 |  | note | • Visual
label | cc8e3298-63c2-5175-a250-2b1920713499 |  | note | – – – – – – – – – – – – – – – – –
label | b59de282-e015-574a-af72-8964e7789b43 |  | note | FREQUENCY: Each pile
label | 85c956ef-d04a-5636-a6cd-02095e6c9487 |  | note | – – – – – – – – – – – – – – – – –
label | ef471b89-63f8-50a2-8489-0c6c11543e3d |  | note | CATEGORY: IP
label | 2ad93007-4bee-5794-b13f-9f9a20d54e25 |  | note | – – – – – – – – – – – – – – – – –
label | ee20b9a7-762c-54db-a4a7-4890b62538a7 |  | note | RESPONSIBILITY:
label | f93ed0fb-1f9b-55b7-a48e-3e641a519a3e |  | note | • Surveyor
label | 594bafd6-b6b9-54db-8af2-21bd1c532211 |  | note | • SE/PE/SPE
label | 4e23f366-151c-5d4f-a24b-b79f0964a8e1 |  | note | – – – – – – – – – – – – – – – – –
label | cfb57e13-c643-5bde-a158-4fb6e48335e3 |  | note | VERIFYING DOCUMENTS: This ITP
text | 984ffcac-1de4-51db-88fc-c22bec98d789 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.4 Inspection of Excavated Material
label | 5a83c3f2-49ed-56b8-9044-e2cff5ce3fdc |  | note | REFERENCE: 607.04
label | 9dac00db-3dbc-5882-8ec3-91e2dcece376 |  | note | – – – – – – – – – – – – – – – – –
label | 66351ea9-0f28-5615-9ac6-3f97cdeb1e8d |  | note | ACCEPTANCE CRITERIA:
label | 2611c619-80c5-5a16-8c0d-13fc4327db44 |  | note | • Excavated material to be inspected by the geotechnical engineer to confirm that the geotechnical strength of the materials in the pile wall base have satisfied the design assumptions.
label | 2ebd6efd-8e9c-57d7-a2fa-83b3016df793 |  | note | • Attach: Geotechnical Field Sheet or Report
label | 27eed6a3-96cd-5299-8acc-e12ccc20bd76 |  | note | – – – – – – – – – – – – – – – – –
label | 458ace61-0fa4-52ad-9552-fcc92387bd34 |  | note | METHOD:
label | 198dd56e-b7ac-52d7-98ab-6677eb617627 |  | note | • Measure
label | 4144e958-a656-5202-8589-b6b62f0aa1ce |  | note | • Visual
label | 09c5a053-74d1-58c1-8b65-06858d0f5795 |  | note | – – – – – – – – – – – – – – – – –
label | d6e09971-9e10-50b1-aec3-ecdef1a8b876 |  | note | FREQUENCY: Each pile
label | fdf1a5f4-f2cc-5ec2-8480-e214fc993887 |  | note | – – – – – – – – – – – – – – – – –
label | 8b7aff69-9e5c-5b73-9640-13f76b650c5b |  | note | CATEGORY: HP
label | db2c8fa2-650b-52b9-9670-e61b5d149377 |  | note | – – – – – – – – – – – – – – – – –
label | e65617e9-14e0-5bf5-bea2-8fc44fb49219 |  | note | RESPONSIBILITY: Geotechnical Engineer
label | 402e9f50-f852-58cd-ac4c-42de7230be31 |  | note | – – – – – – – – – – – – – – – – –
label | df67e5d8-1536-5322-bf03-021aebf78b8a |  | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
text | 4c17856c-adb2-5176-bf86-00f6d91fac47 |  | textbox | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 5.5 Increase in Depth Beyond Design
label | a855b737-51fc-5b03-9fa9-342834f74eee |  | note | REFERENCE:
label | 71c7e04e-219f-5dd7-b9fd-38e962698242 |  | note | 607.04 (a - d)
label | 25eeb2aa-76cb-5f6c-a39f-fdbde7ac1f4c |  | note | Piling Operations Work Procedure
label | b5ac6dce-1073-5653-b08f-bae7037c0cf5 |  | note | – – – – – – – – – – – – – – – – –
label | 3f6a9713-4ac9-5269-a6b1-280f887ba7f1 |  | note | ACCEPTANCE CRITERIA:
label | 369ce681-dbd0-5a93-8575-c5fad3402ba8 |  | note | • Where increasing the pile depth beyond the levels shown on the IFC Drawings is necessary, follow the approved work procedure and obtain confirmation from the geotechnical engineer that the newly bored depth has achieved the required design capacity.
label | 576383c3-35d6-5223-b606-2acd065600ee |  | note | • A full account of the changes shall be submitted for approval to the Nominated Authority:
label | bcf8c6ed-018a-5ac5-8d43-8122c1f91de1 |  | note | • Attach: Geotechnical Engineer's Acceptance of the New Pile Depth
label | 4d45158b-59ad-579c-98cc-06228cceae80 |  | note | – – – – – – – – – – – – – – – – –
label | 2e037ad5-f085-5a02-9771-2cebebdf4241 |  | note | METHOD:
label | 7fe612b5-c064-530c-9c7a-7984070cf3e7 |  | note | • Measure
label | 6ce4b377-19af-5925-8a21-c5f7245347d5 |  | note | • Document Review
label | 632bc1dd-7505-58e2-9569-64dc570b3475 |  | note | – – – – – – – – – – – – – – – – –
label | 184d1af8-8201-5cbe-9706-f8baa8932722 |  | note | FREQUENCY: Where applicable
label | 87f69df9-003a-5c35-8ba7-b8aa41ea3ade |  | note | – – – – – – – – – – – – – – – – –
label | b778d35e-7f6d-5712-a9b7-dfb7bd71b18f |  | note | CATEGORY: HP
label | a3cfc03a-813a-5b34-b832-faf00a80e306 |  | note | – – – – – – – – – – – – – – – – –
label | 0f075fb2-8eb4-55a2-a1b2-da052abd3f10 |  | note | RESPONSIBILITY: Geotechnical Engineer
label | 13b37d69-50b0-591c-90db-10dd95c560d2 |  | note | – – – – – – – – – – – – – – – – –
label | 5797aefa-a794-56d7-8e7d-e9f4d9b7c6c8 |  | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
text | 62f1e31e-48a1-593c-8304-0cbf06cfb97e |  | textbox | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 5.6 Weather Conditions & Evaporation Limits
label | ae0c29d3-aa4e-5418-b8f8-c866285802f8 |  | note | REFERENCE:
label | 1e4423e9-f903-5bbf-a21e-9562dffe212a |  | note | Hot and/or Cold Weather Concreting Procedure
label | 5c8cb70e-b527-5173-803f-f63af5af7fec |  | note | 610.17
label | 5066f9bb-29c2-5d14-aa39-e32287a06c0f |  | note | 610.17 (a) & (e)
label | 5c7a8d98-9e18-5e47-85a2-62c4abbf8639 |  | note | Table 610.171
label | 8cd017f2-7721-5d92-a380-41d8fcedae2d |  | note | – – – – – – – – – – – – – – – – –
label | 6ca1427a-264d-5aeb-ab1d-3681881d5c2d |  | note | ACCEPTANCE CRITERIA:
label | 439ccf99-836b-5a20-854d-61a0e6e35d8c |  | note | • All freshly finished concrete surfaces shall be protected where required from the sun, wind or rain, until curing is implemented.
label | eb303a5b-5422-5766-8bdb-69be56a1991c |  | note | • The temperature of concrete, measured immediately prior to placing, shall not be less than 10°C or greater than 32°C.
label | c75d1bd1-94c9-5462-9d47-a9e1e125dbd9 |  | note | • The air temperature, relative humidity, concrete temperature and wind velocity are measured to determine the evaporation rate of water from the concrete.
label | fd01ecd5-8240-5d64-bd71-aa45525d3ab4 |  | note | • Record: Required information on the Concrete Pour Record.
label | 2c83067c-601b-52c2-bac4-75d1e7a041cc |  | note | – – – – – – – – – – – – – – – – –
label | 5912be87-7efe-5580-82d2-833fad139b0e |  | note | METHOD:
label | 39f932e5-5bbb-5db7-9d37-7ad9ff9060dd |  | note | • Measure
label | 4ad23dc0-0a6f-5d48-97a1-d0641d57d432 |  | note | • Visual
label | 1f584f6f-72b3-58a7-8df7-7409bf28883c |  | note | – – – – – – – – – – – – – – – – –
label | fabded33-5ef7-5195-bc39-16b7567e3a49 |  | note | FREQUENCY: Each pile
label | 519358c4-953c-514c-81cc-487036dc626f |  | note | – – – – – – – – – – – – – – – – –
label | b00227e8-f367-5790-856c-ae4bbe45af68 |  | note | CATEGORY: IP
label | 7ef9aa49-1211-53b1-9700-c61614103741 |  | note | – – – – – – – – – – – – – – – – –
label | bdea8d1a-6c5a-5269-bbd0-17df9e119840 |  | note | RESPONSIBILITY:
label | 23150932-2c09-5134-8794-fe04d1e14037 |  | note | • Foreman
label | 745eda9d-ad46-5cae-a503-e089c7bfa6a7 |  | note | • SE/PE/SPE
label | f238c93c-132c-567a-859f-3e5bb595d1c9 |  | note | – – – – – – – – – – – – – – – – –
label | 5b0f68cf-9085-5f13-a72d-7ae9ebbc4887 |  | note | VERIFYING DOCUMENTS: This ITP
text | f5f62cf1-d161-539b-9b74-50a2b94a626d |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.7 Concrete Testing - Sampling Frequency
label | 7967d8be-3f57-5bb9-8a06-b25832a3f251 |  | note | REFERENCE:
label | 56b5cb11-2918-5c6b-a7fc-e6ad049322e4 |  | note | Site Sampling & Testing Procedure
label | 19f965dd-fff0-518c-8f30-fd0a30393a22 |  | note | 610.16 (b)
label | 2bd06326-37a1-50b0-bb63-590b22db6db8 |  | note | Table 610.161
label | 475ffe7f-8364-5409-938c-2d82ec3190de |  | note | – – – – – – – – – – – – – – – – –
label | c68e842d-3664-5d16-8fc4-51c863ec9908 |  | note | ACCEPTANCE CRITERIA:
label | f2710a07-d46f-539b-8f14-2d9ac7a7d5f1 |  | note | • Concrete cast in one continuous operation to be tested at a frequency as shown below:
label | 2b40e9b9-19ab-52c0-99d5-b7be9e4e86b3 |  | note | 0m3 to 10m3 = 1 sample
label | 0986ea46-fe81-55bf-bd4c-4986160cf962 |  | note | 10m3 to 25m3 = 2 samples
label | 71e54ada-afcf-55d7-98f9-148fbd472c63 |  | note | 25m3 to 50m3 = 3 samples
label | 63ebf705-414d-52e1-b3a3-5c4d1f2f01f8 |  | note | 50m3 to 100m3 = 4 samples + 2 no. VPV cylinders.
label | 1d9daf79-4272-5e23-bfec-1ee823b5e453 |  | note | ○ For each additional 50m3 and additional sample shall be taken.
label | f305a696-c919-5881-965b-ecc06059f342 |  | note | ○ Where the time interval between the end of discharge of one truckload of concrete and the beginning of discharge of the next truckload exceeds 45 minutes, the minimum number of test samples shall be one (1) per truckload of concrete
label | 54012a0c-cd2d-5767-a760-1ed21fdc5dff |  | note | ○ Each sample shall consist of 1 no. slump or spread test and 3 no. compressive strength cylinders minimum.
label | 2198f436-e4ef-514b-87ed-0d1f4c542b75 |  | note | ○ Compressive strength cylinders = 1 no. 7 day strength, 2 no. 28 day strength.
label | 32d2e0c7-3bb9-5d3a-b769-5c3eaaaa9220 |  | note | • Note: Additional cylinders may be required for other purposes such as early strength determination of adjacent piles.
label | 77dad52a-d886-538c-aa71-8e81f0dfaea5 |  | note | • Record: Required information on the Concrete Pour Record.
label | c2df939c-cf73-56b9-99a6-6aca6d1bb0f5 |  | note | – – – – – – – – – – – – – – – – –
label | 374909e6-96f7-5f5a-93dd-e86e4e731e3a |  | note | METHOD: Test
label | 5161e2c5-b1c6-5f6b-b4e4-eea719c5a3b2 |  | note | – – – – – – – – – – – – – – – – –
label | be6f720a-2f56-5f56-be82-db8c958e57e9 |  | note | FREQUENCY: Each pile
label | 54a7c94f-8e47-50ea-b87d-9299f00fdaf4 |  | note | – – – – – – – – – – – – – – – – –
label | e52a3e8c-c948-5cd0-af47-9159e5c38d4d |  | note | CATEGORY: IP
label | 0640c8fc-8741-59a2-a798-dcdafeb1b2eb |  | note | – – – – – – – – – – – – – – – – –
label | ac3f5774-7c35-52a1-8d52-4cfd022d587f |  | note | RESPONSIBILITY:
label | 097df871-4080-58fa-aebf-8f521c535b67 |  | note | • Concrete Tester
label | 5953449c-b379-5857-ae53-07984ab93ad0 |  | note | • Foreman
label | 1831fdba-04ed-5c95-8f2e-0655c217d0f7 |  | note | • SE/PE/SPE
label | edeb24c7-0be0-58f3-bdff-f21bc6ced4e3 |  | note | – – – – – – – – – – – – – – – – –
label | 159f0875-3416-574e-b2c9-6d81d410c560 |  | note | VERIFYING DOCUMENTS: This ITP
text | a667bdd8-f43f-5732-a346-e6f18416a77c |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.8 Concrete Testing - Spread, Passability & Viscosity
label | d5e355c3-22f9-52cc-b809-f4c1ed76585f |  | note | REFERENCE: 610.13 (b)
label | ecff2e8d-026c-5151-b80f-eadcf3e8e0fd |  | note | – – – – – – – – – – – – – – – – –
label | bd0de7cb-a5c8-5c1d-a884-230cf704e170 |  | note | ACCEPTANCE CRITERIA:
label | 00d2db4e-4341-5b13-aafa-b6e42e952acc |  | note | • Spread range = 550mm to 750mm
label | 000c2286-64c6-577d-b251-38b809c434e9 |  | note | • T500 = 2 seconds to 5 seconds (to reach a spread of 500mm)
label | 28021447-fb10-5e4e-9c56-65c4e2377f7b |  | note | • Passability = ≤10mm (aggregate height differential)
label | 7db46fee-0622-51dd-b812-7911d526f4bc |  | note | • Record: Required information on the Concrete Pour Record.
label | a0520175-9d5b-5b14-868a-c5d981fabe8d |  | note | – – – – – – – – – – – – – – – – –
label | 815c7f3c-9344-51fb-bfa8-8c77b8a38f8a |  | note | METHOD: Test
label | 8a77633e-1840-57fb-b887-7a9f8d6f2973 |  | note | – – – – – – – – – – – – – – – – –
label | 02ae2ee9-286a-5b4e-b4ad-4d78f3fee441 |  | note | FREQUENCY: Each sample of Self-compacting Concrete
label | 192bdff0-8e4d-5c7c-b4ee-de4c3f958cf8 |  | note | – – – – – – – – – – – – – – – – –
label | 0bb5974c-1f0b-520b-a18f-84d4225344e1 |  | note | CATEGORY: IP
label | 93a69d61-fe63-5291-9ce0-e7ab74f5b682 |  | note | – – – – – – – – – – – – – – – – –
label | bb6ddc24-8bde-585f-a7a5-26530198548a |  | note | RESPONSIBILITY: Concrete Tester
label | 6d6ed1b8-77c2-5de8-af6d-dd676abfb44f |  | note | – – – – – – – – – – – – – – – – –
label | d16bbabb-4f8e-5517-8d5c-e42af874dfb5 |  | note | VERIFYING DOCUMENTS: This ITP
text | eb3c5250-7317-5a0d-92bf-f543cb7b2ebb |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.9 Concrete Testing - Compressive Strength Cylinders
label | f596f955-3d1d-5182-a9f2-1ec1b1a1ec83 |  | note | REFERENCE: Site Sampling & Testing Procedure 610.16
label | 939ed0e4-4e99-5dff-8c7a-b0a72bd34979 |  | note | – – – – – – – – – – – – – – – – –
label | 197a5ff2-cf1c-5fd4-90d4-7a40c462c3ad |  | note | ACCEPTANCE CRITERIA:
label | 4d932947-d527-57e9-9da5-db917263027e |  | note | • Correct quantity of cylinders manufactured per sample.
label | d79dfd7e-9754-5db1-8a42-f030f2283c3d |  | note | • Record: Required information on the Concrete Pour Record.
label | 5190d5ec-7672-531a-a00a-110b3923f9d4 |  | note | – – – – – – – – – – – – – – – – –
label | c7bb4aed-9674-5ac1-9f77-9c55233c5843 |  | note | METHOD: Test
label | c0d861aa-f6af-5172-b64a-6968078be6ee |  | note | – – – – – – – – – – – – – – – – –
label | 7c003c06-7956-570a-90ff-4b098f85e492 |  | note | FREQUENCY: Each sample
label | 998e5ad6-c4f6-5a73-9779-a21aa679162b |  | note | – – – – – – – – – – – – – – – – –
label | 63e066a4-f27e-5f2b-bced-524794556e33 |  | note | CATEGORY: IP
label | 87aea465-b9dd-5ecf-8850-50e98fc6156d |  | note | – – – – – – – – – – – – – – – – –
label | 463d5e38-b224-56b1-872b-e07e4886072f |  | note | RESPONSIBILITY: Concrete Tester
label | d203b627-5522-5180-949f-81877647550f |  | note | – – – – – – – – – – – – – – – – –
label | b2f49e6a-fd81-5e13-a44f-c2958c239f66 |  | note | VERIFYING DOCUMENTS: This ITP
text | 37d4856a-e143-5915-98f5-cf558e8f5175 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.10 Concrete Placement & Compaction
label | 0ec5fa26-0da7-576c-a858-0edf998d907d |  | note | REFERENCE:
label | f69b9d2e-1f89-5db6-aa87-081193826c69 |  | note | Piling Operations Work Procedure
label | bf071714-e565-5fb0-8088-0b66570c0553 |  | note | 610.18 (a) & (b)
label | f53fdbf8-af6c-545c-ad04-d9842e93eed9 |  | note | 610.18 (d) (i)
label | 25fc0217-47d9-51b7-b802-aeee4060c0a4 |  | note | 607.04
label | 6e77fbc1-8ecc-59cd-95a4-f3472516e993 |  | note | – – – – – – – – – – – – – – – – –
label | de388217-acb1-58cb-94e3-3e19f1615c31 |  | note | ACCEPTANCE CRITERIA:
label | f7e0cff1-0e3e-5d75-bfc1-50f2cd45e3cd |  | note | • All concrete batches are traceable.
label | 9a1956c3-2f9d-5f1a-91cc-0874b5bbd9f7 |  | note | • The concrete delivery hose shall be primed, pressurised before the toe of the auger is extracted.
label | 8382a9b7-75ca-5c1a-a3ec-992d41afca41 |  | note | • The concrete flow, positive pressure and over-supply rate shall follow the approved Piling operations work procedure, be continuous and monitored through-out the concrete pumping process to ensure that the excavation is completely filled, leaving no voids or inclusions.
label | 4fe5445f-badb-5a55-a9ee-be5829addf33 |  | note | • Pile height is to be constructed to ground level or a 300mm above the cut-off level to allow for breaking back of sound concrete.
label | c7fe3dd3-4f0b-57bd-9386-5560e4817e37 |  | note | • Concrete shall not be dropped freely from a height exceeding two metres
label | d84088ac-76bb-5f96-9af1-18459bafaac4 |  | note | • Record: Required information on the Concrete Pour Record.
label | 0c7a8c59-20b8-5787-bedf-853edbac8a57 |  | note | • Attach: Concrete Pour Record
label | cd33c132-d30a-5130-bec5-c9da5e8c790c |  | note | • Attach: Concrete Dockets
label | 86051b19-70c2-5fbd-8837-dacbf5805d98 |  | note | – – – – – – – – – – – – – – – – –
label | e70d4b0c-4533-56f5-8ec3-a3336341bbd1 |  | note | METHOD: Visual
label | a4754f56-37db-5641-9b61-34529fc7eab7 |  | note | – – – – – – – – – – – – – – – – –
label | 8b8e45c9-3473-5e9b-8ecb-32130947876c |  | note | FREQUENCY: Each load
label | 8723953f-eda8-5384-baca-943f459af1a1 |  | note | – – – – – – – – – – – – – – – – –
label | 47efc508-9a07-5895-9800-e2b354fe070c |  | note | CATEGORY: SP
label | 60ac7446-428c-5ca7-9370-b1d8b6fbd9f7 |  | note | – – – – – – – – – – – – – – – – –
label | ab6a4a8d-5808-58f4-8ddf-cfa713d6834f |  | note | RESPONSIBILITY:
label | 337cd787-cc13-5f3b-aff6-130e48442ea7 |  | note | • Foreman
label | 1a53db02-61bb-5abb-a3f2-f51cb8cc411f |  | note | • SE/PE/SPE
label | ea4972cc-9421-5951-94ef-831ef1594ef7 |  | note | – – – – – – – – – – – – – – – – –
label | 4c6bf13d-c485-5b23-b1d2-00a41cc02e14 |  | note | VERIFYING DOCUMENTS: -
text | 3cf4ff1a-7a68-53eb-ab7b-ef8495a2bf4d |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.11 Reinforcement - Placement
label | 1cb698d0-16ea-5d2b-87d5-f76d74477aad |  | note | REFERENCE:
label | afb08fd3-376b-5bc0-80af-bb238b3acd20 |  | note | IFC Drawings
label | 9e680f1a-666c-5edd-ace5-7da0068e2c6c |  | note | 607.04
label | 43faab1a-d765-595e-b929-d02705d875c8 |  | note | – – – – – – – – – – – – – – – – –
label | 8b7560fa-31dc-525c-b042-e696c8c8a96c |  | note | ACCEPTANCE CRITERIA:
label | dcc03959-ee8e-5c56-8744-7067baacdeb6 |  | note | • The cage to descend into the plastic concrete under its self-weight - care to be taken to centralise the cage so that there is no dislodgement of excavated material contaminating the concrete.
label | 1407a344-42aa-5c25-8faf-00ff1c2a9786 |  | note | • Note: Vibration of the cage shall only be performed under approval from the Nominated Authority along with evidence that the vibration does not segregate the placed concrete.
label | 38726d7f-acdb-5baf-a2fb-3d0432b17f2e |  | note | • If the cage cannot be positioned into its final level, the pile shall be rejected.
label | 1c6a29d5-8c62-58b5-a325-8ed459f1e8fd |  | note | – – – – – – – – – – – – – – – – –
label | 8e376135-1b57-5307-b7c6-51c39fb85741 |  | note | METHOD:
label | 4d48fdfc-5ef5-573e-ac53-fafb82903dd7 |  | note | • Measure
label | baae46b1-becd-592c-85b3-ccc05352b4c9 |  | note | • Visual
label | 5ce2e790-b230-5e4a-863c-f02b75b87509 |  | note | – – – – – – – – – – – – – – – – –
label | 7e20dbd2-3bfd-5d2a-b698-1f68f31c9453 |  | note | FREQUENCY: Each pile
label | e763bbfd-2310-5b6b-8ae8-bd00496ecd94 |  | note | – – – – – – – – – – – – – – – – –
label | 8f3341e3-2116-560d-aadb-24ced8b28117 |  | note | CATEGORY: IP
label | f6a43967-6328-5305-8292-50a77b05c2e5 |  | note | – – – – – – – – – – – – – – – – –
label | 0d9c4cb2-59c2-5a89-83be-4796dffb1218 |  | note | RESPONSIBILITY:
label | 5c5c9e9a-55b8-5d3a-b085-3ba808850a84 |  | note | • Foreman
label | 1386bda7-f2fa-5c01-a23f-a07b3cc6fd68 |  | note | • SE/PE/SPE
label | 752d8156-2365-5770-a14d-d43a93afbff5 |  | note | – – – – – – – – – – – – – – – – –
label | 706b675f-1c2d-5c4f-9ca8-05b627b41991 |  | note | VERIFYING DOCUMENTS: This ITP
text | 012ab89c-3272-5e94-b7e3-ef40ba19c058 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.12 Cast-in Items
label | e7de76c3-770d-505a-ab50-d7510b8078b6 |  | note | REFERENCE:
label | 2c6525f8-507e-5303-9172-5399a2b5f742 |  | note | IFC Drawings
label | ceca86a3-8a3a-546f-a48e-17833f75c57a |  | note | 610.46 (a), Table 610.462 (November 2018)
label | 7732b4c7-df30-5179-8416-1d80bb625441 |  | note | 610.47 (a), Table 610.472 (March/June 2019)
label | c01f0ec0-9ed3-5e72-8753-4eb4770b795b |  | note | AS3810.1 Table 3.3.6.2
label | c4320404-6aa6-5ade-b36f-f3287bd6e3fd |  | note | – – – – – – – – – – – – – – – – –
label | ef1bd43a-2ab8-5f02-9c85-74e51ebfb455 |  | note | ACCEPTANCE CRITERIA:
label | 483dcf48-f027-5bb2-b11d-0b52f3391436 |  | note | • All cast-in items are the correct type, grade, quantity, size, orientation and location as shown on the structural drawings and are securely fastened during the hardening of the concrete to prevent dislodgement.
label | 9e49a545-a47d-5f02-842e-4d62bab7798e |  | note | • Any exposed threads, conduits, ducts or voids shall be protected by suitable means to prevent concrete or grout ingress.
label | 7c04f32e-a147-5dd6-858f-d561ee43ed1e |  | note | • Tack welding of any cast-in items shall be performed by someone pre-qualified to do so.
label | 5cf0d91d-a586-50ab-9524-561c751d683e |  | note | • Grout tubes shall be fastened at regular intervals to prevent kinking.
label | 93d31c42-4e0c-5518-aa0e-5e5cc0641806 |  | note | • Placement tolerances to comply with the IFC drawings, if not specified, use the following:
label | 98c9cca6-cb96-504b-ae76-0891c577acdf |  | note | i. Bolts, ferrules, projecting bars & couplers = ±3mm
label | 0bb35c35-6759-5dc6-9adc-901f77c2bb7b |  | note | ii. Running dimensions of a group of the above = ±6mm
label | f53fb823-f6b8-5a0f-b67f-b7e3bf1aeedd |  | note | iii. Ducts and conduit location = ±12mm
label | e4298a1a-ab6f-545f-9902-1d7783f06bed |  | note | iv. Diameter of ducts and conduits = ±3mm
label | a6936804-f4ed-5473-aefc-c65774bdca8f |  | note | – – – – – – – – – – – – – – – – –
label | 751b549e-703a-51aa-8e13-08be24130edd |  | note | METHOD:
label | ba874f29-db59-50e6-bce3-6ead5058d2f2 |  | note | • Measure
label | 72682f0e-1ad2-5ab2-a3ff-c62041b02bbb |  | note | • Visual
label | e08d3602-c4c7-5da6-986c-02894d8170d2 |  | note | – – – – – – – – – – – – – – – – –
label | 0fa2d6ba-dbfc-5629-8a6a-4a67a26b168d |  | note | FREQUENCY: Where applicable, each pile
label | fb74863b-f70d-508d-90df-3ee6c2276316 |  | note | – – – – – – – – – – – – – – – – –
label | 9a9bf514-3be1-59f9-b699-57652e9e0eac |  | note | CATEGORY: IP
label | b47689bd-1883-5307-929f-19e439b6ea13 |  | note | – – – – – – – – – – – – – – – – –
label | fd0694e6-3eea-560e-9682-bea2a2d8c5f0 |  | note | RESPONSIBILITY:
label | 22a32e95-d2e5-5170-929c-a554cee3b332 |  | note | • Foreman
label | da9e6e84-0196-5740-87d3-0863871d1169 |  | note | • SE/PE/SPE
label | 94eac999-fda0-5b0b-9171-22cf13eaaa83 |  | note | – – – – – – – – – – – – – – – – –
label | b39b4ce0-c3f6-5f8b-a33c-6cd09b23ea38 |  | note | VERIFYING DOCUMENTS: This ITP
text | 6c11d63e-9f75-57c5-832b-db96418f0277 |  | textbox | Date Completed:
checkpoint-group |  |  | section | Post-construction Activities
checkpoint-status |  |  | checkpoint | 6.1 Pile Trimming
label | 82bd880c-d9d8-5726-bc10-4e2056cccfa1 |  | note | REFERENCE:
label | 09c73800-63b6-5979-81cb-fd961726ec01 |  | note | IFC Drawings
label | a0593b7f-2020-59b8-a675-3d5d7f640b8e |  | note | AS2159 Clause 7.2.2 - 3
label | ae7a6d23-16d7-5faf-8638-230052fcd703 |  | note | 607.04
label | 456ec6b1-b425-5fbe-918c-6ca2e78f9547 |  | note | – – – – – – – – – – – – – – – – –
label | 8f5d9a85-d326-5c47-8d42-4ed7fbe0d5a9 |  | note | ACCEPTANCE CRITERIA:
label | cac0dff9-e1c6-58f0-8136-7f8f03a69cf1 |  | note | • Piles shall not be broken back until a minimum of 24 hours after completion of the placement of concrete.
label | b8739967-9753-50ba-9594-b43ac82a52de |  | note | • Care shall be taken to ensure that the full cross-sectional area of the pile is at the required RL without any cracking or damage.
label | 36a10a42-fd7b-51ee-97ec-4af28f9d2010 |  | note | • Any weak or damaged concrete shall be removed back to sound concrete.
label | 9cfe4231-2910-53f2-a551-922c902229b8 |  | note | – – – – – – – – – – – – – – – – –
label | aed9b7a5-9984-5943-b633-8da9c090b4f1 |  | note | METHOD:
label | b6473fc2-0fed-5146-ac6d-5c50748905c8 |  | note | • Measure
label | 5717891c-854d-5e1b-8463-72ffdd11dd4d |  | note | • Visual
label | 7e41eb21-2ed8-5980-9478-5263b982c540 |  | note | – – – – – – – – – – – – – – – – –
label | ea1e29a3-cbd2-58db-a5eb-724bf6af3959 |  | note | FREQUENCY: Where applicable, each pile
label | 6de5062c-d9ad-5a68-a589-bfccb1116ed9 |  | note | – – – – – – – – – – – – – – – – –
label | 5e874c96-15f9-5624-88e4-219fb6441073 |  | note | CATEGORY: IP
label | cb994f1b-605d-5d9f-99e9-165423037d48 |  | note | – – – – – – – – – – – – – – – – –
label | 6a2fa62f-a4b8-5b89-8ec1-cb14517e7ac5 |  | note | RESPONSIBILITY: SE/PE/SPE
label | b154257a-7e4d-5063-aaa5-ba8bf72b8aa5 |  | note | – – – – – – – – – – – – – – – – –
label | 9ccc8c54-15dd-5677-9b89-aeaeff2be9fa |  | note | VERIFYING DOCUMENTS: This ITP
text | e47ea150-51f9-5b35-8901-9103d6a4bdad |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 6.2 Compressive Strength Test Results
label | af471017-df3b-55fc-bb09-d3733561516b |  | note | REFERENCE:
label | 8aa23041-53ac-5c97-bb49-124338dcc74a |  | note | IFC Drawings
label | 0d86b191-5a16-5e8c-879d-fe7837973f31 |  | note | Table 610.05.051
label | 304c27d0-0b95-57c6-a35b-ea4dede68dae |  | note | 610.16 (g)
label | 7b28e8a1-22c6-5081-9303-1cac6a1bd853 |  | note | – – – – – – – – – – – – – – – – –
label | c19fc38f-5c20-5a94-a8a8-f398d926036d |  | note | ACCEPTANCE CRITERIA:
label | 851ada47-8a1c-5c56-a0c2-a0b3041f90a9 |  | note | • 7 day compressive strength to comply with table 610.051 for early indication that the strength is tracking correctly.
label | d2a784cb-a72d-5067-924c-b213c66cd269 |  | note | • 28 day compressive strength (average of the 2 no. cylinders) per sample comply with the design strength.
label | 0b898c91-f3ef-54f4-85e6-11c0a05a2deb |  | note | • Note: 1 of the 2 no. 28 day cylinders per sample may be as low as 90% of the required strength, so long as the average meets the required strength.
label | 25d4360f-d89c-507b-936c-5b3a9d37a5f6 |  | note | • Attach: Compressive Strength Test Results
label | f5499451-bde1-5ff5-9e1a-078e878edd14 |  | note | – – – – – – – – – – – – – – – – –
label | 259189d0-0fdb-58c2-98ca-264e69165285 |  | note | METHOD: Document Review
label | e9d6b5d2-8932-5b32-8eea-38012180606d |  | note | – – – – – – – – – – – – – – – – –
label | a024356d-8df6-558e-b2e6-93b7d2faa7a3 |  | note | FREQUENCY: Each cylinder
label | b8beb025-c470-51f6-a44d-820373d33c93 |  | note | – – – – – – – – – – – – – – – – –
label | 8a727588-8b73-5612-90e1-a98d2bee2a81 |  | note | CATEGORY: IP
label | 728ec606-f936-5c99-9de5-0c56e82e6ed8 |  | note | – – – – – – – – – – – – – – – – –
label | d9e5d656-9705-5c70-a046-0e0b580ccf53 |  | note | RESPONSIBILITY: SE/PE/SPE
label | 878055bc-3262-5ccc-88b3-e73c3ea8ed0f |  | note | – – – – – – – – – – – – – – – – –
label | 6f283d6b-dcca-59c6-8369-26a49bd8be87 |  | note | VERIFYING DOCUMENTS: This ITP
text | b7f264fd-0351-5b40-9639-e49be0dd80d0 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 6.3 Pile Integrity Testing
label | 30c45b8f-4c5a-5e70-a883-c1a898c9c447 |  | note | REFERENCE:
label | 00431c98-bcaf-5f0f-9860-2f9b78659d26 |  | note | 607.07
label | 6880e675-d994-5d1d-a7b6-499c606f4095 |  | note | AS2159 Clause 8.8
label | 5bf6e88c-2144-54e4-93e1-5d78dd0eae3c |  | note | – – – – – – – – – – – – – – – – –
label | bfc8d353-f54e-57ff-b59d-bd28db43c2a3 |  | note | ACCEPTANCE CRITERIA:
label | fab6b7e3-3799-5beb-8f0c-fb7a494f40aa |  | note | • Pile integrity testing shall be conducted after the concrete strength has reached 25MPa but not less than 7 days from casting.
label | 607e08b6-49e5-5cd6-82ea-6349b9e1f0fb |  | note | • Cross-sectional area = ≥90%
label | c048a9a2-8f67-5b85-8a53-261150a30f10 |  | note | • Attach: Pile Integrity Test Report
label | b8852c2f-7b5d-5251-b42c-7a9afb9406d9 |  | note | – – – – – – – – – – – – – – – – –
label | 46d54237-8b21-59a2-9d9d-82a381f092ce |  | note | METHOD: Document Review
label | c20bcba8-985c-5880-a6c4-e6fb1886a48d |  | note | – – – – – – – – – – – – – – – – –
label | 1700e520-132c-596b-9bc2-5788819b453f |  | note | FREQUENCY: Each pile
label | a9abe824-a6b8-57e8-91ca-8722002243fb |  | note | – – – – – – – – – – – – – – – – –
label | fbe72c67-5ae6-530d-a709-544e29c81e6d |  | note | CATEGORY: IP
label | 2c9f90ed-153d-53db-a146-2aa8afdb0751 |  | note | – – – – – – – – – – – – – – – – –
label | 2f72e8fb-47ad-5203-a678-7583b7b88b57 |  | note | RESPONSIBILITY:
label | 4de2e63e-19f2-585e-b3d8-5e59b378f715 |  | note | • Testing Consultant
label | 20870682-b9fc-58f4-8729-025ec2ca561b |  | note | • SE/PE/SPE
label | eb1bbf41-a752-5e22-afe9-b25d0d3aefc0 |  | note | – – – – – – – – – – – – – – – – –
label | 281b6870-8f1a-584a-acbc-306d653b9dc8 |  | note | VERIFYING DOCUMENTS: This ITP
text | 66a6190f-ef54-5ce9-9e8c-c5b7d5b48f42 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 6.4 Dynamic Pile Testing
label | aa903e34-0384-5d85-a1c1-0f5a6430e7b5 |  | note | REFERENCE:
label | f45c19bd-6f7a-534b-b4a5-0b22e6132d18 |  | note | 607.07 (b)
label | 0854a456-1f17-5a0e-91df-9ecf92038b3a |  | note | AS2159 Clause 8.7
label | 25001f79-e485-5a05-a0a4-4b89f29c0995 |  | note | – – – – – – – – – – – – – – – – –
label | 62e6ba13-8957-5fa0-9f19-7ee099d6beab |  | note | ACCEPTANCE CRITERIA:
label | 3e545087-18b5-5aa7-a538-bfb39339c126 |  | note | • Dynamic pile testing shall be conducted after the concrete strength has reached the 28 day compressive strength.
label | 0487dfe9-407a-5d9f-bd92-875aa88186d9 |  | note | • Measured Ultimate capacity = ≥ values on IFC drawings
label | 5046b69a-46a1-51c7-9320-081169d2cac9 |  | note | • Attach: Dynamic Pile Test Report
label | 0abba7d0-f500-59ba-93a9-7d0e3a1aaab6 |  | note | – – – – – – – – – – – – – – – – –
label | 7aa6f84f-7dc7-5730-b491-7b43518b172d |  | note | METHOD: Document Review
label | ac22590a-22dd-5a55-93d0-22f5078b1bf4 |  | note | – – – – – – – – – – – – – – – – –
label | 02c066a4-e840-5f9c-97cf-77923de04da8 |  | note | FREQUENCY: Where applicable, 1 test per pile cap / abutment, where pile toe RL varies >2m from the test pile.
label | b31bf7e8-e774-5171-a0d3-3d97eb77de40 |  | note | – – – – – – – – – – – – – – – – –
label | 18f101cf-e60d-5372-987a-d1c294fdf636 |  | note | CATEGORY: IP
label | 147e0887-49e8-5bd6-b7ae-cd0e87e6ce6f |  | note | – – – – – – – – – – – – – – – – –
label | a6087886-a7f8-5c16-9a7a-ce559df1fe73 |  | note | RESPONSIBILITY:
label | 30d10fd0-a141-5567-ac6c-2e0c4ca75c7a |  | note | • Testing Consultant
label | be709147-ef28-55ef-ad49-c1c827eec6c9 |  | note | • SE/PE/SPE
label | 70258f9a-ceb5-54de-b55f-482873159124 |  | note | – – – – – – – – – – – – – – – – –
label | 0c7ee861-30d1-57a2-91d2-b757c48dd30b |  | note | VERIFYING DOCUMENTS: This ITP
text | 3618b106-4261-55e8-9489-62de5a72142e |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 6.5 As-built Survey
label | 65f3a90e-3c25-5cfe-9935-a5f6d5795ebf |  | note | REFERENCE:
label | d2dfc16a-f709-5b69-b5a7-a0723a84b310 |  | note | IFC Drawings
label | f03a8b4e-6279-5634-87fa-579b1957ea70 |  | note | 607.06 (a & b)
label | ec00adde-b345-57a4-8348-c227fe87db75 |  | note | AS2159 Clause 7.2.2
label | c98eec6b-a9e6-5880-8a5b-36050df736af |  | note | – – – – – – – – – – – – – – – – –
label | b073c97b-be1b-5b1c-901b-618f69e74aca |  | note | ACCEPTANCE CRITERIA:
label | a2d39406-9e8f-57a9-9a3f-0efefc977e55 |  | note | • The following tolerances apply to piles:
label | a8fd3f9b-3f05-59e0-aae8-b0da18f722ed |  | note | i. Centre of pile head plan location = ±75mm
label | f34313fa-b0e7-535b-a868-24b7c4541478 |  | note | ii. Variance from vertical or rake = 1:50
label | 41a28fc2-957a-51c6-a7c1-c2e9c95a6d91 |  | note | iii. Irregularities in straightness = 1:100
label | 8b861926-1af4-5f19-a48b-5e6095321bbe |  | note | iv. RL = ±25mm
label | 879cc518-6e2d-5be5-bf00-c8fa3e70234c |  | note | • Attach: Survey As-builts / Survey Report
label | e060c0f8-72c8-5dab-81be-e3318b31e6d8 |  | note | – – – – – – – – – – – – – – – – –
label | 3d42751c-3195-5c0f-9ae5-8182f9fede7f |  | note | METHOD: Document Review
label | f0d64098-e671-500a-85fd-1f4c889948f7 |  | note | – – – – – – – – – – – – – – – – –
label | 5c86c900-0e2a-5b59-8c76-979a7bb5d039 |  | note | FREQUENCY: Each pile
label | 1a578bc1-377a-5290-86bf-db86e51906cc |  | note | – – – – – – – – – – – – – – – – –
label | 188fe300-e28d-5ba1-87d2-5e0042b9f5ba |  | note | CATEGORY: IP
label | 30ce56f9-a385-5336-86a5-1b14770601d3 |  | note | – – – – – – – – – – – – – – – – –
label | ab248bcc-1a96-53a7-b5b0-3f05c4bc26e1 |  | note | RESPONSIBILITY:
label | 51de8547-3225-5b03-9544-a05d867bb37c |  | note | • Surveyor
label | 8c18e31f-5592-55ef-907a-f58227e2d8e9 |  | note | • SE/PE/SPE
label | 99faf69c-25f8-5cfa-ae74-923b2c3b9ae0 |  | note | – – – – – – – – – – – – – – – – –
label | 3af3cb09-72eb-55ae-a720-52a817d4f23a |  | note | VERIFYING DOCUMENTS: This ITP
text | 7e8f2162-2ed5-51d9-99de-1c61a367f2d8 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 6.6 Non-conformance Report (NCR) Closure
label | 829edf49-6b0c-598c-8902-b25319af2de3 |  | note | REFERENCE: MRPA Quality Management Plan
label | ded89642-63c9-50be-9d48-b140c230e69a |  | note | – – – – – – – – – – – – – – – – –
label | 7895ba42-8f35-5704-b18a-2473ec8099e0 |  | note | ACCEPTANCE CRITERIA: Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed.
label | 2e97aa56-cda3-5655-afc6-f3345854e92b |  | note | – – – – – – – – – – – – – – – – –
label | ae9a14d9-5f16-51d5-a836-4d0dafd82530 |  | note | METHOD: Document Review
label | 92f01a70-f1b7-5e18-8f52-5dcff51e4ab9 |  | note | – – – – – – – – – – – – – – – – –
label | 46603636-1513-5519-9f06-e1fbae93f456 |  | note | FREQUENCY: Once, prior to closure of this lot / element / Work area
label | d2db17aa-dd73-5915-beaa-a4f86c9cb8b6 |  | note | – – – – – – – – – – – – – – – – –
label | ff1361ef-3f08-536a-a8b9-c2950301dc16 |  | note | CATEGORY: HP*
label | 407241dd-58cc-591a-8153-b735b9a69352 |  | note | – – – – – – – – – – – – – – – – –
label | cac8e338-73fd-5e96-adf0-d5d24b861094 |  | note | RESPONSIBILITY: SE/PE/SPE
label | fd36a17b-065a-568e-b715-7c7a5728e5ac |  | note | – – – – – – – – – – – – – – – – –
label | 11e821e2-4a07-5ae5-a47c-db419cdbb221 |  | note | VERIFYING DOCUMENTS: This ITP
text | f731fdbe-b344-57ff-9c58-7838c5848fed |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | Metropolitan Roads Program Alliance Final Inspection
label | e1420f2c-78d3-5b3b-ba7a-1cdd08d7d278 |  | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
text | 6ad3d4db-5758-5799-adc6-c68a1311ebe6 |  | textbox | Name:
text | d67a933e-3ebf-5859-8190-fb9719da2fb0 |  | textbox | Position:
text | ffd24bed-16b9-57e3-a900-431932d2e06d |  | textbox | Date Completed:
holdpoint |  |  | signoff | Sign ITP
checklist-sectioned |  |  | checklist | ITP-RAIL-CAMMS-MTM-Conduit and Pit-Temporary Rev 0 | itp |  |  |  | Yes | ITP-RAIL-CAMMS-MTM-Conduit and Pit-Temporary Rev 0 | e26fd899-d5df-4826-b4bb-9b9e8026dd3a
checkpoint-group |  |  | section | Referenced Documentation
checkpoint-status |  |  | checkpoint | Referenced Documentation
label | bf90ed8b-6c22-519d-98d8-06d4df0cfe66 |  | note | Document Title: ITP-RAIL-CAMMS-MTM-Conduit and Pit-Temporary
label | e3efe4a6-a8b7-5484-9057-58bf1a511256 |  | note | ITP Description: Conduit and Pits-Temporary
label | 9686f80d-a5e2-5138-8a00-3ab5dd783b0d |  | note | Document Number (in Teambinder): MRP-0000-MRPA-ALT-ITP-00XX
label | 6c8425a7-21f0-561d-9158-afc2f2989546 |  | note | Discipline (e.g. CIV/STR/RAIL): RAIL
label | 7eab6f97-9dad-50c8-9632-1071756b7ca0 |  | note | Revision Number: 0
label | fe3bb6eb-4410-54c3-9394-d28273527773 |  | note | Revision Date: 30/08/2020
label | 3249d04b-26cd-5581-8099-8f4c10be896f |  | note | ITP created by: Isaac El Zayat
label | 81da3fe3-0c6c-5be1-9106-1549665c1658 |  | note | ITP approved for use by: Victor Mira
label | 37fd94cf-db1d-5775-a897-842b57534db7 |  | note | 1.1 - Non Dependent
label | 9189eda9-272b-52f3-b609-fe0a91081196 |  | note | Reference Documents:
label | 0e598221-7b94-5b4c-8740-58f974e03f18 |  | note | IFC Drawings
label | 8ed73d3c-20d4-5533-a29c-5177f63830be |  | note | L1-CHE-STD-043 (VRIOGS 012.2.1)
label | 985b610d-0718-5160-b307-2efd6ad9cfeb |  | note | Australian Standards
checkpoint-group |  |  | section | Preliminaries-Materials
checkpoint-status |  |  | checkpoint | 2.1 Conduits
label | 1f566cf8-66d2-5744-8945-097202548107 |  | note | REFERENCE:
label | 282c901d-82ba-54c5-b505-094c4790234b |  | note | Comms Conduit: AS/ACIF S008:2006
label | abe96299-4472-5374-b1b8-7615d62d8fdb |  | note | LV Conduit: AS/NZS 3000 - 2000.
label | 10c3dfbc-4d42-59fd-8026-7676d8b33d17 |  | note | L1-CHE-STD-043
label | f1548a03-bc0e-5c54-b6ad-c707827be01d |  | note | ---------------------------------
label | 4e945a6d-57bf-5d36-baae-63498a59ca54 |  | note | ACCEPTANCE CRITERIA:
label | f94a93fa-ee2f-5b71-8a07-1a645b80cf38 |  | note | Comms Conduits: 100Ø (114mm OD), PVC White comms conduit 4.6mm wall thickness
label | 86667eb5-a06b-563d-aff8-c0e8d5a6648a |  | note | LV & Signalling: 100Ø (114mm OD), orange electrical heavy duty 5.9mm wall thickness
label | a2c16ffd-39a1-5a13-b155-3b85b5e7691d |  | note | Inspect materials upon delivery and attached delivery dockets.
label | 32ac31d5-d38d-5171-a784-90a1039dca7e |  | note | ---------------------------------
label | a6bb60ac-bb24-5634-bf00-c145d8fadd49 |  | note | METHOD: Document Review
label | 3408d780-0cc4-528f-b921-188f279bec93 |  | note | ---------------------------------
label | 83524a85-5cdf-58c6-a0ae-d708788496cb |  | note | FREQUENCY: Each Material Type, Each Delivery
label | c708a368-4c2c-585c-b115-6ff70f20037e |  | note | ---------------------------------
label | a67b8cee-6be4-5715-b82f-363c69c23bbb |  | note | CATEGORY: IP
label | 83b42dec-5bd9-569e-a56e-a5600b021000 |  | note | ---------------------------------
label | 290ddaac-b44d-5343-8c16-24e54a88fce3 |  | note | RESPONSIBILITY: SE/PE
label | eae9e3da-6a95-5ae5-8ce3-517c8825c2cd |  | note | ---------------------------------
label | cd8af18e-5501-538a-a330-0043d79c0a95 |  | note | VERIFYING DOCUMENTS:
label | 4687bd63-6601-523f-b498-106e471de7bc |  | note | Attach Material Conformnace Certs, include TB Approval No.
label | 28827953-f9e5-573c-bdca-f8596c754335 |  | note | Attach delivery dockets
text | be89af8b-ed39-5fc2-8378-136f21032f66 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 2.2 Pits and Pit Lids
label | 6d506818-b57a-5bb3-b548-2116ce2d3926 |  | note | REFERENCE:
label | 3235a2fe-c980-5ab4-ba37-5405e5663256 |  | note | IFC Drawings
label | d03300ee-348b-5310-8a35-7b9141bb86a6 |  | note | L1-CHE-STD-043
label | 00e0f5eb-ccad-54a3-88f1-c0f12e287045 |  | note | ---------------------------------
label | 1e27fb79-1634-51a8-a53a-49ef2ce02832 |  | note | ACCEPTANCE CRITERIA:
label | 0b76269e-13f6-56d5-bc7d-fe1658e49bde |  | note | • Pits: Concrete Pits to be made as per AS 3600
label | b3b28c53-38d6-56e3-9903-5649947518c2 |  | note | • Pit Lids: Pit Covers shall comply with AS3996-2006
label | 7a9ad78b-9283-557f-982a-21e3fe5ff662 |  | note | Pit lids in trafficable areas to be Class D, non-trafficable areas to be Class C.
label | 7b92b1e1-d438-524a-bbec-a2a2b15aba7b |  | note | LV, Comms Cover: pit covers shall be labelled with the words “RAILWAYS SIGNALS & COMMUNICATIONS” (L1-CHE-STD-043 14.6)
label | 068d700f-8048-58fb-b7d7-f612d8a75da0 |  | note | Inspect materials upon delivery and attached delivery dockets.
label | 182797c4-8ed7-5b01-8a0e-ecd6cb77f3e2 |  | note | ---------------------------------
label | 60fc863d-0931-5c85-af09-85cc1d34d025 |  | note | METHOD: Document Review
label | 86f14eb0-ab1f-58e3-8061-d2831001d0cd |  | note | ---------------------------------
label | af73d79d-4717-5dac-a8e6-4183eadeb155 |  | note | FREQUENCY: Each Material Type, Each Delivery
label | 47e3cbba-3db0-5389-a34e-b277a1a8e7cd |  | note | ---------------------------------
label | cf60397e-6755-5484-9997-432723e9a66e |  | note | CATEGORY: IP
label | ab79d8cc-260b-58ae-8d4d-9b6cce91bc38 |  | note | ---------------------------------
label | d61f3992-2d52-566e-92ab-22e02ab16b16 |  | note | RESPONSIBILITY: SE/PE
label | c28b82e3-cf53-5ebe-9660-8e00dcafe351 |  | note | ---------------------------------
label | ca609459-7050-50eb-94ca-6a4116066f4e |  | note | VERIFYING DOCUMENTS:
label | a7d8627c-fbee-5c90-8ea7-88ea1afe0ec1 |  | note | Attach Material Conformnace Certs, include TB Approval No.
label | a701adbb-9f0c-5634-a171-f957317ddd9e |  | note | Attach delivery dockets
label | e7dd3031-e21a-5a79-a196-3e65bf00d58e |  | note | Attach Precast Birth Cert
text | 572096ac-5605-5c68-b5d2-ea29d7c8d8f3 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 2.3 Warning/Marker Tape
label | ef80df02-bb70-5ce4-b2e1-48046e974050 |  | note | REFERENCE:
label | a558872b-0457-5402-941a-237de154f372 |  | note | IFC Drawings
label | 9d15a2f1-e17d-5c10-b4ec-8536003986c6 |  | note | L1-CHE-STD-043 6.4
label | 16abf6ed-ec92-56aa-9bba-0b2d3407c14d |  | note | ---------------------------------
label | beba12a2-a3f2-50a8-87d6-082df0d52645 |  | note | ACCEPTANCE CRITERIA:
label | 5d9674b3-844d-5104-9988-e7eadb4f2318 |  | note | • Warning/Marker Tape:
label | 7ad77e8d-dc13-5d9b-8abf-d3987edc894e |  | note | • Above LV:
label | 9122fcfc-5c60-5356-92c7-03c8573a0bcf |  | note | 150mm minimum wide orange coloured PVC
label | 82f14355-0f0c-5582-978a-b06ff970a0a9 |  | note | ‘DANGER RAILWAY SIGNALLING CONDUITS’
label | 1e1ff94c-76d9-5a39-bcf7-bf4512db72bf |  | note | • Above Comms:
label | ae642106-478d-55d8-a443-abeb26f32317 |  | note | 75mm minimum wide white coloured PVC
label | 11bb940e-c8bc-5c73-93ac-04d20c93a7b3 |  | note | ‘WARNING COMMUNICATIONS CABLES’ with an embedded stainless steel trace wire
label | 2c07dbc7-ae07-54e5-a2f4-d61959f6dbf2 |  | note | Inspect materials upon delivery and attached delivery dockets.
label | 049fddd8-d588-5f29-850e-13dfa7712cb8 |  | note | ---------------------------------
label | a7e6e58a-fb40-5063-8e1b-5d8916d9e34e |  | note | METHOD: Document Review
label | d8441dd9-e4fc-513d-bc50-c3a0627eec46 |  | note | ---------------------------------
label | 784215b3-63ea-50a1-b30e-ca0caf4322a4 |  | note | FREQUENCY: Each Material Type, Each Delivery
label | f1c19371-0429-54eb-b25f-b164a6194878 |  | note | ---------------------------------
label | 1907ae65-a1ea-50d9-b939-022f9d6c2d7f |  | note | CATEGORY: IP
label | 89ad9da6-1ed3-5e89-ad47-a8b776453c70 |  | note | ---------------------------------
label | 8b54635c-e91b-5adb-a720-23a50c6a77be |  | note | RESPONSIBILITY: SE/PE
label | 97e4a208-9f01-5fdf-b835-974c12b4d71b |  | note | ---------------------------------
label | 66335cde-18b2-51d0-b536-679628d3cd90 |  | note | VERIFYING DOCUMENTS:
label | 8547a0f4-7c1a-5096-b508-1b4f09fa9ccf |  | note | Attach Material Conformnace Certs, include TB Approval No.
label | 92767350-2ec3-5157-9df7-70b234f3bd4b |  | note | Attach delivery dockets
text | ce026a42-24bb-52f7-94e0-e6aefe9fe6b0 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 2.4 Protection Barriers
label | b042269e-e45b-50fc-b8b6-20f65c79cafb |  | note | REFERENCE:
label | 1dfd535c-2e07-5259-817c-48321860f8cf |  | note | IFC Drawings
label | 449631db-a1c3-547f-ab65-16a1ce1f6372 |  | note | L1-CHE-STD-070
label | 059a40c5-88ec-5b8b-9dfe-bde3a632c876 |  | note | ---------------------------------
label | 0a34e599-0b22-5877-824b-6eb488830854 |  | note | ACCEPTANCE CRITERIA:
label | f989f733-a357-5557-bc30-86c68ac56296 |  | note | Approved plastic protective orange strip (Vinidex or type approved equivalent)
label | 8d94fd48-c6c6-5b6c-a823-b8be72cd9c79 |  | note | Inspect materials upon delivery and attached delivery dockets.
label | cb59e849-3839-55eb-a626-aee09676f8e4 |  | note | ---------------------------------
label | 717a769a-1d87-50fb-b360-0a73b132c901 |  | note | METHOD: Document Review
label | c2dd9435-54d0-5945-8fc7-e73a6c307961 |  | note | ---------------------------------
label | 2b81e876-dee1-574b-a336-4ecf8e1a497d |  | note | FREQUENCY: Each Material Type, Each Delivery
label | f9a18784-9607-5401-9038-bd671ad71655 |  | note | ---------------------------------
label | cc1d6462-2b04-5d15-903d-35eecf86599f |  | note | CATEGORY: IP
label | 7a09221c-dd4e-59bd-abc5-90029e0aa7c6 |  | note | ---------------------------------
label | d3c0ed0c-a95d-58d8-98e7-547708c2d16a |  | note | RESPONSIBILITY: SE/PE
label | cb752997-6860-51e5-8416-d53563f024a7 |  | note | ---------------------------------
label | 0cc4748e-d2e2-5752-9f6f-d3ebd6a3da96 |  | note | VERIFYING DOCUMENTS:
label | 2f2cc158-06b2-55b2-bd94-4c67ebf3e9e9 |  | note | Attach Material Conformnace Certs, include TB Approval No.
label | e8900088-dc30-5df7-a895-0ae044188b34 |  | note | Attach delivery dockets
text | df81d17d-cad3-58d8-b553-ec4e99c5a97a |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 2.5 Backfill Material
label | 03eb518f-ace3-55f4-bc20-e8b810177cec |  | note | REFERENCE:
label | 838df13f-e840-5bc5-bb05-faadffa5f714 |  | note | IFC Drawings
label | 15f91c3a-0175-5294-97ff-7427f2952281 |  | note | L1-CHE-STD-043 Section 2 Table 1
label | 6308ac7c-1685-58b0-acda-d0e81b82e6b8 |  | note | ---------------------------------
label | b025d7eb-4640-5dbe-9a53-66d2397081a1 |  | note | ACCEPTANCE CRITERIA:
label | ea95a501-1842-5cfd-9f41-34667839c1ac |  | note | Material free of rocks that will not pass a 30mm sieve. The material shall be free or organic matter or anything that could dmanage the conduits.
label | 31b6cb02-023e-5a79-9019-5839320eb9d3 |  | note | Inspect backfill material.
label | 8a8b0042-2c7e-5b84-a6df-b012b678c55f |  | note | Attached delivery dockets (if applicable).
label | c3af4524-c51b-5921-b28a-93b1fd70d4b1 |  | note | ---------------------------------
label | 14dd357d-5503-5292-83fa-bcddcf4e64ea |  | note | METHOD: Document Review
label | e7928602-2739-5e84-946b-fcada7bc34ca |  | note | ---------------------------------
label | 8d88bf2b-5fb2-5b45-983f-3ef9ec0f1195 |  | note | FREQUENCY: Each Material Type, Each Delivery
label | 630c937d-5108-53a9-a43a-dd68eeb1e00e |  | note | ---------------------------------
label | c6b6f3cc-6567-5a93-bb79-d68315d2637e |  | note | CATEGORY: IP
label | 75b76b75-3a0e-5efd-9afb-b71d8d0d6b1d |  | note | ---------------------------------
label | 9592a3d1-7ca6-5dd6-98ef-f8bc469a0ec0 |  | note | RESPONSIBILITY: SE/PE
label | 3c25ed44-dcd0-5b49-91d5-b649d8939368 |  | note | ---------------------------------
label | ee551379-aab1-55a9-bb57-b35da3aa72ce |  | note | VERIFYING DOCUMENTS:
label | 27b21db6-3fc6-5ee0-adb4-fb7a68206a1b |  | note | Attach Material Conformnace Certs, include TB Approval No.
label | 7e433f6e-525b-5b6a-92a2-9e625392a5c6 |  | note | Attach delivery dockets (if applicable)
text | 0da65980-8b39-5cd1-ac59-6d480c0565e3 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 2.6 Bedding Sand
label | 7da71428-837b-5761-bd45-269b5bab3529 |  | note | REFERENCE:
label | d67a3be5-04f7-5c12-bd4f-8527d703d753 |  | note | IFC Drawings
label | 4e787d3a-aff5-5933-a2f3-611a7140a188 |  | note | L1-CHE-SPE-313
label | 1dd76df1-9c0f-5423-bd86-c6614a9c5cf5 |  | note | ---------------------------------
label | a5841c79-993d-5a25-8163-8748818db088 |  | note | ACCEPTANCE CRITERIA:
label | 8fb67725-85ab-5828-ab24-9e997bd961dd |  | note | • Recycled Glass Sand shall be free of any perishable matter
label | bfbb350d-6de4-5085-9000-b1676ca896d2 |  | note | • Bedding material and embedment material shall comply with the following grading requirements:
label | 3b148c46-0553-5628-bc14-eec0924065d2 |  | note | 4.75mm passing 100%
label | 5a3f4c5b-7e30-571a-b0a1-b42c5ad42451 |  | note | 2.36mm passing 75-100%
label | 0133516b-237d-5149-b379-4f12a5bc9c6b |  | note | 0.075mm passing 0-5%
label | 67ba5836-cdbb-5d64-90ad-f1b8b66fd21d |  | note | ---------------------------------
label | c84fc911-e01a-5ac0-8a0a-1e261ac460f0 |  | note | METHOD: Document Review
label | d6982ad0-4a0f-5af9-b5da-3f733e2bb82e |  | note | ---------------------------------
label | d3f6e490-5e29-5a55-a79f-228fd4d848e4 |  | note | FREQUENCY: Each Material Type, Each Delivery
label | d989b824-47fb-5e45-9ad4-c871f45b43a8 |  | note | ---------------------------------
label | 0ab1f44b-624e-57f0-b477-cfaef3f8b5ea |  | note | CATEGORY: IP
label | b04e0233-465c-5333-9dd7-a727030bd051 |  | note | ---------------------------------
label | a6a2349f-f907-5257-9efb-0bc0adaa6006 |  | note | RESPONSIBILITY: SE/PE
label | d79ecb9f-ea0c-5ee3-b481-165f3f00495c |  | note | ---------------------------------
label | ec226a2d-6d4e-53c4-bb1f-b569b0ae4887 |  | note | VERIFYING DOCUMENTS:
label | 68d56421-39ea-522a-bd4b-7c67110cbe75 |  | note | Attach Material Conformnace Certs, include TB Approval No.
label | c4500129-608b-5f03-a212-5891d92df0c8 |  | note | Attach delivery dockets
text | 8a2545b8-d09b-5c5e-8938-8fb7aec74f5e |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 2.7 Draw String
label | 62316771-d111-517d-a239-8100ae90e581 |  | note | REFERENCE:
label | 62195fa0-f41d-5d02-b396-6013661914ef |  | note | IFC Drawings
label | 4c557bc7-d6e9-52eb-8170-86148dc41832 |  | note | L1-CHE-STD-043
label | 0eb575cb-c5ba-5300-9722-a0e79a9f9514 |  | note | ---------------------------------
label | 3ac33559-cc2e-542a-aa7d-b8511dcb3386 |  | note | ACCEPTANCE CRITERIA: 6 mm diameter polypropylene blue/yellow
label | d0884ccb-f866-5520-933d-a20debd8ef32 |  | note | ---------------------------------
label | b4528542-249a-59fb-8ca6-b78b61278a87 |  | note | METHOD: Document Review
label | 3a7563ab-c157-57b0-b3f2-1faf79167672 |  | note | ---------------------------------
label | 848e59a1-0bc6-5986-8852-9a549fcb09c6 |  | note | FREQUENCY: Each Material Type, Each Delivery
label | 93b503e3-5807-51db-91d0-d466af4cb78e |  | note | ---------------------------------
label | 2c0700bd-f442-51ce-93c8-c1ac9a99285e |  | note | CATEGORY: IP
label | 467a4688-1cba-5bb6-98c6-447fdbcf3675 |  | note | ---------------------------------
label | 3d8ee86e-473e-522a-bf64-5ccaeb1e1566 |  | note | RESPONSIBILITY: SE/PE
label | 52761bb0-692b-53b3-983a-055dc0368311 |  | note | ---------------------------------
label | 95ce23d8-602f-5482-af0f-36febbc649ba |  | note | VERIFYING DOCUMENTS:
label | 0a1c78d7-ef25-5dfd-adc7-eb30db1ee5d3 |  | note | Attach Material Conformnace Certs, include TB Approval No.
label | e9a7cb62-1225-5ee9-88b9-0958f64322b4 |  | note | Attach delivery dockets
text | 68ba1ec1-f067-5aab-b569-2fdcfecbb8e4 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 2.8 Markers and Marker Posts
label | e605ce09-81e4-52d0-a204-d6c8a8a44ffd |  | note | REFERENCE:
label | 711c6409-3ae3-5c29-9aa2-b19e19e87ee0 |  | note | L1-CHE-STD-043 13.2
label | b9329ba1-2096-51ca-854d-f7a50f7c1d0c |  | note | AS 4799
label | 238fd729-2340-5742-9718-fc34e304cefa |  | note | ---------------------------------
label | eb65e49e-a034-504f-ba31-0f3b12a06774 |  | note | ACCEPTANCE CRITERIA: Markers and Marker Posts are to be manufactured in accordance with AS4799.
label | 2bd4db00-64c6-5102-b8e3-08ca9a15b43b |  | note | ---------------------------------
label | e1f31c35-a5b8-53d9-b0c9-b06389055b72 |  | note | METHOD: Document Review
label | fe32ec1e-a3bd-515f-995f-162d847e643f |  | note | ---------------------------------
label | ec0a976f-e6eb-5f40-a685-b3b236fc7af5 |  | note | FREQUENCY: Each Material Type, Each Delivery
label | 68d1a97b-c9a6-514a-9cf4-8f0f42b881de |  | note | ---------------------------------
label | 7995bc0b-dbd9-5e56-b684-3e1446187c2a |  | note | CATEGORY: IP
label | 4b8bd95f-1cd1-526c-be21-0cab09654bc5 |  | note | ---------------------------------
label | 83373d6a-8f40-5859-8786-7e0c9c31ee5f |  | note | RESPONSIBILITY: SE/PE
label | 445d8569-a71c-50ed-9365-5690e3aeccd3 |  | note | ---------------------------------
label | 0ef611c4-7935-5107-8f81-4dd25c181c66 |  | note | VERIFYING DOCUMENTS:
label | 0f9d709a-141b-5157-8641-73c5695ca12f |  | note | Attach Material Conformnace Certs, include TB Approval No.
label | 73229cdf-0a05-5a0a-8e64-9d4dddd912c0 |  | note | Attach delivery dockets
text | a849f194-a044-5df0-892d-d6f6de1616d5 |  | textbox | Date Completed:
checkpoint-group |  |  | section | Preliminaries-Procedures
checkpoint-group |  |  | section | Pre-construction
checkpoint-status |  |  | checkpoint | 4.1 Survey Set-out
label | 06f68b60-3771-5bc4-af5b-937b2c71f861 |  | note | REFERENCE: IFC Drawings
label | e0aeb3fc-390d-5319-bc26-eb702f28fe79 |  | note | ---------------------------------
label | a52e8b70-167a-5ecb-bc4c-95896c8b2c2f |  | note | ACCEPTANCE CRITERIA: Survey to set out trench alignment and pits, and establish construction control (alignment and level).
label | ff9bc54a-afaa-533a-afa9-cd41b31f936f |  | note | ---------------------------------
label | 7484a3c0-2d02-5504-976e-c84099794196 |  | note | METHOD: Measure, Visual
label | 116c97c4-1d48-50f2-a01f-9a9b57a8f8d3 |  | note | ---------------------------------
label | e0197d6f-6d3f-505f-b871-5499b2157419 |  | note | FREQUENCY: Each element
label | c23c9a0f-05fb-5f4a-ab7a-e957379d37ce |  | note | ---------------------------------
label | 9d9b8f00-5abd-538c-9a64-9ca3a5b3501e |  | note | CATEGORY: IP
label | cf34b04d-b6b1-5a45-8707-66ba90c175c1 |  | note | ---------------------------------
label | 4969e812-3ce0-548a-8d37-4062bbaedfa5 |  | note | RESPONSIBILITY: Surveyor, SE/Site Supervisor
label | bce4d969-e8ea-527a-9166-8f71c40bb421 |  | note | ---------------------------------
label | 85954051-6ee0-5ac5-9920-de16c2220a84 |  | note | VERIFYING DOCUMENTS: This ITP
text | 5b16e36a-3145-5fce-a8a5-0f6e82b8f91e |  | textbox | Date Completed:
checkpoint-group |  |  | section | Construction
checkpoint-status |  |  | checkpoint | 5.1 Trench Excavation
label | abf0684a-a6ae-5de0-9650-5db6da13934d |  | note | REFERENCE:
label | 5f704c55-69fb-59c4-b946-ba73613568d0 |  | note | IFC Drawings
label | f7161ea1-cd2d-55aa-9fbc-8215f1cdafb2 |  | note | L1-CHE-STD-043
label | 4f69e87d-61a3-570e-bd0a-63525e979bda |  | note | ---------------------------------
label | ffa29e0d-f66a-5070-8519-23c9bef6f3b8 |  | note | ACCEPTANCE CRITERIA:
label | 7d563da8-6a23-5a00-9b56-99448b787f10 |  | note | Trench profile and depth as per IFC drawings.
label | 692616c9-2dfa-5c99-8afb-f8737472dc99 |  | note | The width of the trench shall be not less than 200 mm (chain or bucket excavation) or 300 mm (backhoe and other).
label | 92330e20-d6cd-5822-80b5-f3de7b3b3d4e |  | note | The floor of the trench shall be level and free from all loose sharp objects; such as stones or rock of any type, or size, or rail ballast.
label | c0e6f3b5-0070-51fd-8eb9-1c68623bbccb |  | note | ---------------------------------
label | a4847ad8-a464-5523-a088-218df4067a1b |  | note | METHOD: Measure, Visual
label | 6c6c635d-50d7-5389-8554-552f96124ab8 |  | note | ---------------------------------
label | d8a06271-513d-5321-ab28-6bc369098aa7 |  | note | FREQUENCY: Each lot
label | e848d48a-4d07-5936-8e9f-09313c753d91 |  | note | ---------------------------------
label | 65188492-cd61-5d53-91c7-c059feb371cb |  | note | RESPONSIBILITY: SE/Site Supervisor
label | 95e703a0-e9fc-5ffa-844b-04ea252a080d |  | note | ---------------------------------
label | 60e3b842-42da-5cb7-971b-07d0f23721bc |  | note | VERIFYING DOCUMENTS: Sign ITP
text | 226772e8-30bf-54a6-bc9b-a8d8c40c4ced |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.2 Trench Stability
label | d7a00b18-a3c0-5e83-be8f-16300ec12764 |  | note | REFERENCE:
label | 688aa16e-4f27-56c4-95bf-c2ad48695967 |  | note | L1-CHE-SPE-070
label | 8480fa36-e475-50ac-ba54-0fd6a47c1cea |  | note | L1-CHE-STD-043
label | 76030813-cbdb-5fe0-9910-b74ea55076e8 |  | note | L1-CHE-STD-070
label | e8269ead-d349-5491-ae6d-7401bb05d3d6 |  | note | IFC Drawings
label | 8da17f0f-5d46-577b-8ad2-c7c8c7b87ba9 |  | note | MRPA standards
label | d603c5d9-72ef-5ca4-a1b5-fef736485928 |  | note | ---------------------------------
label | 5e3146ac-52de-5094-967e-79b0b5925208 |  | note | ACCEPTANCE CRITERIA:
label | aff49d7d-69e1-55fe-88c9-61ff3663e3d6 |  | note | Trench stability check:
label | 1a346432-87fe-5e4e-9f26-be525cdc1362 |  | note | – Shoring,
label | 8715a2f4-3885-598a-8437-b76d7ec48859 |  | note | – benching
label | 300eec64-38c0-5b27-8403-a46d2589af61 |  | note | – geotech signoff
label | b8c441cc-b004-5fb0-8801-6f5d4f1709d6 |  | note | ---------------------------------
label | 0d29295e-e21e-5d64-bc3f-2c8e235b7446 |  | note | METHOD: Visual, Document Review
label | 5422e6e9-fc9c-5128-b033-6ec827a9c7a2 |  | note | ---------------------------------
label | e7964096-a528-5833-a9ca-5f9e842ec8d9 |  | note | FREQUENCY: Each lot
label | 759e1232-ae97-56a4-914b-3493dfd1ab64 |  | note | ---------------------------------
label | 8f348d03-a637-5d64-8fe5-8c2f65e7c88c |  | note | CATEGORY: IP
label | 1a39db78-83a0-5915-bb33-5adc6cafad30 |  | note | ---------------------------------
label | 93da1aa2-8248-5be3-810c-ea83b04e710e |  | note | RESPONSIBILITY: SE/Site Supervisor
label | ae7bca71-465c-55cd-b03b-1269a2373f01 |  | note | ---------------------------------
label | d147143c-0b28-5152-8be2-81bc8bdac88b |  | note | VERIFYING DOCUMENTS: Sign ITP
text | b6dcb368-7230-5831-a849-e62c986472ae |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.3 Conduit-Bedding Sand
label | cf2b6b15-f6bd-5d2a-b3de-058134edf203 |  | note | REFERENCE:
label | b634d083-9662-5a0f-b78b-48dc838b5cd5 |  | note | IFC Drawings
label | 1ff8437d-9064-504d-a7d8-fb75813c6e3d |  | note | L1-CHE-STD-043
label | eddf0766-01f0-57c9-bc30-2b70409c9077 |  | note | ---------------------------------
label | 9fd422a9-c208-571c-a697-96ae08c821dc |  | note | ACCEPTANCE CRITERIA:
label | 11469c94-07ce-57d5-bef7-f5c2c99cc385 |  | note | 50mm bedding sand to be placed at base of trench in accordance with IFC drawings
label | 0620345a-1c6b-5d95-9e4b-397280b08f11 |  | note | In areas where rock is encountered, the cables shall be laid on a clean bed of sand 100 mm thick
label | 04fe0384-1557-5aa5-b4d2-71dc1452a60b |  | note | ---------------------------------
label | 3da0d8d3-8302-5e9c-9fd9-961f566932c8 |  | note | METHOD: Measure, Visual
label | 727d51c6-7108-5254-85e1-bed19eedcac9 |  | note | ---------------------------------
label | 3c692a17-929f-54f3-ac65-077567bb390b |  | note | FREQUENCY: Each lot
label | 08286d5f-05a5-56d9-bfa0-97e550f1664c |  | note | ---------------------------------
label | 9825b245-9776-5a3f-9a2b-16b344b69e07 |  | note | CATEGORY: IP
label | d464aa5d-2c6c-5035-afe1-9904803265ca |  | note | ---------------------------------
label | 37933f8b-4c8d-5684-841a-245ae5c818e2 |  | note | RESPONSIBILITY: SE/Site Supervisor
label | 246d259d-f75f-53d6-a806-20faa06aee0c |  | note | ---------------------------------
label | d47c0cbb-c854-51db-9bc5-cce94d9c65a2 |  | note | VERIFYING DOCUMENTS: Sign ITP
text | ff45ae51-2360-51e2-9a72-723857307539 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.4 Conduit-Configuration
label | b4cd4b47-e276-5edb-85fc-ecb76075ace8 |  | note | REFERENCE:
label | 1e9f751f-ac13-5d14-afad-40e65cfa4b19 |  | note | IFC Drawings
label | 12050097-ee97-5276-abae-b638f0a287c2 |  | note | L1-CHE-STD-043
label | 4975c10b-07a5-5c25-b8eb-6bf3a291c6a5 |  | note | ---------------------------------
label | 281ca41a-ae20-51f3-bda2-def1b9d494f4 |  | note | ACCEPTANCE CRITERIA:
label | 78df08b1-6ad2-53b2-aef1-7645321e8f7e |  | note | Conduits are configured in accordance with IFC drawings and meet cable separation requirements.
label | ecfdfdf2-1477-5735-b492-02fc02cd4b86 |  | note | Min Cover
label | ec0b3e71-dab2-530b-88f4-747831df89ae |  | note | – Natural Ground: 800mm
label | e8a42497-84f9-5c77-bf23-314d31aa1e0f |  | note | – Under Road: 1200mm
label | 87b1b8a4-58dd-591b-8256-23e2782a53d2 |  | note | ---------------------------------
label | c96cc1d2-5761-5e4a-99a6-0ae1056c1f52 |  | note | METHOD: Measure, Visual
label | b4c0195e-3bc9-5587-8033-bbc8bdc61f94 |  | note | ---------------------------------
label | 8aca18a1-3eee-5dc1-bf32-391f42d348de |  | note | FREQUENCY: Each lot
label | 49c88edf-0cb2-5d72-ba1c-fb9634f04e2a |  | note | ---------------------------------
label | b4335057-e6c6-5160-98e3-3f3d78371aa8 |  | note | CATEGORY: IP
label | e8bd8dce-f9ee-5a04-b156-ee8f085ac23a |  | note | ---------------------------------
label | 22f2088f-5440-5063-b8f5-3a8f459dcf25 |  | note | RESPONSIBILITY: SE/Site Supervisor
label | 4a1e6c9e-5453-5d3e-8aa4-8d9fb590d88a |  | note | ---------------------------------
label | 64622c39-a841-5731-b192-dddb25c67e4e |  | note | VERIFYING DOCUMENTS: Sign ITP
text | 93f02c49-934f-5813-9933-2067599ab70e |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.5 Conduit-Separation of Services
label | ea206090-e14d-5745-9b90-856c85cc0a7a |  | note | REFERENCE:
label | 261afc55-cbcc-5635-a372-ae82d42de17e |  | note | IFC Drawings
label | 57c41735-5ea2-5940-bb53-7b9c91bbbb3b |  | note | TS-SP-013
label | 179b690f-157b-5ea4-bead-a7e5644c1c59 |  | note | L1-CHE-STD-043
label | aad012e0-8b28-50ac-a2f4-0b0ef4bbb92a |  | note | ---------------------------------
label | 1a590a8b-0156-5594-b517-18eb8e106632 |  | note | ACCEPTANCE CRITERIA:
label | ff4f208d-8e57-5149-adaa-4ef11bc8f3a9 |  | note | Separation of services
label | 33dfd4a9-601a-5421-b067-f81befd7e1ca |  | note | – HV: Min. seperation distance between HV conduits at least 50mm
label | f238ca11-4457-57b8-9854-87e9a40aa6eb |  | note | – VicTrack: 100mm from HV
label | 6a9ad61b-56db-5e70-9518-8035fbf29543 |  | note | – Utility: 300mm to utilities
label | a07e4341-2844-5c69-a88a-6d6550dd5afd |  | note | ---------------------------------
label | c1743fa5-6eb5-564c-90dc-81bb3f54b011 |  | note | METHOD: Measure, Visual
label | f7764138-ca03-5741-a4ec-81d837d01292 |  | note | ---------------------------------
label | a16b683f-114e-5c45-b935-f078df941f40 |  | note | FREQUENCY: Each lot
label | add440a5-93e7-5822-8f44-8304ca8814da |  | note | ---------------------------------
label | 2a9290b8-ff55-53b8-9522-03077780d23e |  | note | CATEGORY: IP
label | 531af432-2b39-5ac7-9092-ea5731a80a7d |  | note | ---------------------------------
label | 464c931b-0392-5302-a0fd-a33a307fe07f |  | note | RESPONSIBILITY: SE/Site Supervisor
label | 43b603ba-930c-565e-a35b-80af0ec5d1c8 |  | note | ---------------------------------
label | b8b35e5b-d976-5141-900f-4916300a6301 |  | note | VERIFYING DOCUMENTS: Sign ITP
text | fc037328-b131-5937-b322-5a2f8443a4ad |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.6 Conduit-Joints
label | 18ab26f9-1948-5509-bb71-2ab41064de1e |  | note | REFERENCE:
label | d32d4fd6-05eb-55c9-b25c-5d2a83907488 |  | note | L1-CHE-SPE-070
label | 54eeb862-131a-543d-922f-b4cfa0b1b5c8 |  | note | L1-CHE-STD-043
label | bdde8f06-57f5-53e8-9490-b83321b98c53 |  | note | L1-CHE-STD-070
label | 4560bd08-d7bf-5a9c-8111-8ef590f33da1 |  | note | IFC Drawings
label | e878650f-bdab-51e7-b4f7-4faf6b66a8b6 |  | note | ---------------------------------
label | efcaa11f-9cc1-5a45-a4ee-4a97f0c959fc |  | note | ACCEPTANCE CRITERIA:
label | 47327ba9-abc1-5523-9ea7-37b243ac7af1 |  | note | All conduit joints shall be made by utilising the spigot and socket ends.
label | 91dd5dcc-a228-525d-98c6-a500aeb7a5d5 |  | note | Ends to be joined shall be thoroughly cleaned using a solvent approved by the conduit manufacturer.
label | 75e8db83-b4cd-5145-83f6-34a5be7e5b2f |  | note | The joint shall be impervious to water and shall be glued with an adhesive approved by the conduit manufacturer.
label | c903aa47-a824-5007-808a-9cc3909f8629 |  | note | Socket ends to be placed firmly into the spigots then hit with a mallet to ensure a sound connection
label | eeb8beb1-5ffa-5a2d-9c2f-97cde8a28a37 |  | note | ---------------------------------
label | 670ea1b3-ebe7-5d6f-883a-2393ff554f53 |  | note | METHOD: Visual
label | d299352b-b97d-5e22-8f28-7aeda4ef2226 |  | note | ---------------------------------
label | c8dad3cc-e76d-556f-ba8d-3afb07812bc0 |  | note | FREQUENCY: Each Joint in each trench
label | 90c9334b-4719-5d32-8ba9-fdfbe981e355 |  | note | ---------------------------------
label | 0c25b74f-2bf5-533a-94b3-09146697115d |  | note | CATEGORY: IP
label | 2ccc600f-7a55-5836-903b-61070d0c7f1f |  | note | ---------------------------------
label | dae017fe-ee80-5e55-bc4d-6d341aadefab |  | note | RESPONSIBILITY: SE/Site Supervisor
label | e1d23bd6-e7bc-5988-bb50-a8d70e2e8823 |  | note | ---------------------------------
label | 1b8456c2-7510-5787-8f6f-705d66014256 |  | note | VERIFYING DOCUMENTS: Sign ITP
text | d9142768-86b5-5dce-ab2a-62317c4add93 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.7 Conduit-As Built Pick Up
label | 41b024ba-3db1-5b38-a0a1-58e7b23a6f91 |  | note | REFERENCE:
label | d52aa1a7-11e1-5fe4-acd8-4527a7679d4c |  | note | IFC Drawings
label | 05d7e3fc-ce18-5017-85b8-cfc02e60fcfd |  | note | L1-CHE-STD-043
label | b35d9a0d-dbc6-5a3f-a8b2-3e4cde281e7d |  | note | ---------------------------------
label | b8186c16-440e-5a29-9026-aff17afd8ca2 |  | note | ACCEPTANCE CRITERIA:
label | de66e833-8abb-5415-8423-8a49e59d16a2 |  | note | GPS co-ordinates to an accuracy of ± 0.5 m shall be recorded every ten metres for the entire length of the cable route / trench, and at all changes of direction.
label | d6c4444a-1ede-5131-a7d6-dcb52789f451 |  | note | This method shall also be utilised to capture all;
label | 73aeb6b9-e528-54ec-be2b-0abf90546f73 |  | note | i. Cable joint locations.
label | db31078f-2120-58d3-84a5-04a213cb21a8 |  | note | ii. Cable pit locations.
label | 746ba369-f704-5ce4-a9b0-d513d04415e6 |  | note | iii. Under line crossings
label | cfd072e8-a967-55fd-b87b-c7ab2836547f |  | note | iv. Under road crossings
label | 4a782ea7-7d66-5abb-afc8-4a8ebea3acf9 |  | note | v. Other significant points of the cable route
label | 0d2ee097-ef27-5ba9-a663-d24b42584402 |  | note | ---------------------------------
label | 0e46f47b-25de-5f3c-af82-ba0aceaaf23b |  | note | METHOD: Measure
label | 97db20ae-bf19-5b6c-a2a9-232784c59c69 |  | note | ---------------------------------
label | c4113f93-e06f-54a4-80a3-f582d4c9b166 |  | note | FREQUENCY: Every 10m
label | 83b9bc32-301e-51d7-991c-38bda7f24b3a |  | note | ---------------------------------
label | e17584ef-9030-535f-a2d3-ca747d41eda9 |  | note | CATEGORY: WP
label | c18a924a-a58f-5139-a9c5-3dfa7d6775d1 |  | note | ---------------------------------
label | a222d086-36a9-5580-b240-0ff7f11a3dcd |  | note | RESPONSIBILITY: SE/Site Supervisor
label | 0a122641-408a-51ac-a6fa-0a42fe8d2076 |  | note | ---------------------------------
label | 712cb3c1-4142-5f56-99fd-73bcb6e55fb4 |  | note | VERIFYING DOCUMENTS: Sign ITP
text | 479f6f26-2525-5937-8685-27579cef359b |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.8 Conduit-Bedding Sand Installation
label | a5ecba00-6076-54e7-a966-d53e2745512f |  | note | REFERENCE:
label | 5a860324-69f1-516e-9689-933c07cfb88e |  | note | IFC Drawings
label | feac06ca-d86a-507f-8e5d-79334f1a8540 |  | note | L1-CHE-STD-043
label | 3e7b36a9-21e0-542e-80c6-1756c5415d1c |  | note | ---------------------------------
label | badc9c44-2a6d-52ee-a7e7-ed52da07671d |  | note | ACCEPTANCE CRITERIA:
label | 91af2717-813b-5835-a890-dfd758802a6b |  | note | Bedding sand extends 50mm past edge of conduits.
label | 1cb2a618-c2bc-5c5d-8b38-336e8d741d69 |  | note | Bedding sand extends 100mm above conduits.
label | 03b0b93f-8b13-5f85-b7b1-185c16ddb5bd |  | note | ---------------------------------
label | d07b6f02-af0e-563b-b9d8-01dd0323752d |  | note | METHOD: Visual
label | 7112f32d-e385-5d5f-9fd1-b93f1d2c033e |  | note | ---------------------------------
label | f36c44fc-758b-556e-b86c-326c2fcfd1ce |  | note | FREQUENCY: Each lot
label | d3156323-4283-5abe-a2c3-b5aef3842eff |  | note | ---------------------------------
label | 342a9b99-9471-5118-847d-27c698ff0dd7 |  | note | CATEGORY: IP
label | b389f3a0-2e6c-5c90-92c0-7c9bcc08727e |  | note | ---------------------------------
label | ee910d60-3f45-522f-bac4-7acd7054b6fc |  | note | RESPONSIBILITY: SE/Site Supervisor
label | 3bed6293-3378-5b58-bd07-6a9ef37dafe4 |  | note | ---------------------------------
label | 484d3571-26a7-54b7-8066-2d7410d8f416 |  | note | VERIFYING DOCUMENTS:
label | edc1e544-033b-5dd0-bb57-62f2920f3ebf |  | note | Sign ITP
label | 4cc9b037-8c25-5941-93b2-064c3e841faa |  | note | Attach Delivery Dockets
text | fe0ef891-b01d-5cd5-92cf-2b5a0871e23c |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.9 Conduit-Protective Cover
label | 73311859-1540-5bc8-a7c9-d6692521e149 |  | note | REFERENCE:
label | d21c26e9-74ba-51ca-967d-fdec85fd8389 |  | note | IFC Drawings
label | 30b862d7-fd1b-5df6-8364-0e05ecad348b |  | note | L1-CHE-STD-043
label | 7edc8764-c30d-583f-a150-028c35b39c7c |  | note | ---------------------------------
label | bcdace18-0d59-5fad-86d1-5b01816d5dba |  | note | ACCEPTANCE CRITERIA:
label | 16bc11a9-4ce6-5246-aa75-ebc7662b3a3e |  | note | The cover strip shall be placed on top of the cables and overlap the cables by not less than 50 mm on each side
label | 9f069712-ca4e-5116-be2a-b25bd91b5bd8 |  | note | The protective cover shall be no closer than 75 mm above the cable/s
label | a6db99d9-4669-5af6-846b-fbe32800ac2d |  | note | ---------------------------------
label | c35ef9e2-6e7f-56f4-b1eb-c5a196c78141 |  | note | METHOD: Visual
label | 78292c70-90d0-59c7-8f65-fd55c23df731 |  | note | ---------------------------------
label | 1dffe008-9c4b-5c00-a14f-bc996f3d255b |  | note | FREQUENCY: Each lot
label | be72ca41-8387-544f-ade1-d7d2909265d5 |  | note | ---------------------------------
label | 27f04208-1318-539a-800e-53fbe047c6f8 |  | note | CATEGORY: IP
label | 8f4316fc-37dc-5a4d-bc9b-4794ea2deb7a |  | note | ---------------------------------
label | 95fdb6dd-8b3d-58a7-93cb-45b19c7a647f |  | note | RESPONSIBILITY: SE/Site Supervisor
label | 1391ee5f-0155-5cae-a61b-69cea58de81e |  | note | ---------------------------------
label | 3bfda7e2-287f-5822-b6e3-cb830ba280a4 |  | note | VERIFYING DOCUMENTS: Sign ITP
text | bc60f98e-284b-5f37-8bc1-ac727c9cb3ce |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.10 Conduit-Marker Tape
label | 7381eb02-49e4-520c-8fd0-b26db9055f7f |  | note | REFERENCE:
label | c2bf3ac7-ab7c-594f-96f5-f109e7932e91 |  | note | IFC Drawings
label | 7e02cdd9-0398-5944-afa0-5db623058789 |  | note | L1-CHE-STD-043
label | b94ff2ec-1aac-59f5-8fe5-4248f960c653 |  | note | ---------------------------------
label | 81412166-ba8a-55ca-9b59-235f2c899d0c |  | note | ACCEPTANCE CRITERIA: 150mm wide orange coloured PVC "DANGER RAILWAY SIGNALLING CABLES" marker tape shall be installed in all trenches 300 mm below ground level
label | c690abbf-ab12-5914-829b-d95faa19c75c |  | note | ---------------------------------
label | f41986e5-7413-52f1-9ddc-036817609578 |  | note | METHOD: Visual
label | 11d88636-d172-5400-a2b0-bb5c3c8231ae |  | note | ---------------------------------
label | ad0905a6-39ef-5193-97e1-3cfd5391896d |  | note | FREQUENCY: Each lot
label | aec97f61-5918-5dcb-a233-984c580cfbfd |  | note | ---------------------------------
label | aa25033c-e722-5350-9274-5763df478834 |  | note | CATEGORY: IP
label | deff2ded-2a89-5d98-92c2-fe2384bf8112 |  | note | ---------------------------------
label | fabd5efa-1213-5406-8692-5dab1d3b5cd4 |  | note | RESPONSIBILITY: SE/Site Supervisor
label | bfc755c7-c67f-5268-bd1a-492a48e0a829 |  | note | ---------------------------------
label | 07b3a91c-6157-53cc-9256-2c9ba6fbbb46 |  | note | VERIFYING DOCUMENTS: Sign ITP
text | 52987845-b45d-58de-9e63-87090cc0132f |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.11 Conduit-Backfill Installation
label | bb0b0cbb-e0e0-5228-8503-1937362ade6d |  | note | REFERENCE:
label | a45d370c-5d7b-5f4b-810a-b4e889495e97 |  | note | IFC Drawings
label | 4371c914-c424-5f9d-a66f-e653b1b7141b |  | note | L1-CHE-STD-043 clauses 6.15 and 6.16
label | ce02c79d-b3f5-54ea-b854-d66036e1796c |  | note | ---------------------------------
label | 64f9c4c9-b1fd-5183-bb16-59cc6ba2f215 |  | note | ACCEPTANCE CRITERIA:
label | 6b02e706-8e7d-5b7d-b4ab-b706dc83081a |  | note | Backfill per trench profile
label | 2e68b62d-a7b9-5d8f-ae91-a9100462c4b2 |  | note | – 150mm layers
label | 686426f4-3da9-59f8-80ce-b3436a5a7464 |  | note | Backfill material to pass through 30mm sieve and be free of material that could damage conduit.
label | 0c5d10e3-6418-5d33-9d62-c33458b26d28 |  | note | The trench shall be finished with a slight mound, height equal to approximately 25% of trench width, to provide for further settlement.
label | 04750a70-15ff-56d3-acc0-a8e145a4efc1 |  | note | Trenches under road pavement - backfill to be same material as the road formation material.
label | 2cee32b8-c702-5c9e-bcf8-6d49a900e17b |  | note | ---------------------------------
label | 9fe470cc-fd6f-51d5-82cf-5ff37a00f2c9 |  | note | METHOD: Visual
label | 9500e0c5-9760-5b89-a5a0-577d8acc179d |  | note | ---------------------------------
label | 67282431-1eec-509b-8ed6-2d23a0b8c588 |  | note | FREQUENCY: Each lot
label | e82ad2e6-e119-512c-99c4-6513914e6098 |  | note | ---------------------------------
label | 1b653c0e-4073-564e-8aa3-6ae2355ea1a6 |  | note | CATEGORY: IP
label | ad8574c9-dc5e-595f-8133-747f48a05341 |  | note | ---------------------------------
label | c9174c2e-aa58-5563-929a-b071b1074b38 |  | note | RESPONSIBILITY: SE/Site Supervisor/NA/VicTrack Rep
label | 4a48148a-e07e-5e05-8eff-5cab4175a927 |  | note | ---------------------------------
label | fe7454c1-c64b-5192-ae65-34727c333cc2 |  | note | VERIFYING DOCUMENTS:
label | 24e0f884-b8f5-5e5b-9978-17918b3407ab |  | note | Sign ITP
label | d4e86ac3-6611-5a12-97f3-c4cc4af698ca |  | note | Attached Delivery Dockets
text | c5df2e16-1f19-5c30-8048-fc405d204f13 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.12 Conduit-Compaction Testing
label | a8cb80bc-03d2-58c7-9d2b-da778a2f87af |  | note | REFERENCE: L1-CHE-STD-043 clauses 6.16
label | e8d88c48-beb7-5f33-88b9-1a2036bf092c |  | note | ---------------------------------
label | e7efeca5-f167-544a-a835-7b2506cb86f2 |  | note | ACCEPTANCE CRITERIA:
label | 89d90074-5c4a-5f4b-9e42-882e59455b34 |  | note | Compaction to achieve 95% Standard Compaction.
label | f10db769-dd26-5456-88bf-3ea243afed41 |  | note | The tests shall be taken on a frequency of one (1) test per 200 linear metres per layer or one (1) test per area per layer where any area of excavation is less than 200 metres long.
label | ba1e272f-1875-5d13-a4b7-a04c7e747379 |  | note | ---------------------------------
label | f56ecb4e-27cf-5e5d-acc8-dfd9812e718a |  | note | METHOD: Document Review, Visual
label | f7f83ba4-178a-51a6-a41b-7163abb95a0c |  | note | ---------------------------------
label | 56aaf35d-83ff-5841-9346-869dd335e1fa |  | note | FREQUENCY: Each Layer & Every 200m OR Per Area
label | 472e3681-cbe3-5a23-a8ff-8f92306f1737 |  | note | ---------------------------------
label | b5e1371d-3e00-57ff-a615-8ec6b76d43e5 |  | note | CATEGORY: IP
label | 42877131-f3a9-5ab6-9bca-781f9d26edf9 |  | note | ---------------------------------
label | 0d753054-d7c3-58e9-b9eb-408b36f268e4 |  | note | RESPONSIBILITY: SE/PE
label | cf202e91-8eb3-5e12-bd49-d98d29a38e2a |  | note | ---------------------------------
label | 0a25dde7-3e36-5ad2-8e91-5f6300e48db3 |  | note | VERIFYING DOCUMENTS:
label | 122d4f54-e4af-59b7-bbb3-bdc581d50ab9 |  | note | Sign ITP
label | 20cb7c81-f0cf-5363-a038-f8fc66cd4ee3 |  | note | Attached Test Report
text | 8e49f7fc-2999-5639-a3e6-b8b7681c66db |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.13 Pit-Bedding
label | 6e929e59-d5f8-57fd-8009-96f265cc78bc |  | note | REFERENCE:
label | 9658d7d2-9abe-5cd7-8956-24c7785d3124 |  | note | IFC Drawings
label | 6c5f6177-0ffd-5707-b0e9-f9f522e60030 |  | note | L1-CHE-STD-043
label | b7ec8bb4-dc86-56dd-8bfa-644f239615a4 |  | note | ---------------------------------
label | a247260d-f501-5fd7-9b53-f413a0735320 |  | note | ACCEPTANCE CRITERIA:
label | a0984011-0f42-5a55-a1d9-fb15161d0e99 |  | note | All pits and chambers shall have a prepared foundation of “A” grade 20 mm crushed rock not less than 150 mm thick
label | c1d09a7c-d3ed-5f54-a9fd-edec88829dda |  | note | Gravel drainage sumps shall consist of 20 mm aggregate with a minimum depth of 300 mm
label | 50f1e8a2-a827-53f8-b2ff-ccb78b663626 |  | note | ---------------------------------
label | c5d90adc-01b6-54e0-9a3c-55ffe05dd8c5 |  | note | METHOD: Visual
label | f830c23a-a70f-5cf3-8595-6d5e26053574 |  | note | ---------------------------------
label | eed296fd-7fb8-5bc1-937b-bc54bd0f8be4 |  | note | FREQUENCY: Each Pit
label | f7ab3cb6-04e8-55ab-bffb-86b04478febe |  | note | ---------------------------------
label | 90daa935-7e09-5a43-bfcb-dbab224741e2 |  | note | CATEGORY: IP
label | 3f497314-bf57-5bee-b9f8-b9ccd7d05ac4 |  | note | ---------------------------------
label | ab8dcad5-16fc-5308-932b-22fded47d566 |  | note | RESPONSIBILITY: SE/Site Supervisor
label | f9156e77-bc1f-586c-9a23-91e2c8684b0f |  | note | ---------------------------------
label | 461ba30b-ce93-5089-b3e3-ab5fda6214b7 |  | note | VERIFYING DOCUMENTS:
label | f5026022-dc64-5d34-ae2d-00f52690fcee |  | note | Sign ITP
label | a2878826-dd88-56e2-995a-cb8750162fe0 |  | note | Attach Delivery Dockets
text | 5342bf1c-f0df-5dc2-a343-b2d8909b26fb |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.14 Pit-Orientation
label | ce9064b5-109b-526a-971d-c19cc2681482 |  | note | REFERENCE: IFC Drawings
label | 0280642f-737a-5590-9f72-9112da6e206c |  | note | ---------------------------------
label | edded9a4-e520-59f0-9c57-98a14063934b |  | note | ACCEPTANCE CRITERIA: Pit to be parallel to track and parallel to conduit route.
label | b4a077ab-795c-5a26-9eae-bf4fbfb3f34d |  | note | ---------------------------------
label | af57b689-c0d5-58bf-be95-36d643d7bfe9 |  | note | METHOD: Visual
label | e7ca725c-ad30-5223-8996-6314780bb38c |  | note | ---------------------------------
label | 376d7ae2-aada-5425-9e49-d51fbf3e684d |  | note | FREQUENCY: Each Pit
label | 5c1f5e69-cd27-5e3b-9fdf-2f1431886aea |  | note | ---------------------------------
label | d99272a3-3c8e-5447-b8ba-29dbe918d497 |  | note | CATEGORY: IP
label | b747a786-f899-50f1-9377-95eb6c73928f |  | note | ---------------------------------
label | 92647f0f-176c-5b53-882c-599d8d4c11a6 |  | note | RESPONSIBILITY: SE/Site Supervisor
label | 72c54259-ba01-5073-b551-ed1e26075f51 |  | note | ---------------------------------
label | 322c88be-4b7f-5c17-8c3b-ad076bc71b2d |  | note | VERIFYING DOCUMENTS: Sign ITP
text | 51ac27ec-0dcf-565a-95e1-12a1236bd01a |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.15 Fit off-Conduit Entry
label | 8bbbc45b-ee01-51b5-bdaf-403ad7851ccb |  | note | REFERENCE:
label | be03c965-cd2e-5ee0-a058-1831f1c46b4e |  | note | IFC Drawings
label | 01876e0c-f2bb-5e77-908a-1c48a8cfd794 |  | note | L1-CHE-STD-043
label | 7fd62aaa-b2c0-5a48-9819-d5c9a80a25f1 |  | note | ---------------------------------
label | e0e4e69a-06ef-5b38-a7e3-0d4c1cea1312 |  | note | ACCEPTANCE CRITERIA:
label | ed7951ea-c24e-527e-8fe0-cb663b006187 |  | note | Entry holes shall be 100 mm minimum from the base of the pit or chamber.
label | 13b525b1-d879-5f54-a996-ce861ec029d8 |  | note | The end of conduits shall not protrude more than 50 mm into the pit space
label | f6a32e28-d01f-54a9-ba15-8b56c63eed06 |  | note | ---------------------------------
label | 5d75bd9b-de96-5191-8eb5-9dfd648a9aaf |  | note | METHOD: Visual
label | b4d9b324-be1d-5093-9ec8-059adc623451 |  | note | ---------------------------------
label | b3baead0-eb73-5c9f-97b1-98a96aadd1d1 |  | note | FREQUENCY: Each Pit
label | 498abb0c-19bf-5e2f-bbf1-49ef0c667e89 |  | note | ---------------------------------
label | c9bc3126-70db-54b1-9366-8c134c772ec7 |  | note | CATEGORY: IP
label | 30133cde-9dd6-5562-8ca7-6857e6b19159 |  | note | ---------------------------------
label | e48114f6-f5c7-5729-a035-8b8aa8adcb2e |  | note | RESPONSIBILITY: SE/Site Supervisor
label | 7edcbd9c-7e01-5b08-95f6-24f9d2cc1fa8 |  | note | ---------------------------------
label | 92912a63-8eac-57e9-bc1a-bb0883798201 |  | note | VERIFYING DOCUMENTS: Sign ITP
text | c691f231-2c82-5b90-bc0e-ab3ad14a1a75 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.16 Fit off-Spigots
label | 7255ceae-58bc-510f-863b-6a33fd42ebe6 |  | note | REFERENCE:
label | 7ca5bb9c-a102-5c6d-b8c6-941ec52a7d72 |  | note | IFC Drawings
label | de9d0d13-4c66-5231-b0b5-a02972ce97e7 |  | note | L1-CHE-STD-043
label | 18061692-2349-51e7-9095-2a4fb6e4ae5b |  | note | ---------------------------------
label | 7465b800-cb64-516b-bdb7-ebe6a452ba9d |  | note | ACCEPTANCE CRITERIA: Spigot bush to be installed on conduits being cabled
label | 4ae8467f-8654-5d38-95de-4d5adf754b0f |  | note | ---------------------------------
label | 0b69cf1c-a46e-599d-8c18-82d0a639f7e2 |  | note | METHOD: Visual
label | 6c5e3a4d-6db9-56fe-bc2c-3b7b51fe2496 |  | note | ---------------------------------
label | d0895e1f-9d08-5959-9e1a-a3eebd5505b7 |  | note | FREQUENCY: Each Pit
label | 78ed9aa3-dc10-51c6-bf47-88fbe802a22e |  | note | ---------------------------------
label | 219ebfbd-cdcc-5c84-9e45-5867411bb75e |  | note | CATEGORY: IP
label | 9dca2379-59dc-5b58-91ec-10b908e37ba4 |  | note | ---------------------------------
label | 1c0ebab7-24a7-51bd-a32a-50635882420e |  | note | RESPONSIBILITY: SE/Site Supervisor
label | 169b2ebf-6f6e-5a52-bcb2-35d015b123b1 |  | note | ---------------------------------
label | 9d81f594-c5a7-5c98-8bed-d1df32f5d1b9 |  | note | VERIFYING DOCUMENTS: Sign ITP
text | 0979e033-dd93-5f29-b3a8-313b09a94eb2 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.17 Fit off-Draw Ropes
label | 4074d254-e689-5c9c-9f97-b269db15761e |  | note | REFERENCE:
label | a267b033-a555-5d53-b4dd-1fe2b9897fcf |  | note | IFC Drawings
label | ffe70d7b-b6a1-5622-988a-405e7bf888ed |  | note | L1-CHE-STD-043
label | 3e5eef90-bf7f-505f-9a06-3842c33577a6 |  | note | ---------------------------------
label | 65bcfe82-503c-5768-8870-88d59a4bbd3a |  | note | ACCEPTANCE CRITERIA:
label | acce1bb7-df37-5294-82fb-b87c50735d48 |  | note | The draw wire shall be continuous for the complete length of the conduit run.
label | 313bc700-150a-534b-beb0-442d5e5b860a |  | note | The draw wire shall have a minim of 2 metres of slack within each and every pit along the conduit run, and shall be suitably anchored at each end of the conduit run and then sealed with proprietary end caps
label | ffde1b6f-e94c-5299-bf90-8c4c5500fed4 |  | note | ---------------------------------
label | ee0b0ff6-9dad-5764-9326-ba89586743e1 |  | note | METHOD: Visual
label | 874e57a5-0e14-5e7a-9da3-69e524fcb269 |  | note | ---------------------------------
label | 96367e10-6c83-5a08-9837-1aa5f429152c |  | note | FREQUENCY: Each Pit
label | 00190f78-a539-548a-bbf6-5c69803e65b6 |  | note | ---------------------------------
label | 883e55ea-7e8b-54f5-a219-da0b592abf84 |  | note | CATEGORY: IP
label | 99e71e22-eecc-546a-8dc5-c7d4b4b805bc |  | note | ---------------------------------
label | 44c930a8-3509-5152-b8ca-7c2b2cbe76f0 |  | note | RESPONSIBILITY: SE/Site Supervisor
label | edcdb8cf-b135-5030-bbd7-72e0203ae5c9 |  | note | ---------------------------------
label | 883174bd-24a3-5be2-8dac-cedb0445ad96 |  | note | VERIFYING DOCUMENTS: Sign ITP
text | a5cccea6-8f14-5a49-8402-41193885d3a6 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.18 Fit off-Step Irons
label | 71ba9b5f-fbe9-5728-9d92-d494ec994b43 |  | note | REFERENCE:
label | 59e86a22-60b7-5081-b4ac-a5b1f6e8582d |  | note | IFC Drawings
label | 0502276a-32b0-5767-8d91-0074cfd8e74f |  | note | L1-CHE-STD-043
label | 914b795a-58b9-5df8-b2b7-e11841d72fd0 |  | note | ---------------------------------
label | cec29dd4-e699-5327-b5bf-eecdb2dd3c65 |  | note | ACCEPTANCE CRITERIA:
label | e93bc8d7-cda1-5506-81d4-89a7d6e99ff9 |  | note | Unless otherwise noted on IFC drawings, the below is required:
label | 7733028a-e8bd-57b7-8247-4e0eb7fded38 |  | note | All other Pits: Step irons/rungs to be installed if pit is greater than 1.2m in depth (including lid thickness)
label | 24fe9aab-adb7-5973-b61d-8be74326db01 |  | note | ---------------------------------
label | 1f6219f9-7cc6-5208-a98e-80333a0d7477 |  | note | METHOD: Visual
label | 25c3c192-1f64-54f3-aa91-452f0c582486 |  | note | ---------------------------------
label | 346e6e51-4035-5a5c-bcf7-bff81f58b88b |  | note | FREQUENCY: Each Pit
label | e528e64e-f057-591b-b636-cfee0a0bafd0 |  | note | ---------------------------------
label | 2e074583-571f-584d-bc09-bd925efef47f |  | note | CATEGORY: IP
label | 6706d7b3-dbd1-5caa-88c1-2b5fc89c2bd7 |  | note | ---------------------------------
label | f0e39ad9-e689-5ec3-9fbe-a8c05631193a |  | note | RESPONSIBILITY: SE/Site Supervisor
label | 3aa3d424-1548-56e6-85a9-19b0ec7d4675 |  | note | ---------------------------------
label | 896b5897-2e7d-5693-90c0-c5c9c3d5a447 |  | note | VERIFYING DOCUMENTS: Sign ITP
text | e08f2208-5716-52cc-a783-ee811cbaf668 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.19 Fit off-Spare Conduits
label | 078867e8-e406-58df-9958-76fc1b922c48 |  | note | REFERENCE:
label | ca2d57c6-302e-5a42-aed2-4172bff4ff8a |  | note | IFC Drawings
label | 36351984-fc87-5e38-a1b7-0e2e6649c603 |  | note | L1-CHE-STD-043
label | 3012111c-4847-5725-99fa-bdfd25ff60da |  | note | ---------------------------------
label | cf4a0196-40fa-59df-8d7f-3539f285fbf6 |  | note | ACCEPTANCE CRITERIA: Spare conduits to be capped and to be included on survey report.
label | ccd0a270-bf9e-55ce-9549-071d72836b68 |  | note | ---------------------------------
label | 0cb07a3d-a54a-59ef-80cc-77b669db7808 |  | note | METHOD: Visual
label | f2200096-b4c8-5d5f-8a72-19abbd6f0dec |  | note | ---------------------------------
label | beba62ec-0a4b-5883-8f9c-3a139a67a528 |  | note | FREQUENCY: Each Pit
label | 6ede2914-d6cf-5ba0-a129-0682f334d118 |  | note | ---------------------------------
label | dafd858f-3a7a-554a-bd4f-d7e6c9fd764f |  | note | CATEGORY: IP
label | b02df474-2e99-53da-89f6-7838cb5b79c2 |  | note | ---------------------------------
label | a6a20aee-5690-5bdc-a56d-e6294174c92a |  | note | RESPONSIBILITY: SE/Site Supervisor
label | cafef71a-cf2d-5d2a-aab0-fcb8f5a5634b |  | note | ---------------------------------
label | 54fe0f62-cf52-5942-bf4a-649567794564 |  | note | VERIFYING DOCUMENTS: Sign ITP
text | 4676cacf-b9b8-56b5-b1e1-4bea550a75dd |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.20 Fit off-Pit Lables
label | bc774510-1e67-54f3-b0d8-6ed72694a0c0 |  | note | REFERENCE:
label | 43d45625-90e5-558b-8045-585aa41a0d64 |  | note | IFC Drawings
label | 0fde9cc3-a34c-5cbf-b986-ce3ea4800701 |  | note | L1-CHE-STD-043
label | f333f995-75c3-5fce-8b68-4a848ef6aa9a |  | note | ---------------------------------
label | e6c08311-c982-5f2d-8540-ec612694923d |  | note | ACCEPTANCE CRITERIA:
label | acac89bf-5341-5775-a85c-d4fdfd21d5b3 |  | note | Pit labels Brass Label (30mm x 150mm)
label | 5b925bb5-848f-5e3d-90f4-63cf6837146f |  | note | – Signalling: Railway Signals & Comms
label | 0f6a2a96-70fa-58b2-89be-1b470d8745c4 |  | note | ---------------------------------
label | 29c95b21-ecdb-572f-85fe-68ed656dc03d |  | note | METHOD: Visual
label | 74bc9ef6-3716-5590-89c8-2ea741a836fa |  | note | ---------------------------------
label | 147fc2b8-86be-543d-b95c-aff0c5ede740 |  | note | FREQUENCY: Each Pit Lid
label | 3d4de1a2-7265-5454-9d07-4346fe6be89a |  | note | ---------------------------------
label | 72956e06-dbf0-5da9-9191-1acb57adb6b6 |  | note | CATEGORY: IP
label | 7e7665bb-ed2a-5f40-91de-aab10d68f173 |  | note | ---------------------------------
label | 254a1fd4-4279-5046-8891-2d8807393326 |  | note | RESPONSIBILITY: SE/Site Supervisor
label | 47d1416b-47cc-59cf-bbe7-665d709a1f5f |  | note | ---------------------------------
label | b6e74064-69d9-528b-b4b5-34eaa31e81e7 |  | note | VERIFYING DOCUMENTS: Sign ITP
text | 3572ee51-69e6-5473-991e-15410fe046e9 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.21 Protection and Labeling-Non Trafficable Pits
label | 74537bfe-bd02-5bba-914c-7cfe29834105 |  | note | REFERENCE:
label | 62993115-efe1-52b4-884b-208ff14853cc |  | note | L1-CHE-SPE-070
label | 2a9b9f59-b72f-5933-afba-6d5df565d237 |  | note | L1-CHE-STD-043
label | 5af97cbe-e89b-504e-9741-a03758e4e817 |  | note | L1-CHE-STD-070
label | 8f45259f-a956-5688-910b-5fa255b21517 |  | note | IFC Drawings
label | 80d97669-bbc3-59b4-8a76-78cca8d8316d |  | note | ---------------------------------
label | 80ca2703-6fe0-50d8-ac84-61f6f3fddea4 |  | note | ACCEPTANCE CRITERIA: Non trafficable pit lids to be 50mm above FSL and to have 2 x white bollardes installed at the corners of the pit.
label | 9be96390-54e6-5ada-af24-845c3b616ff5 |  | note | ---------------------------------
label | 60d0b6e3-52b8-53c8-8856-58b34fe67520 |  | note | METHOD: Visual
label | 30957d99-bfb8-586b-83d5-5f75de10d8db |  | note | ---------------------------------
label | 8069d1ad-5c98-5b2b-8c22-88fb3a42aac1 |  | note | FREQUENCY: Each Pit
label | faa20b86-4678-59cb-970a-f3f18672dfbe |  | note | ---------------------------------
label | 41622397-f593-5531-a5e4-5e9c6f20d3a8 |  | note | CATEGORY: IP
label | c007c3c0-a2dc-5720-beaa-3079c8240c6d |  | note | ---------------------------------
label | bc24713f-81f0-5a8b-ac6d-3ab41f8fe19d |  | note | RESPONSIBILITY: SE/Site Supervisor
label | 0cc72b46-e253-5361-9030-a5a2b77a93b9 |  | note | ---------------------------------
label | 4b4ed166-f883-5107-8165-adc02a622cec |  | note | VERIFYING DOCUMENTS: Sign ITP
text | 668f537a-d632-5571-99fa-17ee060b9eec |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.22 Protectipon and Labeling-Cable Route Markers
label | 308e2b03-accf-5b8b-99fe-795ee5b8f94b |  | note | REFERENCE:
label | 71ddb68d-0bbf-507a-9372-31e8e6e10421 |  | note | IFC Drawings
label | 263dc0c4-3340-5102-b4b7-03feda6be638 |  | note | L1-CHE-STD-043
label | 5125832e-671f-52b8-9944-1a59ee3a024f |  | note | ---------------------------------
label | d2671f01-a9c3-543a-8cb3-275d72a32c22 |  | note | ACCEPTANCE CRITERIA:
label | 93e0618f-1dcc-5318-b825-d5cb96309d37 |  | note | Cable Route Markers
label | 853b8425-02f4-5ace-82ec-587108155c15 |  | note | – points entering & leaving the rail corridor
label | f0cefdb1-d911-5ec2-8187-9552e0e10cbd |  | note | – no greater than 100m spacing
label | e649b8ac-32f1-5444-8b00-537df1320ddd |  | note | – Change of direction (more than 5 degrees)
label | 1ed495c9-9aef-5e93-8678-70e05391a4e5 |  | note | – White posts with marker plates for conduit runs
label | e395cb99-6144-5cb0-ad96-650b76ddbd25 |  | note | ---------------------------------
label | 81b77381-6629-53a2-a893-247fe79b5664 |  | note | METHOD: Visual
label | 0985cebe-1def-512f-92ae-bc730a988dce |  | note | ---------------------------------
label | ea701261-9498-5bcb-93f9-b8ec2b725d7c |  | note | FREQUENCY: Per Cable Route
label | 65386ae2-883d-5221-94ed-26a22132499a |  | note | ---------------------------------
label | b63d58ed-e8f9-5671-8046-e9bbe93cce42 |  | note | CATEGORY: IP
label | b8bb3e47-c43b-549f-95cd-60e092049be6 |  | note | ---------------------------------
label | d5196054-fc1f-509b-aec6-f643489da1e4 |  | note | RESPONSIBILITY: SE/Site Supervisor
label | 4afeefd4-9674-5fe1-bb0c-049d2fdcda6f |  | note | ---------------------------------
label | ce5bead0-63ef-5a2e-b157-2b592800aea3 |  | note | VERIFYING DOCUMENTS: Sign ITP
text | 47978279-2b2f-5cf0-9978-383fda0bf60c |  | textbox | Date Completed:
checkpoint-group |  |  | section | Post Construction
checkpoint-status |  |  | checkpoint | 6.1 As-built Survey file
label | be9a9767-598f-55d9-b62e-6fe4bc49af73 |  | note | REFERENCE: L1-CHE-SPE-070 Section 13.1
label | 4c3cb599-54f9-536c-810b-04b59256021f |  | note | ---------------------------------
label | 0634eec1-8e0f-5718-818d-c6194eddf328 |  | note | ACCEPTANCE CRITERIA:
label | fa412b32-6ae3-56b9-8672-a431c7966709 |  | note | Survey report to include but not limited to:
label | c6d93540-80df-5318-87c4-1dc0575d9b7a |  | note | – Cable joint locations.
label | 22a94382-c2bf-57c5-ab67-7f8e174a0a82 |  | note | – Cable pit locations (Corners)
label | 51555784-b70a-504c-b4f3-31ca27971cad |  | note | – Pit dimensions & pit lid type
label | 9b139d67-d045-5d21-b3fe-b68903028092 |  | note | – Under line crossings
label | fcc9aa93-72bc-5a56-bcf0-900290fc1301 |  | note | – Under road crossings
label | 4b7fbdf4-329d-5c02-87d3-52619c849d85 |  | note | – Changes of direction
label | a3bad155-2a72-534a-b18c-0d3fa88cebdc |  | note | – Spare Conduits
label | 1152deeb-150c-5e5c-8b8f-9b2268ba5ce8 |  | note | – Conduits labelled as per trench profile
label | 64122a68-b1ab-5368-8574-bc8936dae21d |  | note | – every 10m
label | 84ead3a6-4aba-52c1-9bdc-1e7c25b039cc |  | note | – Other significant points of the cable route
label | 2780a2b3-e530-5280-94ad-911919a1acf1 |  | note | ---------------------------------
label | bc507128-316e-5aa5-bfb2-32b52cc45927 |  | note | METHOD: Document Review
label | 36cd25a4-0407-5016-9866-c1318046e926 |  | note | ---------------------------------
label | 9be53b44-5938-5aab-bade-3935dce84b37 |  | note | FREQUENCY: Each Design Pack
label | 392a4c1d-e173-5d3f-a1f9-4886fc476b6d |  | note | ---------------------------------
label | 767d69b5-3bc4-546f-ac43-e656d10d6f52 |  | note | CATEGORY: IP
label | 085c3445-3fbc-58d6-9298-e04b24cf2bae |  | note | ---------------------------------
label | 17a465e6-40d2-5452-83a8-4b71d1e2dc16 |  | note | RESPONSIBILITY: SE/PE
label | f73a314d-2b88-581a-8158-45652fcc659b |  | note | ---------------------------------
label | 94e495fa-034e-5cfa-ac91-f8d311a3c2b8 |  | note | VERIFYING DOCUMENTS:
label | c99b6b47-0d0a-5b74-96d8-449bd06092eb |  | note | Sign ITP
label | 673290c6-8e14-5da2-9d73-2be4cc96f757 |  | note | Attached Survey Report
text | d54036ab-a595-53f7-be54-fd9296cb7114 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 6.2 Engineering Redline mark-up
label | b79d37da-091a-584a-a128-6e49f2c91217 |  | note | REFERENCE: IFC Drawings
label | 512fb310-5067-5523-afd0-0ac0fcfbca38 |  | note | ---------------------------------
label | a0d1852f-3170-5af7-adc9-59d98c119b64 |  | note | ACCEPTANCE CRITERIA: As constructed cable plans shall be provided for the entire cable installation and in accordance with AS 4799 and the PTV Infrastructure Drafting Standard.
label | c53c31a8-c877-582d-aa93-0f840a6b3381 |  | note | ---------------------------------
label | 9ea9210d-c8aa-5c37-b580-61cbf07995e9 |  | note | METHOD: Document Review
label | b46c4cad-47c5-513b-8c1d-8dad62bdd0d2 |  | note | ---------------------------------
label | c198fee0-003a-54df-bfa9-99c78deccb7e |  | note | FREQUENCY: Each Design Pack
label | 48ebbd47-f19b-5dbe-b88d-b12b323a208d |  | note | ---------------------------------
label | a508def2-7c12-5093-98b1-4a7f2ca2bb7b |  | note | CATEGORY: IP
label | 7dfc6101-7172-5b36-96c0-b348b6a2ef37 |  | note | ---------------------------------
label | 8510736f-fe54-54d2-9bbb-60712a5faee3 |  | note | RESPONSIBILITY: SE/PE
label | 32f80c9d-4aa0-5aec-a1d0-5a9fec01cfd9 |  | note | ---------------------------------
label | 9ea2d452-7d7b-5002-b08b-0f67dab9df82 |  | note | VERIFYING DOCUMENTS:
label | 80e0023f-7fce-5a6d-bfe4-3806dfa8c5ab |  | note | Sign ITP
label | 0d8cf878-4f95-583d-9084-f15adac248e1 |  | note | Attached RLMU
text | 08864fe6-0201-5aea-bda0-1e94a4e5767f |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | Metropolitan Roads Program Alliance Final Inspection
label | 9cf75333-a764-5237-854c-936b0df0b862 |  | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
text | dade164b-c80b-555b-a6e4-ea3fee3d10f5 |  | textbox | Name:
text | be2b6a30-c9b1-5bad-b529-d52f43218a9b |  | textbox | Position:
text | eeb4cecb-fb9d-5ee6-8835-3afa32185565 |  | textbox | Date Completed:
holdpoint |  |  | signoff | Sign ITP
checklist-sectioned |  |  | checklist | ITP-013-STR-Pile Cap Construction | itp |  |  |  | Yes | ITP-013-STR-Pile Cap Construction Rev 0 | e29a5e1b-8f35-4a6c-aaaa-644d6ccc31e4
checkpoint-group |  |  | section | Referenced Documentation
checkpoint-status |  |  | checkpoint | Referenced Documentation
label | 9537e0d6-10e6-5017-a771-0286fc3d36cc |  | note | Document Title: ITP-013-STR-Pile Cap Construction
label | 39e76b87-b4df-5933-9711-6cc693e2e6aa |  | note | ITP Description: Pile Cap Construction
label | b36e25c6-b26a-58bf-a2df-d9af4aa3b601 |  | note | Document Number (in Teambinder): MRP-0000-MRPA-ALT-ITP-00XX
label | 548fe2b6-45c0-5e55-a006-4310dfc64007 |  | note | Discipline (e.g. CIV/STR/RAIL): STR
label | 301ed352-43a1-5945-bcfb-8919ae0df611 |  | note | Revision Number: 0
label | 499deaa6-ac9a-503e-b9f9-78247084b9be |  | note | Revision Date: 01/12/22
label | db1de2cf-bef8-538c-8ea4-c58101742a73 |  | note | ITP created by: Victor Mira
label | e094fef1-1793-5707-83c0-a3fa7c9768ef |  | note | ITP approved for use by: Victor Mira
label | d7afed2d-2342-5000-bc66-86e84d768526 |  | note | 1.1 Non Dependent
label | 9fda75b7-e628-521f-8df2-61904b584a56 |  | note | Reference: VicRoads Section 602 October 2007
label | 452cfbd9-edc0-5f32-b1ad-42be068b887f |  | note | 1.2 Non Dependent
label | f17613fc-1a91-5070-9e1f-fd8b733637e1 |  | note | Reference: VicRoads Section 610 February 2020
label | c85d8da6-5e6f-55b4-a8c1-79667fd1b7bd |  | note | 1.3 Non Dependent
label | 96380b3b-dbde-5005-9fc3-c447196238f3 |  | note | Reference: VicRoads Section 611 November 2018
label | df4f3ad9-383d-5d4f-bf06-2eb92a8dbf6b |  | note | 1.4 Non Dependent
label | 0052eacb-88cc-5a80-9f4f-0153f446471b |  | note | Reference: VicRoads Section 614 June 2017
label | 1dd5b02c-b293-509c-a0ab-1b33ae031005 |  | note | 1.5 Non Dependent
label | 106f9158-6bdb-543c-b230-2b804ebdfc0e |  | note | Reference: AS3810.1 2018
checkpoint-group |  |  | section | Preliminaries - Materials
checkpoint-status |  |  | checkpoint | 2.1 Concrete Mix
label | 77840da2-3cbe-52b4-a7a8-86e106a9984a |  | note | REFERENCE:
label | 8bf686c7-4ecf-5808-b2f6-60160d22fe3b |  | note | 610.07
label | 5900934b-475c-57a2-a18b-2f2b6d169f9f |  | note | Table 610.071
label | 4aae9b62-df11-5e99-a598-0be4740779df |  | note | IFC Drawings
label | 996cc973-f52d-5655-b739-c13000343e93 |  | note | – – – – – – – – – – – – – – – – –
label | 0d808b45-2a1f-5c6b-b770-994f4e34ed3d |  | note | ACCEPTANCE CRITERIA:
label | c9e95c98-e1ad-51b5-b34d-3fd6fa37f667 |  | note | • Concrete Mix is Registered with VicRoads.
label | e84023b0-1827-5c69-9cee-0e1926a65f29 |  | note | • Concrete mix meets strength, grade, and maximum aggregate size as detailed on drawings.
text | 486b9f5c-6026-597a-b623-f74c3752b5d0 |  | textbox | Enter: Teambinder Material Approval number
label | bf894c69-9df9-5bf4-ad96-165c4171e059 |  | note | – – – – – – – – – – – – – – – – –
label | c1503edf-d4a7-5e35-b77f-ed104d2c1ce8 |  | note | METHOD: Document Review
label | 034ecb16-3638-5e26-9752-45d0e0b035e0 |  | note | – – – – – – – – – – – – – – – – –
label | 25d85e4a-9f90-5e3b-a487-b7a503f412a8 |  | note | FREQUENCY: Once, for each mix design, 4 weeks prior to placement of concrete
label | 6b8e7c31-5317-573e-a635-20090eaa37cc |  | note | – – – – – – – – – – – – – – – – –
label | faacc0ed-d23c-57f0-a55e-25b9ca20a154 |  | note | CATEGORY: HP
label | 16c7c894-531e-55f1-9328-d8d04eff0e70 |  | note | – – – – – – – – – – – – – – – – –
label | 73c476f7-27a3-5e8f-bad6-d5896cb7f118 |  | note | RESPONSIBILITY: Nominated Authority
label | f90986ad-d2b9-5632-849b-58634b19e24e |  | note | – – – – – – – – – – – – – – – – –
label | ed78c1da-546c-5585-9f16-fc7174023a03 |  | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
text | 4763dc47-dd24-5113-b2b8-1de0948a9c79 |  | textbox | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.2 ACRS Certification (for Reinforcement)
label | 81a7e293-eb20-5f8f-b3d6-b0c69594876d |  | note | REFERENCE: 611.05 (a)
label | a781f34f-b69c-54f2-9277-48afdc7adb10 |  | note | – – – – – – – – – – – – – – – – –
label | 8d98135f-c205-5841-9777-7d736d14145e |  | note | ACCEPTANCE CRITERIA:
label | d415f1dd-e647-5b23-b41d-1782069844f6 |  | note | • Current ACRS certification for materials and for bar processing.
label | 0bed4fe9-2d1d-5909-bd0b-759ec7a76cc2 |  | note | • Note: ACRS certificate may cover both aspects or be for each separate portion (e.g 1 for the material supplier and another for the bar processor (bending, cropping and delivery)
text | 47c74bce-7d91-5c71-8eea-ea945bb74efc |  | textbox | Enter: Teambinder Material Approval number
label | a2d532a6-6f7d-5ba6-814a-fe28543bf34f |  | note | – – – – – – – – – – – – – – – – –
label | 42643542-026e-5bf5-b0d2-fb78df2a2448 |  | note | METHOD: Document Review
label | 6cb07bc7-ea02-5aa9-bf9d-5bb4d6aaf57b |  | note | – – – – – – – – – – – – – – – – –
label | 9430b6c0-9bd4-5483-bf0e-75f37e58ab5a |  | note | FREQUENCY: Once for each supplier, 14 days of award of contract
label | ba185520-4ce7-5a10-b01e-e9dfcb318f4a |  | note | – – – – – – – – – – – – – – – – –
label | c99e59af-e153-5512-944c-b4c97331af8b |  | note | CATEGORY: HP
label | 7b76b7a1-362f-58a5-bdd3-b4fde7957047 |  | note | – – – – – – – – – – – – – – – – –
label | 03f962cd-9866-5968-8d12-56179b5ba365 |  | note | RESPONSIBILITY: Nominated Authority
label | 4647b8c9-1027-5e02-a82c-8388749f686e |  | note | – – – – – – – – – – – – – – – – –
label | 1c9df22c-672a-5acc-a64e-576c31c264bf |  | note | VERIFYING DOCUMENTS: This ITP
text | a4516bd0-2f9a-5e30-85f2-8faea10fd560 |  | textbox | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.3 Bar Chairs/Aspros Certification
label | e30df8fd-d0a8-503c-a5ff-7113032df71d |  | note | REFERENCE: 610.26 (a)
label | 797e454c-d125-51b3-9f9b-515378730d36 |  | note | – – – – – – – – – – – – – – – – –
label | 171d7509-4395-516e-a0db-c0b4c7b5958a |  | note | ACCEPTANCE CRITERIA:
label | 3351d11f-b1e5-5775-948e-4f129dcd4822 |  | note | • Plastic bar chairs, wheels, and spacers require bi-annual testing to demonstrate suitability to prevent excessive deformation under loads.
label | fc2ea57c-4ba8-57a9-9d1d-14e15488241b |  | note | • Concrete aspros require annual compressive strength and soluble salt testing is required.
label | 9ffdbed2-6db7-54c0-8a11-e27868a30c2d |  | note | • Relevant test reports demonstrating compliance to this clause shall be submitted for review to the Nominated Authority.
text | c759c006-0919-5f9a-9382-7433dfa75baa |  | textbox | Enter: Teambinder Material Approval number
label | 4097a1eb-5a36-5df1-92ff-666abaf8a6f4 |  | note | – – – – – – – – – – – – – – – – –
label | 19d9e1a8-7f48-50f3-ab52-fe403239e07a |  | note | METHOD: Document Review
label | 9f2aa242-0712-5fbf-8378-33b925df56af |  | note | – – – – – – – – – – – – – – – – –
label | 8c48164b-ade9-5d05-97ed-02102b6f81c4 |  | note | FREQUENCY: Once for each supplier, 14 days prior to placement of reinforcement
label | 82280f6f-eb73-5be0-8f96-ee9f26864715 |  | note | – – – – – – – – – – – – – – – – –
label | fa238b83-7459-5f3d-b098-555eb6281c3f |  | note | CATEGORY: HP
label | b72eb3f4-b68f-5987-bc23-0016de7162b9 |  | note | – – – – – – – – – – – – – – – – –
label | 803c782c-03f7-5c4b-99ad-d271f7d62d05 |  | note | RESPONSIBILITY: Nominated Authority
label | 51eb03f2-fdf9-5fb7-8315-7a95f414c7a7 |  | note | – – – – – – – – – – – – – – – – –
label | 1568d4cc-0073-5395-b690-746afd11381b |  | note | VERIFYING DOCUMENTS: This ITP
text | ea24d8d6-ce2e-5126-9a80-337757c41e84 |  | textbox | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.4 Evaporative Retardant
label | 5baecc5e-3a30-5ab2-ae63-7f147bf5323f |  | note | REFERENCE: 610.17 (f)
label | 4bfbf535-b4fe-50aa-bbaf-07ed453c7b47 |  | note | – – – – – – – – – – – – – – – – –
label | ba1fa5dd-ffd4-5030-b377-52e50907e893 |  | note | ACCEPTANCE CRITERIA:
label | 97b7839e-9c53-59a8-93fc-3d9b11662f6d |  | note | • Details of evaporative retardant, application procedure (including application rates) to be submitted for review to the Nominated Authority.
text | 7cd0b209-e05e-583e-899f-08691d2e06b0 |  | textbox | Enter: Teambinder Material Approval number
label | 3c5a5845-0726-5f97-a3b5-e65042c0db77 |  | note | – – – – – – – – – – – – – – – – –
label | 2594326a-eff5-5aa2-982a-2499055e9db6 |  | note | METHOD: Document Review
label | 1803432e-5879-5104-8275-b68494668738 |  | note | – – – – – – – – – – – – – – – – –
label | 2a6c0e74-008e-5d5e-a029-9b76996c14d0 |  | note | FREQUENCY: Once, for each product, 4 weeks prior to placement of concrete
label | 064ecc01-0810-5b14-a502-30c5dbaeeec1 |  | note | – – – – – – – – – – – – – – – – –
label | d99a5b5c-8c4d-5b82-b59f-d9722c783e53 |  | note | CATEGORY: HP
label | 61317cb3-d735-516c-8e36-63b338ac6c3a |  | note | – – – – – – – – – – – – – – – – –
label | 28ccddef-1f15-5a93-95df-e11bb1110656 |  | note | RESPONSIBILITY: Nominated Authority
label | 06960362-f7cd-500e-84e7-2edd541adb18 |  | note | – – – – – – – – – – – – – – – – –
label | f3c73957-e34e-5499-96a0-ce4c70dc6cdd |  | note | VERIFYING DOCUMENTS: This ITP
text | 1c700ecd-159b-56e7-b932-feb752194e81 |  | textbox | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.5 Curing Compound
label | 6639e5da-4af4-5d75-9d78-7c13fab06341 |  | note | REFERENCE: 610.23 (d)
label | 3f523261-666f-5360-b4b6-3f080bd7260c |  | note | – – – – – – – – – – – – – – – – –
label | 3bd69980-f38c-5aa9-b154-f041669c1bd6 |  | note | ACCEPTANCE CRITERIA:
label | 3ef89396-c644-5620-9031-f9ba8e99434d |  | note | • Details of curing compound and NATA test certificate stating compliance with AS3799 no more than 3 years from issue, to be submitted for review to the Nominated Authority.
text | e74c98c8-1fac-5d88-b81b-10115649f161 |  | textbox | Enter: Teambinder Material Approval number
label | c8c26647-ad7a-56ea-a86c-c943ebdf2a48 |  | note | – – – – – – – – – – – – – – – – –
label | 5d81fd21-51b6-5eac-b0be-137d4aa69e66 |  | note | METHOD: Document Review
label | ca59e8b8-2e0f-58a8-9880-912306c9b560 |  | note | – – – – – – – – – – – – – – – – –
label | e9780934-1cd8-5843-90d1-9ce4fb731ca1 |  | note | FREQUENCY: Once, for each product, 4 weeks prior to placement of concrete
label | 0dc4b7cc-8a75-5e9f-8108-8d8f42d66957 |  | note | – – – – – – – – – – – – – – – – –
label | 69dccb87-f0bf-58e6-af99-6e249b686e3a |  | note | CATEGORY: HP
label | b99af72b-82fb-5348-b0fc-c8f36e60d259 |  | note | – – – – – – – – – – – – – – – – –
label | a5194b14-34dd-5bf8-8ab9-3a8cc44a313d |  | note | RESPONSIBILITY: Nominated Authority
label | 03cf607d-c46c-5658-80c2-4f0f976f9649 |  | note | – – – – – – – – – – – – – – – – –
label | 960fc029-df24-5242-a4a7-a885d1c0a701 |  | note | VERIFYING DOCUMENTS: This ITP
text | e96c8b4b-ea5c-56ae-a02b-56d45bc387c8 |  | textbox | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | Preliminaries - Procedures & Documentation
checkpoint-status |  |  | checkpoint | 3.1 Concrete Placement and Compaction Work Method Statements
label | 56033bd8-92bd-5796-8c35-c40831f14d26 |  | note | REFERENCE: 610.18 (a) (i)
label | 35e6b3c0-b877-5e96-a3ff-f69e9559f9e8 |  | note | – – – – – – – – – – – – – – – – –
label | 7b90a47a-812e-52bc-b38b-751b04068132 |  | note | ACCEPTANCE CRITERIA:
label | a54bb344-117e-53aa-a7c2-fefd6dc1e492 |  | note | • Concrete placement and compaction WMS to be submitted for review to the Nominated Authority.
text | 8684a9b7-12d5-56d5-9d45-db7c126d4bdf |  | textbox | Enter: Teambinder Approval number
label | b181179a-f67d-5e1a-85dd-6c733837f0ce |  | note | – – – – – – – – – – – – – – – – –
label | f62964ae-0ac3-59b1-b26e-1d9cd85c50b0 |  | note | METHOD: Document Review
label | 4b10acd8-b4ea-5c4d-9bb3-0890e6bd2dda |  | note | – – – – – – – – – – – – – – – – –
label | 9d85f99a-cf85-5a2f-8d08-fd7469e22347 |  | note | FREQUENCY: Once, 4 weeks prior to placement of concrete
label | 5c78c291-9a53-5388-9ab4-d13ebcd4b648 |  | note | – – – – – – – – – – – – – – – – –
label | 5c27cfea-ab5b-5633-b01a-2ad2e8fc485c |  | note | CATEGORY: HP
label | d935d828-8061-56a2-87d9-6973c22b3513 |  | note | – – – – – – – – – – – – – – – – –
label | 36132bea-d192-5d31-b560-d191ea84d975 |  | note | RESPONSIBILITY: Nominated Authority
label | 6c98a61b-9c34-5ee0-9703-98c31202668f |  | note | – – – – – – – – – – – – – – – – –
label | e383aecf-d2ab-5d65-86d4-37981485c631 |  | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
text | 28fd0526-6e8a-5366-b90f-a1939238b36a |  | textbox | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.2 Concrete Sampling and Testing Procedure
label | 9bf97174-a24e-5a7f-8ef2-03eada6000ae |  | note | REFERENCE: 610.18 (a) (v)
label | a805eb1d-8e9c-57d8-90d1-d5b9add5db1c |  | note | – – – – – – – – – – – – – – – – –
label | f829bbc3-e103-5b66-952d-cc699a984ef3 |  | note | ACCEPTANCE CRITERIA:
label | 9045fa32-0310-5cc5-be53-b1fd7e13acf6 |  | note | • Concrete sampling and testing procedure to be submitted for review to the Nominated Authority.
text | cfef85b2-b3da-55d0-803e-d8ac23714bda |  | textbox | Enter: Teambinder Approval number
label | 1c4fbc93-1269-5efc-b872-04fe5351202d |  | note | – – – – – – – – – – – – – – – – –
label | 4bed68ee-fe9b-58ad-a6b2-7bd9c225e4e7 |  | note | METHOD: Document Review
label | 831ad3fd-4021-50b5-b024-1e47b1e15357 |  | note | – – – – – – – – – – – – – – – – –
label | 5a57d245-9c1b-5d73-b2ff-2fadda27ccb4 |  | note | FREQUENCY: Once, 4 weeks prior to placement of concrete
label | bfd37efe-69a8-5daf-ae97-88d65b0b7a03 |  | note | – – – – – – – – – – – – – – – – –
label | 4e23c772-2a6b-512d-bdc2-fe1d241f3311 |  | note | CATEGORY: HP
label | 8adfba96-a46f-53e6-8d44-bb716f6b0eb5 |  | note | – – – – – – – – – – – – – – – – –
label | f1bfa603-acdb-56d2-92a7-a749fd40df8f |  | note | RESPONSIBILITY: Nominated Authority
label | 4cdbd056-d66e-5d5c-b7b7-bd7898796e8d |  | note | – – – – – – – – – – – – – – – – –
label | 7c77ac64-7090-52a1-8bfc-e956749d5181 |  | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
text | e871b1e3-f88c-56cf-9e79-a59735fc75d3 |  | textbox | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.3 Concrete Placement and Compaction Toolbox Meeting
label | caae385c-daf1-5096-80d5-6e76fcf3803e |  | note | REFERENCE: 610.18 (a) (iv)
label | 205ea65c-59d0-5d1a-b924-3c305216d072 |  | note | – – – – – – – – – – – – – – – – –
label | 63e828c8-25f4-5ca1-9487-202138abed08 |  | note | ACCEPTANCE CRITERIA:
label | 25c4fd32-9872-505b-8ae3-3794b219eac1 |  | note | • Concrete placement and compaction toolbox meeting held to discuss the quality requirements.
label | 70c7d522-dabe-5f3a-8f60-ca1e238a3cb6 |  | note | • Minutes of this meeting to be submitted to the Nominated Authority.
text | 5e124d36-c34b-5f73-952f-0a29d9018fa5 |  | textbox | Enter: Teambinder Approval number
label | f1ab8116-e6cb-55f7-8050-b4e8b05e98a0 |  | note | – – – – – – – – – – – – – – – – –
label | 7c250af0-74af-5183-94f8-4b8f31439b2d |  | note | METHOD: Document Review
label | 8414664e-b0bf-59e1-b87c-d911bc2ca7ac |  | note | – – – – – – – – – – – – – – – – –
label | c83c280c-3cdc-5a32-8411-213c718d7547 |  | note | FREQUENCY: Once, 4 weeks prior to placement of concrete
label | 7dd82aa8-a08a-5521-948b-d6f2bf5f28be |  | note | – – – – – – – – – – – – – – – – –
label | 0f8f92c7-8b40-5b8f-a23b-bfd72ee3f645 |  | note | CATEGORY: HP
label | e05626c8-a85a-5493-aabc-d930b98b9b6d |  | note | – – – – – – – – – – – – – – – – –
label | 6f40aa42-7fce-5965-bdb5-65a85c6b8196 |  | note | RESPONSIBILITY: Nominated Authority
label | 117e5e8a-7dc8-5efe-bbaf-800a125da239 |  | note | – – – – – – – – – – – – – – – – –
label | e4ca6508-470b-538a-afa8-a14867092c44 |  | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
text | 935de38b-875d-58dd-b167-779cfd24228b |  | textbox | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.4 Hot and/or Cold Weather Concreting Procedure
label | 7b079b2a-e460-5fa5-ad9b-a3bdace03df9 |  | note | REFERENCE: 610.17 (a)
label | 6f3e4406-d02a-50b4-898b-c7c7479ce32b |  | note | – – – – – – – – – – – – – – – – –
label | 920db9ed-9329-5cc4-af7a-70bc146dc982 |  | note | ACCEPTANCE CRITERIA:
label | 0a4024a7-4e2b-5af9-890e-bb420112e6ff |  | note | • Hot and/or cold weather concreting procedure to be submitted for review to the Nominated Authority.
text | e055efc8-ef2a-5582-8eaa-209305554684 |  | textbox | Enter: Teambinder Approval number
label | 932a8aaa-497e-54b9-a6ff-63857f99eaf9 |  | note | – – – – – – – – – – – – – – – – –
label | 6804e185-8a41-5c20-9530-da731d18374e |  | note | METHOD: Document Review
label | a8758758-8069-5ea1-93fe-14a4da69d239 |  | note | – – – – – – – – – – – – – – – – –
label | 406b67c6-26ad-509c-8b38-1865531e387a |  | note | FREQUENCY: Once, 2 weeks prior to placement of concrete
label | f33d510c-2f6c-5824-9e58-3d82647b3fe3 |  | note | – – – – – – – – – – – – – – – – –
label | 647e3d4e-41ab-50bc-99c5-9fd6b661995d |  | note | CATEGORY: HP
label | 476130d3-a3db-5124-8bc8-b693e66bbed9 |  | note | – – – – – – – – – – – – – – – – –
label | af68356f-ac24-5ebf-8bd0-b77e4b28c142 |  | note | RESPONSIBILITY: Nominated Authority
label | b3101959-9b81-5da1-a0e6-1045951ca3b9 |  | note | – – – – – – – – – – – – – – – – –
label | 8fe8d31d-41c0-56f3-8e6e-b9222b95d899 |  | note | VERIFYING DOCUMENTS: This ITP
text | 0f9b0c2c-8121-598c-818f-876d6d8f130e |  | textbox | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.5 Curing Methodology (for Concrete and Grout)
label | 8d1d5327-2f3d-5cf7-b9c0-159c304803f0 |  | note | REFERENCE: 610.23 (a)
label | a2fae9ce-8829-53f9-9600-69f764db72ca |  | note | – – – – – – – – – – – – – – – – –
label | 647b5494-9ad6-5f0c-9607-6f498389c039 |  | note | ACCEPTANCE CRITERIA:
label | 395fe7e0-0f1a-5ac3-bc15-44028df73a0b |  | note | • Curing methodology/procedure to be submitted for review to the Nominated Authority.
text | 5d9e38c2-2e22-59ff-b1d1-3bb2331228c8 |  | textbox | Enter: Teambinder Approval number
label | 5d66bebe-2585-54ae-91c8-c74d0261bc1e |  | note | – – – – – – – – – – – – – – – – –
label | a1f1ed26-7e2a-560a-8191-24bb6674e5b2 |  | note | METHOD: Document Review
label | 65934380-80fc-5908-ad01-58f43aa7209e |  | note | – – – – – – – – – – – – – – – – –
label | 32551c8c-e3b5-50af-9f9a-ba64cbabf626 |  | note | FREQUENCY: Once, 4 weeks prior to placement of concrete
label | 664442af-3b00-58f5-904c-ddd5dee2581c |  | note | – – – – – – – – – – – – – – – – –
label | 1a271b99-68b5-5d00-94af-77c7ee40b495 |  | note | CATEGORY: HP
label | 1d4438f7-5fb6-520d-b4b5-d0eb063f87e2 |  | note | – – – – – – – – – – – – – – – – –
label | ec5231c3-7416-5fda-a132-0bf015154085 |  | note | RESPONSIBILITY: Nominated Authority
label | ada5b814-f946-5ab1-b287-eb7b3069c487 |  | note | – – – – – – – – – – – – – – – – –
label | 7c1acb6b-5183-50a7-aed8-04f948882459 |  | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
text | 64fd3522-7d64-523f-941f-205602481d63 |  | textbox | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.7 Concrete Drilling Procedure
label | 17343267-381f-5726-a936-f4cef22fa69d |  | note | REFERENCE: 610.46
label | 77edfcc6-c0ec-5af0-80af-753e3a52b2f5 |  | note | – – – – – – – – – – – – – – – – –
label | f159cfaf-8dea-522a-b680-fcfef2dc24d7 |  | note | ACCEPTANCE CRITERIA:
label | 21a3b103-bdb9-57e1-ab21-6dc927f6077e |  | note | • Where holes are to be drilled into existing (new or old) concrete members, the locations shall positioned to avoid striking any existing reinforcing bars, tendons and services.
label | f4016fe4-9acf-50fd-b258-225dbf67ae38 |  | note | • The planned locations and drilling procedure shall be submitted for review to the Nominated Authority.
text | b9e15548-a459-5a87-91eb-5c79dde545c0 |  | textbox | Enter: Teambinder Approval number
label | acc62fa3-0ffa-5105-9bed-2609e763ea35 |  | note | – – – – – – – – – – – – – – – – –
label | 6073fc64-af40-5f94-8bd3-512f1e5c7a88 |  | note | METHOD: Document Review
label | b494b93c-aa64-56a3-8318-6f412082f51e |  | note | – – – – – – – – – – – – – – – – –
label | b8e5889c-c01c-547a-bb16-ebca825d0d91 |  | note | FREQUENCY: Where applicable, once, 2 days prior to drilling
label | ea740f62-d13f-5d7e-a27e-4528e5a6f790 |  | note | – – – – – – – – – – – – – – – – –
label | 4b19292a-060f-55e5-adc6-12c4cc12d640 |  | note | CATEGORY: HP
label | 3711cfc5-cca1-57fe-b97c-6174e9396a22 |  | note | – – – – – – – – – – – – – – – – –
label | 816b6a07-9cf5-5c96-b08b-e20d9160982c |  | note | RESPONSIBILITY: Nominated Authority
label | 363ef277-cfd1-5916-b9bf-67141f8bf46c |  | note | – – – – – – – – – – – – – – – – –
label | 36a51185-c15c-55a2-ad2c-1656720a4980 |  | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
text | cc6922bb-50a5-53eb-ade1-5ef73ba7f9f3 |  | textbox | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.8 Temprature difference measuring-Calibration
label | 855ed2c6-f89f-5826-a206-5b43c52db918 |  | note | REFERENCE: MRPA Quality Management Plan
label | 948f3be3-f84e-5300-88ed-445694ca49a0 |  | note | – – – – – – – – – – – – – – – – –
label | ddeff652-a29d-5534-8ed8-259f287deee2 |  | note | ACCEPTANCE CRITERIA:
label | 89df13bd-69e7-55da-9a79-0e270ebfe342 |  | note | • Calibration records are valid and up to date.
label | 1c0c6ae6-a3af-599b-8463-6ce49acd7d6e |  | note | Attach: Calibration certificate
label | 233555c0-2479-502b-a05e-a2a33dcf946e |  | note | – – – – – – – – – – – – – – – – –
label | a21ea0d1-f238-5f5f-b3dd-cecb9f7a8ff2 |  | note | METHOD: Document review
label | 4e157ca7-5d65-54f0-9f2d-d7b7e3c0552f |  | note | – – – – – – – – – – – – – – – – –
label | 8eb2fb9d-9d91-5d02-85ae-7866afb64228 |  | note | FREQUENCY: Where applicable
label | e7350344-2f3d-5254-86bf-17c42fed9e0c |  | note | – – – – – – – – – – – – – – – – –
label | e1074c1c-6958-5796-a564-07ac06274422 |  | note | CATEGORY: HP*
label | 0ed01805-89b9-5ee2-866e-010660664010 |  | note | – – – – – – – – – – – – – – – – –
label | 7f9a8e8f-8409-5e90-8273-4475ab9f06d2 |  | note | RESPONSIBILITY: PE
label | 513e80d6-6145-5212-a06d-ea5a924b68d1 |  | note | – – – – – – – – – – – – – – – – –
label | 3c546660-4785-505b-9e17-f803891bde9e |  | note | VERIFYING DOCUMENTS: This ITP, Attached calibration certificate
text | 1bf25038-4545-512b-8450-177fb45be54a |  | textbox | Date Completed:
checkpoint-group |  |  | section | Pre-construction Activities
checkpoint-status |  |  | checkpoint | 4.1 IFC Drawings
label | 8ba0feac-b66e-59b4-939e-7d10bb7486fc |  | note | REFERENCE: MRPA Quality Management Plan
label | b753b8d3-af69-5ea9-87f5-6a588b823999 |  | note | – – – – – – – – – – – – – – – – –
label | 03f9870f-1883-5c74-8a4a-7b1511494891 |  | note | ACCEPTANCE CRITERIA: Check the revision of the IFC drawings are current as per the drawing register (on Teambinder)
label | f14d70bf-f0da-5b41-856f-0ae628e1bb23 |  | note | – – – – – – – – – – – – – – – – –
label | 6d3843b5-48c7-575a-81c0-0be6899e4f39 |  | note | METHOD: Document Review
label | 6bfdfa72-318e-5124-9dc2-ca2fec9bc05c |  | note | – – – – – – – – – – – – – – – – –
label | 7faa375f-d12a-5321-9725-d7434c8431ed |  | note | FREQUENCY: Prior to starting Works and at regular intervals
label | 49fc630b-0600-512b-a67a-e93a1a06894f |  | note | – – – – – – – – – – – – – – – – –
label | 36dcf768-12fb-52c1-861d-831251476edf |  | note | CATEGORY: HP*
label | 6aefb2ef-9c05-51b2-b8d2-49ed49f9773d |  | note | – – – – – – – – – – – – – – – – –
label | ee7117fd-405c-5d03-86b8-30bb0d874f9e |  | note | RESPONSIBILITY: All
label | 0435f20d-060b-5a68-9334-ddcb7447312c |  | note | – – – – – – – – – – – – – – – – –
label | d853ab1b-6278-5e8d-9419-8cb8c733aad5 |  | note | VERIFYING DOCUMENTS: This ITP
text | 847fb292-a8b6-5af9-a5fd-ee5835de75c6 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 4.2 Survey Set-out
label | f27cbe1b-aecd-5bbe-9664-90757d11167d |  | note | REFERENCE:
label | 44650ab4-667f-5800-9133-95b5f9248d32 |  | note | IFC Drawings
label | 53c5d341-e358-533d-a635-15133a642183 |  | note | 610.47 (a)
label | 42553cf0-cf67-57c8-bbc1-2d079988c890 |  | note | Table 610.472
label | b97ac717-9fa0-559f-99f8-9d736e185ca8 |  | note | – – – – – – – – – – – – – – – – –
label | e9d39b0b-0950-58c3-ae1d-5d9da2e722c0 |  | note | ACCEPTANCE CRITERIA:
label | e133fb56-1b87-58f8-af12-5f8440654cb3 |  | note | • Survey activities undertaken to ensure and validate that all Works meet level and location requirements within the tolerances as per the table 610.462 as applicable to the element.
label | fe448c4d-ccf7-58d1-9015-2bde51327ec8 |  | note | Attach: Lot Map, Marked up drawing which shows the Lot Location and extent
label | ac3e5a97-814d-5160-9710-e035024d82f0 |  | note | – – – – – – – – – – – – – – – – –
label | f8cc10bc-dcc4-5a9b-bc29-8e9c455873e7 |  | note | METHOD: Measure, Visual
label | 1fc955f4-2443-5b76-897d-c8b1e91b247d |  | note | – – – – – – – – – – – – – – – – –
label | 65e2526e-4f90-5130-8848-ffcbcdb52ee7 |  | note | FREQUENCY: Each element
label | e435584b-00c3-5c26-87a3-6c83d3c2299e |  | note | – – – – – – – – – – – – – – – – –
label | d6582612-9b52-51ac-bd4e-90270b30fc3c |  | note | CATEGORY: IP
label | 1d760725-d4c9-5442-aa73-e50a80628f7a |  | note | – – – – – – – – – – – – – – – – –
label | de51f7f3-5cf7-598d-9fca-3ca793a11967 |  | note | RESPONSIBILITY: Surveyor, SE/PE
label | 54d9bd50-c626-5781-bfea-c3ec4c19e4e7 |  | note | – – – – – – – – – – – – – – – – –
label | 08a7ee06-e84c-595d-9288-d7a2ad1c050c |  | note | VERIFYING DOCUMENTS: This ITP
text | fe398c0d-78d7-5cd7-8ff7-2d4824c47369 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | Piles
label | ddd20467-8bfe-5c6a-a89a-106c92be1d88 |  | note | REFERENCE: IFC Drawing
label | 946c46e3-1415-50d8-98cd-19eea09dc610 |  | note | – – – – – – – – – – – – – – – – –
label | 66fdd58c-2e50-522f-aac3-17aa4ed105eb |  | note | ACCEPTANCE CRITERIA:
label | ef1b9b07-f773-5349-972a-28e77b2528ad |  | note | • Related piling Lots are closed.
label | 084c0f97-076b-5217-a5b0-6121468a6e45 |  | note | – Pile design strength is achieved.
label | de3b62c2-4e1b-5a42-8618-d2367041de5c |  | note | – Integrity and Dynamic tests performed and interpreted.
label | ad4a6fb9-88d2-5bb5-a932-3cb191e065e5 |  | note | – Pile is broken back to the design level.
label | f9d032d9-f66f-5e5f-8d18-85b20894804f |  | note | – As-Built Survey performed.
label | a80ee40e-cddc-5701-9920-e9c48085da00 |  | note | – Related piling NCMs are closed.
text | bf88119f-2d95-5679-8180-86332f1661bd |  | textbox | Enter: piling Lot numbers:
label | f75f2dcb-17f3-55d8-83dc-ccb27dfef6df |  | note | – – – – – – – – – – – – – – – – –
label | 9851cf31-db1e-5ba4-b1ce-6d9dbd6e52be |  | note | METHOD: Doument Check
label | d6071318-41d8-5dd8-960e-af3b74ab36b6 |  | note | – – – – – – – – – – – – – – – – –
label | 2cc2324e-d52f-5722-8d1f-4d9e5c0b607a |  | note | FREQUENCY: Each Element
label | 0bf71792-9da9-543f-93ff-1e8897e133e7 |  | note | – – – – – – – – – – – – – – – – –
label | 5802dc25-8566-5857-9a56-e0e1db3b2c85 |  | note | CATEGORY: HP*
label | 940ef90f-136d-5abd-bbfe-1ee65d8ef3ce |  | note | – – – – – – – – – – – – – – – – –
label | 9072513f-1d38-5342-89f4-505b220050ef |  | note | RESPONSIBILITY: PE
label | f61e508e-4b04-58ee-9ea0-59fff0d2df1b |  | note | – – – – – – – – – – – – – – – – –
label | b24d9dcd-b013-5c3d-9151-bb36946232f2 |  | note | VERIFYING DOCUMENTS: Piling Lots
text | 860a69f3-4d8f-5c11-976d-f6b692f7117b |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 4.3 Excavation support
label | e1b01e5f-7aef-5a33-ac61-182605089b62 |  | note | REFERENCE: 602.02
label | f17d13cd-6acc-5de5-ab5d-7024468de96e |  | note | – – – – – – – – – – – – – – – – –
label | c3f578f9-4b52-5091-b34b-743964f09d58 |  | note | ACCEPTANCE CRITERIA:
label | a154ebf1-471e-529d-b4e7-7ec5d618b8b4 |  | note | • For excavations adjacent to railway property, alongside roadways, in or alongside waterways, and excavations deeper than 1.5 m, the Contractor shall submit to the Nominated Authority for review detailed drawings of bracing and/or sheeting proposals, including design calculations and methods of construction and removal.
text | cf644a87-2fa6-55ae-a36b-d123b3276780 |  | textbox | Enter: Teambinder Approval number
label | f6621765-7deb-58c6-9e91-ffb0ca40d073 |  | note | – – – – – – – – – – – – – – – – –
label | 612ac64e-5c03-5dec-99cf-87e47f605802 |  | note | METHOD: Document Review
label | 43738dbb-0da5-542c-9c95-a85b39d21970 |  | note | – – – – – – – – – – – – – – – – –
label | 0372bfda-7421-5b5e-8e07-bfea56701950 |  | note | FREQUENCY: Where applicable, not less than 10 business days prior to excavation
label | 7322e95f-b1eb-5b4c-9455-5afb75073f06 |  | note | – – – – – – – – – – – – – – – – –
label | 945aaa14-8092-5c62-a599-2e69292f1e11 |  | note | CATEGORY: WP
label | 5cdb349c-9947-5954-826e-f03d076a5742 |  | note | – – – – – – – – – – – – – – – – –
label | cdb6ce8f-0da2-518b-83ef-1e0a8a8be17e |  | note | RESPONSIBILITY: SE/PE/SPE
label | cf1bf5d5-5d41-5b31-989b-4cca237cc585 |  | note | – – – – – – – – – – – – – – – – –
label | 86c40481-5925-574a-8a3b-a95879ae6d6b |  | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
text | 1a0c2238-2853-5d87-ab9b-50cfc7910b93 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 4.4 Excavation Inspection
label | d886ccb2-1955-547e-94b6-6afb781e2119 |  | note | REFERENCE: 602.03
label | a27ed158-8fbf-51ea-b545-bdebcd8ddea7 |  | note | – – – – – – – – – – – – – – – – –
label | 9e255c37-dcea-57e1-b77c-e45da9fb6457 |  | note | ACCEPTANCE CRITERIA: Blinding concrete shall not be placed until the bottom of the excavation has been reviewed by the Nominated Authority.
label | 3397f3d3-2545-52cf-9e2c-5dc3b6ba6076 |  | note | – – – – – – – – – – – – – – – – –
label | 014fc285-a637-59c6-8e72-1fe71edccbe1 |  | note | METHOD: Visual
label | a1057273-f4fb-5225-be79-7a224ba4f80f |  | note | – – – – – – – – – – – – – – – – –
label | 2d591db6-2b3a-55ab-9e4b-3a042f61a30a |  | note | FREQUENCY: Where applicable, prior to placing blinding concrete
label | 161a862e-67d9-510b-99df-071a63d7f727 |  | note | – – – – – – – – – – – – – – – – –
label | 8d1f508c-a882-5b43-87f2-427d8b81d99a |  | note | CATEGORY: HP
label | ee61aa3f-9521-5d47-ad75-cb99b4d9e8d0 |  | note | – – – – – – – – – – – – – – – – –
label | 064db2df-4a20-5468-ac14-6ed2692dd7cd |  | note | RESPONSIBILITY: Nominated Authority
label | afe9a744-0055-5aa0-ad70-1936f4452c0b |  | note | – – – – – – – – – – – – – – – – –
label | 39a6aa2d-73a7-563b-b8b0-e724bf7b68e2 |  | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
text | 5767be11-91b6-5365-b741-93a4718f7cc5 |  | textbox | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | Construction Activities
checkpoint-status |  |  | checkpoint | 5.1 Formwork Design and Construction
label | f989043c-a888-5fea-9c7e-9cbe8ae78563 |  | note | REFERENCE:
label | 225bc97b-5721-52d4-8034-3bbadc309547 |  | note | IFC Drawings
label | 9ec08803-66ac-57f6-8a09-f55203642feb |  | note | 614.04
label | 39e6699b-ccb9-552a-967c-4fb263951423 |  | note | 614.05
label | 934dbe8c-169d-5f85-a46b-21ccdcb7ea31 |  | note | 614.06
label | 312d84a7-f950-5c5f-b317-b50a325bf7b9 |  | note | – – – – – – – – – – – – – – – – –
label | 0299bbb2-b569-5f9c-9544-2c50aa30cee9 |  | note | ACCEPTANCE CRITERIA:
label | 7907d739-3bfc-592b-b36b-cb8dfefd26c4 |  | note | • Designed and constructed in such a manner so it can be removed without damage to the concrete.
label | dcc4e3cf-41e2-5d75-89a7-7de97a78f25a |  | note | • Formwork to be rigid, watertight, braced, tied together & selected to achieve the required surface finish.
label | 3051bd3f-635c-5f9c-925e-472b09676885 |  | note | • Formwork shall not be placed where steel & fixtures cannot be inspected.
label | 425b575e-1805-58cb-9ab6-9da60ce912c8 |  | note | – – – – – – – – – – – – – – – – –
label | c555b353-6195-549b-bd31-a2d0c2686486 |  | note | METHOD: Document Review, Visual, Measure
label | 5353c29f-fe92-515e-9c1d-5a1561ab28ad |  | note | – – – – – – – – – – – – – – – – –
label | 07efec0b-f68e-5d3c-b789-6fbc8e29e10d |  | note | FREQUENCY: Each type of element
label | 144bab4e-15f7-50dd-bbcd-cf027e63d2f4 |  | note | – – – – – – – – – – – – – – – – –
label | bab9036a-ef98-5f2c-adec-0bb7b3174779 |  | note | CATEGORY: IP
label | 3937d2b2-6e77-5a1a-85e9-883216487af7 |  | note | – – – – – – – – – – – – – – – – –
label | 4e0ba5aa-c2c3-5319-a233-f10a482ab31b |  | note | RESPONSIBILITY: Temporary Works Designer, Proof Engineer, SE/PE/SPE
label | ebc8675d-8cde-5474-8a87-0c476fac7464 |  | note | – – – – – – – – – – – – – – – – –
label | 9f9c4298-1d1d-5fa8-bf05-389ea71fea76 |  | note | VERIFYING DOCUMENTS: This ITP
text | 0a7062ad-69fa-5266-ad9b-74c8b2d41e76 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.2 Formwork Certification - Formwork Inspection (Members Greater than 2m)
label | e0fcfe68-a581-5abc-bfe3-d3546aaf3371 |  | note | REFERENCE: 614.08
label | 9964a3b2-569e-52a4-b82f-601e3749902f |  | note | – – – – – – – – – – – – – – – – –
label | e08f99eb-c19f-5a83-8601-9f3e2b0b61ed |  | note | ACCEPTANCE CRITERIA:
label | 313efdac-cb4f-5c08-b47e-bc56fae6a1b9 |  | note | • The application of any load shall not proceed until the Certificate of Compliance - Formwork Inspection of the constructed formwork has been reviewed by the Nominated Authority
label | 8d83ac28-748c-5b02-ad7f-b165d16ebe14 |  | note | • Pile caps with heights greater than 2.0 metres
label | 62b106ea-1262-5daf-8074-7f50ec390b7f |  | note | • Any member for which self-compacting concrete is proposed.
label | 475d3dca-b7ca-55d3-8cc0-86b5343090ce |  | note | Attach: Attachment A
label | 43ad4170-69b1-59ab-8538-38840a803846 |  | note | Attach: Attachment B
label | fddf2cb5-0f69-5d43-adbc-8b665c1fa6f5 |  | note | – – – – – – – – – – – – – – – – –
label | 01a1924f-1740-5db2-9907-f1dff9187e67 |  | note | METHOD: Document Review, Visual, Measure
label | 5458ee80-9e29-53d0-b409-5ecf040e1d04 |  | note | – – – – – – – – – – – – – – – – –
label | 07c83501-d41f-5369-8b37-7608f7abec2f |  | note | FREQUENCY: Each element (where greater than 2m)
label | eef2a5fc-2be4-501f-a68a-9af88a2f254b |  | note | – – – – – – – – – – – – – – – – –
label | 5e7bdc60-6c9e-573f-9634-4e59a6b4f521 |  | note | CATEGORY: HP
label | 94524740-a166-5ac9-96cf-1d22a72d7dd5 |  | note | – – – – – – – – – – – – – – – – –
label | aaa188cd-aa66-59ea-9c43-89d4917fdf41 |  | note | RESPONSIBILITY: Temporary Works Designer, Proof Engineer
label | 94d4427b-aba3-5201-904c-70f195bbd6e6 |  | note | – – – – – – – – – – – – – – – – –
label | 984043e0-2959-52bb-86e5-5284ef600921 |  | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
text | ca1d067a-37d5-5aa0-b1e1-2492d6c4e0f2 |  | textbox | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 5.3 Formwork Certification - Formwork Inspection (Members Less than or Equal to 2m)
label | 8533ddc2-cbfe-5ad2-b9dd-0dba4b1ad828 |  | note | REFERENCE: 614.08
label | d3d30b71-1b76-5ced-bb34-d70716af06ba |  | note | – – – – – – – – – – – – – – – – –
label | cdb48712-4f35-5593-8d59-150b118a4c4c |  | note | ACCEPTANCE CRITERIA:
label | 04458d77-ca8a-5c97-ba2a-954a3324e395 |  | note | • The application of any load shall not proceed until the Certificate of Compliance - Formwork Inspection of the constructed formwork has been reviewed by the Nominated Authority
label | c641968d-06bb-59fe-8ed3-62cfeae83f43 |  | note | • Pile caps with heights less than 2.0 metres
label | 4ab4b83a-ca1d-5350-9f32-f8283908b83c |  | note | Attach: Attachment C
label | 88865b05-f395-5a9c-94da-88aabeb2d48b |  | note | – – – – – – – – – – – – – – – – –
label | ed636648-d3a2-5f49-b94d-584db1eee48d |  | note | METHOD: Document Review, Visual, Measure
label | 9f805cc6-339a-5d97-9a0d-6d7161c020cb |  | note | – – – – – – – – – – – – – – – – –
label | 5c528937-cad6-5b3c-befc-ed4ed8cdaeef |  | note | FREQUENCY: Each element (where 2m or less)
label | b15f0711-44b7-5db6-aced-10d3bdcf8817 |  | note | – – – – – – – – – – – – – – – – –
label | 0a9bfa5d-ba02-5153-a959-ad44904011a0 |  | note | CATEGORY: HP
label | e54dd52b-1367-5caa-ac51-9993dfa56b60 |  | note | – – – – – – – – – – – – – – – – –
label | b8a93224-619f-5426-a7b6-210363ecce49 |  | note | RESPONSIBILITY: Temporary Works Designer, Proof Engineer
label | 56b2d3d6-1589-5763-a8bc-101f0976bdf5 |  | note | – – – – – – – – – – – – – – – – –
label | d26c9106-d6e0-542e-adbc-7fce02ff3fd4 |  | note | VERIFYING DOCUMENTS: ConQA Hold Point Release
text | f9e8a1b3-e9d1-59bb-ad2f-bb693f3b9824 |  | textbox | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 5.4 Pre-pour Survey
label | e2da9334-2255-5c8b-b7ee-d75f00d8a313 |  | note | REFERENCE:
label | f5881060-ef34-5ac6-954c-5ff4d84d2606 |  | note | 610.47 (a)
label | 264e9db8-e178-5d8c-910d-7dc83977075d |  | note | Table 610.472
label | f47f9c17-59d1-5ae6-b843-c950b6273195 |  | note | – – – – – – – – – – – – – – – – –
label | bef58e38-821b-54ff-af2e-77a3a44cd706 |  | note | ACCEPTANCE CRITERIA:
label | 2b894aff-08e2-5b5c-ae26-851afeccc642 |  | note | • A pre-pour survey carried out by a surveyor.
label | 69c4e856-a22b-5505-a1ff-ffda3d9ee1b5 |  | note | • Erected formwork within the tolerances as per the table 610.462 as applicable to the element.
label | a8afea04-b18e-56b1-aa17-d9cfe7644f5b |  | note | – – – – – – – – – – – – – – – – –
label | 3d80ea93-709f-5b11-9305-5751e09a1a7d |  | note | METHOD: Measure, Visual
label | f90fac72-027f-57e0-a50d-0a51fc70be07 |  | note | – – – – – – – – – – – – – – – – –
label | 1ca91f2b-f160-5b4c-9827-65c9bae6ab37 |  | note | FREQUENCY: Each element
label | ccd5ba4a-d85e-5f79-8872-b951a625b5b9 |  | note | – – – – – – – – – – – – – – – – –
label | 7855acd7-4f97-53e5-a817-085f570030f9 |  | note | CATEGORY: HP*
label | 755a2c93-44d2-566d-ae90-22ec0941002e |  | note | – – – – – – – – – – – – – – – – –
label | 97ecbd8c-adf0-5ed5-8936-006b9f5204be |  | note | RESPONSIBILITY: Surveyor, SE/PE/SPE
label | df858dac-b1a0-5a85-aa0d-68fa06d27166 |  | note | – – – – – – – – – – – – – – – – –
label | 4b13eb06-f99b-5048-9957-6345c475cb6b |  | note | VERIFYING DOCUMENTS: This ITP
text | e5acf8c2-f406-5797-9445-d3ee66f404be |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.5 Reinforcement Placement
label | 946334a3-fbc6-5467-b276-f85d24ff0a32 |  | note | REFERENCE:
label | 8d625f43-d333-5a35-b53b-aa79b32345b2 |  | note | IFC Drawings
label | f4846816-7eda-51da-9fd4-36196006940c |  | note | 611.06
label | f5a45f27-fcb6-533b-84ab-02b10756c37e |  | note | 611.09
label | 905d251b-cfab-5a44-b487-0c353f24a694 |  | note | 611.10
label | 531cbeeb-8306-5780-8b3c-8d05eda6b3f1 |  | note | 611.11
label | d0e3c5e6-2ef8-5a19-b0f6-658e0d89453b |  | note | 611.12
label | 7a788079-4991-5d0f-92e8-1aff26712351 |  | note | – – – – – – – – – – – – – – – – –
label | eff62d22-7c38-54e9-be0a-db7a6eb1676d |  | note | ACCEPTANCE CRITERIA:
label | 379eaca9-ef85-5dac-938f-55baaae530e5 |  | note | • The correct reinforcement grade, quantity, size, orientation, location and spacing as shown on the structural drawings.
label | 13cf7a8d-dff6-5046-96e7-132e9f957c62 |  | note | • Projecting reinforcement is the correct length and location.
label | 5e51e022-0028-54f4-8805-8570afa0b158 |  | note | • Splice lengths achieve the minimum length and are in contact for this length.
label | 62d61194-84af-5f3f-8eb8-7a71e2cfff4f |  | note | • The reinforcement surface condition is free from dirt, debris and damage.
label | ec75959e-be82-5fc3-abb3-c74a154c5a8b |  | note | • The resulting cage securely held with sufficient ties to limit displacement or deformation during the concrete pour.
label | 31597d6b-f5cb-5603-bdbd-b9270ecd3d5f |  | note | • Minimum cover as shown on the structural drawings for each face has been achieved (including tie wire locations).
label | c20b77ee-cb69-5a2b-8345-27d91f9c8946 |  | note | – – – – – – – – – – – – – – – – –
label | 0d959bc9-1e60-58f5-bf1b-07027bd65d2d |  | note | METHOD: Measure, Visual
label | 7c021ee0-426c-53a1-a8cf-31c64ab3176b |  | note | – – – – – – – – – – – – – – – – –
label | 224c947d-c41d-50f5-baa7-c0727b356d58 |  | note | FREQUENCY: Each element
label | 04a01851-8309-554f-87ec-48bba7fda981 |  | note | – – – – – – – – – – – – – – – – –
label | ff4055ff-d7d8-5d3c-8a03-3111cbafa43e |  | note | CATEGORY: IP
label | 58a0d69e-a905-5513-be92-8a2dad6a7e87 |  | note | – – – – – – – – – – – – – – – – –
label | d514293b-fad4-53e6-bc27-854bba6b531e |  | note | RESPONSIBILITY: Foreman, SE/PE/SPE
label | 7c5ead58-6e21-5fc7-b2bb-8603f86a826d |  | note | – – – – – – – – – – – – – – – – –
label | d6cbaecc-f60c-557b-a0e4-6a220f60386d |  | note | VERIFYING DOCUMENTS: This ITP
text | ace4e8d2-cf74-5c41-80d5-c0bf0b580ee1 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.7 Cast-in Items
label | 867cd10e-9fa1-5126-aec3-f69c72b256d6 |  | note | REFERENCE:
label | b8749262-2713-5814-8b7a-c8e08854a61a |  | note | IFC Drawings
label | 52c108bb-fc94-56e7-8f96-76c7e39da906 |  | note | 610.47 (a)
label | fcf0d529-1cc4-5b40-8dc5-4dc061bb9955 |  | note | Table 610.472
label | eab73f90-f7a6-587e-9bed-7bca0adfa7ee |  | note | AS3810.1 Table 3.3.6.2
label | 3a68e729-61a7-55e5-8498-1514c4b015ca |  | note | – – – – – – – – – – – – – – – – –
label | 25c466ef-51b3-5911-b327-d3796665406f |  | note | ACCEPTANCE CRITERIA:
label | b7338832-9226-5bce-a052-cb4726d79475 |  | note | • All cast-in items are the correct type, grade, quantity, size, orientation and location as shown on the structural drawings and are securely fastened or restrained to withstand impact and pressure during the concreting operations to prevent dislodgement.
label | a5bf10ae-eb56-50c0-a6e2-2a18c4d3d6ab |  | note | • Any exposed threads, conduits, ducts or voids shall be protected by suitable means to prevent concrete or grout ingress.
label | 38d02f77-5f3d-505f-9165-86eddac98571 |  | note | • Tack welding of any cast-in items shall be performed by someone pre-qualified to do so.
label | f8648265-6675-59df-84c1-e1555b939944 |  | note | • Grout tubes shall be fastened at regular intervals to prevent kinking.
label | 681485d4-da3a-54d7-8b32-c6a05fac4e06 |  | note | • Placement tolerances to comply with the IFC drawings, if not specified, use the following:
label | 381e3254-5a0d-5d6d-8316-734789d9c303 |  | note | i. Bolts, ferrules, projecting bars & couplers = ±3mm
label | b7ccb225-8645-5f29-acd8-87a5011d69b7 |  | note | ii. Running dimensions of a group of the above = ±6mm
label | a45ffd1b-1d71-5a85-99a2-82c498ca147e |  | note | iii. Ducts and conduit location = ±12mm
label | ce23c99f-63b1-5f33-885e-bc6e34f94f65 |  | note | iv. Diameter of ducts and conduits = ±3mm
label | 25b0497e-b2d6-59c8-8c17-833d8b8905fb |  | note | – – – – – – – – – – – – – – – – –
label | 0360ec34-6d47-59d0-b54b-f9a8b988d5ff |  | note | METHOD: Measure, Visual
label | b9fa1471-a31e-5173-9e41-05ef2f4863f5 |  | note | – – – – – – – – – – – – – – – – –
label | 6272cf5b-191f-55d5-b48c-25b43cf93fdc |  | note | FREQUENCY: Where applicable, each element
label | f985c651-6dba-5bca-b354-06a0a7c0e621 |  | note | – – – – – – – – – – – – – – – – –
label | 82782dc1-0ba4-5cd6-b469-71737a08a887 |  | note | CATEGORY: IP
label | 5b40996d-7ef1-57e1-83e3-1c6028b061c1 |  | note | – – – – – – – – – – – – – – – – –
label | 0b4cda05-bbbb-5b60-8b83-586d77bf1af0 |  | note | RESPONSIBILITY: Foreman, SE/PE/SPE
label | 641161a9-6db2-536b-a155-e367156c3134 |  | note | – – – – – – – – – – – – – – – – –
label | b82b3d02-0202-5dbf-9e00-35f498cffabe |  | note | VERIFYING DOCUMENTS: This ITP
text | e0b8b495-b1cc-51a2-b989-4a7ff7ae63ee |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.8 Thermal Differential Monitoring
label | bb04dc58-efbb-50a2-951b-b6f8d90646d5 |  | note | REFERENCE: 610.22
label | 2e775b28-5b8f-5bcf-9367-d9272e671733 |  | note | – – – – – – – – – – – – – – – – –
label | ab406813-69d6-5023-9392-a77e7ca624df |  | note | ACCEPTANCE CRITERIA:
label | a19c79af-bb29-5c1a-826a-9aed6f1a0b5c |  | note | • Thermal differential monitoring thermocouples installed.
label | d97cd9d7-64f0-5675-8aa4-119f67ecbc11 |  | note | • Only applicable if the element has:
label | 1b32eb0a-3d19-5286-9654-b9a8f34a5f6b |  | note | i. the smallest sectional dimension exceeding 500mm
label | 4bf64596-e249-5224-810e-7fccd1ef9b97 |  | note | ii. one or more faces being restrained by previously hardened concrete or other external constraints
label | 4659e61c-49da-52e5-aed4-14630a3d2fbb |  | note | – – – – – – – – – – – – – – – – –
label | 79116c33-1704-5fa8-9463-f278aa0d8a82 |  | note | METHOD: Measure
label | d855ecbd-d9b8-5b41-8a5c-0456043d667c |  | note | – – – – – – – – – – – – – – – – –
label | db8b5cb6-e0fa-58ce-9095-262a9e334e0f |  | note | FREQUENCY: Where applicable, each element
label | 82a86f7d-de8a-511c-9647-1cd6a3c1c123 |  | note | – – – – – – – – – – – – – – – – –
label | c14e4684-9ecd-5e62-a698-00591e776e0a |  | note | CATEGORY: IP
label | 85fd0daf-202b-522c-8a3a-bda4bd4eef71 |  | note | – – – – – – – – – – – – – – – – –
label | f0dc3358-3d95-5882-9665-acbc01d7d8cc |  | note | RESPONSIBILITY: Foreman, SE/PE/SPE
label | 00cf5eb1-01e8-5a74-ad7c-ba4318123a23 |  | note | – – – – – – – – – – – – – – – – –
label | 9d178f9d-1769-50aa-bf77-2fcd9c90c410 |  | note | VERIFYING DOCUMENTS: This ITP
text | 6fe9a628-8965-576d-8ef9-c3190f3d936a |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.9 Pre-pour Inspection
label | e280bf7d-1f46-5dc5-8dac-88ed5cfa1b75 |  | note | REFERENCE:
label | c863f2a1-fd3b-5bab-a852-663592acfbb5 |  | note | IFC Drawings
label | c9d06aae-0ff3-5dd3-92e5-01d8eacdc9cd |  | note | 610.18 (a) (ii) & (iii)
label | 701d1f97-eb22-5fcb-a789-a5e283122816 |  | note | – – – – – – – – – – – – – – – – –
label | ea3fb228-a655-575b-b607-2e4f107d98c2 |  | note | ACCEPTANCE CRITERIA:
label | 1fb586fe-5db3-52f6-b260-2292d4898faf |  | note | • Evidence that the forms, reinforcement, electrical continuity and other cast-in items conforming to the requirements of this specification and the drawings has been reviewed by the Nominated Authority
label | ab4e2a15-425f-57e9-9fee-dcdb750cd443 |  | note | • All foreign material has been completely removed from the forms.
label | a2ab0acb-29b9-55f6-aa69-0c2cd6f6ee24 |  | note | – – – – – – – – – – – – – – – – –
label | f22ea55e-73e9-5bf4-bf35-694bf120569f |  | note | METHOD: Measure, Visual
label | 31207fa7-67c8-589e-b67d-dec9e6b8a733 |  | note | – – – – – – – – – – – – – – – – –
label | 0538fb70-86ae-5ff2-b904-c493a2ab187d |  | note | FREQUENCY: Each element
label | 4661ddbd-a134-505d-9620-321ff44698e8 |  | note | – – – – – – – – – – – – – – – – –
label | 5b243b78-9456-5c7d-a519-81d9d2298605 |  | note | CATEGORY: HP
label | caa873f6-2533-5ae2-be3f-38ea3beba202 |  | note | – – – – – – – – – – – – – – – – –
label | 491b9d42-c770-5125-9624-b4d5991d31d0 |  | note | RESPONSIBILITY: Nominated Authority
label | 2a0be196-46d4-5639-b096-1f83d6e7ad54 |  | note | – – – – – – – – – – – – – – – – –
label | 6c364b38-4938-52eb-baf2-7efc7bd6f576 |  | note | VERIFYING DOCUMENTS: ConQA Hold Point Release, Pre-pour checklist
text | b4e0e1c5-78c6-5890-8961-e58f0b10bbb8 |  | textbox | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 5.10 Weather Conditions & Evaporation Limits
label | 6a6b66b9-11c8-5bbe-9380-98975f264607 |  | note | REFERENCE:
label | 7e778dbd-0fe2-5dd9-9e0d-3cfd16a8e382 |  | note | Hot and/or Cold Weather Concreting Procedure
label | b992e6b7-4a9b-5895-ba36-ec10eb1403b6 |  | note | 610.17
label | 71f948cd-5a1d-5033-a53d-d93d87df9b78 |  | note | 610.17 (a) & (e)
label | b2d7b4ca-003f-547c-a741-b4e3f12940de |  | note | Table 610.171
label | 8fd85287-6d6f-59b9-92ad-90888b74a524 |  | note | – – – – – – – – – – – – – – – – –
label | 8c9ec6f5-aa7e-511e-bf6e-7da142956de0 |  | note | ACCEPTANCE CRITERIA:
label | 2786a2e5-83fe-5437-abbd-c38230b66157 |  | note | • All freshly finished concrete surfaces shall be protected where required from the sun, wind or rain, until curing is implemented.
label | 86fdb993-4769-5568-b3bb-9085193b96e5 |  | note | • The temperature of concrete, measured immediately prior to placing, shall not be less than 10°C or greater than 32°C.
label | c92f416d-f8d7-5d51-a051-da60e0792e4a |  | note | • The air temperature, relative humidity, concrete temperature and wind velocity are measured to determine the evaporation rate of water from the concrete.
label | a7dfdafe-8cff-58da-9645-4783b1730e73 |  | note | • When the evaporation rate exceeds 0.50 kg/m²/hr apply evaporation retardant at the rates specified on the manufacturer’s TDS.
label | da93e4af-f1d2-5908-be1e-66a0a6426e34 |  | note | Record: Required information on the Concrete Pour Record.
label | c1c81973-89ee-5e72-bfd1-f4e44b82d147 |  | note | – – – – – – – – – – – – – – – – –
label | 820f6d86-93b4-5537-99fe-d8268b5fc094 |  | note | METHOD: Measure, Visual
label | 0861ada3-9f2b-530d-9523-2cce9e7b7a06 |  | note | – – – – – – – – – – – – – – – – –
label | 8b80e31b-f382-5f1b-af0c-425de5f6b90c |  | note | FREQUENCY: Each element
label | 25faeda0-5465-5560-983a-f80b1243f6af |  | note | – – – – – – – – – – – – – – – – –
label | 9acd93b1-a42f-5e39-a98e-08cccaa1c785 |  | note | CATEGORY: IP
label | 43a366ad-10e7-5565-9b3b-db214d009c50 |  | note | – – – – – – – – – – – – – – – – –
label | 70068ffd-5059-5b52-92d9-8d2af6da476a |  | note | RESPONSIBILITY: Foreman, SE/PE/SPE
label | b9e58c15-9726-51b0-a9bd-71f63a951697 |  | note | – – – – – – – – – – – – – – – – –
label | e28dbd0b-fb00-5da6-97b0-4972dc26e8cb |  | note | VERIFYING DOCUMENTS: This ITP, Concrete Pour Record
text | 0b5f8fff-4b94-59d9-9656-f16950bd7459 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.11 Concrete Testing - Sampling Frequency
label | 1452cca1-dc72-57d7-86df-1b9e35738a50 |  | note | REFERENCE:
label | b3aceef1-ed07-5540-813d-cf7eb17017e0 |  | note | Site Sampling & Testing Procedure
label | 77ec71f7-092c-55f4-bfc8-fe63ada99426 |  | note | 610.16 (b)
label | de990f64-8e16-56de-adc9-a0c79673d991 |  | note | – – – – – – – – – – – – – – – – –
label | edac4b44-b1f8-5653-af68-e7e1c94185b2 |  | note | ACCEPTANCE CRITERIA:
label | b1ef43b6-82f7-5159-9d01-ed78d3a16956 |  | note | • Concrete cast in one continuous operation to be tested at a frequency as shown below:
label | ae1f0b4e-15d8-5a97-a34c-2be72805138f |  | note | ○ 0m3 to 10m3 = 1 sample
label | b484235e-bd93-5297-bb2c-7e9504bf928c |  | note | ○ 10m3 to 25m3 = 2 samples
label | 49eb095e-c166-5abb-9f7d-74e7910eaa63 |  | note | ○ 25m3 to 50m3 = 3 samples
label | 24752c47-ba31-5ba1-b109-c94625b018d8 |  | note | ○ 50m3 to 100m3 = 4 samples + 2 no. VPV cylinders.
label | 820e7551-6f72-552b-a01b-131c92c479eb |  | note | • For each additional 50m3 and additional sample shall be taken.
label | 1cadad57-646f-5da4-bd97-48cd3bfcf813 |  | note | • Where IFC nominates minimum strength development, ensure strength is verified by additional cylinder or other approved method (such as maturity testing).
label | d6857fdc-0baa-5fa6-a87a-3baf003f17d6 |  | note | • Each sample shall consist of 1 no. slump or spread test and 3 no. compressive strength cylinders minimum.
label | ebb543af-8d72-59b1-b425-77f1b2aee9a2 |  | note | • Compressive strength cylinders = 1 no. 7 day strength, 2 no. 28 day strength.
label | f2604a58-3560-5466-b450-41289d44e868 |  | note | • Note: Additional cylinders may be required for other purposes such as early trafficking or removal of formwork.
label | 9c87c8e4-90c0-5cf8-82a2-63037e36fe5a |  | note | Record: Required information on the Concrete Pour Record.
label | c6725099-cf05-522a-93f4-4840f210738f |  | note | – – – – – – – – – – – – – – – – –
label | bd2ae5bf-e653-52f7-8c9d-7d4fe6d454f0 |  | note | METHOD: Test
label | 25768238-1f26-5a99-9598-b08419abe6a6 |  | note | – – – – – – – – – – – – – – – – –
label | 0d6004ba-31cd-5a35-a011-c7be320106c4 |  | note | FREQUENCY: Each element
label | 096c0802-62a3-5914-959f-a09a39093caf |  | note | – – – – – – – – – – – – – – – – –
label | a3df8aff-f5bc-553c-b8ff-787251123c8f |  | note | CATEGORY: IP
label | e4c31a74-8be0-5363-8a53-23e5806a302a |  | note | – – – – – – – – – – – – – – – – –
label | 7b1e685b-9ac8-5493-91a3-1d562e6ff637 |  | note | RESPONSIBILITY: Concrete Tester, Foreman, SE/PE/SPE
label | a07abac0-3ffa-5fdf-8ca0-0bd1709de2af |  | note | – – – – – – – – – – – – – – – – –
label | 7fe2ece7-533c-57bf-a2e1-cf631f9b9e98 |  | note | VERIFYING DOCUMENTS: This ITP, Concrete Pour Record
text | 89c641c6-3d27-5e6e-b88b-76a275374e4a |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.12 Concrete Testing - Slump
label | 3ed606ae-8eb9-5202-a415-445af3193c61 |  | note | REFERENCE: 610.16 (c)
label | f2f03d88-ca8c-5301-a788-f2a6a270bf16 |  | note | – – – – – – – – – – – – – – – – –
label | 9132a241-bfa4-5a08-ba9f-a4f0ab85e75b |  | note | ACCEPTANCE CRITERIA:
label | 8af0e6ab-d1ed-52d0-aeb1-ab6551377fd7 |  | note | • Slump testing tolerances =
label | 32b74541-e010-5f55-bf6b-6de82399fc54 |  | note | <60mm = ±10mm
label | e44cc7a2-0e76-5f81-9a00-2365d3235430 |  | note | ≥60mm to ≤80mm = ±15mm
label | 4cc8d5ae-e808-51ea-a386-5a8e731ade93 |  | note | >80mm to ≤110mm = ±20mm
label | 6258816a-05e4-5463-b433-262a0fbcaaca |  | note | >110mm to ≤150mm = ±30mm
label | 7b33e682-64ef-5620-8ed1-b21e6c56dc09 |  | note | >150mm = ±40mm
label | c2498530-2ca1-5674-9316-2710b3796149 |  | note | Record: Required information on the Concrete Pour Record.
label | 97befe9a-65c8-5949-9ef8-59be5ed55d06 |  | note | – – – – – – – – – – – – – – – – –
label | 909cd082-9628-5875-9a10-1c93bb0d3b0f |  | note | METHOD: Test
label | 2d3d8eee-c3cb-5409-9f59-8f1bf1f17feb |  | note | – – – – – – – – – – – – – – – – –
label | cdc720da-70e2-5fdf-9198-b7c25a304b11 |  | note | FREQUENCY: Each sample of Standard or Superplasticised Concrete
label | a090156f-481d-5e75-8ed1-158287b61a0f |  | note | – – – – – – – – – – – – – – – – –
label | 9acfc5bb-fc3f-533b-bdaa-2231fb83227a |  | note | CATEGORY: IP
label | c4e877ac-032b-5a92-b0ff-cfb8d55b239b |  | note | – – – – – – – – – – – – – – – – –
label | becc38d4-0d8f-5c0d-874d-10cba0dd66cb |  | note | RESPONSIBILITY: Concrete Tester
label | 89da971c-5975-58b7-b7b0-992b9e2f74e3 |  | note | – – – – – – – – – – – – – – – – –
label | 0c7319b9-618f-53df-86a5-8e97e290528b |  | note | VERIFYING DOCUMENTS: This ITP, Concrete Pour Record
text | 15707944-a36c-5c81-8c00-99a29672c0cc |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.13 Concrete Testing - Spread, Passability & Viscosity
label | 964ac323-56ec-5716-a287-08c5c5344836 |  | note | REFERENCE: 610.13 (b)
label | e1edf20b-a90a-5f95-999f-83abbee0c2c9 |  | note | – – – – – – – – – – – – – – – – –
label | 7172fae8-f067-5887-89e5-0163d98f71b4 |  | note | ACCEPTANCE CRITERIA:
label | ea33fcd2-c10a-58c2-95e6-ebb08a11c621 |  | note | • Spread range = 550mm to 750mm
label | ed6e5811-652a-59ee-8aa9-66c68f778bbe |  | note | • T500 = 2 seconds to 5 seconds (to reach a spread of 500mm)
label | b6a16d87-e02f-54c0-b676-33035907c92c |  | note | • Passability = ≤10mm (aggregate height differential)
label | 2cadf85f-9196-5edc-8a29-bb7179b95ee6 |  | note | Record: Required information on the Concrete Pour Record.
label | 10211731-1892-5fd4-8427-03062c8fdbac |  | note | – – – – – – – – – – – – – – – – –
label | 6687948d-aa5b-5170-a76b-5a55d4536bd0 |  | note | METHOD: Test
label | 27c6086d-120b-5a23-8ec6-f81d642bb247 |  | note | – – – – – – – – – – – – – – – – –
label | 61f06bd0-c389-5f9c-bd12-641a71cfbe44 |  | note | FREQUENCY: Each sample of Self-compacting Concrete
label | 81203724-6d9e-53c7-aea6-1354b5117e79 |  | note | – – – – – – – – – – – – – – – – –
label | 6c090134-c042-5985-a379-3f907f675c66 |  | note | CATEGORY: IP
label | 684bd9eb-e14a-5c10-876a-e553a54a8048 |  | note | – – – – – – – – – – – – – – – – –
label | f4e783dc-6b9a-5c9a-9f5f-477f8c312298 |  | note | RESPONSIBILITY: Concrete Tester
label | 2e7c1181-b10d-5075-97be-c44e6cd3aeae |  | note | – – – – – – – – – – – – – – – – –
label | fa262b0c-d93f-5615-9b26-26d8a0610869 |  | note | VERIFYING DOCUMENTS: This ITP, Concrete Pour Record
text | ebf07ea4-09cf-5c56-a288-dafb48e5f45b |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.14 Concrete Testing - Compressive Strength Cylinders
label | d4d16b07-fa0f-54c0-9f3b-eb903a0c7261 |  | note | REFERENCE: Site Sampling & Testing Procedure
label | 2cb198d8-6769-517a-b96d-53f06eb3a223 |  | note | – – – – – – – – – – – – – – – – –
label | 7d4c5699-4f49-5525-a931-5d1ad12433a5 |  | note | ACCEPTANCE CRITERIA:
label | c31e9627-a352-54d3-b8c3-1f17d9893688 |  | note | • Correct quantity of cylinders manufactured per sample.
label | 44aff761-7320-5a4b-b331-75ed0c4927c1 |  | note | Record: Required information on the Concrete Pour Record.
label | bca6fea0-eb5b-52ea-9d32-b5d8f642fdef |  | note | – – – – – – – – – – – – – – – – –
label | 4e45590c-7700-535c-966e-1224d66f652a |  | note | METHOD: Test
label | a935b494-7df6-57bf-b545-af545c8f1ab2 |  | note | – – – – – – – – – – – – – – – – –
label | a0d2f127-494a-567a-ba4c-39cf08d956f4 |  | note | FREQUENCY: Each sample
label | 2c98093d-3c63-52b4-a55e-3d7604ca4f7c |  | note | – – – – – – – – – – – – – – – – –
label | f61e4e65-5043-5bc8-95c3-aaae69df8df2 |  | note | CATEGORY: IP
label | 41d04a20-b59e-5106-a6ec-19a212c8fd4f |  | note | – – – – – – – – – – – – – – – – –
label | 6a78ffea-800f-535d-9985-776b649ec151 |  | note | RESPONSIBILITY: Concrete Tester
label | 24a30eb6-73dc-54bf-b259-157780b51993 |  | note | – – – – – – – – – – – – – – – – –
label | f690b7aa-b4cb-50b9-84f1-a80e7aa92cd3 |  | note | VERIFYING DOCUMENTS: This ITP
text | 47ad1564-5f81-509d-b158-e861f1852689 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.15 Supply & Discharge Rates
label | 5fb3d281-49cf-5e7a-836c-a6531534c344 |  | note | REFERENCE: 610.13 (a) & (f)
label | 48b85441-3bf9-5f2d-8ca6-702f8f638b3d |  | note | – – – – – – – – – – – – – – – – –
label | 8bbcdff3-9295-528a-b597-4da7d210a1ba |  | note | ACCEPTANCE CRITERIA:
label | 81b2aec8-fd8b-5da5-92ae-d1b8b8bf4853 |  | note | • Concrete is supplied at an adequate rate to ensure no cold joints are formed.
label | b2753004-47b5-5c36-9cae-86f2be94f089 |  | note | • No water is to be added once discharge commences.
label | 21e87a76-cb17-5deb-810b-5632d54aca18 |  | note | • Maximum time between batching trucks is 25 minutes.
label | f0c62352-1f52-557b-9af9-75530de12c8b |  | note | • Maximum elapsed time for discharge (including compaction) is 60 minutes from batching unless the mix design has an extension using set retardants.
label | c4190844-30be-593b-ad55-5dc3d5fa192e |  | note | • Concrete that stiffens or is showing signs of stiffening shall not be used.
label | 4aeecf42-a903-56e0-b686-ae23614e4720 |  | note | Record: Required information on the Concrete Pour Record.
label | 17dfcb50-cfdf-533c-a6f8-23ec86163b81 |  | note | – – – – – – – – – – – – – – – – –
label | e3f2887b-9b1e-5bb2-aef8-bccd58fa5e6f |  | note | METHOD: Measure, Visual
label | b6c64d56-48b5-554c-9deb-85f4be729204 |  | note | – – – – – – – – – – – – – – – – –
label | ac5714bb-a84c-58ee-b713-3f1ead49f9ae |  | note | FREQUENCY: Each load
label | 2b486b31-ab25-55f7-a438-ccb78f741ca4 |  | note | – – – – – – – – – – – – – – – – –
label | 2e1eeca9-a1a5-5c93-8b12-f2bc8a5d4fba |  | note | CATEGORY: IP
label | 29c1c572-fe13-5068-9a36-bc9a52299c2c |  | note | – – – – – – – – – – – – – – – – –
label | a4e791f2-875d-5ca1-8a1b-8609236002b6 |  | note | RESPONSIBILITY: Foreman, SE/PE/SPE
label | 3a3276ba-7703-5c29-be6b-8570b0394c59 |  | note | – – – – – – – – – – – – – – – – –
label | 822fcb2a-634b-5ed6-bd12-96e0f571979b |  | note | VERIFYING DOCUMENTS: This ITP, Concrete Pour Record
text | 173f4b65-f265-5a39-89e9-3542804b079d |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.16 Placement & Compaction
label | 0d4f9af7-78d3-5f64-90df-5d0152a99ad2 |  | note | REFERENCE:
label | c8e769b7-464d-5490-a1ea-68f6078949fd |  | note | Placement & Compaction Work Procedure
label | b5882319-1af3-5665-a52a-cf6db4d15e0d |  | note | 610.18 (a) & (b)
label | e63938c0-86cb-54d4-8ed4-fd84d9cf9d3d |  | note | 610.18 (d) (i)
label | 0ee29b00-ccd9-50b8-8787-63af43a998af |  | note | – – – – – – – – – – – – – – – – –
label | b1e5d60d-d63f-5eca-85ae-82a6bbc664da |  | note | ACCEPTANCE CRITERIA:
label | 031eff1a-ab4b-5640-8a45-297da9cffa14 |  | note | • All concrete batches are traceable.
label | bcbac07c-ff86-5da7-a67d-64defa0ef1d6 |  | note | • Where concrete pumps are used, the initial discharge is pumped to waste until a consistent workable mix is discharged.
label | b1d4bc77-c44e-5ab9-8f1f-0891b20677f4 |  | note | • Concrete is not dropped freely from a height exceeding 2m.
label | df84a8a9-0455-5b3c-811e-19686b95f9e7 |  | note | • Concrete is not moved horizontally by use of vibrators.
label | 6688d6b3-e9e2-58cf-91da-9e38b0a01192 |  | note | • Adequate compaction is ensured
label | 688ff7f8-e3ec-5281-a6bf-95c5e573deb9 |  | note | • Care has been taken to fill every part of the form and force concrete under and around reinforcement and embedments.
label | 59a3aea9-9aa9-596c-b61f-c8e6bad08a86 |  | note | • Concrete layers are not more than 350mm
label | e6dd75e7-f622-5a7c-9a4e-2ddc533f4026 |  | note | • Internal vibrators are inserted at spacing not exceeding the manufacturer's zone of influence.
label | 1a5accbf-e60b-5229-bd8c-758205790647 |  | note | • Vibration continued at each point until air bubbles cease to emerge from the concrete.
label | 277ddb4d-6cce-5fde-a91d-2759da590c34 |  | note | Record: Required information on the Concrete Pour Record.
label | 394e32b7-75c8-5181-b792-ce7c5d1ee497 |  | note | Attach: Concrete Pour Record
label | 1770c552-de39-5d0d-b2c3-02ee8e219bdd |  | note | Attach: Concrete Dockets
label | 4e40b09b-fff2-5fb6-9972-ae4b021c3133 |  | note | – – – – – – – – – – – – – – – – –
label | 47408aad-08ae-51a9-9e27-177346f7a7f0 |  | note | METHOD: Visual
label | 2c196314-af18-531e-8ee5-0343e32abb48 |  | note | – – – – – – – – – – – – – – – – –
label | 3dd4d41e-dd8a-5107-bcf3-2d2bca6b03fe |  | note | FREQUENCY: Each load
label | 0b539478-52d8-51bf-90d9-34bc27c755e5 |  | note | – – – – – – – – – – – – – – – – –
label | 618019fc-9f21-5711-8444-1951dcedfa85 |  | note | CATEGORY: SP
label | 5a342f99-2ca7-5a82-b86a-c2f259081974 |  | note | – – – – – – – – – – – – – – – – –
label | 60d14922-8fbd-571c-bdb1-8e2f66fa4090 |  | note | RESPONSIBILITY: Foreman, SE/PE/SPE
label | 1e373b17-cd35-5673-9811-24601276a920 |  | note | – – – – – – – – – – – – – – – – –
label | 54f270fd-6e69-558e-b07d-f39fa0b4593b |  | note | VERIFYING DOCUMENTS: This ITP, Concrete Pour Record
text | 93f99e9f-3817-5a7f-b5c9-0c59667afe88 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.17 Surface Finishes
label | 17a07c3b-0c9c-5092-b8e7-5d7ef2440076 |  | note | REFERENCE:
label | e2cef093-8321-5ac3-a611-53d8bf9edaa1 |  | note | IFC Drawings
label | 6c0dab3e-2e7f-5f3e-bab5-d07d87c7ef35 |  | note | 610.31
label | 8fd2183c-f12d-53f4-bee0-06a89e6f3aee |  | note | 610.20
label | 20d6eb92-0442-5d03-9116-aaf308382cc7 |  | note | – – – – – – – – – – – – – – – – –
label | c411d54c-176a-57c7-be2e-90182feddfb7 |  | note | ACCEPTANCE CRITERIA:
label | 9d9d3be7-69da-5d0b-a70b-3781c1bca755 |  | note | • Surface finish as per IFC drawings.
label | c3ed7cc6-01df-5118-aabf-c407f9edbb2e |  | note | • Where surface finish is not detailed, the VicRoads class finishes will apply as per 610.31.
label | 67a5ff47-37c4-597f-9a66-569d677b9014 |  | note | • Construction joints shall be roughened in locations shown on the drawings - any proposed changes to construction joints shall be subject to approval from the Nominated Authority.
label | 6ce1c90e-f492-5529-9ca9-1196e5bfe540 |  | note | – – – – – – – – – – – – – – – – –
label | c87692a9-c00c-59ff-b8da-253f472063aa |  | note | METHOD: Visual
label | 402c3862-5dda-57a8-a8a4-b8d3d358dc3f |  | note | – – – – – – – – – – – – – – – – –
label | d204fd90-9d44-5a94-b125-f9f2f9d626be |  | note | FREQUENCY: Each element
label | 0b8b62b6-7744-5ac7-abfb-bcd5451bbe9d |  | note | – – – – – – – – – – – – – – – – –
label | ed60af92-ced1-5a03-b04d-9b68e1f7f9ed |  | note | CATEGORY: IP
label | af1e20d5-4c2b-534b-82ef-f9709d88f454 |  | note | – – – – – – – – – – – – – – – – –
label | ee023a2f-d3ff-5cbe-8b2b-a76fa6d50c7b |  | note | RESPONSIBILITY: Foreman, SE/PE/SPE
label | b2f8c654-292a-5585-9fc2-431117476bcd |  | note | – – – – – – – – – – – – – – – – –
label | 8f28e900-62ca-5520-ad77-7d71f05f09d3 |  | note | VERIFYING DOCUMENTS: This ITP
text | d7f93665-f5da-578b-bd5d-c13817fc1fc7 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | Curing-Top Surface
label | 0f59ca59-0855-5195-91f3-e6b3f4a0ccb6 |  | note | REFERENCE: IFC Drawings
label | f3a8c7d5-c866-584f-ba26-082ac553f93b |  | note | – – – – – – – – – – – – – – – – –
label | 83135336-c0d9-52df-989a-d6cffc1af6d1 |  | note | ACCEPTANCE CRITERIA: Top surface of the pile cap shall be water ponded for at least 72 hours following initial set. Alternatively the top surface of the pile cap may be covered with thermal blankets for at least 72 hours and then treated with a curing compound.
label | cb15502e-b351-5197-a712-c470379e0f0d |  | note | – – – – – – – – – – – – – – – – –
label | 3ee2a640-e409-57a9-94c0-08f37056f3ab |  | note | METHOD: Visual
label | c587fedb-3c02-5383-9280-ac83b8aad24c |  | note | – – – – – – – – – – – – – – – – –
label | b2e1b64b-c764-5d15-9879-f46cf581278e |  | note | FREQUENCY: Each element
label | 232ac7fa-ce98-53bf-ad7c-e4f4ef03edf4 |  | note | – – – – – – – – – – – – – – – – –
label | 151bc871-f552-5583-adf4-3ed2a6de4927 |  | note | CATEGORY: IP
label | 3e85173b-7f45-5332-8504-241633f7a556 |  | note | – – – – – – – – – – – – – – – – –
label | e26de55e-358a-5e24-add4-03b4854d2780 |  | note | RESPONSIBILITY: Foreman, SE/PE/SPE
label | 32bf79c4-56b3-5d29-a8c9-4b3b316ddaef |  | note | – – – – – – – – – – – – – – – – –
label | a9735ceb-0b84-56aa-9dea-d7cbe1dd7328 |  | note | VERIFYING DOCUMENTS: This ITP
text | 53aa5c70-ac4d-5699-9940-7498d29e940f |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | Curing after formwork removal
label | f6f11f89-22f7-54ea-93bf-6baa2863f8f5 |  | note | REFERENCE: IFC Drawings
label | d86b3c7c-492a-5e88-9f49-3a3cdb708f9a |  | note | – – – – – – – – – – – – – – – – –
label | 2bec6921-e611-5c27-9cf9-9e0d43a6c20b |  | note | ACCEPTANCE CRITERIA: After formwork removal, seal curing shall be applied to all exposed concrete surfaces to achieve overall of 7 days equivalent wet curing
label | 4d87184e-6d52-59d8-8086-c3255461b2b6 |  | note | – – – – – – – – – – – – – – – – –
label | 56fc2a62-c96e-572c-924c-e2b3e97411fb |  | note | METHOD: Visual
label | e3b195ee-1973-5189-8d0b-8542368aeb94 |  | note | – – – – – – – – – – – – – – – – –
label | a64ac6d9-3f14-541c-b9a9-5d37ab7204fb |  | note | FREQUENCY: Each element
label | 429d030c-0900-5167-b21a-89a2cff2c253 |  | note | – – – – – – – – – – – – – – – – –
label | 3dcbd85f-e14b-5d51-b187-9b055676da6c |  | note | CATEGORY: IP
label | 59694591-5214-5a1c-9d1c-784b13918392 |  | note | – – – – – – – – – – – – – – – – –
label | 9742d88e-cc87-5a12-806a-474f85bf936f |  | note | RESPONSIBILITY: SE
label | 324052a2-c7c3-58ff-b666-6bca3bdaa285 |  | note | – – – – – – – – – – – – – – – – –
label | 9aa0d60a-c753-5c98-82c0-25c0e9b618a2 |  | note | VERIFYING DOCUMENTS: Thip ITP
text | 1344b742-e566-5bde-9b5a-0b484f5d4a36 |  | textbox | Date Completed:
checkpoint-group |  |  | section | Post-construction Activities
checkpoint-status |  |  | checkpoint | 6.1 Thermal Differential Monitoring
label | 356309dd-0854-5aa7-99bb-5d0be899f125 |  | note | REFERENCE: 610.22
label | 3a1d378d-782b-5f50-a464-ba0ba53b8fe0 |  | note | – – – – – – – – – – – – – – – – –
label | ed121305-a9c2-5107-9a6e-058ca45afbca |  | note | ACCEPTANCE CRITERIA:
label | ec241c83-5d3d-5083-86e6-6338ebf6e009 |  | note | • Maximum thermal differential between the core and exposed surface not to exceed 20°C.
label | 28fb4f87-26b6-5fcd-9e66-7ca7eb267ac3 |  | note | • Only applicable if the element has:
label | 4d738641-cede-56f7-8582-987bf658f2e5 |  | note | i. the smallest sectional dimension exceeding 500mm
label | 11582b6a-e8c6-59f6-8d47-608a61da693f |  | note | ii. one or more faces being restrained by previously hardened concrete or other external constraints.
label | 434fd5a8-188d-55d5-ba34-31524038cbdf |  | note | Attach: Thermal Monitoring Report
label | 50074c5b-9659-550c-81d6-588c8cc2c9bb |  | note | – – – – – – – – – – – – – – – – –
label | d6264ead-8a8e-5cd4-bb9d-e068b35bfd18 |  | note | METHOD: Document Review
label | 80c635b0-404c-5b21-a422-ac8ca570e910 |  | note | – – – – – – – – – – – – – – – – –
label | 7a149964-6c2a-5455-863f-a228545cc1c6 |  | note | FREQUENCY: Where applicable, each element
label | b1084a03-96f1-58d7-af4e-a8c87e7fe81a |  | note | – – – – – – – – – – – – – – – – –
label | 436067ff-2155-5453-b6e5-37d9d3ea9056 |  | note | CATEGORY: IP
label | 16e06079-300c-5dbe-9714-f5529165d448 |  | note | – – – – – – – – – – – – – – – – –
label | d314f234-d118-5e30-be8a-8143ec72c46c |  | note | RESPONSIBILITY: Foreman, SE/PE/SPE
label | fb3a9b50-f028-5ee8-9706-7a0eddc7213e |  | note | – – – – – – – – – – – – – – – – –
label | 3c702d29-ac73-59a3-9d0d-35d758b5e4b9 |  | note | VERIFYING DOCUMENTS: This ITP
text | 3f014c2b-65a6-5642-b8b9-6e34d5e56540 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 6.3 Early Age Compressive Strength Test Results - Removal of Formwork
label | f97cc589-8fec-5062-8fe1-de15750ff948 |  | note | REFERENCE: IFC Drawings
label | e6ab1798-70ed-5d4f-85cd-a2868596af84 |  | note | – – – – – – – – – – – – – – – – –
label | 4899e8d1-d248-57f7-81fe-ef6e496c5ce8 |  | note | ACCEPTANCE CRITERIA:
label | 30527d45-e8d9-59e3-8bad-65ca8cfd1802 |  | note | • Formwork shall be removed not earlier than 72 hours. Formwork shall not be removed when the ambient temprature is less than 10 degrees
label | 469a9cba-d5df-5fdf-b745-d02370ce6c26 |  | note | • Where IFC nominates minimum strength development, ensure strength is verified by additional cylinder or other approved method (such as maturity testing).
label | a16d936d-78a5-5e5b-8890-f6b8e2b01cfc |  | note | – – – – – – – – – – – – – – – – –
label | 78a04093-465e-5156-b793-e8c0bfd57edc |  | note | METHOD: Document Review
label | 596e31f8-c8ad-5526-8de4-74c3000a4f9e |  | note | – – – – – – – – – – – – – – – – –
label | e27ddfde-9871-5004-8a5f-3c8db77bdfc4 |  | note | FREQUENCY: Where applicable, each element
label | 23e2d4eb-8907-5be6-8fe8-943e14e2e74e |  | note | – – – – – – – – – – – – – – – – –
label | 62923a3e-809d-51a5-a854-a24fd95bc2ae |  | note | CATEGORY: IP
label | dbffe1df-7998-5493-abf5-88963a7f6f9b |  | note | – – – – – – – – – – – – – – – – –
label | 68d281aa-1766-5001-95f0-ef0dccc71294 |  | note | RESPONSIBILITY: Foreman, SE/PE/SPE
label | 8cba79cd-9494-5a03-b0aa-d7c6a9056173 |  | note | – – – – – – – – – – – – – – – – –
label | a191609d-7c5d-5001-a8cd-833a7fe5212e |  | note | VERIFYING DOCUMENTS: This ITP
text | ef0dcd2d-42b0-51c7-add5-68e3297794de |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 6.4 Surface Inspection - Cracks
label | 7af2a1ca-edd0-50cf-b4d0-25c8ff806458 |  | note | REFERENCE: 610.24
label | 9b3f5b88-4753-5f79-9700-e49ae864145e |  | note | – – – – – – – – – – – – – – – – –
label | c99fc664-62a4-5d9b-9116-330a97d0bcf3 |  | note | ACCEPTANCE CRITERIA:
label | 6a6ff5d0-170c-50b8-9d54-5a2d03e0a974 |  | note | • No cracks greater than 0.2mm (exposure classification B1)
label | 5703a680-b7b7-5fa2-a7ad-83bfec04df25 |  | note | • If cracking is observed follow Structural Concrete Crack Repair ITP for investigation and repair.
label | 8c2403e8-3cff-5c64-8fbe-dd2c49ff0719 |  | note | – – – – – – – – – – – – – – – – –
label | 242108b2-3c07-5e1d-b91b-145a49991c1d |  | note | METHOD: Visual, Measure
label | f231c696-b940-5eef-b0ed-9226e721a9c4 |  | note | – – – – – – – – – – – – – – – – –
label | 212e4dc5-2b8c-5fce-b09d-5403e6af8bc3 |  | note | FREQUENCY: Each element
label | a6fd48ff-a784-5310-a993-8093acb9be37 |  | note | – – – – – – – – – – – – – – – – –
label | 1ede8642-d976-5d3b-9a79-a1f7deb4509e |  | note | CATEGORY: IP
label | 40e98d04-108b-587e-8e89-c78ef6a20996 |  | note | – – – – – – – – – – – – – – – – –
label | 6199c9a6-99c7-5b81-91bb-e1e178264d13 |  | note | RESPONSIBILITY: SE/PE/SPE
label | 31046137-8038-5021-871c-ea8440770daf |  | note | – – – – – – – – – – – – – – – – –
label | fcd1312c-1e35-5c03-9ca1-c0a91bf83d2b |  | note | VERIFYING DOCUMENTS: This ITP
text | a72b1611-5160-59af-8458-4ddac403bb37 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 6.5 Surface Inspection - Surface Finish
label | e6a402fc-ab6f-5891-952c-78f328e663a9 |  | note | REFERENCE:
label | db75d93b-ad09-533c-9665-f9e760e87861 |  | note | IFC Drawings
label | 4377cc09-261c-5c84-80dd-fee1f5990e41 |  | note | 610.31 (a) - (n)
label | afe5f5c2-78c6-5862-bac2-de7d772e749f |  | note | 610.32
label | c79b192d-c67b-5142-97a7-84325db9f2f4 |  | note | – – – – – – – – – – – – – – – – –
label | 792b2c99-730d-5d18-92ea-82f92262ba6a |  | note | ACCEPTANCE CRITERIA:
label | a05a05db-7317-5b5e-bcbd-a592788c4f77 |  | note | • Comply with the IFC drawings and specifications.
label | 8e247ef4-6538-5909-90f6-55ea757698ac |  | note | • Where surface finishes are non-conforming follow Structural Concrete Patch Repair ITP for investigation and repair.
label | 9a2e1b5a-73c1-53c6-9333-84ec9706743b |  | note | – – – – – – – – – – – – – – – – –
label | 16f057fd-985e-50c2-bf77-fa428d67a481 |  | note | METHOD: Visual
label | ec8aed63-ccf6-5415-b58e-82cba0e9f64c |  | note | – – – – – – – – – – – – – – – – –
label | ffb3dc50-b88f-5e12-804a-66f32eb94dc4 |  | note | FREQUENCY: Each element
label | 4047f76f-4ac7-5a73-ae20-fd2f1c01a675 |  | note | – – – – – – – – – – – – – – – – –
label | 720330b4-4cf8-528b-985c-ffddd05226d6 |  | note | CATEGORY: IP
label | 2e810ca5-a7f5-56a0-8d3c-cb47c8eaf465 |  | note | – – – – – – – – – – – – – – – – –
label | 9a3bfce9-5712-5422-918b-b18c6daf927f |  | note | RESPONSIBILITY: SE/PE/SPE
label | f589ae8a-8777-5683-88b0-abf07bb9e88e |  | note | – – – – – – – – – – – – – – – – –
label | f9995a79-33f5-5bb1-a044-1d63c5a5a3a7 |  | note | VERIFYING DOCUMENTS: This ITP
text | 09098749-cf7a-50f1-9863-cbefe3109834 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 6.6 Measurement of Concrete Cover
label | d90c9a97-a1bd-5ce1-b31b-953a7001895a |  | note | REFERENCE: 610.34
label | 64fe079f-e963-5d7a-b44b-d0498e581f24 |  | note | – – – – – – – – – – – – – – – – –
label | 64606b8f-7495-5cf8-97c2-7de09a704775 |  | note | ACCEPTANCE CRITERIA:
label | 7e6951aa-1f62-5bad-8eee-4a60c50f0d87 |  | note | • Concrete covermeter check one 3m2 test area for every 25m2 exterior surface area.
label | e28594b2-7851-5708-b4fa-38d9bd14ec73 |  | note | • Minimum 10 no. measurements recorded in each area.
label | fcf90f7a-ba4a-56f9-bbd9-4d07153ce411 |  | note | • Where low cover is identified, an assessment to evaluate the influence on durability of the structure is submitted to the Nominated Authority.
label | 3448decd-38cd-5ad8-bfa0-45de4a255012 |  | note | Attach: Covermeter Check Record
label | 5d5c3fc0-5b42-5082-96f6-f4f999de3b93 |  | note | – – – – – – – – – – – – – – – – –
label | a516d570-bacf-5413-b069-9f0d5de52c2b |  | note | METHOD: Measure
label | 9f2049a9-f1a9-5829-a66c-86645b7c600c |  | note | – – – – – – – – – – – – – – – – –
label | 71e9cdab-06d4-5f44-a310-cd1900bd8591 |  | note | FREQUENCY: Each element
label | 1d61ac57-f022-5380-99c6-a78a8234609b |  | note | – – – – – – – – – – – – – – – – –
label | fd45f040-b717-5f67-ba9b-9f038eab4f65 |  | note | CATEGORY: IP
label | 3872fd87-eabc-5576-9beb-999457bb5aa9 |  | note | – – – – – – – – – – – – – – – – –
label | 57b3deb8-1b42-5a95-95cb-106a84561b39 |  | note | RESPONSIBILITY: SE/PE/SPE
label | e9823746-001d-5e03-9d90-c8def7f44923 |  | note | – – – – – – – – – – – – – – – – –
label | c0ff9809-8794-5707-b7d0-cf2b28c7c4a3 |  | note | VERIFYING DOCUMENTS: This ITP
text | 0dc690be-cce7-5027-b417-c15f0c9084e0 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 6.7 Early Age Compressive Strength Results - Placement of Fill Against Concrete
label | 0a7ac88a-2c2f-5d4d-8ec8-0ca532e87171 |  | note | REFERENCE:
label | 3335375b-8e54-5988-9c08-3a691e7b4b18 |  | note | Early Loading and Trafficking of Decks and Approach Slab Procedure
label | 639c0854-dbf8-5a19-8af3-cd39f3c8d236 |  | note | 610.35
label | 52b0e50c-3a03-564a-9167-bb07c77e957c |  | note | – – – – – – – – – – – – – – – – –
label | f52006cd-023d-5ff9-b2ff-b0019240dda6 |  | note | ACCEPTANCE CRITERIA:
label | b4c24037-ba8d-5af5-a36b-e941fba59156 |  | note | • Fill is not placed against concrete within 14 days of pour.
label | 50b467be-8bcf-56c3-b1a3-7d2fbd8e0dd7 |  | note | • Proposed placement of fill prior to 14 days - follow the Early Loading and Trafficking of Decks and Approach Slabs Procedure.
label | e2c2bcfc-f99d-5704-a04d-3f5f14c434a1 |  | note | Attach: Concrete Test Results or Maturity Test Results
label | 6e17f5e7-5cf9-5063-bcf1-4f36d12d10ff |  | note | – – – – – – – – – – – – – – – – –
label | 35a04116-43ad-567d-a674-989837a91c83 |  | note | METHOD: Document Review
label | 9b3546cc-da67-5cdb-b386-224d4a5d9359 |  | note | – – – – – – – – – – – – – – – – –
label | b00b1924-dfde-5707-8dd8-bc25b83b9d2f |  | note | FREQUENCY: Where applicable, each substructure element
label | 9b888b61-781c-5235-8b84-9651109270e2 |  | note | – – – – – – – – – – – – – – – – –
label | 4ae874a2-27fa-5c4b-bfab-c438fa2e7eec |  | note | CATEGORY: SP
label | 712bca8e-a87e-56ed-8ae1-03d19815d806 |  | note | – – – – – – – – – – – – – – – – –
label | f81ca7ae-e75c-5d54-a202-1b87b884c3df |  | note | RESPONSIBILITY: Foreman, SE/PE/SPE
label | 82dc7313-25f6-52a4-9cb6-4feb84e9de1b |  | note | – – – – – – – – – – – – – – – – –
label | 1f000f91-cea3-55c2-bd6f-d8d665f269cc |  | note | VERIFYING DOCUMENTS: This ITP
text | 5cbf1990-a102-59ea-af70-b96de977f938 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 6.9 Compressive Strength Test Results
label | 373b180e-c399-5edc-a8c4-abb3f61811e8 |  | note | REFERENCE:
label | 9869a9ce-eda9-5827-94ce-e72550e4bb9d |  | note | IFC Drawings
label | 098f940f-0afa-59b0-b7e4-9569e3647286 |  | note | Table 610.05.051
label | be55346d-e7e8-5c7a-bb27-e3c930897c38 |  | note | 610.16 (g)
label | 6700f49c-7396-5368-a621-6bc904818859 |  | note | – – – – – – – – – – – – – – – – –
label | 1d81514e-4e3c-5b93-aef0-0444d34b0df2 |  | note | ACCEPTANCE CRITERIA:
label | 610b03b6-3b8e-5aaf-aa34-aabf2388e14d |  | note | • 7 day compressive strength to comply with table 610.051 for early indication that the strength is tracking correctly.
label | 73d90ec9-f250-5611-ae22-250045969eb4 |  | note | • 28 day compressive strength (average of the 2 no. cylinders) per sample comply with the design strength.
label | 0ab90d7c-2bc2-53b6-ae5c-57930c936fa9 |  | note | • Note: 1 of the 2 no. 28 day cylinders per sample may be as low as 90% of the required strength, so long as the average meets the required strength.
label | 017a3bc0-5288-5669-ae41-f9a378d966fa |  | note | Attach: Compressive Strength Test Results
label | 4d04eae6-118e-5e2d-b558-707aeb9379f6 |  | note | – – – – – – – – – – – – – – – – –
label | 865d27f3-fe01-599d-8851-7447ed2fe9f7 |  | note | METHOD: Document Review
label | 38bb6a54-bb5a-5f92-ad1d-779b11c8957d |  | note | – – – – – – – – – – – – – – – – –
label | 8e369124-91ed-5a4a-9172-d7e5890fcb6a |  | note | FREQUENCY: Each cylinder
label | 47b44ee6-ae73-552b-a691-d17f16a85286 |  | note | – – – – – – – – – – – – – – – – –
label | a3b6b4cd-dbd5-5221-987e-cefb73adce2f |  | note | CATEGORY: IP
label | 38ba2c6d-a04b-5903-bc77-6f7e3f124d85 |  | note | – – – – – – – – – – – – – – – – –
label | b65358ce-0191-5f0d-ab17-4df2762fe219 |  | note | RESPONSIBILITY: SE/PE/SPE
label | 42a82826-d716-51f1-951e-3fa4285d904b |  | note | – – – – – – – – – – – – – – – – –
label | aa45e722-6947-5e10-bdf8-a4e3c83a5a0b |  | note | VERIFYING DOCUMENTS: This ITP
text | bf7d65f5-9dac-52c1-b569-4197022fc37b |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 6.10 As-built Survey
label | d7e8ff7c-50e7-5cf4-ae8c-30caef91875c |  | note | REFERENCE:
label | 1599c253-205e-5c2f-98d5-fcac9a04600b |  | note | IFC Drawings
label | 44c95ad8-95a7-522a-9504-ba03ed72444c |  | note | 610.47
label | 9137267f-b496-5b42-9148-6e6c469c8735 |  | note | Table 610.472
label | 35b35e41-235a-543f-95d6-1e75a4cfb7eb |  | note | – – – – – – – – – – – – – – – – –
label | 6bc27c65-15be-58e9-b0af-b00736193966 |  | note | ACCEPTANCE CRITERIA:
label | fa72a6d3-7dcd-55bf-9ae0-1b8a76165ed2 |  | note | • Provide record of dimensional measurements to demonstrate concrete members comply with tolerances as per the table 610.462 as applicable to the element.
label | a38585cc-2b53-5fd5-a638-412b8714c8ba |  | note | Attach: Survey As-builts / Survey Report
label | bc890b9a-90cf-5e9d-9a6e-3eeb6b47677a |  | note | – – – – – – – – – – – – – – – – –
label | f0cc7762-626d-587c-972f-f96193708d07 |  | note | METHOD: Document Review
label | 7b877311-d6e9-59db-bf02-525d6cec871f |  | note | – – – – – – – – – – – – – – – – –
label | 85180d42-702d-55d9-ba6f-4060d963d8da |  | note | FREQUENCY: Each element
label | 0ba069b7-8b18-5188-8fd7-f9968134d756 |  | note | – – – – – – – – – – – – – – – – –
label | 47fbf245-1794-5764-b06f-e5dcd8e0adc7 |  | note | CATEGORY: IP
label | eada6bb0-f5f2-5cb9-a55f-de282b6da14e |  | note | – – – – – – – – – – – – – – – – –
label | e9d5238b-a695-5ca5-b526-ca5684857dce |  | note | RESPONSIBILITY: Surveyor, SE/PE/SPE
label | 278d7b5a-4688-5104-b20b-5ae2b62c4090 |  | note | – – – – – – – – – – – – – – – – –
label | 3297b5b4-0e03-5b00-907b-f9e2a70304a0 |  | note | VERIFYING DOCUMENTS: This ITP
text | 1a8d7f9b-471a-5a79-8a93-3f6d995ff20a |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 6.11 Non-conformance Report (NCR) Closure
label | 4bacd47b-0e8e-56d2-8534-1c2ceb44f669 |  | note | REFERENCE: MRPA Quality Management Plan
label | 1fc5516a-4c6c-5c6d-907f-23ae916f36f3 |  | note | – – – – – – – – – – – – – – – – –
label | 471483f7-2a71-5d17-92db-d2206b000461 |  | note | ACCEPTANCE CRITERIA: Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed.
label | 1ab24e33-7231-5ea5-9b88-36e2a2bd063e |  | note | – – – – – – – – – – – – – – – – –
label | 0df896f4-206e-5f2b-a5b4-a66006a2a6cf |  | note | METHOD: Document Review
label | 84b6316c-70ab-5af6-89f1-a11ecb983387 |  | note | – – – – – – – – – – – – – – – – –
label | fa93e875-9310-5968-a442-9757c30613ba |  | note | FREQUENCY: Once, prior to closure of this lot / element / Work area
label | e2692000-6e84-591a-a47f-d6ff9ba05d8b |  | note | – – – – – – – – – – – – – – – – –
label | ea7b90fc-8edf-55f0-a10a-d0e631908d4f |  | note | CATEGORY: HP*
label | c721f139-be9f-5d60-afa5-4d53a5fea655 |  | note | – – – – – – – – – – – – – – – – –
label | 048f8b1c-d034-561d-b120-66e8ad92953f |  | note | RESPONSIBILITY: SE/PE/SPE
label | 15392e12-8f34-5a83-8e86-77841115efef |  | note | – – – – – – – – – – – – – – – – –
label | a1505510-008d-5ced-9058-6eb9022f5619 |  | note | VERIFYING DOCUMENTS: This ITP
text | 41696981-4ed7-5a00-a6a1-217fc4d05550 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | Final Inspection
label | 223c6d4a-d884-5c06-a58e-f662e2e97602 |  | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed above have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
text | fb790ecb-babd-5b44-8ade-9caead5801ec |  | textbox | Name:
text | 4ea57428-8664-5b98-bc5e-0ee1638c1fc4 |  | textbox | Position:
text | 98e44f9c-2d50-5830-8b8a-9bdfb0330e1a |  | textbox | Date Completed:
holdpoint |  |  | signoff | Sign ITP
checklist-sectioned |  |  | checklist | ITP-CIV-CAMMS-Type A Fill - Road Rev 0 | itp |  |  |  | Yes | ITP-CIV-CAMMS-Type A Fill - Road Rev 0 | edb8489a-90f8-492d-ad04-69bd2b474d92
checkpoint-group |  |  | section | 1 - Referenced Documentation
checkpoint-status |  |  | checkpoint | Referenced Documentation
label | fa515f9e-725f-50f4-be1f-a6b2bc0541c0 |  | note | Document Title: ITP-CIV-CAMMS-Type A Fill - Road (Supply and Install)
label | 97300609-12a7-5628-bdc9-4acf6f82efef |  | note | ITP Description: CAMMS-Type A Fill - Road (Supply and Install)
label | 8734d226-5cc2-54e7-842c-e6bd4aa94f1b |  | note | Discipline (e.g. CIV/STR/RAIL: CIV-CAMMS-
label | 88c0230b-74ba-53fb-a74f-612a6c03abe6 |  | note | Revision Number: 0
label | 42ec91ab-4274-588a-852a-d85e0c89c4a4 |  | note | Revision Date: 18/08/22
label | 9ad2ab18-80fe-5bc2-9a88-69329621b123 |  | note | ITP created by: Victor Mira
label | 3bbb779b-ced0-53b0-a080-606bd8a2c886 |  | note | ITP approved for use by: Aldrin Guinchoma
checkpoint-status |  |  | checkpoint | 1.1 - Non Dependent
label | 018bec5b-629f-5969-8100-1e4c5529b396 |  | note | Reference - IFC Drawings
label | 8cbdf062-1778-5cd1-a8ab-1bdc122a39ff |  | note | VicRoads Standard Section 176 (Sept 2008)
label | 0c735927-5aa1-56df-931d-d58294b87d74 |  | note | VicRoads Section 204 (Dec 2015)
label | e438ad5b-24c0-53c6-bb70-2929e7257ec4 |  | note | Code of Practice RC500.20
label | 674407cd-00b1-590c-962b-d62a428b746b |  | note | Code of Practice RC500.5
checkpoint-group |  |  | section | 2 - Preliminaries-Materials
checkpoint-status |  |  | checkpoint | 2.1 - Material Conformance
label | 52961df4-f35e-5d8d-82bf-34d730d52a16 |  | note | Reference - Section 204.04 b)
label | 2b84e997-c714-5362-9f95-282d970aae03 |  | note | Table 204.041
label | f17b8615-076f-554f-8675-ff64038d2b4c |  | note | Acceptance Criteria - Type A material shall comply with the requirements of Table 204.041 and shall be free of topsoil, deleterious and/or perishable matter.
label | 608a3896-a8d7-596c-8ca9-4da4672c6af7 |  | note | • Assigned CBR≥%8%
label | e464fc1f-72d2-5a65-b593-44ed4d1dbca9 |  | note | • Swell ≤ 1.5%
label | 2d679f7b-5d52-5854-8eda-0aafbbb2da10 |  | note | • Permeability ≤ 5X10-9 m/s
label | 0a5eb090-42c7-5d1c-bc0f-e31a073c22f7 |  | note | Grading:
label | 5f88c050-5e87-5579-857d-b9d1b035bdd5 |  | note | • 75.0mm 100%
label | 3ae4cdd7-51ca-5616-9415-d04690a9e3fe |  | note | • 4.75mm 40-80%
label | 6d63dda9-dba8-543d-a9e0-f0985b64a6c6 |  | note | • 0.075mm 10-40%
label | eeac30c5-2700-5c75-acc5-6ba749e43852 |  | note | Reference: Material approval in Teambinder:
label | cda2de01-6a7d-5f28-8d63-0f36fc87acc9 |  | note | Method - Document Review
label | d6121d7e-6b4b-5ca9-a452-1c50748a0e11 |  | note | Frequency - Once, for each material type
label | 36ba39b7-95e1-5196-8164-087c2589eb83 |  | note | Category - HP
label | 42edf10c-17f6-57f4-9c84-f7aac02872dc |  | note | Responsibility - SE/Nominated Authority
label | 91575386-20e0-54b4-b069-1a864be914dc |  | note | Verifying Documents - Supplier Material Conformance Certificate
text | 65b4a28f-3523-5468-990f-692107621028 |  | textbox | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | 3 - Preliminaries-Documentations
checkpoint-status |  |  | checkpoint | 3.1 - Pre-Commencement of Fill Works
label | fb7772ea-2928-5d64-abab-0ee9b87e1cff |  | note | Reference - Section 204.10 (b)
label | ec3730a7-01bf-5755-960f-3f4e1b23bcd2 |  | note | Acceptance Criteria - Areas upon which fills are to be constructed shall be prepared for test rolling by the Contractor.
label | 9cce999f-8537-54a9-abae-acf605fbd48f |  | note | The Contractor shall not commence placing any fill on the prepared areas until the area has been reviewed by the Nominated Authority.
label | 81c14dc5-6a68-5f22-ade4-cbc5723ca03f |  | note | No fill shall be placed against or within 3 m of a structure until the foundation for the fill has been reviewed by the Nominated Authority
label | 24ce2e68-0372-52f6-add6-ee4eb9d97e6c |  | note | Reference: Subgrade Preparation Lot Number:
label | 72e592d4-a744-5a52-b960-ce3f7dbd89ba |  | note | Method - Visual Inspection
label | b2f64a05-cffb-5566-aa65-28e05d141005 |  | note | Frequency - Prior to commencement of fill works
label | 66dcfc49-21e5-5b0b-9a45-8c84d9cdfe58 |  | note | Category - HP
text | 13565228-a81e-5942-8c99-5229585c694d |  | textbox | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | 4 - Pre-construction / Pre-installation Activities
checkpoint-status |  |  | checkpoint | 4.1 - Survey Set Out
label | 30c10061-aff5-5bc9-aa94-796e7d07b33f |  | note | Reference - Design Drawings
label | d7969291-daf8-5361-8143-e74dd381be04 |  | note | Acceptance Criteria - Set out pegs in place and clearly mark out limits of works.
label | 3d48b9e5-abde-5723-941a-f5e4c9059610 |  | note | ATTACH: LOT MARKED UP LOCATION ON THE IFC DRAWING (LOT MAP)
label | 5258f66f-c674-5ad9-9712-5886318e988e |  | note | Method - Visual Inspection
label | fde88d89-17aa-5f75-a538-1e641c33e93f |  | note | Frequency - Each lot prior to commencement
label | 38ebe156-645a-5099-9e5c-f3ae8675baac |  | note | Category - HP*
label | e2c3ab2d-6b12-5b78-b5ff-8d02acdef3d9 |  | note | Responsibility - PE
label | 1334341a-5529-5ccd-9c25-b9a7fbfaf32f |  | note | Verifying Documents - Signed ITP, Lot Map
text | 816184eb-104c-568e-a94d-de06a313982e |  | textbox | Date Completed:
checkpoint-group |  |  | section | 5 - Type A Fill/Verge Activities
checkpoint-status |  |  | checkpoint | 5.1 - Placing of Fill
label | 10a30941-797a-5736-b71f-1d174ef825e3 |  | note | Reference - Section 204.10
label | 46a51074-c20d-517d-a240-16d0b558d981 |  | note | Acceptance Criteria - Type A material shall be spread and compacted in layers not exceeding a compacted thickness of 200 mm.
label | 24482d9d-703f-54e2-a8b8-6ae7925ac326 |  | note | Method - Visual
label | 9c54fdcc-ea3d-55ba-b52f-4835b17783d5 |  | note | Frequency - Each Lot
label | 7f36413a-813c-521b-b651-2c103157bf9e |  | note | Category - WP
label | ddf80980-2c39-5800-9501-c8dd434433d3 |  | note | Responsibility - SE/Site Supervisor
label | 4f873408-d309-5ff5-998c-542e364fd02b |  | note | Verifying Documents - Sign ITP
text | 8c36b90c-0958-598d-a959-7e727f65e2be |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.2 - Test Roll
label | f4a061de-a12b-5084-8de9-640029279965 |  | note | Reference - Section 173.03
label | 6eccbb57-8df9-5a8e-8c4a-555d3e5987c8 |  | note | Section 204.12
label | fbe291ce-3e8c-5377-b11f-08143e04a3a5 |  | note | Acceptance Criteria - Each Layer shall be test rolled in accordance with Section 173. Where site access is restricted, verify with a pickaxe drop or similar, at the Nominated Authorities discretion.
label | 3599d283-f2fa-5c96-b4e5-c23465d3e320 |  | note | Method - Test Roll as per 173.03
label | 6c992841-fee6-51b2-a3a1-32051004a40f |  | note | Frequency - Each Lot/Layer
label | 4edbbf9b-4847-569d-81a9-d9abebd8b03d |  | note | Category - HP
label | 400b3a64-12e9-5cbe-97ac-db2f2b596b27 |  | note | Responsibility - SE/Nominated Authority
label | 34e5ad96-641b-55d8-a8a2-24376cc9bb90 |  | note | Verifying Documents - Sign ITP
text | 5cbd3f60-fad9-5892-b980-c82082334a76 |  | textbox | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 5.3 - Compaction Testing
label | b8b3c8d7-33a3-58d3-a561-3e1930458ead |  | note | Reference - Table 204.131
label | a1dbf03b-67cd-5e63-882c-6939e036cee2 |  | note | Section 204.14 c)
label | ef6c5d7e-8572-5283-a992-28f525bcefc8 |  | note | Table 204.142
label | e34d5ef2-1a8c-53e4-9578-d8ed9e73838a |  | note | Acceptance Criteria - Testing as per 204. Ensure testing is tracked and reports available.
label | e295bf20-dffe-5b11-87eb-278ad1f8b7ed |  | note | • Standard Compactive Effort
label | b12f097d-95e1-5bf8-a832-916d5ca5c44c |  | note | • For work to be tested for compliance with Scale A or Scale B compaction requirements, the number of tests per test lot shall be six.
label | 425d90db-9612-5760-b6bd-f7b2abe0aeec |  | note | • For work to be tested for compliance with Scale C compaction requirements, the number of tests per test lot shall be three.
label | 2389cf5d-6466-526b-a6fd-0ec28abd17ea |  | note | • Compaction and Moisture content
label | ca29e7d1-606e-5b6e-a706-34843002790f |  | note | – Scale A: Characteristic Density Ratio 99%.
label | 63acc9df-b7b7-53ce-ae4b-0950afec8641 |  | note | – Scale B: Characteristic Density Ratio 98%.
label | 777c8f29-d538-5aff-94f4-75a846a360e0 |  | note | – Scale C: Mean Value of Density Ratio: 100%
label | caf2e321-d739-5cf9-a38f-59305f497b8b |  | note | • Lot size - the leser of one day's production or 5,000sqm
label | 34ef067b-3014-5764-a326-41fb4eae33a0 |  | note | ATTACH: COMPACTION TEST RESULTS
label | a720b536-e8fb-58ff-af18-e2db5f08069f |  | note | Method - Review Document
label | 2fb8878a-b625-5104-b78d-2b0da93eb7c3 |  | note | Frequency - Test the first 3 lots. Reduced min. frequency every 2nd lot of like material and work
label | 2d8e7252-3e96-5b79-a7c9-cecffb02c606 |  | note | Category - IP
label | dce3259c-fb0b-5538-bf83-c4df9ac3673f |  | note | Responsibility - SE/Site Supervisor
label | 553ac4b0-36df-50e9-82c7-104e7128387d |  | note | Verifying Documents - Sign ITP, Attach Compaction Test Report
text | a1d675cc-fc87-505f-aae6-a37cc84b600d |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.4 - Preparation of final surface
label | 6d01447b-a809-5b49-9af2-7f6e86402e30 |  | note | Reference - Section 204.15, 204.03 (g)
label | e767c8a5-0078-5476-bb7b-7926409953e6 |  | note | Acceptance Criteria - The top of the Type A material, Cut Floor Level and subgrade surfaces shall be prepared to level and shape within the tolerances specified in Clause 204.03 (g) to produce a smooth, hard, tightly bound surface, free from depressions capable of holding water).
label | 41f83b44-5488-5334-8481-d901ed8e7365 |  | note | Method - Measure
label | 69367945-9730-5217-96a0-204370fffeb4 |  | note | Frequency - Top layer
label | db8a951c-0e5e-5c3d-a387-76451ab7a69e |  | note | Category - IP
label | d8b8e5e6-d4fc-5027-a81b-ea5961c07630 |  | note | Verifying Documents - Signed ITP
text | edee2230-6168-54e2-be86-64039f426ab2 |  | textbox | Date Completed:
checkpoint-group |  |  | section | 6 - Post Construction Activities
checkpoint-status |  |  | checkpoint | 6.1 - Post Compaction Material Property Testing
label | bb0d89d1-f72f-56fa-bb92-16a96eac3fab |  | note | Reference - Table 204,041
label | 4ba0990d-0700-5429-9530-e31d7f1c83b4 |  | note | Table 204.141
label | 3d09453b-17b7-5880-9aea-b7ead27cdeb6 |  | note | Section 204.14 a) or b)
label | 3495ea21-f51b-5520-8229-c695eb0982fc |  | note | Acceptance Criteria - Material Properties (Not Applicable for Scale C):
label | 8b9c3047-19e0-5b46-8ad6-2e964479af81 |  | note | ○ CBR ≥ 3% and Swell ≤ 1.5%
label | 96daf3d7-a326-5738-8f56-e418b3ce3827 |  | note | ○ Max Permeability = 5X10-9 m/s
label | feb7e7a9-1c92-55d0-8223-39ca9ba5898c |  | note | ○ Grading:
label | 5fa340e4-ff15-5779-bf7f-383eee7cdac8 |  | note | – 75.0mm 100%
label | 9ab3deef-722e-5a2e-b455-8dcce7e3df30 |  | note | – 4.75mm 40-80%
label | 829356d0-435b-5216-b154-d6d62db69c1a |  | note | – 0.075mm 10-40%
label | f7ee26ef-22c3-535d-8a5d-7804c59aeab6 |  | note | ○ Max. PI x%Passing 0.425mm = 1000 , PI = 6 to 25
label | 9f738045-ba9a-5e24-b806-69cedc1a0f19 |  | note
label | 25504062-fe8a-5690-a0eb-38547679aea4 |  | note | • Scale A:
label | 2a177682-bfe9-5906-aa46-ccc53e5a4f9c |  | note | ○ CBR & Swell
label | b4c410a0-a85e-5091-8bac-6d98f55272b5 |  | note | – Initial - 1 Lot Test to determine Assigned CBR and swell
label | a1173ecc-851a-57da-9381-0effdde57a1d |  | note | – Reduced - 1 Single CBR test to confirm Assigned CBR and swell per every 2 lots
label | 8c3d11e2-6b56-528d-b00c-fc2e871d9f72 |  | note | ○ Max Permeability
label | 74c505de-bbc7-5273-b506-62746af86cec |  | note | – Initial - 1 test per 2 lots
label | d6c83e8a-ac42-54c0-80c1-2b7b81a2fcba |  | note | – Reduced - 1 test per 4 lots
label | 6d9cd051-887d-5067-bbc0-fd96db1ce0e4 |  | note | ○ Grading:
label | 46f33495-9e1a-5fac-9f82-073e283b5521 |  | note | – Initial - 1 test for each lot tested for compaction
label | 79608768-053c-5bfd-8049-cde5900b9910 |  | note | – Reduced - 1 test for every second lot tested for compaction
label | 5f3929d6-dad3-57d1-95d2-95f1894678c7 |  | note | ○ Max. PI x%Passing 0.425mm & PI
label | 1ab1c814-37fb-5d08-9f92-33705982d8a5 |  | note | – Initial - 1 test per 2 lots
label | 193ee824-1799-5758-b303-4f7723f48ed7 |  | note | – Reduced - 1 test per 4 lots
label | 098bac24-c5cd-5bc1-bf48-e1d25ee4703b |  | note
label | d7279bfc-b393-5cfa-ab42-7160757a8942 |  | note | • Scale B:
label | 86a07eef-1877-51e5-ab87-608df36ad50e |  | note | ○ 1 Lot Test to determine: Assigned CBR and swell, Grading & Max. Particle Dimension, PI and PIx%Passing 0.425mm and permeability.
label | 28b3d773-0acf-5f5e-92ba-1178e00303ea |  | note | ○ Where the first lot passes, no further testing required except where changes to the physical properties of the material are observed.
label | 30484dac-ef41-54df-be37-b2d52f2989ab |  | note | Attach: Post compaction test results:
label | af3528b8-d553-5b59-a0ed-04d6698192db |  | note | Method - Review Document
label | 5bc2f759-b240-56f4-9729-ffdcaf912423 |  | note | Frequency - Refer to Section 204
label | e8c7de5d-064f-53b5-9497-c5bd5514f29e |  | note | Category - IP
label | 17d676e5-45e6-5a7b-9ada-7246e5724141 |  | note | Responsibility - SE/Site Supervisor
label | 4f155af7-dd4b-5401-a95e-7421be4560a8 |  | note | Verifying Documents - Sign ITP, Attach Material Property Test Report
text | 6743d660-3b85-5d91-af3e-205f6367606e |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 6.2 - Survey Conformance
label | bf50e102-c79b-5e43-9ead-a105c4c57979 |  | note | Reference - VicRoads 204.03f,g and h
label | 9dce3e4e-1270-54de-96fb-348b5c43dd79 |  | note | Acceptance Criteria - The level at any point on the subgrade shall not lie more than 20 mm below a 3 m straightedge laid in any direction, except across a crown and water shall not pond at any point.
label | ae38df25-897c-5211-84ed-8f3f20faff9e |  | note | • Level tolerances Scale A:
label | cf950a01-4114-522d-b232-659392494930 |  | note | ○ Range x = +5, -15mm
label | ec92f603-63c1-5ad7-9c6b-aa1cce517b56 |  | note | ○ Max S = 12 mm
label | 6fb0b1b3-94df-56de-a37d-d50af6c924a7 |  | note | ○ 80 measurements per lot
label | 4ca8d217-17f9-5e23-b2ea-567ab48749ad |  | note
label | 58863008-f389-5761-b88c-f2aec5e8f9e5 |  | note | • Level tolerances Scale B:
label | da1a054e-c73a-5ca2-8952-d14a9f08a5fc |  | note | ○ Range x = +5, -25mm
label | 4a7fe63b-8db2-5fc8-835f-f7176415f404 |  | note | ○ Max S = 15 mm
label | 82f1e0b9-2d72-58b6-a143-c6cd3a2671d1 |  | note | ○ 40 measurements per lot
label | d8d3dcc7-5eab-52f7-8ccb-bc4fa9f60eb3 |  | note
label | 836d5878-3366-5c1c-ae12-9e6aa995e2d5 |  | note | • Level tolerances Scale C:
label | eeb0db66-f235-5c61-a58f-01840c674f38 |  | note | ○ Where Scale C is nominated, random levelling is not required; however no point on the subgrade surface shall be more than 10 mm above or 30 mm below the specified level.
label | f2420367-fc5d-5b83-8e4f-2025c87d0a56 |  | note | Method - Document Review
label | 1f514e32-32b8-5d3d-8186-64697b9ac3cd |  | note | Frequency - Top of Type A/Verge
label | 6a070776-b4e1-5a61-aa58-a915991d99ab |  | note | Category - IP
label | bb4f1859-acdd-56c6-be07-92c49dae9332 |  | note | Responsibility - Surveyor, SE/PE/SPE
label | 2ea5f4a4-9b1c-5598-9135-f0ba09b51584 |  | note | Verifying Documents - This ITP, Survey Conformance Report
text | efa91caf-46e3-52e4-814a-eb557dff8193 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 6.3 - Non-conformance Report (NCR) Closure
label | c799b033-002b-5446-8331-dbdd44ff462c |  | note | Reference - MRPA Quality Management Plan
label | 214394a3-4310-5345-904f-e4b3d5355fae |  | note | Acceptance Criteria - Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed in CAMs.
label | 39144b33-71e6-5f50-bd53-1ac47fd79396 |  | note | Method - Document Review
label | 17aa7abb-f4ef-58d5-aba4-81c2f9e26f39 |  | note | Frequency - Once, prior to closure of this lot / element / Work area
label | fa4f174e-e0a2-5337-8ed1-0fbe8c28359c |  | note | Category - HP*
label | 94fc5723-8787-5651-b0c4-0276d3d06a31 |  | note | Responsibility - SE/PE/SPE
label | 6f4190b7-97fc-592c-a29d-84b3c3218bf0 |  | note | Verifying Documents - This ITP
text | 54372667-9ea5-58d7-9f6e-46de2b7e2a23 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | Final Inspection
label | feaf9877-5850-5df2-9d17-a0caf19f37e9 |  | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
text | e930627d-27ef-5029-8a23-ede9b15893fe |  | textbox | Print Name:
text | eb09d6b2-026f-5443-8fb6-736bd2eff34e |  | textbox | Position:
text | 6e09ce7e-6aae-50ec-adbf-8cd2313eb441 |  | textbox | Date:
checklist-sectioned |  |  | checklist | ITP-008-CIV-Stormwater Drainage Supply & Installation | itp |  |  |  | Yes | ITP-008-CIV-Stormwater Drainage Supply & Installation Rev 0 | f0057fe0-c8e4-484c-80e0-9ef7aa4b232d
checkpoint-group |  |  | section | 1.0 - Referenced Documentation
checkpoint-status |  |  | checkpoint | Referenced Documentation
label | e2751394-2957-525f-b752-cd15f3e93bee |  | note | Document Title: ITP-008-CIV-Stormwater Drainage Supply & Installation
label | 5019af8e-450e-5050-9bb2-cd6c42de5ef5 |  | note | ITP Description: Stormwater Drainage Supply & Installation
label | 172f3998-4372-53a2-a02b-2e90fa989d1a |  | note | Document Number (in Teambinder): MRP-0000-MRPA-ALT-ITP-00XX
label | 046a2a61-0ee1-5330-b5bc-65f69d82c49a |  | note | Discipline (e.g. CIV/STR/RAIL): CIV
label | 4ad1f441-8313-5241-86b4-5bb4474713fe |  | note | Revision Number: 0
label | 384b60d7-b146-5da2-a856-88c9d9ef3c3a |  | note | Revision Date: [Date of approval]
label | 73c335ba-638e-5b45-9ac4-d99100aa5118 |  | note | ITP created by: Jon De Castro
label | 296996d7-91fd-5df7-a787-2d4629431844 |  | note | ITP approved for use by: Aldrin Guinchoma
label | 91595832-721e-5119-ae8a-d28c10ba08e0 |  | note | 1.1 - Non Dependent
label | b146aa0c-1173-5045-83e4-36d2901ee8da |  | note | Reference Documents: VicRoads Section 701 (May 2020)
label | 94bac89d-2576-5a14-96b6-f196f0de95c9 |  | note | Acceptance Criteria: N/A
label | e4ed74af-684a-51cf-908b-0deb33078edd |  | note | Method: N/A
label | 9a027dd9-91ba-5d2b-b96d-009adf96567e |  | note | Frequency: N/A
label | 340d6721-def1-50a3-abb4-c51cc399fb1d |  | note | Category: N/A
label | 449581df-0a10-5d08-953c-7e3c70046e44 |  | note | Verifying Documents: N/A
label | 4bc2b308-8c13-533a-bc48-602f09c8f6a9 |  | note | 1.2 - Non Dependent
label | 64360c7e-b6cb-58f2-83cc-41a1562d95aa |  | note | Reference Documents: VicRoads Section 705 (June 2021)
label | 257f28e8-437f-5aea-a9bb-ed5a7b97e8a1 |  | note | 1.3 - Non Dependent
label | 51272973-df6c-5283-8e84-e03d6fe6e451 |  | note | Reference Documents: IFC Drawings
label | 861f54ae-12f4-5da0-bdfb-516cef8f6498 |  | note | 1.4 - Non Dependent
label | b9d149de-1927-5fdd-8c27-d40776fdabaa |  | note | Reference Documents: CHK-001-CIV-Stormwater Drainage Pipes Installation Rev 0
label | 1396c4ce-335b-5b9b-ae1c-e665b2e91b77 |  | note | 1.5 - Non Dependent
label | b2fff9aa-850f-53bd-add0-e0d44437e8e9 |  | note | Reference Documents: CHK-002-CIV-Stormwater Drainage Pits Installation Rev 0
checkpoint-group |  |  | section | 2.0 - Preliminaries-Materials
checkpoint-status |  |  | checkpoint | 2.1 Drainage Reinforced Concrete Pipes (RCP)
label | 72dd290f-837f-55cc-bf3b-c55c6792532b |  | note | REFERENCE:
label | b40fed04-6b40-5613-8d60-834bac321bb1 |  | note | • Section 701.04
label | 98e98bdd-a9a6-5be8-8ccd-274a17ff2996 |  | note | • Section 701.05
label | 344ff1da-7654-5c00-bb93-6d2216a891d6 |  | note | • Section 701.09
label | 11c9af9a-5e28-578e-905c-56b2abc3e07a |  | note | ---------------------------------
label | 2b0c7c20-764a-562a-940b-fc7ace7496fe |  | note | ACCEPTANCE CRITERIA:
label | a40b56c2-df35-5041-83a3-13a3c183ac80 |  | note | • Precast reinforced concrete pipes shall be manufactured, supplied and installed in accordance with AS/NZS 4058 and Sections 701.05 & 701.09
label | 6aee0c3f-7898-5bf8-ad4b-cdb07916bbd0 |  | note | • Precast reinforced concrete box culverts shall comply with the requirements of Section 701.04
label | cda608e8-9a71-5970-a53f-084af8a5ad31 |  | note | • Rubber ring joints shall comply with the requirements of AS 1646
text | dc6fb512-378b-56a9-9222-8257568a81a1 |  | textbox | Enter: Teambinder Material Approval number
label | 8e9ca2b8-be43-5b28-a718-d10196777443 |  | note | ---------------------------------
label | 1fae7860-71c3-55bb-ad05-26274ff95d79 |  | note | METHOD: Document Review
label | 36d6ee04-2dc6-56d7-a667-2a1384d214cd |  | note | ---------------------------------
label | e9ef7a52-186d-513b-b0dc-bd2ec1e5163c |  | note | FREQUENCY: Each lot
label | 247263c0-6668-5b0d-9172-54f76c6c6edd |  | note | ---------------------------------
label | a1c990ac-0d23-5d4d-abe3-3da3063fb6c1 |  | note | CATEGORY: HP
label | f8f2e736-2e91-5c4c-96dc-8e96e1f32801 |  | note | ---------------------------------
label | 39700d8d-a5cd-5848-b825-1dacb76a395c |  | note | RESPONSIBILITY: Nominated Authority
label | 9f51a136-3f27-5f83-8258-406f04c4b7d0 |  | note | ---------------------------------
label | 68c7eee8-569d-5236-ba91-6a0e43aa5fa8 |  | note | VERIFYING DOCUMENTS: Teambinder Material Approval
text | 50bdf263-5863-55fc-a4bd-957d81ba3c17 |  | textbox | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.2 Drainage Flexible Pipes
label | 74632b10-4d0d-55b2-b026-a145b877657a |  | note | REFERENCE: Section 701.08
label | a7fc5cf8-dbe3-58a4-b6e4-471090697a38 |  | note | ---------------------------------
label | adf9f13d-323a-5212-94a1-aafd73f6fceb |  | note | ACCEPTANCE CRITERIA:
label | 543e0cfa-287b-5ea7-9b32-27c73e0753a5 |  | note | • Flexible pipes shall be supplied in accordance with 701.08
text | 17bc7a1c-0736-5058-a6bf-1f1f0742943f |  | textbox | Enter: Teambinder Material Approval number
label | 817618f7-1658-52b0-bfe1-c9aa134839ac |  | note | ---------------------------------
label | 837d8eaf-5751-5a78-817a-7c21618a16dc |  | note | METHOD: Document Review
label | b6e796b2-9a7a-57b1-9138-5d1bbb4ca446 |  | note | ---------------------------------
label | e77996f8-d4b1-5cc1-802d-0292c343e87d |  | note | FREQUENCY: Each lot
label | 35c33040-a2f6-56c1-b2e0-4cea343d982f |  | note | ---------------------------------
label | 639c70b9-886f-58dd-ade9-e449c110d2d6 |  | note | CATEGORY: HP
label | 98c15e25-c9c9-54c4-b803-a1172126e4e8 |  | note | ---------------------------------
label | de577255-0edd-506a-8684-9075564b54ca |  | note | RESPONSIBILITY: Nominated Authority
label | 49b7d6aa-8bca-5302-aea3-aed2dd02e2fd |  | note | ---------------------------------
label | ff81cd81-14d0-5ba0-b3aa-b499ee63244f |  | note | VERIFYING DOCUMENTS: Teambinder Material Approval
text | 5b40e90c-cbde-5e08-8cef-d1bf8e7198c7 |  | textbox | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.3 Precast Drainage Pit
label | 3fa0aa0f-3654-53b1-95e7-e835c3b9d8a9 |  | note | REFERENCE:
label | 25440711-896e-5641-8139-236b4990e065 |  | note | • Section 705.07
label | 7fa67d8f-a1b0-57fc-9c0b-ab13bcb7cc46 |  | note | • Section 705.04
label | fbb2fd70-a471-57a9-8309-49288930bfcd |  | note | • Section 705.09
label | 7913efe1-067a-5eb8-b434-c2cce846b0c6 |  | note | ---------------------------------
label | d0c7518e-795a-5b6b-97e6-83068391d03d |  | note | ACCEPTANCE CRITERIA:
label | cbedd37f-4f0b-5baf-b0a1-421932cb0e03 |  | note | • Precast steel reinforced concrete drainage pits shall be manufactured, supplied and installed in accordance with Section 705.07 & 705.09
label | 5aac7492-a3be-5911-bf7b-c6a1905831b4 |  | note | • All concrete shall be manufactured to the concrete mix design registered by VicRoads and comply with the requirements of Section 705.04. Concrete grades shall comply with Table 705.041
text | ec7b98e7-ccd9-5762-980b-4fa79177fb8f |  | textbox | Enter: Teambinder Material Approval number
label | ee4e8ff5-348a-5019-863b-8b683ef540a8 |  | note | ---------------------------------
label | aa19b129-af88-56dc-96e9-fa75c13f0330 |  | note | METHOD: Document Review
label | 7b82fcba-f576-541b-bd63-9f0cba858232 |  | note | ---------------------------------
label | b6375994-d9e1-5f5e-9836-4dbec8764120 |  | note | FREQUENCY: Each lot
label | fc1a170a-c961-540e-884a-315bc1a380dc |  | note | ---------------------------------
label | ae5a3819-e6e8-526c-884c-39bba251a6ac |  | note | CATEGORY: HP
label | 60189a5a-7b63-5d01-83a9-6122b149ece5 |  | note | ---------------------------------
label | 2d028e7d-af87-5a9f-82cd-f51f2dd5ced0 |  | note | RESPONSIBILITY: Nominated Authority
label | ec465bf5-5e4b-557c-830e-c7d3570135c9 |  | note | ---------------------------------
label | 90b1a268-19bd-5742-a620-60ba29befa23 |  | note | VERIFYING DOCUMENTS: Teambinder Material Approval
text | 5696ace7-acea-5890-a748-f8bb814833ac |  | textbox | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.4 Cast in Place Drainage Pit
label | 90301796-48c9-5307-93dd-0b2c24e1e5a6 |  | note | REFERENCE:
label | d32dde1f-0bef-5c14-9594-bdefb5005b12 |  | note | • Section 705.06
label | 9f6b36d2-b3a8-58cf-b6d1-caa407526fa1 |  | note | • IFC Drawings
label | 29239391-3d09-53e3-94d6-2342bd1b2e8c |  | note | ---------------------------------
label | 179ca199-6f23-528d-87ee-4b169f58d298 |  | note | ACCEPTANCE CRITERIA:
label | 3a261e5a-ee13-5c83-94a7-216b436379ee |  | note | • Cast in place drainage pits shall be constructed in accordance with the requirements of Section 705.06 and at the locations and to the dimensions shown on the drawings.
label | eb05070e-f6e1-5fdf-b6aa-692852f8efe6 |  | note | ---------------------------------
label | a3eeb1b6-98f4-5601-b509-8c7e7804a9cd |  | note | METHOD: Document Review
label | 2447fd27-2168-5814-9cd8-ec071f9ef28f |  | note | ---------------------------------
label | 55cfbef8-31f1-5cdd-b047-86e60e3c9a24 |  | note | FREQUENCY: Each lot
label | 3d84a244-333f-53c0-85b9-78cbce98aef1 |  | note | ---------------------------------
label | 578ae35d-16a7-5397-96a2-a5a2851f0a96 |  | note | CATEGORY: HP
label | 1c40ba4d-db0f-57e4-8b31-be58ea1caa65 |  | note | ---------------------------------
label | 6c24d75a-3e53-55ff-84ea-3dbac70469bf |  | note | RESPONSIBILITY: Nominated Authority
label | cb6b5aac-5409-5417-a934-811072fc1add |  | note | ---------------------------------
label | 8b68dbf4-5ebc-56d1-928a-c2162e0beb01 |  | note | VERIFYING DOCUMENTS: Teambinder Material Approval
text | 633abd7e-78ec-5cc8-b0d4-16eaf6397ed0 |  | textbox | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.5 Drainage Pit - Step Irons
label | 686f6058-be99-52db-8238-1e8179e6a39f |  | note | REFERENCE:
label | 4d856409-8bd6-5b83-ad2f-7d6c4e727559 |  | note | • Section 705.04
label | e8af6840-5858-58ee-92c1-8f064a9e1d93 |  | note | • Section 705.12
label | 93584fc6-7d99-58e4-bddb-dc2433650371 |  | note | ---------------------------------
label | 91d990cb-12f1-57e6-b300-69633f42166c |  | note | ACCEPTANCE CRITERIA:
label | aaedf0ec-4477-51a1-a3c3-27089038ec6c |  | note | • Step irons shall be manufactured by 13mm steel bar covered with polypropylene plastic in accordance with 705.04
label | 0ee6b4b8-6c20-59fb-ae6b-b016d11f4f08 |  | note | • Drainage pits greater than 1.0 m deep shall be fitted with step irons in accordance with Section 705.12
text | 00a03e3f-a75e-5ea8-958e-43d53d005200 |  | textbox | Enter: Teambinder Material Approval number
label | 75db50e3-a3df-50f6-8910-2bf5f23c241a |  | note | ---------------------------------
label | 3d91385f-1a44-5b19-b521-46b45340fa9f |  | note | METHOD: Document Review
label | 557bbb07-c9e8-572c-8e3b-7afaf630d9ee |  | note | ---------------------------------
label | f85923aa-ce1b-5b4f-9407-4402b4faa1fc |  | note | FREQUENCY: Each lot
label | f491e346-ba19-5481-87d2-9eb2c0bb1485 |  | note | ---------------------------------
label | f7422b37-791a-53d0-94eb-d935e5df7c50 |  | note | CATEGORY: HP
label | 5cc66eb4-216f-5b93-a323-fce1d4b8963f |  | note | ---------------------------------
label | 2209f915-d607-54b3-88be-8278724c2ff3 |  | note | RESPONSIBILITY: Nominated Authority
label | 9cc290ca-c270-5b8c-8663-bec5347d0d15 |  | note | ---------------------------------
label | c49db9df-28ba-5e0d-82de-a9f22ea0c5ab |  | note | VERIFYING DOCUMENTS: Teambinder Material Approval
text | 817b6f0a-ce4c-5671-bc7a-a6e5bbdd8726 |  | textbox | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.6 Drainage Bedding Material
label | 3b556434-e477-54d2-b1d1-7a88179818ea |  | note | REFERENCE: Section 701.09
label | b27a2c85-1d4e-5562-b15a-9d3389539b62 |  | note | ---------------------------------
label | d0f8924f-168d-5319-97ca-deb72c0c9de3 |  | note | ACCEPTANCE CRITERIA:
label | 17e61d0e-3e91-5c9f-a7b9-3e474eee8e06 |  | note | • Bedding Material shall be free from perishable matter, lumps and conform with the requirements of Table 701.091 and Table 701.092.
text | 0e5360ca-5dee-5a18-983f-1fc8d0ccff95 |  | textbox | Enter: Teambinder Material Approval number
label | 042933ba-2af5-57ae-8a55-b79ac51e0957 |  | note | ---------------------------------
label | e167d2b7-c37d-54cb-abe2-fd8bb7e96d45 |  | note | METHOD: Document Review
label | a1fad11f-1f34-5c4c-9a00-3492e0c597b4 |  | note | ---------------------------------
label | abb01105-0742-5c45-95c2-ac3cd7f43faa |  | note | FREQUENCY: Each lot
label | 655ab0e2-88d1-5b32-b272-dabf46a9a8f2 |  | note | ---------------------------------
label | b35d3f3d-56c2-5d8c-9451-f86a8d519371 |  | note | CATEGORY: HP
label | 080f1303-d61c-5d59-a97a-94882ef424a0 |  | note | ---------------------------------
label | c7f1f432-852b-5f95-9918-9ab8f8fd6a36 |  | note | RESPONSIBILITY: Nominated Authority
label | 88775c85-8a25-58ea-a97c-5d630e270aa2 |  | note | ---------------------------------
label | 663edf75-9bff-5b25-8bde-436300070a1f |  | note | VERIFYING DOCUMENTS: Teambinder Material Approval
text | 92178d96-9d01-58a9-9b1e-9d78e761c0c6 |  | textbox | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.7 Drainage Backfill Material
label | 2a3108e2-1b4d-5820-b7eb-c2996d1cca43 |  | note | REFERENCE:
label | fc3c85be-c6e3-5c84-ad09-7b980b7d4183 |  | note | • Section 701.09
label | 24e1d0f2-425f-5830-9ac7-e6547d64381c |  | note | • Section 701.19
label | 27265410-0ba9-5cda-9875-7095aa411b4c |  | note | ---------------------------------
label | f60e378b-03d0-5f53-b414-f86cab31f286 |  | note | ACCEPTANCE CRITERIA:
label | 2d8de61c-ae75-5f07-9171-aa922e19bdf0 |  | note | • Ordinary and Selected Backfill Material shall be free from perishable matter, lumps and conform with the requirements of Table 701.091 and Table 701.092.
label | 455b3605-80b4-59e2-a444-1690737d651f |  | note | • Where approved by the Superintendent, culverts in trenches may be backfilled to half the pipe diameter or box culvert height with 3% cement stabilised sand in accordance with Section 701.19
text | c5861fd6-e5eb-5d4d-854d-22e695fb7ed7 |  | textbox | Enter: Teambinder Material Approval number
label | 4a392498-198c-5889-9123-66992ad5b393 |  | note | ---------------------------------
label | e8919ef5-e9f6-533d-80b6-689169bdb7fc |  | note | METHOD: Document Review
label | cd265166-e4f9-538e-af3c-a22790cd8765 |  | note | ---------------------------------
label | 8c75de63-a7db-59ee-b6af-90b7cb014034 |  | note | FREQUENCY: Each lot
label | 81c79b49-dacd-5c81-a2e5-2c359424fa50 |  | note | ---------------------------------
label | 84872e85-7a9d-5586-b9aa-9033abd780e7 |  | note | CATEGORY: HP
label | 2acbaa76-7c19-5093-b234-e1cd3fa72639 |  | note | ---------------------------------
label | ca8bf2e0-3536-5fb8-abd1-22545ce216a2 |  | note | RESPONSIBILITY: Nominated Authority
label | b35beef5-a3ac-58b2-ad7e-d1f4e55ea944 |  | note | ---------------------------------
label | 4cc41ffc-2bee-572b-a742-6aeebb04e585 |  | note | VERIFYING DOCUMENTS: Teambinder Material Approval
text | 67e17d2f-a210-5871-bffe-13a1a9e1884e |  | textbox | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | 3.0 - Preliminaries-Documents
checkpoint-status |  |  | checkpoint | 3.1 Subcontractor ITP (where required)
label | 4911583c-93fb-50b5-90bc-8fb7134adfc7 |  | note | REFERENCE: Subcontractor ITP
label | b27a6cf9-e4d0-5eca-89eb-62cfd02ca5b7 |  | note | ---------------------------------
label | 947402dd-909a-544b-9006-f19d712ccba8 |  | note | ACCEPTANCE CRITERIA: Subcontractor ITP shall conform with the IFC Drawings & Relevant Standards & Specifications.
label | 7fd5184f-d403-54a1-bf39-62ef944cbdb5 |  | note | ---------------------------------
label | 61c2ace9-9865-527b-a9a1-48ab3ec95fc1 |  | note | METHOD: Document Review
label | d5d7fcd2-4259-5d1a-830d-2347f5cc2f6a |  | note | ---------------------------------
label | 529b37b6-c0d5-5e32-911b-a21eaf550ff8 |  | note | FREQUENCY: Each Lot
label | ce562711-8d44-58c8-87b8-b9bdc481ff36 |  | note | ---------------------------------
label | e2d703cc-9d58-5284-a17c-77dd05dd377f |  | note | CATEGORY: HP*
label | a5fb7c65-4553-5b66-8ae5-ec498bd0b5cd |  | note | ---------------------------------
label | c3af47a3-5832-5b02-96d9-65a66d8279be |  | note | RESPONSIBILITY: PE
label | b422fd10-14f2-58ed-a579-d90c0f8fbad4 |  | note | ---------------------------------
label | d4df0739-d035-5cba-b797-034b9f5cbd24 |  | note | VERIFYING DOCUMENTS: Subcontractor ITP
text | 9c14985f-bb42-5b07-a893-5772e3b29b43 |  | textbox | Date Completed:
checkpoint-group |  |  | section | 4.0 - Pre-Construction Activities
checkpoint-status |  |  | checkpoint | 4.1 Survey Set Out - Pits & Pipes
label | f5ba4c92-cc56-54f1-93cd-82da408a1099 |  | note | REFERENCE:
label | d012c4a9-46ad-567c-9376-62731d8a86b7 |  | note | • IFC Drawings
label | 7196cbdd-aeee-5b1f-8d4b-2ab9f7c49ec3 |  | note | • Section 701.10
label | fa558275-abca-52fd-80b4-b8cd7e1bbbf8 |  | note | ---------------------------------
label | 1ca25bbe-f672-5b46-a588-020f6cf83c95 |  | note | ACCEPTANCE CRITERIA:
label | d11320fd-309c-5134-a390-3aa3c0350691 |  | note | • Prior to commencement of excavation for the culverts the Contractor shall confirm the position of all culverts with the Superintendent.
label | ad8abb4f-53cf-534e-8cf3-ef8ef160b6cb |  | note | • Survey activities undertaken to ensure and validate the plan location, height and line of pits and location, invert level, plan of pipes in accordance with design documentation and 701.10
label | e9a8a5a9-8020-5be6-9a37-211601238514 |  | note | ---------------------------------
label | 1b31f3d2-7587-5b30-aa7d-b2f0b8dced6d |  | note | METHOD: Survey
label | cc658ed6-675a-5790-aabd-003421d47e5d |  | note | ---------------------------------
label | 1178068a-96f7-53a8-a9ae-93b90d4c80f7 |  | note | FREQUENCY: Each Lot
label | 880ed773-b9a8-5779-a571-f084df55c4c5 |  | note | ---------------------------------
label | 11d65277-f8e5-5097-b39d-98d3c5708271 |  | note | CATEGORY: HP*
label | 6d620ee5-0d15-5a80-8aa3-a8affd9bfeee |  | note | ---------------------------------
label | 8293ff39-44e1-58e6-a454-5028fc97ccf5 |  | note | RESPONSIBILITY: PE
label | a6d5aeec-bc8b-5323-ae46-3279c5532d30 |  | note | ---------------------------------
label | fbccf4c4-0d12-56b5-91b3-cd0a75e016d9 |  | note | VERIFYING DOCUMENTS:
label | 7b9bec99-d0d0-5727-8d10-c7b39e7f7dd0 |  | note | • CHK-001-CIV-Stormwater Drainage Pipes Installation
label | 999708a8-e016-55f2-890b-75999ded1f21 |  | note | • CHK-002-CIV-Stormwater Drainage Pits Installation
text | 666545f8-f8ba-5137-880c-aff036702ebb |  | textbox | Date Completed:
checkpoint-group |  |  | section | 5.0 - Construction / Installation Activities
checkpoint-status |  |  | checkpoint | 5.1 Pits - Excavation
label | d9090fdd-20ad-574e-8465-0fc76d6f5392 |  | note | REFERENCE:
label | b2fb1d38-ad86-57c2-a4fe-4e249c3ba8b0 |  | note | • IFC Drawings
label | ff6aab59-1004-507d-b41c-c92389eca0c8 |  | note | • Section 705.05
label | 07357c1a-ad93-57a1-bcff-53b39d7449af |  | note | ---------------------------------
label | 6a9ad102-9a8b-5ef0-85fc-72194a727375 |  | note | ACCEPTANCE CRITERIA:
label | 9723be50-9eb1-5960-89c7-e4d9303ce6e8 |  | note | • Excavation shall be to the depth indicated on the IFC drawings or as necessary to secure a satisfactory foundation. Precast pits shall have min of 400mm clearance from all external faces of the pit to each face of the excavation.
label | 3fd052ce-8ab8-5acd-935d-61bb562d313c |  | note | ---------------------------------
label | 6bcb8219-be37-5ec4-8596-22d502197a5f |  | note | METHOD:
label | ed5836a0-3b4d-57ea-9928-65fda8bd97e7 |  | note | • Visual inspection
label | f778cf7b-43c3-55cc-8c6d-5050fa41ea0b |  | note | • Measure
label | 54c3e994-a8c3-5121-8ad4-0bae986d1312 |  | note | ---------------------------------
label | 6117072c-8781-5de9-a09c-90055cae3de7 |  | note | FREQUENCY: Each Lot
label | 6ab9f6c1-74cc-5859-a285-90784ccdc5e4 |  | note | ---------------------------------
label | 9df2089c-fe42-5439-911a-96de66dcaadd |  | note | CATEGORY: IP
label | 99ebbc6d-5b9a-5bdb-aad6-64b137d629c5 |  | note | ---------------------------------
label | c47408f1-aa41-5ed9-b9e4-fc8a772b29c4 |  | note | RESPONSIBILITY: SE
label | 17840d3f-8e91-5c48-8a40-caf49203d41c |  | note | ---------------------------------
label | 9d6156fa-5482-54d7-a75c-08faa1c3b2ea |  | note | VERIFYING DOCUMENTS: CHK-002-CIV-Stormwater Drainage Pit Installation
text | 21ce4176-f476-5cb7-b3b4-8786edc6890a |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.2 Pits - Placement of Bedding Material
label | 31c53472-11b3-5ea8-90d0-9b6295344c08 |  | note | REFERENCE:
label | d1f4ed0a-390a-5d64-8fff-f32bdd169efc |  | note | • IFC Drawings
label | 8251bb28-f753-5518-a071-24aa07b84189 |  | note | • Section 705.05
label | 4088c04b-2a32-5f61-8494-4940f767c0b4 |  | note | ---------------------------------
label | 0c93b7d2-5155-5e6d-bb96-a7b406cbe4a2 |  | note | ACCEPTANCE CRITERIA:
label | cfbbc8ec-f843-5872-b19e-ee905ebb832a |  | note | • Bedding conforming to to 701.09 shall be supplied, placed and compacted to a thickness:
label | 7a029243-e41e-5bc5-b5ee-2ac20b5c2aa3 |  | note | > 80mm for clay foundations
label | 64946dcb-f321-501b-8940-fe690480fb3b |  | note | > 150mm for rock foundations
label | 1347c019-6ded-56b7-bdda-346edd321bb9 |  | note | ---------------------------------
label | acf5346a-8895-5d77-9a26-e9b8a53decb2 |  | note | METHOD:
label | 783c6881-47e2-546f-99b4-d634d11512fa |  | note | • Visual inspection
label | 45dc97f8-fc22-54cf-a93e-fb63f5968537 |  | note | • Measure
label | c0e3c5ba-247f-5c41-8eef-06312b5a8056 |  | note | ---------------------------------
label | e244410e-73e7-554a-8e3d-304bc94691fe |  | note | FREQUENCY: Each Lot
label | bbefca17-2c8c-56ca-a1c6-d5ec0f120bca |  | note | ---------------------------------
label | afdcaee1-a6b2-5b3b-83c7-9892b89538c8 |  | note | CATEGORY: IP
label | 9105a25f-7422-549c-9f3c-6e7899512131 |  | note | ---------------------------------
label | 0a7356e2-7656-5b31-8d08-0582297fe0cd |  | note | RESPONSIBILITY: SE
label | c9bf96c4-eccc-58fc-9402-f1d721830cdc |  | note | ---------------------------------
label | 8eac134a-b2f9-5f68-942e-bf6edc4db7ea |  | note | VERIFYING DOCUMENTS: CHK-002-CIV-Stormwater Drainage Pit Installation
text | 0cb20ae2-0cbd-5c45-8651-aab785e419ab |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.3 Pits - Bedding Testting
label | 58015304-b47a-5dcb-8e63-1b5366b71454 |  | note | REFERENCE:
label | fbb39d7b-166a-5429-9ba6-e3794056d6fa |  | note | • IFC Drawings
label | 98e08fab-5ef6-5e13-8efc-405449648e42 |  | note | • Section 701.20
label | c869aed3-abb5-534e-b11b-a37b84e91434 |  | note | ---------------------------------
label | ecc32a69-4377-5963-908e-c1d2d66609ee |  | note | ACCEPTANCE CRITERIA:
label | d71a11cf-2663-55c1-9466-4f3436604f19 |  | note | • Test a minimum of 20% of all lots for each culvert. (Lot = 1 layer of bedding). The number of tests per lot shall be three
label | 04f1304b-0429-5c02-a464-9b94114bac8c |  | note | • Bedding shall be compacted to refusal using hand held mechanical equipment and material (Swell ≥ 2.5%) and mean moisture ratio of 92% between the completion of rolling and the placement of overlaying layer
label | 3d011ec3-b5c5-5d60-960b-f353bc090509 |  | note | ---------------------------------
label | 67472862-948d-59d6-9ae3-893190402d83 |  | note | METHOD: Compaction Test
label | df4b8302-29aa-5d8f-9fc7-4d668b975e4b |  | note | ---------------------------------
label | 6b90db13-b6a2-5f68-b7a5-4f74326cb37f |  | note | FREQUENCY: Each Lot
label | cdaf2f4a-01fd-50cd-ac8d-e4f025a8bd54 |  | note | ---------------------------------
label | 48f92296-0c1a-5f58-8c74-25d7b3ebff21 |  | note | CATEGORY: IP
label | 01636edf-4548-5d1c-a7c9-479b3b299495 |  | note | ---------------------------------
label | 36c42651-5d48-5a30-87b7-f43235165080 |  | note | RESPONSIBILITY: SE
label | 62ab82be-7424-5077-b7ce-3cdb53682e9c |  | note | ---------------------------------
label | bc13b31b-3670-57f4-b551-d406f28e5f2a |  | note | VERIFYING DOCUMENTS: CHK-002-CIV-Stormwater Drainage Pit Installation
text | 4334dded-8720-5ca5-99d1-fcab46763d81 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.4 Pits - Placement of Precast Drainage Pit
label | fc8fc2d2-523a-50d6-bd8d-24cc8985752e |  | note | REFERENCE:
label | 6a4bcd2e-35f6-5e24-b510-32a48b630a8c |  | note | • IFC Drawings
label | a2bc7f20-2bbe-5d13-b0c5-09248044e7a0 |  | note | • Section 701.10
label | 4fd3f9ae-f79a-50b6-a149-c8be2d0c2ac8 |  | note | ---------------------------------
label | abe61a0e-57fd-5d0f-9c44-4bc2bb6b958f |  | note | ACCEPTANCE CRITERIA:
label | 1ee6d1a9-d3cb-5cff-bb83-695222db36cf |  | note | Survey pick-up to verify:
label | 93c14a19-a150-5749-9a13-357eb6769bb0 |  | note | – Plan location of pits, other than offsets to kerb line or barriers, to be +/- 100mm
label | f25cae3b-fb64-5643-9fd6-da22e4fafb31 |  | note | – Offset of entry pits required to match lines of kerbs or barriers ±20 mm
label | c4ce9071-fd21-58e2-bc5d-498600b96446 |  | note | ---------------------------------
label | 08ec9d15-d893-5ef2-a073-52191af6d8c5 |  | note | METHOD:
label | f5f9d7b6-d086-5965-bf5d-29862501fc7f |  | note | • Visual inspection
label | f57bbef0-a546-58a5-a633-fedd60ebf00a |  | note | • Measure
label | e1f7ec90-d422-5a20-8c36-6868f8356c46 |  | note | ---------------------------------
label | 55be9116-7b3a-53f1-868b-523c03354ccd |  | note | FREQUENCY: Each Lot
label | 8192d9f8-1159-5b8d-a6eb-6e3e3c4ecf0f |  | note | ---------------------------------
label | 2c1cec38-fd99-5bc9-980a-1a49b6cf11f9 |  | note | CATEGORY: IP
label | 12ae1edf-90b2-5558-b420-7199426444d0 |  | note | ---------------------------------
label | 7367cf72-0c0e-5bde-9cc9-0efd8cb1360e |  | note | RESPONSIBILITY: SE
label | b54cac99-1c84-51ba-a74a-f0cd1e3883f3 |  | note | ---------------------------------
label | b25a37a9-ea3e-5f78-97dc-a4aa964fc6f1 |  | note | VERIFYING DOCUMENTS: CHK-002-CIV-Stormwater Drainage Pit Installation
text | 88643f05-573b-5120-b5cf-b6717c9425e8 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.5 Pits - Cast in Place Drainage Pit
label | 6a41d046-af65-5037-8980-e1d220046d61 |  | note | REFERENCE:
label | 480f1597-f5e5-572e-9506-938acafddbf8 |  | note | • IFC Drawings
label | 78b5d320-b9b7-5d27-924f-8e8251040c13 |  | note | • Section 705.06
label | 443d4c39-096b-512b-9a77-57ebddcd702d |  | note | • Section 610
label | 74b91421-f758-532c-970c-d2cc10ef2d53 |  | note | • Section 611
label | 1cbbf914-680c-5824-af60-ced3bd7c8b93 |  | note | ---------------------------------
label | 50b697c0-d19a-5729-b33f-4c9bb71c879a |  | note | ACCEPTANCE CRITERIA:
label | 6d2e4778-e3b9-50dc-bba3-a62361723dac |  | note | • Cast in place drainage pits shall be constructed at the locations and to the dimensions shown on the drawings and in accordance with the requirements of Section 610 and 611.
label | 138b769d-13e1-5533-90f7-b1f61a97b9a6 |  | note | • Cast in place drainage pits shall not be constructed with fibre reinforced concrete (FRC).
label | 850e07cf-4722-5568-86d1-27f2b67b5229 |  | note | ---------------------------------
label | ac2da850-40c9-5f26-af2e-35e300fb11d9 |  | note | METHOD:
label | aa2b47f2-88f5-532c-94f2-0714686a63fd |  | note | • Survey
label | 2a7cfc41-3d6e-59ec-a527-bead44b3f325 |  | note | • Measure
label | 19f81144-3789-576c-8d65-c05e51268bba |  | note | ---------------------------------
label | f6786af2-8cd2-59ae-aa68-f6c2e11d5011 |  | note | FREQUENCY: Each Lot
label | 5f9d7abd-2cec-5cd1-8e34-1d8877bdfb52 |  | note | ---------------------------------
label | 241381ae-c821-5989-8644-3a5e65096baa |  | note | CATEGORY: IP
label | 8e8aa289-4a2a-5f07-8504-139d01468310 |  | note | ---------------------------------
label | 8d879b05-c46f-5380-bf4e-a9db394761e9 |  | note | RESPONSIBILITY: SE
label | 913053a1-49f8-52b0-9926-b2bd8294e017 |  | note | ---------------------------------
label | 73233301-a44d-56a8-b1f8-bd99be4f1d7d |  | note | VERIFYING DOCUMENTS: CHK-002-CIV-Stormwater Drainage Pit Installation
text | f7a6aad5-4a6b-50ae-8575-698f9ec04125 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.6 Pits - Jointing & Drainage Connections
label | 37a20f1c-dd86-5a5f-8dbc-955d58b44456 |  | note | REFERENCE: Section 705.11
label | 8ac5cde8-8fad-586f-9a13-c872aa78c138 |  | note | ---------------------------------
label | 27a806fa-e7ea-5301-a3c9-c77d2a03669d |  | note | ACCEPTANCE CRITERIA:
label | 737b3cde-62f9-5761-bf7f-80814adeca7c |  | note | • All connections to drainage pits shall be neatly made in accordance with Section 705.11.
label | 182a0ade-2c04-59d3-86c1-392008fd953e |  | note | • Openings into drainage pit walls to facilitate drainage connections shall be neatly saw cut to the required size not more than 50mm greater than pipe diameter. Breaking out of holes is not permitted.
label | 1bc08f59-49ed-5ff9-871d-f2b2e6ee8f5b |  | note | • Drainage pits shall be replaced if circumferential or longitudinal cracking occurs as a result of installing holes or if the hole exceeds the pipe diameter by more than 50 mm.
label | a83a08ed-a1a5-5974-884a-b2c728ab428e |  | note | • Exposed reinforcement shall be coated with an approved epoxy treatment to prevent corrosion prior to rendering around the pipes.
label | ff05fe47-c5e9-5fc8-9854-8725f04a3d9d |  | note | ---------------------------------
label | 519bd56b-5f17-560a-b7da-f508f6cf04fd |  | note | METHOD:
label | 509664a4-ae43-55b1-a57a-261e9a97afdc |  | note | • Visual inspection
label | 81113ca8-2859-5e49-b107-b0deab2f891a |  | note | • Measure
label | 367c97fe-3c21-5e9f-ba4c-cec7674d17b0 |  | note | ---------------------------------
label | a120acf8-587b-5396-9d04-9b7a0f42ea24 |  | note | FREQUENCY: Each Lot
label | be2d93c1-ce9c-56c4-8b28-cca8e101eb95 |  | note | ---------------------------------
label | 0c664acb-adb7-5b7e-85f2-e62921d77b7c |  | note | CATEGORY: IP
label | c5658ad7-1cb9-52f7-9243-df29ac789a36 |  | note | ---------------------------------
label | 5429ee84-215f-58b9-8284-96ca994e66b3 |  | note | RESPONSIBILITY: SE
label | 390611d0-7862-5d03-ada4-f8f608a03421 |  | note | ---------------------------------
label | 1ef9014c-87d4-5e9c-90f0-e180fef5e6be |  | note | VERIFYING DOCUMENTS: CHK-002-CIV-Stormwater Drainage Pit Installation
text | fb493ab1-a11f-5bcc-be4a-6c59d5888421 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.7 Pits - Shaping of Floor
label | 2d260c04-8767-53a7-b1ef-f8e02cbe78e1 |  | note | REFERENCE: Section 705.13
label | 492b4301-d3b1-590c-922a-76f713b00d25 |  | note | ---------------------------------
label | f50f0028-0120-5203-8910-0c4b2395c670 |  | note | ACCEPTANCE CRITERIA:
label | 3d73c0b9-4cef-5771-84f4-bc2a09f49fb2 |  | note | • Drainage pit floors shall be smoothly shaped from the inlets to the outlet for a height of one‑third of the diameter of the outlet pipe with cementitious mortar in accordance with Section 705.13.
label | 6e0a229f-bf35-5be8-bd8d-ec02c7b7967a |  | note | ---------------------------------
label | 8493535f-9e12-5a70-b2b8-8043aaa9f7b7 |  | note | METHOD:
label | 117a3e63-4fc1-5b23-b312-d36205c27915 |  | note | • Visual inspection
label | 3c591d15-90a7-5e30-b143-e60edcc45a1e |  | note | • Measure
label | 2e2520e5-16bc-5f50-a8a3-e51c426b9c71 |  | note | ---------------------------------
label | d410eecc-49a1-5c40-8472-649ed2b02173 |  | note | FREQUENCY: Each Lot
label | 0381907f-b328-59a3-b289-4b8ae428475a |  | note | ---------------------------------
label | b14e852e-4df1-5b86-85bd-4217b6bda365 |  | note | CATEGORY: IP
label | dafebe31-2ed9-543d-bc38-7743bf581d17 |  | note | ---------------------------------
label | c8553e28-168f-5cb8-b365-98ecd2591065 |  | note | RESPONSIBILITY: SE
label | 122ec5c8-4882-5ce8-b51f-584187a6f567 |  | note | ---------------------------------
label | 7eb7c4ec-f1ed-58e3-bc7d-16c18841dc65 |  | note | VERIFYING DOCUMENTS: CHK-002-CIV-Stormwater Drainage Pit Installation
text | 1c778f64-a650-51af-bebd-0142fbab4275 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.8 Pits - Step Irons
label | 6eccb508-780e-5415-9e3d-cc70915ef4d9 |  | note | REFERENCE:
label | 68980c60-1036-518e-9dd6-795ee4e782c5 |  | note | • IFC Drawings
label | a1659860-abd7-5238-a38c-4902ef8b6bf1 |  | note | • Section 705.12
label | eed30823-6e84-55b2-9ea5-b9010ed1c62b |  | note | ---------------------------------
label | 0241ae25-cd02-5144-8134-9921b1172310 |  | note | ACCEPTANCE CRITERIA:
label | 2a2014d0-bec8-5300-94b4-e48ea40d247b |  | note | • Drainage pits greater than 1.0m deep shall be fitted with step irons in accordance with 705.12. Ladder rungs shall not opbstruct openings and that water does not discharge on them. Step rungs do not come within 50mm of the top of the riser.
label | b65f2e42-5a58-5aa4-87fc-865936f7d0eb |  | note | • Step irons of an approved proprietary type shall be installed in accordance with the manufacturer's instructions.
label | b558c6fc-fe9c-5a7a-b07c-986617df6e65 |  | note | ---------------------------------
label | 0110630d-54b2-5394-a126-9878236fd338 |  | note | METHOD:
label | f052a075-0598-53d2-b2b3-5481f636c2c0 |  | note | • Visual inspection
label | 695f4266-2cd4-5204-82b0-ee1438525598 |  | note | • Measure
label | 6deba9e0-af83-58db-86c8-cd93af2e944d |  | note | ---------------------------------
label | 362b5101-5022-5604-9b84-2288858c376a |  | note | FREQUENCY: Each Lot
label | 7945e76e-8122-5224-9ad0-a8b5d16cd2f3 |  | note | ---------------------------------
label | 84a5ed44-3046-5cd7-b6aa-bbc8575354db |  | note | CATEGORY: IP
label | 22532fd9-60f2-5602-9b4b-9b25e291542e |  | note | ---------------------------------
label | fdd309df-22a4-5e2a-98ae-64bc7f9f55e3 |  | note | RESPONSIBILITY: SE
label | ab8398d0-9064-57c9-9b04-63a2e9597abe |  | note | ---------------------------------
label | c123437c-027d-5cde-ad91-6b1cdbd2055f |  | note | VERIFYING DOCUMENTS: CHK-002-CIV-Stormwater Drainage Pit Installation
text | f5d5a723-4b4e-51cb-bbae-8b8d60de49e0 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.9 Pits - Fitting of Covers
label | be80c5b3-d487-56e9-896a-3c933721141b |  | note | REFERENCE:
label | 4fbea3a6-ab89-54a0-9601-d8ca75f18992 |  | note | • IFC Drawings
label | 4c11ada6-8eff-548e-a557-36fd9f4f09c0 |  | note | • Section 705.17
label | 91b9d085-2092-5d2f-9a1d-32bd54b21d3c |  | note | ---------------------------------
label | 613caead-f73d-5c43-9b50-c09753dfdd31 |  | note | ACCEPTANCE CRITERIA:
label | 08a3f876-d840-58fb-8c99-6ec4ecb97de4 |  | note | • Frames for drainage pit covers shall be cast into the top of the drainage pit or bedded on fresh mortar, 5 mm thick, consisting of two parts of sand, one part of cement and sufficient water to produce a mix of suitable consistency.
label | 1b19124d-3855-5eae-b733-afcc5434dce8 |  | note | • Height shall be within 10mm of the design level.
label | 319dac53-38ba-5592-90f1-67fd8167bb48 |  | note | ---------------------------------
label | b68971a4-fc65-5986-a69a-77a1ea51ecb4 |  | note | METHOD:
label | 71770c54-5b1f-5739-a4a0-10416de0cd0f |  | note | • Visual inspection
label | 1340edc4-88bd-550b-86cc-cb64ded3807c |  | note | • Measure
label | 592bd8fa-db20-5acf-a5b2-f6ea7473330d |  | note | ---------------------------------
label | 4a53ff84-6fa1-5bc9-bd70-dc3d607a2f0f |  | note | FREQUENCY: Each Lot
label | 14cc3f04-7a89-5143-920a-768d140beb68 |  | note | ---------------------------------
label | 7add3bc7-b614-5a27-ac14-01b8b38db6d8 |  | note | CATEGORY: IP
label | b5f71305-7962-5361-8803-338561dbb1ca |  | note | ---------------------------------
label | b680088d-0d87-57ae-8ba9-cf2b889f9504 |  | note | RESPONSIBILITY: SE
label | aa2a6998-cc74-5996-9dad-c49e5f867e7c |  | note | ---------------------------------
label | a18fb9aa-56ac-592c-8d8f-c75099d7f8b0 |  | note | VERIFYING DOCUMENTS: CHK-002-CIV-Stormwater Drainage Pit Installation
text | ab95933e-5bd4-5d15-8913-baac5207662a |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.10 Pits - Pit Lids
label | 4dd1d453-ec93-5971-877a-44c6af8e5a78 |  | note | REFERENCE: IFC Drawings
label | 87a5342d-db56-51d8-a441-19f5e97cc454 |  | note | ---------------------------------
label | 654cb06e-1493-54db-b8ec-1e9f2e5b7989 |  | note | ACCEPTANCE CRITERIA:
label | 0a879cab-526d-5b90-aaa3-1bacf9e0b0f1 |  | note | • All stormwater pits shall be provided with a locakable pit lid minimum Class D with in-fill material or fibre glass Terra Firm Enduro or similar.
label | 5a21187c-98c4-500f-9615-5384b3ad6037 |  | note | ---------------------------------
label | 1dd6817d-a12d-508a-8ef3-229af0f7520e |  | note | METHOD: Visual inspection
label | fd14c551-cefc-5cbc-bcc2-d51e8ee58010 |  | note | ---------------------------------
label | a5cc1c9d-9b86-5050-9e54-fa673f8903a4 |  | note | FREQUENCY: Each Lot
label | 755bf258-ce9e-58ab-9e62-b9ca4aa31a8e |  | note | ---------------------------------
label | fd0f5f9c-17da-518e-8f75-e95a134e593b |  | note | CATEGORY: IP
label | 42fb48f4-f66d-5395-844a-695be8f9c3a2 |  | note | ---------------------------------
label | 969bf20c-0ab3-53e9-926e-203fbc5a5225 |  | note | RESPONSIBILITY: SE
label | d06b5b78-0645-5bea-9e36-70aad86cd62f |  | note | ---------------------------------
label | 4617416c-9e4c-5700-b6aa-eaae7c7aa193 |  | note | VERIFYING DOCUMENTS: CHK-002-CIV-Stormwater Drainage Pit Installation
text | bb75bcc6-f642-5501-b0dd-82c0e2475289 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.11 Pits - Backfilling Around Drainage Pits
label | 986238ec-3c01-56bd-a658-83d9783949d9 |  | note | REFERENCE: Section 705.18
label | 04a3a570-b95d-54ea-84b2-0622a5053c12 |  | note | ---------------------------------
label | bea3de94-671a-55e1-afec-4861fafc04b2 |  | note | ACCEPTANCE CRITERIA:
label | be70134b-3223-5cac-84d2-b32b615e63e2 |  | note | • Backfilling around drainage pits shall be placed in layers not exceeding 300 mm loose thickness and compacted to refusal using hand held mechanical equipment.
label | 5c37d3a9-30b3-509e-9b58-1eecc138e4ef |  | note | ---------------------------------
label | 8afcc5c0-7338-5a01-bd9b-34b2cd500513 |  | note | METHOD:
label | 3560df30-5b49-51e6-9e70-eb93e36545cd |  | note | • Visual inspection
label | 069c82e4-15f1-5aef-a1ae-165edc02fe7e |  | note | • Measure
label | 6522f5b5-d725-5dd0-a3e5-47c7dd1fa637 |  | note | ---------------------------------
label | 28a96f30-e268-5bb4-b89f-cad5f02f0639 |  | note | FREQUENCY: Each Lot
label | d6382286-6468-5749-a961-a9d368406880 |  | note | ---------------------------------
label | 54319fb6-fdfb-5ae9-8d5c-ad2957857760 |  | note | CATEGORY: IP
label | f2ac6cab-2280-5ad6-b8d6-44f9edb95bd9 |  | note | ---------------------------------
label | 83fc22a4-8103-52af-a95d-3812650e5cd8 |  | note | RESPONSIBILITY: SE
label | f08696c9-c1d0-55bb-8d53-f9d514d19430 |  | note | ---------------------------------
label | f6ec18a8-4a1c-5774-9908-2075269dbedc |  | note | VERIFYING DOCUMENTS: CHK-002-CIV-Stormwater Drainage Pit Installation
text | c4458eb9-7501-55dc-a2aa-7bb34b6a98de |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.12 Pipes - Trench Excavation
label | 825fa705-9050-5597-90f3-00bff881b062 |  | note | REFERENCE:
label | d4bd3fdc-9c96-5e41-952c-8a4308b6022a |  | note | • IFC Drawings
label | ee0781f5-ae46-5154-8436-547d71761da2 |  | note | • Section 701.15
label | 3a9f162b-651a-599b-91b8-579ff1e4d2b3 |  | note | ---------------------------------
label | 957645c1-33c5-55f9-bb5e-e54646c2e816 |  | note | ACCEPTANCE CRITERIA:
label | ad9ed1c8-00bf-55b7-9285-a37b2d45d6e2 |  | note | • Excavation for pipe shall have a horizontal clearance between the pipe and the excavation wall of:
label | bff779d2-7e46-5201-98b5-3c0e856b7493 |  | note | > 300mm, < 600mm for RCP
label | ee3b641b-51a4-52fd-9a3a-957981544cb0 |  | note | > 150mm for Flexible Pipe
label | cbf9b86a-e15b-539c-9d91-19f43511cfc9 |  | note | • The base of the trench shall be compacted to refusal using mechanical plant.
label | 5aaac2b6-0838-5c9a-b39a-d7bc67b4fa59 |  | note | ---------------------------------
label | 793e46bd-339f-515d-813d-e40e3973c6db |  | note | METHOD:
label | 1904dd1e-dd79-540b-b04a-5f2e18cbaeae |  | note | • Visual inspection
label | 564f4027-936c-5d11-b082-7da0e56b2710 |  | note | • Measure
label | 59c30003-b4e9-5713-ab4d-2ca8c5a18d1e |  | note | ---------------------------------
label | 81b37202-ef81-5903-932d-050692d4b07c |  | note | FREQUENCY: Each Lot
label | c5955e7e-6d4e-51ac-907b-311690f285f7 |  | note | ---------------------------------
label | 51ec9f0e-d9f7-5b1c-96c8-a23bd3d9353f |  | note | CATEGORY: IP
label | 98840b93-f8ac-5dbb-aa05-42c52980d17b |  | note | ---------------------------------
label | fee2bc0b-b5f0-55f8-9433-ef788f4a2905 |  | note | RESPONSIBILITY: SE
label | e775e3c8-8267-57fb-89e3-44e0e267ffdd |  | note | ---------------------------------
label | e99cdd42-60c9-54ce-8379-f73c5e77fb52 |  | note | VERIFYING DOCUMENTS: CHK-001-CIV-Stormwater Drainage Pipes Installation
text | d2e65ada-36a5-5218-9138-144a7841eda1 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.13 Pipes - Bedding Placement
label | 0e0be699-77d5-51cd-b098-b4006e835eea |  | note | REFERENCE:
label | 72c6c51f-edea-5fe2-8ea9-2b4ca856cf96 |  | note | • IFC Drawings
label | ca0e2abf-3808-5fd1-ab7a-fe69ea7f3241 |  | note | • Section 701.16
label | a146065c-4e9f-55e7-a57b-1086b66294db |  | note | ---------------------------------
label | 69d8c09e-f4d6-5ec1-8423-28e32b7870e0 |  | note | ACCEPTANCE CRITERIA:
label | 5ff1818c-d783-5de6-90c3-54d9f7625d93 |  | note | • Bedding material shall be provided and placed in the full width of the trench to the below minimum:
label | 3c9dbd09-5166-52a3-96d1-a89830d5dd9c |  | note | > 100mm where D<1500mm
label | 3a9c3b3f-cc53-5910-a616-24ca18a5e0ec |  | note | > 200mmwhwere D≥1500mm
label | 7c45ac09-17f1-5956-a14c-098093c254e1 |  | note | • Bedding material shall be placed and compacted in layers <150mm loose thickness
label | d16b5bcc-527e-573f-8521-3db97e74d166 |  | note | ---------------------------------
label | 5295f10d-38d5-572c-bad4-c6df53d3f0ce |  | note | METHOD:
label | 4a94a0a7-c2e7-533d-aaa2-d5da8c48983e |  | note | • Visual inspection
label | cca4141c-b4ec-5113-9d9e-c4b99012d50f |  | note | • Measure
label | 711a8490-4e76-57ee-b643-93ab2b893013 |  | note | ---------------------------------
label | b36c776d-29d2-5769-9b7a-7d2c5a88459e |  | note | FREQUENCY: Each Lot
label | 32166b85-6859-5ebf-b1f2-9aa61f9e4394 |  | note | ---------------------------------
label | 24807a68-53df-5c55-8306-78ba40a324c0 |  | note | CATEGORY: IP
label | 871f6f7e-43da-554a-b2da-17291b8747c6 |  | note | ---------------------------------
label | 43832779-2508-5636-97de-a7e598d09cde |  | note | RESPONSIBILITY: SE
label | ffc57698-048b-5416-a0d3-6e96858125e5 |  | note | ---------------------------------
label | 72f9ff23-3b72-5fdf-9dd3-174f16386f5c |  | note | VERIFYING DOCUMENTS: CHK-001-CIV-Stormwater Drainage Pipes Installation
text | a4166f13-4e68-5005-864d-72497c2fc716 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.14 Pipes - Bedding Testting
label | 10928101-2b30-58eb-85da-765c8bbc8739 |  | note | REFERENCE:
label | 2f443549-74df-5c9c-bba6-02a07c6b914d |  | note | • IFC Drawings
label | f573bc6d-c43c-5410-b91f-8b4747d223dd |  | note | • Section 701.20
label | 3202c20d-dac3-5665-93c6-5dcf687938f6 |  | note | ---------------------------------
label | 086b3155-879b-585a-b32a-4d3956fb669c |  | note | ACCEPTANCE CRITERIA:
label | da3eef78-54ff-55c1-ae10-e4ee962efa5f |  | note | • Test a minimum of 20% of all lots for each culvert. (Lot = 1 layer of bedding). The number of tests per lot shall be three
label | 9f8e1bdc-218b-51bc-b85e-c120eda2ba28 |  | note | • Bedding shall be compacted to refusal using hand held mechanical equipment and material (Swell ≥ 2.5%) and mean moisture ratio of 92% between the completion of rolling and the placement of overlaying layer
label | 9c38abd8-cdfc-5d35-9f50-ad09bfc5dcc9 |  | note | ---------------------------------
label | bfa2395a-2287-5b47-820a-a038b7993855 |  | note | METHOD: Compaction Test
label | d7c418e7-cad5-57ab-ba35-366e78876c07 |  | note | ---------------------------------
label | 69083f0e-bd45-56ab-836b-506223a45fc1 |  | note | FREQUENCY: Each Lot
label | 48d2bae0-2573-5a68-8caf-c811ffa365bb |  | note | ---------------------------------
label | 61cf5c86-0d4e-5108-b5e4-82cacae831c4 |  | note | CATEGORY: IP
label | 7eca22e3-6fa2-5fce-9933-d788ad68d868 |  | note | ---------------------------------
label | 32c91886-0bc4-5dc1-9116-60b3ead6ac43 |  | note | RESPONSIBILITY: SE
label | 9c08ceb1-9e48-535c-9673-384f8a85451f |  | note | ---------------------------------
label | 5d714ec2-7bb1-5976-b1d7-b9ddb1c0f466 |  | note | VERIFYING DOCUMENTS: CHK-001-CIV-Stormwater Drainage Pipes Installation
text | 53ee4a78-b292-54a0-8153-0d7bfa3997b6 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.15 Pipes - Placement of Pipe - RCP
label | 19709c44-cdfb-5188-a888-1dfbd79a68b2 |  | note | REFERENCE:
label | b3b553f8-050c-5470-9e6d-d6b080cc9e6a |  | note | • IFC Drawings
label | 22f1ec40-5e9c-512b-80bb-f26d7d7c70fe |  | note | • Section 701.17
label | f8f253b0-ca33-56c2-89bf-6305a02d25fd |  | note | • Section 701.20
label | bd43a944-9f03-520b-9f3f-e1818aaf4420 |  | note | ---------------------------------
label | 886035bd-c738-5f10-a9d0-bf844a297e1b |  | note | ACCEPTANCE CRITERIA:
label | 9af674da-62e0-5ce0-ae5f-5de161b4fa97 |  | note | • Laying of pipes shall not commence until the Contractor has verified that culvert bedding complies with the specified lines and levels and compaction requirements, and pipes are not damaged. Laying of pipes or box culverts shall commence from the downstream end.
label | 4d803245-12b4-5014-bcd0-0ec29bad596c |  | note | • Rebate and socket ends of pipe segments shall be placed facing upstream and be fully entered.
label | f0bacef0-3561-58a5-af6f-56c1e9788281 |  | note | • Gaps between spigot and socket are in accordance with the manufacturers specifications
label | 09cb1ffd-bfae-5e31-8520-4969fd6bae43 |  | note | • The lower portion of the pipe shall be in contact with the bedding layer and shaped to accomodate the joint collar along its full length
label | 97d08a9e-28f9-5ba2-9ea4-4639e51417f8 |  | note | • Before proceeding to install the next length of pipe, the conformity of the assembled joint shall be verified by checking that the position of the rubber ring on the spigot, and the clearance and overlap between the spigot and socket, are within the values specified by the manufacturer.
label | 9ad18ded-9158-5e8d-b812-bb48537bea21 |  | note | • The spacing for multiple row culverts shall be as shown in Table 701.171
label | 381caf37-ea10-5bc2-bd97-3c03e4d59d52 |  | note | ---------------------------------
label | 861dd98c-b807-5951-995c-a2c8c9f2f845 |  | note | METHOD:
label | 1ecbb728-4e3f-5664-b030-12aaafb9e5c5 |  | note | • Visual inspection
label | 6612264c-f04b-5d62-a109-dcc7b77fe1ff |  | note | • Measure
label | a959c07a-113d-545d-b099-b6d0eb8469b4 |  | note | ---------------------------------
label | 41d418d5-0fb0-51c8-9afe-5ac647e22fe4 |  | note | FREQUENCY: Each Lot
label | 840f1982-aef1-5dd2-883f-23bf1ec20f37 |  | note | ---------------------------------
label | 29a0049b-34b3-5dce-bdb8-e393cdba97da |  | note | CATEGORY: IP
label | 860c7906-fafd-5390-bd2e-b7eba2b91b4a |  | note | ---------------------------------
label | d522d516-1de6-5635-97e7-eadf637ad1ec |  | note | RESPONSIBILITY: SE
label | c2ecdb98-c201-55dc-a5b5-467a38e83019 |  | note | ---------------------------------
label | 7c27adff-2795-5210-8a39-01c3aa397326 |  | note | VERIFYING DOCUMENTS: CHK-001-CIV-Stormwater Drainage Pipes Installation
text | cf0982bd-7481-5281-a6f9-69caad78c82b |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.16 Pipes-Placement of Pipe - Flexible Pipe
label | 77939416-4402-53a3-becd-ba4ecc8e93b7 |  | note | REFERENCE:
label | 04103d7b-a54d-5592-960b-d1c5decae299 |  | note | • IFC Drawings
label | 7fb3f3f1-25f2-59fe-9fd7-7c08eab0d898 |  | note | • Section 701.17
label | 597ed688-69da-5264-9587-97df2ef58c59 |  | note | • Section 701.22
label | 06b84d03-90b0-5010-87f6-cc0ac5fddd33 |  | note | ---------------------------------
label | 8eabb116-80c9-5e5e-8f80-4aed960691e9 |  | note | ACCEPTANCE CRITERIA:
label | 3c404933-5c7c-5493-aec4-32da6371936b |  | note | • All buried flexible pipe sections supplied shall be assembled in accordance with the manufacturers specifications.
label | 9e484397-69e6-5d18-91a7-732d782f5d3b |  | note | • Before proceeding to install the next length of pipe, the conformity of the assembled joint shall be verified by checking that the position of the rubber ring on the spigot, and the clearance and overlap between the spigot and socket, are within the values specified by the manufacturer.
label | 1d046eda-fc8a-5182-bbbf-4afe2aa71cc9 |  | note | ---------------------------------
label | ec14303d-a5b9-59c5-8f48-72fe2d5a19af |  | note | METHOD: Visual inspection
label | 3f2059e2-f365-5645-bc1b-103338ec7c1e |  | note | ---------------------------------
label | 3d4176d2-0c4e-5b4e-a6b8-fa0fc0243ad8 |  | note | FREQUENCY: Each Lot
label | 8f8b967d-61ef-5b5a-9292-cf24fd2e46dc |  | note | ---------------------------------
label | 9a1cd252-a89b-52f6-a7dd-1fb3e0b8a6b4 |  | note | CATEGORY: IP
label | 1d14b302-1c79-5ec7-b2de-8cfcb0637987 |  | note | ---------------------------------
label | b0b376ab-71bf-5c75-9f4b-b51c6c4669ee |  | note | RESPONSIBILITY: SE
label | b07c028c-3e61-5b9b-8055-392f29180170 |  | note | ---------------------------------
label | f4a44e7d-7519-5955-a9e3-0239a622b5e6 |  | note | VERIFYING DOCUMENTS: CHK-001-CIV-Stormwater Drainage Pipes Installation
text | 03454355-e625-5b36-b33e-8816a794df53 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.17 Pipes - Lifting Holes
label | 611d0660-de20-50d2-ae78-b822da73ce00 |  | note | REFERENCE: Section 701.18
label | 969fff30-944b-50c7-bcc5-051634db6b25 |  | note | ---------------------------------
label | 8f263795-2065-55e8-95e5-f3ca37cf44d2 |  | note | ACCEPTANCE CRITERIA: Lifting holes shall be plugged off in accordance with the manufacturers specifications after the pipe is installed.
label | 0c312676-f16d-5c77-b861-f262ba0ea108 |  | note | ---------------------------------
label | 98ae1f3a-a2a9-58c2-be5d-784b04dc6956 |  | note | METHOD: Visual inspection
label | 7ba8658b-39e5-59fb-a3d4-09c779e4c59a |  | note | ---------------------------------
label | ac2cd612-bc36-50d0-9522-2d23e77a34bb |  | note | FREQUENCY: Each Lot
label | 6a129a82-09ec-5b67-b592-9f19c9aecd81 |  | note | ---------------------------------
label | 7f86853d-6d30-56ab-a2a3-97bb7026ae8a |  | note | CATEGORY: IP
label | 60ea5dd9-6a50-5b49-abea-d48927eaf3be |  | note | ---------------------------------
label | 15b0c0d5-8ae8-5fd7-9106-fc8a3f688c71 |  | note | RESPONSIBILITY: SE
label | 8565fd07-818c-5b50-a98e-23fdde7e8861 |  | note | ---------------------------------
label | 382cc0b0-faef-5976-90ee-b27fdc400f25 |  | note | VERIFYING DOCUMENTS: CHK-001-CIV-Stormwater Drainage Pipes Installation
text | 9dde3ebb-fad0-5b87-9efb-c1831e352566 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.18 Pipes - As-built survey pick-up
label | 4d21a00b-d197-57e6-83af-30a90739bf99 |  | note | REFERENCE:
label | 2d859a68-4f2f-5bf6-8992-dce7db89637e |  | note | • IFC Drawings
label | 06aa52e4-7963-51e1-9e2f-826ea249569f |  | note | • Section 710.10
label | 114b541a-957e-5bde-b253-2b7ba4f20c30 |  | note | ---------------------------------
label | d827eff9-19bc-56fd-b988-dae7e0b456cd |  | note | ACCEPTANCE CRITERIA:
label | 3c047fbd-2d7d-551c-a3e9-75cff5946c81 |  | note | Each run of underground drainage shall be Survey verified prior to backfilling.
label | eb5d4b84-d1a5-516f-b017-751d40159317 |  | note | – Offset pits to kerb +/- 20mm
label | b6d46f49-d242-5618-ab5f-a96026b3e07a |  | note | – Plan location pits not adjacent to kerb +/- 100mm
label | 18082fc2-f894-5222-beb0-1afb8adbfc23 |  | note | – Invert level of pipes at pits +/- 50mm
label | 820b3135-c5a2-5357-b5a6-536093bf4496 |  | note | – departure from design grade +/- 10mm in 10m, provided minimum grade is not less than 1:250
label | c3d5dd27-8dee-5ed8-b1ea-dee55224f815 |  | note | ---------------------------------
label | 902fb734-612f-5a16-b193-9e7f739931b5 |  | note | METHOD: Survey
label | 12aa7995-8f31-53f0-b163-ed5120ccbf46 |  | note | ---------------------------------
label | 3c01f23f-7286-52a6-92c6-c7686eda215b |  | note | FREQUENCY: Each Lot
label | 24018108-1211-56de-9907-75f252a86fb4 |  | note | ---------------------------------
label | 9ed231c4-c6e1-54f4-bc3d-bdaf51a45884 |  | note | CATEGORY: IP
label | 94d2e69f-cd2d-5e08-bb5a-5c175b8f256e |  | note | ---------------------------------
label | 4c4f73b1-b56f-5696-9bc0-ff44a26bfd76 |  | note | RESPONSIBILITY: SE
label | ab4e5d2d-96dd-57a0-82c5-d532dbc0e596 |  | note | ---------------------------------
label | 316e3e3e-1001-5dab-893d-bbc35dd9d140 |  | note | VERIFYING DOCUMENTS: CHK-001-CIV-Stormwater Drainage Pipes Installation
text | b73df8bf-eac6-5560-ad0e-64e8512699a5 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.19 Pipes - Backfill Placement
label | 7a2cc00b-b1cc-527f-8d22-03f4125ae6bb |  | note | REFERENCE:
label | 5d657d4f-23ea-5397-8786-155ed1be4ca3 |  | note | • IFC Drawings
label | 015b0c3e-9397-5093-b8ec-412fba0058df |  | note | • Section 701.16
label | fdb9f601-c31d-502d-9be1-731a68557708 |  | note | ---------------------------------
label | 80a4900f-5f17-569a-beee-fe943ba08d83 |  | note | ACCEPTANCE CRITERIA:
label | 5c9a683e-9e14-517a-86d7-3ee0399cc06d |  | note | • Backfill material shall be placed the full width of the bedding material and compacted in layers <150mm loose thickness.
label | 4183f836-400b-5d9c-b08c-dfa4fb1e4b33 |  | note | • Filling shall not be placed within 2.0m of the open end of the pipe where a further section is to be placed.
label | 3a4dd02a-1c26-5a1f-a92b-4ba8070d37db |  | note | ---------------------------------
label | 4ebc29ec-2c70-557c-9edb-1f78fb6d160f |  | note | METHOD:
label | 5f554034-a70b-5ad2-8ae7-54bdb95a7d56 |  | note | • Visual inspection
label | 11aea135-448d-5db9-a24e-c39640f8671e |  | note | • Measure
label | 5702d10e-bfec-5800-8171-45db2f39e28a |  | note | ---------------------------------
label | 15d7540a-1c98-594a-b1c7-74bfdf7213dd |  | note | FREQUENCY: Each Lot
label | a842ae5c-b054-5a31-bfd6-7773570de5fe |  | note | ---------------------------------
label | f1b9b065-0790-56a6-884e-5e2ad8ef0c46 |  | note | CATEGORY: IP
label | 8740f231-fbbc-572c-9e31-54e10cbcc747 |  | note | ---------------------------------
label | 1068f614-ec91-5189-bf31-959ef937b6c4 |  | note | RESPONSIBILITY: SE
label | 6a16cf15-54c5-5d8e-8deb-6c6bfb3e90fb |  | note | ---------------------------------
label | 9009af6a-5d29-55ba-b9b1-18b6fc1ba44e |  | note | VERIFYING DOCUMENTS: CHK-001-CIV-Stormwater Drainage Pipes Installation
text | 424a8e3e-d74c-5fe0-b02e-a2f2fa5dfa7c |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.20 Pipes - Backfill Testing
label | c0f57d05-a90a-5f42-a4fd-2035b0359677 |  | note | REFERENCE:
label | 240d1e6f-201e-588a-acfc-277091fc902b |  | note | • IFC Drawings
label | b10f906d-b651-5575-9448-14128cf0174d |  | note | • Section 701.20
label | 5d09bbfe-add9-5d6e-a9ec-ea56fc676d59 |  | note | • Section 701.29
label | 0184bf96-4aba-5da0-a7d3-4c5e35090006 |  | note | ---------------------------------
label | aec7f6aa-0c24-5ddf-9bb4-3d975182baa8 |  | note | ACCEPTANCE CRITERIA:
label | 13d82307-84f9-5a53-b699-aae4cbf04399 |  | note | • Test a minimum of 20% of all lots for each culvert. (Lot = 1 layer of bedding or backfill)
label | ae0bd65a-ec8d-53e4-ba2b-13477e8a55f5 |  | note | • Backfill material shall be compacted to a density ratio > 97%. Material which has a swell equal or greater than 2.5% shall be maintained at a mean moisture ratio of 92% between the completion of rolling and the placement of overlaying layer
label | c03a32fb-3d27-54aa-8d93-af3ce64e2690 |  | note | ---------------------------------
label | 0b1b66a2-4864-524c-aad6-f57088886010 |  | note | METHOD: Visual inspection
label | b11c62e5-c555-5efb-a73a-0f926777c508 |  | note | ---------------------------------
label | 9370d6e8-dd47-55ad-8c07-6903160e46f8 |  | note | FREQUENCY: Each Lot
label | 56843ccb-f3a8-5fba-9d8c-786b9a54a59b |  | note | ---------------------------------
label | 1ee078f2-134f-5422-8773-3ba878e7d9f5 |  | note | CATEGORY: HP*
label | 2974e8f9-54fe-5ef7-af35-6649f8b7832d |  | note | ---------------------------------
label | 5691bf3e-3123-5615-99d4-5bbc2d344ed1 |  | note | RESPONSIBILITY: PE
label | 287fe581-0dfc-5691-8fa2-667d7253348e |  | note | ---------------------------------
label | 46711938-2ef5-5edb-aca9-50f2ccf6e0f8 |  | note | VERIFYING DOCUMENTS: CHK-001-CIV-Stormwater Drainage Pipes Installation
text | 4dfc0104-bc2d-555e-b62b-d9cc5036b219 |  | textbox | Date Completed:
checkpoint-group |  |  | section | 6.0 - Post-construction / Post-installation Activities
checkpoint-status |  |  | checkpoint | 6.1 Flushing & CCTV
label | 159bcd39-4510-5d40-b35a-a73ea651ce01 |  | note | REFERENCE:
label | 85eb4301-7474-514f-9f38-62cdc9084881 |  | note | • Section 701.28
label | 199a2224-acbd-54fa-8eea-d04e18edc644 |  | note | • Section 701.30
label | 2f6f6ab6-c932-5214-a874-85efec932a96 |  | note | ---------------------------------
label | 2f08cb28-1de9-504a-9364-5f86797c454b |  | note | ACCEPTANCE CRITERIA:
label | 07d34c6d-4fce-5ae3-a415-ea0f5c5079ee |  | note | • All culverts shall be flushed clean from end to end on completion and maintained in proper working order.
label | 249e3201-6888-5be5-b685-f746065fcde5 |  | note | • All drainage lines constructed shall be inspected, after completion of earthworks to subgrade level and prior to construction of pavement layers, by an independent testing organisation using closed circuit television (CCTV) to verify that the flow of water is not obstructed and to check for visible signs of defects.
label | 237b88b9-b9da-5b2a-9a80-0df04d10ac7e |  | note | ---------------------------------
label | ff9fa6ff-9e71-5852-bbb2-13739ac55962 |  | note | METHOD: Record Review
label | f389914d-4d0b-5dbe-b9b7-28e2e820ded2 |  | note | ---------------------------------
label | f8f37fab-04e8-5c74-8d53-d2495c69ba8c |  | note | FREQUENCY: Each lot
label | 8acb0aa0-3068-5a46-961d-62312e2623b2 |  | note | ---------------------------------
label | 96d0f832-eedf-5084-9ea5-59ecaccf4a98 |  | note | CATEGORY: HP
label | 62622c57-ec3a-50ab-9166-8eb0f9a5dda0 |  | note | ---------------------------------
label | 1c5b6976-8baf-53a9-9319-9c0144060b8c |  | note | RESPONSIBILITY: Nominated Authority
label | 471c5513-2d4d-523d-a58a-60449d0dc30a |  | note | ---------------------------------
label | cb4fcdf8-61ab-55d4-b90b-e7821dceee52 |  | note | VERIFYING DOCUMENTS:
label | ee8c0b8e-5930-5fed-b111-e7b8f1c60b1d |  | note | • This ITP
label | fb7f222d-f561-50da-985c-d590d3dadcb1 |  | note | • CCTV Reports
text | 89c14410-158b-57c5-96b3-aeb87f767805 |  | textbox | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 6.2 As Built Survey
label | a1cbc581-66c4-5e05-a23f-fadbf1e2fbe4 |  | note | REFERENCE: Section 701.10
label | efc6cec3-d607-55c0-8239-0782991995d5 |  | note | ---------------------------------
label | 55262a37-0d2e-5ca6-b05a-6ff06ca4db1b |  | note | ACCEPTANCE CRITERIA: Provide record of dimensional measurements to demonstrate the drainage lines are installed within the tolerances specified in Section 701.10
label | 02c4346b-8e00-5208-8c5c-aa1de16dcf94 |  | note | ---------------------------------
label | f52c8f8c-9c05-5b6f-8037-79b28e1395fa |  | note | METHOD: Document Review
label | de761392-0047-587c-a3f2-2fd0932bd6e8 |  | note | ---------------------------------
label | ea43d0ee-a987-511e-b271-2ea8e9fda5e8 |  | note | FREQUENCY: Each lot
label | 7fb86dcd-3dc6-559a-85a7-8631eccae803 |  | note | ---------------------------------
label | 110b14aa-3038-5595-b2f6-cd63226ff707 |  | note | CATEGORY: IP
label | fb040add-5fb9-5536-a003-c11fcc6f1eff |  | note | ---------------------------------
label | 2db84356-8873-5015-8045-cada1b970b65 |  | note | RESPONSIBILITY: SE
label | 530ddf72-8ccb-53cc-9a5c-2d8349a3229d |  | note | ---------------------------------
label | 8ae65123-89ac-5501-8dba-e2e0216c33db |  | note | VERIFYING DOCUMENTS:
label | 55a676b8-b806-5935-ab7a-a51dd5aecae2 |  | note | • This ITP
label | 96f24d11-a0b5-5d69-949f-8227c170c978 |  | note | • As Built Survey Report
text | beb9e650-b340-5765-87e5-b09d457ecc08 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 6.3 Repairs to Damaged Pipes
label | 038a7a6e-a304-5ebb-b7e1-0a51274a1504 |  | note | REFERENCE: Section 701.31
label | e9432abc-0c4f-5dc7-888e-168e15b6ff6a |  | note | ---------------------------------
label | 0173f728-70ee-5417-adae-6a0aea3f32c3 |  | note | ACCEPTANCE CRITERIA:
label | 6bcc2ce3-ed44-50b2-9b6a-44701160d2fe |  | note | Where inspections after backfilling identify any of the following defects they shall be notified as a non-conformance:
label | f618e6b1-34a1-531b-b50c-aa7fba22db8f |  | note | • cracks wider than 0.5 mm
label | 9f8b5068-1ab9-531d-9bbd-f5f7c9aae961 |  | note | • spalling of concrete
label | 9edcb5ef-f6ce-538f-9b48-9d2ebfd9a07d |  | note | • exposed reinforcement
label | 8ed994c7-cbb1-547b-9090-b5d6e80a5090 |  | note | • joints that are not fully engaged.
label | 59e1e2f2-97ae-5229-966c-3ac9ae0591dd |  | note | Any pipes with defects greater than the following limits shall be removed and replaced:
label | 0870eccd-4e03-5eae-9068-938d23586755 |  | note | • longitudinal cracks greater than 2 mm
label | 83393a75-a530-5d41-8ad4-e23d14474209 |  | note | • circumferential cracks around the full circumference with width greater than 3 mm or with lateral displacement of the cracked sections exceeding 3 mm
label | 6692fa63-5d8f-5831-8ef6-929b56682247 |  | note | • circumferential cracks around part of the circumference with width greater than 4 mm
label | 6bc4a133-19e7-5411-8afe-02503f4ee0d1 |  | note | • penetrations with area greater than 400 mm2
label | 4501d997-9869-54f5-9cb1-67f46ab400b1 |  | note | • pipe joints that are separated.
label | 0e7286d5-1869-5a58-963f-856f4e6a05e2 |  | note | The Superintendent may agree to accept pipes with defects as noted above subject to demonstration that repairs will ensure that pipes will operate effectively for their design life. Consideration will only be given to products and procedures with proven performance and to the following types of treatments:
label | a8700aec-529d-5566-b849-80f68eb57c4e |  | note | • hot sprayed epoxy coatings for cracks not wider than 4 mm with no lateral displacement
label | 45dee190-fa62-5295-936b-71ee9ab223ef |  | note | • fibre glass reinforced epoxy sleeving for cracks not wider than 4 mm with lateral displacements up to 3 mm
label | bc65d82f-c362-5102-8618-e6777e9b4b4e |  | note | • spalled concrete, exposed steel reinforcement and penetrations shall be treated as patch repairs and repaired with polymer modified cementitious repair materials in accordance with the requirements of Section 689.
label | 45da4401-85f5-50d9-b09c-7f529b639a67 |  | note | The Contractor shall submit details of proposed rectification treatments including manufacturer’s product specifications and warranties, the area and thickness of repair treatment, detailed repair procedures, and inspection and test plans.
label | 3f40ad12-8e66-5f63-abec-60de09e76ff2 |  | note | No repairs shall be undertaken without the Superintendent’s approval of the repair materials and procedures.
label | f9000906-fcae-5aae-94a5-e783cc100ada |  | note | All repairs shall be inspected using CCTV to verify compliance with the repair specifications.
label | f1a172b5-0aa5-55c2-b18a-1d544ce7a3c8 |  | note | ---------------------------------
label | 8f9b90c1-10e6-515f-8c66-e5943ce759f0 |  | note | METHOD:
label | 228b213a-b69d-5ed9-b7e3-eab859726860 |  | note | • Document Review for Repair Procedure
label | 848a4b12-318f-5617-8fac-01dbfce80e11 |  | note | • CCTV Report Review
label | d4fa9bc6-d851-5231-801f-0425ca0325d5 |  | note | • Visual Inspection
label | 0e38733b-6976-5add-a297-022942d7130b |  | note | ---------------------------------
label | b3616051-16a7-5568-9967-7c79d6c51df6 |  | note | FREQUENCY: Each lot
label | 6fc051fe-5677-5366-bf9a-703c0e74672a |  | note | ---------------------------------
label | 19756bf2-ae3c-526e-8add-54c0ab597a45 |  | note | CATEGORY: HP
label | ffa2c7e9-7463-52b3-914c-7ac855ad642e |  | note | ---------------------------------
label | 6a195576-b829-52de-b4ee-f20cdecdd1f9 |  | note | RESPONSIBILITY: Nominated Authority
label | 6c8fec64-4055-5e2a-8abf-b4ff42accdca |  | note | ---------------------------------
label | acf23e40-f118-5f6e-9986-6167a9b0a02a |  | note | VERIFYING DOCUMENTS:
label | a1d3f3d9-d2d4-53e1-9186-d58e9d462b4a |  | note | • This ITP
label | 56482cbe-d340-5bac-8407-8e3116d7c06b |  | note | • Approved Repair Procedure
label | fe8797fd-8317-5e34-a714-0204cda238c5 |  | note | • Post Repair CCTV Report
text | 5b8a6c6b-8844-55f3-a248-cce7f23916a5 |  | textbox | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 6.4 Non-conformance Report (NCR) Closure
label | cfafe55a-2b51-58d8-9710-cb8dbd02c4d9 |  | note | REFERENCE: MRPA Quality Management Plan
label | fabcd401-4f32-5273-8889-f467a7a18aca |  | note | ---------------------------------
label | 9f316faa-ee12-5b8c-bbf1-0c5515759ea8 |  | note | ACCEPTANCE CRITERIA: Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed in Teambinder.
label | 4bff4195-fcec-5526-82b5-77dcadb7a1f9 |  | note | ---------------------------------
label | 0a880d20-403a-5491-80bb-26fc301dd006 |  | note | METHOD: Document Review
label | 1a195a48-0ded-5bfa-b366-89bd3b5354f1 |  | note | ---------------------------------
label | 96e014b3-dfa6-58ca-801b-59683ecf740e |  | note | FREQUENCY: Once, prior to closure of this lot / element / Work area
label | c28bc619-9ba4-5c04-b8a3-015bf7b6358e |  | note | ---------------------------------
label | f4f54f2a-be70-5d95-ba01-d82945aabebf |  | note | CATEGORY: HP*
label | f0ece616-3252-5d28-a099-ee55ada31ce6 |  | note | ---------------------------------
label | 452185ca-1ed3-5ad7-9191-61c727168d13 |  | note | RESPONSIBILITY: PE
label | e64fc34e-d7e5-576c-b893-8d9e4276f649 |  | note | ---------------------------------
label | 40e013b2-3180-5dc4-b90d-a48292079636 |  | note | VERIFYING DOCUMENTS: This ITP
text | cb9564e8-9395-5d94-b48a-c0db0d2fc8e1 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | Metropolitan Roads Program Alliance Final Inspection
label | fa8d856f-ad43-55f1-969a-6d1badd09428 |  | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
text | 5fcc9e4b-42d2-58eb-ba33-f3ceea67d3f0 |  | textbox | Name:
text | e6feccf9-68b6-520b-a7cd-3e7668aede9e |  | textbox | Position:
text | fe36629f-e735-5b19-8bed-95332a57a4b6 |  | textbox | Date Completed:
holdpoint |  |  | signoff | Sign ITP
checklist-flat |  |  | checklist | CHK-001-CIV-Stormwater Drainage Pipes Installation | itp |  |  |  | Yes | CHK-001-CIV-Stormwater Drainage Pipes Installation | f23e8c72-1285-4052-838f-3463eb36ef27
checkpoint-status |  |  | checkpoint | CHK-001-CIV-Stormwater Drainage Pipes Installation
label | df65ec0b-6ba1-559c-b72b-db7729f5629a |  | note | Document Title: CHK-CIV-RSS Walls-Fill Placement
label | 1b779c38-9876-500b-b34e-6bb374495813 |  | note | Check list Description: Stormwater Drainage Pipes Installation
label | bf30805b-8d03-5fa1-9c4d-b4ee65077c69 |  | note | Discipline (e.g. CIV/STR/RAIL): CIV
label | 704a448f-8626-5942-89a7-9dde0ec6fd03 |  | note | Revision Number: 0
label | 66c3f9eb-ef5f-59e0-8956-0f98e6fc9356 |  | note | Revision Date: [Date of Approval]
label | 1776e669-8036-555d-b4df-a610d02b6174 |  | note | ITP created by: Jon De Castro
label | 3e6f9545-4ca9-50bb-a1de-601e4ab5dd54 |  | note | ITP approved for use by: Aldrin Guinchoma
checkpoint-status |  |  | checkpoint | 1 - Pipes - Survey Set-out
label | c3150cff-7c1b-5623-a458-e00730683d30 |  | note | REFERENCE:
label | a0e7925a-afe4-5cb4-a190-d74fe6e4427e |  | note | • Section 701.10
label | 4d616d3b-8034-5228-bc98-d87215514553 |  | note | • IFC Drawings
label | 41954206-ee2d-52f9-b0d1-1be94aa0bccf |  | note | • ITP-008-CIV-Stormwater Drainage Supply & Installation - Item 4.1
label | af858038-5c2b-5354-9b95-d5fa59e63475 |  | note | ---------------------------------
label | a8a89ae0-5432-5c48-9b0e-14f02a5c59e6 |  | note | ACCEPTANCE CRITERIA:
label | d3202c83-c345-5b92-98c4-535337fb39e3 |  | note | 1. Pipes are set-out in accordance to IFC Drawings and Section 701.10 with the following tolerances below.
label | c42608c4-f6fc-59be-828f-612943e17ccb |  | note | (a) offset of entry pits required to match lines of kerbs or barriers ±20 mm
label | 167134c7-0f0c-5ca7-ab0b-9d1afbc2e577 |  | note | (b) plan location of pits other than offsets to kerb lines or barriers ±100 mm
label | 35a4433b-70e7-5c40-87ea-4aec4d6dfd90 |  | note | (c) invert level of pipes at pits ±50 mm
label | 373e0d61-e270-50fe-b9f7-ab7f69d17216 |  | note | (d) departure from design grade of pipe runs ±10 mm in 10 m provided minimum grade is not less than 1:250
label | ec3d55ee-9498-54b7-ae3f-9370b4a9a418 |  | note | ---------------------------------
label | ec566088-f1bb-505f-9895-8cd4be29fca3 |  | note | METHOD: Survey
label | deadd600-34d8-5766-b870-3201165846a5 |  | note | ---------------------------------
label | 7c51656c-9e3e-5970-b1da-1928239c7044 |  | note | FREQUENCY: Each Lot
label | 499da845-e6b7-5e08-b223-fc6997c8dc58 |  | note | ---------------------------------
label | 249cc0d8-a627-50b5-8f12-f2fc9848ff99 |  | note | CATEGORY: HP*
label | 168cda13-7777-5c83-988e-19301067562d |  | note | ---------------------------------
label | 853860ba-d941-54c2-8937-64fd1201897c |  | note | RESPONSIBILITY: SE
label | 2532f3dc-8e97-50c4-83d9-bfca33e23441 |  | note | ---------------------------------
label | 25c21758-3e43-5a8d-9ded-82fcbae42d9b |  | note | VERIFYING DOCUMENTS:
label | 7c551d7c-f903-59f1-a473-38f43a6a07cb |  | note | • This Checklist
label | 623df886-0256-5d6c-b542-4718114124a8 |  | note | • Survey Report
label | d9b61adb-7e31-5a64-893c-f4d8d1de45c4 |  | note | ---------------------------------
text | 7b4354b5-9ba8-52f7-9372-6708747cb735 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 2 - Pipes - Trench Excavation
label | e5b1d89f-55c7-5570-b79e-e4893055c2d0 |  | note | REFERENCE:
label | eba746c6-addb-58b5-b0c5-8fe57f2e3a5e |  | note | • IFC Drawings
label | 04c0dd95-95ee-575f-b239-73e824973e81 |  | note | • Section 701.15
label | 8497739a-222f-50bc-8ce7-331e4dbdd305 |  | note | • ITP-008-CIV-Stormwater Drainage Supply & Installation - Item 5.12
label | 4d6dab86-5b34-5bc7-9a32-f21e3ad3b030 |  | note | ---------------------------------
label | 8dfce404-8f10-56c6-8680-3ba2c8511c00 |  | note | ACCEPTANCE CRITERIA:
label | d3548041-9546-50d4-8562-08857f559591 |  | note | 1. Excavation for pipe have a horizontal clearance between the pipe and the excavation wall as per below.
label | ab4af6df-6025-573e-87ee-8c24ab4ea24f |  | note | > 300mm, < 600mm for RCP
label | 1e4c6e5c-dd7e-5b16-9201-62c15f1a692c |  | note | > 150mm for Flexible Pipe
label | 4de97269-3352-50c3-8b9e-7f52a74824d9 |  | note | 2. The base of the trench have been compacted to refusal using mechanical plant.
text | f07689a0-8ccf-530a-b602-62f3b460f542 |  | textbox | Trench depth :
text | 5c6953e8-5e4c-51e8-8295-0b535068c7ec |  | textbox | Drawing Reference No:
label | a751b55d-4600-5f6c-9522-5dd6bbfc4423 |  | note | ---------------------------------
label | c1e56914-8288-5a6b-86df-8ea39fbb3f22 |  | note | METHOD:
label | fa9e33db-0e30-5ca3-95ba-498fa11304a6 |  | note | • Visual inspection
label | 0e6bc5da-53d1-56eb-a66c-e9244d47605e |  | note | • Measure
label | b15dd04f-e594-5238-b4cf-5fe1a62b6b49 |  | note | ---------------------------------
label | edee2e9e-3c6b-5b8d-b543-0c7a27318661 |  | note | FREQUENCY: Each Lot
label | 1d37203e-833d-5c1e-9b5d-e11340b8fee1 |  | note | ---------------------------------
label | 94596141-4ee0-56aa-b005-8c89a1446f44 |  | note | CATEGORY: IP
label | c652b431-a2be-5108-8a54-98ba2f10d34f |  | note | ---------------------------------
label | bbb5b0cd-a9e0-553a-9b6c-9d1b5f1847b9 |  | note | RESPONSIBILITY: SE
label | 28980df3-61d9-54a3-a3bb-791267d042c1 |  | note | ---------------------------------
label | 89ff36cd-ecb9-5c1d-ae46-bdf71b6e5025 |  | note | VERIFYING DOCUMENTS: This Checklist
label | ae652957-cc6a-50da-8481-917eb45e7a63 |  | note | ---------------------------------
text | 5f9c5f34-868e-5f7d-9405-6df7f088f474 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 3 - Pipes - Bedding Placement
label | c79dd703-0125-55c7-b412-b7829190e2bd |  | note | REFERENCE:
label | 19918631-1355-540d-9067-af67416c4262 |  | note | • IFC Drawings
label | 953ee003-799c-5be4-a190-11ec116a2040 |  | note | • Section 701.16
label | 406bba5f-e1e5-58d3-b336-39af5192a96c |  | note | • ITP-008-CIV-Stormwater Drainage Supply & Installation - Item 5.13
label | 8579c786-9bf1-5464-b3e5-b5924aafc609 |  | note | ---------------------------------
label | 45aea435-96b7-51f5-ae87-28f46b7ca5ce |  | note | ACCEPTANCE CRITERIA:
label | 56d66494-4882-5012-bd78-caeb078b6d85 |  | note | 1. Bedding material provided and placed in the full width of the trench to the below minimum:
label | b44dd820-8605-54c0-b6b2-ee2b078b18d5 |  | note | > 100mm where D<1500mm
label | 6c07b52b-8c84-52ed-a062-e14703a37e7a |  | note | > 200mmwhwere D≥1500mm
label | ac67922c-f43f-563e-87da-2662d07cf38e |  | note | 2. Bedding material placed and compacted in layers <150mm loose thickness
label | 66f6b390-a361-5cdd-a877-5f5cbe8a6432 |  | note | @Jesse - please check bedding requirements as per design (use sand bedding?)
label | f38c31ad-3a03-5e5f-8615-2c26addb62df |  | note | ---------------------------------
label | 3a4f2a4e-958b-59f4-abd3-81316b4f9b1e |  | note | METHOD:
label | 1b803729-01c4-57a0-ac58-7f562a06e8d6 |  | note | • Visual inspection
label | a9ac4fe2-1f42-5ce7-bc4d-9cfc15c54ee6 |  | note | • Measure
label | ff62e83e-faa8-5ea0-b0b4-a0c5fd5ff4fa |  | note | ---------------------------------
label | da24fde9-2bcc-5f23-bf14-9f9a46e06d06 |  | note | FREQUENCY: Each Lot
label | 5065f70f-1a0d-5d75-ad77-de00b4705d03 |  | note | ---------------------------------
label | 3a709d60-6023-575a-ad1a-02853d0b9e16 |  | note | CATEGORY: IP
label | a2fad9db-583a-5d32-8c66-286e8ec950b5 |  | note | ---------------------------------
label | 601256c0-c274-54ab-97a6-2eed2fa8b5eb |  | note | RESPONSIBILITY: SE
label | b504838c-210c-5a51-a4bd-84d139c0cb25 |  | note | ---------------------------------
label | a92edf26-71eb-5f31-878c-6d9d0d6d64c8 |  | note | VERIFYING DOCUMENTS:
label | b7fc622f-6097-5639-9e42-24ff8d66032f |  | note | • This Checklist
label | 206f2602-f2ac-57dd-9176-480f1066540e |  | note | • Material Delivery Docket
label | e38be285-0d03-5025-bcb4-80b1d00db38e |  | note | ---------------------------------
text | 822f40c3-f941-5f29-beb9-015f04fe3d81 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 4 - Pipes - Bedding Testting
label | 92ebad86-f548-5f6d-9f70-299788ed230f |  | note | REFERENCE:
label | 4c30525c-0b4e-5964-9d24-aeaf69bbb2ca |  | note | • IFC Drawings
label | 69b166f1-a4f8-5d86-ac94-9a7d7d057780 |  | note | • Section 701.20
label | 289f0efd-349c-576a-b901-6b7c339f1360 |  | note | • ITP-008-CIV-Stormwater Drainage Supply & Installation - Item 5.14
label | c3d385a6-a74b-519c-b1cd-55dc9c86b824 |  | note | ---------------------------------
label | 51df9f40-666c-5611-8737-c531aca05b18 |  | note | ACCEPTANCE CRITERIA:
label | 0ef183a7-61b5-5b99-859e-277b518402ec |  | note | 1. Tested minimum of 20% of all lots for each culvert. (Lot = 1 layer of bedding).
label | 93b11cad-a2ea-5ed9-8a14-430b57ffbbae |  | note | 2. Three (3) tests done per lot.
label | 9df71c89-89ac-59a5-b814-ce3eae499e55 |  | note | 2. Bedding compacted to refusal by hand held mechanical equipment & material (Swell ≥ 2.5%) mean moisture ratio of 92% between the completion of rolling and the placement of overlaying laye.
label | f9376618-d6c7-507a-af2b-1ef789c150c4 |  | note | Responsible Engineer to confirm if the bedding testing is required for this lot.
label | 9a99208b-d41f-56e2-bd07-61dc94238c5c |  | note | ---------------------------------
label | d487dda6-2f55-5c4e-b5fa-7ee83b1ca3a8 |  | note | METHOD: Compaction Test
label | f7915f15-0d5e-524e-b613-fa5f4e220052 |  | note | ---------------------------------
label | f1bb3ec5-f25c-577c-9d6f-77fbb45f91ea |  | note | FREQUENCY: Each Lot
label | ec786328-d33b-5536-abe3-b76dd24b9651 |  | note | ---------------------------------
label | 964c0406-b844-5422-94e0-64a0f405cd79 |  | note | CATEGORY: IP
label | 0b63a39c-1d9d-516a-b777-7d715ed754ea |  | note | ---------------------------------
label | 5539b52e-451b-52cf-906c-f8f339df3cc0 |  | note | RESPONSIBILITY: SE
label | 843dfc14-a6c9-5313-a6f5-fcbc8336e7fb |  | note | ---------------------------------
label | 7712a211-3c3d-5890-9c1a-f38fa5d76a1b |  | note | VERIFYING DOCUMENTS:
label | b7b3c026-6867-5467-b638-14fe1e58487f |  | note | • This Checklist
label | f3e4565d-0e8f-5322-add8-fdddfb26829b |  | note | • Test Reports
label | 42bef36e-0e54-5a0a-a318-4882a543de79 |  | note | ---------------------------------
text | ecaa866c-4949-5977-8fbf-372a55551890 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5 - Pipes - Placement of Pipe - RCP
label | b30d0fdd-2ed7-54a0-9018-589efecd3ff3 |  | note | REFERENCE:
label | b6be9df7-8326-5ec5-a93c-6002e3b569a7 |  | note | • IFC Drawings
label | 380de897-e33c-5cc9-a682-c473d603779c |  | note | • Section 701.17
label | 7eef75bb-5eae-5828-8cd8-df2c2ca4b75b |  | note | • Section 701.20
label | d2d88210-6c69-556b-826b-74be6691ec31 |  | note | • ITP-008-CIV-Stormwater Drainage Supply & Installation - Item 5.15
label | 25c6f4ee-dbbb-5850-a9b1-d705f106ee64 |  | note | ---------------------------------
label | 94b48529-1b8d-5202-949e-a892d719b5b6 |  | note | ACCEPTANCE CRITERIA:
label | b672a755-cb3d-59ec-8401-362fc9bb7991 |  | note | 1. Correct size of pipe installed
text | da41954f-e19f-5aad-b2bb-d6662ccadf41 |  | textbox | Pipe Dia ________;
text | e16b9ecf-86a7-50d5-909f-6d8b20c6aa19 |  | textbox | Drawing Reference No.
label | 204bb45c-4cc5-5c3c-92ff-80d7163050ae |  | note | 2. Pipes phycially checked and confirmed No Damage prior to install
label | bbe42fac-9e60-5a0e-8f47-1601d6df9739 |  | note | 3. Rebate and socket ends of pipe segments placed facing upstream and be fully engaged
label | 5eb30b9b-b732-526f-9a38-1b51e30ab441 |  | note | 4. Gaps between spigot and socket are in accordance with the manufacturers specifications
label | febede3e-7a89-586d-87b6-9978574920fe |  | note | 5. Lower portion of pipe in contact with the bedding layer and shaped to accomodate the joint collar
label | 7120474b-c0b0-5577-b786-26bca1bbaf1d |  | note | 6. Correct type and size of rubber rings used and properly installed at pipe joints
label | bd29b0b8-95f2-5296-b9bf-cc9053fd6982 |  | note | ---------------------------------
label | 71b0feb8-a7a6-5f67-bf67-3585e6714e81 |  | note | METHOD:
label | 0b1c1b3b-d8c2-58d8-913a-ec5af3f02122 |  | note | • Visual inspection
label | 12e01d05-8991-596b-9736-ffc527c5df3c |  | note | • Measure
label | 3f2d0106-9921-5b69-9fdd-02fbe9315381 |  | note | ---------------------------------
label | d28cf396-36ed-59e3-8862-3262258f2ac6 |  | note | FREQUENCY: Each Lot
label | 3fe59217-8898-5d65-990b-451fcd28754d |  | note | ---------------------------------
label | 3475a777-d37f-5647-bfc9-9b8b87ae2ec0 |  | note | CATEGORY: IP
label | fcc73449-3df4-5a30-a5c1-5b9ab4039f95 |  | note | ---------------------------------
label | d55b3696-7965-5f70-845e-47710a42926e |  | note | RESPONSIBILITY: SE
label | c98b632c-c4ad-5987-bf8d-3ac8df5d84b0 |  | note | ---------------------------------
label | 4feac54b-2b24-5189-be26-ce8dc6401c30 |  | note | VERIFYING DOCUMENTS:
label | 31349771-fa8d-518b-8770-068e9f67e11b |  | note | • This Checklist
label | f168511a-4675-5e57-9882-bcd6aad88725 |  | note | • Material Delivery Docket
label | d6ede80c-fc0a-5b2e-8673-32a3989756b9 |  | note | ---------------------------------
text | 7ae4e9d4-484c-5196-8058-a0821a9b6342 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 6 - Pipes - Placement of Pipe - Flexible Pipe
label | ea9b2c26-73bd-5159-ad56-13d4444883a6 |  | note | REFERENCE:
label | df0a8c89-61af-5908-9caf-9dcbda8f0788 |  | note | • IFC Drawings
label | 10ea1cca-c5ce-584d-8487-c04f89fd2f01 |  | note | • Section 701.17
label | f189aefa-974e-52cf-a8c8-201f3bed0f4e |  | note | • Section 701.22
label | 999c966e-ca07-5def-8bce-545c9cfd52b9 |  | note | • ITP-008-CIV-Stormwater Drainage Supply & Installation - Item 5.16
label | d1eba592-0391-5d2e-9755-ea29c9e4e25b |  | note | ---------------------------------
label | c29c6f12-2cd1-52c6-8756-43a4a4ff8cc0 |  | note | ACCEPTANCE CRITERIA:
label | 26eb02a9-6d2f-5388-baa8-17910adb9df2 |  | note | 1. Correct size of pipe installed
text | 755fd166-d726-59f7-9980-83f5bb4ad29a |  | textbox | Pipe Dia ________;
text | bd5b51d9-36ed-5306-8493-9870148834b4 |  | textbox | Drawing Reference No.
label | 94eb5020-1b0b-534e-a76c-dc8b2f87e097 |  | note | 2. Pipes phycially checked and confirmed No Damage prior to install
label | 9396acc2-95b2-5a03-8251-b7c6afc8f5aa |  | note | 3. Rebate and socket ends of pipe segments placed facing upstream and be fully engaged
label | 5208c2c1-64a8-5450-8aa6-f5e64bbe1d66 |  | note | 4. Gaps between spigot and socket are in accordance with the manufacturers specifications
label | 1b23cb4b-1a7c-51d6-aa3e-5201d42ef5a7 |  | note | 5. Lower portion of pipe in contact with the bedding layer and shaped to accomodate the joint collar
label | ef3b2001-0f22-595d-b6a7-675862dc97c0 |  | note | 6. Correct type and size of rubber rings used and properly installed at pipe joints
label | 356fd3e9-152d-58e2-8516-49441efa51c6 |  | note | ---------------------------------
label | f94afdcf-389c-57c2-9fc8-b788cfa07b22 |  | note | METHOD:
label | fc7fc727-e73f-5247-ab03-1033ee705dae |  | note | • Visual inspection
label | 37160b48-cf58-56d5-9610-6e0bd77128c0 |  | note | • Measure
label | 90ef1d9a-23d0-5950-a82a-0771dd2ab279 |  | note | ---------------------------------
label | b0ac1bfb-895b-50a9-b941-519075e831a5 |  | note | FREQUENCY: Each Lot
label | cf92028c-5e85-570f-9990-6826f1723911 |  | note | ---------------------------------
label | a3e2092d-e03c-5958-ac96-a986e41b4cde |  | note | CATEGORY: IP
label | e871a691-b361-5c92-bfd9-739560e16f59 |  | note | ---------------------------------
label | a472b088-47ea-5094-ab57-066cda6f850c |  | note | RESPONSIBILITY: SE
label | 627cc046-a920-5041-94d8-150a172c9cb4 |  | note | ---------------------------------
label | 4cc828d6-0fbc-549a-972e-9587ca019c24 |  | note | VERIFYING DOCUMENTS:
label | 4232de70-cecb-55a2-be3e-a54a318883ed |  | note | • This Checklist
label | 22a4a331-0f7e-5145-be3f-1d5dbb5b9275 |  | note | • Material Delivery Docket
label | 7c88bbe6-1a19-5806-ac81-11bacda63872 |  | note | ---------------------------------
text | d7348ffa-ca5a-5216-bca0-32b965322487 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 7 - Pipes - Lifting Holes
label | 7b4ee363-78e8-5338-b4c6-64daeb6d31f8 |  | note | REFERENCE:
label | 7b3a56c4-7566-5e7b-9d72-bf95790ea04e |  | note | • Section 701.18
label | 7f603943-a231-5ec7-b894-9433ded51b8e |  | note | • ITP-008-CIV-Stormwater Drainage - Item 5.17
label | 16ce9115-a613-57ed-afe7-a9189829962f |  | note | ---------------------------------
label | 6f0987b0-04f2-52bf-bdeb-c38f12b3eb9a |  | note | ACCEPTANCE CRITERIA:
label | 3f6baa53-c3eb-502f-a20e-e265ba42473e |  | note | 1. Lifting holes plugged off in accordance with the manufacturers specifications after the pipe is installed.
label | 91ff6361-da86-544c-985e-4a0f5fc17ad5 |  | note | ---------------------------------
label | 369c1fc0-79ad-51e0-9006-0f9010f29c00 |  | note | METHOD: Visual inspection
label | 485e9410-9f2f-58a7-8255-2959d2beeae0 |  | note | ---------------------------------
label | af1e22d1-f37d-5547-a3d4-41623fdb536d |  | note | FREQUENCY: Each Lot
label | e07f2770-b879-5733-ab15-f6c9fedc86f4 |  | note | ---------------------------------
label | 89ba3910-61f9-5da3-b81a-7681b35c6971 |  | note | CATEGORY: IP
label | 14f18c2f-13e1-5d3d-af67-e834cef96ee7 |  | note | ---------------------------------
label | f031eceb-ca10-5911-ae87-0dbdd63cfc6e |  | note | RESPONSIBILITY: SE
label | 8062e0c4-cffa-5ce8-ba98-caf354279e58 |  | note | ---------------------------------
label | ff261f91-a077-5696-a19b-1b1dd6367e71 |  | note | VERIFYING DOCUMENTS: This Checklist
label | 4c114d7f-23e2-5632-a788-3c4193fbc7e3 |  | note | ---------------------------------
text | d35521a7-cc60-5c78-bc45-e105323f7a43 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 8 - Pipes - Survey Conformance
label | e59c069e-13af-55e2-a6cf-013774a063aa |  | note | REFERENCE:
label | c16d6c68-fc51-5c25-916d-2c19af494787 |  | note | • Section 710.10
label | d7a6e47d-49a6-5ac9-8892-cb0deaec7840 |  | note | • ITP-008-CIV-Stormwater Drainage Supply & Installation - Item 5.18
label | df7a3424-8a2f-5682-a88d-172677e198e8 |  | note | ---------------------------------
label | d3863150-676b-5c37-8137-76f74bd9a312 |  | note | ACCEPTANCE CRITERIA:
label | 60a957e7-8b55-52ae-80b2-3b5b39981074 |  | note | Each run of underground drainage shall be Survey verified prior to backfilling.
label | 433a677d-92f7-56c0-b552-f753888b242e |  | note | - Offset pits to kerb +/- 20mm
text | 4ee8252a-64fd-5d3f-a1f7-4d74d3dbcc98 |  | textbox | Drawing Ref No.
label | 9271cb4b-f753-5697-8360-0df819492ad2 |  | note | - Plan location pits not adjacent to kerb +/- 100mm
text | 7cff72fb-92f7-568a-8118-50fd14a1a07a |  | textbox | Drawing Ref No.
label | a6fdc512-dc97-5c42-a71d-8528092543af |  | note | - Invert level of pipes at pits +/- 50mm
text | 4abbc5c1-f673-562a-bbb2-0c54e4695e95 |  | textbox | Drawing Ref No.
label | 5b64542b-f7bb-5e8a-b1f6-7ce75c0c2c43 |  | note | - Departure from design grade +/- 10mm in 10m, provided minimum grade is not less than 1:250
text | 60fb2ab8-2674-5ab8-be1f-8d55c5fba408 |  | textbox | Drawing Ref No.
label | 17e29867-17dc-58e2-8dd6-df1444b8be3d |  | note | ---------------------------------
label | 3ada5af9-f5f4-5ad9-b387-f8990bf18e68 |  | note | METHOD:
label | 66afaf8d-d536-5efd-8369-c13920d6223c |  | note | • Visual inspection
label | 6fe3e997-f8a2-5ea5-867c-c0cc36938333 |  | note | • Measure
label | 2aea05dc-668f-5d58-89f0-55046fb43b4f |  | note | ---------------------------------
label | 8136d328-b071-57ba-9e3f-d47504f381a1 |  | note | FREQUENCY: Each Lot
label | 2b3cd24e-5fe7-5757-b54d-beab180e9543 |  | note | ---------------------------------
label | ce99ae4b-b614-5b1f-8e91-d60a2cedf0e9 |  | note | CATEGORY: IP
label | e70128fe-bfcc-5264-bc08-4e0cb1b7b960 |  | note | ---------------------------------
label | 57444569-e5a0-58d6-81e2-14a48cdac209 |  | note | RESPONSIBILITY: SE
label | 3839ae40-2967-575d-b8fa-7b420ed00f5d |  | note | ---------------------------------
label | 9f01ba70-6409-5997-aa2d-e1aba84f5540 |  | note | VERIFYING DOCUMENTS:
label | b1549a8a-e264-5fdd-9df7-3df0a4612aca |  | note | • This Checklist
label | 51888c51-2aaf-5fda-add3-8af3ae2e1f72 |  | note | • Survey Report
label | 81c7a690-bea6-5d0d-919f-61f8e55243db |  | note | ---------------------------------
text | 8ebe90a2-562d-5b3a-9939-111c651f8259 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 9 - Pipes - Backfill Placement
label | d18c858a-98b4-5221-a077-9da464e1f2d7 |  | note | REFERENCE:
label | 3e64a74b-911c-5949-b337-30a0bc4ba639 |  | note | • IFC Drawings
label | abce7f3e-6036-52f5-8b88-535af6244698 |  | note | • Section 701.16
label | e8f5121c-e2c0-56ed-aa82-252cc25bbc2a |  | note | • ITP-008-CIV-Stormwater Drainage Supply & Installation - Item 5.19
label | c1afc56d-3418-573c-a330-984eb1ef6622 |  | note | ---------------------------------
label | 6a893158-8fc8-52ed-820e-e0cf63cfae40 |  | note | ACCEPTANCE CRITERIA:
label | 094cd364-3cf5-59a2-a2a5-4dffae292de6 |  | note | 1. Correct type of Backfill material used.
label | e7872f4b-ba29-53aa-9e75-ff62e8bb14ab |  | note | 2. Backfill material placed full width of bedding material and compacted in layers <150mm loose thickness.
label | ced22cf4-35f1-53aa-9966-12df34d64f5e |  | note | 3. Filling not placed within 2.0m of the open end of the pipe.
label | 431e6fc4-fd52-556f-a9ef-95e763445350 |  | note | ---------------------------------
label | 3e9cd06a-9879-5b1a-8759-27e01f7f1ede |  | note | METHOD:
label | f4e238cb-fed0-5ce5-bec3-1a6860bdc9c5 |  | note | • Visual inspection
label | cf46d304-b4b2-5915-a9b3-63913aa18f10 |  | note | • Measure
label | d0a65b53-c664-54c7-b708-98de549315d9 |  | note | ---------------------------------
label | a80de2d5-3c6c-5129-8a3b-55f021372853 |  | note | FREQUENCY: Each Lot
label | ea1f1a1d-9758-5222-92a7-ec2986dd46ec |  | note | ---------------------------------
label | 5081c8b3-793a-5e62-98e1-8668ca81324e |  | note | CATEGORY: IP
label | 953ff398-f3c4-52c3-bf68-661e1da93590 |  | note | ---------------------------------
label | 42f40ce7-6b32-50c0-9e87-5f2037304ab2 |  | note | RESPONSIBILITY: SE
label | 09c13c42-319a-55f8-a4f2-640efdc27496 |  | note | ---------------------------------
label | d0c13d22-2897-5fed-97e2-aa1e7246d3c6 |  | note | VERIFYING DOCUMENTS: This Checklist
label | 58cf576e-7202-5f45-a9e4-32a98f0989f3 |  | note | ---------------------------------
text | c6ecb9c6-911f-584a-8516-7e18bbb8cbcb |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 10 - Pipes - Backfill Testing
label | 42215a9c-0282-5019-b79e-4bac1baae06e |  | note | REFERENCE:
label | 8864f408-d79e-5590-b9a0-f86435f790f5 |  | note | • IFC Drawings
label | 1505783e-a3cd-5784-88de-3b3bcb0936d2 |  | note | • Section 701.20
label | 66d7fa30-bbc1-5731-9b38-0fa79b3449ce |  | note | • Section 701.29
label | b66894f2-a4c9-54de-ad51-892f2de0b39a |  | note | • ITP-008-CIV-Stormwater Drainage Supply & Installation - Item 5.20
label | 94266ccc-107b-521c-81e0-4f664e25742c |  | note | ---------------------------------
label | 56e64257-7a83-59dc-a1dc-3ddefc4eb9f1 |  | note | ACCEPTANCE CRITERIA:
label | 8325f19f-4bdd-565f-a65a-5206417774e9 |  | note | 1. Tested minimum of 20% of all lots for each culvert. (Lot = 1 layer of bedding or backfill).
label | 4fe1820b-3476-5346-96fd-8e52c2616ecd |  | note | 2. Backfill material compacted to a density ratio > 97%.
label | 30902efc-2957-5fea-9506-89c9033f395e |  | note | 3. Material with ≥ 2.5% have been maintained at a mean moisture ratio of 92% between the completion of rolling and the placement of overlaying layer.
label | 48c244f4-76d1-5032-8387-b5f911efeab1 |  | note | ---------------------------------
label | 77916850-75db-56ad-8998-da2fb6291868 |  | note | METHOD: Compaction Test
label | 75829d92-63fd-5c7d-b830-57be4e7b46ef |  | note | ---------------------------------
label | 2d89138c-dff6-548e-967c-2cc0ba4fcd57 |  | note | FREQUENCY: Each Lot
label | bff8cf0e-5f9c-52e0-9e96-566378f8f951 |  | note | ---------------------------------
label | a027a232-840c-5662-ba93-857fc857c846 |  | note | CATEGORY: HP*
label | 333cc2ac-7947-5369-a48d-f35ac05ae252 |  | note | ---------------------------------
label | f432ffa4-d7da-55db-82de-3cb2e89db50a |  | note | RESPONSIBILITY: SE
label | 8dae3f14-d0f5-5ce3-acf4-3eaeeba6ed98 |  | note | ---------------------------------
label | bde8b943-3476-50d2-8048-db3735fd6ef7 |  | note | VERIFYING DOCUMENTS:
label | f25f981d-ecb0-5887-9cac-4f6d0926e364 |  | note | • This Checklist
label | 98d4fb04-c91c-53e5-93dc-1c0da552f5b4 |  | note | • Test Results
label | 46fced91-913d-5a2c-ac8f-ce10b6ec5097 |  | note | ---------------------------------
text | 3e2a86b7-c250-5635-8ba3-e5778a893515 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 11 - Flushing & CCTV
label | 223ec606-d16d-50e9-8698-c95f013bce7b |  | note | REFERENCE: ITP-008-CIV-Stormwater Drainage Supply & Installation - Item 6.1
label | da77b9e5-d128-5732-a47c-956ffd3ad66b |  | note | ---------------------------------
label | cfed7973-99d9-5172-96f7-af007843a8d9 |  | note | ACCEPTANCE CRITERIA: In accordance with Section 701.28, Section 701.30
label | d2b7a980-e9f4-578a-850a-38f1136fdee1 |  | note | ---------------------------------
label | e0205d3a-77f1-57d5-990a-714348f4cfa8 |  | note | METHOD: Record Review
label | d26c0d0d-6309-51ea-80e5-4c55a9310f5e |  | note | ---------------------------------
label | 86683f10-26ce-52e3-9776-3e1a17836447 |  | note | FREQUENCY: Each lot
label | 89dfcba3-978c-55a0-8d6d-69a236c4138f |  | note | ---------------------------------
label | b381bec0-d883-597f-9b4a-8e122945925e |  | note | CATEGORY: HP
label | dd36f027-765b-5f83-9ce2-99a9a2c65033 |  | note | ---------------------------------
label | 0c8161a1-9457-5362-8ce6-25df8fa8c151 |  | note | RESPONSIBILITY: Nominated Authority
label | 4eae47eb-9cb0-548a-9ed9-1651d1ee5655 |  | note | ---------------------------------
label | ead224f4-fe0c-5812-b826-2059a3aca106 |  | note | VERIFYING DOCUMENTS: ITP-008-CIV-Stormwater Drainage Supply & Installation
label | 8d77ecab-2eb0-50d8-820c-4a6c3089ce8e |  | note | ---------------------------------
text | 238dbd5b-73de-51fb-8fde-5c8043ddb732 |  | textbox | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 12 - As Built Survey
label | 02cbda5e-de77-5110-b9bb-925c8fa34270 |  | note | REFERENCE: ITP-008-CIV-Stormwater Drainage Supply & Installation - Item 6.2
label | ae3a83c8-796e-5c7f-b8e7-368e23bed857 |  | note | ---------------------------------
label | 4124ff31-df21-5d0c-b091-41e12b3fcd1d |  | note | ACCEPTANCE CRITERIA: In accordance with Section 701.10
label | ada45123-d9b2-56f2-8f92-0dc1c2bc6bf2 |  | note | ---------------------------------
label | 4a31779f-5220-5a2b-9450-b5228f423226 |  | note | METHOD: Document Review
label | 81d3a5de-ceac-5c4b-8375-da4473c55058 |  | note | ---------------------------------
label | 2ac9d08b-209c-5e51-9442-61c62eb75992 |  | note | FREQUENCY: Each lot
label | 1ccb1502-56a9-5255-a473-602a890d0341 |  | note | ---------------------------------
label | 43a8661f-d4b7-5bc8-a71a-cdabc7720827 |  | note | CATEGORY: IP
label | 5f52fd99-1c99-5729-98d0-5f2245a5392d |  | note | ---------------------------------
label | 2bc4674a-0c1c-5f1f-a92f-eb46d8b0d370 |  | note | RESPONSIBILITY: SE
label | a6affb12-4b10-5051-a8b2-ccaca3b3e89e |  | note | ---------------------------------
label | a274c8fd-df99-5358-9ffc-158b770b3b12 |  | note | VERIFYING DOCUMENTS: ITP-008-CIV-Stormwater Drainage Supply & Installation
label | 5e9bf8aa-9ffa-5874-bb48-1ff022c502b1 |  | note | ---------------------------------
text | 11af37d4-a2f8-5e0b-aa9c-071768509e2d |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 13 - Repairs to Damaged Pipes
label | 92f6067d-4a9b-5737-bb8a-f1d2f3423024 |  | note | REFERENCE: ITP-008-CIV-Stormwater Drainage Supply & Installation - Item 6.3
label | 2cabd0db-21cb-5d42-9199-d05ded6c2710 |  | note | ---------------------------------
label | a0127f98-f078-531b-ad4d-e4390cba34bf |  | note | ACCEPTANCE CRITERIA: In accordance with Section 701.31
label | 3cd1217b-44cd-5f2c-9b24-7dc39dbe0266 |  | note | ---------------------------------
label | fcc474a3-5d1d-5ba0-97a2-516bce4bcfa1 |  | note | METHOD:
label | 3b50ec38-36bd-5fdf-802e-3d7154cdb568 |  | note | • Document Review for Repair Procedure
label | 55e999c5-1814-59f6-ba1f-23e2e10d5a4b |  | note | • CCTV Report Review
label | 072a6ad4-adbc-53e9-a5c6-034c1fba255a |  | note | • Visual Inspection
label | 3a15ddee-2a2b-5d59-abc8-51dd65b5f431 |  | note | ---------------------------------
label | 08d216c7-c3b8-508b-8b80-be491d72e498 |  | note | FREQUENCY: Each lot
label | 0f176964-8fc4-54fc-8057-51fcab5c387b |  | note | ---------------------------------
label | f6be7a73-b82c-5076-8d86-b2e6128c7d40 |  | note | CATEGORY: HP
label | 0d4a80af-3b4c-53c6-973d-6b4b2e108317 |  | note | ---------------------------------
label | 4c8ad30f-6cca-5e16-8360-0f83f992124d |  | note | RESPONSIBILITY: Nominated Authority
label | bb9a92da-f146-5f81-a152-1351cda01e4e |  | note | ---------------------------------
label | d0bb0a36-44ab-5398-878f-78c8c1aa9664 |  | note | VERIFYING DOCUMENTS: ITP-008-CIV-Stormwater Drainage Supply & Installation
label | ff4892e5-382f-5401-9355-fc5153d3eb04 |  | note | ---------------------------------
text | f5ed33b4-2091-5bfa-b288-aa446e22cdc3 |  | textbox | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 14 - Non-conformance Report (NCR) Closure
label | 737de136-8a01-56ec-a045-cf13933c9d47 |  | note | REFERENCE: ITP-008-CIV-Stormwater Drainage Supply & Installation - Item 6.4
label | 13778a3a-5db4-5829-a7a0-62b79bb54520 |  | note | ---------------------------------
label | 2e86a138-efba-50bd-ab8b-bcb101ea5c52 |  | note | ACCEPTANCE CRITERIA: In accordance with MRPA Quality Management Plan
label | 42def169-1650-5eb2-a828-f0667022c404 |  | note | ---------------------------------
label | 3b894f6f-a14f-5b65-bab1-b555b818a2f7 |  | note | METHOD: Document Review
label | 543843b4-7c14-5894-abef-9d959cfe4544 |  | note | ---------------------------------
label | b68e0cfb-7dfa-59ee-8b13-31bea864b66e |  | note | FREQUENCY: Once, prior to closure of this lot / element / Work area
label | 0f4156ac-4ca1-58c5-82d9-7dfa96312357 |  | note | ---------------------------------
label | 368ad1ca-8a40-5f6a-9265-d6230429b384 |  | note | CATEGORY: HP*
label | 81b90a05-0c56-59d3-a1a0-f202c3b52c09 |  | note | ---------------------------------
label | 5d87f7f8-921c-56fa-95a6-40c12c62e000 |  | note | RESPONSIBILITY: PE
label | 5f07443a-320f-5469-b1ee-30fd952b4748 |  | note | ---------------------------------
label | ce41f619-0433-559f-9f54-79b4c3cb792a |  | note | VERIFYING DOCUMENTS: ITP-008-CIV-Stormwater Drainage Supply & Installation
label | 8f018539-594a-5a74-bb2f-4f5e793cf5a6 |  | note | ---------------------------------
text | 680251d5-91ba-5c8d-be70-8b22834da0f6 |  | textbox | Date Completed:
checklist-sectioned |  |  | checklist | ITP-CIV-CAMMS-Unbound Flexible Pavement Construction Rev 0 | itp |  |  |  | Yes | ITP-CIV-CAMMS-Unbound Flexible Pavement Construction Rev 0 | f744d3ee-8c8f-4d67-a40d-fdb4ba43a3d4
checkpoint-group |  |  | section | 1 - Referenced Documentation
checkpoint-status |  |  | checkpoint | Referenced Documentation
label | b55c62ca-d792-5c30-b0a4-165e6a9296ea |  | note | Document Title: ITP-CIV-CAMMS-Unbound Flexible Pavement
label | 13f61ea6-3ac9-54c7-8d07-91a9066e6cbe |  | note | ITP Description: Unbound Flexible Pavement
label | 91b15e8d-0d0b-5667-8294-4f4e79cfb9b1 |  | note | Document Number (in Teambinder): MRP-0000-MRPA-ALT-ITP-00XX
label | 793cf508-63f8-5dfa-9f91-19bbdbe8d3cc |  | note | Discipline (e.g. CIV/STR/RAIL): CIV-CAMMS-
label | c3cea942-d328-5d3d-9301-a38552e4b570 |  | note | Revision Number: 0
label | e02035c2-00ad-5a12-bc04-0339495ab972 |  | note | Revision Date: 06/09/2022
label | abe33643-1e73-5566-bd3a-285677a8a75e |  | note | ITP created by: Victor Mira
label | 4f1461ef-2092-5ac4-a88b-9338ac36061c |  | note | ITP approved for use by: Aldrin Guinchoma
label | 227fb451-4571-57fc-95ce-599f2b621019 |  | note | 1.1 - Non Dependent
label | 36666f14-99f3-509b-8ce3-015e4a2b269e |  | note | Reference Documents: IFC Drawings
label | 559a7b5a-6740-54f3-869d-fd62c4fae118 |  | note | 1.2 - VicRoads Section 173 (10/9/2008)
label | 4fba219a-4678-5882-b5cd-987e808a70d5 |  | note | 1.3 - VicRoads Section 304 (13/8/13)
label | da660cb4-376d-519e-97f7-dcdc526ca729 |  | note | 1.4 - VicRoads Section 801 (19/07/18)
label | 7130887a-d95c-5e6f-9d3a-dc7cb4e4656c |  | note | 1.5 - VicRoads Section 812 (13/07/16)
checkpoint-group |  |  | section | 2 - Preliminaries-Materials
checkpoint-status |  |  | checkpoint | 2.1 Crushed Rock Mix Design
label | 68a902b3-c1e6-58de-8a46-20956b389639 |  | note | REFERENCE:
label | 4751b681-53e9-50fb-9db1-f83c07a8cc8f |  | note | Section 304.03
label | 8366ef5e-cc0e-5be9-8149-d293b9b30d27 |  | note | Section 304.05
label | ef8fd89a-7800-54f7-b587-5a28a61016f8 |  | note | Section 812.04
label | 67800bb9-7a78-5310-a90c-6c024e688be7 |  | note | Table 812.121
label | ac927852-f881-5e43-a56c-1ca11bb27a13 |  | note | IFC Drawings
label | 56367f0e-c33c-52c9-9d34-40e4e1747f63 |  | note | ---------------------------------
label | 1fc216b2-a2c7-5b37-89b6-c99990ceb593 |  | note | ACCEPTANCE CRITERIA:
label | da489b47-34b2-5c45-b1fe-90c26f52f2e1 |  | note | All crushed rock proposed for use shall be current registered mixes in accordance with VicRoads Code of Practice RC500.02 and conform to specified requirements applicable to that class of product.
text | acbada30-6bf8-5bf5-ba43-018dbe1d3068 |  | textbox | Enter: Teambinder Material Approval number
label | 099915b6-b0d9-561c-9bb7-92e54a1116d7 |  | note | ---------------------------------
label | 3900d7b9-c07e-52fa-8f1d-86ae4e9fd37a |  | note | METHOD: Document Review
label | 2101cb7a-99ef-5ec2-bfd1-cea79804647b |  | note | ---------------------------------
label | 85b19f5a-03b1-510c-8558-23c4737fb7ad |  | note | FREQUENCY: Material conformance as per Table 812.121
label | b4a9dc93-de53-57c7-9561-921f67ffc044 |  | note | ---------------------------------
label | 555fbab6-8e5d-57a1-91cb-1d352fa09110 |  | note | CATEGORY: HP
label | d9a34524-0503-5175-892a-1c2d2e3e6c1e |  | note | ---------------------------------
label | 2d43b345-40cf-5d30-a968-821a51fa5092 |  | note | RESPONSIBILITY: NA
label | 8d4cecf1-e86b-5dc8-be7c-63e2fa39f2f9 |  | note | ---------------------------------
label | b63fcff2-a5d2-500a-a79c-0d274b0342b4 |  | note | VERIFYING DOCUMENTS: TeamBinder Material Approval Number
text | d30a2296-79f3-5e6a-8161-e8b8d8bcf821 |  | textbox | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | 3 - Preliminaries-Documentations
checkpoint-status |  |  | checkpoint | 3.1 Subgrade Preparation
label | 0a77fc9a-cd97-5345-8cff-4a6fc6d3d8f6 |  | note | REFERENCE: 304.04
label | 9dcd28bd-0e21-52f5-a571-296f0ca43c53 |  | note | ---------------------------------
label | cb8fe355-79ec-5e91-95de-540868fc6533 |  | note | ACCEPTANCE CRITERIA:
label | 94a030a0-8ac3-5b26-8c0a-981d645bfe6b |  | note | Prior to placing subbase material, the subgrade shall meet the requirements of Section 204.
label | ba45e699-1062-50d6-a60d-f2384b1e070e |  | note | Reference: Subgrade Preparation/Type fill Lot Number:
label | e65e0f0e-ac83-5c56-80fd-3e58620f803a |  | note | ---------------------------------
label | d76d8c23-44e0-5753-abed-0a5bd24e52a5 |  | note | METHOD: Document Review
label | d3d08d4b-4d83-5a85-9834-704cb4f24441 |  | note | ---------------------------------
label | 72110011-8105-5b79-83ab-918691611c35 |  | note | FREQUENCY: Each Lot
label | 8b0cfad9-5cc9-5e43-9116-cd31f46e6e47 |  | note | ---------------------------------
label | 3355057c-9191-58fb-82c2-0e2e4c78d8ff |  | note | CATEGORY: HP*
label | ac4c4c19-812f-5c8f-b649-796ca7403866 |  | note | ---------------------------------
label | a041c668-9c95-5dbe-8ac9-a28267432740 |  | note | RESPONSIBILITY: PE
label | d52543bb-4727-57f2-8082-5dc5c53b9a26 |  | note | ---------------------------------
label | f454bbb4-6c59-54cc-9591-49abecd42a2f |  | note | VERIFYING DOCUMENTS: Underlying layer Lot number
text | 778513dc-057c-5981-bec9-8982df6bb7d9 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 3.2 Select Scale
label | 6d7cc770-950a-5318-ba93-7526a788e108 |  | note | REFERENCE:
label | 9e0feb14-2d60-5d3d-9a30-684020a484ae |  | note | Project Requirement Specifications
label | 345e0b14-ff5b-501d-95f0-bab4580add89 |  | note | IFC Drawings
label | c9ea8d1a-b337-558b-8992-b7b8af7bf17e |  | note | ---------------------------------
label | 68266dd1-c597-515f-a440-08efd011da97 |  | note | ACCEPTANCE CRITERIA:
label | 169bbf9e-dcf6-557a-bbb0-2ae098ea66ea |  | note | Specify site specific scale:
text | 2ee37d7a-3f91-5504-8744-be908d03fb74 |  | textbox | Enter: Site Specific Scale (A, B or C)
label | 27c5eb12-913d-5cef-a7e7-e6164acbdaf5 |  | note | ---------------------------------
label | 6ccad292-f733-5c7f-ae80-818943703a86 |  | note | METHOD: Document Review
label | 412ccf13-5431-5267-9990-7fa814d45626 |  | note | ---------------------------------
label | 425894c3-d09f-5482-8cc3-3347d2a2b0f6 |  | note | FREQUENCY:
label | f26abbaf-eb6d-57ef-89d8-22b799a6dd2b |  | note | Prior to Commencement
label | d3083ceb-b2d9-5a35-868f-1f4e26ad6ff5 |  | note | Each lot
label | 5c59ba97-8280-55a9-bc8a-66f0e3f262cd |  | note | ---------------------------------
label | 4052575c-0a81-5592-b760-0dd21175a9cd |  | note | CATEGORY: HP*
label | 96230fa2-a7d4-5cec-8deb-18f5a366fc1a |  | note | ---------------------------------
label | 51aea4e4-e81c-58da-ac21-c24d8ed4e072 |  | note | RESPONSIBILITY: PE
label | 07cc8e69-c803-5efa-9d6f-6b48a3c6d09b |  | note | ---------------------------------
label | 1033ea59-d351-56e5-a79c-12094146064b |  | note | VERIFYING DOCUMENTS: Sign ITP
text | e1f4ea25-c5b1-55fe-a09b-c4843baac350 |  | textbox | Date Completed:
checkpoint-group |  |  | section | 4 - Pre-construction / Pre-installation Activities
checkpoint-status |  |  | checkpoint | 4.1 Survey Set-out and Lot size
label | 5409ac50-a78f-5950-8b06-bcf37ce72cbc |  | note | REFERENCE:
label | 4c19df48-11f4-531f-bc86-f6865ceb1c11 |  | note | IFC Drawings
label | cceac362-32e6-507a-ad53-4c37ca164790 |  | note | Section 304.06
label | 170aa09d-0885-5d35-a47e-0c925a63c77b |  | note | ---------------------------------
label | f2536fbe-317f-5649-a038-213dd81753c3 |  | note | ACCEPTANCE CRITERIA:
label | b7a59640-6cd5-5d6b-8df2-cb035a3e1e2b |  | note | Lot size shall be the lesser of 4000sqm or a days production.
label | 223d9cf2-cd4d-51dc-89cd-83caf06ecf51 |  | note | Set out pegs are in place and clearly mark out limits of works as per IFC Drawings and VR 304.06.
label | 77993d6a-47a9-5e11-9b74-2a0344b9ad6c |  | note | ATTACH: LOT MARKED UP LOCATION ON THE IFC DRAWING (LOT MAP)
label | 78862ad8-2c08-597d-b451-6f6913661239 |  | note | ---------------------------------
label | 1b0127dd-e441-5bf3-9f28-d8afce054975 |  | note | METHOD:
label | 03bbaece-49ba-51ee-a8b6-85409b1e8678 |  | note | Survey
label | 5e8c7bc6-8b59-5370-8374-26540f992247 |  | note | Document Review
label | a7b4571e-e366-5365-95ca-a222693655f4 |  | note | Measure
label | d6fdc7cf-b8b2-5439-834b-ae4d475f04db |  | note | ---------------------------------
label | 9d2cdf13-c855-5900-b6cc-a515aa229f1c |  | note | FREQUENCY: Each lot
label | 4f354337-be00-58e9-accd-40b8cdfeee2a |  | note | ---------------------------------
label | 1dc9dd2c-bb17-5487-9dd0-4c1d60bd872f |  | note | CATEGORY: IP
label | c79e69dc-90c8-539d-ae83-9e860a75283b |  | note | ---------------------------------
label | 3612b60d-3a6b-5de9-bbb3-a9603110d6d1 |  | note | RESPONSIBILITY: Surveyor/SE
label | baad0808-19d1-5990-906a-37a6846bc62a |  | note | ---------------------------------
label | 74f337a1-f617-587d-830b-44ef45fff1c2 |  | note | VERIFYING DOCUMENTS: Sign ITP
text | 6b29f2dc-d36c-5639-ace0-7e28e720bacf |  | textbox | Date Completed:
checkpoint-group |  |  | section | 5 - Construction / Installation Activities
checkpoint-status |  |  | checkpoint | 5.1 Crushed Rock Delivery Dockets
label | e888277f-1119-5abc-bde0-3647bfbd6740 |  | note | REFERENCE: 304.04
label | 9b32beba-3398-529a-9eb3-a4d19e57e47b |  | note | ---------------------------------
label | e1ecc8d3-5d85-5c23-8886-5cda59fe8a62 |  | note | ACCEPTANCE CRITERIA:
label | a6b49288-492f-5abd-b2ac-1ae5a31074a1 |  | note | A delivery docket for each load shall be issued to the Superintendent at the point of delivery. Check Delivery docket for compliance to the referenced Material Approval (Line Item 2.1)
label | 88c936af-18b0-51fc-b2d8-747430a81813 |  | note | ATTACH: Delivery Docket(s)
label | 011452d6-a4f6-57df-ad3f-db8feb166519 |  | note | ---------------------------------
label | 68a06e94-9efa-55c7-b92e-1f7c046c5eb8 |  | note | METHOD: Document Review
label | f7d2b292-9a4a-507c-ba5a-ef93de679049 |  | note | ---------------------------------
label | 6b907202-b678-520b-8506-116d64178633 |  | note | FREQUENCY: Each Lot
label | 267477f9-cf95-584a-8363-024cec832c52 |  | note | ---------------------------------
label | 947f035d-6efb-58b5-b824-092854a9f7d6 |  | note | CATEGORY: IP
label | d1f46f3b-a35b-54ea-a419-c01e1fcf9db4 |  | note | ---------------------------------
label | 3caab89e-bfc9-554b-a065-4dcfcb211cff |  | note | RESPONSIBILITY: SE
label | c3329b50-052c-54c4-bcea-3c0986b403e2 |  | note | ---------------------------------
label | b198e82a-183c-563b-904a-eda4658982cf |  | note | VERIFYING DOCUMENTS:
label | 6132c422-e79a-5df2-be45-21d3b0f64041 |  | note | Attached Docket
label | 6436ad19-a2ae-5872-a193-35ce744e89b8 |  | note | Sign ITP
text | 24cd4e46-6e38-5838-88f9-72d86df445aa |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.2 Placement of Material
label | 8021135a-1436-5029-b0cb-96a8fd49333c |  | note | REFERENCE:
label | 3f4067c4-d870-585d-b660-4e16952a2c43 |  | note | Section 304.03
label | ee1f82d7-82ae-5a24-968e-3ad41d06f65d |  | note | Section 304.06
label | 63a05123-8bc2-598a-9401-7d03f626a506 |  | note | Section 304.08
label | 3de5777d-3ca0-5c9c-b26a-c6ead229f516 |  | note | ---------------------------------
label | 49e70309-4983-5e6e-b417-dd3386e990a4 |  | note | ACCEPTANCE CRITERIA:
label | c85841d3-dd1d-5850-82d6-e1dc626e568b |  | note | Place and compact layer. Surface finish is smooth and uniform. Free from segregated areas.
label | 4e8d0fe1-8fa0-5ec3-9773-d5bd30221c4c |  | note | Base layer shall not exceed 150mm. Subbase layer shall not exceed 200mm. Minimum layer thickness shall be 4 times the nominal size of the material.
label | d1dfcd97-121a-50f5-892f-fd78991c19b6 |  | note | Water added to the pavement material shall be clean and substantially free from detrimental impurities such as oils, salts, acids, alkalis and vegetable substances.
label | c75e935f-40e5-5057-ac3d-a32f38ef2c4a |  | note | At no location shall water pond on the surface of any pavement layer.
label | fbd5db62-ba6b-536b-b6a0-b6b97e7848cc |  | note | ---------------------------------
label | 1d406a74-ac29-573b-b35a-568538547b59 |  | note | METHOD: Visual and Measure
label | d020afee-fac8-5ba2-a7d6-709a59be7493 |  | note | ---------------------------------
label | 7cfdcb63-aaeb-545c-b9ea-e7a9ddf586c0 |  | note | FREQUENCY: Each lot
label | 27c4e985-587b-51c8-9e83-b01c5e30e895 |  | note | ---------------------------------
label | a1dbe192-093e-5485-af8d-3a78bab7e384 |  | note | CATEGORY: IP
label | 3e8b5874-dd25-58af-a441-239088a5dd32 |  | note | ---------------------------------
label | 4ba77cfe-fe4f-550b-8f1e-55dc230895d4 |  | note | RESPONSIBILITY: SE/Site Supervisor
label | fc53907c-6bcd-576a-9f2d-2e5d6334e699 |  | note | ---------------------------------
label | e53d2792-cbb5-5125-8bad-117e2f924f53 |  | note | VERIFYING DOCUMENTS: Sign ITP
text | 03c5fa2f-caa1-530d-aaca-4125f1c757d4 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.3 Construction - Jointing
label | 64123a85-1d02-5f19-9453-4844d573de1d |  | note | REFERENCE: Section 304.07
label | ba4668de-6477-5670-8461-6a5ae415f54d |  | note | ---------------------------------
label | 539f24af-9fba-5ec9-aee8-ba60a8a5f3fc |  | note | ACCEPTANCE CRITERIA:
label | 864dd519-79f4-50e0-92c6-ab97ff7c9c4a |  | note | The layout of joints shall conform to the following requirements:
label | 0af072d6-394f-5d3d-ab66-66ba9ebd508f |  | note | (a)material shall be spread in such a manner as to minimize the number of joints;
label | 4bd06322-9544-5c96-8c06-de20a3497113 |  | note | (b)for all pavement layers, transverse joints in adjoining paver runs shall be offset by not less than 2 m;
label | 293aa40a-5624-5c73-8d3f-548e0a2b5868 |  | note | (c)transverse joints shall be offset from one layer to the next by not less than 2 m;
label | 5851416f-b2d0-5856-bfe2-cd580837e20b |  | note | (d)longitudinal joints shall be offset from one layer to the next by not less than 150 mm;
label | 4f1feef5-2283-5963-851e-6ecfa3f790e0 |  | note | (e)longitudinal joints shall be located within 300 mm of the planned position of traffic lanes lines or within 300 mm of the centre of a traffic lane.
label | 5ba5b430-c84f-5350-a141-b00bfb8907e0 |  | note | ---------------------------------
label | a008ea52-f60c-5d98-ae21-349d8aa97603 |  | note | METHOD: Visual and Measure
label | d3aef334-c0d8-5fed-87e5-78bb78ea1c92 |  | note | ---------------------------------
label | d3001caf-47ae-5d67-935e-4d884711ac6e |  | note | FREQUENCY: Each lot
label | cdbc1da8-6ff2-5ecf-ae52-a4a4a529149d |  | note | ---------------------------------
label | 4f2c5ec1-2d52-56da-94f7-e43c8608f8da |  | note | CATEGORY: IP
label | 733883d5-a871-5443-a545-980606eff550 |  | note | ---------------------------------
label | b5133e64-d470-5d51-9f01-874f3b929876 |  | note | RESPONSIBILITY: SE/Site Supervisor
label | bf948f03-ceb3-52b7-ae63-0a571afdc19b |  | note | ---------------------------------
label | 41bdf602-39cc-523b-b28a-4f6429b5ecb2 |  | note | VERIFYING DOCUMENTS: Sign ITP
text | 76dacd57-462d-5753-99e4-c913c373f31d |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.4 Compaction test (Frequency)
label | 8eecee5b-2b46-57ab-91d1-5362ecc28d53 |  | note | REFERENCE: 304 .11 (b)
label | 3a573e89-60c3-5c2d-b255-c62a548d3bf7 |  | note | ---------------------------------
label | 1dca3086-5fa6-59a5-ba35-15162f7ffdce |  | note | ACCEPTANCE CRITERIA:
label | e980943f-1537-5888-950e-2e8dfd9cbd62 |  | note | The Contractor shall initially test every lot for acceptance of compaction in accordance with the requirements of the Specification.
label | 1ba1c076-c564-5b1c-8f94-755249eba709 |  | note | The Contractor may reduce the frequency of compaction testing to the minimum test frequency (One per 2 Lots).
label | 15d9c8df-722e-5604-abb0-2b0f830e128b |  | note | Scales A and B: 6 samples
label | b7cdb2eb-cd50-5a38-a86f-017578def4c3 |  | note | Scale C: 3 Samples
label | 2a8363d9-5a75-5d22-8637-18f5f0b04d61 |  | note | Pass: Tested
label | 532b0cb4-2d40-50f4-a32e-db77e21c3973 |  | note | NA: Not Tested
label | 860d4b10-a8aa-58ff-b905-fc12cecb4fc3 |  | note | ---------------------------------
label | e003a94e-eef6-5287-b134-01eb5bc6783c |  | note | METHOD: Visual
label | 9ee6a47a-f402-5008-93b5-54ee050f6093 |  | note | ---------------------------------
label | 3a7488f0-38b7-5766-a23f-96e8038e63da |  | note | FREQUENCY: Each Lot Where applicable
label | 782c5fba-caef-5c66-95fd-0167f90cbcd3 |  | note | ---------------------------------
label | 1021c69c-3d0f-56ed-900d-584499651654 |  | note | CATEGORY: IP
label | d3e9ae6e-a945-5e6e-942b-b4abd51ad972 |  | note | ---------------------------------
label | 37e92ba0-65a0-58c7-8626-5a6055929544 |  | note | RESPONSIBILITY: SE
label | 1041ba27-50b1-575a-a56d-7733d3f838fc |  | note | ---------------------------------
label | 600a8c1f-4e05-587b-9ba7-6f24a9f1ce90 |  | note | VERIFYING DOCUMENTS: Sign ITP
text | b0b5ee3c-8310-5622-9e6c-6a8162bf8bad |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.5 Post Compaction Materials Testing (Frequency)
label | b507b699-4342-5a28-aea5-ac48c6cac71f |  | note | REFERENCE: 304.11 (c)
label | a5d5af23-a01a-53e9-bf88-70a69fd1f3e5 |  | note | ---------------------------------
label | 9e0638ae-1a18-5088-ac74-cdb9cb682e69 |  | note | ACCEPTANCE CRITERIA:
label | da2ff6e4-cc41-509e-914f-728ec3f5ee68 |  | note | ○ SCALE A: The first lot of each pavement layer shall be tested for post-compaction grading and PI. If the lot satisfies the requirements specified in 6.1 as applicable, the Contractor may test at the minimum frequency:
label | 0f9d2dc2-3598-5c28-b3e9-7712afcdbb58 |  | note | Compaction:
label | 81a2653b-8fda-5543-9096-e40701a996ce |  | note | Lower Subbase: none
label | 0fd9fe5d-f6cf-534b-9164-ac7353d6ddc0 |  | note | Upper Subbase: 1 in 4
label | 0ac3d048-5861-53f1-a1e1-51b8913fbc15 |  | note | Base: 1 in 2
label | 2069c7c6-0080-58f7-9443-a94aafb579f2 |  | note | PI:
label | 858ba2ca-eeca-5b4e-9ca0-543366de3fdc |  | note | Upper Subbase and Lower Base: 1 (two samples) in 8
label | 37d0a479-e77c-5e75-a2af-65c687781b18 |  | note | Upper Base: 1 (two samples) in 4
label | 485cec2a-0513-5c16-b762-0e7d66310019 |  | note | ○ SCALE B: the first lot of each pavement course shall be tested for post-compaction grading and PI.
label | 316b2364-ac93-59f1-819a-850f1ea59e6c |  | note | ○ SCALE C: Post compaction grading and PI testing is not required (CHOOSE NA)
label | 579f35ea-5b48-5542-8564-8fd388ae9091 |  | note | ---------------------------------
label | 16549729-6931-5d7f-87f5-5036437aff82 |  | note | METHOD: Visual
label | 80e04843-a658-58f7-bf22-98a3e8d8522f |  | note | ---------------------------------
label | 56ef0c12-cea3-5771-b7b2-a19ab8154b88 |  | note | FREQUENCY: Each Lot Where applicxable
label | d75f02ab-81c8-57c2-b40e-76e6e5a512aa |  | note | ---------------------------------
label | 84931af5-1c11-5fdb-8657-23047830793a |  | note | CATEGORY: IP
label | 2e9c2c8d-3328-52fc-8c0e-191de90ac8b2 |  | note | ---------------------------------
label | 32af05aa-d46d-5418-9b8f-fec60d590ab5 |  | note | RESPONSIBILITY: SE
label | 4d6afa15-f53d-58c7-bdad-f3650682e000 |  | note | ---------------------------------
label | 86acb60a-93cd-5887-be3a-63c9d0d8f896 |  | note | VERIFYING DOCUMENTS: Sign ITP
text | 81129061-42f6-5fbb-aa43-6b3072cd91db |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 5.6 Proof Roll
label | 436c3a55-c9f4-542c-9ff8-38c32884b96b |  | note | REFERENCE: Section 304.08
label | e3ef5946-659f-5ae2-8758-a4f417086f89 |  | note | ---------------------------------
label | d29ace57-b6cf-5013-8212-86cc74662812 |  | note | ACCEPTANCE CRITERIA: All pavement layers shall be compacted to withstand rolling and shall be test rolled in accordance with Section 173 prior to acceptance of the layer.
label | ee2920f8-bb61-52ba-ae01-fe5e45f9a058 |  | note | ---------------------------------
label | d2e78016-9b70-5b72-9eff-2417fc32f749 |  | note | METHOD: Visual
label | 7bad6757-d77d-5a7d-ae8d-dfabb95b4f33 |  | note | ---------------------------------
label | 4bd6b641-949d-5c8a-b39a-8144c277812a |  | note | FREQUENCY: Each lot
label | da7df698-a768-5127-92cf-65a242eb470d |  | note | ---------------------------------
label | fddf0efe-1dfa-5cff-b778-6bdb74967567 |  | note | CATEGORY: HP
label | 163788a4-d81f-594d-b9f3-f40c200138f0 |  | note | ---------------------------------
label | 8106c381-8e83-5474-b61d-104057cf7a6c |  | note | RESPONSIBILITY: Nominated Authority
label | df37c5f6-1b1f-5beb-af87-3e046c24022e |  | note | ---------------------------------
label | 413a0a31-4a84-53f2-98cb-52cc7cd052b7 |  | note | VERIFYING DOCUMENTS: Sign ITP
text | dff9c164-91a3-5d47-a3c0-351e611a0fd7 |  | textbox | Date Completed:
holdpoint |  |  | signoff | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 5.7 Protection of compacted layer
label | 05eec8b2-a56e-5c65-b425-426229b33c74 |  | note | REFERENCE: Section 304.09
label | 764dc145-4b8c-5cc8-a696-831bb6cbda36 |  | note | ---------------------------------
label | 24319235-d618-565d-9f28-6a9da47ea55e |  | note | ACCEPTANCE CRITERIA: The surface of each compacted layer shall be kept moist, in good condition and free from contamination until the subsequence pavement work is to commence.
label | 2567b0c4-945d-5d4b-9a04-c005587560a2 |  | note | ---------------------------------
label | 4a86fc96-c807-5f5e-b561-fe23a476c4ba |  | note | METHOD: Visual
label | 03b437f3-48d3-5f77-a43b-8c5f98f660a6 |  | note | ---------------------------------
label | 909a33c3-42f3-5d76-8c3e-07fcd4208e1d |  | note | FREQUENCY: Each lot
label | e73be73e-2caa-5a8b-9435-334d5033636e |  | note | ---------------------------------
label | d342a9a3-22ba-5ec9-b19d-32d731b56139 |  | note | CATEGORY: IP
label | d28b7024-d37d-5642-8fb2-4cd767fa3a1e |  | note | ---------------------------------
label | e01790d6-026d-5b3c-89b0-7a8cd5653259 |  | note | RESPONSIBILITY: SE/Site Supervisor
label | 8ed8244f-1839-5523-9f32-ad25e98233bd |  | note | ---------------------------------
label | 42bcd6ad-c661-55a5-ae72-f016fa54264f |  | note | VERIFYING DOCUMENTS: Sign ITP
text | 062dd11f-9616-58f3-9788-e2ac28490f0f |  | textbox | Date Completed:
checkpoint-group |  |  | section | 6 - Post Construction Activities
checkpoint-status |  |  | checkpoint | 6.1 Compaction Testing (results)
label | 85d432d4-6c9a-570f-91e6-629a343c9981 |  | note | REFERENCE:
label | f4e32e1a-b6fe-5466-bea1-0b88e395cfb7 |  | note | Section 173
label | 8f712bb4-defe-59ea-a933-37c1a597055c |  | note | Section 304.08
label | 7079092d-bd25-59a0-9e2b-652cb4b97b15 |  | note | Table 304.081
label | e411fe84-d11e-5fa9-9496-de630c30d1c6 |  | note | ---------------------------------
label | 589abf5d-285a-5439-8d17-a24df0e85fa5 |  | note | ACCEPTANCE CRITERIA:
label | 01108911-6712-5751-be85-f7a08494f74c |  | note | During compaction, material Moisture Content ≥ 85% of OMC and maintained until test rolling has been completed.
label | aca9c562-4300-5293-a22f-9e8d17f5c30f |  | note | Density Ratio to be based on tests performed with Modified Comp active Effort.
label | 221a2a46-7bd3-5c22-9500-ffdf0fc25280 |  | note | ○ Scale A:
label | e5e6adab-18c0-54ae-938f-671bbeec1a67 |  | note | – Subbase Layer Characteristic Density Ratio (CDR) ≥ 98%
label | 2f1515bb-165e-5c04-9da2-baac231cb577 |  | note | – Base Layer CDR ≥ 100%
label | b76766b4-8cf6-5e3d-8502-8034a2f9f476 |  | note | ○ Scale B:
label | c0a9ca9d-fa0a-5fb0-9d86-9e61efffb97e |  | note | – Subbase Layer CDR ≥ 97%–
label | 577cc1b3-3a37-5144-b05c-bfaab5492732 |  | note | – Base Layer CDR ≥ 98%
label | 3528040c-2567-5199-9e7d-1f92e09049fe |  | note | – 6 tests per lot for lots >500sqm. If the lot is < 500sqm, then 3 tests per lot.
label | 63058b58-127d-5b52-81b8-875a483ff8aa |  | note | ○ Scale C:
label | 6d11b966-004a-5908-b849-887bdc59a05b |  | note | – Mean Value of Density Ratio (3 tests):
label | 1de1e6ea-80d6-5bd3-bcb3-42bfbdb299cb |  | note | – Subbase Layers >98%
label | 9b52a5dc-252f-5720-b504-cecea3810693 |  | note | – Base Layers >100%
label | 6249b548-bf8b-53f7-b900-0f20a5fd0278 |  | note | ATTACH: Compaction Test Results
label | 25f6798e-eeb5-5185-8c96-3ec18b63f1d8 |  | note | ---------------------------------
label | 359cf896-8ca6-5695-9994-89b460f3bbba |  | note | METHOD: Document Review
label | 2e2cbf31-0f2d-5aca-af6c-9115b48aa7f1 |  | note | ---------------------------------
label | 52704361-bdc8-5d5f-86de-678065c24165 |  | note | FREQUENCY: Each Lot Where applicxable
label | 71d1806e-12dc-559e-b11d-0358f10670ac |  | note | ---------------------------------
label | 7fbb39ac-ad51-50e6-9a87-a30597f37e90 |  | note | CATEGORY: IP
label | 9c945e17-5e38-5ea2-bc2b-6fcd7fae42c2 |  | note | ---------------------------------
label | a202f23b-623c-5509-b1b5-b2dde76c7342 |  | note | RESPONSIBILITY: PE
label | 70a41860-71b7-56a3-a0dc-e62479cd30cd |  | note | ---------------------------------
label | 5f261207-de99-5126-a8ef-b57aee0c62e2 |  | note | VERIFYING DOCUMENTS: Compaction Test Rersults
text | 83433fe2-b080-51b3-9c8d-15ade7ca7b6e |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 6.2 Post Compaction Materials Testing (Results)
label | 513b8e86-e315-5db1-a856-2df69fbe9e79 |  | note | REFERENCE:
label | 31fff90d-b7f1-5bd5-afbc-11eced2ed0e0 |  | note | Section 304.10
label | 781cae46-8135-5359-874e-fc57594960c4 |  | note | Section 304.11
label | f65daeeb-d048-59ce-a7c6-9a1f84f236c9 |  | note | RC 500.02
label | 05788357-72d5-5995-b60b-e797d68ee422 |  | note | ---------------------------------
label | 21743c15-4db3-5604-9c79-cf9db691c0ec |  | note | ACCEPTANCE CRITERIA:
label | c04d89d7-a8ac-5d11-87c1-25e88bbb0466 |  | note | Note: Refer to IFC drawings to confirm material required. Material property requirements will vary depending on material type.
label | 75b5c973-7435-5508-aef9-6b75b005d04b |  | note | ○ 20mm Class 3:
label | 45f592d6-1945-5fc6-ac95-18c8e577d3db |  | note | – Grading
label | 3ddea421-fe35-578c-8bf4-47ae3953b58d |  | note | 26.5mm 100%
label | b4750c40-241d-5222-8a56-760755eee81e |  | note | 19.0mm 95-100%
label | f2401ea0-0eca-54ca-b36f-f4fb49c6fbeb |  | note | 13.2mm 75-95%
label | b70c938d-987f-552c-ae7c-6c42c6a52fa3 |  | note | 9.5mm 60-90%
label | e1a3c8a5-4eb6-52a2-9606-d2204f20833c |  | note | 4.75mm 42-76%
label | 078676b2-5201-53fc-a7ff-a8058b2cb81b |  | note | 2.36mm 28-61%
label | 86c7bb21-ec27-57eb-b64c-193db13ed4ec |  | note | 0.425mm 14-29%
label | 3124e430-4cf6-532c-a6b2-3b66e59db80f |  | note | 0.075mm 6-14%
label | de401da6-9ab2-5da4-956f-dc5c0f22cccd |  | note | PI between 0 to 10
label | 461e843d-b478-5ff7-a68b-6c64b7cd0fe0 |  | note | ○ 20mm Class 4:
label | 4dcd3bb4-7eca-58b6-a1cc-204255b8706f |  | note | – Grading
label | d8369a0d-92cc-501a-9bce-863178479d5d |  | note | 26.5mm 100%
label | 43c19236-42ba-5332-8623-d2e568828df8 |  | note | 4.75mm 42-76%
label | 5f6c1716-785b-527b-a24a-ed7c70e976e2 |  | note | 0.425mm 10-28%
label | 5ee8ec8d-86b9-524e-8df7-772609a9dee3 |  | note | 0.075mm 2-14%
label | deeef6e8-8c43-5000-841d-46cd6f0a24f2 |  | note | PI between 0 to 20
label | 45672309-51fd-50b2-9f3d-ffe2b83e6112 |  | note | PI x % passing 0.425 mm sieve (max) 450
label | cb06c1ef-8283-5132-b42d-b705c223ddd6 |  | note | ○ Scale C: Post compaction material te
label | 6c89b3fc-8d22-55d3-8c72-c3682f3d63c3 |  | note | ---------------------------------
label | 484e37b2-afdc-5b38-9627-fb4c23b5f342 |  | note | METHOD: Document Review
label | 875a1b92-887d-5778-9ae3-ca9d69fbe79e |  | note | ---------------------------------
label | 29fd9910-1802-5016-966a-cdae2f93fe57 |  | note | FREQUENCY: Each Lot Where applicable
label | 39cd36af-4b92-5781-bba1-4dcb8affec4e |  | note | ---------------------------------
label | 6002bb76-8930-556d-a914-31c56e22c18f |  | note | CATEGORY: IP
label | c3fa00cd-28f4-5bbf-bd85-1d5b5642bf1d |  | note | ---------------------------------
label | e3eca85f-abc7-5f41-b835-2ae0b5f4557f |  | note | RESPONSIBILITY: PE
label | 652ce04c-220c-579d-8fd9-8aca4552514d |  | note | ---------------------------------
label | c361a182-ac46-5253-b266-4119a9fc975c |  | note | VERIFYING DOCUMENTS: Compaction Test Rersults
text | c1e5dbc3-1643-5ed6-b90c-40416a02ee28 |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | 6.3 Survey As-Built - Surface Level
label | 09a18864-81ae-526a-9689-e749deda7e62 |  | note | REFERENCE:
label | f1f1e660-e4dd-5292-9f1c-abb723e0a4dc |  | note | IFC Drawings
label | f0262e6a-0e62-506f-836a-f6bc2a022a8c |  | note | Section 304.06
label | 8dc87aac-7c92-5426-9621-70a7d0cc4cc3 |  | note | Table 304.061
label | 7065bbff-a65b-5462-b501-a4782e82fecf |  | note | Table 304.062
label | 4a100fce-5675-5309-85b2-deca0551efae |  | note | ---------------------------------
label | 00037401-05f9-5321-b6a6-90d2a9633e89 |  | note | ACCEPTANCE CRITERIA:
label | cec57e67-6746-5957-90ab-e12c7e38489f |  | note | No point on the surface of any pavement layer shall vary by more than 8 mm from a 3 m straight edge placed in any direction.
label | cee12b34-33fc-5b2e-ab1a-2cbcad30ef1d |  | note | Subbase course shall be not < the specified thickness by more than 15 mm.
label | 95f9d542-8e6f-5924-a3ae-0506dbcbafee |  | note | Base Course shall be not < the specified thickness by more than 10 mm. The avg. thickness over every 100m shall not be < specified thickness.
label | d771d4af-b012-5c5c-9c89-6e2e990563af |  | note | The combined thickness of subbase and base courses shall be not < the specified thickness by more than 15 mm.
label | a0c46964-1526-5a07-b1a6-45e194764894 |  | note | ○ Scale A: A minimum of 80 measurements per lot
label | e900a0e5-0215-5b94-8284-48c02e7bdbe9 |  | note | Subbase: mean range +4mm to -8mm, maximum Standard Deviation of 8mm
label | e95b82a6-c5a0-5523-a85f-da0d2a48950c |  | note | Base: mean range ±5mm, maximum Standard Deviation of 8mm
label | 377ba864-1658-57cf-b1d9-dc54734452a8 |  | note | ○ Scale B: A minimum of 40 measurements per lot
label | 59242fc7-7163-5d4b-8611-55ef6076c227 |  | note | Subbase: mean range +6mm to -12mm, maximum Standard Deviation of 13mm
label | 28d868ec-0a0c-5bd3-a476-b7f53e3488cf |  | note | Base: mean range ±8mm, maximum Standard Deviation of 10mm
label | a6a6221d-3bb5-5c58-9f24-e6ff08cf2f78 |  | note | ○ Scale C:
label | 268559e6-f051-5554-9718-4217592c3e58 |  | note | Lower Subbase (mm) +15/ -25
label | bab41298-b6be-585f-8641-4662942476c9 |  | note | Upper Subbase (mm) +10/ -25
label | 1593b53b-202b-5541-8b75-9eb657a30b70 |  | note | Base (mm) +/-15
label | 8323ed6f-f6bc-59c0-afdd-5ab4a0c3c61f |  | note | ---------------------------------
label | b36345d6-71dd-51fd-afd5-1bf4f9429b64 |  | note | METHOD: Document Review
label | f0f90a9b-4ed2-55d4-8210-19273fe72597 |  | note | ---------------------------------
label | 508dce27-1df2-5661-a131-772f88f75134 |  | note | FREQUENCY: Each lot
label | 404fe49d-18b4-55e1-8e7a-8fb49df33373 |  | note | ---------------------------------
label | 4c74e684-d08c-54e9-8cf9-f226ef378843 |  | note | CATEGORY: IP
label | 82285ee8-50dc-5f94-991f-6612bdb35eda |  | note | ---------------------------------
label | ba98b8dc-2aa2-5cce-a494-4418b282a37c |  | note | RESPONSIBILITY: PE/Surveyor
label | a9c04c23-4a3a-5b6f-94e4-4fc54437bf76 |  | note | ---------------------------------
label | 3b910d95-599b-5354-95d7-ff2d038a7baa |  | note | VERIFYING DOCUMENTS: Survey Conformance Report
text | a5e3ef50-8e92-5128-9dab-248deabb16fd |  | textbox | Date Completed:
checkpoint-status |  |  | checkpoint | Metropolitan Roads Program Alliance Final Inspection
label | 466a1ce8-e38e-5edb-9ae0-330f1362419a |  | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
text | 3f9dca37-9bf9-58ab-82ae-87009338a9d8 |  | textbox | Name:
text | 217c0efb-6411-59ce-b868-f024c44b8d48 |  | textbox | Position:
text | 2fad6147-33e2-5546-a328-edf245079e42 |  | textbox | Date Completed:
holdpoint |  |  | signoff | Sign ITP