## res_ITP-CIV Delineation Fence R
type | name | values | prefix | postfix | usage count | user addable | template name
checklist-flat | CHK-004-STR-CAMMS-RSS Walls-Fill Placement | itp |  |  |  |  | CHK-004-STR-CAMMS-RSS Walls-Fill Placement
checkpoint | CHK-004-STR-CAMMS-RSS Walls-Fill Placement
label | Document Title: CHK-004-STR-CAMMS-RSS Walls-Fill Placement
label | Check list Description: RSS Walls-Fill Placement
label | Discipline (e.g. CIV/STR/RAIL): STR
label | Revision Number: 0
label | Revision Date: 19/12/2022
label | ITP created by: Victor Mira
label | ITP approved for use by: Victor Mira
checkpoint | 1 - Soil reinforcement - Straps
label | REFERENCE: 682.08
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA:
label | • Reinforcing elements shall be placed on top of the compacted fill material and connected to the wall panels.
label | • Any twists, kinks, sags or deviations in the reinforcing elements shall be removed prior to the placement of fill material on the reinforcing.
label | – – – – – – – – – – – – – – – – –
label | METHOD: Visual
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Each strap
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: IP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: SE/PE
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: This Checklist
label | – – – – – – – – – – – – – – – – –
textbox | Date Completed:
checkpoint | 2 - Soil reinforcements - Connections
label | REFERENCE:
label | • IFC Drawings
label | • Schedule of lengths: MRP-052-C-RFL-DRG-33-CBE-CSW-1302,1403,1503,1602
label | • Connections arrangement: MRP-052-C-RFL-DRG-33-CBE-CSW-1901
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA:
label | Grid Strips are to be installed at the back of each panel in correct length and to the correct anchors at the back of each panel
label | – Bolts are to be snug tight.
label | – – – – – – – – – – – – – – – – –
label | METHOD: Visual
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Each Fill Layer
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: IP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: SE/PE
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: This Checklist
label | – – – – – – – – – – – – – – – – –
textbox | Date Completed:
checkpoint | 3 - Soil reinforcements - Plan arrangement
label | REFERENCE:
label | • IFC Drawings
label | • Arrangements: MRP-052-C-RFL-DRG-33-CBE-CSW-1102 to 1104
label | • VR682.06
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA:
label | Plan positions of Grid Strips are to be as IFC Drawings.
label | – Grid Strips shall not overlapped
label | – Grid Strips are not to pass over pile cap. RSS used in conjunction with a bridge abutment shall be independent of the bridge structure.
label | – – – – – – – – – – – – – – – – –
label | METHOD: Visual
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Each fill layer
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: IP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: SE/PE
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: This Checklist
label | – – – – – – – – – – – – – – – – –
textbox | Date Completed:
checkpoint | 4 - Soil reinforcements - vertical deviation
label | REFERENCE: IFC Drawings
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: The vertical deviation of the soil reinforcementshall be within +1% upwards and -0.3% downwards of the soil reinforcement length, relative to the connection height
label | – – – – – – – – – – – – – – – – –
label | METHOD: Measure, Survey
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Each fill Layer
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: IP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: Surveyor/SE
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: This Checklist
label | – – – – – – – – – – – – – – – – –
textbox | Date Completed:
checkpoint | 5 - Fill-Pacement
label | REFERENCE: 204.10
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA:
label | • Fill layers to be spread and compacted in layers not exceeding a compacted thickness of 200mm
label | • All RSS fill layers to be spread from the back face of panel to tail of soil reinforcing straps
label | – – – – – – – – – – – – – – – – –
label | METHOD: Measure, Visual
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Each fill layer
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: IP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: PE/SE
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: This Checklist
label | – – – – – – – – – – – – – – – – –
textbox | Date Completed:
checkpoint | 6 - Select backfill - moisture content
label | REFERENCE: IFC Drawings
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Moisture content of the backfill shall be maintained evenly at all times. Moisture content shall be within 0% to -2% of the optimum moisture content. Any backfill material exceeding the optimum moisture content, must be allowed to dry
label | – – – – – – – – – – – – – – – – –
label | METHOD: Measure
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Each Fill Layer
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: IP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: PE/SE
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: Attached Test Results
label | – – – – – – – – – – – – – – – – –
textbox | Date Completed:
checkpoint | 7 - Select backfill - placement
label | REFERENCE: IFC Drawings
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA:
label | • Select backfill shall be placed in accordance with Vicroads section 204 and compacted to 98% of standard proctor density.
label | • Compaction within 1 meter of the wall face shall be achieved by a light weight (Hand Operated) mechanical tamper roller or vibratory system. No large compaction equipment shall be allowed in this zon. Compaction beyond 1 meter of the wall face shall be in accordance with the table VR 204.111
label | – – – – – – – – – – – – – – – – –
label | METHOD: Measure
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Each Fill Layer
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: HP*
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: PE/SE
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: This Checklist
label | – – – – – – – – – – – – – – – – –
textbox | Date Completed:
checkpoint | 8 - Select backfill - reduced frequency
label | ACCEPTANCE CRITERIA:
label | After three consecutive lots of like material have achieved the specified requirement, the contractor may seek the superintendent's agreement to reduce the frequency of testing of subsequent lots to the minimum requirement specified in table 204.142:
textbox | Three Consecutive Lots tested to satisfy this requirement.
label | – – – – – – – – – – – – – – – – –
label | METHOD: Document review
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Each Fill Layer
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: IP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: Nominated Authority/PE
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: Referenced Lots in This Checklist
label | – – – – – – – – – – – – – – – – –
textbox | Date Completed:
checkpoint | 9 - Select Backfill - Testing frequency-acceptance
label | REFERENCE:
label | • IFC Drawings
label | • VR 204.14
label | • VR 682.16
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA:
label | • Testing frequency shall be in accordance with Vicroad Specification section 204.14
label | • The Contractor shall submit compaction test results for each layer of fill placement to the Superintendent for review and acceptance. No further fill placement shall be allowed if the total thickness of fill placement is greater than 1 m measured from the last layer that has been accepted. If any layer is found to be not in compliance with the compaction requirement, that layer and the layers above it shall be removed
label | Attach: Compaction test results
label | – – – – – – – – – – – – – – – – –
label | METHOD: Measure
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Each Fill Layer or every second layer as agreed
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: HP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: Nominated Authority
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: Attached Test Results
label | – – – – – – – – – – – – – – – – –
textbox | Date Completed:
holdpoint | NOMINATED AUTHORITY HOLDPOINT
checkpoint | 10 - Select backfill - acceptance
label | REFERENCE: VR 204.12
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: All layers of fill shall be test rolled in accordance with VR 173. The contractor Shall provide for the superintendent to be present during all test rolling
label | – – – – – – – – – – – – – – – – –
label | METHOD: Visual
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Every Fill Layer
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: HP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: Nominated Authority
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: This Checklist
label | – – – – – – – – – – – – – – – – –
textbox | Date Completed:
holdpoint | NOMINATED AUTHORITY HOLDPOINT