## res_ITP-CIV Delineation Fence R
type | name | values | prefix | postfix | usage count | user addable | template name
checklist-flat | CHK-005-STR-CAMMS-RSS Walls-Precast Panel installation | itp |  |  |  |  | CHK-005-STR-CAMMS-RSS Walls-Precast Panel installation
checkpoint | CHK-005-STR-CAMMS-RSS Walls-Precast Panel installation
label | Document Title: CHK-005-STR-CAMMS-RSS Walls-Precast Panel installation
label | Check list Description: RSS Walls - Panel installation
label | Discipline (e.g. CIV/STR/RAIL): STR
label | Revision Number: 0
label | Revision Date: 19/12/2022
label | ITP created by: Victor Mira
label | ITP approved for use by: Victor Mira
checkpoint | 1 - Panels-survey set out-Tolerance
label | REFERENCE:
label | • IFC Drawings
label | • MRP-052-C-RFL-DRG-33-CBE-CSW-1201
label | • MRP-052-C-RFL-DRG-33-CBE-CSW-1202
label | • MRP-052-C-RFL-DRG-33-CBE-CSW-1203
label | • MRP-052-C-RFL-DRG-33-CBE-CSW-1204
label | • VR 682.20
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Plan position shown on the drawings at the base of the wall shall not exceed ±15mm (refer to drawings for WP locations)
label | – – – – – – – – – – – – – – – – –
label | METHOD: Measure
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Base course panels
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: IP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: Surveyor/PE
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: This Checklist
label | – – – – – – – – – – – – – – – – –
textbox | Date Completed:
checkpoint | 2 - Panel installation
label | REFERENCE:
label | IFC Drawing:
label | ○ Schedules:
label | • MRP-052-C-RFL-DRG-33-CBE-CSW-1302
label | • MRP-052-C-RFL-DRG-33-CBE-CSW-1403
label | • MRP-052-C-RFL-DRG-33-CBE-CSW-1503
label | • MRP-052-C-RFL-DRG-33-CBE-CSW-1602
label | ○ Instructions:
label | • MRP-052-C-RFL-DRG-33-CBE-CSW-1803
label | • MRP-052-C-RFL-DRG-33-CBE-CSW-1804
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA:
label | RSS Panels are to be installed as per IFC Drawings and specified schedule.
label | – Check for correct architectural pattern
label | – Check for Weephole Locations
label | – Check the 19mm nominal gap to be maintained
label | – Check the 1 in 40 slope is to be maintained
label | – – – – – – – – – – – – – – – – –
label | METHOD: Visual, Measure
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Each panel
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: WP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: SE
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: This Checklist
label | – – – – – – – – – – – – – – – – –
textbox | Date Completed:
checkpoint | 3 - Panel installation - Abutment interfaces
label | REFERENCE:
label | • IFC Drawings
label | • MRP-052-C-SME-DRG-32-MPK-CSW-2052
label | • MRP-052-C-RFL-DRG-33-CBE-CSW-1105
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA:
label | – 20mm nominal gap between panels and Abutment wall is to be maintained
label | – 300mm wide x 6mm thk Galvanized plates fixed to abutment wall and Adjacent panel as per IFC drawings.
label | – 600mm wide BITAC tape installed
label | – – – – – – – – – – – – – – – – –
label | METHOD: Measure
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Where applicable
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: IP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: SE/PE
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: This Checklist
label | – – – – – – – – – – – – – – – – –
textbox | Date Completed:
checkpoint | 4 - Drainage - base of the Wall
label | REFERENCE:
label | • IFC Drawings
label | • MRP-052-C-SME-DRG-32-MPK-CSW-2053
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA:
label | To install 300mmx300mm Granular backfill in Geotextile BIDIM A64 around 100mm Dia. Perforted plastic pipewith 0.5%min fall to 50mm Dia weepholesin RSS panels.
label | – Geotextile BIDIM A64
label | – 300mmx300mm Granular backfill
label | – 100mm Dia. Perforted plastic pipe
label | – Perforated pipe to have 0.5% mnimum fall to 50mm weepholes in RSS panels
label | – – – – – – – – – – – – – – – – –
label | METHOD: Visual
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Each wall
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: IP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: SE/PE
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: This Checklist
label | – – – – – – – – – – – – – – – – –
textbox | Date Completed:
checkpoint | 5 - Filter fabric - Installation
label | REFERENCE:
label | • IFC Drawings
label | • MRP-052-C-RFL-DRG-33-CBE-CSW-1803
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Install Filter Fabric against all vertical and horizontal joints
label | – – – – – – – – – – – – – – – – –
label | METHOD: Visual
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Each course of panel installation
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: IP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: SE
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: This Checklist
label | – – – – – – – – – – – – – – – – –
textbox | Date Completed:
checkpoint | 6 - Drainage - Strip Drain
label | REFERENCE:
label | • IFC Drawings
label | • MRP-052-C-SME-DRG-32-MPK-CSW-2053
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA:
label | • Install 150mm wide vertical strip drain "PRODRAIN PD20"-at every vertical joint between panels in RSS wall.
label | • Ensure no gap is formed between strip drain and RSS panels
label | – – – – – – – – – – – – – – – – –
label | METHOD: Visual
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Each course of panel installation
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: IP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: SE
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: This Checklist
label | – – – – – – – – – – – – – – – – –
textbox | Date Completed:
checkpoint | 7 - Panel installation - Survey reference points
label | REFERENCE: VR 682.21
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: To ensure compliance with the tolerances specified in clause 682.20, the Contractor shall install stable and permanent survey reference points on a not more than 5 m (horizontal) by 2 m (vertical) grid covering the whole face of the RSS
label | – – – – – – – – – – – – – – – – –
label | METHOD: Visual
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Each course of panel installation
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: IP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: Surveyor/SE
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: This Checklist
label | – – – – – – – – – – – – – – – – –
textbox | Date Completed:
checkpoint | 8 - Panels installation - Conformance Survey
label | REFERENCE:
label | • IFC Drawings
label | • VR 682.06
label | • VR 682.17
label | • VR 682.20
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA:
label | The level and alignment of each course of facing panels shall be checked progressively after placement of each course and prior to placement of the next course to ensure compliance with the dimensional and positional tolerances stated in the design. The Contractor shall record the results of this checking together with details of any non-conformances and the associated corrective actions
label | – Relative displacement of adjoining smooth panel faces shall not exceed ±15mm measured normal to face of the wall
label | – Local deviation of the wall face at any location with a 3m straight edge, shall not exceed 15mm
label | – Variation in gap width between facing panels shall not exceed 5mm per meter length and 10mm over the full lenght of the gap
label | – The wall level shall not deviate from the specified level by more than ±20mm
label | – The tolerance of position measured at the top of the wall face shall not excedd 5mm per 1m of wall height
label | – The verticality of the RSS wall facing shall lean backward at a minimum slope of 1(H) in 40 (V)
label | Attach: Survey Report
label | – – – – – – – – – – – – – – – – –
label | METHOD: Survey, Measure
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Each course of panel installation
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: HP*
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: Surveyor/PE
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: Survey Report
label | – – – – – – – – – – – – – – – – –
textbox | Date Completed: