## Master List Templates
Id | Type | Name | Values | Prompting Name
ec7948c3-7b89-4ab1-9a90-bd066e43ba05 | checklist | ITP-000 - Pre - Construction Rev1 | itp | ITP-000 - Pre - Construction
506e5e0e-4e8d-414c-bc28-45f44fcfae34 | section | 1.0 - Pre-Construction Checklist
bb1b890f-0cb3-4c5a-a6f5-446b4065d82e | checkpoint | 1.1 - Communication (1)
e6f27722-502f-58c2-b426-2305736b810c | note | ACTIVITY / DESCRIPTION: Community and emergency services
6258feca-81d0-5706-bf01-9d7eed536c8f | date | Date:
4f6316b9-fedf-499d-9762-6cd5cc620113 | checkpoint | 1.1 - Communication (2)
137e7b09-4d54-57aa-9ea8-39c135260c65 | note | ACTIVITY / DESCRIPTION: Emergency response plan
83221d13-ffc0-5de9-bbca-0f2d05b3bb00 | date | Date:
db95abb7-c978-4764-a800-6de2d2b0385e | checkpoint | 1.2 - Approved Construction Documentation (1)
2c70a2e1-e3c5-594a-ad68-52f8fb752c64 | note | ACTIVITY / DESCRIPTION: IFC drawings (PDF, hardcopy)
3c20a521-3ae2-5314-8779-3a3f6c5b25f2 | date | Date:
1ed25072-4fcc-4fd4-8ddc-ba434ce7df22 | checkpoint | 1.2 - Approved Construction Documentation (2)
11dbcb17-275f-5dbb-84b8-1ea8d03d3bf7 | note | ACTIVITY / DESCRIPTION: Digital (CAD) files (Surveyor)
18063c05-15b8-58b4-b289-2c22f5bec7be | date | Date:
628a0d05-08b8-4c6a-83d9-70116d2c05be | checkpoint | 1.2 - Approved Construction Documentation (3)
4ce8e019-0bf8-568f-a1a1-9c77a6d5b1ce | note | ACTIVITY / DESCRIPTION: Budget / Resource arrangement POs (incl. sub-contract agreements)
5b8904b9-7e7a-5642-9e32-209e001adc65 | date | Date:
d91fe6f8-7fb3-4faf-9207-97bf00c9d4b9 | checkpoint | 1.2 - Approved Construction Documentation (4)
645bf9e9-61d0-551b-8ab2-742fc17952ee | note | ACTIVITY / DESCRIPTION: Quantities / Specifications
a5bd8f41-895a-5c25-a239-ab3a71a6b63e | date | Date:
f4719456-1071-4d3c-9fec-7385ad8384bd | checkpoint | 1.3 - Dilapidation Report (records and photographs) (1)
23a39979-2f30-542b-b34f-b8a606c6ecd3 | note | EXTERNAL REFERENCE: Hold Point (HP)
430309b8-514a-5878-a61d-c0b20019dc09 | note | ACTIVITY / DESCRIPTION: Residential (ie: structures, access/gate, letterbox, fence)
f3e08c44-dffe-5016-851a-e4bd3ea02bcb | date | Date:
6b04975a-d93d-4e71-9ca6-b5620cd15ce9 | signoff | AUTHORITY HOLDPOINT
12ca0316-e4de-42f3-8da6-662f03ddc498 | checkpoint | 1.3 - Dilapidation Report (records and photographs) (2)
7244d7e9-09bc-5133-a337-962e3e7de2e3 | note | EXTERNAL REFERENCE: Hold Point (HP)
08f48c8c-b29b-5bde-a5c0-5db75156e260 | note | ACTIVITY / DESCRIPTION: Business (ie: structures, access/fence/gate, signs/letterbox)
e8d3772c-485d-5d46-9833-578b30de8cd3 | date | Date:
3b40ac63-c535-47f1-8bdb-74def4c4f850 | signoff | AUTHORITY HOLDPOINT
2ebe271c-fc0b-490f-9d92-2bca7c1006f5 | checkpoint | 1.3 - Dilapidation Report (records and photographs) (3)
b1161ed9-9fef-5fe8-932d-82e2ed9a07e4 | note | EXTERNAL REFERENCE: Hold Point (HP)
4d1b6287-c606-58af-8dd2-12cff0abd6fc | note | ACTIVITY / DESCRIPTION: Agricultural (ie: access, livestock, fence/gate)
a42d04c0-ff2c-5436-b2e8-1ee9ecca2e17 | date | Date:
ab37b5a7-57ce-443e-80ad-61c24a6ac789 | signoff | AUTHORITY HOLDPOINT
9e76dc01-ccf0-4e89-bcda-311dc9659e9a | checkpoint | 1.4 - Heritage / Cultural listed areas: (1)
0a20d56b-1eb3-556d-9026-612a8fa504e5 | note | EXTERNAL REFERENCE: Hold Point (HP)
412f68fa-a9c9-598c-b8aa-cfab9f73f067 | note | ACTIVITY / DESCRIPTION: "No Go Zone"
dda313ea-2131-587c-af5d-c4d40276d947 | date | Date:
b76e7864-4c8a-497d-a0bb-715d25c76419 | signoff | AUTHORITY HOLDPOINT
44686010-6df2-4a6f-a41f-fa5f012e3c45 | checkpoint | 1.4 - Heritage / Cultural listed areas: (2)
2b46c0bb-336b-5ab5-b694-14ba8d5d95c0 | note | EXTERNAL REFERENCE: Hold Point (HP)
89ae91b8-c56e-5dd4-bf0b-f12f14621ea4 | note | ACTIVITY / DESCRIPTION: Tourist attraction
1169444e-24c2-53a9-a0d8-1a1c5a55c794 | date | Date:
46976b36-15f5-43a6-9f48-7cdffceaeb5e | signoff | AUTHORITY HOLDPOINT
ece9aae3-7806-4437-9989-b248534b3792 | checkpoint | 1.5 - Protected Environment (1)
232def67-1d5f-56c3-9e6b-a93553ecf3bf | note | EXTERNAL REFERENCE: Hold Point (HP)
5f975cc0-b2ff-5564-9a4a-9869b241de7a | note | ACTIVITY / DESCRIPTION: Flora
1a139fbf-6379-53d4-a909-b1eb5f584d67 | date | Date:
74258bbf-360c-488d-a28a-50eaee22af78 | signoff | AUTHORITY HOLDPOINT
9d211495-a126-4974-92e5-1c9026df4e00 | checkpoint | 1.5 - Protected Environment (2)
2ee6f03e-b2de-58e1-8e08-34073ff0ed93 | note | EXTERNAL REFERENCE: Hold Point (HP)
0ef2076f-8f1b-5547-8c97-07f89b68d45f | note | ACTIVITY / DESCRIPTION: Fauna
935ae3a8-2680-5fcf-bb60-0e80e35c1d84 | date | Date:
3b9d9fef-f609-4eb2-a8db-df35a6280651 | signoff | AUTHORITY HOLDPOINT
8f77462d-ce5e-4bd0-bd70-742f0eec3929 | checkpoint | 1.5 - Protected Environment (3)
8361494e-2ef3-5ef6-9324-99c0d60afdea | note | EXTERNAL REFERENCE: Hold Point (HP)
bb94b0e4-1ff6-5ed6-9518-b52104666749 | note | ACTIVITY / DESCRIPTION: Water bodies
a6320b06-2180-525b-9324-83467fdac279 | date | Date:
0c39cbb8-dea7-4094-82bb-a9dcf68b775f | signoff | AUTHORITY HOLDPOINT
b753e1dd-55d2-4f32-b18b-3b13286788bd | checkpoint | 1.6 - Site Pre-start checklist, and supporting documents (1)
4d0e7d85-db70-50b2-a112-4be2c7a2bc40 | note | ACTIVITY / DESCRIPTION: Dial Before You Dig
b9512c41-5e6f-50b4-b302-2b1e86969f05 | date | Date:
d2c13cf0-661d-4123-b565-8bcb0faa0c7b | checkpoint | 1.6 - Site Pre-start checklist, and supporting documents (2)
9f9f74aa-fef9-5389-85cf-68a058f0cad0 | note | ACTIVITY / DESCRIPTION: Excavation Permit
fb1b3d1a-ffa9-5c89-84bc-935a0f14c755 | date | Date:
754225c2-8308-4714-9a7c-6fc32c6bc7fd | checkpoint | 1.6 - Site Pre-start checklist, and supporting documents (3)
eb0da7a7-b40d-516f-8a21-70da80294ea9 | note | ACTIVITY / DESCRIPTION: Assess and arrange for Service location
aa3db215-a525-5952-a488-c96443dc8e40 | date | Date:
024486ff-edc7-40d5-bf72-8850f1e7d2af | section | 2.0 - Pre-Commencement Checklist
73e71e67-a3aa-4ee4-a041-46b45cbc5b32 | checkpoint | 2.1 - Traffic Items (1)
219e153c-34ac-530c-9618-b17528289be5 | note | ACTIVITY / DESCRIPTION: VMS boards
d59c19b3-ab5e-55d6-8f72-65bf2cc933f2 | date | Date:
c1c93cbe-a777-492c-9e6e-0fbf59983d24 | checkpoint | 2.1 - Traffic Items (2)
40537772-448f-5021-b861-346ce535c0ab | note | ACTIVITY / DESCRIPTION: TGS/TMP, MoA
bc22d5d7-8d2a-5cf5-95b0-8f1ce1f61d65 | date | Date:
a373fe9c-e74e-40b4-9b65-1682d1557bc2 | checkpoint | 2.2 - Site marks / references (1)
7222e648-5ebb-54d7-a3ee-4f53060f49a9 | note | ACTIVITY / DESCRIPTION: Limit of Works
2ec47ee6-abfb-523f-878d-1e0a376b9c9b | date | Date:
14c7cb9d-f208-426b-8022-f86375318965 | checkpoint | 2.2 - Site marks / references (2)
c4196c09-8497-5e7d-abcb-7084bab05b35 | note | ACTIVITY / DESCRIPTION: Survey control point
97e3fe00-ed0e-5fc9-940e-e4cdbf31cc77 | date | Date:
4dee1a61-622e-41b5-8aa5-fd7c5781f4cb | checkpoint | 2.3 - Services, inspect/identify clash points: (1)
7ba32668-63a5-5faf-8d34-0c6454d68734 | note | ACTIVITY / DESCRIPTION: Sewer, Water
09ec3b17-bf39-5023-b2b6-6f4b1d5d5694 | date | Date:
e54a5eed-5f32-4a1c-ad5e-e8e1766818da | checkpoint | 2.3 - Services, inspect/identify clash points: (2)
71cbea25-cdec-5fe4-b4f0-8072a81257df | note | ACTIVITY / DESCRIPTION: Gas, Electricity
71ff9c9f-86fa-5791-bcb0-7249db27aa35 | date | Date:
312527e0-5e5f-4b4b-bec0-c033036a4b46 | checkpoint | 2.3 - Services, inspect/identify clash points: (3)
9346209e-8d80-5310-af05-a3bae73bcbd8 | note | ACTIVITY / DESCRIPTION: Telecommunication
1bbd0831-b4b7-50da-b126-635c3fdc6f91 | date | Date:
5597bfce-7124-45f5-9cc6-ccc4725e1487 | checkpoint | 2.3 - Services, inspect/identify clash points: (4)
a60de8f4-24d0-5fcd-82ca-c112ab21741d | note | ACTIVITY / DESCRIPTION: Drainage (ie: council/shire, Other state authority)
74d84631-64fd-5ed8-a4b2-61860885b26e | date | Date:
1b77da62-2c91-4b45-9592-2097031f5220 | checkpoint | 2.3 - Services, inspect/identify clash points: (5)
01bcd3e6-26ab-5137-b622-4c9ca69ff619 | textbox | ACTIVITY / DESCRIPTION: Other specify:
1b5693cf-1601-59cc-a48d-f4bb08991699 | date | Date:
a622f273-5f8b-441b-9028-0d4a48324858 | checkpoint | 2.4 - Site-Traffic Risk Assessment, including: (1)
0c804654-ad59-51f1-ae7d-48e6e9bf0b04 | textbox | ACTIVITY / DESCRIPTION: O/H and U/G services flagged "No Go Zone"
8b2724e9-7df2-5d6d-908f-87549f86fb0f | date | Date:
c3c63897-0579-4ff8-a8f3-e058ee326284 | checkpoint | 2.4 - Site-Traffic Risk Assessment, including: (2)
abbda1d3-7c6c-5e6c-af72-571fd4a345d3 | textbox | ACTIVITY / DESCRIPTION: Trees(s) marked and approved for trimming or removal
021cf184-01a0-51cf-9446-c83bb22da090 | date | Date:
27221d83-48eb-4d78-b372-5b83bb209154 | checkpoint | 2.5 - SWMSs reviewed: (1)
1eacaf2c-c04e-5ff7-9325-90d9c48cec31 | textbox | ACTIVITY / DESCRIPTION: Site-specific
0bb07632-2f94-5ea7-a558-b820930f1c99 | date | Date:
bc2295c1-f237-404a-8c3b-8ac54367d715 | checkpoint | 2.5 - SWMSs reviewed: (2)
e036ee75-e886-54cf-acd2-e0bbf47e014c | textbox | ACTIVITY / DESCRIPTION: Spotter required / arranged
05881025-1e77-5f01-837d-8867dbd8482d | date | Date:
66b75e59-aa24-441c-9afd-c14f48b00ba4 | checkpoint | 2.6 - Site Access (incl. VicRoads pre-commencement - meeting with superintendent) (1)
028de256-9b8e-54ba-8a3e-7d74d3933972 | textbox | ACTIVITY / DESCRIPTION: Sight and Clearance Distances:
b208738c-f16c-5770-af3e-17763ba4a610 | date | Date:
1ee340b3-1ac5-486e-ac75-1a9f45fcfac3 | checkpoint | 2.6 - Site Access (incl. VicRoads pre-commencement - meeting with superintendent) (2)
1058298f-9ad0-5d19-90b5-7eeef3daea9c | textbox | ACTIVITY / DESCRIPTION: Stop-slow areas, spotter, slips, confined space/work at height
9198d1a5-6aca-5001-bf77-f68519df304c | date | Date:
6995948b-0c19-4f77-8fb1-f3d9472f8178 | checkpoint | 2.6 - Site Access (incl. VicRoads pre-commencement - meeting with superintendent) (3)
de6ee94b-8e54-525b-9c9b-187403b8d828 | textbox | ACTIVITY / DESCRIPTION: Vehicle access to properties
72dd73e5-6cb0-5b64-84ed-1e80acab2035 | date | Date:
0d337ec7-94c9-4562-8598-49a0f5c4f661 | checkpoint | 2.6 - Site Access (incl. VicRoads pre-commencement - meeting with superintendent) (4)
bd2bf265-6826-5882-8aca-cd6edac5340c | textbox | ACTIVITY / DESCRIPTION: Proximity to Services: clearance requirements
b5dfec9a-0ae6-5ed7-b5cd-13852792b5da | date | Date:
ead8a1f3-7559-4f03-9352-98fc6eaf5c40 | checkpoint | 2.6 - Site Access (incl. VicRoads pre-commencement - meeting with superintendent) (5)
0afa1408-8f65-5dec-a111-19f431215f85 | textbox | ACTIVITY / DESCRIPTION: Proximity to Water: supply point, watertable/dam/river/coast/port
f2848b2c-8df4-52d5-af73-65e26d4d1b87 | date | Date:
ef92f9df-7eb2-435d-b79a-c265ddc5f624 | checkpoint | 2.6 - Site Access (incl. VicRoads pre-commencement - meeting with superintendent) (6)
2d84ae2b-3d7c-599a-86d3-b3e7ebd46e40 | textbox | ACTIVITY / DESCRIPTION: Site compound/Plant parking, material stockpile area, "dumpsite"
e051b90b-cac2-5bda-8101-6cdcfec749b8 | date | Date:
a393892b-b867-45d1-8c2f-9133392571d6 | section | 3.0 - Construction
f4eb0f64-3d11-4bf2-a816-73172d1b42d5 | checkpoint | 3.1 - Vegetation Removal (1)
1cab15f0-5e7b-5c96-a725-76781f197099 | note | EXTERNAL REFERENCE: Hold Point (HP)
37e5a847-d5ec-5561-ac5f-748f41747f5f | note | ACTIVITY / DESCRIPTION: Spotter, Traffic Control
469f7783-cce5-5766-8600-c0ba06b3e33b | date | Date:
e561e711-c152-4d07-b21d-66df85f66441 | signoff | AUTHORITY HOLDPOINT
55e0a9cb-cfce-496f-a205-bbbca7a9f903 | checkpoint | 3.1 - Vegetation Removal (2)
a859cd75-a4c1-54c0-afbc-a300243a2e1a | note | EXTERNAL REFERENCE: Hold Point (HP)
d5b0f6a4-2099-5ae9-87ab-76e906d0d5e9 | note | ACTIVITY / DESCRIPTION: Equipment, Access
923e39d6-c933-5b25-92a2-17a4c7d97360 | date | Date:
797081e5-8338-4e4f-bfeb-98917c58692c | signoff | AUTHORITY HOLDPOINT
1d860393-f8bf-45b7-bf83-f55c7f174e58 | checkpoint | 3.1 - Vegetation Removal (3)
77fc8179-01a8-5de1-be4e-a37535b31a98 | note | EXTERNAL REFERENCE: Hold Point (HP)
87c85ec8-5ae7-5d2a-adc8-98a01d70a7ac | note | ACTIVITY / DESCRIPTION: Soil erosion / water contamination
f6aed4ff-758c-5563-aaec-3d02eaf92d2d | date | Date:
b0a58810-0af8-4066-b9fb-a71b31e17b1e | signoff | AUTHORITY HOLDPOINT
b7321300-f332-41f3-a265-1234b410b202 | checkpoint | 3.2 - Contaminated Materials
862c77d5-a076-5349-aa81-bcb31ec4949b | note | ACTIVITY / DESCRIPTION: Contaminated Materials
32e3f890-2c02-52ea-bf37-1a874b0b9ec8 | date | Date:
8aa6e0cc-5d25-4a60-a9d7-6a55fbce6ceb | checkpoint | 3.3 - Traffic Items (1)
3cec7a10-622c-5e33-8373-42a2631396b5 | note | EXTERNAL REFERENCE: Hold Point (HP)
5e1e9cc2-8a6d-5a3c-8cb5-7b5d3b9221ba | note | ACTIVITY / DESCRIPTION: External review: Road Safety Audit
59c52f51-46d5-5079-b49c-1171224b7fd4 | date | Date:
6bbd4b82-1dea-409f-9277-9c4bef46ff23 | signoff | AUTHORITY HOLDPOINT
cc6495e2-124b-4074-bf86-4e454507afa5 | checkpoint | 3.3 - Traffic Items (2)
8eb94ed4-6acc-5864-8445-d5fd59ccbc9d | note | EXTERNAL REFERENCE: Hold Point (HP)
15ec0df4-b540-5603-94f9-a7bf4bd688e6 | note | ACTIVITY / DESCRIPTION: Internal review: adjust hold-time (traffic lights / traffic controller), flowbias, identify peak-hour period(s) / public transport / rubbish collection
ba2d424f-e07d-5a9f-803d-32be44fddeaf | date | Date:
ca55ed71-9ef2-41b8-b237-2dcf62379026 | signoff | AUTHORITY HOLDPOINT
4954d163-13e4-4ee9-899b-268a99781b67 | checkpoint | 3.4 - Trenching works (1)
fd7bbf0d-957b-5f55-a51e-1efc04516634 | note | ACTIVITY / DESCRIPTION: Review escape plan (routes)
7593820d-1516-5ada-9470-03e9b001907d | date | Date:
75296157-50a4-447a-b649-98848df5a9ab | checkpoint | 3.4 - Trenching works (2)
a5fa4824-9515-5be5-99c1-6bb10b5e2b94 | note | ACTIVITY / DESCRIPTION: Review ground / water conditions
e3d10731-e374-597a-a285-8c9b94b7f8e3 | date | Date:
bca066ad-6d6e-4587-b58d-491f4dbc743e | checkpoint | 3.4 - Trenching works (3)
c1be90d4-adf0-5abe-8239-6f205b20eeeb | note | ACTIVITY / DESCRIPTION: Indentify Shoring / Benching requirements
c61d7548-b876-50b5-8132-bd371b837029 | date | Date:
eb267d9b-e897-48e3-82d6-ef9236856089 | checkpoint | 3.5 - Drainage Works (1)
f6dd6785-19a9-5698-9390-35804760059b | note | ACTIVITY / DESCRIPTION: Assess surface-water impact – flow-path / catchment / outlet
15f9c08d-de9c-5eee-bbb8-b51160f6ec31 | date | Date:
a001a3cf-22d2-4c20-873b-1e738cde50ac | checkpoint | 3.5 - Drainage Works (2)
f7e2f46b-d835-57a2-ae6e-10d853f18e72 | note | ACTIVITY / DESCRIPTION: Surface drainage (swale drain)
67f68621-d3c7-5577-97fd-10a4936f7510 | date | Date:
dcb3d0b2-d044-4e31-bd29-a386ccfb4319 | checkpoint | 3.5 - Drainage Works (3)
0c8e4bb0-500f-5729-9a5b-10e6f778a663 | note | ACTIVITY / DESCRIPTION: Sub-surface drain pipe and aggregate (agricultural drains / "agi pipe")
a255cb4c-8eaf-5175-baf8-816cc0270fa4 | date | Date:
2dc63166-00f5-4cac-ab3e-806aed2ba661 | checkpoint | 3.5 - Drainage Works (4)
479ffa13-c5fd-518b-9d9f-ea8dc618374f | note | ACTIVITY / DESCRIPTION: Review confined space entry
398f8d24-c01b-5cd6-abf4-266f570fad88 | date | Date:
cfdf667c-2ba5-49a4-9408-7a8591fe58a3 | checkpoint | 3.5 - Drainage Works (5)
b9164c3b-7b37-567f-982f-c03c51acb950 | note | ACTIVITY / DESCRIPTION: Review lifting methods (load / equipment / plant / crane)
283b5fa8-b68d-50da-a580-5cf7faa7b029 | date | Date:
7f3d683d-f3b5-4086-978c-2a5c63d1252c | checkpoint | 3.5 - Drainage Works (6)
5e6fc178-5be6-51d5-865c-698d223474b8 | note | ACTIVITY / DESCRIPTION: Levels
d2918e5e-86c9-54dc-8127-aab434333995 | date | Date:
bfccd875-e979-42cb-971d-e1f4b3474e3f | checkpoint | 3.5 - Drainage Works (7)
1662e6a7-0386-52bd-8a9f-f566df06206d | note | ACTIVITY / DESCRIPTION: Pit covers / Grates
1da7eb42-be09-58cf-8f39-047f3abc1436 | date | Date:
bec5c66f-230c-4036-9d20-a021e24f4b76 | checkpoint | 3.6 - Structural Items (1)
5bb36a25-8acb-51b9-ba68-3da979928c87 | note | EXTERNAL REFERENCE: Hold Point (HP)
9cf22238-c949-53ac-aa7f-fe054762c153 | note | ACTIVITY / DESCRIPTION: Crown units / culvert
cf184cf2-88a5-52c2-9b80-7670ae16b74f | date | Date:
4ebe9f6f-fc5d-4692-808f-beeee483c5a9 | signoff | AUTHORITY HOLDPOINT
8da2805d-0e6a-4075-b5c2-f70636883660 | checkpoint | 3.6 - Structural Items (2)
7a9ebbed-de21-56c8-a434-272bb7dc3d41 | note | EXTERNAL REFERENCE: Hold Point (HP)
b4ec60d2-620b-5720-adbf-39d8cc1a3f17 | note | ACTIVITY / DESCRIPTION: Retaining structure works
a856f55b-4c73-57b2-8e5e-23f893cf1244 | date | Date:
85aaa81b-691a-4b99-8e28-35b3cce01f9d | signoff | AUTHORITY HOLDPOINT
fab14ed3-3bda-422d-aea0-44462df3aef2 | checkpoint | 3.6 - Structural Items (3)
db904c1f-778c-5ee3-a73a-ecdd449010be | note | EXTERNAL REFERENCE: Hold Point (HP)
ad0a05bd-65a9-5358-be6a-07628591fd3b | note | ACTIVITY / DESCRIPTION: Bridge works
fb431245-769c-5726-bd68-d70cad3c3751 | date | Date:
3256c727-9df6-4346-9a8d-a74be95568b2 | signoff | AUTHORITY HOLDPOINT
b54bd7aa-dd80-475b-a572-b814c27c71df | checkpoint | 3.7 - Concrete kerb works: (1)
4e83a662-87af-584f-8d91-292cab1937d1 | note | ACTIVITY / DESCRIPTION: Alignment / level
9084ffe3-5527-5440-b8d1-8d5d3a1be359 | date | Date:
73ec6383-3102-44c3-91bc-7088f2fe3391 | checkpoint | 3.7 - Concrete kerb works: (2)
ed1dc1f0-117c-5394-96ff-2ad947d3db58 | note | ACTIVITY / DESCRIPTION: profile / finish
ed0df4d6-4539-5db6-9d53-f10d384e2757 | date | Date:
980487b0-24c5-4273-a598-11ff8b37d2d3 | checkpoint | 3.8 - Concrete Works (1)
9cb9c99d-31ff-5065-9de0-5c9efe86cd01 | note | EXTERNAL REFERENCE: Hold Point (HP)
4555486a-0e50-5c78-97e9-5acc7489a8e2 | note | ACTIVITY / DESCRIPTION:
e290765f-51b5-580b-8cf5-66b3be991bb3 | date | Date:
c3488558-a77d-485b-8b94-1f986cdb7522 | signoff | AUTHORITY HOLDPOINT
8ad63936-0e1a-4300-8882-88d2325e3399 | checkpoint | 3.8 - Concrete Works (1)
cbddb7dc-7965-527e-8604-d0f59ed7cf96 | note | EXTERNAL REFERENCE: Hold Point (HP)
79934066-2a33-55b4-b790-32e626d8074d | note | ACTIVITY / DESCRIPTION: (in-situ & pre-cast) - Bedding material / blinding material
e10c73aa-244b-56d5-9b3b-677156da6681 | date | Date:
a19049ed-7ac2-418e-a4ff-2c91334bb8b8 | signoff | AUTHORITY HOLDPOINT
ce96ee44-2c12-4fd9-84a8-fd71e6814422 | checkpoint | 3.8 - Concrete Works (2)
df46743f-9e58-5dc9-acce-7c996c1b0db0 | note | EXTERNAL REFERENCE: Hold Point (HP)
c0df993f-67d3-581c-bbf2-47691fed7330 | note | ACTIVITY / DESCRIPTION: (in-situ) - Formwork, duct-work
4ae24711-c212-5c14-a915-8ec828dde90d | date | Date:
4fd4c7a2-690a-485d-b364-dc9f3f3a7441 | signoff | AUTHORITY HOLDPOINT
8fd4143a-d3f5-4d84-96fe-cf55e66e911b | checkpoint | 3.8 - Concrete Works (3)
4b5a48b0-275b-5eaf-a393-1b7bfc67ef83 | note | EXTERNAL REFERENCE: Hold Point (HP)
57b1b11a-1cae-5935-83cf-3a545eba2023 | note | ACTIVITY / DESCRIPTION: (pre-cast) Alignment/dimensions
aebe87c5-1f12-595a-a287-6b3a1be6dac6 | date | Date:
0a043d4e-c975-4545-9181-1f5e5613eba4 | signoff | AUTHORITY HOLDPOINT
cf3f2a86-4e76-4739-82ad-9b20e72ea05d | checkpoint | 3.8 - Concrete Works (4)
46b7835c-3393-50ce-bc2a-ac65a53757e3 | note | EXTERNAL REFERENCE: Hold Point (HP)
a6d0a595-de69-5bf4-8c9c-096947c82311 | note | ACTIVITY / DESCRIPTION: (in-situ) - Rebar layout
adef0c6e-e4a3-5d5e-ae57-f80fcf047b39 | date | Date:
8dafd2b1-8146-46b3-890d-f60a776511f9 | signoff | AUTHORITY HOLDPOINT
4f4404b0-e73e-4c25-a76a-2466a8403eb5 | checkpoint | 3.8 - Concrete Works (5)
42910eff-d18b-5269-87d0-c1ec995729fd | note | EXTERNAL REFERENCE: Hold Point (HP)
d140611b-6ba1-55b0-a7dd-7af3e430efd3 | note | ACTIVITY / DESCRIPTION: (in-situ) - Concrete mix / Compaction / Placement method(s)
187420f9-647a-5bc2-8b0e-d53ad848608c | date | Date:
8e4160a3-1bde-4820-998c-a4d4c3ca0f79 | signoff | AUTHORITY HOLDPOINT
9fefc923-eef2-4b1c-a0ed-5b1390fc1a10 | checkpoint | 3.8 - Concrete Works (6)
604bbfa1-4836-5ad2-85b5-9b7006c2ee8a | note | EXTERNAL REFERENCE: Hold Point (HP)
262509b8-ced2-597e-a5cb-a75976506bb5 | note | ACTIVITY / DESCRIPTION: (pre-cast) - Lift points / placement method
3551f2cf-f97b-5556-b09e-1cfc50d7cd5b | date | Date:
2976a003-b4ff-41a8-bb88-682d21cd7e8b | signoff | AUTHORITY HOLDPOINT
42b27439-aae0-479c-96be-f27ab5427ca5 | checkpoint | 3.8 - Concrete Works (7)
cbe630c5-4be8-57e4-a782-def703791116 | note | EXTERNAL REFERENCE: Hold Point (HP)
43422f83-6406-5907-85ae-4d6ef87f137d | note | ACTIVITY / DESCRIPTION: (in-situ & precast) - Pre-stress works (where applicable)
b93c9931-f628-5460-8b05-e02bef831907 | date | Date:
0a6f5824-24f1-4b1f-a3f4-d9621dea5785 | signoff | AUTHORITY HOLDPOINT
6118b315-e4d3-485a-bc8a-5fdac3ce0d06 | checkpoint | 3.8 - Concrete Works (8)
a1534231-1814-58fe-8bc9-0bf703c80aa8 | note | EXTERNAL REFERENCE: Hold Point (HP)
3959aebd-efe2-51e1-991c-f987dc9057ac | note | ACTIVITY / DESCRIPTION: (in-situ & precast) Finish
419da4d6-6b52-5eb8-a145-7761e51949d4 | date | Date:
c405d90e-f0fb-4399-bf7a-b56330b49f5f | signoff | AUTHORITY HOLDPOINT
89c0daa7-7f02-48b7-8bbb-8b3097541cd6 | checkpoint | 3.9 - Unsuitable sub-grade / sub-base / Stabilisation treatment (1)
9be36065-a1cb-5a8e-ac1d-008886293ed7 | note | EXTERNAL REFERENCE: Hold Point (HP)
93b5a13e-e894-50d5-813b-574ff6463518 | note | ACTIVITY / DESCRIPTION: Require in-situ testing / laboratory report (where required)
d7ae2396-94a0-5a9e-ad3f-4fc6496cb7f2 | date | Date:
06036741-40d7-4332-b711-9140ce7d4f6f | signoff | AUTHORITY HOLDPOINT
30454fe1-eb90-465c-a078-1336dec66ab1 | checkpoint | 3.9 - Unsuitable sub-grade / sub-base / Stabilisation treatment (2)
662603f2-d921-5a27-9a6a-8aae01dd1522 | note | EXTERNAL REFERENCE: Hold Point (HP)
dec3ec97-d98c-5dc5-bc16-78aa064e6223 | note | ACTIVITY / DESCRIPTION: Material dockets (ie: Lime / Cement)
a928a9c0-b4cf-578b-8b39-287e73f04aa1 | date | Date:
1b279548-1bd4-45e8-ad5f-a0477359a71e | signoff | AUTHORITY HOLDPOINT
773d00cd-66ea-444e-a86d-d6aab077d1a6 | checkpoint | 3.9 - Unsuitable sub-grade / sub-base / Stabilisation treatment (3)
73d4214b-096b-5466-afed-f123a7ae0be7 | note | EXTERNAL REFERENCE: Hold Point (HP)
637f418b-0705-5ad7-be69-c5eb1b133b14 | note | ACTIVITY / DESCRIPTION: Density results
d17488cc-60b5-52fd-aed6-fa9f858227b3 | date | Date:
a08daee9-f5c0-47bf-9ef2-e68064c69b4c | signoff | AUTHORITY HOLDPOINT
e322bad3-404f-4587-a749-b127f1733122 | checkpoint | 3.9 - Unsuitable sub-grade / sub-base / Stabilisation treatment (4)
43e8db1c-d6ae-5f22-bf9d-fd7fa721f92d | note | EXTERNAL REFERENCE: Hold Point (HP)
2c6b4a52-154a-567b-83ac-6335e46b90ef | note | ACTIVITY / DESCRIPTION: Proof-roll
4a684b97-6d96-500d-9bab-b42ad14eb5f0 | date | Date:
68e6916d-15a8-4029-9acd-e6ecb75accee | signoff | AUTHORITY HOLDPOINT
361f7507-c152-4740-92f9-9bab00978d3c | checkpoint | 3.10 - Pavement Works (1)
edb85706-5505-58cb-b813-ca93cab573f1 | note | EXTERNAL REFERENCE: Hold Point (HP)
9a7c7cd5-75c1-559f-ad83-297c8eefb6cf | note | ACTIVITY / DESCRIPTION: Density results
a4d15a2b-d3a1-5fab-ba52-8a62234442cc | date | Date:
0ea5c1c2-5872-4eb1-9773-33e6a47a21df | signoff | AUTHORITY HOLDPOINT
dc5002f5-ad85-4d60-8978-9fa1caa01d9b | checkpoint | 3.10 - Pavement Works (2)
6c86a36e-1c2b-5900-9305-a897701fbfaa | note | EXTERNAL REFERENCE: Hold Point (HP)
1de26549-c9bf-5c7a-9eaa-41e96afbb8f8 | note | ACTIVITY / DESCRIPTION: Proof-roll / Test Rolling
3cb70c70-be7c-5660-8cfa-82c5ef680799 | date | Date:
ffd0760a-f76f-4e58-b23c-af422768bd31 | signoff | AUTHORITY HOLDPOINT
1ce26c32-7d5d-4787-8e9b-621b400222e2 | checkpoint | 3.10 - Pavement Works (3)
c4e732d4-e269-534e-b8ff-2075a0067d2a | note | EXTERNAL REFERENCE: Hold Point (HP)
2f8f5c5c-716c-5297-9b78-b3ac06b2af32 | note | ACTIVITY / DESCRIPTION: Dryback results (NB: required prior to sealing works)
0be33575-9e08-5ec5-b0a7-07e0175b3568 | date | Date:
8799fc49-1764-4723-b282-9a3711007f67 | signoff | AUTHORITY HOLDPOINT
9cda9b78-24d5-45dd-9984-1b4606177db7 | checkpoint | 3.10 - Pavement Works (4)
d7a587fc-196e-5a63-a5c6-212e4e55d1e7 | note | EXTERNAL REFERENCE: Hold Point (HP)
4a7351f6-c346-5c8c-8f1b-9335c2c07056 | note | ACTIVITY / DESCRIPTION: Ball Penetration Test
ff7308a0-2a8f-5b16-95ba-4e268d9cdfb6 | date | Date:
7f24d8c8-60fe-438f-ac2c-3e81bfcab2cc | signoff | AUTHORITY HOLDPOINT
98858a12-4a3c-4ef8-b53b-04c0226f49d1 | checkpoint | 3.11 - Utility Services, Traffic / Public lights (1)
5773b127-b81a-59f2-8961-672edfd9d95d | note | ACTIVITY / DESCRIPTION: Level & Location (ie: clearance requirement)
f189c5a2-7632-58d2-9a88-63c4f15d3a9b | date | Date:
8eaf6c32-b2b7-4e5a-9444-fefe6d20fb66 | checkpoint | 3.11 - Utility Services, Traffic / Public lights (2)
6e5385a5-3b7b-57a5-9e20-4abae3b4dd32 | note | ACTIVITY / DESCRIPTION: Approved equipment for installation
344c5d9e-d7fa-523a-9adc-9342f1201129 | date | Date:
91890935-158e-40b9-aa71-f19066499b7d | checkpoint | 3.11 - Utility Services, Traffic / Public lights (3)
351e38af-d749-5dd5-a727-e13be1354ae3 | note | ACTIVITY / DESCRIPTION: Pit and conduit (ie: clearance requirement)
841cac14-37b0-5904-a230-e2d543a86a05 | date | Date:
af8f1ce1-2ccc-4f1a-bfe2-62237911c846 | checkpoint | 3.11 - Utility Services, Traffic / Public lights (4)
66d4152f-0178-5442-9850-46f8432d38a9 | note | ACTIVITY / DESCRIPTION: Audits by relevant authority / hand-over procedure
4bdf3e18-b201-5d17-bc7e-e515011c3707 | date | Date:
6402d019-4706-44f4-819d-e6cb9407f3cd | checkpoint | 3.12 - Pavement Surface Works (1)
ffc06c16-b190-5e53-bc27-6600c528ef48 | note | EXTERNAL REFERENCE: Hold Point (HP)
88072e80-0d0e-54a3-a817-664b21923bf8 | note | ACTIVITY / DESCRIPTION: Seal (ie: suitable material, spray-sheet details)
dc023705-525d-5f81-ac0b-6ee6d18d4c1a | date | Date:
2256846d-1f29-4cda-9ada-91c2812e4359 | signoff | AUTHORITY HOLDPOINT
814b5b45-90dc-4ae1-a32b-6fb45003c251 | checkpoint | 3.12 - Pavement Surface Works (2)
701c8aed-f5de-5658-b4a7-e37c6c8d96af | note | EXTERNAL REFERENCE: Hold Point (HP)
2ad4e868-dbe8-5fd4-852f-6d03091b4759 | note | ACTIVITY / DESCRIPTION: Asphalt (ie: material dockets)
bbe2ee03-df3f-5846-bab3-63112b143462 | date | Date:
8da7637c-d95f-451c-9b8c-65c644c46282 | signoff | AUTHORITY HOLDPOINT
1189fa11-6530-4708-bc0d-3b9bd96b760b | checkpoint | 3.13 - Landscape (1)
c47bca78-c4ea-5663-9d0a-5df4fb629fb6 | note | ACTIVITY / DESCRIPTION: Seed / Grass
a8ba22b6-cbab-581d-b38d-3879ae33d9b1 | date | Date:
30b90162-863e-4a8e-b5b7-5ffe496c1950 | checkpoint | 3.13 - Landscape (2)
7eeecf5b-d93f-5eb5-969d-45bfd2a14f02 | note | ACTIVITY / DESCRIPTION: Hydro-seed / Hydromulch
02ddacd0-cb66-509e-a8fc-991d63944896 | date | Date:
7228ee54-a67f-47ab-ab42-333d14c6f328 | checkpoint | 3.13 - Landscape (3)
978d6ef9-0791-5752-8f9b-d22f16335e00 | note | ACTIVITY / DESCRIPTION: Street furniture
54eff99d-8058-572a-8821-4cf0cc0d27ff | date | Date:
e4261a40-ef24-4c51-a4f7-bc560ddf8099 | checkpoint | 3.13 - Landscape (4)
27f493b8-64d2-54df-89d4-b769b0c5ead8 | note | ACTIVITY / DESCRIPTION: Maintenance arrangement / period: 3 / 6 / 12 / 18 / 24 months
6576b4e3-3f41-56b6-8461-793e8f9ab4ac | date | Date:
bd642e35-645a-453b-8f53-a719e45d6db8 | section | 4.0 - Practical Completion
2db86639-1a42-4f81-85a0-4c7259c608a2 | checkpoint | 4.1 - Road Fixtures (1)
43e329bb-76af-5d73-bf31-7d2d1c998a95 | note | EXTERNAL REFERENCE: Hold Point (HP)
895211b8-1959-551b-94f6-1dc94f3edf17 | note | ACTIVITY / DESCRIPTION: Linemarking & RRPMs
a6b12caf-efb8-5009-8c20-aa99cdac572b | date | Date:
2ffbb314-993b-4819-af5d-58665dab80bd | signoff | AUTHORITY HOLDPOINT
064dae2c-3dd1-49da-be8f-473db404c1e9 | checkpoint | 4.1 - Road Fixtures (2)
1dc0757e-c689-5ea7-b9e6-90022cb23c44 | note | EXTERNAL REFERENCE: Hold Point (HP)
3e5ce256-eb21-50d4-8b3d-b23f076ab26a | note | ACTIVITY / DESCRIPTION: Signs
96ad4902-844e-5471-897c-fd2b53716465 | date | Date:
f16224fc-7bcf-4d79-8783-477672ce87b4 | signoff | AUTHORITY HOLDPOINT
1f9b40f7-9ad9-4b17-addf-4291fa82fe28 | checkpoint | 4.1 - Road Fixtures (3)
811c64f3-46d9-5823-a1ab-4fcb5a84c4c8 | note | EXTERNAL REFERENCE: Hold Point (HP)
df4ddbb5-52d9-5811-9374-e9d912e4ec0f | note | ACTIVITY / DESCRIPTION: Guide posts
44f78845-cdea-5ee0-a1f4-8b3edca7bc64 | date | Date:
3c861e70-53d6-4db0-97e8-5af62e436823 | signoff | AUTHORITY HOLDPOINT
317b0749-52a8-4c74-a9de-638fef256931 | checkpoint | 4.2 - Safety Barrier Works (1)
f07a90d3-e3cb-505c-b092-e69dfea0c102 | note | EXTERNAL REFERENCE: Hold Point (HP)
6ee626b0-c424-5d0d-93a2-5b94acf51dfa | note | ACTIVITY / DESCRIPTION: Guardrail
35fb547a-5a20-597a-b810-a975f004cde9 | date | Date:
752024bc-ebd4-4f2c-a845-25285c5b3594 | signoff | AUTHORITY HOLDPOINT
1aebfb00-53c7-4133-afe7-03a51992cd0d | checkpoint | 4.2 - Safety Barrier Works (2)
92df4c2e-1ae0-5253-8610-51bc4e1b06cd | note | EXTERNAL REFERENCE: Hold Point (HP)
bba34ff1-9ea3-5518-bf6d-8b1ccf5f0a6a | note | ACTIVITY / DESCRIPTION: Wire-rope
383afdcf-e884-503b-9ead-39cc532fcb27 | date | Date:
31f46e23-7fc4-437c-b162-969574f0b050 | signoff | AUTHORITY HOLDPOINT
da547094-b943-4ebf-a00b-878e57be9d33 | checkpoint | 4.2 - Safety Barrier Works (3)
b81129e8-8a67-579f-aeb3-2bcea3ae949b | note | EXTERNAL REFERENCE: Hold Point (HP)
80752d29-196a-59a9-ab60-4e99af91433d | note | ACTIVITY / DESCRIPTION: Motorcycle-safe fixtures
ad117929-0402-5f2d-86fb-edba7ab78eaf | date | Date:
87cbc774-0f7f-47bf-870d-955bd54f22cd | signoff | AUTHORITY HOLDPOINT
0953ff2b-a116-4f0f-8221-861e448041f9 | checkpoint | 4.3 - Fences and Gates
f7230881-6417-504c-b6f7-d940307940be | note | ACTIVITY / DESCRIPTION: Fences and Gates
f2194732-7626-548f-b712-894db3509011 | date | Date:
e6640a44-1781-4873-b1ed-b0259b4af084 | checkpoint | 4.4 - Quality Ride Test
ad48874f-e750-5ab1-9613-8d0376132bb0 | note | EXTERNAL REFERENCE: Hold Point (HP)
9e52f830-712c-5482-ae98-710d53ecb076 | note | ACTIVITY / DESCRIPTION: Quality Ride Test
482837ee-0bbd-5cbd-bc87-72edadbc2dee | date | Date:
3c817810-95c6-4723-8b4c-d1722e2ec43f | signoff | AUTHORITY HOLDPOINT
cfb3a837-b1d3-4291-a6c1-3ff1cdda929b | section | 5.0
7e48ef31-bbd7-4beb-a7d9-94cf9a680775 | checkpoint | 5.1 - End-of-Defects liability period (EDLP): 3 / 6 / 12 / 18 / 24 months (1)
90e9cd06-9135-5896-903d-03da135aeb1c | note | EXTERNAL REFERENCE: Hold Point (HP)
e233111b-ee6a-5d4a-b0c2-9b101957d6ae | note | ACTIVITY / DESCRIPTION: Linemarking & RRPMs
47998745-5a7d-5116-9432-a3413d86ce66 | date | Date:
d26c3bb2-cc76-4b9e-83c0-1fa5007b8628 | signoff | AUTHORITY HOLDPOINT
247095d1-3765-416e-9524-b97a9a174e2f | checkpoint | 5.1 - End-of-Defects liability period (EDLP): 3 / 6 / 12 / 18 / 24 months (2)
c189a0ff-90c5-5874-bac6-bbe2f46069f3 | note | EXTERNAL REFERENCE: Hold Point (HP)
d9386149-3c31-5c05-867b-7af66c215c63 | note | ACTIVITY / DESCRIPTION: Signs, guide posts
9be5c458-7cc3-5042-9dce-dfeb281ecd11 | date | Date:
105f7805-cc45-49b8-84b7-ab4b8458fcf5 | signoff | AUTHORITY HOLDPOINT
3c796aa6-9bd5-483b-a646-2aad979b2d84 | checkpoint | 5.1 - End-of-Defects liability period (EDLP): 3 / 6 / 12 / 18 / 24 months (3)
2d90792a-a9ce-5e28-a0ed-3be2b7155639 | note | EXTERNAL REFERENCE: Hold Point (HP)
2744ffa1-f4b8-5f5d-8061-1eb00966f6b4 | note | ACTIVITY / DESCRIPTION: Seal / Asphalt surface
ed8a7a46-26b8-5e55-88aa-ab827485b1be | date | Date:
5fe117a1-97d0-46af-bb52-2c048ea625de | signoff | AUTHORITY HOLDPOINT
51fb0002-3d38-43df-9aae-c61344e5f466 | checkpoint | 5.1 - End-of-Defects liability period (EDLP): 3 / 6 / 12 / 18 / 24 months (4)
9a9bab70-3bd7-5a08-b23f-64eed17b403e | note | EXTERNAL REFERENCE: Hold Point (HP)
e4d4a010-81bf-5fce-9136-4be8e73bd139 | note | ACTIVITY / DESCRIPTION: Landscape (where applicable)
9b12f7dd-cdf3-536c-84d4-50e2d4b694de | date | Date:
38ad7416-84d2-430f-b111-2b0da8d53443 | signoff | AUTHORITY HOLDPOINT
eb50e3ba-eb29-4d9a-9cc1-b8698bebf7d3 | checkpoint | Final Inspection
78035bf4-fc43-5262-babb-710b0370407a | note | The signature below veriﬁes that this ITP has been completed in accordance with the Fulton Hogan’s Quality system Procedures and veriﬁes lot compliance with speciﬁcations.
26bcb08c-94e9-5cef-8014-01480efefa37 | textbox | Print Name:
8770fd6d-e7f8-5a8c-9305-19f1dc660ed9 | textbox | Position:
9eb131b1-9cb4-5da5-b537-9057d2ce48ae | date | Date:
4f75df59-8ec0-41ae-bb5c-778e680816f6 | signoff | Sign ITP
fd1c54cd-7863-4ac5-8fca-658b3cdf63bb | checklist | ITP-001 - Reconstruct Fill | itp | ITP-001 - Reconstruct Fill
f69fd665-cf01-48a8-bd52-1d560d17bf4d | section | Preliminary Works
da6f6856-a67b-4a23-b310-65d72afedd06 | checkpoint | 1.1 - Check for correct documentation
0df3d42b-7ac5-536b-9cc5-f9db9459e82f | note | FREQUENCY: Prior to commencing any activity
7b095347-9c02-5b31-ad59-fae1a7be63ad | note | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are:
18c2ef4e-663c-5429-9e7c-abf8d901524a | note | — Using the correct and complete set of drawings
3c524e3c-936d-5d33-b496-4c148b339252 | note | — All drawings are the latest revision
c01c798e-4da6-542b-8308-9d60c09255e3 | note | REFERENCE DOCUMENTS: Drawings and drawing registers
9d85bd6c-d32a-5d05-a7b7-284838fd7696 | note | INSPECTION / TEST METHOD: Visual inspection
7bcceae7-fc70-5009-8a16-f774ae1c472c | note | RECORD OF CONFORMITY: This ITP signed
743a2a9d-1cfb-5be3-8b02-f8b84e387ba6 | note | HP*
b802b6ee-3b1f-57e3-980e-716851dc80f8 | note | RESPONSIBILITY: Site Engineer/ Site Foreman
ce5106a8-12dc-51f6-9bb6-541ec7eb9736 | date | Date Completed:
5459b15a-d489-4a21-aa26-086dd5b5448e | checkpoint | 1.2 - Implementation of all measures and controls
5d088608-07be-5017-bfd5-c27e28948313 | note | FREQUENCY: Prior to commencing any activity
27505093-c980-5c92-8248-6aa1a40c675c | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: PMP, EMP, ECP, TMP, SWMS.
f56b06f7-6855-5976-b90d-b946afbc9f80 | note | REFERENCE DOCUMENTS: PMP, EMP, ECP, TMP, SWMS
f47cebf0-2525-54da-9901-e3c08dede777 | note | INSPECTION / TEST METHOD: Visual Inspection
541b8e34-5ba6-53b2-9624-4da2bf27b8d1 | note | RECORD OF CONFORMITY: This ITP signed
af2a91ed-999a-5cbc-a6f7-34bfebdf0d02 | note | HP*
59ad19f2-e711-57fe-a6a2-2bc123354426 | note | RESPONSIBILITY: Site Engineer/ Site Foreman
227c2fc1-70ea-57f5-b9fc-48b956ef5e25 | date | Date Completed:
775a4c0d-a3a0-4e34-b34d-54cb4d553664 | checkpoint | 1.3 - Dilapidation
300b385c-93de-5622-b6a7-0a7d24186546 | note | FREQUENCY: Prior to start
7659f7ce-33ed-59fc-8cbe-10c71740a435 | note | ACCEPTANCE CRITERIA: Dilapidation report has been completed prior to establishment of site.
842a9550-fd7d-5264-b046-516335263aab | note | REFERENCE DOCUMENTS: N/A
ed4abf11-12f4-59e9-840d-c2453afee4b7 | note | INSPECTION / TEST METHOD: Verify
5cbeae1f-e0ad-5b7a-9622-fa0c9beae95c | note | RECORD OF CONFORMITY: This ITP signed
30975608-9558-5eef-8855-6e10af2194e5 | note | HP*
33f22440-0a0b-58a3-aa41-6c78593d49fe | note | RESPONSIBILITY: Site Engineer/ Site Foreman
92668af1-fed1-53ac-b112-87a10c8afb68 | date | Date Completed:
8c7744e2-6c5e-41ea-915f-35b0cb1947c3 | checkpoint | 1.4 - Installation of sediment and environmental controls
0c52d109-2072-55b7-891d-2f50c6531531 | note | FREQUENCY: Per layer
e555690d-44d4-5bbd-92b3-d01f0536cacc | note | ACCEPTANCE CRITERIA: Adequate sediment and environmental controls have been implemented as per the site EMP & ECP
8c69c1e1-fb3f-5c58-a89b-fdbaa0a7e7b3 | note | REFERENCE DOCUMENTS: EMP, ECP
f312069e-a5fd-528a-9bb2-f554d942c66e | note | INSPECTION / TEST METHOD: Visual inspection
ab1900e3-bf85-55ef-b356-0a47275c3a80 | note | RECORD OF CONFORMITY: This ITP signed
9aba4537-3a11-5589-86a3-1a782d5954ff | note | IP
4f83fbb9-e14b-5954-b966-1cce11219fec | note | RESPONSIBILITY: Site Engineer/ Site Foreman
7638dd47-a9bf-5740-91d8-6b696ccb318f | date | Date Completed:
5dd4e3a9-e45e-44b6-a1bf-acc304524d4c | checkpoint | 1.5 - Service Identification
ae4d6842-3530-5dbc-835e-4dcef2537ac0 | note | FREQUENCY: Prior to start
a0356781-eab8-565d-8257-aa3fd32db7a0 | note | ACCEPTANCE CRITERIA: All services are located and the relevant service authorities have been consulted and permits obtained
5c1dd812-8a17-5fd6-bc82-5c2fef1c2c14 | note | REFERENCE DOCUMENTS: DBYD
0d6d7e92-09bc-5878-b63b-4beb97d4a52e | note | INSPECTION / TEST METHOD: Verify
7dd25ccb-5a42-5afa-a475-00bc6f9b6172 | note | RECORD OF CONFORMITY: This ITP signed
23fa7da0-408a-5171-a948-86ee279aff0f | note | HP*
b87389ed-f57f-5e67-a0b2-3f68676caa36 | note | RESPONSIBILITY: Site Engineer
5267d9fb-bc40-53a8-bb00-b4a34edfd512 | date | Date Completed:
cd06b4ff-31c0-48a0-a54f-b0f557faded3 | section | Construction Works
dbb6d077-6eb2-45a3-ba53-f35ab14d3199 | checkpoint | 2.1 - Site Setout Survey
478f6501-9292-5097-9d86-973a768a5c5f | note | FREQUENCY: At Commencement
b7523de0-1002-55fc-8fe3-018da32f8a67 | note | ACCEPTANCE CRITERIA: Setout of excavation and works to be done by DTP Geotechnical Engineer
c430790c-0212-51ca-879e-88add4edf8f2 | note | REFERENCE DOCUMENTS: Design IFC Drawings
d6a299a2-e31c-577d-9a0a-fe2151b06ddd | note | INSPECTION / TEST METHOD: Visual Inspection
1aed6a19-3046-5255-860d-b2e7fd97180f | note | RECORD OF CONFORMITY: This ITP signed
6cc4bfa6-238f-5b38-81f2-7101b3c38519 | note | HP
1e011506-bb71-524f-bb57-acf7b6622418 | note | RESPONSIBILITY: Superintendent/ Site Engineer
b928ef21-705c-56db-851f-08bc4a6991cd | date | Date Completed:
41c3c515-bdef-4133-9e25-48e16b50ef42 | signoff | AUTHORITY HOLDPOINT
869e8f2c-19fb-422f-a655-dfc1ff6b4115 | checkpoint | 2.1 - Saw cutting
fde766d9-d5a7-537b-859c-32194d7896fe | note | FREQUENCY: Where required
f7c4f04d-56fd-5c1d-9460-5bbd9087b36d | note | ACCEPTANCE CRITERIA: An excavation permit must be issued prior to any saw cutting commencing.
a03e0af8-942b-590d-8577-bd2ebc626729 | note | ○ Extent and location of cuts to be clearly set out and checked prior to saw cutting
3153d236-bf2f-5ca1-af8a-d03987b17328 | note | REFERENCE DOCUMENTS: Design IFC Drawings
37d9cc1b-1879-5726-8604-1570b3dc28ba | note | INSPECTION / TEST METHOD: Visual Inspection
47d8ad3c-2780-5c43-bead-409e135f662f | note | RECORD OF CONFORMITY: This ITP signed
70a1c972-3f9c-5839-a863-8575dc51ee1c | note | IP
400d40f0-6d97-5a63-a081-2bcfeb31b603 | note | RESPONSIBILITY: Site Engineer
0d4c3a55-c400-5190-86dc-39cd7f45ff57 | date | Date Completed:
9dced8d8-2708-437c-8a93-418bfd7ae8cc | checkpoint | 2.2 - Excavation Works
2472e626-c530-5854-a2fc-c686eafca85f | note | FREQUENCY: During excavation
898dca46-5213-5eab-b20b-033021583519 | note | ACCEPTANCE CRITERIA: An excavation permit must be issued prior to any excavation commencing.
addedfb4-a59c-5f3d-992e-d9eb39f82f6e | note | ○ Excavation operations shall not disturb areas outside the limit of excavation and always remain within the parameters of the Native Vegetation permit.
5c266a2e-eae4-5407-98d8-7989149ef059 | note | REFERENCE DOCUMENTS: Exc Permit Native Veg Permit Design Dwg
5634ebc0-5235-5fb1-bfa5-a83c2a230e76 | note | INSPECTION / TEST METHOD: Visual Inspection
1e684fef-c8fd-5f66-b17b-58766b8d8a50 | note | RECORD OF CONFORMITY: This ITP signed
a26d5006-8277-50ce-ba96-7b3cdfa16f0c | note | HP*
a062ab4a-7f84-5312-9ba0-4edca17a01dc | note | RESPONSIBILITY: Site Engineer
551426c4-528c-5447-9889-b249078cfb1c | date | Date Completed:
29398ca2-c25c-4cdf-aa70-ff4b7e840821 | checkpoint | 2.3 - Inspection of the Base of the Fill
61e578f4-4d61-5c01-95ef-512d2abbc008 | note | FREQUENCY: Post-Excavation
d0000475-c024-5122-a725-3e0867bb5c9b | note | ACCEPTANCE CRITERIA: Floor of layers to be free draining towards face (0.5%) or sub-soil drain installed taken to ends of site outletting below toe of works.
952e29fc-da62-5f58-95ec-d44aadae0e93 | note | ○ The Superintendent and Works Supervisor shall inspect sub-grade material prior to placement of rock in accordance with clause 204.04
8c489047-1ae5-5490-aff5-5b2985a46c19 | note | REFERENCE DOCUMENTS: 204.06 Vicroads Technical advice
5d401884-c6ef-519b-b72d-532b731cdc8d | note | INSPECTION / TEST METHOD: Visual Inspection
97631994-468a-5dbd-9338-ade280ffe801 | note | RECORD OF CONFORMITY: This ITP signed
0a0daa82-ff62-5149-8513-973e2785971d | note | HP
c369570f-94ce-5fea-a031-1f67fc7ceb96 | note | RESPONSIBILITY: Project Supervisor, Geo-Technical engineer
d41005b0-f794-516d-8fd0-0e5b392920f2 | date | Date Completed:
258d2981-1fd0-4a1a-a5ad-2387782f9a4e | signoff | AUTHORITY HOLDPOINT
09961d14-9d8b-4566-9abd-07fdc187f93f | checkpoint | 2.4 - Benching
9e74761e-eead-500d-9340-b4a1e3f177fa | note | FREQUENCY: Each lot
da8218dd-b6a1-5582-aad1-dd9baf32276b | note | ACCEPTANCE CRITERIA: Benches to be cut at widths of 0.7m. Maximum overall excavation angle must not exceed 60 degrees (0.6h:1v).
5c46b1b5-b6f9-5d02-a567-23144da8c5dd | note | REFERENCE DOCUMENTS: Design IFC Drawings
763490ff-36a7-55e3-81b1-eb5c500ec3af | note | INSPECTION / TEST METHOD: Visual Inspection
42a4f05f-ed56-5e14-a832-3a3a80a7e757 | note | RECORD OF CONFORMITY: This ITP signed
b31d4fa5-6ed9-55fa-b74e-f8b21bc03294 | note | IP
053b7659-7293-5349-a685-eec110efe19a | note | RESPONSIBILITY: Site Engineer/ Site Foreman
ee988228-793f-5586-aa1e-cbedb5315a94 | date | Date Completed:
f0c1ca8b-f860-4bef-b680-2277e14ffe9d | checkpoint | 2.5 - Disposal of Material
227c9cf0-a5eb-5c01-814c-445def52a64e | note | FREQUENCY: All times
ed559a14-1360-5548-abf1-f52eaea5daa9 | note | ACCEPTANCE CRITERIA: Surplus material, debris and demolished material are to be sorted and transported off site. Material to be kept in condition for re-use where possible.
d19073cf-48ae-52bc-beb5-58fe6bab7d36 | note | REFERENCE DOCUMENTS: Conctract Specification 402.03
e8b82133-6167-5775-a078-cd896a4162f1 | note | INSPECTION / TEST METHOD: Visual Inspection
a2518f12-262b-5f63-a8f9-a2f66c9d78b3 | note | RECORD OF CONFORMITY: This ITP signed
49c85208-2e34-545b-a743-c22a826be78e | note | IP
dacf8692-7246-5560-994e-ec9abc799427 | note | RESPONSIBILITY: Site Engineer/ Site Foreman
1440e16c-0520-5a6a-8712-1d35551f5d96 | date | Date Completed:
2a930544-2057-42b9-9bce-58e77a0e4266 | checkpoint | 2.6 - Placement of Rock Fill & Geotextile
06a2a1a3-fad2-5868-b511-1c109b93ccc4 | note | FREQUENCY: Per layer
35ef2f22-14a3-52fc-b394-6e56b7586e74 | note | ACCEPTANCE CRITERIA: Machinery must be approved weights and only used in staging as detailed for the impact & load assessment. Un-approved machinery cannot be used.
476c0ceb-fcdf-5d8b-825d-998369d060a6 | note | ○ Ensure extents of rock fill is wrapped in approved Geotextile layer.
f5a2fa6b-3ca0-5d97-853c-8bc2a7eaabe9 | note | REFERENCE DOCUMENTS: Work Methodology
879eaa4b-b27b-5826-b942-5b91ba819b16 | note | INSPECTION / TEST METHOD: Visual Inspection
931916ab-542f-5d39-a761-c9cfcfda0d66 | note | RECORD OF CONFORMITY: This ITP signed
63c380ef-13f2-57f6-953f-f2357b621041 | note | HP*
387ad945-0712-54d9-ab34-a476e4317642 | note | RESPONSIBILITY: Site Engineer/ Site Foreman
dda36f1e-fb02-5669-aa5e-9a01ca91834a | date | Date Completed:
abe476b6-f52a-441b-904e-48f5de694aef | checkpoint | 2.7 - Test Rolling
24247b09-e01e-5f42-af0f-a6105b30732d | note | FREQUENCY: Each lot
8826aa5b-49a5-5d6d-ab5c-0f6dc958207a | note | ACCEPTANCE CRITERIA: Base of excavation prepared and test rolled in accordance with Section 173 & 204 prior to placement of geotextile and geogrid.
15d7252e-9864-5c91-bc91-213e684be9ed | note | REFERENCE DOCUMENTS: Section 173 & 204
3bad1982-0ab4-53cb-91fd-bf63e49d979a | note | INSPECTION / TEST METHOD: Proof Roll
fa133e60-b527-5bec-934a-dee26ea4b71a | note | RECORD OF CONFORMITY: This ITP signed
157cd1ad-7c66-524e-89fa-875aa351502f | note | HP
45098959-85cd-50db-8cb9-8981e29a7ece | note | RESPONSIBILITY:
d8edb3a4-161b-550b-a15d-06c681341c7c | date | Date Completed:
83a30329-fcfb-44a0-8d64-269dc15a6fc0 | signoff | AUTHORITY HOLDPOINT
462489da-36ad-4306-95f1-31ed58b32508 | checkpoint | 2.8 - Placement of 40mm Class 3 Crushed Rock Layers and Geogrid
e71a2773-4958-56e9-80d3-ad77344a9caa | note | FREQUENCY: Per layer
f1c1b493-3290-5856-85b1-abd2b0f752e3 | note | ACCEPTANCE CRITERIA: Density testing each layer as per section 304 at compaction standard C (not less than 98%). Density Test Results for first to layers to be provided to DTP Prior to placement of remaining layors.
46822ff7-f2f3-5b7f-ae59-77a4767cd6ea | note | ○ Placement of approved non-woven geogrid shall be roller out perpendicular to the centreline with no joints parallel to the centreline. The Geogrid shall wrap around each layer as per drawing (refer section 210 and placed at the base of excavation in conjunction with Geotextile fabric.
d09af92a-cc51-516f-abd3-c2de68419ea4 | note | REFERENCE DOCUMENTS: Section 173, 204 & 210
f84f047b-4780-579b-80c3-5ba8453d7bfb | note | INSPECTION / TEST METHOD: Density Testing/ Visual Inspection
6510fc94-44c8-5794-8f46-51f817bab019 | note | RECORD OF CONFORMITY: This ITP signed & Test Reports
dbbbe3ec-d5b7-5699-8df0-53f3c3bec84f | note | TP
e760fd0f-4127-5481-9b18-2d7a67c42589 | note | RESPONSIBILITY: Site Engineer/ Site Foreman/DPT Geo-Technical Engineer
6cd990f6-5a4b-57ff-b823-dff65c6af855 | date | Date Completed:
debb7aeb-b29a-4918-a4b4-502750e10fde | checkpoint | 2.9 - Placement of Subase layer 20mm Class 3 Crushed Rock Placed in two equal layers
917e5429-4d4b-5521-958c-f03230ca1366 | note | FREQUENCY: Per layer
060228ec-1b6b-52d3-a8e6-f2ecdbcf9363 | note | ACCEPTANCE CRITERIA: Density testing each layer as per section 304 at compaction standard C (not less than 98%)
e34500f2-2a28-5dc9-9e56-833a2a446d93 | note | REFERENCE DOCUMENTS: Section 304
0113f621-139d-5779-97da-ac360f28e4dc | note | INSPECTION / TEST METHOD: Density Testing
73d159a0-73e4-5c58-a417-30f279b1cc98 | note | RECORD OF CONFORMITY: This ITP signed & Test Reports
290e8042-ec5f-57b2-aa7d-c0c4ebd402f7 | note | TP
30075499-929f-5000-8033-ef29fb9a5db3 | note | RESPONSIBILITY: Site Engineer/ Site Foreman
b707a13b-596e-5a61-ab7e-00bafddce50b | date | Date Completed:
92b0113d-e06f-477b-a67f-a5c55aacbfbb | checkpoint | 2.10 - Placement of Jute Matting
8f4ed717-bd3f-5150-83b2-06463038a5ac | note | FREQUENCY: Each lot
96569b0f-7ae4-50e2-8b1a-b373d5cf9f6d | note | ACCEPTANCE CRITERIA: Place local topsoil 50mm minimum thickness along the batter of the works and place jute matting over extent of works ensuring jute mat is pinned in place.
2d90053a-250e-5b49-89a3-890d7dc5b78b | note | REFERENCE DOCUMENTS: Design IFC Drawings
f9b80090-119b-5a58-a35c-2ef199f57c90 | note | INSPECTION / TEST METHOD: Visual Inspection
d6e5b775-601b-5dad-accc-918488df8ded | note | RECORD OF CONFORMITY: This ITP Signed
f7cb94c2-32fe-53bf-98dd-25f64b483b43 | note | IP
130e241a-98c1-5687-b950-23402b2b2fba | note | RESPONSIBILITY:
7945f9c0-2bf0-5918-a083-889cbe079776 | date | Date Completed:
61a4b05e-9b9d-432b-8082-ba233c1aa209 | checkpoint | 2.11 - Kerbing
31c68678-dffd-546b-b151-5948cdcfc865 | note | FREQUENCY: During Installation
3028d2eb-73ab-546f-b1ca-8055f58dc059 | note | ACCEPTANCE CRITERIA: As Per Kerb & Channel ITP_002
24188e6a-2f1b-5af3-980d-804975de460d | note | REFERENCE DOCUMENTS: ITP 002
133ec748-4ed7-5d39-b3c5-243b835bc586 | note | INSPECTION / TEST METHOD: Review
e4b2fe19-c38a-5205-bb59-e70519bb60a3 | note | RECORD OF CONFORMITY: This ITP signed & Kerb & Channel ITP
dc2df7be-0553-53a7-a76a-240856f79c17 | note | IP
1e3496d3-329b-51b9-a0c3-0bd45c5e408d | note | RESPONSIBILITY: Site Engineer/ Site Foreman
f4d1e314-5e00-5046-a85e-6874990a7991 | date | Date Completed:
2ff25980-6b82-495c-a838-ce21e5c3123d | checkpoint | 2.23 - Guardrail
88615858-49f8-5049-b6dc-3eab5c868d03 | note | FREQUENCY: During Installation
7228b860-a8b9-5fab-8ac9-b248a3ce0c0c | note | ACCEPTANCE CRITERIA: As Per Guardrail ITP_003
30fb68d7-bc0d-515c-88f8-02073c46c69d | note | REFERENCE DOCUMENTS: ITP 003
556de1c3-df1a-5059-ad20-36a385bbcf03 | note | INSPECTION / TEST METHOD: Review
0b68730f-fbf9-55fd-aa11-bfbab4dd9d60 | note | RECORD OF CONFORMITY: This ITP signed & Guardrail ITP
5f46ea79-771f-553e-b30b-05c0878fca0a | note | IP
8f6b5bcb-67be-59a9-a506-a0b6509b7780 | note | RESPONSIBILITY: Site Engineer/ Site Foreman
c91bcc00-9084-5481-8667-59c1de89d6bc | date | Date Completed:
b82902b1-17e0-44d3-85ca-e6f3240be9fb | checkpoint | 2.13 - Asphalt
bd5c18d1-5c2f-590d-a89f-4b8c1c2c88fb | note | FREQUENCY: During Installation
539b89ee-4c84-5710-94c6-abe724ee9c33 | note | ACCEPTANCE CRITERIA: As Per Asphalt ITP_004
bec4afe8-b56e-50f8-bc18-d1b9358097cf | note | REFERENCE DOCUMENTS: ITP 004
9acfb34e-d810-5618-bf98-a76930ae80fe | note | INSPECTION / TEST METHOD: Review
1f3efbfb-4a21-56ba-8df5-368c8fd3a7a0 | note | RECORD OF CONFORMITY: This ITP Signed & Asphalt ITP
737cc8d4-4c6c-528d-aee8-cb59c649d48d | note | IP
af7ac68a-bc1b-57f2-b60b-bd5966eabd3c | note | RESPONSIBILITY: Site Engineer/ Site Foreman
9d389deb-9ba8-5d0a-8a92-64b9a00054e1 | date | Date Completed:
e3d7cd09-31c1-4edd-8571-6d1ccac713cf | checkpoint | Final Inspection
d922a188-45b4-534a-b299-e9e7274eaa9b | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
69e443fc-4425-5299-9aaa-3fe08116294e | textbox | Print Name:
404d550a-8f31-5812-b792-d3787d606d40 | textbox | Position:
db1ea37c-6895-5734-aac5-f24d7af06dda | date | Date:
0aabbe7c-b934-4c6d-89af-1d82712da3e5 | signoff | Sign ITP
054ede44-8eb6-4e13-878e-4004cdbdc4e2 | checklist | ITP-002 - Cement Stabilisation | itp | ITP-002 - Cement Stabilisation
857405fa-85ca-48bc-809a-9bd1da8daf36 | section | Cement Stabilisation
211533ca-5805-4d71-b0d7-6792fc45bd60 | checkpoint | 1 - Mix Design
384fb554-cf0d-59eb-90bf-b6fb71af28cc | note | FREQUENCY - Prior to start
3747d49e-3a7b-5282-91ac-8ad2be9c21f0 | note | ACCEPTANCE CRITERIA - Mix design to be selected based on pavement material investigation. Binder application rates to be confirmed with client prior to start.
00628e39-730f-58fa-a3e3-112bbd4a6faf | note | REFERENCE DOCUMENTS - VR 307.05
8a535256-11e1-58cb-b799-c5503eb2436f | note | INSPECTION / TEST METHOD - Record
ea5f15e2-3aa6-5193-81e4-c0a092f2624e | note | RECORD OF CONFORMITY - Record
8bd7767d-ebcc-52d4-82dc-2bed99e3cafc | note | HP*
3d743550-9f10-5b89-8973-62aa79108fbf | note | RESPONSIBILITY - Project Engineer
7a85e3f7-b11a-584e-bc50-4aa201f36a92 | date | Date Completed:
9f3911a5-4f47-4aed-9fe4-13bf8764d9be | checkpoint | 2 - Preliminary level confirmation
ff60f601-c148-5ad6-865e-6e15a6df273b | note | FREQUENCY - Prior to start
47dd3d87-6faa-545c-9b8b-1432adb632b8 | note | ACCEPTANCE CRITERIA - The surface level of the area to be stabilised shall be confirmed to be within level tolerances prior to commencement of stabilisation. Unless otherwise specified, +15/-25mm.
cfba47b5-42ce-5e3b-82c2-78bd0b60accd | note | REFERENCE DOCUMENTS - VR 307.03(a)
3e4c02e1-3bd5-5847-877c-63876c6ac8ce | note | INSPECTION / TEST METHOD - Visual
b854368f-d066-54cf-b68e-960c327abea5 | note | RECORD OF CONFORMITY - Visual
c8e50bac-7d05-55f8-93bf-7f413e73cf32 | note | IP
882145fe-1483-5a40-969b-ec6fd593a72d | note | RESPONSIBILITY - Project Engineer
291853e0-f4f3-5ccf-b09d-2c3a6d896633 | date | Date Completed:
00d54696-f99b-422e-a4e7-92b5ee393315 | checkpoint | 3 - Binder Supply
4314f9c8-937c-52d6-a4be-78395e9c0939 | note | FREQUENCY - Each production day
be703c3e-6bde-5d42-a367-a8614a91bc75 | note | ACCEPTANCE CRITERIA - Quicklime & Hydrated Lime to meet requirements of AS1672. Cement supply to comply with AS 3972. ALI shown on delivery dockets.
63431d19-7f04-5275-b328-01d6c2c0b9f3 | note | REFERENCE DOCUMENTS - VR 307.04
dd137de7-7213-5ce5-8cfb-e3f303cd1c42 | note | INSPECTION / TEST METHOD - Test Report
886b7eb6-0a20-5ff0-8a27-507197a0bd8a | note | RECORD OF CONFORMITY - Test Report
a2fae1e3-07d8-501a-8bdc-18289ddcc3ad | note | IP
1a362821-71ab-5f57-ac45-3d8851abce12 | note | RESPONSIBILITY - Project Engineer
42fe5711-fbc1-58cb-b688-783194f68df2 | date | Date Completed:
234b66b2-9e36-4b87-aecd-5314e6bc8ef9 | checkpoint | 4 - Spreading of stabilising agent
5eb8c8ba-94d6-565d-8e3b-c07d43f00aef | note | FREQUENCY - Each Lot
a7c83163-734a-5a43-bb11-cf27fa89866e | note | ACCEPTANCE CRITERIA - Binder shall be spread at the specified rate. In passes not exceeding 15kg/m2. No traffic to be allowed after spreading other than construction traffic. Matt test & load cell outputs recorded for QA purposes.
17ea66b5-9f67-55e7-a63d-982c391529b4 | note | REFERENCE DOCUMENTS - VR 307.14
1d069a39-16af-5c76-818d-80b31ca96351 | note | INSPECTION / TEST METHOD - QA Report
99502a6e-6287-5f68-b48a-fc88df335496 | note | RECORD OF CONFORMITY - QA Report
29d85bdf-96e1-5c51-bc9d-c2fb87284596 | note | IP
f4126577-e218-533c-b299-0da63d056a05 | note | RESPONSIBILITY - Project Engineer
0bfc193c-9866-5ae9-b9ff-cc00a05432e4 | date | Date Completed:
11df4343-a2f8-4fcf-8d99-f5ae3086c484 | checkpoint | 5 - Slaking of Lime
689de229-9953-50cd-a7fc-3719119a48d2 | note | FREQUENCY - Each Run
e64fd0ca-f44c-513a-bb3c-6997920552a0 | note | ACCEPTANCE CRITERIA - If quicklime is used it shall be slaked with sufficient water to allow full slaking to take place prior to mixing. Full slaking will be deemed to have been achieved when all quicklime that has been spread has changed from a cream coloured granulate to a fine white powder and there is a cessation of rising vapours.
69b5e4d2-e046-5510-bfb7-99431304bfa5 | note | REFERENCE DOCUMENTS - VR 307.08 (c)
d4e17935-f15a-5986-b205-fcb1ec7e945f | note | INSPECTION / TEST METHOD - Visual
63699f4c-9ba0-5483-a167-0fcd1324d384 | note | RECORD OF CONFORMITY - Visual
abc4eed3-8d04-5651-9024-c9660992cc11 | note | IP
c12d786b-5867-5b6e-80c8-a7dbd9d18e2c | note | RESPONSIBILITY - Project Engineer
a1b36ae5-a2e3-5339-8498-978042f82172 | date | Date Completed:
95799c10-a35f-420f-a9fb-b026e36c660c | checkpoint | 6 - Mixing of stabilising agent
132c0357-59f9-58c4-92cf-47893713d041 | note | FREQUENCY - Each Run
0c162f02-8828-53e7-9221-592547e43113 | note | ACCEPTANCE CRITERIA - Mixing shall commence as soon as practical after spreading of the cementitious binder. Water to be added as required to achieve and maintain close to optimum moisture content. Mixing depth to be physically checked.
1914ca6e-9fe8-5a02-bc2c-cef9d5d2513e | note | REFERENCE DOCUMENTS - VR 307.08(e)
76f30061-b855-590d-bd7f-2857f706424b | note | INSPECTION / TEST METHOD - Visual/ QA report
21a16b57-d02f-52b8-a29f-08128e924330 | note | RECORD OF CONFORMITY - Visual/ QA report
de5435da-fa9d-5c1b-b8d1-1f7653c60491 | note | IP
cb5c192c-b3b2-5edf-9322-121cf79db2cc | note | RESPONSIBILITY - Project Engineer
f81eb0ca-2dbe-5780-8f0f-e25d036ad971 | date | Date Completed:
0922a61f-0aa9-4d6e-91b8-8035ee7356c7 | checkpoint | 7 - Compaction
e2dd7b21-32aa-5576-88b7-8881d10616c5 | note | FREQUENCY - Each Run
c0dcd38b-59c3-5d9e-8133-b792dc851266 | note | ACCEPTANCE CRITERIA - Compaction of the stabilised layer shall commence immediately after mixing.
a58ad524-b1bf-593b-ab93-00fe9b72126b | note | ○ All compaction shall be completed within the times specified in Table VR 307.052 after addition of the cementitious binder.
3d01408b-dce5-590d-810b-9b9591e639d8 | note | REFERENCE DOCUMENTS - VR 307.08(f)
032625a9-5c46-5e9c-834d-93eeddc95e00 | note | INSPECTION / TEST METHOD - Visual
07ef0049-c5db-54a3-826b-13aa632ec3ea | note | RECORD OF CONFORMITY - Visual
a1967668-8f94-554a-8a9a-12ba6c0affa2 | note | TP
3a7b0ca6-9f2d-5792-972d-6a7ba9fe57d8 | note | RESPONSIBILITY - Project Engineer
2e4d3d6e-cbd6-5d69-a87a-fa03b7ecd377 | date | Date Completed:
7f1669fd-991e-452f-982e-da1036b3efda | checkpoint | 8 - Trimming
e72c0e36-f4f6-5b58-8ba4-c5a07fcd550c | note | FREQUENCY - Each Lot
7dd8ab88-306f-5b30-a5ff-d1c77ddc4576 | note | ACCEPTANCE CRITERIA - On completion of initial rolling, the stabilised material shall be trimmed to the specified surface tolerances. Water may be applied during this operation to replace evaporated moisture.
3e37b5e4-b0bc-56e0-85e3-55f3394fe361 | note | REFERENCE DOCUMENTS - VR 307.08(g)
620a1526-adf8-5246-993b-ad4f9d697efa | note | INSPECTION / TEST METHOD - Visual
185f82f3-d9ce-595d-a82e-8c5be90c776f | note | RECORD OF CONFORMITY - Visual
9b192d14-67ef-5c8f-bac4-9ca024e3295f | note | IP
220194bd-e879-5ab5-b423-4cab8a2fbd69 | note | RESPONSIBILITY - Project Engineer
ed38ae14-636d-511f-bd58-cfec4d8d60f5 | date | Date Completed:
b62aa8d4-d01f-4451-b0ed-4bc8c75e6852 | checkpoint | 9 - Test Rolling
0f07b646-7dd3-5604-b1d2-3eb4e2d8ae18 | note | FREQUENCY - Each Lot
31203af8-29f9-591b-8b9b-88389900d9f2 | note | ACCEPTANCE CRITERIA - Stabilised layers shall pass test rolling in accordance with Section 173, prior to acceptance of the layer.
4ac80e37-bd42-5cfd-a218-688e5a3756af | note | REFERENCE DOCUMENTS - VR 307.10
5337b595-e3a0-521a-9886-11137dc059f4 | note | INSPECTION / TEST METHOD - Visual
b34708e6-945c-57d7-9573-012a94832280 | note | RECORD OF CONFORMITY - Visual
3b876763-2a72-5ff5-a4c7-fbf2a807c7e1 | note | HP, WP
c8fe3744-2c66-5b38-aede-483b034e7271 | note | RESPONSIBILITY - Project Engineer / DTP
86b292d8-967f-5192-9037-7387c0f61331 | date | Date Completed:
446662e0-2cbd-4d6b-b6e9-87f42b382e8e | signoff | AUTHORITY HOLDPOINT
b8230bd9-3c25-4f4c-87c4-a626ec0f10e1 | checkpoint | 10 - Compaction Testing
fff40d79-c68d-5832-adf7-4bff052991ea | note | FREQUENCY - Each Lot
d6ceb9b0-4a8c-5d8e-ad51-a8775c03fcbb | note | ACCEPTANCE CRITERIA - If required, density testing to be undertaken as per table 307.151 or otherwise specified
c014796f-6467-5535-944f-a2119eee4f88 | note | REFERENCE DOCUMENTS - VR 307.15
f7dbd2ad-70c3-507b-bb08-ed3c2a8acd8c | note | INSPECTION / TEST METHOD - Test Report
71b0c00d-0aff-5a88-bac4-7db11c566d54 | note | RECORD OF CONFORMITY - Test Report
1e1fba40-14e4-5882-9046-3a5e4b681cd7 | note | TP
4e793f49-f7dd-592b-a4fd-9f5629a9ad98 | note | RESPONSIBILITY - Project Engineer
f9e824d4-ce33-50ad-9a8e-3430912d5675 | date | Date Completed:
719f67f7-a2bb-4b5d-bb6e-1287188872c6 | checkpoint | 11 - Maintenance of Stabilised layer
ce86cc5b-3214-5a74-adbd-2f4cdd42b925 | note | FREQUENCY - Each Lot
77afaea5-2ed6-515e-97b5-76e6d1988d00 | note | ACCEPTANCE CRITERIA - Surface shall be kept moist and protected from damage by traffic and construction activities until further pavement layer is applied.
d1710ddb-4225-5f91-8d11-34cea298b2cb | note | REFERENCE DOCUMENTS - VR 307.11
f2cababd-5598-527a-a464-5c1a0d5d50b9 | note | INSPECTION / TEST METHOD - Visual
a61bb987-a201-54e5-aa93-f16f924c339a | note | RECORD OF CONFORMITY - Visual
39525603-82ff-5729-8ef0-049b053a4e5d | note | IP
7f62279c-845f-5bf9-ba10-39c77cd0c4df | note | RESPONSIBILITY - Project Engineer
cdee3857-4918-5cd5-9266-93c210cf44b0 | date | Date Completed:
8d41508b-d7b7-445c-a62c-ef47bcc0b43f | checkpoint | Final Inspection
a90427b8-034d-55db-9b7c-9859e00c27d9 | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
a5e37654-341b-58fe-8d5c-c8794614a70a | textbox | Print Name:
d6770516-17fb-5f07-ba7e-09b5c3d48fca | textbox | Position:
c4b6b016-d4e2-5b46-b4a7-bcd5fb415363 | date | Date:
e174e8ac-105b-412c-96d1-2550f6fa80bf | signoff | Sign ITP
e4d91f30-602c-4365-ab8b-bc4317e9f11d | checklist | ITP-002 - Earthworks Rev1 | itp | ITP-002 - Earthworks
041be6b1-3e2a-46b4-95c2-ebdd3a6e9dc3 | section | 1 - Preliminary Works
db88af9a-cdf3-47ac-9c82-e84c3c5bab96 | checkpoint | 1.1 - Check for correct documentation
9f22898e-7745-5cb1-8fbf-5dfb55c3470b | note | FREQUENCY: Prior to commencing any activity
a7e8916f-6809-5480-87d1-39a41cf29cf8 | note | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are:
cfcf23bb-bce5-579f-a3bd-919b218f5d5a | note | – using the correct and complete set of drawings
0effba81-0f86-5039-b38b-c02f89f1fcbe | note | – all drawings are the latest revision
24e76e3f-2e2c-5ca3-bca3-cf550aca57ff | note | REFERENCE DOCUMENTS: IFC Drawings
922a8a72-cdae-5595-bf90-e96cff252ccd | note | METHOD: Visual Inspection
36991505-2071-52e7-b65e-a9c29da7f7ed | note | RECORD: Signed ITP
88bdfa93-b2cb-557b-bdce-8cbe68017271 | note | IHP
17fb348a-1fdb-5d77-93ef-364daf30d75f | note | RESPONSIBILITY: FH Project Manager
8e2d6a07-3965-5bd5-9cbf-c7cefabb997a | date | Date Completed:
63f732d4-fb68-4278-b1c8-99a6b6f52dd5 | checkpoint | 1.2 - Implementation of all measures and controls
404e3f5c-873d-5caa-9916-d3dff3970534 | note | FREQUENCY: Prior to commencing any activity
91edf25c-6b82-560b-9d38-49de60c0f58e | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: EMP, TMP & SWMS.
df07def4-f3d8-5d19-bf79-372725340570 | note | REFERENCE DOCUMENTS: EMP, TMP & SWMS
68c6143c-2ad2-5443-ad43-b64d6ac357ab | note | METHOD: Visual Inspection
b81b340c-9cd0-557f-8459-e1716d949d89 | note | RECORD: Signed ITP
4e0c890e-45f1-5c8c-8ae4-a11df59c25cb | note | IHP
728f178b-85cd-5772-be7c-b0f9ddc34068 | note | RESPONSIBILITY: FH Project Manager
2c9c3cb3-5753-5493-83df-73ed8a7214e2 | date | Date Completed:
ebcaa8be-5566-4a05-bccc-176c748758e1 | section | 2 - Construction Works
a0206c4e-d128-4db2-81c4-fa23904a0d72 | checkpoint | 2.1 - Survey Set-Out
a6a163fc-aa73-591e-9660-616cb75f3c3a | note | FREQUENCY: Prior to commencement of excavation.
69996aca-d05f-5eb3-8516-d82d68cb5129 | note | ACCEPTANCE CRITERIA: Area has been set out in accordance with the drawings
5ff3cd9d-93f1-5e28-a2a2-79d47e9d2e02 | note | REFERENCE DOCUMENTS: Work Procedure
9a2bc0b0-7163-57ee-a27a-cb5721d4029d | note | METHOD: Verify
a9f530cd-d595-547f-a8b9-5e65bb31009f | note | RECORD: Signed ITP
b771a12d-dd64-5ecf-95a2-7bfae6c9ba6d | note | IP
6749daa1-b38c-5b22-a798-417dfa97478f | note | RESPONSIBILITY: FH Project Manager
febc95d0-065c-5d55-bffe-aa71950a834a | date | Date Completed:
5fe129e3-cacf-4d83-a253-9a7117626978 | checkpoint | 2.2 - Excavation Permit
fd583744-384c-57f4-9f9c-3d5863d09ed6 | note | FREQUENCY: Each Lot
4806dffe-9fcc-5e7c-879f-946796c2ad95 | note | ACCEPTANCE CRITERIA: An excavation permit or DBYD must be issued prior to any excavation commencing. Plant and equipment shall be appropriate for the task. Excavation operations shall not disturb areas outside the limit of excavation
69248a25-a217-50f3-b6b2-22825a5042b2 | note | REFERENCE DOCUMENTS: Excavation Permit
f3c3da83-c84d-523c-8de0-97878b14cf48 | note | METHOD: Verify
8ad7643a-b47b-5e14-b7cf-f6aa5e826c2e | note | RECORD: Signed ITP
f70bc8f6-8b49-573d-bdd8-a302e2e804fd | note | IHP/IP
b4010a2b-c0fb-55e1-aa0e-5226628f69bc | note | RESPONSIBILITY: FH Project Manager/FH SEQ Adviser
67d17488-9fd3-570b-abce-c55d4259c1d2 | date | Date Completed:
42cf7591-47c0-4cf1-9372-96c8b5bfc312 | checkpoint | 2.3 - Sub grade Material Properties
8a8d9868-2117-5cfb-a8f1-4d9676506db8 | note | FREQUENCY: Each Lot
18c219a3-0bb1-5e5c-99f3-103a9618dd71 | note | ACCEPTANCE CRITERIA: In situ material within 400mm of cut ﬂoor level to be consistent with Type B. i.e. CBR>assigned value (must be greater than 2), Swell < 2.5%.
16191bf4-f69f-5daa-a3a8-9b386f2362ed | note | ○ If parameter met, rip and re compact 150mm. If parameters not met remove 400mm of material and replace with conforming type B.
f38c7d12-6d68-5a86-a4b1-e7fa3764626e | note | REFERENCE DOCUMENTS: VcRoads Std Specs 204.06 (e)
3367f729-fef8-527c-a3b6-58e161d8d615 | note | METHOD: Site Inspection/Test Report
88c643e9-723d-5af1-a8bf-8b55d805061a | note | RECORD: Signed ITP & Test Report
ec8a3b45-f17d-5fc4-a6bc-e85ee109c254 | note | TP/AP
aef5de5f-da68-5319-b0cd-6609340a1483 | note | RESPONSIBILITY: FH Project Manager/External testing Company representative/RRV Superintendent
2e731720-889c-5080-a53a-a9608fc249a0 | date | Date Completed:
9dd5abbd-f9b3-4f31-8d5b-f8de8c554251 | checkpoint | 2.4 - Inspection of Subgrade Material
f4aa726f-5902-515c-a24a-faff3a266a23 | note | FREQUENCY: Each Lot
86ee1b29-d638-55d4-a713-2c0ced376ca9 | note | ACCEPTANCE CRITERIA: Prior to commencing excavation in any area and during excavation work, the Superintendent and the Contractor shall inspect each type of material encountered and subject to veriﬁcation by appropriate laboratory testing, agree on the category of the material in accordance with Clause 204.04
1927e66f-e00f-56e2-a9fa-f17e506ae6fd | note | REFERENCE DOCUMENTS: VcRoads Std Specs 204.06 (e)
1c01f8b4-c502-5711-b987-626f180a8582 | note | METHOD: Visual Inspection
4b3cd2c8-81e3-5f4b-89dc-04c17238eb00 | note | RECORD: Signed ITP
fa482470-682a-594a-8b00-8f81cbd22a29 | note | IHP/AP
8c1329c5-8315-5bba-83c2-d62f2463a953 | note | RESPONSIBILITY: FH Project Manager/RRV Superintendent
796307c4-48b1-55bc-8561-93be3c7a2b9b | date | Date Completed:
a5154711-7169-4204-8733-942f210dce3a | checkpoint | 2.5 - Material Classiﬁed as Silt
cc4f1382-2058-560f-a25c-7825087bddba | note | FREQUENCY: Prior to commencing
69a27b9e-0971-5730-b647-476604d9203e | note | ACCEPTANCE CRITERIA: Material classiﬁed as silt, either before or after compaction, is not acceptable as Type A material without stabilisation to the satisfaction of the Superintendent.
9b970472-96b7-5fb5-9beb-d39487a960ae | note | REFERENCE DOCUMENTS: VcRoads Std Specs 204.04 (e)
737cc393-451f-54c4-8239-22a1ebfecd9b | note | METHOD: Visual Inspection
328a220e-6ed7-547a-8532-c2423aeb3ab0 | note | RECORD: Signed ITP
9aa10554-8883-5bee-967a-bc655027ba0f | note | IHP/AP
e28c853a-d17f-5f8e-ab33-e501c84f45e7 | note | RESPONSIBILITY: FH Project Manager/RRV Superintendent
3dc12c84-6222-5039-91a3-31c4886d26cc | date | Date Completed:
a2e8ff1d-e2db-47e9-9131-37b176e9269d | checkpoint | 2.6 - Acceptance of Rock Subgrade (when applicable)
984a2686-690d-5e32-9aac-64b20dceb8df | note | FREQUENCY: Prior construction of the regulating layer.
d2974f8d-ff96-5595-996c-01752fc7a1e9 | note | ACCEPTANCE CRITERIA: Prior to construction of the regulating layer, the areas of rock subgrade shall be presented to the Superintendent for acceptance.
42b13d52-7b77-5153-a0aa-50d427479a6d | note | ○ Any necessary amendments to the subsurface drainage design including transverse subsurface drainage at the interfaces shall be presented to Superintendent for review.
e2cc4731-f580-563d-b5cd-2153c7840702 | note | REFERENCE DOCUMENTS: VcRoads Std Specs 204.04 (f)
b4dd4049-27f9-561d-bdd7-327775e36404 | note | METHOD: Site Inspection/ Document Review
ee2c31a2-6424-5b49-8c60-7e32887b6928 | note | RECORD: Signed ITP
744835bc-19db-5380-834f-446581c84450 | note | IHP/AP
4908672d-fd70-55bc-bdf3-66170611d1cf | note | RESPONSIBILITY: FH Project Manager/RRV Superintendent
16007b9b-96cb-55d1-9967-f29ac9a007a5 | date | Date Completed:
d3d956df-6dd3-4a51-b619-a0aaff7c8545 | checkpoint | 2.7 - Unsuitable Material
662e537b-3dc5-5097-9f1a-d1e2472d4f4d | note | FREQUENCY: Each lot as required
a71a6a2c-508b-5c3d-9a4e-6429a98a6fd5 | note | ACCEPTANCE CRITERIA: Where unsuitable material is encountered, proposed in-situ treatment must be submitted to the superintendent for review
558261c2-eef0-5e2b-abc4-72dfd7d8f148 | note | REFERENCE DOCUMENTS: VcRoads Std Specs 204.07 (d)
b11c4aee-5774-5906-bd84-795b14bf753c | note | METHOD: Visual Inspection
eb7db5e7-b89a-530b-9c0a-3c61d35ea2c1 | note | RECORD: Signed ITP & Test Reports
c03e9544-439a-5dd2-b780-61ba80d958a5 | note | IHP/AP/TP
8ffb7039-16cb-5e36-9f0c-763669152821 | note | RESPONSIBILITY: FH Project Manager/RRV Superintendent/External testing Company representat ive
24567dd4-b55c-5b0a-9f2d-08e58ad9c626 | date | Date Completed:
cac80486-2ff6-40cf-a2f5-0a0fedb662f3 | checkpoint | 2.8 - Groundwater
fa7c841d-5dde-52f1-83ec-a9f752af4565 | note | FREQUENCY: Each lot as required
c4a4e4c7-c722-5f1c-9c46-0931616f68ea | note | ACCEPTANCE CRITERIA: Where groundwater is encountered the contractor shall notify the superintendent and submit proposed action for review. The Contractor shall submit any necessary approvals from relevant authorities for the treatment and disposal of this groundwater.
e16015e6-1465-57f7-b447-4cb75eed87dd | note | REFERENCE DOCUMENTS: VcRoads Std Specs 204.07 (h)
5b5ddabc-c6ba-5c71-8f1e-f93e60d4d436 | note | METHOD: Visual Inspection
4d4c7789-6dc1-50e2-a609-133d35c3b912 | note | RECORD: Signed ITP & Test Reports
89c2d327-5996-5a95-a840-b8161f5dad67 | note | IHP/AP
c829b9ad-9bac-5969-bb92-e4cb18e3258a | note | RESPONSIBILITY: FH Project Manager/RRV Superintendent
e6060839-a0df-52a6-9ee4-0878d19f92a4 | date | Date Completed:
5f54baa4-4f68-49c8-8c1f-cc398519ec35 | checkpoint | 2.9 - Trimming and level conformity
1d75baad-95cc-53cb-a48a-3cee78106f8a | note | FREQUENCY: Each lot as required
530b07da-c549-5093-a7b6-8580a77c7c9c | note | ACCEPTANCE CRITERIA: The level at any point on the subgrade shall not lie more than 20 mm below a 3 m straightedge laid in any direction, except across a crown and water shall not pond at any point.
b6a12067-bdab-5013-a074-18088f9637b0 | note | ○ Level tolerances: Range x (Mean value of all measurements) (Scale A) x = +5, -25mm (Scale B )x = +5, -15mm
42f44353-7c0a-5b10-8d20-fb80bb068879 | note | ○ Max S (Standard deviation of all readings) (Scale A) = 12 mm (Scale B) = 15 mm
55873f47-8a3a-5aae-a841-a981f623cb31 | note | ○ No. measurements (Scale A) 80 per lot (Scale B) 40 per lot
936f372e-dc47-5d5f-97a5-1e5ee7aa1d93 | note | REFERENCE DOCUMENTS: VcRoads Std 204.03 (f,g,h) Table 204.031
e4989bad-b1f3-5da1-9c82-f1ecf92e35d6 | note | METHOD: Survey
fbab1469-7ba3-584a-bc9c-d8a0ded9098c | note | RECORD: Signed ITP & Survey Report
ec729980-7484-52f3-899c-641d3c6a65aa | note | SCP
0d4e4f9d-a50f-572b-a3c8-4015aee01927 | note | RESPONSIBILITY: FH Project Manager/External Surveyor
1eba8df2-5ce0-5a7e-9ee4-e641df8f73ca | date | Date Completed:
647d4aef-4b98-48db-a2ef-683bfb8b4444 | section | 3 - Testing Requirements
2a5348ae-37cf-42aa-8691-24cd70b0e241 | checkpoint | 3.1 - Test Rolling
e4838aa4-0831-53c8-af56-ef87deb7dc00 | note | FREQUENCY: Each lot as required
ebfe8c2c-7072-520e-983d-ea12651dee66 | note | ACCEPTANCE CRITERIA: No visible deformation or springing in presence of Superintendent's Rep. ( Cl 173) Plant to comply with requirements of Cl 173.03.
07167bbe-4541-5121-a43a-d66c8138dfd2 | note | ○ Pneumatic tyred plant nominated for test rolling procedures shall have a mass of not less than 20 tonne and shall have a ground contact pressure under either the front or rear wheels of not less than 450 kPa per tyre.
4d633fbc-86dd-5327-ae25-63511619fd3a | note | REFERENCE DOCUMENTS: Vicroads Speciﬁcatio n Section173.03 173.03 (ii)
b690086e-2b16-55a6-a4ba-0a3d9cc6a863 | note | METHOD: Visual Inspection
a2cfcafd-c912-51ea-8589-4013d844c886 | note | RECORD: Signed ITP
329da984-1775-5746-98e4-bfb7b6d87d71 | note | IHP/WP
acd44a95-66ce-5951-9de5-ea76b6b3c381 | note | RESPONSIBILITY: FH Project Manager/RRV Superintendent
ab51850b-e5db-54f5-8f55-8f87b27f698f | date | Date Completed:
621ce0c4-9af3-4b46-888d-cf6369961f19 | checkpoint | 3.2 - Compaction Testing
d0d8135e-0aee-58b3-b13b-85d03cbe12e0 | note | FREQUENCY: Each lot as required
51bc3704-98bf-53d0-8898-0fea14413b07 | note | ACCEPTANCE CRITERIA: Ripped and re- compacted material below Cut Floor Level = minimum compaction 98%.
a1fd407d-561c-5f87-83b0-1130368f4eea | note | ○ Type B Material placed within 400 mm of top of Type B Material = minimum compaction 98%.
28db0e72-15d6-5540-a2f4-836df77cbd1b | note | ○ Type B material 400mm below the top of Type B material and Top 150mm of where ﬁll is to be constructed = minimum compaction 95%.
16e3e721-d2e9-5bec-9e33-f32fec9f93d0 | note | REFERENCE DOCUMENTS: Vicroads Speciﬁcatio n Table 204.131
0af583be-64ce-5e7b-ac63-97f34e3c6fd0 | note | METHOD: Compaction Test
ff2cdd83-3c8c-59c3-bfee-48d86a903c95 | note | RECORD: Signed ITP & Test Reports
88f7c6e1-dba0-53ba-829e-e90649b9ffd9 | note | IHP/AP/TP
20c0850d-adb9-55b8-814e-3eca59d19260 | note | RESPONSIBILITY: FH Project Manager/RRV Superintendent/External testing Company representative
8bd8c81a-e117-560e-9836-8a66a320a22c | date | Date Completed:
f0364a66-006f-4930-88f7-8c86f3992cf1 | checkpoint | Final Inspection
07dc476b-ee3e-5f14-9936-4d67578e9468 | note | The signature below veriﬁes that this ITP has been completed in accordance with the Fulton Hogan’s Quality system Procedures and veriﬁes lot compliance with speciﬁcations.
b60cbf1e-91de-521c-ac14-d8677a8e8eb0 | textbox | Print Name:
af220352-f2da-5e7b-91fe-f8836c153cd8 | textbox | Position:
7baf6ee6-1169-52ee-bde7-6f9c15e51f10 | date | Date:
f93a14e7-af96-493c-a76e-ad5eb730d85d | signoff | Sign ITP
03b6dd15-6a8e-58af-86fe-27776b93d631 | checklist | ITP-004 - Underground Drainage | itp | ITP-004 - Underground Drainage
56f12a57-1e96-5877-8041-0f0eb46d12c8 | section | 1 - Preliminary Works
aa5b427d-339a-5d3d-b6c5-84f70f776c33 | checkpoint | 1.1 - Obtain MOA and Traﬃc Management Plans. Ensure Traﬃc Management Plan is adhered to.
ff7f771d-f196-5e94-89c0-d98ee7bccdc5 | note | FREQUENCY: Prior to commencing works
f1e48edd-754f-5254-98e2-0d81f4bf1295 | note | ACCEPTANCE CRITERIA: Refer to the VicRoads Traﬃc Management speciﬁcation 166
846dc3d1-3f0d-548b-88ce-ec81a4516cfc | note | REFERENCE DOCUMENTS: Traﬃc Mgmt. Plan
3b32932d-65ad-5802-8d9b-f12f832e80a9 | note | METHOD: Visual Inspection
9af47316-48b4-5e62-a789-d9cb5127c919 | note | RECORD: Signed ITP
09237390-a739-5faf-b772-8dade004f4a6 | note | IHP
7c013968-a164-5048-9bf4-0e39e513a1eb | note | RESPONSIBILITY: SWA Project Manager
30b0e11b-b6b1-5617-ae1d-0998085e5877 | date | Date Completed:
277ed93f-4550-5150-83c9-df642f820a8c | checkpoint | 1.2 - Purchase of pre-cast pits, pipes and end-walls
195669b0-1473-5494-a15a-ad3ec8a39b49 | note | FREQUENCY: Approval prior to placement of order
31a43218-3e13-5342-b183-b8ec49858bb2 | note | ACCEPTANCE CRITERIA: Refer to Construction Drawings
5700c480-85eb-5218-93a3-706a1f664619 | note | REFERENCE DOCUMENTS: Vic roads Standard drawings
dd1103a1-592e-5fa2-a1df-403df97b4a5e | note | METHOD: Review and approval of documentation, Visual inspection
b1ea887b-e0bf-56d9-9b74-1e58a173bb73 | note | RECORD: Signed ITP
87e90362-6a1a-532a-b98e-3458a3a56f01 | note | IHP
ef83053c-2695-53b4-b1cd-2a6e14967af3 | note | RESPONSIBILITY: SWA Project Manager
4eee7202-5202-5afd-a007-1628a7ce0d0f | date | Date Completed:
ac047a58-71cb-5537-8556-237da2441d20 | section | 2 - Construction Works
3fc2718d-49ae-5211-b493-7b1d37994476 | checkpoint | 2.1 - CONFORMITY WITH DRAWINGS - The Contractor shall set out the drainage work in accordance with the drawings or as speciﬁed.
41bc5e39-ebc3-5862-ae41-6030e1febc70 | note | FREQUENCY: Each lot as required
8048936d-695b-5cdd-937b-b38056a05933 | note | ACCEPTANCE CRITERIA: Prior to commencement of excavation for the culverts the Contractor shall conﬁrm the position of all culverts with the Superintendent.
44adf031-0957-5d70-9ecf-c9728a776289 | note | REFERENCE DOCUMENTS: Vicroads std sec 701.09
2af47ceb-97b3-5f1e-8621-68cb1577ea32 | note | METHOD: Construction Drawings
4eb6ebae-de34-501e-b1c7-690696fc4379 | note | RECORD: Signed ITP
c1e9b9c5-bfe7-56fc-8315-e88f4513fc5d | note | IHP
0314b7e7-da94-50cc-96a9-00fc9f06bed8 | note | RESPONSIBILITY: SWA Project Manager/Site Supervisor
b225dc7d-df7d-533f-8ab6-615287710640 | date | Date Completed:
2ef4dc01-6d04-55e0-b499-703d38ded273 | checkpoint | 2.2 - CONFORMITY WITH DRAWINGS – The culverts constructed shall be constructed true to line and level
2253bb94-74fd-544f-b1be-00da20521073 | note | FREQUENCY: Each Lot
d326f21e-5a8e-5f77-b41b-fd03ece16966 | note | ACCEPTANCE CRITERIA: Unless speciﬁed otherwise the tolerance on location of pipes compared to the design or a change to the design notiﬁed in accordance with this clause shall be:
91a11db4-0d59-5076-8514-b961491675e5 | note | (a) oﬀset of entry pits required to match lines of kerbs or barriers ±20 mm
7af79b61-d7d4-592d-b239-f1ea814f9603 | note | (b) plan location of pits other than oﬀsets to kerb lines or barriers ±100 mm
5ccb1813-f18a-572c-ad93-988c6e037d8b | note | (c) invert level of pipes at pits ±50 mm (d) departure from design grade of pipe runs ±10 mm in 10 m provided minimum grade is not less than 1:250
d89417c4-1dbd-54c6-a591-3542d3627404 | note | REFERENCE DOCUMENTS: Vicroads std sec 701.09
6e29027b-260e-5746-8b1e-04e31e593e2a | note | METHOD: Construction Drawings
f646c043-e403-532e-bf52-ac5c9d1595e4 | note | RECORD: Signed ITP
5796186f-716a-5899-afe2-91ea32a06e83 | note | IHP
08433fe9-66f6-596e-b684-be188dd7aa3d | note | RESPONSIBILITY: SWA Project Manager/Site Supervisor
f4968ee5-7261-587f-a4c3-61303e64aad8 | date | Date Completed:
9229842c-f53c-55b8-95c3-6daceb99e979 | checkpoint | 2.3 - EXCAVATION
eb6a81b1-106b-5f34-acc5-de0ef1dc8f6b | note | FREQUENCY: Each Lot
d37c6318-756c-531a-b22b-17daa23f131a | note | ACCEPTANCE CRITERIA: For pipe culverts, the width of trench at and below the level of the top of the pipe shall be such that the horizontal clearance from the outside of the pipe to the wall of the trench is within the limits Min 300mm and Max. 600mm
5f543bae-e0ac-5b82-80d5-ad5d368ef555 | note | REFERENCE DOCUMENTS: VicRoads Std Specs 701.14
239f74ed-19b8-5b33-a3e6-4f71c526e866 | note | METHOD: On-site Measurement
c5554e91-31f3-535b-a926-8a87cca0db04 | note | RECORD: Signed ITP & Drainage Checklist
a828992a-5878-5fea-a175-7d8ac53ec858 | note | WP
33b10b9d-3efd-5adc-aff9-bbe3d9ff2872 | note | RESPONSIBILITY: Project Engineer/Site Supervisor
d8375f6f-ff33-5a15-b156-fb2952ca0d6e | date | Date Completed:
84b19f5b-5c46-57cf-a2f6-06554dc3aa79 | checkpoint | 2.4 - CULVERT BEDDING - Bedding material shall be provided and placed for the full width of the trench or, where the culvert is to be placed without trenching, to a width 0.8 m greater than the overall width of the culvert
25edea32-d970-5686-9c14-edca3b9efbfc | note | FREQUENCY: Each Lot
eb66c574-bb8f-5179-b2c3-6a00493b25af | note | ACCEPTANCE CRITERIA: The compacted thickness of bedding material following any shaping necessary shall be not less than:
3388aab4-97b7-511f-94a8-f344513ebbc7 | note | ○ 100 mm where D < 1500 mm
7d4a4a5d-71ea-55d7-af83-c565b0b0ecd2 | note | ○ 200 mm where D ≥ 1500 mm where D is the nominal pipe diameter or culvert width.
63c746b0-d9c2-53e3-82b2-3869e08c7f7f | note | REFERENCE DOCUMENTS: VcRoads Std Specs 701.15
1efcf702-d6c4-5fc2-b96a-28f08dfcd303 | note | METHOD: Site Inspection
18a937f2-a3e1-5bfd-80bd-dcaa997371f6 | note | RECORD: Signed ITP
cfb493f4-4784-5d48-844f-4e73bfc61023 | note | WP
bfa05788-6b45-5bad-ac25-11dc14849300 | note | RESPONSIBILITY: Project Engineer/Site Supervisor
164537f7-8e27-51d7-84f9-89a18d28af18 | date | Date Completed:
9d74312e-086b-5ab1-b8fa-c13e8a502894 | checkpoint | 2.5 - PLACEMENT OF FILLING
c1c0360c-17a2-5ff3-bc82-281da7c28cc7 | note | FREQUENCY: Each lot as required
bd9a776e-abe2-546a-b401-bb87129b5561 | note | ACCEPTANCE CRITERIA: (a) Unless the culvert is installed through an existing paved area, selected and ordinary backﬁll shall be placed as follows under, around, and above the culvert after the sections are bedded and compacted as speciﬁed in Clause 701.15.
160d80d9-ff77-5f51-b798-2054f70cd708 | note | (I) Culvert Under Area not to be Paved
0520f71c-d372-5b7a-915f-3b14a6e7c495 | note | ○ The trench shall be backﬁlled with selected backﬁll material to a level 0.3 m above the top of the culvert and with ordinary backﬁll material above that level.
288ada38-b0ab-508b-a609-231cf2a5eb01 | note | REFERENCE DOCUMENTS: VcRoads Std Specs 701.18
c11628d9-8c2f-547c-a3d4-bd3c29584dbd | note | METHOD: Site Inspection
34d13068-7144-586d-9cb4-8dc1e9561164 | note | RECORD: Signed ITP
fa434381-2d8a-5b79-8a37-a56f27a08b6b | note | WP
95987a52-448a-5ad6-ad46-d0a13403a993 | note | RESPONSIBILITY: Project Engineer/Site Supervisor
96f4d2af-c83c-5fea-88d4-62590757ddd1 | date | Date Completed:
3f774b8d-db9a-51be-a68e-24815f5896cb | checkpoint | 2.6 - INSPECTION OF DRAINAGE LINES BENEATH PAVEMENTS
138dc408-69fc-5f5a-8457-3469d3d95724 | note | FREQUENCY: Each lot as required
9a2feca4-3283-5092-bfd0-a4678f117675 | note | ACCEPTANCE CRITERIA: Unless approved otherwise by the Superintendent, all drainage lines constructed beneath pavements shall be inspected, after completion of earthworks to subgrade level and prior to construction of pavement layers, by an independent testing organisation using closed circuit television (CCTV).
4e9109f9-343f-5fbc-9da1-718231d95947 | note | ○ Reporting of the CCTV inspections shall be in accordance with WSA 05 2013 – Conduit Inspection Reporting Code of Australia, published by Water Services Association of Australia.
87e7f08a-f96f-5d07-b90d-aa12b5d88b49 | note | REFERENCE DOCUMENTS: VcRoads Std Specs 701.28
62e347ab-b426-508c-ae0c-1024c9cc5cfa | note | METHOD: Visual inspection
d7f8dc8d-3819-5d55-8f64-c2b409877f47 | note | RECORD: Signed ITP
8089c255-87cb-5470-a96e-b2c801bafb1d | note | HP/AP
c3e603f4-4c5b-53b7-8f4f-ee08d4470d78 | note | RESPONSIBILITY: Project Engineer/Clients Superinten dent
d5bd297f-9113-5a39-b980-f5e0b8f88b12 | date | Date Completed:
5d0bf3c2-9d31-5144-bcdd-4b712c1f0027 | signoff | AUTHORITY HOLDPOINT
554ac80d-3a13-5271-8a6f-e2f6eed39f0c | checkpoint | 2.7 - Where required installation of Geofabric or Jute matting and beaching material in swale drains
cd3f9388-74bb-5021-a6db-086733703b09 | note | FREQUENCY: After installation of pipes, pits, end-walls and placement of asphalt wearing coarse
bf175921-e803-564c-8f3d-1bf7d662556d | note | ACCEPTANCE CRITERIA: Rock used, should be an assortment of sizes where possible. The smallest rock size must be able to resist dislodgment in peak ﬂows. Rock shall be placed with a geo-textile liner.
a88ccc67-6170-5043-a577-bb75f2d995aa | note | REFERENCE DOCUMENTS: NIL
c4b9166f-c4a8-5869-8242-4ff325f26b11 | note | METHOD: Visual inspection
8d82beaf-77e0-5b9c-877d-eefb3b017b03 | note | RECORD: Signed ITP
bdadf9cc-a6a1-5f77-81ee-d96f0df941b1 | note | IHP
d4dafda0-0727-562c-994e-7c2f64c04999 | note | RESPONSIBILITY: Project Engineer/Si te Supervisor
aebf675d-db93-5925-94f6-6aaaedf55e39 | date | Date Completed:
6654a5b9-b49f-507b-92a0-605d8a01ad64 | section | 3 - Testing Requirements
d0124663-714e-56dc-8e0b-cd503b4b8a31 | checkpoint | 3.1 - REQUIREMENTS FOR TESTING AND ACCEPTANCE OF COMPACTION AND MOISTURE CONTENT - Bedding and backﬁll materials shall be placed and compacted in layers not exceeding 150 mm loose thickness.
38f7f3fd-186b-5a94-9d3c-d46cfddc8722 | note | FREQUENCY: 3 per Lot (A lot shall consist of one layer of bedding or backﬁll for a culvert length between adjacent pits or endwalls)
39406688-46e7-5934-88dd-11172fada3d6 | note | ACCEPTANCE CRITERIA: (a) Bedding Bedding shall be compacted to refusal using hand held mechanical equipment. Bedding material which has a swell equal to or greater than 2.5% shall be maintained at a mean moisture ratio of 92% between the completion of rolling and the placement of the overlying layer.
fc9b0346-7df2-5e7c-8e79-36472f115322 | note | (b) Backﬁll
84515d71-0f2e-55eb-9c0a-e16782ff187a | note | (i) Material of Nominal Size 40 mm or Less After Compaction Backﬁll material which will have a nominal size after compaction of 40 mm or less shall be compacted to a mean value of density ratio of not less than 97%. Backﬁll material which has a swell equal to or greater than 2.5% shall be maintained at a mean moisture ratio of 92% between the completion of rolling and the placement of the overlying layer.
73d39840-e6d7-5c0b-8fd4-8bafe562197f | note | (ii) Material of Nominal Size Greater than 40 mm After Compaction Backﬁll material which will have a nominal size after compaction greater than 40 mm shall be compacted using a grading, mixing, watering and rolling procedure. Backﬁll material which has a swell equal to or greater than 2.5% shall be maintained at a mean moisture ratio of 92% between the completion of rolling and the placement of the overlying layer.
396e2c2c-1b7b-578c-bd19-8bc8eb1b9057 | note | REFERENCE DOCUMENTS: Vicroads std sec 701.19
b4b94626-f9df-5024-bf29-1e39dbd6c81e | note | METHOD: Lab Test
74d128c5-1452-5f90-beee-94ceb44c230b | note | RECORD: Signed ITP
3782413a-7cf5-5707-89ed-a514e9b0186e | note | IHP
020dfa56-df5b-5eee-81e0-d26e3b402d1a | note | RESPONSIBILITY: SWA Project Manager
1492241a-2e16-51e4-bc88-241b9eba531f | date | Date Completed:
e4df1e76-54d1-5b97-b96b-bf3da9d4c209 | checkpoint | Final Inspection
bd0e6189-8169-5e75-838d-b3124d3c7a13 | note | The signature below veriﬁes that this ITP has been completed in accordance with the Fulton Hogan’s Quality system Procedures and veriﬁes lot compliance with speciﬁcations.
0db37f49-dd06-5ab4-9403-1ca4a21edb57 | textbox | Print Name:
f9cbb62d-571f-5bfd-bb23-97eeb63cd4a6 | textbox | Position:
52ce646b-4fd7-5d88-bf27-a1d49b30da0a | date | Date:
20ae8cc0-7e50-549a-b298-b7d0166643ab | signoff | Sign ITP
676c0dc5-3d4c-4d0d-8c3d-cb430e079773 | checklist | ITP-005 - Crushed Rock Class 2 | itp | ITP-005 - Crushed Rock Class 2
a7c01852-e10f-4bbd-aedd-6f66b710dc41 | section | 1 - Preliminary Works
b8ff2abc-8817-464f-a7b6-584c55b03f47 | checkpoint | 1.1 - Crushed Rock Mix design
b893e869-4fea-5400-aef4-bd3a82fd8dc7 | note | FREQUENCY: Prior to Commencing Work
67a1cfd6-c73e-56f8-a9f6-2e053f32259e | note | ACCEPTANCE CRITERIA: Crushed rock mixes proposed for use on specified works shall be registered in accordance with VicRoads Code of Practice for Registration of Crushed Rock Mix Designs as listed in Section 175.
3e86ac57-c71d-5ba6-90f9-ca14696ecb9c | note | REFERENCE DOCUMENTS: VicRoads Spec. Cl.812.09
f9e83717-2ba4-5d33-8cf6-d883fde8e7c4 | note | INSPECTION/TEST METHOD: Document Review
a8ff5066-85e7-5680-97ab-2f75724d7517 | note | RECORD OF CONFORMITY: Mix Design VicRoads Approval
9d4219f5-9e18-58e6-9fe3-e67172c10dfd | note | HP*
ad577942-127e-5a92-8410-9be1f2e8f5f2 | note | RESPONSIBILITY: Project Engineer
a0880a7f-0855-5d3c-b945-86610cea2d0c | date | Date Completed:
1d41ea1f-fae0-4d58-aabd-ad265610043d | section | 2 - Placing Fill
62b23fe3-ef1b-4226-a0fa-193d962d3393 | checkpoint | 2.1 - Transverse Joints
99bb88ae-007d-5048-9a2c-5ec460cb096b | note | FREQUENCY: Check prior to placing material
ef8118c1-bcf5-51a2-87af-c9ace2201fb8 | note | ACCEPTANCE CRITERIA: Material should be spread to minimize number of jointsTransverse joints shall be offset from one layer to next by not less than 2 metres
513d9fe7-554c-5df5-8c83-7902aae5ed13 | note | REFERENCE DOCUMENTS: VicRoads Spec. Cl.304.07 (a), Cl.304.07 (c)
ce711816-e815-59c4-a1b7-a239bd67b54f | note | INSPECTION/TEST METHOD: Site Inspection
bddf9f8b-454c-5c35-9ed1-91fa38c002dc | note | RECORD OF CONFORMITY: Signed ITP
d75e896d-9eec-57e8-b314-ccbdd8537d11 | note | IP
f586b5e7-0b4e-56d7-aefa-20152cc9c2ab | note | RESPONSIBILITY: Project Engineer
887b7376-711a-5fd6-8b9d-053f298f192f | date | Date Completed:
5509e709-c808-4199-95a1-ae8ff6225b45 | checkpoint | 2.2 - Longitudinal Joints
fbb0310c-9af1-5603-9687-8de821920689 | note | FREQUENCY: Check prior to placing material
eaf2e228-595c-50b5-8c27-ec0253790e0c | note | ACCEPTANCE CRITERIA: Material should be spread to minimize number of jointsLongitudinal joints offset from one layer to next by not less than 150mmLongitudinal joints to be located within 300mm from planned traffic lane lines or within 300 mm of the centre of a traffic lane.
fcdb5ca4-b7fa-5770-832c-ab5719f8233e | note | REFERENCE DOCUMENTS: VicRoads Spec. Cl.304.07 (a), Cl.304.07 (d), Cl.304.07 (e)
d4ddedfc-bce5-57e1-bada-a02910b09773 | note | INSPECTION/TEST METHOD: Site Inspection
574d0f7d-1083-5251-8f97-f5db8827c0db | note | RECORD OF CONFORMITY: Signed ITP
73507be5-6e44-5ddf-a757-eaf129d3f3d3 | note | IP
631bcee7-5b63-5fd3-9736-dfe0750e8707 | note | RESPONSIBILITY: Project Engineer
b1b82ebf-6912-588e-94f8-737dad3086df | date | Date Completed:
ce405cb9-ac24-44b3-afda-0d4f4ca52ca2 | checkpoint | 2.3 - Lot Size
3aa867e1-dda0-5c81-89c6-0c8af05fe594 | note | FREQUENCY: Check prior to placing material
6aafaa08-1f0f-5648-a300-408bf1e2247a | note | ACCEPTANCE CRITERIA: A single lot shall be considered a single layer of 4000m2 or one days production in a single layer, whichever is lesser.
d966c5bd-c1de-5d8d-993e-ef0b3e5ddc5e | note | REFERENCE DOCUMENTS: VicRoads Spec. Cl.304.08 (b)(ii), Table 304.111
430e644e-1534-5f5e-814d-36fd5d921653 | note | INSPECTION/TEST METHOD: Site Inspection
6e063d09-2e39-5655-9615-da95d092240e | note | RECORD OF CONFORMITY: Signed ITP
517545a0-f6ff-5782-9046-0368a980a4bd | note | IP
d6adc4a8-2c74-5b51-bf7a-6691dd1dcfb8 | note | RESPONSIBILITY: Project Engineer
9fdf7d63-2128-5d29-ae66-7e5d3eaf5b22 | date | Date Completed:
fec62321-06cc-4b43-b613-d07f30dea7a4 | checkpoint | 2.4 - Proof Roll
98564637-b2a8-5c81-828c-92ecbfc88774 | note | FREQUENCY: After placing material
65742847-85c9-5bf5-90ca-f0eb0884d62d | note | ACCEPTANCE CRITERIA: Pavement lots should be subject to proof roll as outlined in VicRoads Section 173, under supervision of Superintendent
14eb7bd1-1f96-5700-95b7-b36059300472 | note | REFERENCE DOCUMENTS: VicRoads Spec. Cl.304.08(b)(iv), Cl. 173
095f59d1-7069-509f-a14a-e5e641ddf06c | note | INSPECTION/TEST METHOD: Site Inspection
74149970-4aec-5e45-8e0d-4031673e3b5e | note | RECORD OF CONFORMITY: Signed ITP
a3107613-093c-55fd-be8b-1648b517d181 | note | HP
6a22060e-d6d8-537a-980a-51758196a342 | note | RESPONSIBILITY: Project Engineer / DTP / VIVA
a9901f72-1da7-57e6-9008-a3b637c8eda6 | date | Date Completed:
d392bc65-2cb9-4cca-8bf6-3b2cc505fb79 | signoff | AUTHORITY HOLDPOINT
702c65f0-5167-4d45-acb3-89fcfef6a9f5 | section | 3 - Testing Requirements
760c8a41-d630-46b3-ab1d-92c36a24881f | checkpoint | 3.1 - Determine Testing Scale & Initial testing frequency
aaa6f55f-6a82-5abe-ae03-58f08bcdc0dd | note | FREQUENCY: Prior to Testing
ef35cf70-4621-53cc-835b-7eeb1a7a767c | note | ACCEPTANCE CRITERIA: Table 204.161 from VicRoads Standard nominates the level of testing required for acceptance of Surface Level Measurement.
764eb108-3d66-54e9-86c8-3e33c977491a | note | ○ Scale B - Initially test every lot until 2 consecutive lots of like material and/or work have achieved the standards specified in Clauses 304.08. and 304.10. If no failures, Reduced Frequency applies as specified in Table 304.111.
626562b0-88d3-59c8-893a-0e25990bca82 | note | REFERENCE DOCUMENTS: VicRoads Spec. Table 204.161
5302b1e4-f270-5089-abdb-922dd00733e7 | note | VicRoads Spec.
c1e874a4-3260-58c5-b842-780e1c112129 | note | ○ Cl.304.08 (a)
b0260730-334d-55df-9ff1-c0cb65fef98d | note | ○ Cl.304.11 (b)
11781de8-482c-5606-836a-5d1335d409f6 | note | ○ Cl.304.11 (c)(i)
7994d65e-7a67-5006-8dda-0cc760e016c4 | note | ○ Table 304.111
5b5b9f26-5857-5c87-ad58-4ffe02a7dfd8 | note | INSPECTION/TEST METHOD: Document Review/ Site Inspection
7ce88dad-0b39-51e8-81fd-26050bfb83b4 | note | RECORD OF CONFORMITY: Signed ITP
2d2ea3ca-b76d-5c82-ad53-8723bbf6f13a | note | IP
d54e14a1-0b0c-5a38-9c58-eef4a72d5727 | note | RESPONSIBILITY: Project Engineer
ff89c13a-28d9-5533-934c-56e6026f5818 | date | Date Completed:
9ea74c3a-7990-458e-b9cc-ce7cc9b8712d | checkpoint | 3.2 - Modified Compactive Effort
6d520bd6-29c1-5ae8-a162-753bcc917cfd | note | FREQUENCY: As per 3.1
5e57f232-a612-57d4-932b-c1c097534ae7 | note | ACCEPTANCE CRITERIA: Characteristic Value of Density Ratio for Subbase:- > 97.0% (Scale B) 1 per every lot
a9999452-9cf3-525f-9e20-70f38502c08e | note | REFERENCE DOCUMENTS: VicRoads Spec. Table 304.081
95657a30-dce7-59b9-b63a-069c9c861a1e | note | INSPECTION/TEST METHOD: Site Inspection
239d06e7-3529-593c-b79d-f381437f1d33 | note | RECORD OF CONFORMITY: Test Records
41a83d58-832c-53b9-9937-2ffee8e40fde | note | TP
7757315f-f41c-5022-97ec-f1595ac55fec | note | RESPONSIBILITY: Project Engineer
a098d406-1906-5696-911b-2c290a6cdd66 | date | Date Completed:
4c893940-8d55-4c22-a1af-df2263507712 | checkpoint | 3.3 - Survey Level Conformity
035cdcca-8e35-5d04-a09f-b093faaa878d | note | FREQUENCY: At completion
b7cbba40-6394-5634-b412-5374a394c976 | note | ACCEPTANCE CRITERIA: Scale B:
3acb5a60-ef2f-5cda-94dd-a27222405eaf | note | – Minimum number of measurements per lot: 40 For Upper
72394234-7e74-5e89-91a0-a64060b67633 | note | – Upper Subbase: Mean + 6mm to – 12mm with a maximum Standard Deviation of 8mm
9c01780e-4115-5185-91f9-a2ee5b5e7c5f | note | – Lower Subbase: Mean +8mm to –16mm with a maximum Standard Deviation of 10mm.
bdfba48c-1b4d-58fb-b2e5-9b06e6e47786 | note | – Base: Mean ± 8mm with a maximum Standard Deviation of 8mm.
eaf70417-84af-506b-a947-e6a3cd3c137d | note | REFERENCE DOCUMENTS: VicRoads Spec. Table 304.061, Table 304.062
421504d5-8526-552c-95fd-53a5766adddf | note | INSPECTION/TEST METHOD: Site Inspection
0b013088-c6f3-51e1-9b2c-750bdad5e150 | note | RECORD OF CONFORMITY: Test Records
d57dff8a-6f0c-5686-b5f1-bb61b0a3b9d7 | note | TP
b3100ef7-497e-50db-9caf-be5607ba9d2d | note | RESPONSIBILITY: Project Engineer
144331fe-4309-5dac-863b-e46b2a9518e7 | date | Date Completed:
a3e83dc3-be84-49cb-8790-bfa87923f394 | checkpoint | Final Inspection
a94cec0c-2c8a-5a22-953d-d34b2e63d92e | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
531f55e5-cfe3-5e9b-95a2-491feb947bed | textbox | Print Name:
9fa74147-ab4d-52ef-9e47-0b67345c502c | textbox | Position:
f2cbc9f7-36db-502d-9f76-0f669cefa1a6 | date | Date:
ae6e6015-0b51-417a-a7e7-3f280d803298 | signoff | Sign ITP
defe6850-8fe3-4675-9e3f-6619bcf134b4 | checklist | ITP-005 - Flexible Pavement Construction Rev1 | itp | ITP-005 - Flexible Pavement Construction
e0c6afb1-d081-49e6-a3e6-0ca26e18c0d0 | section | 1 - Preliminary Works
6aad694d-4d34-409d-abb2-04c06b19fddd | checkpoint | 1.1 - SET OUT OF WORKS
3016739b-f27a-53f2-8402-35ea025d61f9 | note | FREQUENCY: Each lot as required
7de9cb9b-ac7b-5c82-b6b1-cd58bf6b491f | note | ACCEPTANCE CRITERIA: Ensure relevant construction drawing are being used to determine set-out of works.
7cb60180-a301-54e0-80fc-0db5392b915b | note | ○ Ensure all survey pegs are aligned max 40m apart and the oﬀset distances and heights are in accordance with relevant drawings
0c67b6ed-9d79-5a07-8ce6-7947b23d422a | note | ○ Refence checking to be conducted with string lines
77758217-08b1-5c4d-add6-f2b813f9371e | note | REFERENCE DOCUMENTS: Vicroads std sec 100.6
ee0d8b14-8136-5837-8034-03c5d1d899f7 | note | METHOD: Survey set-out
c8a50dcf-9701-56ff-a24a-9904f1aa82b6 | note | RECORD: Signed ITP
9890a84f-7a71-54d8-a9c4-4f2432ab7621 | note | SCP
bf7686fb-8f28-5810-9342-5bccc07f7eeb | note | RESPONSIBILITY: FH Project Manager
e050f7a5-269a-5655-930a-50b6e963d208 | date | Date Completed:
f6a9c829-3854-4b1b-9792-1e4106c31c2f | checkpoint | 1.2 - CONFORMITY WITH DRAWINGS - Random Level Assessment - Scale B Surface Level Requirements
5709f79b-82e5-546a-a991-a5a044abbbdc | note | FREQUENCY: Prior to commencing any activity
0af9cbcc-c6e4-5cf3-96b4-db93a5806215 | note | ACCEPTANCE CRITERIA: Level measurements shall be taken at random locations over the area of the lot in accordance with Section 173 – Examination and Testing of Materials and Work (Roadworks). The number of measurements taken within each lot shall not be less than the number speciﬁed in Table 204.031. Random level assessments of the surface shall be undertaken in lots not exceeding 4000 m2.
ed68e4dc-42d3-5d0a-b289-c8e048655024 | note | REFERENCE DOCUMENTS: Vicroads std sec 204.03
3044cec5-1ec9-52ac-b330-8f4296a89553 | note | METHOD: Survey Report
1f1bb01c-82eb-58b8-9514-c56a6ed3c3f0 | note | RECORD: Signed ITP
a22fba69-ed66-500b-9023-5258af39eb97 | note | IHP
7b2b8aec-5ce0-5ecf-879b-bef5b875b8a4 | note | RESPONSIBILITY: FH Project Manager
5642fae0-a70b-5d4c-b327-49b574cf22ea | date | Date Completed:
fce85f4f-14d5-4590-ad03-5eb78862c55d | section | 2 - Construction Works
ac8ac35b-1a80-42f9-84d7-e9e031adbcbb | checkpoint | 2.1 - REQUIREMENTS FOR TESTING AND ACCEPTANCE OF COMPACTION (a) General
300f9a1d-78b5-517f-96eb-1dce17baaa38 | note | FREQUENCY: Each lot as required
49267f4b-91f8-5d38-92ea-7c1787b96b23 | note | ACCEPTANCE CRITERIA: Material during compaction shall have a moisture content of not less than 85% of optimum. After completion of compaction of a layer, the moisture content of the material in the layer shall be maintained at a moisture content of not less than 85% of optimum until test rolling has been completed.
4b0c5800-0a8f-542b-8dc2-99048ee8dd3e | note | REFERENCE DOCUMENTS: Vicroads std sec 304.08
698a77aa-02d0-5819-b737-3c5f5e11b06d | note | METHOD: Visual & Laboratory Report
832b6c06-2978-5e73-a10c-926064fbbc03 | note | RECORD: Signed ITP
0e9e8661-1f9a-5f13-88ab-00147fe9d411 | note | IHP/AP
8a111ca6-2a12-56ce-b879-029c550c945f | note | RESPONSIBILITY: FH Project Manager/RRV Superintendent
542b8657-06fa-5c7c-9892-65a6a12e5891 | date | Date Completed:
dc1b5734-b41a-4687-acfa-aa500cd1638a | checkpoint | 2.2 - REQUIREMENTS FOR TESTING AND ACCEPTANCE OF COMPACTION (b) Material of Nominal Size 40 mm or Less
9470e639-065b-5529-bb39-e3d97e00f01c | note | FREQUENCY: Each Lot
935789c4-4827-5643-afdf-8bf910887855 | note | ACCEPTANCE CRITERIA: The calculation of density ratio shall be based on tests performed using Modiﬁed compactive eﬀort. The work shall be assessed for compliance with Scale B requirements being not less than 97%. See table 304.081.
599a2cbd-efd9-5845-b6e0-2e6ce1bf181c | note | ○ For work to be tested for compliance with Scale B requirements, the number of tests per lot shall be six. See table 304.121.
991fcb3e-c957-5d0c-95b0-c3b0f3d239b9 | note | ○ The maximum thickness of any pavement base layer shall not exceed 150 mm and the maximum thickness of any subbase layer shall not exceed 200 mm.
ff09d6ca-fa97-52bf-a65e-d9341fb1cde9 | note | ○ The minimum thickness of any pavement layer shall be 4 times the nominal size of the material.
0ee7eeed-c245-546b-be24-f3700afa0c1d | note | REFERENCE DOCUMENTS: Vicroads std sec 304.08
d755f721-e392-5ee0-9873-bba2b97c4ea1 | note | METHOD: Laboratory Test Report
3e2dc3bb-a3de-5e24-a99e-8d8d469bcbc4 | note | RECORD: Signed ITP
e70cadcc-dca3-509c-a1bd-cd32a41e52e0 | note | IHP/IP/AP
992d0d2a-b67a-56ae-96f8-64eb43956455 | note | RESPONSIBILITY: FH Project Manager/FH Site supervisor/RRV Superintendent
ead3b575-85f4-53d2-847a-0d3f3fb3711c | date | Date Completed:
1bf8ab50-a0bb-4967-a192-8ae201eb9585 | checkpoint | 2.3 - TEST ROLL PAVEMENT LAYER
6aaef28f-934d-5979-a4f9-f6a3387ad91f | note | FREQUENCY: Each Lot
4f42abe0-3213-5586-86ae-a9c220f64ad6 | note | ACCEPTANCE CRITERIA: The Contractor shall not commence placing any ﬁll on the prepared areas until the area has been reviewed by the Superintendent. The Contractor shall provide for the Superintendent to be present during all test rolling.
9ab9d3e4-575a-5966-92de-b3bd2852c3f2 | note | REFERENCE DOCUMENTS: VcRoads Std Specs 173.03 & 204.12
37069f31-3bd4-55be-bbd3-782565b19723 | note | METHOD: Proof roll
8363e224-2979-5096-b1d0-2977a75edda5 | note | RECORD: Signed ITP & Test Report
f8ae737d-ead3-592b-acef-56b77d037708 | note | HP/AP
98a059c7-c208-58f1-9bd3-ab6da4a9ff18 | note | RESPONSIBILITY: FH Project Manager/RRV Superintendent
012cdc0c-4b22-5dd7-be39-0e6be51c76b4 | date | Date Completed:
656a6422-0c72-4498-bcbf-47cad835da3f | signoff | AUTHORITY HOLDPOINT
36cceae5-9991-47a7-8a6e-674f79c744ba | checkpoint | 2.4 - CONFORMITY WITH DRAWINGS - Random Level Assessment - Scale B Surface Level Requirements
be7a0dab-a7de-5425-a9f7-0872bd643d95 | note | FREQUENCY: Each Lot
8ac2cea4-0c34-5e6a-af04-ab0330c7cafc | note | ACCEPTANCE CRITERIA: The surface level of the pavement courses shall be measured in accordance with the requirements of Section 173 and every test lot shall meet either Scale B requirements as speciﬁed in Clause 304.12.
34ba8b37-e7ef-5088-af91-dee241111e17 | note | ○ Random level assessments of the surface shall be undertaken in lots not exceeding 4000 m2.
c13fcf63-66a0-5b5d-86e8-7655b6bcfcc4 | note | ○ Each level measurement shall be taken at random locations over the area of the lot in accordance with the VicRoads Test Method and the number of measurements taken within each lot shall not be less than the number speciﬁed in Table 304.061. Surface Level Tolerance as per Table 304.062
49377f82-1f08-5c7c-8d07-0510bc3c7116 | note | REFERENCE DOCUMENTS: VcRoads Std Specs 304.06
467cb9ff-65e5-5a67-96f6-e3472a23bcf0 | note | METHOD: Survey report
1f517208-595b-52a1-b7b5-6de2427dffd6 | note | RECORD: Signed ITP
bafeecc9-fb9f-5537-af23-ef0289aa7c28 | note | IHP/WP
5e11b8f2-83da-575d-ae7f-8212a8938301 | note | RESPONSIBILITY: FH Project Manager/RRV Superintendent
c72a87d4-dc8b-5248-9130-f8b987e78627 | date | Date Completed:
f7beb224-8513-4f2c-be87-afa5174b3e20 | checkpoint | Final Inspection
9f3e7459-0f48-539e-b62f-0051aa02af90 | note | The signature below veriﬁes that this ITP has been completed in accordance with the Fulton Hogan’s Quality system Procedures and veriﬁes lot compliance with speciﬁcations
e23f12e4-7430-55e9-875d-7d58c5e71680 | textbox | Print Name:
252d6726-c8ec-5152-b33d-e1901b8209d7 | textbox | Position:
9a7a57b1-c245-5856-bf3c-90c26ec4b213 | date | Date:
74fdf172-6767-4888-82c6-98d5085c1c45 | signoff | Sign ITP
8c94227a-f364-43b2-b3ec-dacaf6d02577 | checklist | ITP-006 - Kerb & Channel Rev1 | itp | ITP-006 - Kerb & Channel
8879bde7-f167-4544-a44e-9e6e991a7807 | section | 1 - Preliminary Works
fad773f0-f1b4-4e86-b88c-f48651544f1c | checkpoint | 1.1 - Check for correct documentation
84b52823-6554-5d22-b74d-bbbb7953ac3b | note | FREQUENCY: Prior to commencing any activity
25b701f8-a6c1-5ffd-978a-21d429b1b745 | note | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are:
bff70637-fa1e-569e-b3b5-3037db238f41 | note | – using the correct and complete set of drawings
878c0e4a-c68b-58b9-9788-33420f670532 | note | – all drawings are the latest revision
7edd3299-e235-5e11-8b7c-cd19f3f942a7 | note | REFERENCE DOCUMENTS: Vicroads std sec 100.6
b7e55fbd-c60f-556b-83ff-9f6c5cdc6fc2 | note | METHOD: Drawing Register
315d8951-a96d-59d1-947a-9aa7dd09b8f5 | note | RECORD: Signed ITP
53d5c2a9-59a1-5c7d-be9f-a6a15fe7fd41 | note | IHP
3d5acab1-54d7-5919-8e4d-50f41171846d | note | RESPONSIBILITY: Site Supervisor
5c9e0a67-d250-569a-ab0e-a43afcc4fcee | date | Date Completed:
ee070219-ac34-446a-81f2-5a06a8b2e797 | checkpoint | 1.2 - Implementation of all measures and controls
7b791d4b-4536-58b6-b113-1715ceaf4027 | note | FREQUENCY: Prior to commencing any activity
8eeebd41-f363-52a3-98f1-4a380421c75b | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: EMP, TMP & SWMS.
51797da7-a13a-5257-be7b-cf2db64839f5 | note | REFERENCE DOCUMENTS: EMP, TMP & SWMS
cd1ea59c-2600-5edc-a424-ee762a04bb05 | note | METHOD: Visual Inspection
0cb6e195-d37e-53a2-a17a-ee89222b027e | note | RECORD: Signed ITP
058a1b09-13fe-547a-bbd9-4e9f6c5bbe72 | note | IP
95afaa1c-2a46-52fe-a7f6-c1876ed146c5 | note | RESPONSIBILITY: FH Project Manager/Site Supervisor
82a29c45-1c78-5175-a3ab-d87bf3dceb46 | date | Date Completed:
6456fc27-f8b8-400b-8fcc-c10dd851e0de | checkpoint | 1.3 - Setting Out
5720d38d-11cd-5a7b-abf1-867bcfaa2432 | note | FREQUENCY: Prior to commencing any activity
8ae199b1-a824-52e0-b3ce-7e5ae783d2e8 | note | ACCEPTANCE CRITERIA: Chainage locations clearly identiﬁed for extent of kerb and channel by qualiﬁed surveyor. Oﬀset for lip of kerb alignment shall be set minimum of 1m from Back of Kerb (BOK) and with ﬁnished heights indicated on survey peg.
2ffd5746-f1f9-5a83-aab3-1d405fef8995 | note | REFERENCE DOCUMENTS: Vicroads std sec 703.13
edea9efd-7038-5bbb-b69a-25ea6f091959 | note | METHOD: Survey Setout
4a38ce19-19f3-5e45-a92a-1d4473d6c00c | note | RECORD: Signed ITP
43d357f9-8384-53d3-ae0e-776a79b0dd8e | note | IP
3cfcd109-3693-56e9-ab3c-80e2a3b94d00 | note | RESPONSIBILITY: FH Project Manager/Site Supervisor
bf92743b-c281-5411-b6d7-5b1e82ce2cff | date | Date Completed:
fa68ff76-2f11-46a6-a030-cab601c9e1c3 | section | 2 - Construction Works
2bc11d9a-86a0-4982-bfb8-138ab59e5ce1 | checkpoint | 2.1 - Excavation
bdce75b2-efdd-561d-8401-2f6896b082b6 | note | FREQUENCY: Check prior to placing material
e5952b58-750d-5236-a754-c0d0bb6f8655 | note | ACCEPTANCE CRITERIA: The base preparation for kerb and channel shall consist of a boxed out area to a depth of 355mm below FL and 1150mm wide. Excavation shall not extend more than 150mm from the edge of the adjacent face.
8e68226c-2549-55a5-88c8-07a67c4c762f | note | REFERENCE DOCUMENTS: Vicroads std sec 703.20
c31e2673-0ce1-5c9c-9f1b-297aecb4ec69 | note | METHOD: Survey/Site Inspection
9b146cd0-98ff-507d-b415-d3ba3dd225fb | note | RECORD: Signed ITP
28008720-84fd-5650-9e96-52a5668a32cc | note | IP
4ed50d98-ad52-5de1-8c51-dcd1fca44375 | note | RESPONSIBILITY: FH Project Manager/Site Supervisor
24c465b5-09ac-54b4-8940-96aa60289a82 | date | Date Completed:
91956484-29ca-4819-bbc3-f9bdde4d60e3 | checkpoint | 2.2 - Subgrade Inspection
bffe911a-d360-5ffc-9100-bb7655a74bf2 | note | FREQUENCY: Check prior to placing material
12bfb0af-d4a0-5f78-8972-4a71dc99c6b5 | note | ACCEPTANCE CRITERIA: Test roll subgrade to check for No visual deformation or springing. Where deformation is exhibited, the Engineer or Superintendent is to be notiﬁed immediately.
38f277d2-c48a-5c3c-bbf5-0a4defa7db97 | note | REFERENCE DOCUMENTS: Vicroads std sec 173.03, 173.03 (ii)
cc2e45f1-786b-5cfc-93a0-dd04e8900d67 | note | METHOD: Visual Inspection
e402636f-bb71-532c-8c15-e63ac851d3b0 | note | RECORD: Signed ITP
43042ba2-576f-55b7-be77-1e0b98f68b30 | note | IP
3f86b167-a13c-5742-933d-84beb9862cea | note | RESPONSIBILITY: FH Project Manager/Site Supervisor
1c8e75ac-50e7-5bff-b9fe-26fe1b23fdf9 | date | Date Completed:
7221a3bd-dd61-4eb7-ad07-e9f41641687a | checkpoint | 2.3 - Bedding Preparation
8f3e387f-ae0f-5ba6-a023-0a7f89049e68 | note | FREQUENCY: Each lot as required
2d9a5efb-0f36-5cef-99a3-80504d35ca64 | note | ACCEPTANCE CRITERIA: Bedding material to be used for base preparation shall consist of size 20mm Class 3 or Class 4 crushed rock at a minimum of 100mm compacted thickness. Preparation of ﬁnished base shall be 190mm below lip of kerb as per survey marks.
fce76eab-f4fa-534d-bb51-84912b39cc21 | note | REFERENCE DOCUMENTS: VcRoads Std Specs 703.21
c5f6e624-1596-5163-8718-7985781ab488 | note | METHOD: Site Inspection
a6afe809-487e-5f30-99fb-5026df7f9169 | note | RECORD: Signed ITP
bec5b087-45bc-5549-b0c6-c67bedf86bfb | note | IP
a9e64e8c-b432-55ce-9347-9e8b0e352aca | note | RESPONSIBILITY: FH Project Manager/Site Supervisor
334857db-f9a0-5f05-9356-f7ac950f4b8c | date | Date Completed:
9a33a04c-4080-479b-9e61-5581c196b86f | checkpoint | 2.4 - Kerb Concrete Mixture/Strength
b6ec300d-338c-512f-951a-008fd44b1407 | note | FREQUENCY: Each lot as required
8ce07619-77c6-56eb-b194-f4bc3b471491 | note | ACCEPTANCE CRITERIA: Traﬃc routes a minimum of or equivalent to 320kg of cementitious binder material or geopolymer binder per m3 of concrete – VR 330/32
034a7bf9-a6ce-5c93-a75b-d03467b6958a | note | REFERENCE DOCUMENTS: VcRoads Std Specs 703.05, 703.11
d31388e5-3e9d-5b30-b62a-1ac495a2f8e1 | note | METHOD: Delivery Dockets
7234b192-a109-544a-9f0a-f2f9c7837602 | note | RECORD: Signed ITP
acf1f7ab-1529-52c7-a2a2-14cdc4a360ad | note | IP
aecbf32c-fa5a-51f6-b641-c3fe8c144749 | note | RESPONSIBILITY: FH Project Manager/Site Supervisor
e7bb9a94-2e8b-5a10-a359-93f0887da65c | date | Date Completed:
4ad1460c-da42-4f4e-94d8-e8405baa4d0f | checkpoint | 2.5 - Tolerances on Line, Level & Shape
096055c3-ffc3-5e27-ba4b-10d04d4b99b5 | note | FREQUENCY: Each lot as required
4af7699f-3100-56d1-bfc1-4fc2de7ad27d | note | ACCEPTANCE CRITERIA: All surfaces shall be ﬁnished in conformity with the lines, grades, thicknesses and cross sections shown on the drawings or as speciﬁed. Kerb and channel shall be constructed to the level of the adjoining pavement with a tolerance of 0 to +10mm. Except on curves or in shaped areas, the deviation of the ﬁnished work from a 3m straight edge shall not exceed 5mm at any point.
6d6394dc-f612-5e53-8bae-f53d8ffa5ac9 | note | REFERENCE DOCUMENTS: VcRoads Std Specs 703.15
8a1001b2-2a1d-507d-9fe9-15b6def4b2ff | note | METHOD: Visual Inspection
45acdeec-fd68-56da-a414-4574c123f9d4 | note | RECORD: Signed ITP
43c870a0-bcb4-5399-b14d-9a06f2f49fc7 | note | IHP
87bea593-eaaa-5df8-87eb-23d3e41ea152 | note | RESPONSIBILITY: FH Project Manager/Site Supervisor
83b8b372-ec7d-5d03-ae2e-41242888e9ee | date | Date Completed:
80537036-4cd9-4b83-994b-bff6d9ca122b | checkpoint | 2.6 - Kerb and Channel Finish
ba42db2d-5036-5738-82df-889f39fa45ac | note | FREQUENCY: Each lot as required
6d57c2be-b68d-5a46-b4e2-ca32f8537aea | note | ACCEPTANCE CRITERIA: All edging shall consist of a smooth, uniformed and of a trowel ﬁnish. The mortar used shall consist of two parts of ﬁne aggregate, one part cement and suﬃcient water to produce a mix of suitable consistency. Thickness of the rendering shall not exceed 3mm.
ca88f8d6-b306-5d01-bf87-ae2537c0ad13 | note | REFERENCE DOCUMENTS: VcRoads Std Specs 703.21 (a)
5322c92f-b0df-5d4e-a73f-d94b7aaef688 | note | METHOD: Visual Inspection
292acfb1-f666-504f-ae0f-efba2aac4f0e | note | RECORD: Signed ITP
323b3806-81e9-540c-8d48-87f283ff30f3 | note | IHP
50382cd9-791e-5769-97a4-bc27be44f487 | note | RESPONSIBILITY: FH Project Manager/Site Supervisor
836ec7c1-199f-5afd-b280-e852d77c4661 | date | Date Completed:
7541a9da-aeaa-491a-836d-92cc45406287 | checkpoint | 2.7 - Kerb Backﬁll
9082c245-b31b-55aa-a429-bd4b6889a984 | note | FREQUENCY: Each lot as required
83b5cd47-9e11-5ecd-a576-2747c60bdb9c | note | ACCEPTANCE CRITERIA: Once concrete has cured, topsoil which is free from perishable matter, shall be placed ﬁrmly compacted in layers less than 150mm thick and to a width of no less than 300mm behind the edging to the top of the edging.
513a68e7-a6fb-5f69-9aeb-63553f6eb2b0 | note | REFERENCE DOCUMENTS: VcRoads Std Specs 703.29
85e33604-6189-5a53-803f-ce3bc0e8fa34 | note | METHOD: Visual Inspection
91419dc7-ae29-50d1-8f30-f6939e501dc2 | note | RECORD: Signed ITP
e4725430-dd86-52f8-91bc-08cd51256b0d | note | IHP
f73874ed-713a-5905-9700-5bc314b5d1b4 | note | RESPONSIBILITY: FH Project Manager/Site Supervisor
4b703cd8-70cf-5e35-9b55-ac8619394ca5 | date | Date Completed:
81d9c11c-4183-48bf-86cb-fa9d1db410f5 | section | 3 - Testing Requirements
55085e33-af69-4666-93bd-6fd8a38daee1 | checkpoint | 3.1 - Compaction Testing
9f0c8d70-a3e5-5b18-94df-06b9013ee1a8 | note | FREQUENCY: Each lot as required
e5a1c76e-3c80-51db-b771-be21189a53c5 | note | ACCEPTANCE CRITERIA: For work to be tested for compliance with Scale A or Scale B requirements, the number of tests per lot shall be six. A small lot is classed as an area equivalent to or less than 500m2 and requires only 3 individual tests. Compaction testing for crushed rock material shall be no less than 98%.
e0770393-5887-52be-8aef-e7a4ccb9c2f7 | note | REFERENCE DOCUMENTS: Vicroads std sec 304.08 (b) Table 304.081, 173.04 (d)
7a98754d-fc87-5886-bf96-0609c922332c | note | METHOD: Test Point
e9a66aa5-1fed-545e-ab3c-72cdd420b610 | note | RECORD: Signed ITP
5dbb304c-3cfd-54e2-b5f1-55e4c377a2ed | note | TP/HP/AP
c1a12411-34e4-56fa-8c2a-646b2b9b5e36 | note | RESPONSIBILITY: External Geo tester/FH Project Manager/RRV Superintendent
c7e7a0ac-e77e-5b06-83f5-8bddbfe04250 | date | Date Completed:
4a7d163f-d33a-4bb7-aaea-bfae8f2626d8 | signoff | AUTHORITY HOLDPOINT
49fc9fba-995b-4232-82ba-ac1b5f0eb2d7 | checkpoint | 3.2 - Conformance Testing for concrete strength & consistency.
ffa14f04-f3dc-5795-ab08-4afb3427e8f8 | note | FREQUENCY: Each lot as required
8c55d656-8823-5443-828b-864554752d1e | note | ACCEPTANCE CRITERIA: The minimum compression strength requirements for each strength grade shall be as shown in Table 703.111
c734b423-d679-505e-90ee-e64c91037f61 | note | REFERENCE DOCUMENTS: Vicroads std sec Table 703.111
ac26ec99-ed47-5ff2-bf00-ecc07cb21100 | note | METHOD: Survey Report
b6ecebfc-c9a9-5a24-82c9-2ece776121ae | note | RECORD: Signed ITP & Test Reports
0a0eb407-60d4-5a59-92a8-f59863fefc87 | note | TP/HP/AP
df2aa92f-aceb-5d4a-9eef-5c74334ea720 | note | RESPONSIBILITY: External Surveyor/FH Project Manager/RRV Superintendent
84218fcc-0e1a-5e48-b677-606e25206bc6 | date | Date Completed:
07ba52d3-913a-4f4f-a81e-59240a68882d | signoff | AUTHORITY HOLDPOINT
ccff9eb0-19f1-4385-aedc-a263c18c6cca | checkpoint | Final Inspection
f0161430-3416-51dd-bb1d-1afcff70a2d7 | note | The signature below veriﬁes that this ITP has been completed in accordance with the Fulton Hogan’s Quality system Procedures and veriﬁes lot compliance with speciﬁcations.
c10db360-dad1-53af-828b-0cc51a178e71 | textbox | Print Name:
1567a9db-c5e7-5f22-ab05-8fa2e366d4b2 | textbox | Position:
09b7980c-8c25-576a-99bc-bad56dfef392 | date | Date:
48824ad3-fdf9-4e88-932a-d5e6724713cc | signoff | Sign ITP
ad11a893-a1e0-4e7c-9acf-fa344183bd76 | checklist | ITP-007 - Hot Mix Asphalt Rev1 | itp | ITP-007 - Hot Mix Asphalt
8fb2fb16-98bf-426d-88aa-9db02aa770ac | section | 1 - Preliminary Works
ede63562-15a8-49e6-a138-c9d3f73a29b4 | checkpoint | 1.1 - Site Inspection and Base Conditions
3f834e13-2d65-5e96-af44-d4f865b775cf | note | FREQUENCY: Prior to commencing paving.
7f4aaf7d-ea7c-57ae-862c-e3627e1744da | note | ACCEPTANCE CRITERIA: Surface on which asphalt is to be placed is essentially dry and free from surface water. All manhole and valve covers have been raised or lowered to the new surface level of the pavement.
9e4d56ea-80ed-5110-80d9-a9d426f88dec | note | REFERENCE DOCUMENTS: Vicroads std sec 407.14, AS2150 10.1
e4cb8c23-59aa-5cab-8b37-425285ef37e4 | note | METHOD: Visual Inspection
11317d58-0b46-5641-baea-8de96121e4cc | note | RECORD: Signed ITP
4fcaa443-4c66-550a-9e52-7b572b32ccb5 | note | WP
e1492f32-cbdf-59bd-95a8-41828a70ad2c | note | RESPONSIBILITY: Site supervisor
fc9adb00-4a54-54b6-9a6e-11b5cd0f3f82 | date | Date Completed:
2c2fafc3-517c-4fdf-80c3-5bd1753902ec | checkpoint | 1.2 - Ambient Conditions for Asphalt Placement
0051143d-ce08-5377-9528-05e4b1972c38 | note | FREQUENCY: Prior to commencing paving.
966837aa-0136-5210-8593-06168c6e16f8 | note | ACCEPTANCE CRITERIA: Asphalt shall not be placed if the majority of the surface area is below:
6f006a6e-5e35-5fcf-8fc3-d53060bd3656 | note | ○ Base & Intermediate Courses: 5°C for conventional binders or 10°C for PMBs & Class 600
ae5e7da2-bf5c-5e6d-b875-4b44eb8e8e78 | note | ○ Wearing Courses: 10°C for conventional binders or 15°C for PMBs.
9cbafb4b-c8ec-525c-8c33-94a3fa730f1d | note | REFERENCE DOCUMENTS: Vicroads std sec 407.13
ca57b2a5-dad2-5782-a4e7-32283ffa5e27 | note | METHOD: Calibrated thermometer
45862ec1-96d4-5731-992b-7f02222c44c8 | note | RECORD: Signed ITP
059b3ffb-f0bf-5395-ad51-7479c61e2f5f | note | IP
0d976075-3a95-59f7-a325-b6ca869ba998 | note | RESPONSIBILITY: Project Engineer/Site supervisor
29f42c2e-4dd4-5e09-adb2-447cc5eabb58 | date | Date Completed:
f1600b24-630b-491f-9364-aa6f655fb4d8 | checkpoint | 1.3 - Surface Preparation
cc8f3109-166c-567e-8e02-adf6d305eead | note | FREQUENCY: Prior to commencing paving.
26ae563e-922a-597e-892c-dc9981875d68 | note | ACCEPTANCE CRITERIA: The area to be paved is free of all loose and deleterious material
84e6248d-b8c3-588e-9ae3-35c466641c9d | note | REFERENCE DOCUMENTS: Vicroads std sec 407.14, AS2150 10.3
cbbb5fe5-43b9-5815-9e1e-b05b303dee39 | note | METHOD: Sweep Clean and Inspect
b6830653-cf9f-549c-8a6d-e3cc94841bd1 | note | RECORD: Signed ITP
eeeaf889-78c7-5e55-8f01-c49552934989 | note | WP
9eb55e7f-b490-5e94-8076-9c8a4d315ce3 | note | RESPONSIBILITY: Project Engineer/Site Supervisor
622dee39-7e2c-5ea9-93e6-a6569bc6efff | date | Date Completed:
7a77a56e-fae2-469d-8f2d-f47c1bae510a | section | 2 - Construction Works
eef53c1c-0d40-4df3-a368-c0c16439a710 | checkpoint | 2.1 - Application of Tack Coat
fcf5daa4-f3ea-5ab6-b11a-f1a94cc7c03b | note | FREQUENCY: Prior to commencing paving
4b752ebb-ceb4-589c-ad09-08a768433de5 | note | ACCEPTANCE CRITERIA: Tack coat to be sprayed in a uniform ﬁlm over the surface area at a rate of 0.15-0.30 L/m2 of residual binder (60% bitumen). This rate is to be doubled on joints and chases. Tack coat must be allowed to turn from brown to black before paving. NOTE: Tack coat is not required on clean, freshly placed asphalt or primed surfaces or when the layer to be placed exceeds 50mm unless directed by the Client
3bc89894-caed-5119-8884-2e22f06eeb6c | note | REFERENCE DOCUMENTS: Vicroads std sec 407.15, AS2150 11
41cd073c-3baf-5928-a296-20b1782c6c3a | note | METHOD: Visual Inspection & photo evidence
3b80514f-7697-5158-b438-6bcdb489a786 | note | RECORD: Signed ITP/Spray Record
11ed2dc6-7574-55de-8f5c-4e8740262cf7 | note | WP
5972f22a-ecb0-5d8a-9926-0296cef7f77b | note | RESPONSIBILITY: Project Engineer/Site Supervisor
8becd464-895a-54a1-ba77-8bf2510289ee | date | Date Completed:
f09e4948-b94b-45e3-8872-112203ec69c1 | checkpoint | 2.2 - Planned Joints
3d9bebdb-edee-5a9a-a68f-0adbf8d6304e | note | FREQUENCY: Prior to commencing paving
af02af11-ef94-5f87-a84b-bdac1189a08b | note | ACCEPTANCE CRITERIA: A site speciﬁc paving plan shall be generated by the contractor prior to asphalt commencement to adhere to the following: Transverse Joints: Oﬀset from layer to layer by at least 2m Longitudinal Joints: Oﬀset from layer to layer by at least 150mm and be within 300mm of the lane line or centre of lane. Wearing course shall be on lane lines. Where new pavement abuts an existing pavement, the existing pavement shall be removed in steps to achieve an oﬀset from layer to layer of not less than 150mm.
fbc5289f-cb4a-53e8-a582-347e97402175 | note | REFERENCE DOCUMENTS: Vicroads std sec 407.17 (b) & (c)
aa5fb8b1-0a71-576b-bbfc-d95a5f2f107a | note | METHOD: Measure and mark out runs and submit Paving Plan to Client if requested
9b218da2-7f8f-5250-84c0-c6b98d7fa4c1 | note | RECORD: Signed ITP/Job Sheet
fbcaadfd-4b6d-52b4-8c64-e48931e2b7ae | note | WP
e763dfe0-392d-52d9-851f-e89373318740 | note | RESPONSIBILITY: Project Engineer/Site Supervisor
c2315f14-b51d-52a3-92ad-7b79c663cbad | date | Date Completed:
af3b61a8-064b-4d93-aa39-8dce306aeb93 | checkpoint | 2.3 - Commencement of Placing
ca135723-8dc0-5243-8c56-b5a2df43cc53 | note | FREQUENCY: Prior to commencing Paving
2ea2ac5e-3833-56dd-b966-05315132d7a6 | note | ACCEPTANCE CRITERIA: The placement of asphalt on the sub- base or granular base for a new pavement or for an overlay of an existing bituminous surfaced pavement shall not commence until the consent to proceed is obtained from the Vicroads Superintendent.
d3393fe3-1f59-5b2a-83bd-15caab350630 | note | REFERENCE DOCUMENTS: VcRoads Std Specs 407.18
ff5dc533-bd62-5e67-b6ab-91d0dad1356d | note | METHOD: Visual Inspection
95041c7b-7a4e-53e1-bddb-f15632c51634 | note | RECORD: Signed ITP
fac73d84-3b12-5028-8c32-454f9213a515 | note | HP
f310ae5b-7a5e-576d-8055-6094b44a2990 | note | RESPONSIBILITY: Fulton Hogan Project Engineer
a3d16390-796f-588c-b3e1-0a1fae3a6b3d | date | Date Completed:
d0ff0d2c-0dc7-413e-bfea-5ed441febb5c | signoff | AUTHORITY HOLDPOINT
8d367f90-bfe4-4de7-89ee-4a110fc4123d | checkpoint | 2.4 - Delivery of Mix
9f4bc750-2ba5-5940-adfd-a3488a665acc | note | FREQUENCY: Each Load
09e565b9-8176-5a1d-9347-a661bf9ed33c | note | ACCEPTANCE CRITERIA: Asphalt is not segregated, binder is not separated or does not contain uncoated particles and the temperature from mixing plant is not more than 175°C.
68d368cf-b3ec-5eb3-95b2-058a3d09fb07 | note | REFERENCE DOCUMENTS: VcRoads Std Specs 407.16, Table 407.081
49ba27b9-3dd7-52f5-bb90-a4c51054ea91 | note | METHOD: Visual Inspection & Delivery Docket
4cdc5a9d-9b87-54c1-bc3f-8ef5150f9a2f | note | RECORD: Signed ITP & Production Dockets
b6011e42-927c-5cc3-9720-48e9c3770919 | note | WP
e652227f-a255-5636-9789-d9abd907dc79 | note | RESPONSIBILITY: Project Engineer/Site Supervisor
1b46a552-1094-5807-a20b-cf811549e602 | date | Date Completed:
3319d752-5fed-47a3-98cd-8c53095a7515 | checkpoint | 2.5 - Traceability
94a90b12-b7a4-5ef0-a739-0e3ddf426627 | note | FREQUENCY: Each Load
5aac4146-087c-5db4-811b-f3831d3f735d | note | ACCEPTANCE CRITERIA: Ability to locate asphalt test results placed in three dimensions i.e. start/end chainage, oﬀset/lane and layer
2fe90295-67c1-51b0-9f67-378311b9a058 | note | REFERENCE DOCUMENTS: Fulton Hogan Quality Plan
b49d7eae-fe9e-5a99-bfd2-172d2bea1dd3 | note | METHOD: Project Engineer/Site Supervisor
b09146e7-6b81-5e6a-833c-63925f07c72c | note | RECORD: Signed ITP & Traceability
125993a2-8284-5075-8cab-060337a2e480 | note | IP
fd05b92a-3e2d-5c75-a0f7-9a98d4503f1a | note | RESPONSIBILITY: Project Engineer/Site Supervisor
35a1cf1c-832c-5fb4-ac13-679cc1fb38c5 | date | Date Completed:
f3916154-dda6-4c51-8f7e-28fc0c0076d6 | checkpoint | 2.6 - Layer Thickness and Level Control
9cf74044-338d-5b2f-8175-8bba3db84109 | note | FREQUENCY: Regularly during paving
30088601-42cf-5572-b3b4-c0bf3b07dec6 | note | ACCEPTANCE CRITERIA: Thickness of asphalt layer conforms to asphalt thickness on drawings or speciﬁcations
9027471c-e9c1-52c3-b5fd-9612598dbbcf | note | REFERENCE DOCUMENTS: VcRoads Std Specs 407.20
e38a8591-e198-5e4e-bfe8-0931733c76fd | note | METHOD: Dips, string line, measurements oﬀ kerb
00b0ee1a-5fb0-50d5-bdd0-d773fd2ac078 | note | RECORD: Signed ITP & Traceability
34498218-76ad-5ec1-9f2e-66e0373ec633 | note | WP
9633fc36-56c1-5e3d-b990-f644867ebe76 | note | RESPONSIBILITY: Project Engineer/Site Supervisor
c2277a29-bdc0-5e70-b96c-93352691fb46 | date | Date Completed:
03e46b50-2e0b-47f7-afc4-6ef8461cec24 | checkpoint | 2.7 - Paver Stoppages
75f7d136-2ef7-5cb4-a769-10bd53fead2a | note | FREQUENCY: If paver stops
ccb7896b-c309-5658-a86b-49bd76502d4f | note | ACCEPTANCE CRITERIA: A transverse joint shall be constructed if the asphalt in front of the screed cools to below 120°C
3fd3c13e-97d2-530b-b6a2-90c271c2232d | note | Asphalt should be ramped down by constructing a temporary wedge of dense graded or cold mixed asphalt. Max ramp grade:
f3d2b4fb-9579-560a-afdf-6f5370481f26 | note | ○ 40km/h – 20-1
3c87fbc8-e43a-569e-8e6b-fd81912e42b0 | note | ○ 60km/h – 30-1
2548d814-ddbb-54ce-b866-6416396f481f | note | ○ 80km/h – 40-1
f738f555-a562-5e7e-ae72-b352477cae95 | note | ○ >80km/h – 50-1
1d082437-e1fc-5db4-9823-4aaff7c20a3e | note | REFERENCE DOCUMENTS: VcRoads Std Specs 407.20 (c)
19f55e99-208b-537b-8428-3baffd692a4d | note | METHOD: Thermometer
0d6c7135-065e-5dc6-9328-094e63c84dec | note | RECORD: Signed ITP & Traceability
f5ef8b7c-a7a7-58ad-9729-caf9a4bd8315 | note | WP
df6ade87-644d-5a45-b572-ec0b6c92483b | note | RESPONSIBILITY: Project Engineer/Site Supervisor
5d4e947a-b8f6-5124-af10-db71353ebb9d | date | Date Completed:
f41e8cda-2392-4608-8910-953ac39cfe02 | checkpoint | 2.8 - Surface Finish of Wearing Course
ea52c2d7-0085-5388-abab-9892adef0110 | note | FREQUENCY: During paving and after ﬁnal roll
241b3cbc-5ebf-5082-8183-92f6585e6b24 | note | ACCEPTANCE CRITERIA: The ﬁnished surface of asphalt wearing course shall be of uniform appearance, free of dragged areas, cracks, open textured patches and roller marks
4198cc13-e4fe-5c08-9cb9-b48de680d10b | note | REFERENCE DOCUMENTS: VcRoads Std Specs 407.23 (a) (i)
bb53d7f1-6d04-5bde-b4a4-7d09eb83501e | note | METHOD: Visual Inspection
03deb5a0-570c-5a40-8d38-8f8f2a7a1813 | note | RECORD: Signed ITP & Traceability
191f27b6-54bb-5c6e-9b42-52d1934e0871 | note | WP
a2bb6d80-05e2-5379-a77d-fe660b8ae3f3 | note | RESPONSIBILITY: Project Engineer/Site Supervisor
c10f9c16-8ba4-51a1-9a7a-6fd169ad38f4 | date | Date Completed:
7f9930b5-a97f-4125-9b92-07df73307d2a | checkpoint | 2.9 - Kerb and Channel
30d44fe1-2b64-5d4c-8bdf-19c3761d47bb | note | FREQUENCY: During paving and after ﬁnal roll
4e694115-e864-5759-8dc0-3c7a1f8bb744 | note | ACCEPTANCE CRITERIA: The edge of the wearing course shall be either ﬂush with or not more than 5 mm above the lip of the channel unless otherwise speciﬁed
59b14065-9094-5100-a4f5-ed3cf0b5f1ec | note | REFERENCE DOCUMENTS: VcRoads Std Specs 407.23 (a) (ii)
ba054bec-4d36-5f93-ad66-a4e3c0d52b48 | note | METHOD: Visual Inspection & Measurement
eb8c880c-a14f-5917-afa7-9d798987239f | note | RECORD: Signed ITP & Traceability
58424747-707c-5c37-970c-925b94bfba77 | note | WP
e7d0485c-2043-5ee2-978a-a36c0b6b98ee | note | RESPONSIBILITY: Project Engineer/Site Supervisor
4cbde6ac-a031-5147-b9cb-f16210a771cc | date | Date Completed:
a9901a7e-2d10-45b7-bcc0-4648f36119a3 | checkpoint | 2.10 - Alignment of layers not placed against concrete edge
f9b7a7bb-3124-5f75-be18-9e0fed6d4e03 | note | FREQUENCY: During paving and at completion of work
913608e6-d198-5747-ae7c-8932301c8ba1 | note | ACCEPTANCE CRITERIA: The edge of asphalt layers shall not be more than 50mm inside nor more than 100mm outside, the designed oﬀset from centreline or design line. The rate of change of oﬀset of the edge of layer shall not be greater than 25mm in 10m
a2d7c24e-091c-593e-a968-36daad056f82 | note | REFERENCE DOCUMENTS: VcRoads Std Specs 407.23 (a) (iv)
20294112-5983-54a1-9da9-a24a8fde2b6c | note | METHOD: Alignment as marked by Surveyor and measured
3e6ffaf1-ccd6-52ce-8fd7-7d55e4f5d385 | note | RECORD: Survey Report
63132329-2f23-5e51-b11d-539677c27072 | note | SCP
3324b555-8393-5383-a273-c383ff42af5a | note | RESPONSIBILITY: Client Surveyor, Project Engineer, Site Supervisor
8b930a72-01ed-54b2-9c97-0c76b1483fcd | date | Date Completed:
d184dd7e-cbaa-46bd-ac1a-9906091a6be6 | checkpoint | 2.11 - Width of layers not placed against concrete edge
996eea8e-97b6-58e5-b8b9-e648c1c9e294 | note | FREQUENCY: During paving and at completion of work
dff7e596-edd3-50cf-aafa-be9e414f1208 | note | ACCEPTANCE CRITERIA: The width of asphalt layers shall not be less than the design or speciﬁed width of layer by more than 50mm or greater than the design or speciﬁed width by more than 100mm.
5d73ebd1-242b-5f0f-ae3a-9043ec512675 | note | REFERENCE DOCUMENTS: VcRoads Std Specs 407.23 (a) (v)
605d41af-00ed-5909-ab61-93f4b9f7e5d7 | note | METHOD: Measurement
71cc70d3-fcfb-51ed-b1ce-70e11470dfa1 | note | RECORD: Survey Report
82a3eb0d-e633-520c-a07b-2092c9f49528 | note | IP
c9b84b8a-565f-556d-91c2-1606fc1f57e9 | note | RESPONSIBILITY: Project Engineer/Site Supervisor
941ef6a5-2c0d-5138-8bfd-bdb18e5ace4b | date | Date Completed:
7d720ddb-b79c-432d-a2a8-42c2d8d40f4d | checkpoint | 2.12 - Traﬃcking of Asphalt & Paving of multiple layers
d6cdd5ed-933c-57d3-967d-5de43e92795a | note | FREQUENCY: During paving and at completion of work
530d699c-e7ce-597f-8881-e47553facc80 | note | ACCEPTANCE CRITERIA: Traﬃcking of asphalt or placement of asphalt over freshly laid asphalt layer is not permitted unless the majority of the asphalt has a surface temperature lower than 50°C
9ec5f66e-f8a9-5945-90e5-ab5bc0b6a837 | note | REFERENCE DOCUMENTS: VcRoads Std Specs 407.23 (a) (v)
6cc230fa-5735-513b-b121-de5922973e49 | note | METHOD: Measurement or suﬃcient time has lapsed
2a6678cf-3e9d-5b54-91c7-a000014fe5aa | note | RECORD: This ITP
3f82afca-0113-50cd-bef9-c68fdbc02e4b | note | IP
f65f8789-5a61-5265-b02f-f5e78511d78f | note | RESPONSIBILITY: Project Engineer/Site Supervisor
658464a3-fb02-5a7a-b969-cee6831a1e2d | date | Date Completed:
6b239baa-b897-4caf-ac33-eef5790d6617 | section | 3 - Testing Requirements
0497fb4d-7220-442e-95ab-e648b421e16f | checkpoint | 3.1 - Compaction
43da187d-4ee1-52ec-99ae-1d2899dc4708 | note | FREQUENCY: Per Lot (6 shot test)
eea7fdbf-969a-57dc-b602-4ac42c97b06c | note | ACCEPTANCE CRITERIA: For layers <50mm, if characteristic density ratio is:
ac9bedea-dc81-5ed0-8fdf-8ae680322c26 | note | ○ 95.0% or greater Accept lot
c2c78e48-77c0-5afd-a417-29b411bc8c5c | note | ○ 94.9% to 93.0% Lot may be accepted at reduced rate
94bfa61e-4811-50f0-9c85-491576e4cd57 | note | ○ 92.9% or less Remove and replace asphalt
d20510cb-cbac-5792-b93a-c5ebf1067f8d | note | For layers ≥50mm, if characteristic thickness is:
8d2ee423-6f18-50f4-ba36-e9e6c7445552 | note | ○ 96.0% or greater Accept lot
c5a3d2ea-fb24-585a-abc7-1538b698ac10 | note | ○ 95.0% to 94.0% Lot may be accepted at reduced rate.
4cc2da49-7595-5b68-b0cd-66463c829230 | note | ○ 93.9% or less Remove and replace asphalt
893103f3-ff7b-5396-be9b-740f69521e8d | note | REFERENCE DOCUMENTS: Vicroads std sec Table 407.221
d676de8f-24eb-581e-b117-88f510a03ad5 | note | METHOD: Compaction Testing
984973ae-ab1c-52f9-8ef2-0c5b9a897f90 | note | RECORD: Asphalt Field Compaction Report
c32dac89-0182-5655-93ec-1096da5f539a | note | TP
663b4d59-3802-5dc7-bd59-f930269c7625 | note | RESPONSIBILITY: Fulton Hogan Laboratory Technician Veriﬁed by Project Engineer
825e9305-7ec9-5a09-bc6b-7521ba06391a | date | Date Completed:
b5647df6-e575-45d3-80a9-c5e6a2bfb0b5 | checkpoint | 3.2 - Surface Levels
e684b7e1-7869-5697-a878-1da3446244e1 | note | FREQUENCY: Each lot as required
13d9f8c8-8077-5c3a-bfbc-ac65c3dd961d | note | ACCEPTANCE CRITERIA: Individual departures from design not to exceed ±5mm with a standard deviation of no greater than 8mm (Scale A)
d464146f-3121-5560-8c93-3aeb8fac294f | note | REFERENCE DOCUMENTS: Vicroads std sec Table 407.222
509bd4b0-3dda-54dc-a0aa-282686c0445d | note | METHOD: Survey
91c1b990-aede-547a-b0a3-063003ab6ba7 | note | RECORD: Signed ITP & Survey Reports
09beb6dd-3cfc-5a41-818f-cbac6af5c2b6 | note | SCP
18fb2f0c-d5b2-5a5b-b88b-ead251e2d2b7 | note | RESPONSIBILITY: External Surveyor Project Engineer to verify
4502068a-2f54-5591-9f3c-17f6d87cab22 | date | Date Completed:
40141e30-1b41-4007-9f0b-f6661b40041e | checkpoint | Final Inspection
c3323dcd-6149-57b6-b5e8-dc3d5a695462 | note | The signature below veriﬁes that this ITP has been completed in accordance with the Fulton Hogan’s Quality system Procedures and veriﬁes lot compliance with speciﬁcations.
d3a06a2d-8fee-5d34-9579-0b6b7ea92a73 | textbox | Print Name:
93e0cf83-857b-5ba4-856e-bceb24078209 | textbox | Position:
7b7b1426-44c6-53a8-b5ad-66c8f08dfa61 | date | Date:
079cfed8-940e-431e-88dc-9effac30299f | signoff | Sign ITP
860dfd61-dd11-4d89-bb82-6e7b0d3b337b | checklist | ITP-008 - Line Marking Rev1 | itp | ITP-008 - Line Marking
237e246a-f20f-45f6-be8f-c9f75ba8fb0b | section | 1 - Preliminary Works
d9467c3e-40cc-42c7-a935-2aec828fae14 | checkpoint | 1.1 - Line marking Conformance
0ffc9ce5-fdc7-57bf-a25d-57d3902893ef | note | FREQUENCY: Prior to commencing any activity
4866c740-3409-58b7-ab94-a061ca278716 | note | SPECIFICATION REFERENCE: 721.A05
2ff8830b-f0fd-535c-ae6e-099adbcbb61c | note | ACCEPTANCE CRITERIA: Materials to be used conform with speciﬁcation
2d196ff3-9eb7-542d-ac72-35f872220eca | note | METHOD: Record Review
16f7c0b5-4fcc-5276-9037-76e8b84afea2 | note | RECORDS: Material sheet
26d8d127-181b-5553-a224-92cbe9eb9fce | note | RESPONSIBILITY: IP - Contractor Representative, WP - FH Representative
48e42163-0311-5d29-b7e7-978a4c66c295 | date | Date Completed:
a83a825c-4905-413c-961c-9868f51dad08 | checkpoint | 1.2 - Site preparation
2766b790-4313-5ba0-a449-2de74bb9d9c4 | note | FREQUENCY: Prior to commencing any activity
a8374c38-5c28-5d50-b79e-e8cd3b1d43a2 | note | SPECIFICATION REFERENCE: 721.A06
1a8648cd-7380-5a90-8417-10a396adebef | note | ACCEPTANCE CRITERIA: Removal of any existing unsound, obsolete or redundant pavement markings. Removal of any foreign material or debris.
04ccf158-2d4c-5971-9d25-c5ba1532866a | note | METHOD: Visual and photos
eceb05a9-3d7a-50ee-ba6d-95630c5c22c0 | note | RECORDS: Photos
01885bc8-92ab-5b07-a796-446ca64c46c1 | note | RESPONSIBILITY: IP - Contractor Representative, WP - FH Representative
5adae9f1-d684-595d-a5c8-9aefa011ed07 | date | Date Completed:
e621e62f-1521-4de4-86f2-0589279e9e0f | checkpoint | 1.3 - Set-out of Pavement Markings
a2d34b1f-7548-5e6b-b6c5-92b0e34b6c15 | note | FREQUENCY: Prior to commencing any activity
a4b35e5b-57b3-51b9-914d-671133adcd2c | note | SPECIFICATION REFERENCE: 721.A09
1d2cbe13-7872-5d19-be7c-7f4b817ce566 | note | ACCEPTANCE CRITERIA: Pavement markings to set-out in accordance with IFC Drawings
bee989b5-18ae-5e5f-875f-423a74ee7c8d | note | METHOD: Visual and photos
162bcdf5-4fb7-5369-9f3a-61b885a4a758 | note | RECORDS: Photos
a39e3baf-84ca-52c0-bf03-dd60aa272857 | note | RESPONSIBILITY: IP - Contractor Representative, HP - FH Representative
7b4eb61b-7289-58e2-9a66-069c927f4541 | date | Date Completed:
9c3bb038-2c00-473e-85fe-ac214556750a | signoff | AUTHORITY HOLDPOINT
122605c9-54fa-490b-906a-2df18b2efd65 | section | 2 - Installation
50d83829-cbeb-4eb1-a870-7b03c092ba49 | checkpoint | 2.1 - Line marking Installation
cb1be43d-1296-59d3-ab35-0b4d1ef78730 | note | FREQUENCY: During Construction
ac489085-4a2e-589e-a7f3-fbe5679d552c | note | SPECIFICATION REFERENCE: 721.E01
d7117b9d-814e-521d-9e3b-ca9e05065d42 | note | ACCEPTANCE CRITERIA: Line marking installed as per IFC Drawings
b03afa3b-dbf7-587f-b7c4-524ac88efae9 | note | METHOD: Visual and photos
047e502f-47d2-5bb7-a306-380f2d2686b3 | note | RECORDS: Photos
e4876d94-e966-5ea4-8bd9-ef70a2e93232 | note | RESPONSIBILITY: IP - Contractor Representative, WP - FH Representative
055b0990-8940-5205-89a8-0189752f2c2b | date | Date Completed:
1a091473-631a-4722-917e-0bc186130871 | checkpoint | 2.2 - Glass bead Install
0dee327d-3e4d-58dd-b772-39531a5a3b34 | note | FREQUENCY: During line marking works
d30f5856-3b0c-5f68-9fdb-e7ebfbfe867a | note | SPECIFICATION REFERENCE: 721.E01
93de12f7-2ce1-5b4a-af44-cbd9ef369804 | note | ACCEPTANCE CRITERIA: Glass beads sprinkled/sprayed on to line marking while in a ﬂuid state to ensure embedment. Glass beads to have uniform distribution.
c4c1e040-2a84-5fb0-8413-2f624e92a222 | note | METHOD: Visual and photos
597c61c9-d65b-5396-bd5a-688fa6a776da | note | RECORDS: Photos
77645359-f205-5a75-bee0-ed07424ee172 | note | RESPONSIBILITY: IP - Contractor Representative, WP - FH Representative
f6cffa82-d152-5508-abcc-8667acacfd4a | date | Date Completed:
3f461f9c-848a-4632-b5f5-420064bae601 | section | 3 - Compliance
8d0e1fe8-a18c-4260-a6e7-3cee37398187 | checkpoint | 3.1 - Completion Inspection
6e9e9d42-2c61-540e-b78a-a538f6214923 | note | FREQUENCY: Upon Construction
1fbc4932-7588-53a0-b9c6-9f662d25401c | note | SPECIFICATION REFERENCE: 721.E01
b8c13a98-3405-517d-b0b4-cd17ea559bbd | note | ACCEPTANCE CRITERIA: Completed marking shall be uniform in appearance, texture, width and thickness and the surface shall be free from blister, air bubbles, tears, lumps, streats, overlaps, unbeaded areas, tyre marks or other defects.
8d981a55-2fd3-58d6-83a2-1a402ff8c72e | note | ○ Edges and cuts-oﬀs shall be neat and sharp, and there shall be no visible run-oﬀ, overspray, dribbles,splash or spiliage on to the surrounding area, or on to parked or passing vehicles
0ca387a4-14dc-574d-81b6-2c46d7dd75b1 | note | METHOD: Visual and photos
aa56a327-8c10-5212-a673-b568a8304edc | note | RECORDS: Photos
79c0a7e8-a38f-5067-b8e6-ff5119635528 | note | RESPONSIBILITY: IP - Contractor Representative, WP - FH Representative
2bfd393f-8a77-5d6a-8755-16ad438b33ae | date | Date Completed:
da7db3cf-ecb8-4b92-9b37-f56ecb7858db | checkpoint | Final Inspection
eb97ab66-ca72-5d4e-a87f-e37fae14c102 | note | The signature below veriﬁes that this ITP has been completed in accordance with the Fulton Hogan’s Quality system Procedures and veriﬁes lot compliance with speciﬁcations.
8ede4843-2fc2-55cb-bfca-c5c943071667 | textbox | Print Name:
482720df-f3f2-5040-83e0-39c8be31ccb0 | textbox | Position:
f3ba2c38-8829-5c79-8797-d81944cfa08b | date | Date:
18633851-de57-49be-9b71-7bbe0c335526 | signoff | Sign ITP
41b1572e-b2fb-53b0-8c57-7655a1fefb56 | checklist | ITP-009 - Road Signage Checklist | itp | ITP-009 - Road Signage Checklist
1b96c8c3-d3cb-5511-bdc0-8ad038818b89 | checkpoint | Inspection Checklist Items
dc9b7c6f-a3ed-5493-8998-dbc970ea3834 | textbox | Sign Code & Dimensions
a917188f-ab1a-5f77-b82e-144aef0167e9 | textbox | Chainage Location
c5198dd8-98c3-59ae-a1b4-113408481183 | textbox | Number & Post per Assembly
2477ad5e-17d6-5890-b4ad-005a3ffec528 | textbox | Mounting Height (H) (mm) & Spacing b/w post(S) (mm)
98565e99-e225-56ba-bf92-09385b9da396 | textbox | Post Hole Depth (D) (mm)
64db3e30-c50c-5fe8-8663-c497b25407f1 | textbox | Fitting Type and Number of Fitting
dd0678d8-3635-54eb-bb12-b59c577f0e13 | date | Footing and Sign Installation Date
9600558b-1bcf-560a-b940-10cd212b3d9d | note | Photos
e4df1e76-54d1-5b97-b96b-bf3da9d4c209 | checkpoint | Final Inspection
4c619913-70b2-59b9-8e85-7aa07009facc | note | The signature below veriﬁes that this ITP has been completed in accordance with the Fulton Hogan’s Quality system Procedures and veriﬁes lot compliance with speciﬁcations.
7c9377e4-e5f8-5220-be1f-c2b39c3c57de | textbox | Print Name:
f6476e10-3a1a-5684-898c-a073d3a3fdf6 | textbox | Position:
bd7fa19e-daa1-5a8b-9ef3-03c4d76e0e2f | date | Date:
20ae8cc0-7e50-549a-b298-b7d0166643ab | signoff | Sign ITP
981e7153-3854-5c45-8bbb-2905670016f0 | checklist | ITP-010 - Guardrail | itp | ITP-010 - Guardrail
56f12a57-1e96-5877-8041-0f0eb46d12c8 | section | 1 - Preliminary Works
78f2eb97-4d27-5397-9616-d0974c63c400 | checkpoint | 1.1 - Check for correct documentation
0ec57c45-86f2-5bdc-b58b-a216f96427bf | note | FREQUENCY: Prior to commencing any activity
086cb6b8-35d8-503d-979c-02b0754ff62e | note | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are:
ab817a45-c92b-5e09-af6c-7c7e05ebd0bf | note | – using the correct and complete set of drawings
0e87b665-1836-5f00-8bd9-0aff94e5fb43 | note | – all drawings are the latest revision..
aa50f204-8caf-51f3-b943-d67d410f8d74 | note | REFERENCE DOCUMENTS: Design Drawings
4a0abe65-ea75-56fc-871d-5432bf3fb90c | note | METHOD: Visual Inspection
251f8e93-1153-5553-8544-9e01118b4ab8 | note | RECORD: Signed ITP
03256eb2-10f7-5eb2-acbc-768daed6ab0d | note | IP
82c51713-01e0-5753-b05a-f8bc425c1a90 | note | RESPONSIBILITY: Project Manager/ Site Supervisor
6dcf91aa-ca4f-5cd5-bded-9751eee20558 | date | Date Completed:
457fc29c-5478-51c3-a60f-061f5ba4ad0d | checkpoint | 1.2 - Implementation of all measures and controls
5afcc918-dc4a-558f-aa76-735dfd2c28bb | note | FREQUENCY: Prior to commencing any activity
663cff31-6696-5aa8-af87-521b6453cf31 | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: EMP, TMP & SWMS
6a2336c7-2787-58be-84c1-3df28befa56c | note | REFERENCE DOCUMENTS: EMP, TMP & SWMS
c37a8318-8c2d-5a69-8c75-a83252fb4bc3 | note | METHOD: Visual Inspection
f341f913-15fa-54c4-97bd-e055ff085002 | note | RECORD: Signed ITP
5742e225-b980-5fa7-b89e-fd6a8e25bfc2 | note | IP
12c453ab-0f00-53a1-9a99-d7a762d45f9b | note | RESPONSIBILITY: Project Manager/ Site Supervisor
179b0df0-6817-59e8-83a9-f173c1ad472a | date | Date Completed:
73920d7e-e2c5-5db3-bfa8-d36b7058a4c5 | checkpoint | 1.3 - Setting Out
4c70ffe9-0fd7-59db-aade-198edbbb95fa | note | FREQUENCY: Prior to commencing any activity
8dd0c908-2af4-5773-b10c-1cdd07379690 | note | ACCEPTANCE CRITERIA: Chainage locations clearly identiﬁed for extent of kerb and channel by qualiﬁed surveyor.
caac9424-8219-5a49-be8c-0b27d7d96fdf | note | ○ Oﬀset for lip of kerb alignment shall be set minimum of 1m from Back of Kerb (BOK) and with ﬁnished heights indicated on survey peg.
f0a37273-72f2-5e02-a92c-218a38f5abef | note | REFERENCE DOCUMENTS: Drawings 708.08
a0b2264e-1557-5811-a657-fa658781abaf | note | METHOD: Document Review
25ba3632-56f1-5b5b-b635-2d5d334c04af | note | RECORD: Signed ITP
f9e669d5-a8fc-5868-88b2-85fd11d2861b | note | IP
5f22be86-56b4-51c7-a4f6-77db6d3b4243 | note | RESPONSIBILITY: Project Manager/ Site Supervisor Superintendent
540fad9a-8918-51a5-bfb3-689327283865 | date | Date Completed:
ac047a58-71cb-5537-8556-237da2441d20 | section | 2 - Construction Works
9579dbba-7fbc-5ddf-a026-c6bd5bf26814 | checkpoint | 2.1 - Supply of materials
07311716-27c3-59bc-8c66-34ff2ec8f1e8 | note | FREQUENCY: Each Delivery
41fd03e0-71a3-5cf0-8d71-d65231baead1 | note | ACCEPTANCE CRITERIA: All materials are to be on VicRoads current accepted products list and conform with the detailed design
8e743b2d-c7ea-5d17-8f27-b941961e81bb | note | REFERENCE DOCUMENTS: 708.04, 708.05 Detailed design
65b15744-9046-51d6-9b49-9c0cb11e31e5 | note | METHOD: Visual Inspection
70bdaa8e-43b7-5dea-8b64-f89f86506728 | note | RECORD: Signed ITP
1e7a1bf2-e8a9-5d1c-bb3b-ec9a92bfb1d2 | note | IP
d5b348f3-513f-539d-9466-d8c71722ef26 | note | RESPONSIBILITY: Project Manager/ Site Supervisor
0c0c4c74-906d-528e-b904-8c78909e065c | date | Date Completed:
a11c7727-374c-58fe-ae54-aad72e43d297 | checkpoint | 2.2 - Installation
85a5de76-58b8-5d60-aee8-b55099377790 | note | FREQUENCY: Each lot as required
8db5e8bf-9e53-5d1f-a2c4-2912b045a9c6 | note | ACCEPTANCE CRITERIA: The oﬀset, height and post spacing is to conform with VicRoads speciﬁcations and the detailed design
88f58727-1259-5f70-9b1b-a724f725415a | note | ○ Where the face of guardrail is less that 1m behind back of kerb, the mounting height should be measured from lip of kerb. Otherwise measure from ground level Fasteners are to be snug tightened to AS4100
c5f6a30b-5ebc-515c-b4c2-7a399533416b | note | REFERENCE DOCUMENTS: Detailed design 708.08 SD3661 AS4100
5f83d83c-6406-5083-9409-db6c8a43b72d | note | METHOD: Visual Inspection
fe660ed2-bef8-5c2e-9d8f-c860f088952e | note | RECORD: Signed ITP
b2c24674-080a-5153-8c78-959dfae3b2bb | note | IP
01ba80f2-36ab-5720-b70e-1c3e7a2f224c | note | RESPONSIBILITY: SWA Engineer/Site Supervisor
cd466e90-8a5b-5335-b067-d55ed355d4d9 | date | Date Completed:
1a622dd6-72db-5c53-b748-bd2deb588d9c | checkpoint | 2.3 - End Treatments
51b415f8-bb9e-5625-823b-01f660682781 | note | FREQUENCY: Each lot as required
57c5859d-5b20-5d54-8805-88afb2bad015 | note | ACCEPTANCE CRITERIA: Guardrail end treatments are to be installed to VicRoads speciﬁcations
0bbb2739-8a95-53a2-ace1-5e372d6aed4b | note | REFERENCE DOCUMENTS: Detailed design 708.08
6ea32cbc-291c-531d-b0a3-17bcdbd44c54 | note | METHOD: Visual Inspection
370fc108-8336-590c-b227-ef32a7bac163 | note | RECORD: Signed ITP
623b922e-10a0-5aee-bbb3-be120111e4dd | note | IP
edfa7fad-f9b0-59fe-badc-78506f6adf76 | note | RESPONSIBILITY: SWA Engineer/Site Supervisor
c070f63d-cad9-520d-a077-313ac75e4be6 | date | Date Completed:
7d961610-33b0-5075-8b0b-29fcab9d6e50 | checkpoint | 2.4 - Motorcycle rub rail
4d5697fd-9c4c-5f8f-a59d-ac37aa7b95a5 | note | FREQUENCY: Each lot as required
a748f548-eee9-5b61-873c-7ce62cbd9938 | note | ACCEPTANCE CRITERIA: Where speciﬁed, motorcycle rub rail is to be installed on the new length of guardrail
237b6204-7728-5f89-802a-f6314a444077 | note | REFERENCE DOCUMENTS: Detailed design 708.09
7509c32b-e1e2-562b-b3f5-6ad6425f2f4d | note | METHOD: Visual Inspection
e6c525e7-02f8-56aa-83bc-8a3ea15886d5 | note | RECORD: Signed ITP
54c65d0e-d8a3-539d-a84c-45b0a1bc4744 | note | IP
6ac946d1-567f-5d9d-8b3d-0ce869d45aaf | note | RESPONSIBILITY: SWA Engineer/Site Supervisor
29a00349-f5ee-5795-8f98-7a256ef90ccf | date | Date Completed:
e4df1e76-54d1-5b97-b96b-bf3da9d4c209 | checkpoint | Final Inspection
6ca108b5-1937-510e-89f1-beae553f2df9 | note | The signature below veriﬁes that this ITP has been completed in accordance with the Fulton Hogan’s Quality system Procedures and veriﬁes lot compliance with speciﬁcations.
68028ba3-22e7-5c2e-bfd6-3aaf14cc3eb5 | textbox | Print Name:
d1dbdee0-8b8e-5e3e-80e4-a67262f3bc1a | textbox | Position:
59922202-9206-54e2-84fd-08300ad09ec6 | date | Date:
20ae8cc0-7e50-549a-b298-b7d0166643ab | signoff | Sign ITP
03f66bb4-f5f3-461d-b781-a49c242883f1 | checklist | ITP-011 - Sprayed Bituminous Surfacing | itp | ITP-011 - Sprayed Bituminous Surfacing
93fa33f8-7709-4651-a627-7b7c9e2c601b | section | Details
61445f3d-639c-4a8c-8504-0d21de680733 | checkpoint | 1 - Preparation of sealing
cff9242f-fbf8-5414-a073-7c24f2147ca9 | note | SPECS REFERENCE: VR 408.02
d7002269-39bb-5c18-8acb-7d67cb836944 | note | DOCUMENTATION OR ACTION: Constructed to meet specified shape and level requirements Homogeneous and consistent with the material in the pavement base layer
03e69ba4-7cfd-5e10-a787-fc76737e851d | note | ○ Uniform in texture
997ca655-6d14-5f63-ae43-deefda2fe657 | note | ○ Free of tearing and scabbing Free of lamination on or within 75 mm of the finished surface
ee5eb2d6-c6e0-54ac-bd58-9dff98adee76 | note | ○ Level with adjacent sealed areas and edgings at the Joints
07fa5320-f833-52ca-a4d8-56e1d5423a70 | note | ○ A hard dense and tight surface capable of being swept with a rotary road broom or similar
22bec890-726e-545b-869f-9fe06789423a | note | ○ Free of looses and foreign materials
c96b2033-e4df-546e-bac8-fbb7867b0095 | note | ○ Dried back to the moisture content and embedment requirements specified in Clause 310.03
97c6f657-3ea3-5663-a1ba-4581d6e97bba | note | RESPONSIBILITY: Subcontractor
e9f9a715-c5a1-5aa8-b0d9-8eba4fdf9cc0 | date | Date:
53907519-1ab6-4476-9938-2962499da213 | checkpoint | 2 - Preparation Testing
7c634490-6015-538a-a348-f9d2cfe61861 | note | SPECS REFERENCE: VR 408.03
c56e711e-aff9-5a3d-b1ed-07ff2b29065a | note | DOCUMENTATION OR ACTION: Testing Scale B
44652329-ef93-515f-8534-88c1cd58a165 | note | ○ Maximum lot size 4000m2
8644e199-81a1-50c7-ae3b-880e86303553 | note | RESPONSIBILITY: Subcontractor
de0a892a-c892-5f26-b12e-41d9d924a6d9 | date | Date:
65490af4-83a4-4c27-aef5-6be9b8b7fdef | checkpoint | 3 - Commencement of Work
fef1d9b1-725a-5e37-96a4-f394d2fc4cf2 | note | SPECS REFERENCE: VR 408.03
a25ddcf7-7c52-5924-8844-b95750a8813e | note | DOCUMENTATION OR ACTION: HP - Work shall not commence until the contractor and the Superintendent have agreed that the road or pavement surface is fit and ready for surfacing no more than 24 prior to the work occurring.
1d32c36a-8ed9-5339-8a45-3d003584a501 | note | RESPONSIBILITY: HP VR Rep. AP
ff6d0caa-d896-5f33-8d7a-59f94181363d | note | ○ Site Eng
3b6e8706-a439-5fa4-badd-caae6bf1deea | note | ○ Superintendent
7782d94d-6c9f-564b-b7c9-10c4bd99bf72 | date | Date:
839c7d89-ca80-4cb2-bd8f-cef957b74b57 | signoff | AUTHORITY HOLDPOINT
b4a40e44-a39d-43e3-bf76-36129bdc832f | checkpoint | 4 - Limits of Work
e18accc4-2d19-5919-930f-f409a1b99a0e | note | SPECS REFERENCE: VR 408.04
7e243a63-d5e4-5050-aa9d-5db4b0edc39c | note | DOCUMENTATION OR ACTION: Limits of works shall be marked out as per drawing and table 408.161
2cce2553-e5cf-5d81-8814-5f1f40a8ee4f | note | RESPONSIBILITY: Subcontractor
387ae2b0-c89d-51a1-ba02-f295ab0bb789 | date | Date:
563edd87-7324-4f54-9e4f-fb1fa2a3cee5 | checkpoint | 5 - Materials
6db03085-d758-5c99-a3a4-a58934548ce5 | note | SPECS REFERENCE: VR 408.06 & 408.07
891f46eb-3c91-590e-91f2-325a15392390 | note | DOCUMENTATION OR ACTION: Materials to comply with specification, contractor to confirm materials to be used
64781f3f-a6ac-5604-a58a-f9a8ac13d58e | note | RESPONSIBILITY: Subcontractor
df73da13-cfa5-507a-b8d5-f3fd861f0aa5 | date | Date:
45b6c6a6-c68a-4e35-a8f2-c510f0620819 | checkpoint | 6 - Application
8f6b9b7f-0b2f-518a-a972-5bb9dd0cf155 | note | SPECS REFERENCE: VR 408.10
1a7e132d-8708-59b9-b608-c7a77e215fef | note | DOCUMENTATION OR ACTION: Supply Seal design to superintendent for review prior to application of seal and application rate not to be less than 0.1L/m2 for design
5ff11baa-48fd-572f-9990-0ce0ae2ffbad | note | ○ Minimum air and pavement temperature to e not less than 15 degree C
bf3a2abd-ad0f-559e-825e-5708f3e46793 | note | RESPONSIBILITY: HP Subcontractor
222ce37d-b482-598d-85d0-f9d23d9ab337 | note | ○ HP VR Rep. AP
bc32dd88-2348-57d0-ad19-95308a7838d4 | note | ○ Site Eng
57a265c7-a187-54d0-be46-3cef9c455607 | note | ○ Superintendent
e0022086-b80f-58a5-8ea7-c7ffa8f4bf63 | date | Date:
eeca1da1-4600-4fc1-8b3d-9b7029bf1987 | signoff | AUTHORITY HOLDPOINT
da74c6f9-4421-4d05-a8d4-c06a4df50890 | checkpoint | 7 - Removal of Loose Aggregate
79365212-2431-5aa9-af12-628355a4dd65 | note | SPECS REFERENCE: VR 408.11
eb58a75d-62c5-53eb-8e06-84bc5864fc28 | note | DOCUMENTATION OR ACTION: Aggregate to be removed within 48 hours of application.
11ba391d-064e-5d05-98a4-e0d9439ee920 | note | ○ Road to remain appropriately signed until aggregate is removed.
3a0ba5ad-9765-52d3-9646-aab916ec96ac | note | RESPONSIBILITY: Subcontractor
c9ee018a-9160-5029-9b7f-3344f79d7c27 | date | Date:
a7862975-0bb7-4178-9932-8669feafa809 | checkpoint | 8 - Acceptance of Loose Aggregate
6cdcba82-98f3-5cb4-ae57-8152ab7eb73a | note | SPECS REFERENCE: VR 408.12
93dde1d9-04d7-53ff-8580-4edafe0b6426 | note | DOCUMENTATION OR ACTION: ACCEPTANCE OF SEAL
7c66ee3b-9bd8-5e5d-94d1-0561220aee67 | note | ○ Accepted application rate shall not be 0.1L/m2 less than seal design rate
a9496df0-d14a-50ad-8ead-72b15f418dad | note | ○ Surface texture shall be based on visual assessment
97b29395-f65b-5e70-8a52-19d5e89bb215 | note | ○ Aggregate retention shall be based on visual assessment
acc827c7-f818-5b09-98ea-0c3e99ee1942 | note | ○ The seal shall appear visually uniform.
7e93cd0b-3a5f-5386-8179-375e0355db1a | note | RESPONSIBILITY: HP Subcontractor
48645473-3fca-5301-8600-9dbe96a446af | note | ○ HP VR Rep. AP
9a8b9bae-fc69-535f-8f39-29b0afcaba3e | note | ○ Site Eng
fde1ea6d-a8d3-5e63-a71a-21e8ea979b64 | note | ○ Superintendent
a359a989-ace0-54d9-a870-609bb7380fd8 | date | Date:
729f4191-3252-4a0e-bc0b-a5205e8e1d72 | signoff | AUTHORITY HOLDPOINT
4bbbd276-1409-4b7e-8cc3-003929e7fe06 | checkpoint | 9 - Maintenance of Seals (Repairs to Seal)
5c3eae87-5151-5708-9019-90ba14fcbfc7 | note | SPECS REFERENCE: VR 408.14
37ddc42b-f785-56b9-bfed-9e9f3f88e1cd | note | DOCUMENTATION OR ACTION: HP - Superintenden t to approve the proposed treatment to effect the above work before undertaking the work.
55c29598-be38-5343-ae21-2ba328f3f1cf | note | ○ HP - Where the treatment for protection or repair of a seal involves the application of a further seal coat the Superintenden t shall approve prior.
c2b7714b-6c69-5c9b-8e9d-623eb1cbb504 | note | RESPONSIBILITY: HP Subcontractor
6842f207-63a1-52b3-8781-affd1675d053 | note | ○ HP VR Rep. AP
15f70d05-08aa-5d97-9878-9eb73d7d720a | note | ○ Site Eng
92f41fee-4a70-532b-b1ce-dbad34bbdda3 | note | ○ Superintendent
cd1b0a17-c7fd-5944-b209-f82c5d70fd20 | date | Date:
a282a80b-0bb9-4165-a879-c6c00e36851b | signoff | AUTHORITY HOLDPOINT
0f4d7f4a-48ec-4de1-93ed-bba1db217d39 | checkpoint | Final Inspection
00d6ecf3-5858-5420-94a9-5dbf1851a393 | note | This is to verify that the final inspection has been carried out in accordance with the Fulton Hogan’s Quality Procedures and Project Quality Strategy and the product is hereby certified to conform with the contract specifications:
35eaab8e-8b45-586c-ac1d-4c6fb0f8f6ba | textbox | Print Name:
96576342-c889-57f0-8c40-42beab02b0d3 | textbox | Position:
fe9f077d-c8a5-556a-b72b-6bbacf73c5a4 | date | Date:
e55d43e2-7d63-4b95-acde-9602d72b45bd | signoff | Sign ITP
071f267e-65d6-5ec1-ae3e-4fd51de41713 | checklist | ITP-015 - Drainage Checklist | itp | ITP-015 - Drainage Checklist
13f7ffd1-5e39-5df6-8ea1-5ca3fe37ae75 | checkpoint | Pit Details
afd16bda-97e3-5754-8cbb-5ee0a29304bc | textbox | Pit No.
bb7ea087-37fb-5cd4-a859-16092d3bfe5f | textbox | Pit Type
3700b52b-7d10-594f-95f2-b8e9dab30909 | textbox | Dimension
41e518d5-d2c6-5512-b24c-a7bc2898354f | textbox | Inlet Level
2ab54a67-4535-5730-b9c8-a8be2f5c6bb4 | textbox | Outlet Level
c1384ddb-1ec4-550c-bd3c-4778cc89c5c9 | textbox | FSL
290caf0d-9fba-5a85-a0dd-73e9cb030aad | textbox | Pit Depth
f5136021-0cd5-516d-b858-1c4ccd860983 | checkpoint | Checklist Items
ac624d40-08bc-5426-9b5b-c423dd5c0b32 | textbox | Drainage Line Number
daa29e46-8508-5a48-b08d-f361bd3ae10f | textbox | Pipe Size
e4639f21-6947-5345-a311-15e53939e1f9 | textbox | Trench Width (mm)
499ecc76-afc3-516c-88d2-3c7a49542bfe | textbox | Minimum Cover (mm)
d2056b63-946c-5f28-b703-ec88f0006d41 | textbox | Beading Depth (mm)
ffd080c2-bbf6-53a0-9d39-930b9730536f | date | Start Date
515a47c7-7afb-50ee-b28d-2539758af222 | date | Finish Date
5fafde7d-7fad-516a-aec6-4672c04f8451 | checkpoint | Pipe/Pits/End Walls
3cfaf860-9b55-5617-b805-a33a0edf6914 | note | Pipes/Pits/End Wall in sound condition?
d4d0a798-2bbd-5bd2-86b0-698bcc3f625c | date | Start Date
829e1b3b-f075-58d3-bfe4-8c32bdbba046 | date | Finish Date
0eac159f-b12f-5d66-8d10-01cc4f217314 | checkpoint | Laying Direction
870fdf83-eae7-550c-8b8f-51b95043010a | note | The direction of Laying Satisfactory i.e Collar on Upstream?
ff9b4f1b-9a73-5a34-be7c-4fbdaac7d65d | date | Start Date
a56660c3-2851-551b-b087-3dbea48313df | date | Finish Date
66cf5018-577f-5abd-a910-ac97cbd0a061 | checkpoint | Rubber Joint
f90311b1-ba4f-5fec-b632-b87d0bcff459 | note | Rubber Joints in Satisfactory condition?
c4ef5e28-032f-5e32-96aa-dea191a1df86 | date | Start Date
3399d266-167e-5a7e-960e-a90cefa99f68 | date | Finish Date
284d6a6b-59fe-5706-b0ab-0ca0e8f7f5ad | checkpoint | Gap Filling
97d086c1-dac2-5af5-8835-2f81a6f7f8bc | note | All the holes have been mortared to satisfactory condition?
2d35c2c4-4f3d-540a-b840-2305de4e50f9 | date | Start Date
9d077d7d-e1de-5a54-b9ca-c5dc9f487873 | date | Finish Date
1e3d31a3-16a4-5503-92f7-d36c6b0d7d2e | checkpoint | Step Irons
6448d217-65bd-5977-b378-0e887266a884 | note | Step Irons Installed in the Pit greater than 1000mm?
1a6d2c1e-2d63-5ae4-aa0c-ccdb11fc4325 | date | Start Date
4334c58c-5249-5bd2-82b0-431bad66f96a | date | Finish Date
e4df1e76-54d1-5b97-b96b-bf3da9d4c209 | checkpoint | Final Inspection
4e42773f-3821-5e50-a586-f0f5f566380c | note | The signature below veriﬁes that this ITP has been completed in accordance with the Fulton Hogan’s Quality system Procedures and veriﬁes lot compliance with speciﬁcations.
6db91f04-ea88-5494-894e-9f5a266a884d | textbox | Print Name:
2d884928-1d04-5d03-b9a2-196391ae2f4d | textbox | Position:
85dc6342-20eb-5e07-af92-556a8c64f6fc | date | Date:
20ae8cc0-7e50-549a-b298-b7d0166643ab | signoff | Sign ITP
d8c5d0b3-b309-4557-be7e-eb7e696b8d14 | checklist | ITP-045 - General Concrete Paving Rev1 | itp | ITP-045 - General Concrete Paving
ee718103-0f4f-4115-8144-930487f652d8 | section | 1 - Preliminary Works
65c28b11-8c8e-4b11-ae75-09180521d32f | checkpoint | 1.1 - Check for correct documentation
a678cf0b-eee3-5ee2-ba1e-2698419ffd56 | note | FREQUENCY: Prior to commencing any activity
47358bec-9698-578b-b6bf-9c5a1a29faa4 | note | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are:
6d64e38c-a22e-55e8-aa72-7a7623804bdb | note | – using the correct and complete set of drawings
dc61fe6c-ce6e-5a56-9988-7d99b813ce4e | note | – all drawings are the latest revision
28e48fbe-703d-574a-b2ec-0872126bc1f0 | note | REFERENCE DOCUMENTS: IFC Drawings
a41eae10-5575-5298-9645-996511f48af3 | note | METHOD: Visual Inspection
d8373706-0733-51f5-812c-2102162f3e95 | note | RECORD: Signed ITP
0efc2203-0b5f-53eb-ab46-905ce5f7ad62 | note | IHP
11a97480-fbec-5a71-aa01-75f72a828b52 | note | RESPONSIBILITY: FH Project Manager
8ec2ed40-c950-5beb-8165-c163be134472 | date | Date Completed:
a16c11bd-94d9-4d2c-8518-603ac09d8372 | checkpoint | 1.2 - Implementation of all measures and controls
73dc78dd-b9f9-5bd2-9c75-227762730a87 | note | FREQUENCY: Prior to commencing any activity
da63006d-c68c-557a-9f4e-8c888a7a0c11 | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: EMP, TMP & SWMS.
956296d5-dd4f-5c52-aa8b-de3deb9875f0 | note | REFERENCE DOCUMENTS: EMP, TMP & SWMS
04f1d6bf-e310-537e-9c2e-e8f00d4f1671 | note | METHOD: Visual Inspection
54b29d5a-fa22-54c2-a491-e30197a0126b | note | RECORD: Signed ITP
0a79697e-c55c-5de7-8d17-64f5662c12a4 | note | IHP
a9d4c4b7-03b5-5241-8bc4-fc75e86d44e9 | note | RESPONSIBILITY: FH Project Manager
5da36c95-34e2-5278-80f4-8cbd8f07e0e0 | date | Date Completed:
b55f3b7e-fed5-4682-8a4f-c99eab94b3c3 | section | 2 - Construction Works
8945263f-d853-403b-8259-72ad2c65e046 | checkpoint | 2.1 - Survey Set-Out
7143d719-47c1-5eeb-8aad-76b9d6177d12 | note | FREQUENCY: Prior to commencement of excavation.
3dd9ee5a-6b04-590b-8217-adb47393a6a6 | note | ACCEPTANCE CRITERIA: Area has been set out in accordance with the drawings
fa11f811-fde4-519f-b31d-741af12c6f00 | note | REFERENCE DOCUMENTS: Work Procedure
808235a6-9ad0-591c-ad7c-9cc4c46547f7 | note | METHOD: Verify
8e24cc82-5a5f-51a4-9ec0-121d5ea608d5 | note | RECORD: Signed ITP
ef822d52-52c0-51a7-8268-fb8cb9d3a69f | note | IP
50f12078-7ab4-5f5e-bd16-74cb03252efd | note | RESPONSIBILITY: FH Project Manager
1db20acb-4da9-50c5-9bc5-f9ebe0b70cab | date | Date Completed:
d360dd5f-38ab-4df6-858f-ef63a8895896 | checkpoint | 2.2 - Excavation Permit
bf6a906c-0e98-5bfb-aca3-bd33a8420d25 | note | FREQUENCY: Each Lot
ca4ccb1b-73fc-5b85-8f66-4c7559cd490a | note | ACCEPTANCE CRITERIA: An excavation permit or DBYD must be issued prior to any excavation commencing. Plant and equipment shall be appropriate for the task. Excavation operations shall not disturb areas outside the limit of excavation
dca373db-7b05-5d38-aca6-70b5085cf55f | note | REFERENCE DOCUMENTS: Excavation Permit
2f9bd74f-5d2b-517a-9f16-5cf28b103ae1 | note | METHOD: Verify
37e9bd4b-15cf-5442-9b75-9507835523b0 | note | RECORD: Signed ITP
91dc7219-9477-5202-ba77-232f4f6e69b9 | note | IHP/IP
1aba0382-3c61-5941-b76e-4c1d6c5b3cfc | note | RESPONSIBILITY: FH Project Manager/FH SEQ Adviser
0e120987-8a7a-58e5-ae32-f6aae258e285 | date | Date Completed:
1f9327e9-516c-4294-b51d-9ba3bfa20c0e | checkpoint | 2.3 - Formwork
295d85a9-3915-5068-bfb7-a2af9df94fec | note | FREQUENCY: Each Lot
771c2cbd-2e28-54f6-8aae-8bd4c7a682ad | note | ACCEPTANCE CRITERIA: Formwork shall comply with the requirements of AS 3610
ee8bdbe6-3094-5b19-88a9-964a7d45ecb1 | note | REFERENCE DOCUMENTS: AS 3610
7a60bac8-cc48-519d-88d3-e72b39b9c89f | note | METHOD: Site Inspection
100fbb9f-c059-5f79-b7e8-f65a4658d5f0 | note | RECORD: Signed ITP
41cf2064-9ce4-5a04-bf91-677477147041 | note | IP
fc29822f-f5cf-535d-812f-de5ca5dcfad1 | note | RESPONSIBILITY: FH Project Manager
c10ba11f-71ba-5175-9621-bd15ee6b3812 | date | Date Completed:
e660d5f3-3efc-4702-93fb-f55c5d75570c | checkpoint | 2.4 - Reinforcement
4555017e-aeab-5579-861b-24ea9a8736da | note | FREQUENCY: Each Lot
67abc454-3e80-5124-8264-71057ef307ac | note | ACCEPTANCE CRITERIA: Steel reinforcement shall comply with the requirements of AS/NZS 4671. Minimum cover of 50mm.
9dbf8066-1b28-521e-ac19-e32e0afa52aa | note | REFERENCE DOCUMENTS: AS/NZS 4671
bb951a37-1511-5454-a9af-6ea3165a2063 | note | METHOD: Visual Inspection
fe70f0af-3ba7-5d3c-bb7d-da7590a0cc79 | note | RECORD: Signed ITP
36fec6dc-4671-5e7c-bbb5-2680aa9a18d0 | note | IP
bc377710-27a8-5613-859c-c2a8c4b24cbe | note | RESPONSIBILITY: FH Project Manager
dcaffb91-3dee-5b16-bd3c-7f90aefba176 | date | Date Completed:
da2b1b77-169d-4574-ab09-a3f5d5e8a127 | checkpoint | 2.5 - Temporary Drainage Provisions
7a80d2b0-3b43-56c1-85ab-9e32f039607a | note | FREQUENCY: Prior to commencing
63f96b53-70c3-54ae-9dfc-40a497c9e157 | note | ACCEPTANCE CRITERIA: If obstructing waterways, culverts or channels, temporary diversion of discharge of drainage and stormwater to be in place. Obtain written approval from relevant waterway authority.
c3a72674-8de6-52b7-ab74-631d159f7376 | note | REFERENCE DOCUMENTS: VcRoads Std Specs 703.15
b431ddb8-8a11-57ec-b35d-4c351a70637d | note | METHOD: Visual Inspection
451eea4a-d34c-53fc-9526-c54b4fca6722 | note | RECORD: Signed ITP
96b6202c-4cf3-55a7-876f-50f52955919a | note | IHP
7b9d281c-46f5-507e-beb9-36c965d0b68b | note | RESPONSIBILITY: FH Project Manager
05f9598b-d35e-5726-a476-a89b72d1f576 | date | Date Completed:
fd81ec31-49f8-4212-994e-42c9e11f0eb0 | checkpoint | 2.6 - Bedding
f8fdcaab-c661-5d4b-8fc6-847b7ccc0be2 | note | FREQUENCY: Each lot as required
f6250143-c792-5a8f-be0c-d6bf3477ad5e | note | ACCEPTANCE CRITERIA: Crushed rock bedding material as per drawings
b29243b9-b444-5b77-902e-2ffed39af517 | note | ○ Bedding trimmed, moistened, and compacted as necessary
70e200d5-0d2b-5b4e-aded-7ed05ff0b5b8 | note | ○ Bedding compacted thickness: Footpaths and other surfacing ≥ 50mm
8f2fe147-9e17-59cd-a828-5e93f44ac856 | note | REFERENCE DOCUMENTS: VcRoads Std Specs 703.18 IFC Drawings
42840c7b-f45b-5e15-962d-a120738d692c | note | METHOD: Site Inspection/ Document Review
a0b4b235-9ac9-5e05-ba77-0e0eae64048c | note | RECORD: Signed ITP
d9518778-070e-5f25-929c-0527b29d66a8 | note | IHP/AP
7f45acf4-66cc-5f39-b47c-673ab0ae844f | note | RESPONSIBILITY: FH Project Manager/RRV Superintendent
ecdd2fd6-8b4c-544d-89c1-f26c3d57a9d7 | date | Date Completed:
ce1c4f73-eb1d-4c02-bb48-00a4e27fdff8 | checkpoint | 2.7 - Concrete Placement
1c68cf3a-4740-5ee3-aa79-ee123be169a8 | note | FREQUENCY: Each lot as required
7f706949-1a89-573a-b670-9049f8006325 | note | ACCEPTANCE CRITERIA: Concrete strength as per drawing speciﬁcation
0ebaf9ef-7b06-58a1-bec4-a57d08eaf184 | note | ○ Comply with requirements of AS1379
9f67beb7-0567-50ab-b93c-f7bf822dfb81 | note | ○ Aggregates to comply with Table 703.051
b9d29c8c-cfeb-55d2-a0f1-34c52ce8f728 | note | ○ Extrusion machines cement content ≥ 320kg/m3
75be63ff-0ab0-53fa-8d55-6369b938a574 | note | ○ Surface pitting < 5mm diameter
c6861856-9520-5926-b2f0-0392b52335f1 | note | ○ Concrete to be satisfactorily compacted. Proﬁle transitions between 10-20mm per metre.
fa6f36fb-83f9-540d-90b4-651595d1d7c7 | note | REFERENCE DOCUMENTS: VicRoads Std Specs 703.04(b), VicRoads Std Specs 703.20, VicRoads Std Specs 703.21 IFC Drawings AS 1379
8312bdd7-6690-5c3a-a2e0-e1000227e84f | note | METHOD: Visual Inspection
4eddb95c-5ab5-5fce-ab07-5d33103e59a6 | note | RECORD: Signed ITP & Test Reports
f35b47b3-395a-5c56-a6cd-537298fdf2a1 | note | IHP/AP/TP
f3dd9770-ebe8-52d9-b84a-de63cef423e4 | note | RESPONSIBILITY: FH Project Manager/RRV Superintendent/External testing Company representat ive
f5c477af-e372-5b4d-89c0-116cb8cb1dad | date | Date Completed:
2073f5ee-3ad7-41f9-966e-6bb3b0e8aa4d | checkpoint | 2.8 - Finish Surfaces
6a2c015c-865b-5735-95ae-fde7814c9bbb | note | FREQUENCY: Each lot as required
029ce11f-2172-5f68-b475-078923ea3231 | note | ACCEPTANCE CRITERIA: Footpaths and other Surfacing: Wooden ﬂoat ﬁnish
ded89165-d9b2-58fc-8eff-c4ca576cc40b | note | REFERENCE DOCUMENTS: VcRoads Std Specs 703.22
e22b5289-68ed-5f5e-bded-285c4367ad90 | note | METHOD: Visual Inspection
7b0494e4-d68b-58e2-9266-d327246da3d6 | note | RECORD: Signed ITP & Test Reports
44c318db-ddeb-59ef-b629-a142d56e96e3 | note | IHP/AP
5a31a44a-5147-59ad-bc85-6ba2586dfa81 | note | RESPONSIBILITY: FH Project Manager/RRV Superintendent
6310e9a9-de3d-5bcd-a206-eed60fb2340f | date | Date Completed:
e76df3a4-290e-40cc-a763-9b0a1b7cb098 | checkpoint | 2.9 - Tolerances
9a93f120-d4e1-5593-a741-e8aae09268ba | note | FREQUENCY: Each lot as required
d1475efb-ff0f-5afc-9db4-40e1fc52bb73 | note | ACCEPTANCE CRITERIA: Match existing surfaces ± 5mm
c3d6dcea-f4c4-52e9-b99d-c429f4a1234b | note | Section dimensions:
8a0f9332-07a4-5eeb-b4ba-819847adb333 | note | ○ Within 5mm and 15mm for width; and
e6ff4f09-0479-565b-a2d0-2e08d7d07323 | note | ○ Within ±3mm for dimensions less than 25mm.
3f4d58cd-2d24-587e-85ed-2de6546124ee | note | Concrete footpath:
cc77f7a4-6b60-50b2-ac7c-3fc5e204dd93 | note | ○ 150mm thick
921d43b1-cb50-52fa-9a6a-0b162f0e0f4a | note | ○ SL72 reinforcement
34ebcac8-eae6-5f3b-b299-d16ba8bd5a37 | note | Concrete Surfacing:
143705d7-1780-591e-bbaa-7006a68c765c | note | ○ Type 1 100mm
15a0cc5f-6dd2-5259-8497-c562df302457 | note | ○ Type 2 150mm
222386a7-0786-5ece-899d-8c3ba011f4f4 | note | REFERENCE DOCUMENTS: VicRoads Std Specs 703.13 IFC Drawings
4b265422-316b-546c-b016-e3fb374e6835 | note | METHOD: Visual Inspection
3f16f303-fe92-5636-80db-6f0f47ba5214 | note | RECORD: Signed ITP
044f889f-5161-5edd-91a8-2843da374532 | note | IHP
601979c2-322f-5c62-ad0b-eaa14aae8eae | note | RESPONSIBILITY: FH Project Manager
94be7381-98be-50f4-9de9-6be188f9b923 | date | Date Completed:
9a68e8c7-1760-46a9-beab-bb69f6b979b1 | checkpoint | 2.10 - Joints
739f5244-2600-5330-b4e3-f50218f1cf28 | note | FREQUENCY: Each lot as required
9a54c6d3-35f4-5da4-8c78-18be884f63b9 | note | ACCEPTANCE CRITERIA: Footpaths and other surfacing:
3ec372bb-1b75-5ab8-a83d-2920df7dbdae | note | ○ Expansion joints at 12.5m regular intervals
c716083c-2261-584d-9511-b5f95c51184f | note | ○ Control joints at 2.5m regular intervals
f2cb709b-314d-5eb9-b658-6cf4458c350b | note | ○ 20mm deep and 5mm wide
dca62a8c-df60-575f-b597-de18c6dab629 | note | ○ Prevent bonding between edging and surfacing. Either paint back of edging with bitumen or use a strip of bituminous felt material.
bf1330bf-003a-5571-88ad-0a34a4c44291 | note | REFERENCE DOCUMENTS: VicRoads Std Specs 703.23
2a3fc51d-81a8-5a7f-9e39-fde0dea01981 | note | METHOD: Visual Inspection
729d21ac-d19b-51d4-869d-7a2f88041b72 | note | RECORD: Signed ITP
46d49ae4-9488-5882-8685-bc37aa268313 | note | IHP
832d053e-8cb9-5ad6-bca5-b7c7e4ed089e | note | RESPONSIBILITY: FH Project Manager
ab414be7-383f-578c-a19d-c8e4ed80518a | date | Date Completed:
7b71b39e-8813-4a9a-a717-b1c86f054fc3 | checkpoint | 2.11 - Backﬁlling
1b3ba207-95ea-5b32-bdc8-9ee7f77015db | note | FREQUENCY: Each lot as required
1c0963be-9f7d-5a91-a98a-30833735d197 | note | ACCEPTANCE CRITERIA: Topsoil compacted in layers < 150mm
8a1c5021-85cd-5d6d-bc31-c6b6d22df184 | note | ○ Width ≥ 300mm behind edging to top of edging
4003e6f2-a6d7-576d-ab45-610f6ce3b96a | note | ○ Topsoil placed after 3 days of concrete placement
4b98ac1b-900f-5b57-bb75-4bcca0d5c4e7 | note | REFERENCE DOCUMENTS: VicRoads Std Specs 703.26
03a623f8-6158-54fc-83aa-b407cb5ebf43 | note | METHOD: Visual Inspection
71493979-bcf5-5d26-a27f-9b65f1dbe69a | note | RECORD: Signed ITP
05bd00b5-5f8a-55ae-982e-795e255290af | note | IHP
36647594-ba02-5d5c-befe-65585d23885d | note | RESPONSIBILITY: FH Project Manager
aabf1989-3179-5dbc-a1f9-66d1f87bb6d8 | date | Date Completed:
ebb46c88-1159-4772-93f1-21f11c679723 | checkpoint | Final Inspection
707109ac-fa76-597d-80ad-513a946aa019 | note | The signature below veriﬁes that this ITP has been completed in accordance with the Fulton Hogan’s Quality system Procedures and veriﬁes lot compliance with speciﬁcations.
09db49a6-4811-55a0-a8fd-a15ef120e826 | textbox | Print Name:
644fb0d4-793a-599a-bbac-eabc7f8feaa3 | textbox | Position:
b6180b90-47f1-50fe-87b1-7d62645e6fcd | date | Date:
ea4d1aad-b2a7-4a2d-b185-e8ae23dc8e39 | signoff | Sign ITP
99e3f24f-a60d-451b-8cfb-fb612a715198 | checklist | Proof Roll |  | Proof Roll
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
e4b19a51-35ba-4f79-b684-1067444740d8 | checkpoint | Proof Roll
fb379d65-bb79-5f43-82fb-94ee8432e1f5 | note | FREQUENCY - Each Lot
1f80bc96-c1da-540e-85c4-7d53c9b791cf | note | ACCEPTANCE CRITERIA - Stabilised layers shall pass test rolling in accordance with Section 173, prior to acceptance of the layer.
16162740-7f58-51b5-aaad-4be408deb23d | note | REFERENCE DOCUMENTS - VR 307.10
3f723108-0521-5ad2-874b-96b2a53a599f | note | INSPECTION / TEST METHOD - Visual
61da5592-7413-56f7-94a3-05abaa610fdf | note | RECORD OF CONFORMITY - Visual
4209055a-2aaa-5f3a-9c1f-85d07f51c923 | note | HP, WP
c602e713-940e-555e-9b96-35bfe0617239 | note | RESPONSIBILITY - Project Engineer / DTP
4f8230f2-7144-5bb4-aa0c-bc486b1f9dc0 | date | Date Completed:
4c8be00a-c372-4015-8ffe-5567fbf235eb | signoff | AUTHORITY HOLDPOINT