## Testing Summary
|  | Contractor : | [15 empty] | Project Name :
MRPV Team Binder Lot No. | Contractor's system Lot No. | Construction Element | Activity | Designed Material | Used Material | Layer | Lot Description | Location | Zone | Stage | Test Request No. | Name of Test | Test Request Date | Test Report Issue Date | Turn around Time (days) | Report No. | Responsible Engineer | Chainage From | Chainage To | Length (m) | Width (m) | Lot Size (m2) | Thickness (mm) | Material Source | Scale of Road | Specified Requirement for the test | Characteristic Density Ratio (CDR) | Mean Density Ratio (MDR) | Density Decay Correction Factor | Characteristic Moisture Ratio (CMR) | Mean Moisture Ratio (MMR) | Assigned CBR | Assigned Swell | Single CBR | Single Swell | Plasticity Index (PI) | Liquid Limit (LL) | Weighted Plasticity Index (WPI) | Identification of Silt PI Vs LL | Permeability | Sieve Analysis/Grading (Passing) | [10 empty] | Emerson No. | Co-efficient of uniformity | Effective Internal Friction Angle | Dryback Test |  | Ball Embedment | Unconfined Compressive Strength (UCS) | Any other project specific test | Pass / Fail | Failed Test Name | NCR No | Comments
[29 empty] | Cement Stab. Only | [11 empty] | 75mm | 53mm | 37.5mm | 26.5mm | 19mm | 13.2mm | 9.5mm | 4.75mm | 2.36mm | 0.425mm | 0.075mm |  |  |  | Mean Moisture Ratio | High Individual Moisture Ratio
1140-XXX-CIL-0001 | XXX-YYY-ZZZ-0001 | Earthwork | Type A Capping | Type A | Class 4 | Subgrade layer 1 | Type A Capping for Pavement Type BG-2 | Monash Freeway | Freeway South | Freeway Inbound East | TR-0001 | Density | 2024-12-30 | 2025-01-04 | 5 | R-123456 | XXX YYY | 1000 | 1200 | 200 | 15 | 3000 | 200 | Fulton Hogan | A | 99% | 97% | [32 empty] | Fail | Compaction | 1140-XXX-NCR-0001 | Rework required
Information in Green/Blue highlighted sections are to be filled in by the contractor and the information in the yellow highlighted sections are to be filled in by the tEsting Sub-contractor.
Menu
Build Report