## Sheet1
ConQA Team Notes:
Document Title: |  | ITP-275-RAIL-CPD-Aluminothermic Welding and Stressing
ITP Description: |  | Aluminothermic Welding and Stressing
Project: |  | Calder Park Drive
Discipline (e.g. CIV/STR/RAIL: |  | RAIL
Revision Number: |  | 0
Revision Date: |  | 2025-05-08
ITP created by: |  | Jake Argentaro
ITP approved for use by: |  | Pradeep Talasila
Special Notes to ConQA Team : |  | ITP to be used at Calder Park Drive Project Only
Inspection & Test Plan - Aluminothermic Welding and Stressing
|  |  | Document Title: ITP-275-RAIL-CPD-Aluminothermic Welding and Stressing | [5 empty] | Revision: | 0
[9 empty] | Date: | 2025-05-08
Legend: HP: Hold Point, HP* Internal Hold Point, WP: Witness Point, IP: Inspection Point, SP: Surveillance Point
Item | Task/Activity Description | Reference | Acceptance Criteria | Inspection / Test |  |  | Responsibility | Verifying Documents | Date Completed | Sign-off
|  |  |  | Method | Frequency | Category
1 | Referenced Documentation
1.1 | Drawing Pack - Rail Track and Civil | MRP-DPK-080-00-CPW-0063-0 Rail Track & Civil Drawings - Calder Park Drive | N/A | N/A | N/A | N/A | N/A | N/A | NA | N/A
1.2 | Railway Track Materials – Part 1: Steel Rails | AS 1085.1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
1.3 | Welding Rail Steels | AS 1085.2 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
1.4 | Flash Butt Welding Specification | A1340 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
1.5 | Hot Works Procedure | A1606 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
1.6 | Welded Track Management Manual Chapter 7 - Requirements For Welding Track Procedure | A4597 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
1.7 | Welded Track Management Chapter 9 Stress Control for Continuous Welded Rail Procedure | A4589 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
1.8 | Welded Track Management Metro Track - Chapter 10 - Closure Rails Procedure | A4598 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
1.9 | PTDT Form B - Track Certifier Booking Form | A4263 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
1.10 | Welded Track Management - Chapter 13 - Monitoring of Welded Track Procedure | A4588 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
1.11 | Non-Destructive Hand Testing Of Rail - Track Procedure | A4550 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
1.12 | Track Construction - ITP | ITP-XXX-RAIL-CPD-Track Construction | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
2 | Preliminaries - Materials
2.1 | Supply of Weld Kits | AS1085.20 Railway Track Material Part 1: Steel Rails A4588 Welded Track Management - Chapter 13 - Monitoring of Welded Track Procedure | Weld kits supplied are within expiry period and conform to the requirements of applicable standards. Enter: Teambinder Material Approval number | Visual Measure Document Review | Upon Delivery | HP | PE/Nominated authority | Material approval in TeamBinder This ITP Signed Off Attach: Delivery Dockets/Site Photos
3 | Preliminaries - Procedures & Documentation
3.1 | Primary Documentations | A4263 PTDT Form B - Track Certifier Booking Form A1606 Hot Works Procedure | MRP-DPK-091-00-CPW-0063 Rail Track & Civil Drawings - Progress Street | Document review and approval | Prior to works commencing | HP | SE/PE | This ITP Signed Off Attach: Approved PTDT
3.2 | Pre-Commencement of Work | ITP, Quality Checklist, SWMS, | All approved by relevant representative. | Document review and approval | Once (Prior to Works) | HP | SE/PE | This ITP Signed Off Attach: Approved templates
3.3 | Welding Procedures & Quality Documentation | AS1085.20 Railway Track Material Part 1: Steel Rails A4588 Welded Track Management - Chapter 13 - Monitoring of Welded Track Procedure | WPS (Welding Procedure Specifications), WPQR (Welding Procedure Qualification Records), WQR (Welder Qualification Register) | Document review and approval | Once (Prior to Works) | HP | SE/PE | This ITP Signed Off
4 | Pre-Construction Activities
4.1 | Approval of IFC drawings | MRP-DPK-080-00-CPW-0063-0 Rail Track & Civil Drawings - Calder Park Drive | Approved IFC Drawings | Document review and approval | Prior to works commencing | HP | SE/PE | This ITP Signed Off
5 | Construction Activities
5.1 | Aluminothermic Welding | AS1085.20 Railway Track Material Part 1: Steel Rails | Verify Aluminothermic welding carried out in accordance with AS1085.20 | Visual Inspection | As Task Progresses | IP | SE/PE Track Supervisor Welder | This ITP Signed Off Attach: Site Photos
5.2 | Alignment of Welds | AS1085.20 Railway Track Material Part 1: Steel Rails L2-TRK-PRO-014 Welded Track Management Manual Chapter 11 – Rail Welding Process Section 4.9 | Alignment inspection shall be carried out on each weld and record results. Horizontal Alignment ± 0.5mm Vertical Alignment + 0.5mm, - 0.0mm | Visual Inspection Test & Measure | Each Weld | IP | SE/PE Track Supervisor Welder | This ITP Signed Off Attach: Inspection Records & site photos
5.3 | Welder's Identification Marks | AS1085.20 Railway Track Material Part 1: Steel Rails A1340 Flash Butt Welding Specification Section 4.3.5 | Stamp ID on the field side of the rail head adjacent to the weld. | Visual Inspection | Each Weld | IP | SE/PE Track Supervisor Welder | This ITP Signed Off Attach: Site Photos
5.4 | Stressing Track Lengths | AS1085.20 Railway Track Material Part 1: Steel Rails A4200 Metro Track - Management Chapter 11 Welding Process Procedure Section 5 A4598 Welded Track Management Metro Track - Chapter 10 - Closure Rails Procedure Table 7. | Ensure track lengths area stressing accordance with Metro Track - Management Chapter 11 Welding Process Procedure (A4200), Minimum Closure Length taken as 13. 7 meters if not Detailed in Welded Track Management Metro Track - Chapter 10 - Closure Rails Procedure (A4598) table 7. | Survey and Visual Inspection | As Task Progresses | IP | SE/PE Track Supervisor Track Surveyor | This ITP Signed Off Attach: Inspection Records & site photos
5.5 | Stress Free Temperature | A4589 Welded Track Management Chapter 9 Stress Control for Continuous Welded Rail Procedure Section 5.1.2 | The design SFT is 38°C and all stressing is to be carried out to this design SFT. | Test and Measure | Each Weld | IP | SE/PE Track Supervisor Welder | This ITP Signed Off Attach: Inspection Records & site photos
5.6 | Weld Ultrasonic Testing | A4588 Welded Track Management - Chapter 13 - Monitoring of Welded Track Procedure AS 1085.11 Permanent Way Material – Head-hardened Rail, Figure C2. A4589 Welded Track Management Chapter 9 Stress Control for Continuous Welded Rail Procedure Section 6.20 | Ultrasonic testing to be carried out within 14 days and in accordance with A4588 Welded Track Management - Chapter 13 - Monitoring of Welded Track Procedure The cross section of the area of the head and web shall be completely scanned; • The foot area shall be scanned in accordance with AS 1085.11 Permanent Way Material – Head-hardened Rail, Figure C2. • Welds shall be scanned to both directions. | Inspection / Test | Each Weld within 14 days | IP | SE/PE Track Supervisor | This ITP Signed Off Attach: Ultrasonic Weld Test Results
6 | Post-Construction Activities
6.1 | Rail Stressing Records | A4589 Welded Track Management Chapter 9 Stress Control for Continuous Welded Rail Procedure Section 6.21 | Complete Stressing Recorded documentation | Measure and Document Review | Each Weld | IP | SE/PE Track Supervisor | This ITP Signed Off Attach: Rail Stressing Documentation
6.2 | Track Certification | MTMF020000-1 – Track Form A T MTMF020000-2 – Track Form B A4549: MAINTAINING TRACK INTEGRITY PROCEDURE | - Track Geometry Conformance Certificate - Track System and Component | Visual Measure Document Review | Once (upon completion of occupation works) | HP | Nominated Authority (MTM Infrastructure Track Certifier) Project Cert III Rail Infrastructure | This ITP Signed Off Attach: Relevant Conformance Certs as per acceptance criteria
6.3 | As-Built Drawings | As-Built Drawing Management Procedure (A8197) | IFC drawings (including cables, patches and labels) are marked up with redlines and supplied the Project and MTM. | Document review and approval | Once | HP | SE/PE | This ITP Signed Off Attach: Redline mark-up drawings
6.4 | Non-conformance Report (NCR) Closure | MTM Quality Management Plan | Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed. | Document Review | Once, prior to closure of this lot / element / Work area | HP | SE/PE | This ITP Signed Off
Final Inspection
On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
Print Name: Position: Signature: Date: / /