## Sheet1
ConQA Team Notes:
Document Title: |  | ITP-279-RAIL-CPD-Track Formation - Structural Fill
ITP Description: |  | Track Formation - Structural Fill
Project |  | Calder Park Drive
Discipline (e.g. CIV/STR/RAIL: |  | RAIL
Revision Number: |  | 0
Revision Date: |  | 2025-05-08
ITP created by: |  | Jake Argentaro
ITP approved for use by: |  | Pradeep Talasila
Special Notes to ConQA Team : |  | ITP to be used at Calder Park Drive Project Only
Inspection & Test Plan - Track Formation - Structural Fill
|  |  | Document Title: ITP-279-RAIL-CPD-Track Formation - Structural Fill | [5 empty] | Revision: | 0
[9 empty] | Date: | 2025-05-08
Legend: HP: Hold Point, HP* Internal Hold Point, WP: Witness Point, IP: Inspection Point, SP: Surveillance Point
Item | Task/Activity Description | Reference | Acceptance Criteria | Inspection / Test |  |  | Responsibility | Verifying Documents | Date Completed | Sign-off
|  |  |  | Method | Frequency | Category
1 | Referenced Documentation
1.1 | Drawing Pack - Rail Track and Civil | MRP-DPK-080-00-CPW-0063-0 Rail Track & Civil Drawings - Calder Park Drive | N/A | N/A | N/A | N/A | N/A | N/A | NA | N/A
1.2 | Metro Engineering Specifications - Earthworks & Formation Specification | L1-CHE-SPE-178 (VERSION 3) | N/A | N/A | N/A | N/A | N/A | N/A | NA | N/A
1.3 | Metro Engineering Specifications - Earthworks & Formation Standard | L1-CHE-STD-029 (VERSION 4) | N/A | N/A | N/A | N/A | N/A | N/A | NA | N/A
1.4 | Australian Standard - Methods of testing soils for engineering purposes | AS 1289 | N/A | N/A | N/A | N/A | N/A | N/A | NA | N/A
2 | Preliminaries - Materials
2.1 | Structural Fill Material Conformance (1 of 2) | L1-CHE-SPE-178 - Clause 5.11.2.1. Table 4 | Structural fill materias shall have the following properties: • % passing 53.0mm sieve 80-100% • % passing 2.36mm sieve 15-100% • % passing 0.425mm sieve 0-70% • % passing0.075mm sieve 0-30% Enter: Teambinder Material Approval number | Document Review | Once, for each material type - prior to works commencement | HP | PE/Nominated authority | Material approval in TeamBinder This ITP Signed Off
2.2 | Structural Fill Material Conformance (2 of 2) | L1-CHE-SPE-178 - Clause 5.11.4.1. Table 5 AS 1289 | Structural fill must comply with the following requirements: • Soaked CBR 8% min compacted to 100% standard dry density • Liquid Limit 40% Max. • Plasticity Index 20% Max. • Dry Density 1.8t/m³ Min. Refer to AS 1289 for Tests Enter: Teambinder Material Approval number | Document Review | Once, for each material type - prior to works commencement | HP | PE/Nominated authority | Material approval in TeamBinder This ITP Signed Off
3 | Preliminaries - Procedures & Documentation
3.1 | Pre-Commencement of Fill Works | L1-CHE-SPE-178 - Clause 5.12.5. Table 7 AS1289 Tests | The Contractor shall not commence placing any fill on the prepared areas until the area has been reviewed by the Responsible Engineer. | Visual Inspection | Prior to commencement of fill works | HP | SE/PE | This ITP Signed Off MTM representative signoff Attach: Site Photos
4 | Pre-Construction Activities
4.1 | Approval of IFC drawings | MRP-DPK-080-00-CPW-0063-0 Rail Track & Civil Drawings - Calder Park Drive | Approved IFC Drawings | Document review and approval | Prior to works commencing | HP | SE/PE | This ITP Signed Off
4.2 | Survey Set Out | IFC Drawings | Set out pegs in place and clearly mark out limits of works. | Visual Inspection | Prior to commencement of fill works | HP* | SE/PE/SPE | This ITP Signed Off
5 | Construction Activities
5.1 | Structural Fill Preparation and Installation - (1 of 3) | L1-CHE-SPE-178 - Clause 5.11.3. L1-CHE-STD-029 - Clause 8.1. | Where Rail Subgrade CBR < 3%: - Required minimum depth of structural fill is 1000mm - 8% min CBR, Compacted to 100% (Standard Compaction Test) Where a layers to be constructed in fill it shall be constructed in uniform thickness not exceeding 200mm lose. 3 tests per 1000m³ 3 tests if 500-1000m³ Atleast 2 tests if < 500m³ | Standard Compaction Test | Each Lot | HP | SE/PE | This ITP Signed Off Attach: Compaction Test Report
5.2 | Structural Fill Preparation and Installation - (2 of 3) | L1-CHE-SPE-178 - Clause 5.11.3. L1-CHE-STD-029 - Clause 8.1. | Where Rail Subgrade 3% < CBR < 8%: - Required minimum depth of structural fill is 500mm - 8% min CBR, Compacted to 100% (Standard Compaction Test) Where a layers to be constructed in fill it shall be constructed in uniform thickness not exceeding 200mm lose. 3 tests per 1000m³ 3 tests if 500-1000m³ Atleast 2 tests if < 500m³ | Standard Compaction Test | Each Lot | HP | SE/ | This ITP Signed Off Attach: Compaction Test Report
5.3 | Structural Fill Preparation and Installation - (3 of 3) | L1-CHE-SPE-178 - Clause 5.11.3. L1-CHE-STD-029 - Clause 8.1. | Where Rail Subgrade CBR > 8%: - Structural fill can directly be placed onto subgrade and compacted to 100% - 8% min CBR, Compacted to 100% (Standard Compaction Test) Where a layers to be constructed in fill it shall be constructed in uniform thickness not exceeding 200mm lose. 3 tests per 1000m³ 3 tests if 500-1000m³ Atleast 2 tests if < 500m³ | Standard Compaction Test | Each Lot | HP | SE | This ITP Signed Off Attach: Compaction Test Report
5.4 | Proof rolling | L1-CHE-SPE-178 - Clause 4.6. | Proof roll as per L1-CHE-SPE-178 - Clause 4.6. | Proof roll | Each Lot | HP | SE/Nominated Authority | This ITP Signed Off MTM representative Signoff
6 | Post -Construction Activities
6.1 | Structural Fill Finishing and Tolerances - For track constructed on embankment / Survey Conformance | L1-CHE-SPE-178 - Clause 5.11.6. | Structural fill shall be within +0 to -35mm of approved design surface level Structural fill shall be within +0 to +50mm of 3m straightedge laid on final structural surface parallel and perpendicular to centreline | Document Review | Each Lot | IP | SE/Surveyor | This ITP Signed Off Attach: Survey Conformance Report
6.2 | Non-conformance Report (NCR) Closure | MRPA Quality Management Plan | Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed. | Document Review | Once, prior to closure of this lot / element / Work area | HP* | SE/PE/SPE | This ITP Signed Off
Final Inspection
On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
Print Name: Position: Signature: Date: / /