## Sheet1
| Link in at intersection of Layard and Waihopai Street (1) | W | Manifold bolts to be torqued to manufacture's specification, to be checked and witnessed by the Site representative before backfilling. | PE to DI connection to be done as per the detail H in sheet 16 of the drawing | Before backfilling | Inspection | Photos |  | Site Engineer | - Link in at intersection of Layard and Waihopai Street (1) | ACTION (W, M, H) - W | Conformance Criteria (What's Required) - Manifold bolts to be torqued to manufacture's specification, to be checked and witnessed by the Site representative before backfilling. | Detail - PE to DI connection to be done as per the detail H in sheet 16 of the drawing | Frequency - Before backfilling | Inspection / Test Method - Inspection | Verification Records - Photos | Standard - | Signatory - Site Engineer | - Link in at intersection of Layard and Waihopai Street (1)
| Link in at intersection of Layard and Waihopai Street (2) | W | Thrust protection to be constructed (x2) | As per detail H in sheet 16 and typical details as per sheet 18 | Before backfilling | Inspection | Photos |  | Site Engineer | - Link in at intersection of Layard and Waihopai Street (2) | ACTION (W, M, H) - W | Conformance Criteria (What's Required) - Thrust protection to be constructed (x2) | Detail - As per detail H in sheet 16 and typical details as per sheet 18 | Frequency - Before backfilling | Inspection / Test Method - Inspection | Verification Records - Photos | Standard - | Signatory - Site Engineer | ACTION (W, M, H) - W
| Removal of existing teeand bends and reinstated with straight through pipe and associated bends/thrust protection at intersection of Layard and Waihopai Streets | W | Pipe reinstated through old line and thrust protected | As per detail L in sheet 16 and typical details sheet 18 | per connection | Inspection | Photos | AS/NZS 4130 | Site Engineer | - Removal of existing teeand bends and reinstated with straight through pipe and associated bends/thrust protection at intersection of Layard and Waihopai Streets | ACTION (W, M, H) - W | Conformance Criteria (What's Required) - Pipe reinstated through old line and thrust protected | Detail - As per detail L in sheet 16 and typical details sheet 18 | Frequency - per connection | Inspection / Test Method - Inspection | Verification Records - Photos | Standard - AS/NZS 4130 | Signatory - Site Engineer | Conformance Criteria (What's Required) - Manifold bolts to be torqued to manufacture's specification, to be checked and witnessed by the Site representative before backfilling.
D5.4.2 | Isolation Valve WAIHOPAI-LAYARD CH15 (1) | W | Spindle height to be max 600mm from surface | The valve should be installed in accordance with the standard drawing details in sheet 17 fig.W4 CHAR(AMP) W9 | Per each valve | Inspection | Photos |  | Site Engineer | D5.4.2 - Isolation Valve WAIHOPAI-LAYARD CH15 (1) | ACTION (W, M, H) - W | Conformance Criteria (What's Required) - Spindle height to be max 600mm from surface | Detail - The valve should be installed in accordance with the standard drawing details in sheet 17 fig.W4 CHAR(AMP) W9 | Frequency - Per each valve | Inspection / Test Method - Inspection | Verification Records - Photos | Standard - | Signatory - Site Engineer | Detail - PE to DI connection to be done as per the detail H in sheet 16 of the drawing
D5.4.2 | Isolation Valve WAIHOPAI-LAYARD CH15 (2) | W | Thrust wall installed | Thrust wall constructed as per fig.W9 of page 17 of the drawings | Per each valve | Inspection | Photos |  | Site Engineer | D5.4.2 - Isolation Valve WAIHOPAI-LAYARD CH15 (2) | ACTION (W, M, H) - W | Conformance Criteria (What's Required) - Thrust wall installed | Detail - Thrust wall constructed as per fig.W9 of page 17 of the drawings | Frequency - Per each valve | Inspection / Test Method - Inspection | Verification Records - Photos | Standard - | Signatory - Site Engineer | Frequency - Before backfilling
D5.4.2 | Isolation Valve WAIHOPAI-LAYARD CH15 (3) | W | Surface box finish | cast iron valve box to be flush with the finished surface level. | Per each valve | Inspection | Photos |  | Site Engineer | D5.4.2 - Isolation Valve WAIHOPAI-LAYARD CH15 (3) | ACTION (W, M, H) - W | Conformance Criteria (What's Required) - Surface box finish | Detail - cast iron valve box to be flush with the finished surface level. | Frequency - Per each valve | Inspection / Test Method - Inspection | Verification Records - Photos | Standard - | Signatory - Site Engineer | Inspection / Test Method - Inspection
D8.3 D8.4 | Lateral connection to house no#90 Layard Street | W | The min depth of the connection 700mm in the road and 300mm to 375mm below the GL at the boundary to the top of the toby, to be checked and witnessed by site rep. | As per fig.W20 of sheet 17 and specifications in D8.3 and D8.4 | Per each connection | Inspection | Photos | AS/NZS 4129 | Site Engineer | D8.3 D8.4 - Lateral connection to house no#90 Layard Street | ACTION (W, M, H) - W | Conformance Criteria (What's Required) - The min depth of the connection 700mm in the road and 300mm to 375mm below the GL at the boundary to the top of the toby, to be checked and witnessed by site rep. | Detail - As per fig.W20 of sheet 17 and specifications in D8.3 and D8.4 | Frequency - Per each connection | Inspection / Test Method - Inspection | Verification Records - Photos | Standard - AS/NZS 4129 | Signatory - Site Engineer | Verification Records - Photos
D8.3 D8.4 | Lateral connection to house no#92 Layard Street | W | The min depth of the connection 700mm in the road and 300mm to 375mm below the GL at the boundary to the top of the toby, to be checked and witnessed by site rep. | As per fig.W20 of sheet 17 and specifications in D8.3 and D8.4 | Per each connection | Inspection | Photos | AS/NZS 4129 | Site Engineer | D8.3 D8.4 - Lateral connection to house no#92 Layard Street | ACTION (W, M, H) - W | Conformance Criteria (What's Required) - The min depth of the connection 700mm in the road and 300mm to 375mm below the GL at the boundary to the top of the toby, to be checked and witnessed by site rep. | Detail - As per fig.W20 of sheet 17 and specifications in D8.3 and D8.4 | Frequency - Per each connection | Inspection / Test Method - Inspection | Verification Records - Photos | Standard - AS/NZS 4129 | Signatory - Site Engineer | Standard -
D8.3 D8.4 | Lateral connection to house no#4 Waihopai Street | W | The min depth of the connection 700mm in the road and 300mm to 375mm below the GL at the boundary to the top of the toby, to be checked and witnessed by site rep. | As per fig.W20 of sheet 17 and specifications in D8.3 and D8.4 | Per each connection | Inspection | Photos | AS/NZS 4129 | Site Engineer | D8.3 D8.4 - Lateral connection to house no#4 Waihopai Street | ACTION (W, M, H) - W | Conformance Criteria (What's Required) - The min depth of the connection 700mm in the road and 300mm to 375mm below the GL at the boundary to the top of the toby, to be checked and witnessed by site rep. | Detail - As per fig.W20 of sheet 17 and specifications in D8.3 and D8.4 | Frequency - Per each connection | Inspection / Test Method - Inspection | Verification Records - Photos | Standard - AS/NZS 4129 | Signatory - Site Engineer | Signatory - Site Engineer
D8.3 D8.4 | Lateral connection to house no#7 Waihopai Street | W | The min depth of the connection 700mm in the road and 300mm to 375mm below the GL at the boundary to the top of the toby, to be checked and witnessed by site rep. | As per fig.W20 of sheet 17 and specifications in D8.3 and D8.4 | Per each connection | Inspection | Photos | AS/NZS 4129 | Site Engineer | D8.3 D8.4 - Lateral connection to house no#7 Waihopai Street | ACTION (W, M, H) - W | Conformance Criteria (What's Required) - The min depth of the connection 700mm in the road and 300mm to 375mm below the GL at the boundary to the top of the toby, to be checked and witnessed by site rep. | Detail - As per fig.W20 of sheet 17 and specifications in D8.3 and D8.4 | Frequency - Per each connection | Inspection / Test Method - Inspection | Verification Records - Photos | Standard - AS/NZS 4129 | Signatory - Site Engineer | - Link in at intersection of Layard and Waihopai Street (2)
D8.3 D8.4 | Lateral connection to house no#8 Waihopai Street | W | The min depth of the connection 700mm in the road and 300mm to 375mm below the GL at the boundary to the top of the toby, to be checked and witnessed by site rep. | As per fig.W20 of sheet 17 and specifications in D8.3 and D8.4 | Per each connection | Inspection | Photos | AS/NZS 4129 | Site Engineer | D8.3 D8.4 - Lateral connection to house no#8 Waihopai Street | ACTION (W, M, H) - W | Conformance Criteria (What's Required) - The min depth of the connection 700mm in the road and 300mm to 375mm below the GL at the boundary to the top of the toby, to be checked and witnessed by site rep. | Detail - As per fig.W20 of sheet 17 and specifications in D8.3 and D8.4 | Frequency - Per each connection | Inspection / Test Method - Inspection | Verification Records - Photos | Standard - AS/NZS 4129 | Signatory - Site Engineer | ACTION (W, M, H) - W
D8.3 D8.4 | Lateral connection to house no#18 Waihopai Street | W | The min depth of the connection 700mm in the road and 300mm to 375mm below the GL at the boundary to the top of the toby, to be checked and witnessed by site rep. | As per fig.W20 of sheet 17 and specifications in D8.3 and D8.4 | Per each connection | Inspection | Photos | AS/NZS 4129 | Site Engineer | D8.3 D8.4 - Lateral connection to house no#18 Waihopai Street | ACTION (W, M, H) - W | Conformance Criteria (What's Required) - The min depth of the connection 700mm in the road and 300mm to 375mm below the GL at the boundary to the top of the toby, to be checked and witnessed by site rep. | Detail - As per fig.W20 of sheet 17 and specifications in D8.3 and D8.4 | Frequency - Per each connection | Inspection / Test Method - Inspection | Verification Records - Photos | Standard - AS/NZS 4129 | Signatory - Site Engineer | Conformance Criteria (What's Required) - Thrust protection to be constructed (x2)
D5.5 | Fire Hydrant WAIHOPAI FH01 at CH90 (1) | W | Hydrant outlet is between 200mm CHAR(AMP) 400mm from the finished ground level | The fire hydrant should be installed in accordance with the standard drawing details in sheet 17 fig.W1. section 3 of NZS 4522. | Per each hydrant | Inspection | Photos | NZS 4522 | Site Engineer | D5.5 - Fire Hydrant WAIHOPAI FH01 at CH90 (1) | ACTION (W, M, H) - W | Conformance Criteria (What's Required) - Hydrant outlet is between 200mm CHAR(AMP) 400mm from the finished ground level | Detail - The fire hydrant should be installed in accordance with the standard drawing details in sheet 17 fig.W1. section 3 of NZS 4522. | Frequency - Per each hydrant | Inspection / Test Method - Inspection | Verification Records - Photos | Standard - NZS 4522 | Signatory - Site Engineer | Detail - As per detail H in sheet 16 and typical details as per sheet 18
D5.5 | Fire Hydrant WAIHOPAI FH01 at CH90 (2) | W | Surface box finish | cast iron valve box to be flush with the finished surface level. | Per each hydrant | Inspection | Photos | NZS 4522 | Site Engineer | D5.5 - Fire Hydrant WAIHOPAI FH01 at CH90 (2) | ACTION (W, M, H) - W | Conformance Criteria (What's Required) - Surface box finish | Detail - cast iron valve box to be flush with the finished surface level. | Frequency - Per each hydrant | Inspection / Test Method - Inspection | Verification Records - Photos | Standard - NZS 4522 | Signatory - Site Engineer | Frequency - Before backfilling
D5.5 | Fire Hydrant WAIHOPAI FH01 at CH90 (3) | W | Paint marking, RRPM and Hydrant marker | Hydrant paint markings as per NZS4501:1972 and as per detail W18, marker post as per detail W11 | Per each hydrant | Inspection | Photos | NZS 4522 | Site Engineer | D5.5 - Fire Hydrant WAIHOPAI FH01 at CH90 (3) | ACTION (W, M, H) - W | Conformance Criteria (What's Required) - Paint marking, RRPM and Hydrant marker | Detail - Hydrant paint markings as per NZS4501:1972 and as per detail W18, marker post as per detail W11 | Frequency - Per each hydrant | Inspection / Test Method - Inspection | Verification Records - Photos | Standard - NZS 4522 | Signatory - Site Engineer | Inspection / Test Method - Inspection
| Link in at intersection of Waihopai Street and High Street (1) | W | Manifold bolts to be torqued to manufacture's specification, to be checked and witnessed by the Site representative before backfilling. | PE to DI connection to be done as per the detail I in sheet 16 of the drawing | Before backfilling | Inspection | Photos |  | Site Engineer | - Link in at intersection of Waihopai Street and High Street (1) | ACTION (W, M, H) - W | Conformance Criteria (What's Required) - Manifold bolts to be torqued to manufacture's specification, to be checked and witnessed by the Site representative before backfilling. | Detail - PE to DI connection to be done as per the detail I in sheet 16 of the drawing | Frequency - Before backfilling | Inspection / Test Method - Inspection | Verification Records - Photos | Standard - | Signatory - Site Engineer | Verification Records - Photos
| Link in at intersection of Waihopai Street and High Street (2) | W | Thrust protection to be constructed (x2) | As per detail I in sheet 16 and typical details as per sheet 18 | Before backfilling | Inspection | Photos |  | Site Engineer | - Link in at intersection of Waihopai Street and High Street (2) | ACTION (W, M, H) - W | Conformance Criteria (What's Required) - Thrust protection to be constructed (x2) | Detail - As per detail I in sheet 16 and typical details as per sheet 18 | Frequency - Before backfilling | Inspection / Test Method - Inspection | Verification Records - Photos | Standard - | Signatory - Site Engineer | Standard -
D8.3 D8.4 | Lateral connection to house no#11 Waihopai Street needs confirmation | W | The min depth of the connection 700mm in the road and 300mm to 375mm below the GL at the boundary to the top of the toby, to be checked and witnessed by site rep. | As per fig.W20 of sheet 17 and specifications in D8.3 and D8.4 | Per each connection | Inspection | Photos | AS/NZS 4129 | Engineers Representative | D8.3 D8.4 - Lateral connection to house no#11 Waihopai Street needs confirmation | ACTION (W, M, H) - W | Conformance Criteria (What's Required) - The min depth of the connection 700mm in the road and 300mm to 375mm below the GL at the boundary to the top of the toby, to be checked and witnessed by site rep. | Detail - As per fig.W20 of sheet 17 and specifications in D8.3 and D8.4 | Frequency - Per each connection | Inspection / Test Method - Inspection | Verification Records - Photos | Standard - AS/NZS 4129 | Signatory - Engineers Representative | Signatory - Site Engineer
D8.3 D8.4 | Lateral connection to house no#22 Waihopai Street | W | The min depth of the connection 700mm in the road and 300mm to 375mm below the GL at the boundary to the top of the toby, to be checked and witnessed by site rep. | As per fig.W20 of sheet 17 and specifications in D8.3 and D8.4 | Per each connection | Inspection | Photos | AS/NZS 4129 | Site Engineer | D8.3 D8.4 - Lateral connection to house no#22 Waihopai Street | ACTION (W, M, H) - W | Conformance Criteria (What's Required) - The min depth of the connection 700mm in the road and 300mm to 375mm below the GL at the boundary to the top of the toby, to be checked and witnessed by site rep. | Detail - As per fig.W20 of sheet 17 and specifications in D8.3 and D8.4 | Frequency - Per each connection | Inspection / Test Method - Inspection | Verification Records - Photos | Standard - AS/NZS 4129 | Signatory - Site Engineer | - Removal of existing teeand bends and reinstated with straight through pipe and associated bends/thrust protection at intersection of Layard and Waihopai Streets
D5.4.2 | Isolation Valve WAIHOPAI-HIGH CH126 (1) | W | Spindle height to be max 600mm from surface | The valve should be installed in accordance with the standard drawing details in sheet 17 fig.W4 CHAR(AMP) W9 | Per each valve | Inspection | Photos |  | Site Engineer | D5.4.2 - Isolation Valve WAIHOPAI-HIGH CH126 (1) | ACTION (W, M, H) - W | Conformance Criteria (What's Required) - Spindle height to be max 600mm from surface | Detail - The valve should be installed in accordance with the standard drawing details in sheet 17 fig.W4 CHAR(AMP) W9 | Frequency - Per each valve | Inspection / Test Method - Inspection | Verification Records - Photos | Standard - | Signatory - Site Engineer | ACTION (W, M, H) - W
D5.4.2 | Isolation Valve WAIHOPAI-HIGH CH126 (2) | W | Thrust wall installed | Thrust wall constructed as per fig.W9 of page 17 of the drawings | Per each valve | Inspection | Photos |  | Site Engineer | D5.4.2 - Isolation Valve WAIHOPAI-HIGH CH126 (2) | ACTION (W, M, H) - W | Conformance Criteria (What's Required) - Thrust wall installed | Detail - Thrust wall constructed as per fig.W9 of page 17 of the drawings | Frequency - Per each valve | Inspection / Test Method - Inspection | Verification Records - Photos | Standard - | Signatory - Site Engineer | Conformance Criteria (What's Required) - Pipe reinstated through old line and thrust protected
D5.4.2 | Isolation Valve WAIHOPAI-HIGH CH126 (3) | W | Surface box finish | cast iron valve box to be flush with the finished surface level. | Per each valve | Inspection | Photos |  | Site Engineer | D5.4.2 - Isolation Valve WAIHOPAI-HIGH CH126 (3) | ACTION (W, M, H) - W | Conformance Criteria (What's Required) - Surface box finish | Detail - cast iron valve box to be flush with the finished surface level. | Frequency - Per each valve | Inspection / Test Method - Inspection | Verification Records - Photos | Standard - | Signatory - Site Engineer | Detail - As per detail L in sheet 16 and typical details sheet 18
D8.3 D8.4 | Lateral connection to house no#26 Waihopai Street | W | The min depth of the connection 700mm in the road and 300mm to 375mm below the GL at the boundary to the top of the toby, to be checked and witnessed by site rep. | As per fig.W20 of sheet 17 and specifications in D8.3 and D8.4 | Per each connection | Inspection | Photos | AS/NZS 4129 | Site Engineer | D8.3 D8.4 - Lateral connection to house no#26 Waihopai Street | ACTION (W, M, H) - W | Conformance Criteria (What's Required) - The min depth of the connection 700mm in the road and 300mm to 375mm below the GL at the boundary to the top of the toby, to be checked and witnessed by site rep. | Detail - As per fig.W20 of sheet 17 and specifications in D8.3 and D8.4 | Frequency - Per each connection | Inspection / Test Method - Inspection | Verification Records - Photos | Standard - AS/NZS 4129 | Signatory - Site Engineer | Frequency - per connection
D8.3 D8.4 | Lateral connection to house no#25 Waihopai Street | W | The min depth of the connection 700mm in the road and 300mm to 375mm below the GL at the boundary to the top of the toby, to be checked and witnessed by site rep. | As per fig.W20 of sheet 17 and specifications in D8.3 and D8.4 | Per each connection | Inspection | Photos | AS/NZS 4129 | Site Engineer | D8.3 D8.4 - Lateral connection to house no#25 Waihopai Street | ACTION (W, M, H) - W | Conformance Criteria (What's Required) - The min depth of the connection 700mm in the road and 300mm to 375mm below the GL at the boundary to the top of the toby, to be checked and witnessed by site rep. | Detail - As per fig.W20 of sheet 17 and specifications in D8.3 and D8.4 | Frequency - Per each connection | Inspection / Test Method - Inspection | Verification Records - Photos | Standard - AS/NZS 4129 | Signatory - Site Engineer | Inspection / Test Method - Inspection
D8.3 D8.4 | Lateral connection to house no#29 Waihopai Street | W | The min depth of the connection 700mm in the road and 300mm to 375mm below the GL at the boundary to the top of the toby, to be checked and witnessed by site rep. | As per fig.W20 of sheet 17 and specifications in D8.3 and D8.4 | Per each connection | Inspection | Photos | AS/NZS 4129 | Site Engineer | D8.3 D8.4 - Lateral connection to house no#29 Waihopai Street | ACTION (W, M, H) - W | Conformance Criteria (What's Required) - The min depth of the connection 700mm in the road and 300mm to 375mm below the GL at the boundary to the top of the toby, to be checked and witnessed by site rep. | Detail - As per fig.W20 of sheet 17 and specifications in D8.3 and D8.4 | Frequency - Per each connection | Inspection / Test Method - Inspection | Verification Records - Photos | Standard - AS/NZS 4129 | Signatory - Site Engineer | Verification Records - Photos
D5.5 | Fire Hydrant WAIHOPAI FH02 at CH178 (1) | W | Hydrant outlet is between 200mm CHAR(AMP) 400mm from the finished ground level | The fire hydrant should be installed in accordance with the standard drawing details in sheet 17 fig.W1. section 3 of NZS 4522. | Per each hydrant | Inspection | Photos | NZS 4522 | Site Engineer | D5.5 - Fire Hydrant WAIHOPAI FH02 at CH178 (1) | ACTION (W, M, H) - W | Conformance Criteria (What's Required) - Hydrant outlet is between 200mm CHAR(AMP) 400mm from the finished ground level | Detail - The fire hydrant should be installed in accordance with the standard drawing details in sheet 17 fig.W1. section 3 of NZS 4522. | Frequency - Per each hydrant | Inspection / Test Method - Inspection | Verification Records - Photos | Standard - NZS 4522 | Signatory - Site Engineer | Standard - AS/NZS 4130
D5.5 | Fire Hydrant WAIHOPAI FH02 at CH178 (2) | W | Surface box finish | cast iron valve box to be flush with the finished surface level. | Per each hydrant | Inspection | Photos | NZS 4522 | Site Engineer | D5.5 - Fire Hydrant WAIHOPAI FH02 at CH178 (2) | ACTION (W, M, H) - W | Conformance Criteria (What's Required) - Surface box finish | Detail - cast iron valve box to be flush with the finished surface level. | Frequency - Per each hydrant | Inspection / Test Method - Inspection | Verification Records - Photos | Standard - NZS 4522 | Signatory - Site Engineer | Signatory - Site Engineer
D5.5 | Fire Hydrant WAIHOPAI FH02 at CH178 (3) | W | Paint marking, RRPM and Hydrant marker | Hydrant paint markings as per NZS4501:1972 and as per detail W18, marker post as per detail W11 | Per each hydrant | Inspection | Photos | NZS 4522 | Site Engineer | D5.5 - Fire Hydrant WAIHOPAI FH02 at CH178 (3) | ACTION (W, M, H) - W | Conformance Criteria (What's Required) - Paint marking, RRPM and Hydrant marker | Detail - Hydrant paint markings as per NZS4501:1972 and as per detail W18, marker post as per detail W11 | Frequency - Per each hydrant | Inspection / Test Method - Inspection | Verification Records - Photos | Standard - NZS 4522 | Signatory - Site Engineer | D5.4.2 - Isolation Valve WAIHOPAI-LAYARD CH15 (1)
D8.3 D8.4 | Lateral connection to house no#30 Waihopai Street | W | The min depth of the connection 700mm in the road and 300mm to 375mm below the GL at the boundary to the top of the toby, to be checked and witnessed by site rep. | As per fig.W20 of sheet 17 and specifications in D8.3 and D8.4 | Per each connection | Inspection | Photos | AS/NZS 4129 | Site Engineer | D8.3 D8.4 - Lateral connection to house no#30 Waihopai Street | ACTION (W, M, H) - W | Conformance Criteria (What's Required) - The min depth of the connection 700mm in the road and 300mm to 375mm below the GL at the boundary to the top of the toby, to be checked and witnessed by site rep. | Detail - As per fig.W20 of sheet 17 and specifications in D8.3 and D8.4 | Frequency - Per each connection | Inspection / Test Method - Inspection | Verification Records - Photos | Standard - AS/NZS 4129 | Signatory - Site Engineer | ACTION (W, M, H) - W
D8.3 D8.4 | Lateral connection to house no#38 Waihopai Street | W | The min depth of the connection 700mm in the road and 300mm to 375mm below the GL at the boundary to the top of the toby, to be checked and witnessed by site rep. | As per fig.W20 of sheet 17 and specifications in D8.3 and D8.4 | Per each connection | Inspection | Photos | AS/NZS 4129 | Site Engineer | D8.3 D8.4 - Lateral connection to house no#38 Waihopai Street | ACTION (W, M, H) - W | Conformance Criteria (What's Required) - The min depth of the connection 700mm in the road and 300mm to 375mm below the GL at the boundary to the top of the toby, to be checked and witnessed by site rep. | Detail - As per fig.W20 of sheet 17 and specifications in D8.3 and D8.4 | Frequency - Per each connection | Inspection / Test Method - Inspection | Verification Records - Photos | Standard - AS/NZS 4129 | Signatory - Site Engineer | Conformance Criteria (What's Required) - Spindle height to be max 600mm from surface
D8.3 D8.4 | Lateral connection to house no#33 Waihopai Street | W | The min depth of the connection 700mm in the road and 300mm to 375mm below the GL at the boundary to the top of the toby, to be checked and witnessed by site rep. | As per fig.W20 of sheet 17 and specifications in D8.3 and D8.4 | Per each connection | Inspection | Photos | AS/NZS 4129 | Site Engineer | D8.3 D8.4 - Lateral connection to house no#33 Waihopai Street | ACTION (W, M, H) - W | Conformance Criteria (What's Required) - The min depth of the connection 700mm in the road and 300mm to 375mm below the GL at the boundary to the top of the toby, to be checked and witnessed by site rep. | Detail - As per fig.W20 of sheet 17 and specifications in D8.3 and D8.4 | Frequency - Per each connection | Inspection / Test Method - Inspection | Verification Records - Photos | Standard - AS/NZS 4129 | Signatory - Site Engineer | Detail - The valve should be installed in accordance with the standard drawing details in sheet 17 fig.W4 CHAR(AMP) W9
| Link in at intersection of Waihopai and Terrace Streets (1) | W | Manifold bolts to be torqued to manufacture's specification, to be checked and witnessed by the Site representative before backfilling. | PE to DI connection to be done as per the detail J in sheet 16 of the drawing | Before backfilling | Inspection | Photos |  | Site Engineer | - Link in at intersection of Waihopai and Terrace Streets (1) | ACTION (W, M, H) - W | Conformance Criteria (What's Required) - Manifold bolts to be torqued to manufacture's specification, to be checked and witnessed by the Site representative before backfilling. | Detail - PE to DI connection to be done as per the detail J in sheet 16 of the drawing | Frequency - Before backfilling | Inspection / Test Method - Inspection | Verification Records - Photos | Standard - | Signatory - Site Engineer | Frequency - Per each valve
| Link in at intersection of Waihopai and Terrace Streets (2) | W | Thrust protection to be constructed (x2) | As per detail J in sheet 16 and typical details as per sheet 18 | Before backfilling | Inspection | Photos |  | Site Engineer | - Link in at intersection of Waihopai and Terrace Streets (2) | ACTION (W, M, H) - W | Conformance Criteria (What's Required) - Thrust protection to be constructed (x2) | Detail - As per detail J in sheet 16 and typical details as per sheet 18 | Frequency - Before backfilling | Inspection / Test Method - Inspection | Verification Records - Photos | Standard - | Signatory - Site Engineer | Inspection / Test Method - Inspection
| Capping of existing tees to blank abandoned ends. Intersection of Waihopai and Terrace Streets | W | Tee ends blanked and thrust protected | As per typical details in sheet 18 | per connection | Inspection | Photos | AS/NZS 4130 | Site Engineer | - Capping of existing tees to blank abandoned ends. Intersection of Waihopai and Terrace Streets | ACTION (W, M, H) - W | Conformance Criteria (What's Required) - Tee ends blanked and thrust protected | Detail - As per typical details in sheet 18 | Frequency - per connection | Inspection / Test Method - Inspection | Verification Records - Photos | Standard - AS/NZS 4130 | Signatory - Site Engineer | Verification Records - Photos
D5.4.2 | Isolation Valve WAIHOPAI-TERRACE CH238 (1) | W | Spindle height to be max 600mm from surface | The valve should be installed in accordance with the standard drawing details in sheet 17 fig.W4 CHAR(AMP) W9 | Per each valve | Inspection | Photos |  | Site Engineer | D5.4.2 - Isolation Valve WAIHOPAI-TERRACE CH238 (1) | ACTION (W, M, H) - W | Conformance Criteria (What's Required) - Spindle height to be max 600mm from surface | Detail - The valve should be installed in accordance with the standard drawing details in sheet 17 fig.W4 CHAR(AMP) W9 | Frequency - Per each valve | Inspection / Test Method - Inspection | Verification Records - Photos | Standard - | Signatory - Site Engineer | Standard -
D5.4.2 | Isolation Valve WAIHOPAI-TERRACE CH238 (2) | W | Thrust wall installed | Thrust wall constructed as per fig.W9 of page 17 of the drawings | Per each valve | Inspection | Photos |  | Site Engineer | D5.4.2 - Isolation Valve WAIHOPAI-TERRACE CH238 (2) | ACTION (W, M, H) - W | Conformance Criteria (What's Required) - Thrust wall installed | Detail - Thrust wall constructed as per fig.W9 of page 17 of the drawings | Frequency - Per each valve | Inspection / Test Method - Inspection | Verification Records - Photos | Standard - | Signatory - Site Engineer | Signatory - Site Engineer
D5.4.2 | Isolation Valve WAIHOPAI-TERRACE CH238 (3) | W | Surface box finish | cast iron valve box to be flush with the finished surface level. | Per each valve | Inspection | Photos |  | Site Engineer | D5.4.2 - Isolation Valve WAIHOPAI-TERRACE CH238 (3) | ACTION (W, M, H) - W | Conformance Criteria (What's Required) - Surface box finish | Detail - cast iron valve box to be flush with the finished surface level. | Frequency - Per each valve | Inspection / Test Method - Inspection | Verification Records - Photos | Standard - | Signatory - Site Engineer | D5.4.2 - Isolation Valve WAIHOPAI-LAYARD CH15 (2)
D8.3 D8.4 | Lateral connection to house no#42 Waihopai Street | W | The min depth of the connection 700mm in the road and 300mm to 375mm below the GL at the boundary to the top of the toby, to be checked and witnessed by site rep. | As per fig.W20 of sheet 17 and specifications in D8.3 and D8.4 | Per each connection | Inspection | Photos | AS/NZS 4129 | Site Engineer | D8.3 D8.4 - Lateral connection to house no#42 Waihopai Street | ACTION (W, M, H) - W | Conformance Criteria (What's Required) - The min depth of the connection 700mm in the road and 300mm to 375mm below the GL at the boundary to the top of the toby, to be checked and witnessed by site rep. | Detail - As per fig.W20 of sheet 17 and specifications in D8.3 and D8.4 | Frequency - Per each connection | Inspection / Test Method - Inspection | Verification Records - Photos | Standard - AS/NZS 4129 | Signatory - Site Engineer | ACTION (W, M, H) - W
D8.3 D8.4 | Lateral connection to house no#46 Waihopai Street | W | The min depth of the connection 700mm in the road and 300mm to 375mm below the GL at the boundary to the top of the toby, to be checked and witnessed by site rep. | As per fig.W20 of sheet 17 and specifications in D8.3 and D8.4 | Per each connection | Inspection | Photos | AS/NZS 4129 | Site Engineer | D8.3 D8.4 - Lateral connection to house no#46 Waihopai Street | ACTION (W, M, H) - W | Conformance Criteria (What's Required) - The min depth of the connection 700mm in the road and 300mm to 375mm below the GL at the boundary to the top of the toby, to be checked and witnessed by site rep. | Detail - As per fig.W20 of sheet 17 and specifications in D8.3 and D8.4 | Frequency - Per each connection | Inspection / Test Method - Inspection | Verification Records - Photos | Standard - AS/NZS 4129 | Signatory - Site Engineer | Conformance Criteria (What's Required) - Thrust wall installed
D8.3 D8.4 | Lateral connection to house no#52 Waihopai Street | W | The min depth of the connection 700mm in the road and 300mm to 375mm below the GL at the boundary to the top of the toby, to be checked and witnessed by site rep. | As per fig.W20 of sheet 17 and specifications in D8.3 and D8.4 | Per each connection | Inspection | Photos | AS/NZS 4129 | Site Engineer | D8.3 D8.4 - Lateral connection to house no#52 Waihopai Street | ACTION (W, M, H) - W | Conformance Criteria (What's Required) - The min depth of the connection 700mm in the road and 300mm to 375mm below the GL at the boundary to the top of the toby, to be checked and witnessed by site rep. | Detail - As per fig.W20 of sheet 17 and specifications in D8.3 and D8.4 | Frequency - Per each connection | Inspection / Test Method - Inspection | Verification Records - Photos | Standard - AS/NZS 4129 | Signatory - Site Engineer | Detail - Thrust wall constructed as per fig.W9 of page 17 of the drawings
D5.5 | Fire Hydrant WAIHOPAI FH03 at CH285 (1) | W | Hydrant outlet is between 200mm CHAR(AMP) 400mm from the finished ground level | The fire hydrant should be installed in accordance with the standard drawing details in sheet 17 fig.W1. section 3 of NZS 4522. | Per each hydrant | Inspection | Photos | NZS 4522 | Site Engineer | D5.5 - Fire Hydrant WAIHOPAI FH03 at CH285 (1) | ACTION (W, M, H) - W | Conformance Criteria (What's Required) - Hydrant outlet is between 200mm CHAR(AMP) 400mm from the finished ground level | Detail - The fire hydrant should be installed in accordance with the standard drawing details in sheet 17 fig.W1. section 3 of NZS 4522. | Frequency - Per each hydrant | Inspection / Test Method - Inspection | Verification Records - Photos | Standard - NZS 4522 | Signatory - Site Engineer | Frequency - Per each valve
D5.5 | Fire Hydrant WAIHOPAI FH03 at CH285 (2) | W | Surface box finish | cast iron valve box to be flush with the finished surface level. | Per each hydrant | Inspection | Photos | NZS 4522 | Site Engineer | D5.5 - Fire Hydrant WAIHOPAI FH03 at CH285 (2) | ACTION (W, M, H) - W | Conformance Criteria (What's Required) - Surface box finish | Detail - cast iron valve box to be flush with the finished surface level. | Frequency - Per each hydrant | Inspection / Test Method - Inspection | Verification Records - Photos | Standard - NZS 4522 | Signatory - Site Engineer | Inspection / Test Method - Inspection
D5.5 | Fire Hydrant WAIHOPAI FH03 at CH285 (3) | W | Paint marking, RRPM and Hydrant marker | Hydrant paint markings as per NZS4501:1972 and as per detail W18, marker post as per detail W11 | Per each hydrant | Inspection | Photos | NZS 4522 | Site Engineer | D5.5 - Fire Hydrant WAIHOPAI FH03 at CH285 (3) | ACTION (W, M, H) - W | Conformance Criteria (What's Required) - Paint marking, RRPM and Hydrant marker | Detail - Hydrant paint markings as per NZS4501:1972 and as per detail W18, marker post as per detail W11 | Frequency - Per each hydrant | Inspection / Test Method - Inspection | Verification Records - Photos | Standard - NZS 4522 | Signatory - Site Engineer | Verification Records - Photos
D8.3 D8.4 | Lateral connection to house no#53 Waihopai Street | W | The min depth of the connection 700mm in the road and 300mm to 375mm below the GL at the boundary to the top of the toby, to be checked and witnessed by site rep. | As per fig.W20 of sheet 17 and specifications in D8.3 and D8.4 | Per each connection | Inspection | Photos | AS/NZS 4129 | Site Engineer | D8.3 D8.4 - Lateral connection to house no#53 Waihopai Street | ACTION (W, M, H) - W | Conformance Criteria (What's Required) - The min depth of the connection 700mm in the road and 300mm to 375mm below the GL at the boundary to the top of the toby, to be checked and witnessed by site rep. | Detail - As per fig.W20 of sheet 17 and specifications in D8.3 and D8.4 | Frequency - Per each connection | Inspection / Test Method - Inspection | Verification Records - Photos | Standard - AS/NZS 4129 | Signatory - Site Engineer | Standard -
D8.3 D8.4 | Lateral connection to house no#54 Waihopai Street | W | The min depth of the connection 700mm in the road and 300mm to 375mm below the GL at the boundary to the top of the toby, to be checked and witnessed by site rep. | As per fig.W20 of sheet 17 and specifications in D8.3 and D8.4 | Per each connection | Inspection | Photos | AS/NZS 4129 | Site Engineer | D8.3 D8.4 - Lateral connection to house no#54 Waihopai Street | ACTION (W, M, H) - W | Conformance Criteria (What's Required) - The min depth of the connection 700mm in the road and 300mm to 375mm below the GL at the boundary to the top of the toby, to be checked and witnessed by site rep. | Detail - As per fig.W20 of sheet 17 and specifications in D8.3 and D8.4 | Frequency - Per each connection | Inspection / Test Method - Inspection | Verification Records - Photos | Standard - AS/NZS 4129 | Signatory - Site Engineer | Signatory - Site Engineer
D8.3 D8.4 | Lateral connection to house no#58 Waihopai Street | W | The min depth of the connection 700mm in the road and 300mm to 375mm below the GL at the boundary to the top of the toby, to be checked and witnessed by site rep. | As per fig.W20 of sheet 17 and specifications in D8.3 and D8.4 | Per each connection | Inspection | Photos | AS/NZS 4129 | Site Engineer | D8.3 D8.4 - Lateral connection to house no#58 Waihopai Street | ACTION (W, M, H) - W | Conformance Criteria (What's Required) - The min depth of the connection 700mm in the road and 300mm to 375mm below the GL at the boundary to the top of the toby, to be checked and witnessed by site rep. | Detail - As per fig.W20 of sheet 17 and specifications in D8.3 and D8.4 | Frequency - Per each connection | Inspection / Test Method - Inspection | Verification Records - Photos | Standard - AS/NZS 4129 | Signatory - Site Engineer | D5.4.2 - Isolation Valve WAIHOPAI-LAYARD CH15 (3)
| Link in at intersection of Waihopai Street and Lamond Street West (1) | W | Manifold bolts to be torqued to manufacture's specification, to be checked and witnessed by the Site representative before backfilling. | PE to DI connection to be done as per the detail I in sheet 16 of the drawing | Before backfilling | Inspection | Photos |  | Site Engineer | - Link in at intersection of Waihopai Street and Lamond Street West (1) | ACTION (W, M, H) - W | Conformance Criteria (What's Required) - Manifold bolts to be torqued to manufacture's specification, to be checked and witnessed by the Site representative before backfilling. | Detail - PE to DI connection to be done as per the detail I in sheet 16 of the drawing | Frequency - Before backfilling | Inspection / Test Method - Inspection | Verification Records - Photos | Standard - | Signatory - Site Engineer | ACTION (W, M, H) - W
| Link in at intersection of Waihopai Street and Lamond Street West (2) | W | Thrust protection to be constructed (x2) | As per detail I in sheet 16 and typical details as per sheet 18 | Before backfilling | Inspection | Photos |  | Site Engineer | - Link in at intersection of Waihopai Street and Lamond Street West (2) | ACTION (W, M, H) - W | Conformance Criteria (What's Required) - Thrust protection to be constructed (x2) | Detail - As per detail I in sheet 16 and typical details as per sheet 18 | Frequency - Before backfilling | Inspection / Test Method - Inspection | Verification Records - Photos | Standard - | Signatory - Site Engineer | Conformance Criteria (What's Required) - Surface box finish
D8.3 D8.4 | Lateral connection to house no#60 Waihopai Street | W | The min depth of the connection 700mm in the road and 300mm to 375mm below the GL at the boundary to the top of the toby, to be checked and witnessed by site rep. | As per fig.W20 of sheet 17 and specifications in D8.3 and D8.4 | Per each connection | Inspection | Photos | AS/NZS 4129 | Site Engineer | D8.3 D8.4 - Lateral connection to house no#60 Waihopai Street | ACTION (W, M, H) - W | Conformance Criteria (What's Required) - The min depth of the connection 700mm in the road and 300mm to 375mm below the GL at the boundary to the top of the toby, to be checked and witnessed by site rep. | Detail - As per fig.W20 of sheet 17 and specifications in D8.3 and D8.4 | Frequency - Per each connection | Inspection / Test Method - Inspection | Verification Records - Photos | Standard - AS/NZS 4129 | Signatory - Site Engineer | Detail - cast iron valve box to be flush with the finished surface level.
D5.4.2 | Isolation Valve WAIHOPAI-LAMOND CH347 (1) | W | Spindle height to be max 600mm from surface | The valve should be installed in accordance with the standard drawing details in sheet 17 fig.W4 CHAR(AMP) W9 | Per each valve | Inspection | Photos |  | Site Engineer | D5.4.2 - Isolation Valve WAIHOPAI-LAMOND CH347 (1) | ACTION (W, M, H) - W | Conformance Criteria (What's Required) - Spindle height to be max 600mm from surface | Detail - The valve should be installed in accordance with the standard drawing details in sheet 17 fig.W4 CHAR(AMP) W9 | Frequency - Per each valve | Inspection / Test Method - Inspection | Verification Records - Photos | Standard - | Signatory - Site Engineer | Frequency - Per each valve
D5.4.2 | Isolation Valve WAIHOPAI-LAMOND CH347 (2) | W | Thrust wall installed | Thrust wall constructed as per fig.W9 of page 17 of the drawings | Per each valve | Inspection | Photos |  | Site Engineer | D5.4.2 - Isolation Valve WAIHOPAI-LAMOND CH347 (2) | ACTION (W, M, H) - W | Conformance Criteria (What's Required) - Thrust wall installed | Detail - Thrust wall constructed as per fig.W9 of page 17 of the drawings | Frequency - Per each valve | Inspection / Test Method - Inspection | Verification Records - Photos | Standard - | Signatory - Site Engineer | Inspection / Test Method - Inspection
D5.4.2 | Isolation Valve WAIHOPAI-LAMOND CH347 (3) | W | Surface box finish | cast iron valve box to be flush with the finished surface level. | Per each valve | Inspection | Photos |  | Site Engineer | D5.4.2 - Isolation Valve WAIHOPAI-LAMOND CH347 (3) | ACTION (W, M, H) - W | Conformance Criteria (What's Required) - Surface box finish | Detail - cast iron valve box to be flush with the finished surface level. | Frequency - Per each valve | Inspection / Test Method - Inspection | Verification Records - Photos | Standard - | Signatory - Site Engineer | Verification Records - Photos
D8.3 D8.4 | Lateral connection to house no#62 Waihopai Street | W | The min depth of the connection 700mm in the road and 300mm to 375mm below the GL at the boundary to the top of the toby, to be checked and witnessed by site rep. | As per fig.W20 of sheet 17 and specifications in D8.3 and D8.4 | Per each connection | Inspection | Photos | AS/NZS 4129 | Site Engineer | D8.3 D8.4 - Lateral connection to house no#62 Waihopai Street | ACTION (W, M, H) - W | Conformance Criteria (What's Required) - The min depth of the connection 700mm in the road and 300mm to 375mm below the GL at the boundary to the top of the toby, to be checked and witnessed by site rep. | Detail - As per fig.W20 of sheet 17 and specifications in D8.3 and D8.4 | Frequency - Per each connection | Inspection / Test Method - Inspection | Verification Records - Photos | Standard - AS/NZS 4129 | Signatory - Site Engineer | Standard -
D8.3 D8.4 | Lateral connection to house no#64 Waihopai Street | W | The min depth of the connection 700mm in the road and 300mm to 375mm below the GL at the boundary to the top of the toby, to be checked and witnessed by site rep. | As per fig.W20 of sheet 17 and specifications in D8.3 and D8.4 | Per each connection | Inspection | Photos | AS/NZS 4129 | Site Engineer | D8.3 D8.4 - Lateral connection to house no#64 Waihopai Street | ACTION (W, M, H) - W | Conformance Criteria (What's Required) - The min depth of the connection 700mm in the road and 300mm to 375mm below the GL at the boundary to the top of the toby, to be checked and witnessed by site rep. | Detail - As per fig.W20 of sheet 17 and specifications in D8.3 and D8.4 | Frequency - Per each connection | Inspection / Test Method - Inspection | Verification Records - Photos | Standard - AS/NZS 4129 | Signatory - Site Engineer | Signatory - Site Engineer
D8.3 D8.4 | Lateral connection to house no#71 Waihopai Street | W | The min depth of the connection 700mm in the road and 300mm to 375mm below the GL at the boundary to the top of the toby, to be checked and witnessed by site rep. | As per fig.W20 of sheet 17 and specifications in D8.3 and D8.4 | Per each connection | Inspection | Photos | AS/NZS 4129 | Site Engineer | D8.3 D8.4 - Lateral connection to house no#71 Waihopai Street | ACTION (W, M, H) - W | Conformance Criteria (What's Required) - The min depth of the connection 700mm in the road and 300mm to 375mm below the GL at the boundary to the top of the toby, to be checked and witnessed by site rep. | Detail - As per fig.W20 of sheet 17 and specifications in D8.3 and D8.4 | Frequency - Per each connection | Inspection / Test Method - Inspection | Verification Records - Photos | Standard - AS/NZS 4129 | Signatory - Site Engineer | D8.3 D8.4 - Lateral connection to house no#90 Layard Street
D8.3 D8.4 | Lateral connection to house no#66 Waihopai Street | W | The min depth of the connection 700mm in the road and 300mm to 375mm below the GL at the boundary to the top of the toby, to be checked and witnessed by site rep. | As per fig.W20 of sheet 17 and specifications in D8.3 and D8.4 | Per each connection | Inspection | Photos | AS/NZS 4129 | Site Engineer | D8.3 D8.4 - Lateral connection to house no#66 Waihopai Street | ACTION (W, M, H) - W | Conformance Criteria (What's Required) - The min depth of the connection 700mm in the road and 300mm to 375mm below the GL at the boundary to the top of the toby, to be checked and witnessed by site rep. | Detail - As per fig.W20 of sheet 17 and specifications in D8.3 and D8.4 | Frequency - Per each connection | Inspection / Test Method - Inspection | Verification Records - Photos | Standard - AS/NZS 4129 | Signatory - Site Engineer | ACTION (W, M, H) - W
D8.3 D8.4 | Lateral connection to house no#70 Waihopai Street | W | The min depth of the connection 700mm in the road and 300mm to 375mm below the GL at the boundary to the top of the toby, to be checked and witnessed by site rep. | As per fig.W20 of sheet 17 and specifications in D8.3 and D8.4 | Per each connection | Inspection | Photos | AS/NZS 4129 | Site Engineer | D8.3 D8.4 - Lateral connection to house no#70 Waihopai Street | ACTION (W, M, H) - W | Conformance Criteria (What's Required) - The min depth of the connection 700mm in the road and 300mm to 375mm below the GL at the boundary to the top of the toby, to be checked and witnessed by site rep. | Detail - As per fig.W20 of sheet 17 and specifications in D8.3 and D8.4 | Frequency - Per each connection | Inspection / Test Method - Inspection | Verification Records - Photos | Standard - AS/NZS 4129 | Signatory - Site Engineer | Conformance Criteria (What's Required) - The min depth of the connection 700mm in the road and 300mm to 375mm below the GL at the boundary to the top of the toby, to be checked and witnessed by site rep.
D5.5 | Fire Hydrant WAIHOPAI FH04 at CH393 (1) | W | Hydrant outlet is between 200mm CHAR(AMP) 400mm from the finished ground level | The fire hydrant should be installed in accordance with the standard drawing details in sheet 17 fig.W1. section 3 of NZS 4522. | Per each hydrant | Inspection | Photos | NZS 4522 | Site Engineer | D5.5 - Fire Hydrant WAIHOPAI FH04 at CH393 (1) | ACTION (W, M, H) - W | Conformance Criteria (What's Required) - Hydrant outlet is between 200mm CHAR(AMP) 400mm from the finished ground level | Detail - The fire hydrant should be installed in accordance with the standard drawing details in sheet 17 fig.W1. section 3 of NZS 4522. | Frequency - Per each hydrant | Inspection / Test Method - Inspection | Verification Records - Photos | Standard - NZS 4522 | Signatory - Site Engineer | Detail - As per fig.W20 of sheet 17 and specifications in D8.3 and D8.4
D5.5 | Fire Hydrant WAIHOPAI FH04 at CH393 (2) | W | Surface box finish | cast iron valve box to be flush with the finished surface level. | Per each hydrant | Inspection | Photos | NZS 4522 | Site Engineer | D5.5 - Fire Hydrant WAIHOPAI FH04 at CH393 (2) | ACTION (W, M, H) - W | Conformance Criteria (What's Required) - Surface box finish | Detail - cast iron valve box to be flush with the finished surface level. | Frequency - Per each hydrant | Inspection / Test Method - Inspection | Verification Records - Photos | Standard - NZS 4522 | Signatory - Site Engineer | Frequency - Per each connection
D5.5 | Fire Hydrant WAIHOPAI FH04 at CH393 (3) | W | Paint marking, RRPM and Hydrant marker | Hydrant paint markings as per NZS4501:1972 and as per detail W18, marker post as per detail W11 | Per each hydrant | Inspection | Photos | NZS 4522 | Site Engineer | D5.5 - Fire Hydrant WAIHOPAI FH04 at CH393 (3) | ACTION (W, M, H) - W | Conformance Criteria (What's Required) - Paint marking, RRPM and Hydrant marker | Detail - Hydrant paint markings as per NZS4501:1972 and as per detail W18, marker post as per detail W11 | Frequency - Per each hydrant | Inspection / Test Method - Inspection | Verification Records - Photos | Standard - NZS 4522 | Signatory - Site Engineer | Inspection / Test Method - Inspection
D8.3 D8.4 | Lateral connection to house no#75 Waihopai Street | W | The min depth of the connection 700mm in the road and 300mm to 375mm below the GL at the boundary to the top of the toby, to be checked and witnessed by site rep. | As per fig.W20 of sheet 17 and specifications in D8.3 and D8.4 | Per each connection | Inspection | Photos | AS/NZS 4129 | Site Engineer | D8.3 D8.4 - Lateral connection to house no#75 Waihopai Street | ACTION (W, M, H) - W | Conformance Criteria (What's Required) - The min depth of the connection 700mm in the road and 300mm to 375mm below the GL at the boundary to the top of the toby, to be checked and witnessed by site rep. | Detail - As per fig.W20 of sheet 17 and specifications in D8.3 and D8.4 | Frequency - Per each connection | Inspection / Test Method - Inspection | Verification Records - Photos | Standard - AS/NZS 4129 | Signatory - Site Engineer | Verification Records - Photos
D8.3 D8.4 | Lateral connection to house no#74 Waihopai Street | W | The min depth of the connection 700mm in the road and 300mm to 375mm below the GL at the boundary to the top of the toby, to be checked and witnessed by site rep. | As per fig.W20 of sheet 17 and specifications in D8.3 and D8.4 | Per each connection | Inspection | Photos | AS/NZS 4129 | Site Engineer | D8.3 D8.4 - Lateral connection to house no#74 Waihopai Street | ACTION (W, M, H) - W | Conformance Criteria (What's Required) - The min depth of the connection 700mm in the road and 300mm to 375mm below the GL at the boundary to the top of the toby, to be checked and witnessed by site rep. | Detail - As per fig.W20 of sheet 17 and specifications in D8.3 and D8.4 | Frequency - Per each connection | Inspection / Test Method - Inspection | Verification Records - Photos | Standard - AS/NZS 4129 | Signatory - Site Engineer | Standard - AS/NZS 4129
D8.3 D8.4 | Lateral connection to house no#78 Waihopai Street | W | The min depth of the connection 700mm in the road and 300mm to 375mm below the GL at the boundary to the top of the toby, to be checked and witnessed by site rep. | As per fig.W20 of sheet 17 and specifications in D8.3 and D8.4 | Per each connection | Inspection | Photos | AS/NZS 4129 | Site Engineer | D8.3 D8.4 - Lateral connection to house no#78 Waihopai Street | ACTION (W, M, H) - W | Conformance Criteria (What's Required) - The min depth of the connection 700mm in the road and 300mm to 375mm below the GL at the boundary to the top of the toby, to be checked and witnessed by site rep. | Detail - As per fig.W20 of sheet 17 and specifications in D8.3 and D8.4 | Frequency - Per each connection | Inspection / Test Method - Inspection | Verification Records - Photos | Standard - AS/NZS 4129 | Signatory - Site Engineer | Signatory - Site Engineer
D5.4.2 | Isolation Valve WAIHOPAI-MOANA CH438 (1) | W | Spindle height to be max 600mm from surface | The valve should be installed in accordance with the standard drawing details in sheet 17 fig.W4 CHAR(AMP) W9 | Per each valve | Inspection | Photos |  | Site Engineer | D5.4.2 - Isolation Valve WAIHOPAI-MOANA CH438 (1) | ACTION (W, M, H) - W | Conformance Criteria (What's Required) - Spindle height to be max 600mm from surface | Detail - The valve should be installed in accordance with the standard drawing details in sheet 17 fig.W4 CHAR(AMP) W9 | Frequency - Per each valve | Inspection / Test Method - Inspection | Verification Records - Photos | Standard - | Signatory - Site Engineer | D8.3 D8.4 - Lateral connection to house no#92 Layard Street
D5.4.2 | Isolation Valve WAIHOPAI-MOANA CH438 (2) | W | Thrust wall installed | Thrust wall constructed as per fig.W9 of page 17 of the drawings | Per each valve | Inspection | Photos |  | Site Engineer | D5.4.2 - Isolation Valve WAIHOPAI-MOANA CH438 (2) | ACTION (W, M, H) - W | Conformance Criteria (What's Required) - Thrust wall installed | Detail - Thrust wall constructed as per fig.W9 of page 17 of the drawings | Frequency - Per each valve | Inspection / Test Method - Inspection | Verification Records - Photos | Standard - | Signatory - Site Engineer | ACTION (W, M, H) - W
D5.4.2 | Isolation Valve WAIHOPAI-MOANA CH438 (3) | W | Surface box finish | cast iron valve box to be flush with the finished surface level. | Per each valve | Inspection | Photos |  | Site Engineer | D5.4.2 - Isolation Valve WAIHOPAI-MOANA CH438 (3) | ACTION (W, M, H) - W | Conformance Criteria (What's Required) - Surface box finish | Detail - cast iron valve box to be flush with the finished surface level. | Frequency - Per each valve | Inspection / Test Method - Inspection | Verification Records - Photos | Standard - | Signatory - Site Engineer | Conformance Criteria (What's Required) - The min depth of the connection 700mm in the road and 300mm to 375mm below the GL at the boundary to the top of the toby, to be checked and witnessed by site rep.
| Link in at intersection of Waihopai Street and Moana Street (1) | W | Manifold bolts to be torqued to manufacture's specification, to be checked and witnessed by the Site representative before backfilling. | PE to DI connection to be done as per the detail K in sheet 16 of the drawing | Before backfilling | Inspection | Photos |  | Site Engineer | - Link in at intersection of Waihopai Street and Moana Street (1) | ACTION (W, M, H) - W | Conformance Criteria (What's Required) - Manifold bolts to be torqued to manufacture's specification, to be checked and witnessed by the Site representative before backfilling. | Detail - PE to DI connection to be done as per the detail K in sheet 16 of the drawing | Frequency - Before backfilling | Inspection / Test Method - Inspection | Verification Records - Photos | Standard - | Signatory - Site Engineer | Detail - As per fig.W20 of sheet 17 and specifications in D8.3 and D8.4
| Link in at intersection of Waihopai Street and Moana Street (2) | W | Thrust protection to be constructed (x2) | As per detail K in sheet 16 and typical details as per sheet 18 | Before backfilling | Inspection | Photos |  | Site Engineer | - Link in at intersection of Waihopai Street and Moana Street (2) | ACTION (W, M, H) - W | Conformance Criteria (What's Required) - Thrust protection to be constructed (x2) | Detail - As per detail K in sheet 16 and typical details as per sheet 18 | Frequency - Before backfilling | Inspection / Test Method - Inspection | Verification Records - Photos | Standard - | Signatory - Site Engineer | Frequency - Per each connection
| Removal of existing tee and bends and reinstated with straight through pipe and associated bends/thrust protection at intersection of Waihopai Street and Moana Street | W | Pipe reinstated through old line and thrust protected | As per detail L in sheet 16 and typical details sheet 18 | per connection | Inspection | Photos | AS/NZS 4130 | Site Engineer | - Removal of existing tee and bends and reinstated with straight through pipe and associated bends/thrust protection at intersection of Waihopai Street and Moana Street | ACTION (W, M, H) - W | Conformance Criteria (What's Required) - Pipe reinstated through old line and thrust protected | Detail - As per detail L in sheet 16 and typical details sheet 18 | Frequency - per connection | Inspection / Test Method - Inspection | Verification Records - Photos | Standard - AS/NZS 4130 | Signatory - Site Engineer | Inspection / Test Method - Inspection
D2.7 | Trenching and excavation | M | In accordance with NZS 4407 | AP65 Subbase particle size and sand equivalent | Daily | Inspection | RCP and digging checklist | NZS 4407 | Site Engineer | D2.7 - Trenching and excavation | ACTION (W, M, H) - M | Conformance Criteria (What's Required) - In accordance with NZS 4407 | Detail - AP65 Subbase particle size and sand equivalent | Frequency - Daily | Inspection / Test Method - Inspection | Verification Records - RCP and digging checklist | Standard - NZS 4407 | Signatory - Site Engineer | Verification Records - Photos
D2.9.1 | Pressure testing CHAR(AMP) disinfection (1) | H | AS/NZS 2566:2 Section 6.3 | pressure testing of the new PE main | Prior to link in | Testing | Test records | AS/NZS 2566:2 Section 6.3 | Engineers Representative | D2.9.1 - Pressure testing CHAR(AMP) disinfection (1) | ACTION (W, M, H) - H | Conformance Criteria (What's Required) - AS/NZS 2566:2 Section 6.3 | Detail - pressure testing of the new PE main | Frequency - Prior to link in | Inspection / Test Method - Testing | Verification Records - Test records | Standard - AS/NZS 2566:2 Section 6.3 | Signatory - Engineers Representative | Standard - AS/NZS 4129
D2.9.1 | Pressure testing CHAR(AMP) disinfection (2) | H | NZS 4404:2004 Appendix C AS/NZS 2566:2 Section 7 | Disinfection of the new PE main | Prior to link in | Testing | Test records | NZS 4404:2004 Appendix C AS/NZS 2566:2 Section 7 | Engineers Representative | D2.9.1 - Pressure testing CHAR(AMP) disinfection (2) | ACTION (W, M, H) - H | Conformance Criteria (What's Required) - NZS 4404:2004 Appendix C AS/NZS 2566:2 Section 7 | Detail - Disinfection of the new PE main | Frequency - Prior to link in | Inspection / Test Method - Testing | Verification Records - Test records | Standard - NZS 4404:2004 Appendix C AS/NZS 2566:2 Section 7 | Signatory - Engineers Representative | Signatory - Site Engineer
D1.3.3 | Engineer's inspections | H | Inspection report | Enginer's inspection for pipe, concrete pre pour, pre sealing | As required | Inspection | Email |  | Engineers Representative | D1.3.3 - Engineer's inspections | ACTION (W, M, H) - H | Conformance Criteria (What's Required) - Inspection report | Detail - Enginer's inspection for pipe, concrete pre pour, pre sealing | Frequency - As required | Inspection / Test Method - Inspection | Verification Records - Email | Standard - | Signatory - Engineers Representative | D8.3 D8.4 - Lateral connection to house no#4 Waihopai Street
C1.18 | Surface Reinstatement (1) | H | Engineer's Approval | Mark out the trench including overcuts | Prior to surfacing | Inspection | Email |  | Engineers Representative | C1.18 - Surface Reinstatement (1) | ACTION (W, M, H) - H | Conformance Criteria (What's Required) - Engineer's Approval | Detail - Mark out the trench including overcuts | Frequency - Prior to surfacing | Inspection / Test Method - Inspection | Verification Records - Email | Standard - | Signatory - Engineers Representative | ACTION (W, M, H) - W
C1.18 | Surface Reinstatement (2) | H | NDM testing | Provide NDM test results for AP65 and AP40 layers | Prior to surfacing | Testing | Test records |  | Engineers Representative | C1.18 - Surface Reinstatement (2) | ACTION (W, M, H) - H | Conformance Criteria (What's Required) - NDM testing | Detail - Provide NDM test results for AP65 and AP40 layers | Frequency - Prior to surfacing | Inspection / Test Method - Testing | Verification Records - Test records | Standard - | Signatory - Engineers Representative | Conformance Criteria (What's Required) - The min depth of the connection 700mm in the road and 300mm to 375mm below the GL at the boundary to the top of the toby, to be checked and witnessed by site rep.
Detail - As per fig.W20 of sheet 17 and specifications in D8.3 and D8.4
Frequency - Per each connection
Inspection / Test Method - Inspection
Verification Records - Photos
Standard - AS/NZS 4129
Signatory - Site Engineer
D8.3 D8.4 - Lateral connection to house no#7 Waihopai Street
ACTION (W, M, H) - W
Conformance Criteria (What's Required) - The min depth of the connection 700mm in the road and 300mm to 375mm below the GL at the boundary to the top of the toby, to be checked and witnessed by site rep.
Detail - As per fig.W20 of sheet 17 and specifications in D8.3 and D8.4
Frequency - Per each connection
Inspection / Test Method - Inspection
Verification Records - Photos
Standard - AS/NZS 4129
Signatory - Site Engineer
D8.3 D8.4 - Lateral connection to house no#8 Waihopai Street
ACTION (W, M, H) - W
Conformance Criteria (What's Required) - The min depth of the connection 700mm in the road and 300mm to 375mm below the GL at the boundary to the top of the toby, to be checked and witnessed by site rep.
Detail - As per fig.W20 of sheet 17 and specifications in D8.3 and D8.4
Frequency - Per each connection
Inspection / Test Method - Inspection
Verification Records - Photos
Standard - AS/NZS 4129
Signatory - Site Engineer
D8.3 D8.4 - Lateral connection to house no#18 Waihopai Street
ACTION (W, M, H) - W
Conformance Criteria (What's Required) - The min depth of the connection 700mm in the road and 300mm to 375mm below the GL at the boundary to the top of the toby, to be checked and witnessed by site rep.
Detail - As per fig.W20 of sheet 17 and specifications in D8.3 and D8.4
Frequency - Per each connection
Inspection / Test Method - Inspection
Verification Records - Photos
Standard - AS/NZS 4129
Signatory - Site Engineer
D5.5 - Fire Hydrant WAIHOPAI FH01 at CH90 (1)
ACTION (W, M, H) - W
Conformance Criteria (What's Required) - Hydrant outlet is between 200mm CHAR(AMP) 400mm from the finished ground level
Detail - The fire hydrant should be installed in accordance with the standard drawing details in sheet 17 fig.W1. section 3 of NZS 4522.
Frequency - Per each hydrant
Inspection / Test Method - Inspection
Verification Records - Photos
Standard - NZS 4522
Signatory - Site Engineer
D5.5 - Fire Hydrant WAIHOPAI FH01 at CH90 (2)
ACTION (W, M, H) - W
Conformance Criteria (What's Required) - Surface box finish
Detail - cast iron valve box to be flush with the finished surface level.
Frequency - Per each hydrant
Inspection / Test Method - Inspection
Verification Records - Photos
Standard - NZS 4522
Signatory - Site Engineer
D5.5 - Fire Hydrant WAIHOPAI FH01 at CH90 (3)
ACTION (W, M, H) - W
Conformance Criteria (What's Required) - Paint marking, RRPM and Hydrant marker
Detail - Hydrant paint markings as per NZS4501:1972 and as per detail W18, marker post as per detail W11
Frequency - Per each hydrant
Inspection / Test Method - Inspection
Verification Records - Photos
Standard - NZS 4522
Signatory - Site Engineer
- Link in at intersection of Waihopai Street and High Street (1)
ACTION (W, M, H) - W
Conformance Criteria (What's Required) - Manifold bolts to be torqued to manufacture's specification, to be checked and witnessed by the Site representative before backfilling.
Detail - PE to DI connection to be done as per the detail I in sheet 16 of the drawing
Frequency - Before backfilling
Inspection / Test Method - Inspection
Verification Records - Photos
Standard -
Signatory - Site Engineer
- Link in at intersection of Waihopai Street and High Street (2)
ACTION (W, M, H) - W
Conformance Criteria (What's Required) - Thrust protection to be constructed (x2)
Detail - As per detail I in sheet 16 and typical details as per sheet 18
Frequency - Before backfilling
Inspection / Test Method - Inspection
Verification Records - Photos
Standard -
Signatory - Site Engineer
D8.3 D8.4 - Lateral connection to house no#11 Waihopai Street needs confirmation
ACTION (W, M, H) - W
Conformance Criteria (What's Required) - The min depth of the connection 700mm in the road and 300mm to 375mm below the GL at the boundary to the top of the toby, to be checked and witnessed by site rep.
Detail - As per fig.W20 of sheet 17 and specifications in D8.3 and D8.4
Frequency - Per each connection
Inspection / Test Method - Inspection
Verification Records - Photos
Standard - AS/NZS 4129
Signatory - Engineers Representative
D8.3 D8.4 - Lateral connection to house no#22 Waihopai Street
ACTION (W, M, H) - W
Conformance Criteria (What's Required) - The min depth of the connection 700mm in the road and 300mm to 375mm below the GL at the boundary to the top of the toby, to be checked and witnessed by site rep.
Detail - As per fig.W20 of sheet 17 and specifications in D8.3 and D8.4
Frequency - Per each connection
Inspection / Test Method - Inspection
Verification Records - Photos
Standard - AS/NZS 4129
Signatory - Site Engineer
D5.4.2 - Isolation Valve WAIHOPAI-HIGH CH126 (1)
ACTION (W, M, H) - W
Conformance Criteria (What's Required) - Spindle height to be max 600mm from surface
Detail - The valve should be installed in accordance with the standard drawing details in sheet 17 fig.W4 CHAR(AMP) W9
Frequency - Per each valve
Inspection / Test Method - Inspection
Verification Records - Photos
Standard -
Signatory - Site Engineer
D5.4.2 - Isolation Valve WAIHOPAI-HIGH CH126 (2)
ACTION (W, M, H) - W
Conformance Criteria (What's Required) - Thrust wall installed
Detail - Thrust wall constructed as per fig.W9 of page 17 of the drawings
Frequency - Per each valve
Inspection / Test Method - Inspection
Verification Records - Photos
Standard -
Signatory - Site Engineer
D5.4.2 - Isolation Valve WAIHOPAI-HIGH CH126 (3)
ACTION (W, M, H) - W
Conformance Criteria (What's Required) - Surface box finish
Detail - cast iron valve box to be flush with the finished surface level.
Frequency - Per each valve
Inspection / Test Method - Inspection
Verification Records - Photos
Standard -
Signatory - Site Engineer
D8.3 D8.4 - Lateral connection to house no#26 Waihopai Street
ACTION (W, M, H) - W
Conformance Criteria (What's Required) - The min depth of the connection 700mm in the road and 300mm to 375mm below the GL at the boundary to the top of the toby, to be checked and witnessed by site rep.
Detail - As per fig.W20 of sheet 17 and specifications in D8.3 and D8.4
Frequency - Per each connection
Inspection / Test Method - Inspection
Verification Records - Photos
Standard - AS/NZS 4129
Signatory - Site Engineer
D8.3 D8.4 - Lateral connection to house no#25 Waihopai Street
ACTION (W, M, H) - W
Conformance Criteria (What's Required) - The min depth of the connection 700mm in the road and 300mm to 375mm below the GL at the boundary to the top of the toby, to be checked and witnessed by site rep.
Detail - As per fig.W20 of sheet 17 and specifications in D8.3 and D8.4
Frequency - Per each connection
Inspection / Test Method - Inspection
Verification Records - Photos
Standard - AS/NZS 4129
Signatory - Site Engineer
D8.3 D8.4 - Lateral connection to house no#29 Waihopai Street
ACTION (W, M, H) - W
Conformance Criteria (What's Required) - The min depth of the connection 700mm in the road and 300mm to 375mm below the GL at the boundary to the top of the toby, to be checked and witnessed by site rep.
Detail - As per fig.W20 of sheet 17 and specifications in D8.3 and D8.4
Frequency - Per each connection
Inspection / Test Method - Inspection
Verification Records - Photos
Standard - AS/NZS 4129
Signatory - Site Engineer
D5.5 - Fire Hydrant WAIHOPAI FH02 at CH178 (1)
ACTION (W, M, H) - W
Conformance Criteria (What's Required) - Hydrant outlet is between 200mm CHAR(AMP) 400mm from the finished ground level
Detail - The fire hydrant should be installed in accordance with the standard drawing details in sheet 17 fig.W1. section 3 of NZS 4522.
Frequency - Per each hydrant
Inspection / Test Method - Inspection
Verification Records - Photos
Standard - NZS 4522
Signatory - Site Engineer
D5.5 - Fire Hydrant WAIHOPAI FH02 at CH178 (2)
ACTION (W, M, H) - W
Conformance Criteria (What's Required) - Surface box finish
Detail - cast iron valve box to be flush with the finished surface level.
Frequency - Per each hydrant
Inspection / Test Method - Inspection
Verification Records - Photos
Standard - NZS 4522
Signatory - Site Engineer
D5.5 - Fire Hydrant WAIHOPAI FH02 at CH178 (3)
ACTION (W, M, H) - W
Conformance Criteria (What's Required) - Paint marking, RRPM and Hydrant marker
Detail - Hydrant paint markings as per NZS4501:1972 and as per detail W18, marker post as per detail W11
Frequency - Per each hydrant
Inspection / Test Method - Inspection
Verification Records - Photos
Standard - NZS 4522
Signatory - Site Engineer
D8.3 D8.4 - Lateral connection to house no#30 Waihopai Street
ACTION (W, M, H) - W
Conformance Criteria (What's Required) - The min depth of the connection 700mm in the road and 300mm to 375mm below the GL at the boundary to the top of the toby, to be checked and witnessed by site rep.
Detail - As per fig.W20 of sheet 17 and specifications in D8.3 and D8.4
Frequency - Per each connection
Inspection / Test Method - Inspection
Verification Records - Photos
Standard - AS/NZS 4129
Signatory - Site Engineer
D8.3 D8.4 - Lateral connection to house no#38 Waihopai Street
ACTION (W, M, H) - W
Conformance Criteria (What's Required) - The min depth of the connection 700mm in the road and 300mm to 375mm below the GL at the boundary to the top of the toby, to be checked and witnessed by site rep.
Detail - As per fig.W20 of sheet 17 and specifications in D8.3 and D8.4
Frequency - Per each connection
Inspection / Test Method - Inspection
Verification Records - Photos
Standard - AS/NZS 4129
Signatory - Site Engineer
D8.3 D8.4 - Lateral connection to house no#33 Waihopai Street
ACTION (W, M, H) - W
Conformance Criteria (What's Required) - The min depth of the connection 700mm in the road and 300mm to 375mm below the GL at the boundary to the top of the toby, to be checked and witnessed by site rep.
Detail - As per fig.W20 of sheet 17 and specifications in D8.3 and D8.4
Frequency - Per each connection
Inspection / Test Method - Inspection
Verification Records - Photos
Standard - AS/NZS 4129
Signatory - Site Engineer
- Link in at intersection of Waihopai and Terrace Streets (1)
ACTION (W, M, H) - W
Conformance Criteria (What's Required) - Manifold bolts to be torqued to manufacture's specification, to be checked and witnessed by the Site representative before backfilling.
Detail - PE to DI connection to be done as per the detail J in sheet 16 of the drawing
Frequency - Before backfilling
Inspection / Test Method - Inspection
Verification Records - Photos
Standard -
Signatory - Site Engineer
- Link in at intersection of Waihopai and Terrace Streets (2)
ACTION (W, M, H) - W
Conformance Criteria (What's Required) - Thrust protection to be constructed (x2)
Detail - As per detail J in sheet 16 and typical details as per sheet 18
Frequency - Before backfilling
Inspection / Test Method - Inspection
Verification Records - Photos
Standard -
Signatory - Site Engineer
- Capping of existing tees to blank abandoned ends. Intersection of Waihopai and Terrace Streets
ACTION (W, M, H) - W
Conformance Criteria (What's Required) - Tee ends blanked and thrust protected
Detail - As per typical details in sheet 18
Frequency - per connection
Inspection / Test Method - Inspection
Verification Records - Photos
Standard - AS/NZS 4130
Signatory - Site Engineer
D5.4.2 - Isolation Valve WAIHOPAI-TERRACE CH238 (1)
ACTION (W, M, H) - W
Conformance Criteria (What's Required) - Spindle height to be max 600mm from surface
Detail - The valve should be installed in accordance with the standard drawing details in sheet 17 fig.W4 CHAR(AMP) W9
Frequency - Per each valve
Inspection / Test Method - Inspection
Verification Records - Photos
Standard -
Signatory - Site Engineer
D5.4.2 - Isolation Valve WAIHOPAI-TERRACE CH238 (2)
ACTION (W, M, H) - W
Conformance Criteria (What's Required) - Thrust wall installed
Detail - Thrust wall constructed as per fig.W9 of page 17 of the drawings
Frequency - Per each valve
Inspection / Test Method - Inspection
Verification Records - Photos
Standard -
Signatory - Site Engineer
D5.4.2 - Isolation Valve WAIHOPAI-TERRACE CH238 (3)
ACTION (W, M, H) - W
Conformance Criteria (What's Required) - Surface box finish
Detail - cast iron valve box to be flush with the finished surface level.
Frequency - Per each valve
Inspection / Test Method - Inspection
Verification Records - Photos
Standard -
Signatory - Site Engineer
D8.3 D8.4 - Lateral connection to house no#42 Waihopai Street
ACTION (W, M, H) - W
Conformance Criteria (What's Required) - The min depth of the connection 700mm in the road and 300mm to 375mm below the GL at the boundary to the top of the toby, to be checked and witnessed by site rep.
Detail - As per fig.W20 of sheet 17 and specifications in D8.3 and D8.4
Frequency - Per each connection
Inspection / Test Method - Inspection
Verification Records - Photos
Standard - AS/NZS 4129
Signatory - Site Engineer
D8.3 D8.4 - Lateral connection to house no#46 Waihopai Street
ACTION (W, M, H) - W
Conformance Criteria (What's Required) - The min depth of the connection 700mm in the road and 300mm to 375mm below the GL at the boundary to the top of the toby, to be checked and witnessed by site rep.
Detail - As per fig.W20 of sheet 17 and specifications in D8.3 and D8.4
Frequency - Per each connection
Inspection / Test Method - Inspection
Verification Records - Photos
Standard - AS/NZS 4129
Signatory - Site Engineer
D8.3 D8.4 - Lateral connection to house no#52 Waihopai Street
ACTION (W, M, H) - W
Conformance Criteria (What's Required) - The min depth of the connection 700mm in the road and 300mm to 375mm below the GL at the boundary to the top of the toby, to be checked and witnessed by site rep.
Detail - As per fig.W20 of sheet 17 and specifications in D8.3 and D8.4
Frequency - Per each connection
Inspection / Test Method - Inspection
Verification Records - Photos
Standard - AS/NZS 4129
Signatory - Site Engineer
D5.5 - Fire Hydrant WAIHOPAI FH03 at CH285 (1)
ACTION (W, M, H) - W
Conformance Criteria (What's Required) - Hydrant outlet is between 200mm CHAR(AMP) 400mm from the finished ground level
Detail - The fire hydrant should be installed in accordance with the standard drawing details in sheet 17 fig.W1. section 3 of NZS 4522.
Frequency - Per each hydrant
Inspection / Test Method - Inspection
Verification Records - Photos
Standard - NZS 4522
Signatory - Site Engineer
D5.5 - Fire Hydrant WAIHOPAI FH03 at CH285 (2)
ACTION (W, M, H) - W
Conformance Criteria (What's Required) - Surface box finish
Detail - cast iron valve box to be flush with the finished surface level.
Frequency - Per each hydrant
Inspection / Test Method - Inspection
Verification Records - Photos
Standard - NZS 4522
Signatory - Site Engineer
D5.5 - Fire Hydrant WAIHOPAI FH03 at CH285 (3)
ACTION (W, M, H) - W
Conformance Criteria (What's Required) - Paint marking, RRPM and Hydrant marker
Detail - Hydrant paint markings as per NZS4501:1972 and as per detail W18, marker post as per detail W11
Frequency - Per each hydrant
Inspection / Test Method - Inspection
Verification Records - Photos
Standard - NZS 4522
Signatory - Site Engineer
D8.3 D8.4 - Lateral connection to house no#53 Waihopai Street
ACTION (W, M, H) - W
Conformance Criteria (What's Required) - The min depth of the connection 700mm in the road and 300mm to 375mm below the GL at the boundary to the top of the toby, to be checked and witnessed by site rep.
Detail - As per fig.W20 of sheet 17 and specifications in D8.3 and D8.4
Frequency - Per each connection
Inspection / Test Method - Inspection
Verification Records - Photos
Standard - AS/NZS 4129
Signatory - Site Engineer
D8.3 D8.4 - Lateral connection to house no#54 Waihopai Street
ACTION (W, M, H) - W
Conformance Criteria (What's Required) - The min depth of the connection 700mm in the road and 300mm to 375mm below the GL at the boundary to the top of the toby, to be checked and witnessed by site rep.
Detail - As per fig.W20 of sheet 17 and specifications in D8.3 and D8.4
Frequency - Per each connection
Inspection / Test Method - Inspection
Verification Records - Photos
Standard - AS/NZS 4129
Signatory - Site Engineer
D8.3 D8.4 - Lateral connection to house no#58 Waihopai Street
ACTION (W, M, H) - W
Conformance Criteria (What's Required) - The min depth of the connection 700mm in the road and 300mm to 375mm below the GL at the boundary to the top of the toby, to be checked and witnessed by site rep.
Detail - As per fig.W20 of sheet 17 and specifications in D8.3 and D8.4
Frequency - Per each connection
Inspection / Test Method - Inspection
Verification Records - Photos
Standard - AS/NZS 4129
Signatory - Site Engineer
- Link in at intersection of Waihopai Street and Lamond Street West (1)
ACTION (W, M, H) - W
Conformance Criteria (What's Required) - Manifold bolts to be torqued to manufacture's specification, to be checked and witnessed by the Site representative before backfilling.
Detail - PE to DI connection to be done as per the detail I in sheet 16 of the drawing
Frequency - Before backfilling
Inspection / Test Method - Inspection
Verification Records - Photos
Standard -
Signatory - Site Engineer
- Link in at intersection of Waihopai Street and Lamond Street West (2)
ACTION (W, M, H) - W
Conformance Criteria (What's Required) - Thrust protection to be constructed (x2)
Detail - As per detail I in sheet 16 and typical details as per sheet 18
Frequency - Before backfilling
Inspection / Test Method - Inspection
Verification Records - Photos
Standard -
Signatory - Site Engineer
D8.3 D8.4 - Lateral connection to house no#60 Waihopai Street
ACTION (W, M, H) - W
Conformance Criteria (What's Required) - The min depth of the connection 700mm in the road and 300mm to 375mm below the GL at the boundary to the top of the toby, to be checked and witnessed by site rep.
Detail - As per fig.W20 of sheet 17 and specifications in D8.3 and D8.4
Frequency - Per each connection
Inspection / Test Method - Inspection
Verification Records - Photos
Standard - AS/NZS 4129
Signatory - Site Engineer
D5.4.2 - Isolation Valve WAIHOPAI-LAMOND CH347 (1)
ACTION (W, M, H) - W
Conformance Criteria (What's Required) - Spindle height to be max 600mm from surface
Detail - The valve should be installed in accordance with the standard drawing details in sheet 17 fig.W4 CHAR(AMP) W9
Frequency - Per each valve
Inspection / Test Method - Inspection
Verification Records - Photos
Standard -
Signatory - Site Engineer
D5.4.2 - Isolation Valve WAIHOPAI-LAMOND CH347 (2)
ACTION (W, M, H) - W
Conformance Criteria (What's Required) - Thrust wall installed
Detail - Thrust wall constructed as per fig.W9 of page 17 of the drawings
Frequency - Per each valve
Inspection / Test Method - Inspection
Verification Records - Photos
Standard -
Signatory - Site Engineer
D5.4.2 - Isolation Valve WAIHOPAI-LAMOND CH347 (3)
ACTION (W, M, H) - W
Conformance Criteria (What's Required) - Surface box finish
Detail - cast iron valve box to be flush with the finished surface level.
Frequency - Per each valve
Inspection / Test Method - Inspection
Verification Records - Photos
Standard -
Signatory - Site Engineer
D8.3 D8.4 - Lateral connection to house no#62 Waihopai Street
ACTION (W, M, H) - W
Conformance Criteria (What's Required) - The min depth of the connection 700mm in the road and 300mm to 375mm below the GL at the boundary to the top of the toby, to be checked and witnessed by site rep.
Detail - As per fig.W20 of sheet 17 and specifications in D8.3 and D8.4
Frequency - Per each connection
Inspection / Test Method - Inspection
Verification Records - Photos
Standard - AS/NZS 4129
Signatory - Site Engineer
D8.3 D8.4 - Lateral connection to house no#64 Waihopai Street
ACTION (W, M, H) - W
Conformance Criteria (What's Required) - The min depth of the connection 700mm in the road and 300mm to 375mm below the GL at the boundary to the top of the toby, to be checked and witnessed by site rep.
Detail - As per fig.W20 of sheet 17 and specifications in D8.3 and D8.4
Frequency - Per each connection
Inspection / Test Method - Inspection
Verification Records - Photos
Standard - AS/NZS 4129
Signatory - Site Engineer
D8.3 D8.4 - Lateral connection to house no#71 Waihopai Street
ACTION (W, M, H) - W
Conformance Criteria (What's Required) - The min depth of the connection 700mm in the road and 300mm to 375mm below the GL at the boundary to the top of the toby, to be checked and witnessed by site rep.
Detail - As per fig.W20 of sheet 17 and specifications in D8.3 and D8.4
Frequency - Per each connection
Inspection / Test Method - Inspection
Verification Records - Photos
Standard - AS/NZS 4129
Signatory - Site Engineer
D8.3 D8.4 - Lateral connection to house no#66 Waihopai Street
ACTION (W, M, H) - W
Conformance Criteria (What's Required) - The min depth of the connection 700mm in the road and 300mm to 375mm below the GL at the boundary to the top of the toby, to be checked and witnessed by site rep.
Detail - As per fig.W20 of sheet 17 and specifications in D8.3 and D8.4
Frequency - Per each connection
Inspection / Test Method - Inspection
Verification Records - Photos
Standard - AS/NZS 4129
Signatory - Site Engineer
D8.3 D8.4 - Lateral connection to house no#70 Waihopai Street
ACTION (W, M, H) - W
Conformance Criteria (What's Required) - The min depth of the connection 700mm in the road and 300mm to 375mm below the GL at the boundary to the top of the toby, to be checked and witnessed by site rep.
Detail - As per fig.W20 of sheet 17 and specifications in D8.3 and D8.4
Frequency - Per each connection
Inspection / Test Method - Inspection
Verification Records - Photos
Standard - AS/NZS 4129
Signatory - Site Engineer
D5.5 - Fire Hydrant WAIHOPAI FH04 at CH393 (1)
ACTION (W, M, H) - W
Conformance Criteria (What's Required) - Hydrant outlet is between 200mm CHAR(AMP) 400mm from the finished ground level
Detail - The fire hydrant should be installed in accordance with the standard drawing details in sheet 17 fig.W1. section 3 of NZS 4522.
Frequency - Per each hydrant
Inspection / Test Method - Inspection
Verification Records - Photos
Standard - NZS 4522
Signatory - Site Engineer
D5.5 - Fire Hydrant WAIHOPAI FH04 at CH393 (2)
ACTION (W, M, H) - W
Conformance Criteria (What's Required) - Surface box finish
Detail - cast iron valve box to be flush with the finished surface level.
Frequency - Per each hydrant
Inspection / Test Method - Inspection
Verification Records - Photos
Standard - NZS 4522
Signatory - Site Engineer
D5.5 - Fire Hydrant WAIHOPAI FH04 at CH393 (3)
ACTION (W, M, H) - W
Conformance Criteria (What's Required) - Paint marking, RRPM and Hydrant marker
Detail - Hydrant paint markings as per NZS4501:1972 and as per detail W18, marker post as per detail W11
Frequency - Per each hydrant
Inspection / Test Method - Inspection
Verification Records - Photos
Standard - NZS 4522
Signatory - Site Engineer
D8.3 D8.4 - Lateral connection to house no#75 Waihopai Street
ACTION (W, M, H) - W
Conformance Criteria (What's Required) - The min depth of the connection 700mm in the road and 300mm to 375mm below the GL at the boundary to the top of the toby, to be checked and witnessed by site rep.
Detail - As per fig.W20 of sheet 17 and specifications in D8.3 and D8.4
Frequency - Per each connection
Inspection / Test Method - Inspection
Verification Records - Photos
Standard - AS/NZS 4129
Signatory - Site Engineer
D8.3 D8.4 - Lateral connection to house no#74 Waihopai Street
ACTION (W, M, H) - W
Conformance Criteria (What's Required) - The min depth of the connection 700mm in the road and 300mm to 375mm below the GL at the boundary to the top of the toby, to be checked and witnessed by site rep.
Detail - As per fig.W20 of sheet 17 and specifications in D8.3 and D8.4
Frequency - Per each connection
Inspection / Test Method - Inspection
Verification Records - Photos
Standard - AS/NZS 4129
Signatory - Site Engineer
D8.3 D8.4 - Lateral connection to house no#78 Waihopai Street
ACTION (W, M, H) - W
Conformance Criteria (What's Required) - The min depth of the connection 700mm in the road and 300mm to 375mm below the GL at the boundary to the top of the toby, to be checked and witnessed by site rep.
Detail - As per fig.W20 of sheet 17 and specifications in D8.3 and D8.4
Frequency - Per each connection
Inspection / Test Method - Inspection
Verification Records - Photos
Standard - AS/NZS 4129
Signatory - Site Engineer