## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-flat |  |  | checklist | Exposed Areas |  |  |  |  | Yes | Roof Tops & Exposed Areas | 22ad53ed-09d3-4e26-963a-f35f670c311e
checkpoint-status |  |  | checkpoint | Area accessible & ready (If failed please take a photo)
checkpoint-status |  |  | checkpoint | Surface has been checked and confirmed acceptable
checkpoint-status |  |  | checkpoint | Has a bucket test been completed by others to ensure compliance falls to waste
label | ac5cf337-95cb-57f3-bbf9-a1783e940f9c |  | note | GCP Silcor 575 LB Floors 1.5mm DFT
holdpoint |  |  | signoff | Signed by RCC, Tight Seal
checkpoint-status |  |  | checkpoint | Primer (Ensure photo is taken)
checkpoint-status |  |  | checkpoint | Correct curing time allowed 1hr (Primer)
checkpoint-status |  |  | checkpoint | Ensure joints are treated in accordance with post completion movement tolerances
checkpoint-status |  |  | checkpoint | Caulking Preparation
checkpoint-status |  |  | checkpoint | 1st Coat (Ensure photo is taken)
checkpoint-status |  |  | checkpoint | Correct curing time allowed 12hr (1st Coat)
checkpoint-status |  |  | checkpoint | 2nd Coat (Ensure photo is taken)
checkpoint-status |  |  | checkpoint | Correct curing time allowed 12hr (2nd Coat)
checkpoint-status |  |  | checkpoint | Detailed areas such as pipe penetrations, pits, joints, pile capping installed as per specification
checkpoint-status |  |  | checkpoint | Application to correct DFT (Ensure photo is taken)
checkpoint-status |  |  | checkpoint | Correct curing time allowed 12hr (Silcor Top Coat 75)
holdpoint |  |  | signoff | Signed by RCC & Tight Seal
checklist-sectioned |  |  | checklist | Internal Liquid Waterproofing ITP |  |  |  |  | Yes | Internal Liquid Waterproofing ITP | 5d0e10db-18ce-4ae6-9d19-6b2fcfe3467a
checkpoint-group |  |  | section | Below screed membrane
checkpoint-status |  |  | checkpoint | Area accessible and ready (If failed please take a photo)
checkpoint-status |  |  | checkpoint | Surface has been checked and confirmed acceptable
checkpoint-status |  |  | checkpoint | Has a bucket test been completed by others to ensure compliance falls to waste
holdpoint |  |  | signoff | Signed by RCC, Tight Seal
checkpoint-status |  |  | checkpoint | Ensure moisture content of slab is under 4.5% (Ensure photo is taken)
label | 035b1e04-b468-524f-9e13-46e458c7fd19 |  | note | GCP Silcor 560 Floors 1.5mm DFT GCP Silcor 145 Walls 1.0mm DFT
checkpoint-status |  |  | checkpoint | Primer (Ensure photo is taken) - SILCOR Primer BS
checkpoint-status |  |  | checkpoint | Correct curing time allowed 1hr (Primer)
checkpoint-status |  |  | checkpoint | Angles installed
checkpoint-status |  |  | checkpoint | Caulking Preparation
checkpoint-status |  |  | checkpoint | 1st Coat (Ensure photo is taken)
checkpoint-status |  |  | checkpoint | Correct curing time allowed 12hr (1st Coat)
checkpoint-status |  |  | checkpoint | 2nd Coat (Ensure photo is taken)
checkpoint-status |  |  | checkpoint | Correct curing time allowed 12hr (2nd Coat)
checkpoint-status |  |  | checkpoint | Tie / Broadcast coat applied (Ensure photo is taken) - Silcor 575 - Sand will be applied with Tie coat
checkpoint-status |  |  | checkpoint | Correct curing time allowed 12hr (Tie / Broadcast coat)
checkpoint-status |  |  | checkpoint | Detailed areas such as pipe penetrations, pits, joints, pile capping installed as per specification
checkpoint-status |  |  | checkpoint | Application to correct DFT (Ensure photo is taken) DFT required for walls (1.0mm) and floor (1.5mm)
checkpoint-status |  |  | checkpoint | Flood Test 24 hours (Ensure photo is taken)
holdpoint |  |  | signoff | Signed by RCC & Tight Seal
checklist-flat |  |  | checklist | Epoxy Flooring |  |  |  |  | Yes | Epoxy Flooring | 6cc73bc6-03a3-4718-a1a1-ee6c9322700c
checkpoint-status |  |  | checkpoint | Area accessible & ready (If failed please take a photo)
checkpoint-status |  |  | checkpoint | Surface has been checked and confirmed acceptable
checkpoint-status |  |  | checkpoint | Has a bucket test been completed by others to ensure compliance falls to waste
label | 0a08b699-2bc3-57ce-bac5-6f6a6ab6bab9 |  | note | Hychem SF32
holdpoint |  |  | signoff | Signed by RCC, Tight Seal
checkpoint-status |  |  | checkpoint | Coving installed
checkpoint-status |  |  | checkpoint | Primer (Ensure photo is taken)
checkpoint-status |  |  | checkpoint | Correct curing time allowed 12 hr (Primer)
checkpoint-status |  |  | checkpoint | 1st Coat (Ensure photo is taken)
checkpoint-status |  |  | checkpoint | Correct curing time allowed 12hr (1st Coat)
checkpoint-status |  |  | checkpoint | Ensure the correct grit has been installed to suit R value for project
checkpoint-status |  |  | checkpoint | 2nd Coat (Ensure photo is taken)
checkpoint-status |  |  | checkpoint | Correct curing time allowed 12hr (2nd Coat)
checkpoint-status |  |  | checkpoint | Detailed areas such as pipe penetrations, pits, joints, pile capping installed as per specification
holdpoint |  |  | signoff | Signed by RCC, Tight Seal
checklist-flat |  |  | checklist | Planter Boxes |  |  |  |  | Yes | Exposed Area & Planter Boxes (Spray) | b2df52c9-f90a-45bc-b4fe-67497691fef7
checkpoint-status |  |  | checkpoint | Area accessible & ready (If failed please take a photo)
checkpoint-status |  |  | checkpoint | Surface has been checked and confirmed acceptable
checkpoint-status |  |  | checkpoint | Has a bucket test been completed by others to ensure compliance falls to waste
label | fbbfeb37-fdac-5a94-ae08-0051b98d2a99 |  | note | Chemspray 790 1.5mm DFT
holdpoint |  |  | signoff | Signed by RCC, Tight Seal
checkpoint-status |  |  | checkpoint | Primer (Ensure photo is taken)
checkpoint-status |  |  | checkpoint | Correct curing time allowed 1hr (Primer)
checkpoint-status |  |  | checkpoint | Ensure joints are treated in accordance with post completion movement tolerances
checkpoint-status |  |  | checkpoint | Caulking Preparation
checkpoint-status |  |  | checkpoint | 1st Coat (Ensure photo is taken)
checkpoint-status |  |  | checkpoint | Correct curing time allowed 1hr (1st Coat)
checkpoint-status |  |  | checkpoint | Detailed areas such as pipe penetrations, pits, joints, pile capping installed as per specification
checkpoint-status |  |  | checkpoint | Application to correct DFT (Ensure photo is taken)
checkpoint-status |  |  | checkpoint | Correct curing time allowed 12hr (Silcor Top Coat 75)
holdpoint |  |  | signoff | Signed by RCC, Tight Seal
checklist-flat |  |  | checklist | External Step Downs |  |  |  |  | Yes | External Step Downs | b3ed8b5c-cefb-4d05-bf7e-59c768d539c0
checkpoint-status |  |  | checkpoint | Area accessible & ready (If failed please take a photo)
checkpoint-status |  |  | checkpoint | Surface has been checked and confirmed acceptable
checkpoint-status |  |  | checkpoint | Has a bucket test been completed by others to ensure compliance falls to waste
label | 9a977ee9-c93e-51f6-9b1f-19ee5f0b71f7 |  | note | GCP Silcor 560 Floors 1.5mm DFT
checkpoint-status |  |  | checkpoint | Angles have been installed
checkpoint-status |  |  | checkpoint | Primer (Ensure photo is taken)
checkpoint-status |  |  | checkpoint | Correct curing time allowed 1hr (Primer)
checkpoint-status |  |  | checkpoint | Ensure joints are treated in accordance with post completion movement tolerances
checkpoint-status |  |  | checkpoint | Caulking Preparation
checkpoint-status |  |  | checkpoint | 1st Coat (Ensure photo is taken)
checkpoint-status |  |  | checkpoint | Correct curing time allowed 12hr (1st Coat)
checkpoint-status |  |  | checkpoint | 2nd Coat (Ensure photo is taken)
checkpoint-status |  |  | checkpoint | Correct curing time allowed 12hr (2nd Coat)
checkpoint-status |  |  | checkpoint | Detailed areas such as pipe penetrations, pits, joints, pile capping installed as per specification
checkpoint-status |  |  | checkpoint | Application to correct DFT (Ensure photo is taken)
checkpoint-status |  |  | checkpoint | Correct curing time allowed 12hr (UV Stable)
checkpoint-status |  |  | checkpoint | Ensure all penetrations by others are sealed to ensure works are not compromised.
holdpoint |  |  | signoff | Signed by RCC & Tight Seal
checklist-flat |  |  | checklist | Expansion Joints |  |  |  |  | Yes | Expansion Joints | d4c3c2ce-5b97-4cc3-a453-b83de6836b36
checkpoint-status |  |  | checkpoint | Area accessible & ready (If failed please take a photo)
checkpoint-status |  |  | checkpoint | Surface has been checked and confirmed acceptable
checkpoint-status |  |  | checkpoint | Has a bucket test been completed by others to ensure compliance falls to waste
checkpoint-status |  |  | checkpoint | Chase floor and install P5
checkpoint-status |  |  | checkpoint | Install IB
label | fdf317d8-bd1f-52ce-a89f-8e09aa0383d3 |  | note | Wolfin IB
checkpoint-status |  |  | checkpoint | Weld strips from P5 to P2 onto Wolfin IB
checkpoint-status |  |  | checkpoint | Projects to signoff on installation (Wolfin)
holdpoint |  |  | signoff | Signed by Wolfin, RCC & Tight Seal
checklist-flat |  |  | checklist | Balcony |  |  |  |  | Yes | External Balcony ITP | fc117b6b-66e4-46da-b392-35647d467fd4
checkpoint-status |  |  | checkpoint | Area accessible and ready (If failed please take a photo)
checkpoint-status |  |  | checkpoint | Surface has been checked and confirmed acceptable
checkpoint-status |  |  | checkpoint | Has a bucket test been completed by others to ensure compliance falls to waste
label | 38c2d4be-cfa0-5c1a-a64e-bf6f50f4eed2 |  | note | GCP Silcor 560 Floors 1.5mm DFT GCP Silcor 145 Walls 1.0mm DFT
holdpoint |  |  | signoff | Signed by RCC & Tight Seal
checkpoint-status |  |  | checkpoint | Primer (Ensure photo is taken)
checkpoint-status |  |  | checkpoint | Correct curing time allowed 1hr (Primer)
checkpoint-status |  |  | checkpoint | Ensure joints are treated in accordance with post completion movement tolerances
checkpoint-status |  |  | checkpoint | Caulking Preparation
checkpoint-status |  |  | checkpoint | 1st Coat (Ensure photo is taken)
checkpoint-status |  |  | checkpoint | Correct curing time allowed 12hr (1st Coat)
checkpoint-status |  |  | checkpoint | 2nd Coat (Ensure photo is taken)
checkpoint-status |  |  | checkpoint | Correct curing time allowed 12hr (2nd Coat)
checkpoint-status |  |  | checkpoint | Detailed areas such as pipe penetrations, pits, joints, pile capping installed as per specification
checkpoint-status |  |  | checkpoint | Application to correct DFT (Ensure photo is taken) DFT required for walls (1.0mm) and floor (1.5mm)
checkpoint-status |  |  | checkpoint | UV Stable top coat applied (Ensure photo is taken)
checkpoint-status |  |  | checkpoint | Correct curing time allowed 12hr (UV Stable)
checkpoint-status |  |  | checkpoint | Ensure all penetrations by others are sealed to ensure works are not compromised.
holdpoint |  |  | signoff | Signed by RCC & Tight Seal