## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist-flat | ITP - Culvert Replacements | itp |  |  |  | Yes | ITP - Culvert Replacements
checkpoint | Preliminary and General - Traffic Management Plan
label | Acceptance Criteria: Approved TMP
label | Test: Inspect
label | Verifying Records: Checklist
label | Frequency: Daily
label | Standard / Specification: TDC Approved TM Plan
label | DNR: Hold
date | Date:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | Preliminary and General - Safe Work Method Statement
label | Acceptance Criteria: Approved SWMS
label | Test: Inspect
label | Verifying Records: Inspect
label | Frequency: Prior to start of work
label | Standard / Specification: Downer Approved SWMS
label | DNR: Hold
date | Date:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | Materials - Material compliance
label | Acceptance Criteria: Ensure all materials compliance and preconstruction documents are reviewed prior to construction
label | Test: Inspect
label | Verifying Records: Copies of all compliance certificates
label | Frequency: Prior to construction
label | Standard / Specification: NZTA F/3
label | DNR: Witness
date | Date:
checkpoint | Preliminary and General - Service Plans & Locate
label | Acceptance Criteria: Marked on site & service plans kept on site. Water, Storm Water, Waste Water, Telecommunications & Power.
label | Test: Inspect
label | Verifying Records: Inspect
label | Frequency: Prior to start of work
label | Standard / Specification: 0
label | DNR: Hold
date | Date:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | Preliminary and General - Notify Local Iwi
label | Acceptance Criteria: Notify Local Iwi to determine whether or not works are in high sensitivity area and require cultural monitor
label | Test: Inspect
label | Verifying Records: Inspect
label | Frequency: Prior to start of work
label | Standard / Specification: 0
label | DNR: Hold
date | Date:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | Preliminary and General - Accidental Discovery of archaeological matter NB: Applicable only when discovery are made during construction activities
label | Acceptance Criteria: Construction supervisor advised by operator
label | • All work within 100m of the site ceased immediately
label | • Site secured to ensure archaeological matter remains undisturbed
label | • Client Rep/Engineer informed by construction Manager"
label | Test: Notification
label | Verifying Records: Notification
label | Frequency: Every archaeological accidental discovery
label | Standard / Specification: 0
label | DNR: Hold
date | Date:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | Preliminary and General - Permit - To Dig
label | Acceptance Criteria: Produce & Handover permit to dig to foreman & crew.
label | Test: Inspect
label | Verifying Records: Inspect
label | Frequency: Per Work Activity
label | Standard / Specification: 0
label | DNR: Hold
date | Date:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | Stormwater Drainage - Trench Width
label | Acceptance Criteria: The minimum trench width shall be 300 mm wider than the external diameter of the collar of the pipe being laid, providing the haunching metal is compacted under and at the sides of the pipe.
label | Test: Measure
label | Verifying Records: Measure
label | Frequency: Continuous
label | Standard / Specification: 0
label | DNR: Witness
date | Date:
checkpoint | Stormwater Drainage - Sub-grade strength
label | Acceptance Criteria: Base of Excavation to be levelled and undisturbed
label | • 50 KPa ≤ 70 mm / blow – no soft raft required
label | • 35-50 KPa – between 100-70 mm/blow
label | • install ‘softground’ (SD344/3) construct on a layer of 50 KPa
label | • Less than 35 KPa - >100 mm/blow – speak to the designer "
label | Test: Scala penetrometer
label | Verifying Records: Scala penetrometer
label | Frequency: Every 17m
label | Standard / Specification: 0
label | DNR: Inspection
date | Date:
checkpoint | Stormwater Drainage - Bedding depth
label | Acceptance Criteria: In accordance with SD344
label | Test: Inspect
label | Verifying Records: Inspect
label | Frequency: Continuous
label | Standard / Specification: In Accordance with TDC Spec
label | DNR: Witness
date | Date:
checkpoint | Stormwater Drainage - Pipe Line and Level
label | Acceptance Criteria: TNZ F/3 Minimum 1 in 80 = 1.25%
label | Test: Measure
label | Verifying Records: Measure
label | Frequency: Continuous
label | Standard / Specification: TNZ F/3: Pipe culvert construction
label | DNR: Inspection
date | Date:
checkpoint | Stormwater Drainage - Pipe cover
label | Acceptance Criteria: Shall be as specified in the CSS Part 4; 750 mm with a minimum grade specified depending on the pipe diameter from Transit Highway Surface Drainage Guide.
label | Test: Measure
label | Verifying Records: Measure
label | Frequency: Daily
label | Standard / Specification: 0
label | DNR: Inspection
date | Date:
checkpoint | Stormwater Drainage - Trench Backfilling/compaction
label | Acceptance Criteria: Indentation < 7mm for fill
label | • Indentation <5mm for subgrade improvement
label | Test: Proof Rolling - Wheel Roller min loading 6259kg /metre width of fill
label | Verifying Records: Proof Rolling - Wheel Roller min loading 6259kg /metre width of fill
label | Frequency: Each layer of fill placed
label | • Max layer thickness 200mm
label | Standard / Specification: 0
label | DNR: Inspection
date | Date:
checkpoint | Pavement - Subbase AP65 construction - compaction
label | Acceptance Criteria: Subbase - mean greater than or equal to 95% and no results below 92%
label | Test: NDM – maximum dry density MDD
label | Verifying Records: NDM Results
label | Frequency: NZS4402:1986 1 test per 1000m3 placed
label | Standard / Specification: NZS4402:1986 Test 6.1.1
label | DNR: Witness
date | Date:
checkpoint | Pavement - Basecourse construction – compaction TNZ B/2
label | Acceptance Criteria: Basecourse – mean greater than or equal to 98% and no result below 95%
label | Test: NDM – maximum dry density MDD
label | Verifying Records: NDM Results
label | Frequency: 5 tests per homogenous lot of up to 1000m2 of laid pavement TNZ B/2:2005 Construction unbound granular pavement layers
label | Standard / Specification: TNZ B/2:2005 Construction unbound granular pavement layers
label | DNR: Inspection
date | Date:
checkpoint | Pavement - Subbase/ Basecourse (including cement treated) construction – deflection
label | Acceptance Criteria: Subbase - a minimum 95th percentile deflection of D0 = 1.7mm and D600 = 0.7mm
label | • Basecourse - a minimum 95th percentile deflection of D0 = 1.2mm and D600 = 0.6mm
label | Test: Benkelman beam or falling weight deflectometer
label | Verifying Records: Benkleman Beam Test Results
label | Frequency: Each lane inner and outer wheel tracks every 10m TNZ T/1 Benkleman Beam Deflection Measurements
label | Standard / Specification: TNZ T/1 Benkleman Beam Deflection Measurements
label | DNR: Hold
date | Date:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | Surfacing - Surface preparation
label | Acceptance Criteria: Sawcut edges in permanent surfaces
label | Test: Visual
label | Verifying Records: Visual
label | Frequency: Prior to sealing
label | Standard / Specification: SNZ HB 2002:2003 Code of Practise for Working in the Road
label | DNR: Inspection
date | Date:
checkpoint | Surfacing - Preparation for sealing / surfacing - Check list App 2
label | Acceptance Criteria: Site Surface inspection By Client/Consultant
label | Test: Visual Inspection
label | Verifying Records: Visual Inspection
label | Frequency: Once
label | Standard / Specification: 0
label | DNR: Inspection
date | Date:
checkpoint | Surfacing - Compaction
label | Acceptance Criteria: Compaction commenced as soon as the asphalt has cooled sufficiently to support rollers weight without undue displacement.
label | • Compaction using vibratory roller and pneumatic tyred roller
label | • NZTA Core Samples: 150 mm nominal dia except where total asphalt layer thickness falls below 40 mm sample can be 100 mm"
label | Test: Lab test
label | Verifying Records: Lab test
label | Frequency: 0
label | Standard / Specification: 0
label | DNR: Inspection
date | Date:
checkpoint | Surfacing - Thickness
label | Acceptance Criteria: Non-structural component of the pavement: the specified layer thickness shall not be less than the average measured thickness of each lot.
label | • Structural component: the average thickness of any individual layer in a lot shall be not less than the specified thickness by more than 10% and the total thickness of any core not more than 5 mm less than that specified.
label | • NB: Where confirmation of asphalt thickness is required, it shall be determined by coring to a recognised random sampling plan.
label | Test: Inspection
label | Verifying Records: Inspection
label | Frequency: As required
label | Standard / Specification: 0
label | DNR: Inspection
date | Date:
checkpoint | Disestablishment - Making the site tidy
label | Acceptance Criteria: The site shall be clean and tidy on completion of work with all surplus material removed
label | Test: At practical completion of works
label | Verifying Records: At practical completion of works
label | Frequency: When project completed
label | Standard / Specification: 0
label | DNR: Inspection
date | Date:
checkpoint | Disestablishment - Project completion walkover
label | Acceptance Criteria: Walk over with Project Coordinator
label | Test: Signed off by Project Coordinator
label | Verifying Records: Signed off by Project Coordinator
label | Frequency: At practical completion of works
label | Standard / Specification: 0
label | DNR: Inspection
date | Date: