## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist-flat | ITP 01 - Partition Walls | [5 empty] | ITP 01 - Partition Walls - Rev A | a7c560ae-c88a-4bf0-976a-cafd31f64e33
checkpoint | 1 - Set out walls
label | Reference Documents - Architect drawings (MQT_ID series) Architect Specification (MQT_IS_SPE_1)
label | Acceptance Criteria - Partition Plan and Partition Wall Details approved by Lendlease.
label | ○ Architectural Specification – 0522 Partitions And Linings Australian Standard: AS/NZS 4600:2005, AS/NS 1170:2002
label | Frequency - Each location
label | Verification Records/Comments - Visual Checklist
label | Inspection By: Subcontractor - S
label | Inspection By: Lendlease - S
checkpoint | 3 - Metal stud wall frame
label | Reference Documents - Architect drawings (MQT_ID series) Architect Specification (MQT_IS_SPE_1)
label | ○ Refer to Lendlease CiDD for All Alerts and Guidelines for Smoke doors and Baffle
label | Acceptance Criteria - Partition Plan and Partition Wall Details approved by Lendlease.
label | ○ Architectural Specification – 0522 Partitions And Linings Studco Wall design & installation manual Volume 3.2 Australian Standard: AS/NZS 4600:2005, AS/NS 1170:2002
label | Frequency - Each location
label | Verification Records/Comments - Visual Checklist
label | Inspection By: Subcontractor - S
label | Inspection By: Lendlease - S
checkpoint | 4 - Noggins
label | Acceptance Criteria - As per scope of work.
label | ○ Studco Wall design & installation manual Volume 3.2 Architectural Specification – 0522 Partitions And Linings Australian Standard: AS/NZS 4600:2005, AS/NS 1170:2002
label | Frequency - Each location
label | Verification Records/Comments - Visual Checklist
label | Inspection By: Subcontractor - S
label | Inspection By: Lendlease - S
checkpoint | 5 - Check no screws in deflection head
label | Acceptance Criteria - No screws in deflection head
label | Frequency - Each location
label | Verification Records/Comments - Visual Checklist
label | Inspection By: Subcontractor - S
label | Inspection By: Lendlease - S
checkpoint | 6 - Service Check for pre-installation of sheets
label | Reference Documents - Service Sign- off checklist
label | Acceptance Criteria - All service checklists are signed off by relevant trades
label | Frequency - Each location
label | Verification Records/Comments - Visual Checklist
label | Inspection By: Subcontractor - S
label | Inspection By: Lendlease - HP
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 7 - Sheet all walls
label | Reference Documents - Architect drawings (MQT_ID series) Architect Specification (MQT_IS_SPE_1)
label | ○ Refer to Lendlease CiDD for All
label | ○ Alerts and Guidelines for Fibre Cement and Smoke doors and Baffle
label | Acceptance Criteria - Partition Plan and Partition Wall Details approved by Lendlease.
label | ○ Check wall types before installation (F/R, Acoustic, Wet Area, PBD etc).
label | ○ Architectural Specification – 0522 Partitions And Linings Boral installation manual revision 2016. Batts insulation installation guide. Australian Standard: AS/NZS 2589.1:1997
label | Frequency - Each location
label | Verification Records/Comments - Visual Checklist
label | Inspection By: Subcontractor - S
label | Inspection By: Lendlease - S
checkpoint | 8 - Caulking
label | Acceptance Criteria - Boral installation manual revision 2016 Australian Standard: AS 1530.4-2014, AS4072.1-2005, AS1157-1972
label | Frequency - Each location
label | Verification Records/Comments - Visual Checklist
label | Inspection By: Subcontractor - S
label | Inspection By: Lendlease - S
checkpoint | 9 - Check insulation in walls
label | Reference Documents - Architect drawings (MQT_ID series) Architect Specification (MQT_IS_SPE_1)
label | Acceptance Criteria - Partition Plan and Partition Wall Details approved by Lendlease.
label | ○ Batts Insulation Installation Guidelines Architectural Specification – 0819 Insulation and Barriers Australian Standard: AS/NZS 4859:1 – 2018, AS/NZS 1530.3 : 1999, AS/NZS1530 Part 1:1994
label | Frequency - Each location
label | Verification Records/Comments - Visual Checklist
label | Inspection By: Subcontractor - S
label | Inspection By: Lendlease - S
checkpoint | 10 - Stopping to walls
label | Reference Documents - Refer to Lendlease CiDD - Alerts and Guidelines for Setting Compounds for Plasterboard
label | Acceptance Criteria - Boral installation manual revision 2016. Australian Standard: AS/NZS 2589.1:1997
label | Frequency - Each location
label | Verification Records/Comments - Visual Checklist
label | Inspection By: Subcontractor - S
label | Inspection By: Lendlease - S
checkpoint | 11 - Sanding to walls
label | Acceptance Criteria - Boral installation manual revision 2016. Australian Standard: AS/NZS 2589.1:1997
label | Frequency - Each location
label | Verification Records/Comments - Visual Checklist
label | Inspection By: Subcontractor - S
label | Inspection By: Lendlease - S
checkpoint | 12 - Clean up / Check walls for patching / Materials Receipt Inspection
label | Reference Documents - Architect drawings (MQT_ID series) Architect Specification (MQT_IS_SPE_1)
label | ○ Refer to ITP No: 5 Incoming Goods
label | Acceptance Criteria - Waste all cleaned. Tools and materials placed well.
label | ○ Partition Plan and Partition Wall Details approved by Lendlease.
label | Frequency - Each location
label | Verification Records/Comments - Visual Checklist
label | Inspection By: Subcontractor - S
label | Inspection By: Lendlease - R
checkpoint-no-status | Comments:
date | Date of Inspection:
text | Carried out by: