## Sheet1
ConQA Team Notes:
Document Title: |  | ITP-059-CIV-Brunt-Supply/Installation of Recycled HDPE Drainage Pipe
ITP Description: |  | Installation of Recycled HDPE Drainage Pipe
Discipline (e.g. CIV/STR/RAIL: |  | CIV
Revision Number: |  | 0
Revision Date: |  | 2023-08-08
ITP created by: |  | Kamel Alshobaki
ITP approved for use by: |  | Jon De Castro
Special Notes to ConQA Team : |  | ITP for Brunt Rd only
Inspection Test Plan: Supply & Installation of Recycled HDPE Drainage Pipe
|  |  | Document No.: ITP-059-CIV-Brunt-Supply/Installation of Recycled HDPE Drainage Pipe | [5 empty] | Revision: | 0
[9 empty] | Date: | 2023-08-08
Legend: HP: Hold Point, HP* Internal Hold Point, WP: Witness Point, IP: Inspection Point, SP: Surveillance Point
Item | Task/Activity Description | Reference | Acceptance Criteria | Inspection / Test |  |  | Responsibility | Verifying Documents | Date Completed | Sign-off
|  |  |  | Method | Frequency | Category
1 | Referenced Documentation
1.1 | Relevant Standards/Specs | AS 2566 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
1.2 | Relevant Standards/Specs | VicRoads Sec 701 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
1.3 | Relevant Standards/Specs | IFC Drawings | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
2 | Preliminaries - Materials
2.1 | Drainage Flexible Pipes | Section 701.08 | Flexible pipes shall be supplied in accordance with 701.08 Prior to incorporating into the Project Works, plastic flexible pipes and fittings, shall obtain a signed Certificate of Conformance verifying that the materials and components comply with the requirements of VR 701 Standard. Buried flexible pipes shall not be used directly under the road pavement area. Enter: Teambinder Material Approval number [free text box] | Document Review | Each lot | HP | Nominated Authority | ConQA Hold Point Release
2.2 | Precast Drainage Pit | Section 705.07 Section 705.04 Section 705.09 | Precast steel reinforced concrete drainage pits shall be manufactured, supplied and installed in accordance with Section 705.07 & 705.09 All concrete shall be manufactured to the concrete mix design registered by VicRoads and comply with the requirements of Section 705.04. Concrete grades shall comply with Table 705.041 Enter: Teambinder Material Approval number [free text box] | Document Review | Each lot | HP | Nominated Authority | ConQA Hold Point Release
2.3 | Cast in Place Drainage Pit | Section 705.06 IFC Drawings | Cast in place drainage pits shall be constructed in accordance with the requirements of Section 705.06 and at the locations and to the dimensions shown on the drawings. | Document Review | Each lot | HP | Nominated Authority | ConQA Hold Point Release
2.4 | Drainage Pit - Step Irons | Section 705.04 Section 705.12 | Step irons shall be manufactured by 13mm steel bar covered with polypropylene plastic in accordance with 705.04 Drainage pits greater than 1.0 m deep shall be fitted with step irons in accordance with Section 705.12 Enter: Teambinder Material Approval number [free text box] | Document Review | Each lot | HP | Nominated Authority | ConQA Hold Point Release
2.5 | Drainage Bedding Material | Section 701.09 | Bedding Material shall be free from perishable matter, lumps and conform with the requirements of Table 701.091 and Table 701.092. Enter: Teambinder Material Approval number [free text box] | Document Review | Each lot | HP | Nominated Authority | ConQA Hold Point Release
2.6 | Drainage Backfill Material | Section 701.09 Section 701.19 | Ordinary and Selected Backfill Material shall be free from perishable matter, lumps and conform with the requirements of Table 701.091 and Table 701.092. Where approved by the Superintendent, culverts in trenches may be backfilled to half the pipe diameter or box culvert height with 3% cement stabilised sand in accordance with Section 701.19 Enter: Teambinder Material Approval number [free text box] | Document Review | Each lot | HP | Nominated Authority | ConQA Hold Point Release
3 | Preliminaries - Procedures & Documentation
3.1 | Subcontractor ITP (where required) | Subcontractor ITP | Subcontractor ITP shall conform with the IFC Drawings & Relevant Standards & Specifications. Attach: Signed-off Subcontractor ITP | Document Review | Each lot | HP* | PE | This ITP Signed Off
3.2 | Check the type, size and class of pipes and other drainage structures to be laid | Work ActivityPack | Check Supplied items are: - To correct spec, type, size and quantity - Defect free, safely stored & prevented from UV Exposure - Markings have been made as required | Visual Review Document | Each lot | IP | Supervisor SE/PE/SPE | This ITP Signed Off
4 | Pre-Construction Activities
4.1 | Survey Set Out - Pits & Pipes | IFC Drawings Section 701.10 | Prior to commencement of excavation for the flexible pipes, the Contractor shall confirm the position of all pipes with the Superintendent/Surveyor. Survey activities undertaken to ensure and validate the plan location, height and line of pits and location, invert level, plan of pipes in accordance with design documentation and VR701.10 | Survey | Each Lot | HP* | PE | This ITP Signed Off
5 | Construction Activities
5.1 | Set out the works for each drainage system | AS 2566 IFC Drawing | Establish Pegs (or equivalent)survry marks to identify location, length, and levels as per design drawings and schedules and check if: - Inlet/outlet heights fit in with natural surface (ie not too high or low) - Inlet/outlet location suitable for water-course (eg no drainage problems) - Pits relocated (through RFI’s) in order to avoid cutting of pipes | Inspection Survey | Each lot | IP | Supervisor SE/PE/SPE | This ITP Signed Off
5.2 | Confirm position of all Drainage line/culverts | VicRoads 701.09 IFC Drawing | Prio to commencement of excavation for the Drainage the contractor shall confirm the position of all drainage line with the Surveyor. | Visual Inspection | Each lot | HP* | Supervisor SE/PE/SPE Surveyor | This ITP Signed Off
5.3 | Excavate trench to the underside of bedding to correct width | AS 2566 IFC Drawing | Width and depth of pipe trench as per AS 2566.1. Refer to right table For other structures, the clear width between structure wall & face of excavation is ≥ 300mm or 1/3 height of excavation face, whichever is greater Trenches > 1.5m deep are either shored or benched The excavation is ≤ 50mm beyond the specified width and depths of the trench For pipes under embankments - the first embankment is constructed to a height ≥ 0.7 times the external dia of the pipe above the top of the bed zone, and for a min lateral distance past the boundary of the trench of 2.5 times the external dia of the pipe - Trenches done after the construct of the embankment to the level of the underside of the Selected Material Layer No welding/ anchor block systems etc. required. This system is just a simple lubrication of the end of pipe. | Inspection | Each lot | IP | Supervisor SE/PE/SPE | This ITP Signed Off
5.4 | Install pipes in accordance to manufacturer’s instructions and design documentations | RPM Installation and Handling Guildelines | Pipe laid from inlet to outlet Pipe support conforming to AS2566 Polypropylene Pipes (Blackmax or StormPro) Correct size and class of pipes are laid with socket end placed upstream Pipe ends cleaned and rubber rings / bands installed as per manufacture’s recommendations Inlet/outlet heights fit in with natural surface (not too high or low) HDPE Pipes to be cleaned, beaded and jointed by suitably qualified personnel. Electrofusion Welding or Butt Welding of pipes permissible. Joints allowed to cool prior to lifting or shifting into position. nchor blocks provided at 3m spacing max., at bends, junctions and where shown on drawings Subsurface drainage installed at the discharge end of pipes Add check lengths as per the minimum required Width to edge of trench, 150mm 300mm above pipe with selected backfill material. | Inspection | Each lot | IP | Supervisor SE/PE/SPE | This ITP Signed Off
5.5 | Verify that completed pipeline against survey marksdesign level and alignments | AS 2566 IFC Drawing | Completed pipeline is inline and within ±200mm of location (plan) Invert level are within 20mm of the design level at any point To be checked at each pit and headwall Horizontal Position for Pits in Kerb to be o +-200mm longitudinally o +-20mm perpendiculat to kerb alignment | Inspection | Each lot | IP | Supervisor SE/PE/SPE | This ITP Signed Off
5.6 | Place and spread haunch, side zone, overlay and backfill embedment, replacement and backfill material,, compact and test to specified densities | VicRoads Spec. Cl. 701.26, 701.20 | Placed in 150mm layers and compact to 95% std compaction If stabilised sand used, the materials been vibrated to obtain complete placement & compaction of material under & around pipe and the placed stabilised materials are firm a day after placement If 10/14mm aggregates used, the materials been vibrated to obtain complete placement & compaction of material under & around pipes. A minimum of 20% of all lots for each culvert shall be tested. | Inspection | Each lot | IP | Supervisor SE/PE/SPE | This ITP Signed Off
5.7 | Inlet/Outlet Structures | VicRoads Spec. 701.23 | Refer to Pit supply & installation ITP | Inspection | Each lot | IP | Supervisor SE/PE/SPE | This ITP Signed Off
5.8 | Flushing System | VicRoads Spec. Cl. 701.26 | Each Drainage/Culvert line is to be flushed clean from end to end on completion. and maintained in proper working order. | Inspection | Each lot | HP* | Nominated Authority | This ITP Signed Off
5.9 | Engage pipe inspection video subcontractor to take footage of all completed new pipes. | VicRoads Spec 701.28 | All Drainage line constructed shall be inspected after completion of earthworks to subgrade level and prior to construction of pavement layers, by independent Testing Organization using closed circuit television(CCTV). The report shall be provided to the Nominated Authority. Attach: CCTV Report | Inspection | Each lot | HP | Nominated Authority | ConQA Hold Point Release
6 | Post-construction / Post-installation Activities
6.1 | As-built Survey Conformance | MRPA Quality Management Plan | Survey activities undertaken to validate correct construction Attach: Surevy Report, Engineering Asset From | Survey Document Review | Each lot | IP | Supervisor SE/PE/SPE | This ITP Signed Off
6.2 | Non-conformance Report (NCR) Closure | MRPA Quality Management Plan | Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed. | Document Review | Once, prior to closure of this lot / element / Work area | HP* | SE/PE/SPE | This ITP Signed Off
On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
Print Name: Position: Signature: Date: / /