## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | ITP-059-CIV-Brunt-Supply & Installation of Recycled HDPE Drainage Pipe | itp |  |  |  | Yes | ITP-059-CIV-Brunt-Supply & Installation of Recycled HDPE Drainage Pipe
section | 1. Referenced Documentation
checkpoint-no-status | 1. Referenced Documentation
label | Document Title: ITP-059-CIV-Brunt-Supply/Installation of Recycled HDPE Drainage Pipe
label | ITP Description: Installation of Recycled HDPE Drainage Pipe
label | Document Number (in Teambinder): MRP-0000-MRPA-ALT-ITP-00XX
label | Discipline (e.g. CIV/STR/RAIL): CIV
label | Revision Number: 0
label | Revision Date: 8/08/2023
label | ITP created by: Kamel Alshobaki
label | ITP approved for use by: Jon De Castro
checkpoint | 1.1 - Relevant Standards/Specs
label | Reference - AS 2566
checkpoint | 1.2 - Relevant Standards/Specs
label | Reference - VicRoads Sec 701
checkpoint | 1.3 - Relevant Standards/Specs
label | Reference - IFC Drawings
section | 2. Preliminaries - Materials
checkpoint | 2.1 - Drainage Flexible Pipes
note | Reference - Section 701.08
note | Acceptance Criteria - Flexible pipes shall be supplied in accordance with 701.08
note | ○ Prior to incorporating into the Project Works, plastic flexible pipes and fittings, shall obtain a signed Certificate of Conformance verifying that the materials and components comply with the requirements of VR 701 Standard.
note | ○ Buried flexible pipes shall not be used directly under the road pavement area.
textbox | Enter: Teambinder Material Approval number
note | Method - Document Review
note | Frequency - Each lot
note | Category - HP
note | Responsibility - Nominated Authority
note | Verifying Documents - ConQA Hold Point Release
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.2 - Precast Drainage Pit
note | Reference - Section 705.07, Section 705.04, Section 705.09
note | Acceptance Criteria - Precast steel reinforced concrete drainage pits shall be manufactured, supplied and installed in accordance with Section 705.07 & 705.09
note | ○ All concrete shall be manufactured to the concrete mix design registered by VicRoads and comply with the requirements of Section 705.04. Concrete grades shall comply with Table 705.041
textbox | Enter: Teambinder Material Approval number
note | Method - Document Review
note | Frequency - Each lot
note | Category - HP
note | Responsibility - Nominated Authority
note | Verifying Documents - ConQA Hold Point Release
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.3 - Cast in Place Drainage Pit
note | Reference - Section 705.06 IFC Drawings
note | Acceptance Criteria - Cast in place drainage pits shall be constructed in accordance with the requirements of Section 705.06 and at the locations and to the dimensions shown on the drawings.
note | Method - Document Review
note | Frequency - Each lot
note | Category - HP
note | Responsibility - Nominated Authority
note | Verifying Documents - ConQA Hold Point Release
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.4 - Drainage Pit - Step Irons
note | Reference - Section 705.04, Section 705.12
note | Acceptance Criteria - Step irons shall be manufactured by 13mm steel bar covered with polypropylene plastic in accordance with 705.04
note | ○ Drainage pits greater than 1.0 m deep shall be fitted with step irons in accordance with Section 705.12
textbox | Enter: Teambinder Material Approval number
note | Method - Document Review
note | Frequency - Each lot
note | Category - HP
note | Responsibility - Nominated Authority
note | Verifying Documents - ConQA Hold Point Release
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.5 - Drainage Bedding Material
note | Reference - Section 701.09
note | Acceptance Criteria - Bedding Material shall be free from perishable matter, lumps and conform with the requirements of Table 701.091 and Table 701.092.
textbox | Enter: Teambinder Material Approval number
note | Method - Document Review
note | Frequency - Each lot
note | Category - HP
note | Responsibility - Nominated Authority
note | Verifying Documents - ConQA Hold Point Release
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.6 - Drainage Backfill Material
note | Reference - Section 701.09, Section 701.19
note | Acceptance Criteria - Ordinary and Selected Backfill Material shall be free from perishable matter, lumps and conform with the requirements of Table 701.091 and Table 701.092.
note | ○ Where approved by the Superintendent, culverts in trenches may be backfilled to half the pipe diameter or box culvert height with 3% cement stabilised sand in accordance with Section 701.19
textbox | Enter: Teambinder Material Approval number
note | Method - Document Review
note | Frequency - Each lot
note | Category - HP
note | Responsibility - Nominated Authority
note | Verifying Documents - ConQA Hold Point Release
holdpoint | AUTHORITY HOLDPOINT
section | 3. Preliminaries - Procedures & Documentation
checkpoint | 3.1 - Subcontractor ITP (where required)
note | Reference - Subcontractor ITP
note | Acceptance Criteria - Subcontractor ITP shall conform with the IFC Drawings & Relevant Standards & Specifications.
note | Attach: Signed-off Subcontractor ITP
note | Method - Document Review
note | Frequency - Each lot
note | Category - HP*
note | Responsibility - PE
note | Verifying Documents - This ITP Signed Off
checkpoint | 3.2 - Check the type, size and class of pipes and other drainage structures to be laid
note | Reference - Work ActivityPack
note | Acceptance Criteria - Check Supplied items are:
note | – To correct spec, type, size and quantity
note | – Defect free, safely stored & prevented from UV Exposure
note | – Markings have been made as required
note | Method - Visual Review Document
note | Frequency - Each lot
note | Category - IP
note | Responsibility - Supervisor, SE/PE/SPE
note | Verifying Documents - This ITP Signed Off
section | 4. Pre-Construction Activities
checkpoint | 4.1 - Survey Set Out - Pits & Pipes
note | Reference - IFC Drawings Section 701.10
note | Acceptance Criteria - Prior to commencement of excavation for the flexible pipes, the Contractor shall confirm the position of all pipes with the Superintendent/Surveyor.
note | ○ Survey activities undertaken to ensure and validate the plan location, height and line of pits and location, invert level, plan of pipes in accordance with design documentation and VR701.10
note | Method - Survey
note | Frequency - Each Lot
note | Category - HP*
note | Responsibility - PE
note | Verifying Documents - This ITP Signed Off
section | 5. Construction Activities
checkpoint | 5.1 - Set out the works for each drainage system
note | Reference - AS 2566 IFC Drawing
note | Acceptance Criteria - Establish Pegs (or equivalent)survry marks to identify location, length, and levels as per design drawings and schedules and check if:
note | – Inlet/outlet heights fit in with natural surface (ie not too high or low)
note | – Inlet/outlet location suitable for water-course (eg no drainage problems)
note | – Pits relocated (through RFI’s) in order to avoid cutting of pipes
note | Method - Inspection Survey
note | Frequency - Each lot
note | Category - IP
note | Responsibility - Supervisor, SE/PE/SPE
note | Verifying Documents - This ITP Signed Off
checkpoint | 5.2 - Confirm position of all Drainage line/culverts
note | Reference - VicRoads 701.09 IFC Drawing
note | Acceptance Criteria - Prior to commencement of excavation for the Drainage the contractor shall confirm the position of all drainage line with the Surveyor.
note | Method - Visual Inspection
note | Frequency - Each lot
note | Category - HP*
note | Responsibility - Supervisor, SE/PE/SPE, Surveyor
note | Verifying Documents - This ITP Signed Off
checkpoint | 5.3 - Excavate trench to the underside of bedding to correct width
note | Reference - AS 2566 IFC Drawing
note | Acceptance Criteria - Width and depth of pipe trench as per AS 2566.1. Refer to right table
note | ○ For other structures, the clear width between structure wall & face of excavation is ≥ 300mm or 1/3 height of excavation face, whichever is greater
note | ○ Trenches > 1.5m deep are either shored or benched
note | ○ The excavation is ≤ 50mm beyond the specified width and depths of the trench
note | ○ For pipes under embankments
note | – the first embankment is constructed to a height ≥ 0.7 times the external dia of the pipe above the top of the bed zone, and for a min lateral distance past the boundary of the trench of 2.5 times the external dia of the pipe
note | – Trenches done after the construct of the embankment to the level of the underside of the Selected Material Layer
note | ○ No welding/ anchor block systems etc. required. This system is just a simple lubrication of the end of pipe.
note | Method - Inspection
note | Frequency - Each lot
note | Category - IP
note | Responsibility - Supervisor, SE/PE/SPE
note | Verifying Documents - This ITP Signed Off
checkpoint | 5.4 - Install pipes in accordance to manufacturer’s instructions and design documentations
note | Reference - RPM Installation and Handling Guildelines
note | Acceptance Criteria - Pipe laid from inlet to outlet
note | ○ Pipe support conforming to AS2566
note | ○ Polypropylene Pipes (Blackmax or StormPro)
note | ○ Correct size and class of pipes are laid with socket end placed upstream
note | ○ Pipe ends cleaned and rubber rings / bands installed as per manufacture’s recommendations
note | ○ Inlet/outlet heights fit in with natural surface (not too high or low)
note | ○ HDPE Pipes to be cleaned, beaded and jointed by suitably qualified personnel.
note | ○ Electrofusion Welding or Butt Welding of pipes permissible.
note | ○ Joints allowed to cool prior to lifting or shifting into position.
note | ○ Anchor blocks provided at 3m spacing max., at bends, junctions and where shown on drawings
note | ○ Subsurface drainage installed at the discharge end of pipes
note | ○ Add check lengths as per the minimum required
note | ○ Width to edge of trench, 150mm
note | ○ 300mm above pipe with selected backfill material.
note | Method - Inspection
note | Frequency - Each lot
note | Category - IP
note | Responsibility - Supervisor, SE/PE/SPE
note | Verifying Documents - This ITP Signed Off
checkpoint | 5.5 - Verify that completed pipeline against survey marksdesign level and alignments
note | Reference - AS 2566 IFC Drawing
note | Acceptance Criteria - Completed pipeline is inline and within ±200mm of location (plan)
note | ○ Invert level are within 20mm of the design level at any point
note | ○ To be checked at each pit and headwall
note | ○ Horizontal Position for Pits in Kerb to be
note | • +-200mm longitudinally
note | • +-20mm perpendiculat to kerb alignment
note | Method - Inspection
note | Frequency - Each lot
note | Category - IP
note | Responsibility - Supervisor, SE/PE/SPE
note | Verifying Documents - This ITP Signed Off
checkpoint | 5.6 - Place and spread haunch, side zone, overlay and backfill embedment, replacement and backfill material,, compact and test to specified densities
note | Reference - VicRoads Spec. Cl. 701.26, 701.20
note | Acceptance Criteria - Placed in 150mm layers and compact to 95% std compaction
note | ○ If stabilised sand used, the materials been vibrated to obtain complete placement & compaction of material under & around pipe and the placed stabilised materials are firm a day after placement
note | ○ If 10/14mm aggregates used, the materials been vibrated to obtain complete placement & compaction of material under & around pipes.
note | ○ A minimum of 20% of all lots for each culvert shall be tested.
note | Method - Inspection
note | Frequency - Each lot
note | Category - IP
note | Responsibility - Supervisor, SE/PE/SPE
note | Verifying Documents - This ITP Signed Off
checkpoint | 5.7 - Inlet/Outlet Structures
note | Reference - VicRoads Spec. 701.23
note | Acceptance Criteria - Refer to Pit supply & installation ITP
note | Method - Inspection
note | Frequency - Each lot
note | Category - IP
note | Responsibility - Supervisor, SE/PE/SPE
note | Verifying Documents - This ITP Signed Off
checkpoint | 5.8 - Flushing System
note | Reference - VicRoads Spec. Cl. 701.26
note | Acceptance Criteria - Each Drainage/Culvert line is to be flushed clean from end to end on completion. and maintained in proper working order.
note | Method - Inspection
note | Frequency - Each lot
note | Category - HP*
note | Responsibility - Nominated Authority
note | Verifying Documents - This ITP Signed Off
checkpoint | 5.9 - Engage pipe inspection video subcontractor to take footage of all completed new pipes.
note | Reference - VicRoads Spec 701.28
note | Acceptance Criteria - All Drainage line constructed shall be inspected after completion of earthworks to subgrade level and prior to construction of pavement layers, by independent Testing Organization using closed circuit television(CCTV). The report shall be provided to the Nominated Authority.
note | Attach: CCTV Report
note | Method - Inspection
note | Frequency - Each lot
note | Category - HP
note | Responsibility - Nominated Authority
note | Verifying Documents - ConQA Hold Point Release
holdpoint | AUTHORITY HOLDPOINT
section | 6. Post-construction / Post-installation Activities
checkpoint | 6.1 - As-built Survey Conformance
note | Reference - MRPA Quality Management Plan
note | Acceptance Criteria - Survey activities undertaken to validate correct construction
note | Attach: Survey Report, Engineering Asset From
note | Method - Survey Document Review
note | Frequency - Each lot
note | Category - IP
note | Responsibility - Supervisor, SE/PE/SPE
note | Verifying Documents - This ITP Signed Off
checkpoint | 6.2 - Non-conformance Report (NCR) Closure
note | Reference - MRPA Quality Management Plan
note | Acceptance Criteria - Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed.
note | Method - Document Review
note | Frequency - Once, prior to closure of this lot / element / Work area
note | Category - HP*
note | Responsibility - SE/PE/SPE
note | Verifying Documents - This ITP Signed Off
checkpoint | Final Inspection
note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
textbox | Name:
textbox | Position:
date | Date Completed:
signoff | Sign ITP