## General
GENERAL DETAILS
Project Name: | Crystal Twin Culvert Replacement
Project Location: | RP 7.6km Matahorua Road, Tutira, Hastings District
Downer Project Number: | 551124 - WO# 662062
Client: | Hastings District Council (attn. Nigel Beaston, Stantec)
Contract Number:
Document Control: | ITP Version: | 1 | Status: | Draft | Date: | 2023-05-17
ITP Description: | Inspection Test Plan for large-scale culvert replacement after damage caused by Cyclone. DN3200 HDPE culvert being installed. Includes fill (>10m), headwalls and road reconstruction. 1. General / Establishment / Disestablishment 2. Earthworks 3. Culvert Install 4. Inlet Headwall 5. Outlet Headwall 6. Roading
Specification: | Not yet avaliable. Generally to NZTA Bridge Spec.
Drawings: | Not yet avaliable.
Prepared By: | Name: | Briar Thomas | Signature: |  | Date: | 2023-05-17
SIGNATURES – CLOSE-OUT & APPROVAL
Downer Approval | Name: |  | Signature: |  | Date:
Client Approval | Name: | Andy Mott / Nigel Beaston | Signature: | via email (18/05/2023 @ 21:04) | Date: | 2023-05-18

## 2. Earthworks
2. EARTHWORKS
Item No. | Activity/ Task Description | Inspection Point: Quality Control Activity | Acceptance Criteria | Verifying Document | Frequency | Inspection Type (Visual, other) | Responsible | Inspection
[8 empty] | Key | By (Role Key) | Date
2.1 | Site Clearing - remove loose material | Site Condition | All loose material removed including topsoil, silt, tree debris, rocks etc. | Photos Onsite Inspection | Once | Visual Inspection | Project Manager | Visual Verification | Project Manager | 26/04/2023 (Weekly Report #1)
2.2 | Site clearing - form bench and/or roughen rock subgrade | Site Condition | Safe working platform for machinery. Roughening of papa rock subgrade - no smooth surface visiable. | Photos Onsite Inspection | As required | Visual Inspection | Project Manager | Visual Verification | Project Manager | 01/05/2023 (Weekly Report #2)
2.3 | Confirm Fill Material - AP65 | Material Quality | Engineer approval of lab results | WSP Lab Results | Once - or again if source changes | Engineer Approval | Project Manager | Hold Point | Engineer | 08/05/2023 (Weekly Report #3)
2.4 | Confirm Fill Material - won on-site | Material Quality | Engineer approval of lab results | WSP Lab Results | Once - or again if source changes | Engineer Approval | Project Manager | Hold Point | Engineer | 05/05/2023 (via email)
2.5 | Confirm Fill Material - local quarry | Material Quality | Engineer approval of lab results | WSP Lab Results | Once - or again if source changes | Engineer Approval | Project Manager | Hold Point | Engineer | 05/05/2023 (via email)
2.6 | Subgrade Inspection | Site Condition | All loose material removed, roughen or bench papa subgrade, graded base to ensure water can drain away. | Photos Onsite Inspection | Once | Visual Inspection | Project Manager | Inspection | Engineer | 01/05/2023 (Weekly Report #2)
2.7 | Subgrade Survey | Quantity Control | Complete survey | WSP Drone Survey | Once - when site is at subgrade | Survey Record | Stantec (Engineer) | Operation | Engineer | 2023-05-08
2.8 | Onsite Compaction Limits | Quality Control | Plateau Testing - observation of plateau in wet density | WSP Plateau Test Results | When material or compaction device changed | Review Results | Project Manager | Review | Engineer | 08/05/2023 (Weekly Report #3)
2.9 | Compaction | Quality Control | NDM Testing Fill below culvert invert: Average MDD of 98%, min 95% Fill around & above culvert: Average MDD of 95%, min 92% Locations (incl. lit number and height) recorded. If fails, further 3 tests within 5m. If any of those fail, dig out, replace & recompact. | WSP NDM Results (every 2-3 layers) and DNZ Onsite NDM Records (every layer) | x3 each layer | Review Results | Project Manager | Monitor, Review & Hold Point (if not met) | Engineer | Ongoing Included in Weekly Reports #3 & #4 so far
2.10 | Seperation of existing fill that cannot be safely removed | Quality Control | Geotextile (Strength Class C) placed between existing fill that cannot be safely removed and new fill (mitigate fines migration). | Photos Onsite Inspection | As required | Visual Inspection | Project Manager | Visual Verification | Engineer
2.11