## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist-flat | ITP - 2. Earthworks | itp |  |  |  |  | ITP - 2. Earthworks
checkpoint | 2.1 - Site Clearing - remove loose material
label | Inspection Point: Quality Control Activity - Site Condition
label | Acceptance Criteria - All loose material removed including topsoil, silt, tree debris, rocks etc.
label | Verifying Document - Photos, Onsite Inspection
label | Frequency - Once
label | Inspection Type (Visual, other) - Visual Inspection
label | Responsible - Project Manager
label | Inspection: Key - Visual Verification
label | Inspection: By (Role Key) - Project Manager
label | Inspection: Date - 26/04/2023 (Weekly Report #1)
checkpoint | 2.2 - Site clearing - form bench and/or roughen rock subgrade
label | Inspection Point: Quality Control Activity - Site Condition
label | Acceptance Criteria - Safe working platform for machinery. Roughening of papa rock subgrade - no smooth surface visiable.
label | Verifying Document - Photos, Onsite Inspection
label | Frequency - As required
label | Inspection Type (Visual, other) - Visual Inspection
label | Responsible - Project Manager
label | Inspection: Key - Visual Verification
label | Inspection: By (Role Key) - Project Manager
label | Inspection: Date - 01/05/2023 (Weekly Report #2)
checkpoint | 2.3 - Confirm Fill Material - AP65
label | Inspection Point: Quality Control Activity - Material Quality
label | Acceptance Criteria - Engineer approval of lab results
label | Verifying Document - WSP Lab Results
label | Frequency - Once - or again if source changes
label | Inspection Type (Visual, other) - Engineer Approval
label | Responsible - Project Manager
label | Inspection: Key - Hold Point
label | Inspection: By (Role Key) - Engineer
label | Inspection: Date - 08/05/2023 (Weekly Report #3)
holdpoint | HOLD POINT
checkpoint | 2.4 - Confirm Fill Material - won on-site
label | Inspection Point: Quality Control Activity - Material Quality
label | Acceptance Criteria - Engineer approval of lab results
label | Verifying Document - WSP Lab Results
label | Frequency - Once - or again if source changes
label | Inspection Type (Visual, other) - Engineer Approval
label | Responsible - Project Manager
label | Inspection: Key - Hold Point
label | Inspection: By (Role Key) - Engineer
label | Inspection: Date - 05/05/2023 (via email)
holdpoint | HOLD POINT
checkpoint | 2.5 - Confirm Fill Material - local quarry
label | Inspection Point: Quality Control Activity - Material Quality
label | Acceptance Criteria - Engineer approval of lab results
label | Verifying Document - WSP Lab Results
label | Frequency - Once - or again if source changes
label | Inspection Type (Visual, other) - Engineer Approval
label | Responsible - Project Manager
label | Inspection: Key - Hold Point
label | Inspection: By (Role Key) - Engineer
label | Inspection: Date - 05/05/2023 (via email)
holdpoint | HOLD POINT
checkpoint | 2.6 - Subgrade Inspection
label | Inspection Point: Quality Control Activity - Site Condition
label | Acceptance Criteria - All loose material removed, roughen or bench papa subgrade, graded base to ensure water can drain away.
label | Verifying Document - Photos, Onsite Inspection
label | Frequency - Once
label | Inspection Type (Visual, other) - Visual Inspection
label | Responsible - Project Manager
label | Inspection: Key - Inspection
label | Inspection: By (Role Key) - Engineer
label | Inspection: Date - 01/05/2023 (Weekly Report #2)
checkpoint | 2.7 - Subgrade Survey
label | Inspection Point: Quality Control Activity - Quantity Control
label | Acceptance Criteria - Complete survey
label | Verifying Document - WSP Drone Survey
label | Frequency - Once - when site is at subgrade
label | Inspection Type (Visual, other) - Survey Record
label | Responsible - Stantec (Engineer)
label | Inspection: Key - Operation
label | Inspection: By (Role Key) - Engineer
label | Inspection: Date - 8/05/2023
checkpoint | 2.8 - Onsite Compaction Limits
label | Inspection Point: Quality Control Activity - Quality Control
label | Acceptance Criteria - Plateau Testing - observation of plateau in wet density
label | Verifying Document - WSP Plateau Test Results
label | Frequency - When material or compaction device changed
label | Inspection Type (Visual, other) - Review Results
label | Responsible - Project Manager
label | Inspection: Key - Review
label | Inspection: By (Role Key) - Engineer
label | Inspection: Date - 08/05/2023 (Weekly Report #3)
checkpoint | 2.9 - Compaction
label | Inspection Point: Quality Control Activity - Quality Control
label | Acceptance Criteria - NDM Testing
label | • Fill below culvert invert: Average MDD of 98%, min 95%
label | • Fill around & above culvert: Average MDD of 95%, min 92%
label | • Locations (incl. lit number and height) recorded.
label | • If fails, further 3 tests within 5m. If any of those fail, dig out, replace & recompact.
label | Verifying Document - WSP NDM Results (every 2-3 layers) and DNZ Onsite NDM Records (every layer)
label | Frequency - x3 each layer
label | Inspection Type (Visual, other) - Review Results
label | Responsible - Project Manager
label | Inspection: Key - Monitor, Review & Hold Point (if not met)
label | Inspection: By (Role Key) - Engineer
label | Inspection: Date - Ongoing, Included in Weekly Reports #3 & #4 so far
checkpoint | 2.10 - Seperation of existing fill that cannot be safely removed
label | Inspection Point: Quality Control Activity - Quality Control
label | Acceptance Criteria - Geotextile (Strength Class C) placed between existing fill that cannot be safely removed and new fill (mitigate fines migration).
label | Verifying Document - Photos, Onsite Inspection
label | Frequency - As required
label | Inspection Type (Visual, other) - Visual Inspection
label | Responsible - Project Manager
label | Inspection: Key - Visual Verification
label | Inspection: By (Role Key) - Engineer