## Breakdown
| PROJECT BREAKDOWN | [7 empty] | CHECKLISTS
Tier 1 | Tier 2 | Tier 3 | Tier 4 |  | Tier 5 | Tier 6 | Tier 7 | Tier 8
Site QA
| Internal Fitout & Services | [7 empty] | FitOut
|  | Level 3 | Theaters | OT1 |  |  |  |  | Walls Preline Checklist
|  |  |  | OT2 |  |  |  |  | Ceiling Preline Checklist
|  |  |  | OT3 |  |  |  |  | Walls Postline Checklist | For All Rooms
|  |  |  | OT4 |  |  |  |  | Ceiling Postline Checklist incl high level services
|  |  |  | OT5 |  |  |  |  | Flooring Checklist
|  |  |  | OT6 |  |  |  |  | Final sign off
OT7
Case Trolley Storage 1
Scrub 02
Case Trolley Storage 2 & 3
Scrub 03
Case Trolley Storage 4 & 5
Scrub 04
Case Trolley Storage 6
Corr 21
Corr 22
Equip 07
Exit Cath 02
Equip 02
Scrub 01
Exit Cath 01
Equip 01
Equip
Equip 09
Equip 08
Cath Lab
Comp
Cath St
Future Cath Lab/OT
Control
Lead Aprons
Store
Office 02
Corr 20
Clean Up
Dirty Lift 06
|  |  | Recovery Stage 1 | Staff Base 02
CU/MED 02
Corr 23
Corr 24
Corr 25
ISO 11
|  | Level 3 | ICU | ICU Bay 01
ICU Bay 02
ICU Bay 03
ICU Bay 04
ICU Bay 05
ICU Bay 06
Equip 02
Corr 11
Team Leaders
ICU Lounge
ICU Staff Base
Stairs 03
CU/MED 01
|  |  | HDU | HDU Bed 01
ENS 01
HDU Bed 02
ENS 02
HDU Bed 03
ENS 03
HDU Bed 04
ENS 04
Corr 10
A/L 03
INT 01
ST.WC.01
REL.RM
Store 1
CCN
Write Up
Corr 09
DU/Disp 02
Equip 01
Linen Bay
Corr 20
Officve 02
Corr 19
ST.WC.01
ST.WC.02
Office 01
Office
Pathology
Pharm
WC.01
WC.02
Prep 02
Cleaner
Corr 08
Linen
AWC
Trolley Bed Park
Equip
Control S/B 02
Corr 16
Sterile Store
Non Sterile Store
Med Rec
Office
Office 01
Recept 01
Corr 03
Wait
Corr 05
Cons 01
Corr 04
WC
Cons 02
INT 01
INT 02
INT 03
INT 04
INT 05
Corr 06
Recovery Stage 02
DU 01
Equip
BEV
Corr 29
Corr 26
A ENS
Recovery Stage 03
Corr 28
Store
PAT Owned Store
BEV
Cleaner
WC.01
WC.02
Interview
Staff Base 03
Corr 27
|  | Level 4 |  | BED 01
BED 02
BED 03
BED 04
BED 05
BED 06
BED 07
BED 08
BED 09
BED 10 & 11
BED 12
BED 13
BED 14
BED 15
BED 16 & 17
BED 18
BED 19
BED 20
BED 21
BED 22
BED 23
BED 24
BED 25
BED 26
BED 31
BED 32
BED 33
BED 34
BED 35
BED 36
BED 37
Corr 01
Corr 02
Corr 03
Corr 04
Corr 05
Corr 06
Corr 07
Corr 08
|  | Level 2 |  | Decon
Loan-In
AWC
ST.WC.
CORR 04
Lobby
CORR 07
WAIT
GYM
Reception
Consult 01
Trolley Wash
Airlock
Consult 02
Consult 03
Trolley Washer and Foyer
Office
Cleaner
Consult 05
Consult 04
Consult 06
Consult 07
Inspection/Packaging
CORR 11
CORR 06
Stair 03
CORR.
Steriliser
S/B
CORR 12
Store
Ward Dispatch
Consult 08
BEV.
Hot Desks
Female Change
Male Change
Sterile Store
Clean Lobby
Clean Lift
Dirty Lift
Dirty Lobby
M. Change A/L
F. Change A/L
Theatre Lounge
CORR 08
Plant 03
CORR 09
UPS
COMMS
CORR 10
|  | Level 1 |  | Dry Store
Freeze
Cool
Delivery
Office
Kitchen
CORR 04
Lobby
Entry A/L
House-Keeping Store
Chem. St.
Pharmacy
Female Locker
WC
Male Locker
WC
CORR 02
CORR 03
Clean Linen
Laundry
Cleaner
Bed Store
Mainten. Man.
Store
Office
CORR 03
De-Boxing Room
Clean Lift 05
Dirty Lift 06
Store Manager
Comms
CORR 06
CORR 07
Bike Store
Loading
Bin Washing
Dirty Linen
Cont. Waste
Plant 02
Plant 01
|  | Stair 03 |  | Level 2
Level 3
Level 4
Level 5
|  | Stair 04 |  | Level 1
Level 2
Level 3
Checkpoint | Can we add text when selecting this checkpoint
Bool | What does dthis mean
button | Just to check that we have done this correctly

## FITOUT
checklist | Wall Preline
section | Interior Framing
checkpoint | Reference Drawings ( add numbers and revisions)
checkpoint | Trades QA received, reviewed, attached and approved
checkpoint | All framing setout correctly & surveyed in respective area
bool | Spot checks on frames for square
bool | Spot checks on frame level
bool | Fixings are correct including seismic requirements
bool | Service Nogs installed
checkpoint | Any additional photos, comments and observations
section | Plumbing Walls First Fix
checkpoint | Trades QA received, reviewed, attached and approved
checkpoint | Plumbing install First fix complete - checks done based on elevations of current drawings
checkpoint | Any additional photos, comments and observations
checkpoint | Council inspection and testing complete and signed off
section | Fire Protection Walls (Alarms) First Fix
checkpoint | Trades QA received, reviewed, attached and approved
checkpoint | First Fix checks with Subcontractor (alarms)
checkpoint | All required 1st fix testing complete
checkpoint | Any additional photos, comments and observations
section | Mechanical Services Wall First Fix
checkpoint | Trades QA received, reviewed, attached and approved
checkpoint | First Fix checks with subcontractor
checkpoint | Any additional photos, comments and observations
section | Electrical Wall First Fix
checkpoint | Trades QA received, reviewed, attached and approved
checkpoint | First Fix checks with Subcontractor
checkpoint | All required first fix testing complete
checkpoint | Any additional photos, comments and observations
section | Data Wall First Fix
checkpoint | Trades QA received, reviewed, attached and approved
checkpoint | All required first fix completed
checkpoint | Any additional photos, comments and observations
section | Security Wall First Fix
checkpoint | Trades QA received, reviewed, attached and approved
checkpoint | All required first fix completed
checkpoint | Any additional photos, comments and observations
section | AV Wall First Fix
checkpoint | Trades QA received, reviewed, attached and approved
checkpoint | All required first fix completed
checkpoint | Any additional photos, comments and observations
section | Insulation/Acoustic
checkpoint | Trades QA received, reviewed, attached and approved
checkpoint | Spot checks on correct product
checkpoint | Spot checks on correct R value
checkpoint | Fitting Snug
checkpoint | Any additional photos, comments and observations
section | Council Sign Off
checkpoint | Council preline inspection passed
checklist | Ceiling Preline incl High Level Services
section | QA - Plumbing First Fix
checkpoint | Reference Drawings ( add numbers and revisions)
checkpoint | Trades QA received, reviewed, attached and approved
checkpoint | Services Seismic Restraint installed
checkpoint | Consultants Inspection sign off
checkpoint | Any additional photos, comments and observations
checkpoint | Council inspection and testing complete and signed off
checkpoint | Engineer has signed off Seismic restraints
checkpoint | Witness testing of pipework by Hawkins
section | Fire Protection (Sprinklers & Alarms) First Fix
checkpoint | Reference Drawings ( add numbers and revisions)
checkpoint | Trades QA received, reviewed, attached and approved
checkpoint | Services Seismic Restraint installed
checkpoint | Consultant inspection sign off
checkpoint | Any additional photos, comments and observations
checkpoint | Engineer has signed off Seismic restraints
checkpoint | Witness testing of pipework by Hawkins
section | Mechanical Services First Fix
checkpoint | Reference Drawings ( add numbers and revisions)
checkpoint | Trades QA received, reviewed, attached and approved
checkpoint | Services Seismic Restraint installed
checkpoint | Any additional photos, comments and observations
checkpoint | All required testing complete
checkpoint | Engineer has signed off Seismic restraints
checkpoint | Consultant sign off
checkpoint | All ends covered/protected to reduce debris
checkpoint | Witness testing of compliance check by Hawkins
section | Electrical First Fix
checkpoint | Trades QA received, reviewed, attached and approved
checkpoint | All required testing complete
checkpoint | Services Seismic Restraint installed
checkpoint | Any additional photos, comments and observations
checkpoint | Consultant sign off
checkpoint | Engineer has signed off Seismic restraints
checkpoint | Witness testing of compliance check by Hawkins
section | Data First Fix
checkpoint | Trades QA received, reviewed, attached and approved
checkpoint | All required testing complete
checkpoint | Any additional photos, comments and observations
checkpoint | Consultant sign off
checkpoint | Engineer has signed off Seismic restraints
checkpoint | Witness testing of compliance check by Hawkins
section | Security First Fix
checkpoint | Trades QA received, reviewed, attached and approved
checkpoint | All required testing complete
checkpoint | Any additional photos, comments and observations
checkpoint | Consultant sign off
checkpoint | Engineer has signed off Seismic restraints
checkpoint | Witness testing of compliance check by Hawkins
checkpoint | Passive Fire Works Complete
section | Rondo Ceiling Grid Installation
checkpoint | Service penetrations mark out completed, checked and acceptable (clashes considered)
checkpoint | Ceiling Grid ( pass when all below ticked)
bool | Ceiling height correct
bool | Appropriate fixings used and installed as per required specification
bool | Appropriate spacings for respective grid elements
bool | Perimeter channel/angle installed correctly
bool | All strong backs installed where required to meet specification
bool | Seismic Restraint installed as per the KCL Drawings
checkpoint | Trades QA received, reviewed, attached and approved
checkpoint | Any additional photos, comments and observations
section | Insulation Prior to Lining
checkpoint | Trades QA received, reviewed, attached and approved
checkpoint | Insulation pre lining works completed, checked & approved
bool | Correct product & R value as per specification
bool | Fitting Snug
checkpoint | Any additional photos, comments and observations
section | Council Sign Off
checkpoint | Council preline inspection passed
checklist | Walls Postline
checkpoint | Correct linings installed as per linings plan
checkpoint | Bracing fixings installed correctly as per requirements
checkpoint | Linings cut out for flush boxes neat and tidy
checkpoint | All screws installed flush
checkpoint | Wall approved for stopping
checkpoint | Stopping light check complete ready for paint
checklist | Ceiling Postline
checkpoint | Correct linings installed as per linings plan
checkpoint | Fixings as per specification including if glue required
checkpoint | Service penetrations cut out as per architecture RCP
checkpoint | Any ceiling hatches installed & fixed correctly
checkpoint | Ceiling approved for stopping
checkpoint | Stopping light check complete ready for paint
checklist | Flooring
checkpoint | Floor substrate clean, dry, ready for finishes
checkpoint | Finishes as per architectural plans
checkpoint | Trim thresholds junction as per detail
checkpoint | Any additional photos, comments and observations
checklist | Final Sign Off
checkpoint | Doors Installed including drop down seals if applicable
checkpoint | Hardware as per approved schedule
checkpoint | Architraves and skirtings installed
checkpoint | Electrical Power/Lighting second fix installed
checkpoint | Sprinkler/Alarm second fix installed
checkpoint | Security second fix installed
checkpoint | Data second fix installed
checkpoint | HVAC second fix installed
checkpoint | Floor finishes installed as per architectural plan
checkpoint | Paint correct colour
checkpoint | Door signage installed
checkpoint | Manifestations on glazing
checkpoint | Joinery installed correctly