## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist-flat | CHK-004-STR-CAMMS-RSS Walls-Fill Placement | itp |  |  |  | Yes | CHK-004-STR-CAMMS-RSS Walls-Fill Placement Rev 1 | ef837412-106f-47c6-bfc5-78304603772f
checkpoint-status | CHK-004-STR-CAMMS-RSS Walls-Fill Placement
label | Document Title: CHK-004-STR-CAMMS-RSS Walls-Fill Placement
label | Check list Description: RSS Walls-Fill Placement
label | Discipline (e.g. CIV/STR/RAIL): STR
label | Revision Number: 1
label | Revision Date: 1/05/2023
label | ITP created by: Victor Mira
label | ITP approved for use by: Victor Mira
checkpoint-status | 1 - Soil reinforcement - Straps
label | REFERENCE: 682.08
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Reinforcing elements shall be placed on top of the compacted fill material and connected to the wall panels.
label | • Any twists, kinks, sags or deviations in the reinforcing elements shall be removed prior to the placement of fill material on the reinforcing.
label | – – – – – – – – – – – – – – – – –
label | METHOD: Visual
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Each strap
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: IP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: SE/PE
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: This Checklist
label | – – – – – – – – – – – – – – – – –
text | Date Completed:
checkpoint-status | 2 - Soil reinforcements - Connections
label | REFERENCE: Installation manual
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Correct number of reinforcing element shall be attached to each panel
label | – – – – – – – – – – – – – – – – –
label | METHOD: Visual
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Each panel
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: IP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: SE/PE
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: This Checklist
label | – – – – – – – – – – – – – – – – –
text | Date Completed:
checkpoint-status | 3 - Soil reinforcements - Connections
label | REFERENCE: IFC Drawings
label | • Schedule of lengths: MRP-052-C-RFL-DRG-33-CBE-CSW-1302,1403,1503,1602
label | • Connections arrangement: MRP-052-C-RFL-DRG-33-CBE-CSW-1901
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Grid Strips are to be installed at the back of each panel in correct length and to the correct anchors at the back of each panel
label | – Bolts are to be snug tight.
label | – – – – – – – – – – – – – – – – –
label | METHOD: Visual
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Each fill layer
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: IP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: SE/PE
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: This Checklist
label | – – – – – – – – – – – – – – – – –
text | Date Completed:
checkpoint-status | 4 - Soil reinforcements - Plan arrangement
label | REFERENCE: IFC Drawings
label | • Arrangements: MRP-052-C-RFL-DRG-33-CBE-CSW-1102 to 1104 VR682.06
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Plan positions of Grid Strips are to be as IFC Drawings.
label | – Grid Strips shall not overlapped
label | – – – – – – – – – – – – – – – – –
label | METHOD: Visual
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Each fill Layer
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: IP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: Surveyor/SE
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: This Checklist
label | – – – – – – – – – – – – – – – – –
text | Date Completed:
checkpoint-status | 5 - Soil reinforcements - Plan arrangement
label | REFERENCE: IFC Drawings
label | • Arrangements: MRP-052-C-RFL-DRG-33-CBE-CSW-1102 to 1104 VR682.06
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Plan positions of Grid Strips are to be as IFC Drawings.
label | – Grid Strips are not to pass over pile cap. RSS used in conjunction with a bridge abutment shall be independent of the bridge structure.
label | – – – – – – – – – – – – – – – – –
label | METHOD: Visual
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Where applicable
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: IP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: PE/SE
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: This Checklist
label | – – – – – – – – – – – – – – – – –
text | Date Completed:
checkpoint-status | 6 - Soil reinforcements - vertical deviation
label | REFERENCE: IFC Drawings
label | • MRP-052-C-RFL-DRG-33-CBE-CSW-1702
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: The vertical deviation of the soil reinforcement shall be within +1% upwards and -0.3% downwards of the soil reinforcement length, relative to the connection height.
label | • Avoid clash with drainage as directed in IFC Drawings.
label | – – – – – – – – – – – – – – – – –
label | METHOD: Measure, Survey
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Each Fill Layer
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: IP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: Surveyor/SE
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: This Checklist
label | – – – – – – – – – – – – – – – – –
text | Date Completed:
checkpoint-status | 7 - Fill - Pacement
label | REFERENCE: 204.10
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Fill layers to be spread and compacted in layers not exceeding a compacted thickness of 200mm
label | • All RSS fill layers to be spread from the back face of panel to tail of soil reinforcing straps
label | – – – – – – – – – – – – – – – – –
label | METHOD: Measure, Visual
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Each Fill Layer
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: IP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: PE/SE
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: This Checklist
label | – – – – – – – – – – – – – – – – –
text | Date Completed:
checkpoint-status | 8 - Select backfill - moisture content
label | REFERENCE: IFC Drawings
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Moisture content of the backfill shall be maintained evenly at all times.
label | • Moisture content shall be within 0% to -2% of the optimum moisture content. Any backfill material exceeding the optimum moisture content, must be allowed to dry
label | – – – – – – – – – – – – – – – – –
label | METHOD: Measure
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Each Fill Layer
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: IP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: PE/SE
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: Attached Test Results
label | – – – – – – – – – – – – – – – – –
text | Date Completed:
checkpoint-status | 9 - Select backfill - placement
label | REFERENCE: IFC Drawings
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Select backfill shall be placed in accordance with Vicroads section 204 and compacted to 98% of standard proctor density.
label | • Compaction within 1 meter of the wall face shall be achieved by a light weight (Hand Operated) mechanical tamper roller or vibratory system.
label | • No large compaction equipment shall be allowed in this zone.
label | • Compaction beyond 1 meter of the wall face shall be in accordance with the table VR 204.111
label | – – – – – – – – – – – – – – – – –
label | METHOD: Measure
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Each Fill Layer
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: HP*
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: PE/SE
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: This Checklist
label | – – – – – – – – – – – – – – – – –
text | Date Completed:
checkpoint-status | 10 - Select back fill - reduced frequency
label | ACCEPTANCE CRITERIA: After three consecutive lots of like material have achieved the specified requirement, the contractor may seek the superintendent's agreement to reduce the frequency of testing of subsequent lots to the minimum requirement specified in table 204.142:
textbox | Three Consecutive Lots tested to satisfy this requirement.
label | – – – – – – – – – – – – – – – – –
label | METHOD: Document review
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Each Fill Layer
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: IP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: Nominated Authority/PE
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: Referenced Lots in This Checklist
label | – – – – – – – – – – – – – – – – –
text | Date Completed:
checkpoint-status | 11 - Select Backfill - Testing frequency - acceptance
label | REFERENCE: IFC Drawings
label | • VR 204.14
label | • VR 682.16
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Testing frequency shall be in accordance with Vicroad Specification section 204.14
label | • The Contractor shall submit compaction test results for each layer of fill placement to the Superintendent for review and acceptance.
label | • No further fill placement shall be allowed if the total thickness of fill placement is greater than 1 m measured from the last layer that has been accepted.
label | • If any layer is found to be not in compliance with the compaction requirement, that layer and the layers above it shall be removed
label | Attach: Compaction test results
label | – – – – – – – – – – – – – – – – –
label | METHOD: Measure
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Each Fill Layer or every second layer as agreed
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: HP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: Nominated Authority
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: Attached Test Results
label | – – – – – – – – – – – – – – – – –
text | Date Completed:
holdpoint | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status | 12 - Select backfill - acceptance
label | REFERENCE: VR 204.12
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: All layers of fill shall be test rolled in accordance with VR 173. The contractor Shall provide for the superintendent to be present during all test rolling
label | – – – – – – – – – – – – – – – – –
label | METHOD: Visual
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Every Fill Layer
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: HP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: Nominated Authority
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: This Checklist
label | – – – – – – – – – – – – – – – – –
text | Date Completed:
holdpoint | NOMINATED AUTHORITY HOLDPOINT
checklist-flat | CHK-005-STR-CAMMS-RSS Walls-Precast Panel installation | itp |  |  |  | Yes | CHK-005-STR-CAMMS-RSS Walls-Precast Panel installation Rev 1 | d71bc5c4-ce89-47cf-a34e-0b1df4c1e5ba
checkpoint-status | CHK-005-STR-CAMMS-RSS Walls-Precast Panel installation
label | Document Title: CHK-005-STR-CAMMS-RSS Walls-Precast Panel installation
label | Check list Description: RSS Walls - Panel installation
label | Discipline (e.g. CIV/STR/RAIL): STR
label | Revision Number: 1
label | Revision Date: 1/05/2023
label | ITP created by: Victor Mira
label | ITP approved for use by: Victor Mira
checkpoint-status | 1 - Panels - survey set out - Tolerance
label | REFERENCE: IFC Drawings
label | • MRP-052-C-RFL-DRG-33-CBE-CSW-1201
label | • MRP-052-C-RFL-DRG-33-CBE-CSW-1202
label | • MRP-052-C-RFL-DRG-33-CBE-CSW-1203
label | • MRP-052-C-RFL-DRG-33-CBE-CSW-1204
label | • VR 682.20
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Plan position shown on the drawings at the base of the wall shall not exceed ±15mm (refer to drawings for WP locations)
label | – – – – – – – – – – – – – – – – –
label | METHOD: Measure
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Base course panels
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: IP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: Surveyor/PE
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: This Checklist
label | – – – – – – – – – – – – – – – – –
text | Date Completed:
checkpoint-status | 2 - Mark - up panel for construction team
label | REFERENCE: Construction Manual
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Mark number of strips per row on the back of each panel.
label | – Mark design locatoin (Wall number, row and column) as per elevation drawings on the back of each panel
label | – – – – – – – – – – – – – – – – –
label | METHOD: Visual
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Each panel
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: IP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: SE
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: This Checklist
label | – – – – – – – – – – – – – – – – –
text | Date Completed:
checkpoint-status | 3 - Panel installation
label | REFERENCE: IFC Drawing:
label | Schedules:
label | • MRP-052-C-RFL-DRG-33-CBE-CSW-1302
label | • MRP-052-C-RFL-DRG-33-CBE-CSW-1403
label | • MRP-052-C-RFL-DRG-33-CBE-CSW-1503
label | • MRP-052-C-RFL-DRG-33-CBE-CSW-1602
label | Instructions:
label | • MRP-052-C-RFL-DRG-33-CBE-CSW-1803
label | • MRP-052-C-RFL-DRG-33-CBE-CSW-1804
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: RSS Panels are to be installed as per IFC Drawings and specified schedule.
label | – Check for correct architectural pattern
label | – Check for Weephole Locations
label | – Check the 19mm nominal gap to be maintained
label | – Check the 1 in 40 slope is to be maintained
label | – – – – – – – – – – – – – – – – –
label | METHOD: Visual, Measure
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Each panel
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: WP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: SE
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: This Checklist
label | – – – – – – – – – – – – – – – – –
text | Date Completed:
checkpoint-status | 4 - Panel installation - Abutment interfaces
label | REFERENCE: IFC Drawings
label | • MRP-052-C-SME-DRG-32-MPK-CSW-2052
label | • MRP-052-C-RFL-DRG-33-CBE-CSW-1105
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: 20mm nominal gap between panels and Abutment wall is to be mainatined
label | – 300mm wide x 6mm thk Galvanized plates fixed to abutment wall and Adjacent panel as per IFC drawings.
label | – 600mm wide BITAC tape installed
label | – – – – – – – – – – – – – – – – –
label | METHOD: Measure
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Where applicable
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: IP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: SE/PE
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: This Checklist
label | – – – – – – – – – – – – – – – – –
text | Date Completed:
checkpoint-status | 5 - Filter fabric - Installation
label | REFERENCE: IFC Drawings
label | • MRP-052-C-RFL-DRG-33-CBE-CSW-1803
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Install Filter Fabric against all vertical and horizontal joints
label | – – – – – – – – – – – – – – – – –
label | METHOD: Visual
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Each course of panel installation
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: IP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: SE
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: This Checklist
label | – – – – – – – – – – – – – – – – –
text | Date Completed:
checkpoint-status | 6 - Drainage - Strip Drain
label | REFERENCE: IFC Drawings
label | • MRP-052-C-SME-DRG-32-MPK-CSW-2053
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Install 150mm wide vertical strip drain "PRODRAIN PD20"-at every vertical joint between panels in RSS wall.
label | • Ensure no gap is formed between strip drain and RSS panels
label | – – – – – – – – – – – – – – – – –
label | METHOD: Visual
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Each course of panel installation
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: IP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: SE
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: This Checklist
label | – – – – – – – – – – – – – – – – –
text | Date Completed:
checkpoint-status | 7 - Panel installation - Survey reference points
label | REFERENCE: VR 682.21
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: To ensure compliance with the tolerances specified in clause 682.20, the Contractor shall install stable and permanent survey reference points on a not more than 5 m (horizontal) by 2 m (vertical) grid covering the whole face of the RSS
label | – – – – – – – – – – – – – – – – –
label | METHOD: Visual
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Each course of panel installation
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: IP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: Surveyor/SE
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: This Checklist
label | – – – – – – – – – – – – – – – – –
text | Date Completed:
checkpoint-status | 8 - Traceability of precast units and records
label | REFERENCE: VR 620.09
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Unique ID of precast panel is recorded.
label | ATTACH: marked-up elevation drawings or installation record with reference to panel ID
label | – – – – – – – – – – – – – – – – –
label | METHOD: Visual
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Each panel
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: IP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: SE/PE
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: Attached marked-up drawing or installation record
label | – – – – – – – – – – – – – – – – –
text | Date Completed:
checkpoint-status | 9 - Panels installation - Conformance Survey
label | REFERENCE: IFC Drawings
label | • VR 682.06
label | • VR 682.17
label | • VR 682.20
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: The level and alignment of each course of facing panels shall be checked progressively after placement of each course and prior to placement of the next course to ensure compliance with the dimensional and positional tolerances stated in the design.
label | The Contractor shall record the results of this checking together with details of any non-conformances and the associated corrective actions
label | – Relative displacement of adjoining smooth panel faces shall not exceed ±15mm measured normal to face of the wall
label | – Local deviation of the wall face at any location with a 3m straight edge, shall not exceed 15mm
label | – Variation in gap width between facing panels shall not exceed 5mm per meter length and 10mm over the full lenght of the gap
label | – The wall level shall not deviate from the specified level by more than ±20mm
label | – The tolerance of position measured at the top of the wall face shall not excedd 5mm per 1m of wall height
label | – The verticality of the RSS wall facing shall lean backward at a minimum slope of 1(H) in 40 (V)
label | Attach: Survey Report
label | – – – – – – – – – – – – – – – – –
label | METHOD: Survey, Measure
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Each course of panel installation
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: HP*
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: Surveyor/PE
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: Survey Report
label | – – – – – – – – – – – – – – – – –
text | Date Completed:
checklist-sectioned | ITP-012-STR-RSS Wall-Main | itp |  |  |  | Yes | ITP-012-STR-RSS Wall Main Rev 1 | cff17963-117f-4710-9ec3-3daf3faa28a7
checkpoint-group | Referenced Documentation
checkpoint-status | Referenced Documentation
label | Document Title: ITP-012-STR-RSS Wall-Main
label | ITP Description: RSS Wall-Main
label | Document Number (in Teambinder): MRP-0000-MRPA-ALT-ITP-00XX
label | Discipline (e.g. CIV/STR/RAIL): STR
label | Revision Number: 1
label | Revision Date: 1/05/2023
label | ITP created by: Victor Mira
label | ITP approved for use by: Victor Mira
label | 1.1 Non Dependent
label | Reference: VicRoads Section 682 November 2018
label | 1.2 Non Dependent
label | Reference: VicRoads Section 204 December 2015
label | 1.3 Non Dependent
label | Reference: IFC drawings
checkpoint-group | Preliminaries-Materials
checkpoint-status | 2.1 Concrete-Leveling Pad
label | REFERENCE: IFC drawings
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: CONCRETE COMPRESSIVE STRENGTH GRADE MUST NOT BE LESS THAN N25 FOR LEVELLING COURSE AND BACKING BLOCKS;
text | Reference: Teambinder MA number:
label | – – – – – – – – – – – – – – – – –
label | METHOD: Document Review
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Each element
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: HP*
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: PE/Nominated Authority
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: Material approval
text | Date Completed:
checkpoint-status | 2.2 Select fill
label | REFERENCE: IFC Drawings
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Select fill shall comply with the requirements of the RSS designer:
label | • UNIT WEIGHT: 22 ± 2 kN/m³
label | • INTERNAL FRICTION ANGLE ≥ 34.5°
label | ○ Gradation:
label | • 150mm: 100% PASSING
label | • 37.5mm: 60 TO 100% PASSING
label | • 9.5mm: 25 TO 100% PASSING
label | • 2.36mm: 15 TO 100% PASSING
label | • 0.6mm: 10 TO 100% PASSING
label | • 0.075mm: 0 TO 15% PASSING
label | ○ Electrochemical Properties:
label | • RESISTIVITY >1000 Ω-cm
label | • CHLORIDES <200 mg/kg
label | • SULPHATES <200 mg/kg
label | • ORGANIC CONTENT 0%
label | ○ Structural Properties:
label | • COEFFICIENT OF UNIFORMITY ≥ 5
label | • LIQUID LIMIT ≤ 30%
label | • PLASTICITY INDEX ≤ 12
label | • The select backfill must meet the minimum requirements of Vicroads Type A filling
textbox | Reference: Material approval in Teambinder
label | – – – – – – – – – – – – – – – – –
label | METHOD: Document Review
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Each material specification
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: HP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: Nominated Authority
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: Material approval
text | Date Completed:
holdpoint | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status | 2.3 General fill
label | REFERENCE: IFC Drawings
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Backfill behind the reinforced block shall be Vicroads Type B or better and:
label | pH > 5.5
label | CHLORIDES < 2000 mg/kg
label | SULPHATES < 1000 mg/kg
label | Reference: Material approval in Teambinder
label | – – – – – – – – – – – – – – – – –
label | METHOD: Document Review
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Each material specification
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: HP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: Nominated Authority
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: Material approval
text | Date Completed:
holdpoint | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status | 2.4 Perforated Pipe-material
label | REFERENCE: IFC Drawings
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Perforated plastic pipe perforations shall be a maximum width of 1.5mm and minimum length of 150mm per m2
label | Reference: Teambinder MA number:
label | – – – – – – – – – – – – – – – – –
label | METHOD: Document review, Measure
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Each wall
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: HP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: Nominated Authority
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: Material approval
text | Date Completed:
holdpoint | NOMINATED AUTHORITY HOLDPOINT
checkpoint-group | Preliminaries-Documents
checkpoint-status | 3.1 RSS Panels
label | REFERENCE: IFC drawings
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Precast supplier is required to provide the following Quality Assurance documentation for each element, typically this consists of:
label | i. Certificate of Compliance / Birth Certificate
label | – 1. Concrete strength;
label | – 2.Date of manufacture;
label | – 3.Unique Identification number;
label | – 4.Mass;
label | – 5.Confirmation of number, type and capacity of lifting inserts;
label | – 6.Quality assurance sign-off.
label | ii. Compressive strength test results
label | iii. Precast Lifting Design
label | iv. Pre-pour check sheet / ITP
label | v. Post-pour check sheet / ITP
label | vi. Covermeter check record
label | vii. Record of dimensional measurements
label | Collate: Precast Quality Assurance Documentation so it can be uploaded into Teambinder pre-cast supply Lot (don't attach it here)
textbox | Reference: Precast panels MDR Lot in TeamBinder:
label | – – – – – – – – – – – – – – – – –
label | METHOD: Document Review
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Once for each type of panels
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: IP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: PE
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: Precast panels Birth certificates and MDR Lot
text | Date Completed:
checkpoint-group | Pre-Construction Activities
checkpoint-status | 4.1 Foundation
label | REFERENCE: IFC Drawings
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: The foundation material beneath the RSS fill shall be inspected on site by a qualified geotechnical Engineerto ensure that the soil conditions meet the assumed material properties:
label | • Description: Stiff Clay or better
label | • Unit Weight: 18 kN/m3
label | • Effective friction angle: 28°
label | • Effective Cohession: 5 kPa
label | • Undrained cohesion: 80 kPa
label | – – – – – – – – – – – – – – – – –
label | METHOD: Test, Document Review, Visual
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Each retaining Wall
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: HP*
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: PE/Geotechnical Engineer
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: This ITP, Test results
text | Date Completed:
checkpoint-status | 4.2 Foundation
label | REFERENCE: IFC Drawings
label | • MRO-052-C-SME-DRG-32-MPK-CSW-2053
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Where the foundation material does not meet the assumed material parameters, the existing ground shall be replaced with VR Type A fill Compacted in accordance with VR 204
label | – Ground improvement works shall be keyed into surrounding material at minimum 200mm Bench width
label | – Ground improvement works shall extend beyond either side of bridge approach to detail show in IFC drawing
label | – – – – – – – – – – – – – – – – –
label | METHOD: Visual
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Each retaining wall
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: IP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: PE/Geotechnical Engineer
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: This ITP
text | Date Completed:
checkpoint-status | 4.3 Foundation
label | REFERENCE: VR 204.12, VR 204.11
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Areas upon which fills are to be constructed shall be test rolled in accordance with VR 173
label | • No Fill shall be placed against or within 3 meters of a structure until the foundation for the fill has been reviewed by the superintendant
label | – – – – – – – – – – – – – – – – –
label | METHOD: Visual
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Each retaining Wall
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: HP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: PE/Nominated Authority
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: This ITP
text | Date Completed:
holdpoint | NOMINATED AUTHORITY HOLDPOINT
checkpoint-status | 4.4 Levelling Pad-Survey Set out
label | REFERENCE: IFC Drawings
label | • VR 682.20
label | • MRP-052-C-RFL-DRG-33-CBE-CSW-1201
label | • MRP-052-C-RFL-DRG-33-CBE-CSW-1202
label | • MRP-052-C-RFL-DRG-33-CBE-CSW-1203
label | • MRP-052-C-RFL-DRG-33-CBE-CSW-1204
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Survey activities to be undertaken to ensure and validate that all Works meet level and location requirements within the tolerances as per the tables in IFC Drawings and Vicroads Specification
label | – – – – – – – – – – – – – – – – –
label | METHOD: Measure, Visual
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Each retaining Wall
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: IP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: Surveyor, SE/PE
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: This ITP
text | Date Completed:
checkpoint-group | Construction / Installation Activities
checkpoint-status | 5.1 Form Levelling pad
label | REFERENCE: IFC Drawings
label | • MRP-052-C-RFL-DRG-33-CBE-CSW-1201
label | • MRP-052-C-RFL-DRG-33-CBE-CSW-1202
label | • MRP-052-C-RFL-DRG-33-CBE-CSW-1203
label | • MRP-052-C-RFL-DRG-33-CBE-CSW-1204
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Form timber shutters to edge of levelling pad
label | – Levelling pad is a 500mm wide by 150mm thick unreinforced concrete footing
label | – The leveling course level shall NOT deviate from the specified level by mor than ±3mm.
label | – 20mm Nominal gap between levelling pad and adjacent ground beam is to be maintained
label | – – – – – – – – – – – – – – – – –
label | METHOD: Measure, Visual
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Each Lot
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: IP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: SE/Site Supervisor
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: This ITP
text | Date Completed:
checkpoint-status | 5.2 Leveling Pad Concrete Pour
label | REFERENCE: IFC Drawings
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Concrete to be placed in accordance with 610.
label | Attach: Concrete Delivery Docket
label | – – – – – – – – – – – – – – – – –
label | METHOD: Visual
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Each Lot
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: IP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: SE/Site Supervisor
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: Concrete Pour record
text | Date Completed:
checkpoint-status | 5.3 Leveling Pad Concrete Testing
label | REFERENCE: IFC Drawings
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Concrete testing for compressive strength shall be undertaken at the testing frequency specified in VicRoads Section 610.16 (b)
label | Attach: Concrete test report
label | – – – – – – – – – – – – – – – – –
label | METHOD: Document Review
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Each Lot
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: IP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: PE
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: Attach Concrete Test Report
text | Date Completed:
checkpoint-status | 5.4 Levelling Pad-Post Pour Survey-Levelling Course
label | REFERENCE: IFC Drawings
label | • MRP-052-C-RFL-DRG-33-CBE-CSW-1201
label | • MRP-052-C-RFL-DRG-33-CBE-CSW-1202
label | • MRP-052-C-RFL-DRG-33-CBE-CSW-1203
label | • MRP-052-C-RFL-DRG-33-CBE-CSW-1204
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Levelling course level shall not deviate from the specified level by more than ±3mm
label | – Plan position shown on the drawings at the base of the wall shall not exceed ±15mm (refer to drawings for WP locations)
label | – – – – – – – – – – – – – – – – –
label | METHOD: Measure, Visual
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Each retaining Wall
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: IP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: PE/Surveyor
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: Attach Survey Report
text | Date Completed:
checkpoint-status | 5.5 Wall Panels Installation
label | REFERENCE: 682.17
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: The level and alignment of each course of facing panels shall be checked progressively after placement of each course and prior to placement of the next course to ensure compliance with the dimensional and positional tolerances stated in the design.
label | • The Contractor shall record the results of this checking together with details of any non-conformances and the associated corrective actions
label | • Refer to checklist for each course of panels
label | Attach: Lot map
label | – – – – – – – – – – – – – – – – –
label | METHOD: Visual, Measure
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Each course of facing panel
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: HP*
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: PE/SE
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: Inspection record checklist: CHK-CIV-RSS Pre-cast panel installation
text | Date Completed:
checkpoint-status | 5.6 Drainage-base of the Wall
label | REFERENCE: IFC Drawings
label | • MRP-052-C-SME-DRG-32-MPK-CSW-2053
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: To install 300mmx300mmGranular backfill in Geotextile BIDIM A64 around 100mm Dia. Perforted plastic pipewith 0.5%min fall to 50mm Dia weepholesin RSS panels.
label | – Geotextile BIDIM A64
label | – 300mmx300mmGranular backfill
label | – 100mm Dia. Perforted plastic pipe
label | – Perforated pipe to have 0.5% mnimum fall to 50mm weepholes in RSS panels
label | – – – – – – – – – – – – – – – – –
label | METHOD: Visual
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Each wall
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: IP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: SE/PE
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: This Checklist
text | Date Completed:
checkpoint-status | 5.7 Fill
label | REFERENCE: 682.16
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: The Contractor shall submit compaction test results for each layer of fill placement to the Superintendent for review and acceptance.
label | • No further fill placement shall be allowed if the total thickness of fill placement is greater than 1 m measured from the last layer that has been accepted.
label | • If any layer is found to be not in compliance with the compaction requirement, that layer and the layers above it shall be removed.
label | • Refer to checklist for each fill layer
label | Attach: Lot map
label | – – – – – – – – – – – – – – – – –
label | METHOD: Visual, Test, Measure
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Each layer of fill
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: HP*
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: PE/SE
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: Inspection record checklist: CHK-CIV-RSS Fill installation
text | Date Completed:
checkpoint-group | Post-construction / Post-installation Activities
checkpoint-status | 6.1 As-built Survey
label | REFERENCE: MRPA Quality Management Plan
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Provide record of dimensional measurements to demonstrate that all Works meet level and location requirements within the tolerances
label | Attach: Survey As-built / Survey Report
label | – – – – – – – – – – – – – – – – –
label | METHOD: Document Review
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Each element
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: IP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: Surveyor, SE/PE/SPE
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: Survey Report
text | Date Completed:
checkpoint-status | 6.2 Wall Post construction monitoring
label | REFERENCE: VR 682.20, VR 682.21
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: The Contractor shall take measurements of the position of the RSS at the points defined in clause 682.20(a) to (f) at intervals not exceeding one month for the first six months immediately following completion of the RSS and at intervals not exceeding six months thereafter until the end of the Defects Liability Period.
label | (a) plan position shown on the drawings, at base of wall shall not exceed ⌖15 mm;
label | (b) relative displacement of adjoining smooth panel faces shall not exceed 15 mm measured normal to face of wall;
label | (c) local deviation of the wall face measured at any location with a 3 m straight edge shall not exceed 15 mm;
label | (d) the tolerance on position measured at the top of the wall face shall not exceed 5 mm per 1 metre of wall height;
label | (e) the wall level shall not deviate from the specified level by more than 20 mm;
label | (f) variation in gap width between facing panels shall not exceed 5 mm per metre length and 10 mm over the full length of the gap.
label | The measurements shall be recorded in writing and reported to the Superintendent within two weeks of the survey.
label | – – – – – – – – – – – – – – – – –
label | METHOD: Measure, Survey
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Each wall
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: IP
text | Date Completed:
checkpoint-status | 6.3 Non-conformance Report (NCR) Closure
label | REFERENCE: MRPA Quality Management Plan
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed.
label | – – – – – – – – – – – – – – – – –
label | METHOD: Document Review
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Once, prior to closure of this lot / element / Work area
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: HP*
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: SE/PE/SPE
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: This ITP
text | Date Completed:
checkpoint-status | Final Inspection
label | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
text | Name:
text | Position:
text | Date Completed:
holdpoint | Sign ITP