## Sheet1
ConQA Team Notes:
Document Title: |  | ITP-STR-CAMMS-Precast Crosshead (Supply & Installation)
ITP Description: |  | CAMMS-Precast Crosshead (Supply & Installation)
Discipline (e.g. CIV/STR/RAIL: |  | STR
Revision Number: |  | 0
Revision Date: |  | 2023-05-17
ITP created by: |  | Isaac El Zayat
ITP approved for use by: |  | Victor Mira
Special Notes to ConQA Team : |  | ITP to be used in CAMMS road
Inspection & Test Plan - Precast Crosshead (Supply & Installation)
[9 empty] | Revision: | 0
[9 empty] | Date: | 2023-05-17
Legend: HP: Hold Point, HP* Internal Hold Point, WP: Witness Point, IP: Inspection Point, SP: Surveillance Point
Item | Task/Activity Description | Reference | Acceptance Criteria | Inspection / Test |  |  | Responsibility | Verifying Documents | Date Completed | Sign-off
|  |  |  | Method | Frequency | Category
1 | Referenced Documentation
1.1 | Non Dependent | VicRoads Section 169 July 1993 | N/A | N/A | N/A | N/A | N/A | N/A | NA | N/A
1.2 | Non Dependent | VicRoads Section 610 March 2019 | N/A | N/A | N/A | N/A | N/A | N/A | NA | N/A
1.3 | Non Dependent | VicRoads Section 611 November 2018 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
1.4 | Non Dependent | VicRoads Section 613 June 2017 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
1.5 | Non Dependent | VicRoads Section 620 May 2009 | N/A | N/A | N/A | N/A | N/A | N/A | NA | N/A
2 | Preliminaries - Materials
2.1 | Grout - Product Selection - Epoxy Grout | IFC Drawings | Details of the materials and the proportions of grout mixture shall be submitted for review. Product to be selected based on the following criteria: i. have the required strength at 28 days as noted on the IFC drawings. ii. have the characteristics capable of being applied to the minimum and maximum thickness as noted on the IFC drawings. Enter: Teambinder Material Approval number [free text box] | Document Review | Once, for each product, prior to placement of product | HP | Nominated Authority | This ITP
3 | Preliminaries - Procedures & Documentation
3.1 | Precast Elements | IFC Drawings 610.47 (a) Table 610.474 620.09 | Precast supplier is required to provide the following Quality Assurance documentation for each element, typically this consists of: i. Certificate of Compliance / Birth Certificate ii. Compressive strength test results iii. Precast Lifting Design iv. Pre-pour check sheet / ITP v. Pre-stressing check sheet / ITP vi. Post-pour check sheet / ITP vii. Covermeter check record viii. Record of dimensional measurements to demonstrate compliance with dimensional tolerances of precast and bearing plates (where applicable) shown on table 610.473 Note: Different revisions of 610 have different clause numbers Collate: Precast Quality Assurance Documentation so it can be uploaded into Teambinder (don't attach it here) Enter: Teambinder Approval number [free text box] | Document Review | Each element | IP | PE/SPE | This ITP
4 | Pre-installation Activities
4.1 | Precast Element - Minimum Concrete Compressive Strength | 620.03 Ancon Lifting Design | Lifting of precast units to be minimum concrete compressive strength of 20 Mpa. Ancon lifting design requires minimum concrete compressive stgrength of 30 Mpa. Verify compressive strength test results prior to lift. | Document review | Each element | HP* | SE/PE/SPE | This ITP
4.2 | IFC Drawings | MRPA Quality Management Plan | Revision of the IFC drawings are current as per the drawing register (on Teambinder) | Document Review | Prior to starting Works and at regular intervals | HP* | All | This ITP
4.3 | Survey Set-out of Precast Elements | IFC Drawings 610.47 (a) Table 610.472 | Survey activities undertaken to ensure and validate that all Works meet level and location requirements within the tolerances as per the Table 610.473 as applicable to the element. | Measure | Each element | IP | Surveyor PE/SPE | This ITP
4.4 | Scabble (Green Cut) Column | 610.2 | Construction joints shall be prepared to produce a well-bonded interface between hardened concrete and freshly placed concrete. 3mm of coarse aggregate to be exposed. Surface to be moistened, with excess water removed. | Visual | Each element | IP | SE/PE/SPE | This ITP
4.5 | Install Packers | IFC Drawings Temporary Works Table 610.472 | Place packers to the survey marks at each column in accordance with approved temporary works and tolerances. Scabbled surface to be levelled where packers to be placed. Packers to be checked for survey tolerance of crosshead reduced level. (±10mm for reduced level for piers as per 610.472 (ix)) | Measure Visual | Each element | IP | Surveyor SE/PE/SPE | This ITP
4.6 | Bleed tube | IFC Drawings | Minimum 3 No.Bleed tubes per pile are installed | Visual | Each pile | IP | PE/SPE | This ITP
4.7 | Sealant & Bleed Tubes | IFC Drawings Product TDS / Application Guide | Seal perimeter of column, excluding 3 No. min bleed tubes per column to be equally spaced. Thin layer of wax compound to be applied to forms to minimise grout sticking. Do NOT pre-soak when using resin based grouts. | Visual | Each element | IP | SE/PE/SPE | This ITP
4.8 | Grout tubes | IFC Drawings | Grout tubes are inserted to the bottom of the corrugated sheath (Duct) | Visual Measure | Each Duct | IP | PE/SPE | This ITP
5 | Construction/Installation Activities
5.1 | Precast Handling | 620.07 Crane Lift Study | Unless otherwise specified, precast elements shall be lifted using the lifting points provided and supported with the top surface uppermost at all times. | Visual | Each element | IP | PE/SPE | This ITP
5.2 | Precast Placement | IFC Drawings 610.27 | Precast elements shall be placed onto the bearing shims and not released from the crane until sufficiently braced in accordance with the approved temporary works design and/or IFC drawings. The Gap between precast crosshead and pile Min 15mm Max 30mm | Measure Visual | Each element | IP | Surveyor SE/PE/SPE | This ITP
5.3 | Grout mixing | Manufacturer Instruction Product TDS / Application Guide | Pour the entire contents of the hardener pack into the base container. Mix the hardener slowly into the base using a slow speed heavy duty mixer. Once combined the product should be mixed at 350 to 400 RPM for 2 to 3 minutes until a uniform mix is obtained. Pot life @ 20 degrees celcius: 30mins | Visual | Each duct | HP* | PE/SPE | This ITP
5.4 | Grout injection - Bleed tubes | IFC Drawings | Grout allowed to flow until all bleed water is expelled and grout flows freely from each bleed tube. Then lock off bleed tube. | Visual | Each duct | HP* | PE/SPE | This ITP
5.5 | Grout injection - Ducts | IFC Drawings | Grout injected in a continuous pour until grout emerges from the top of all ducts Attach: Completed Grout Pour Checklist Attach: Completed Grout Pour Record | Visual | Each pile | HP* | PE/SPE | This ITP -Grout Pour Checklist
5.6 | Testing - Sampling Frequency | IFC Drawings 610.28 610.33 | Three (3) 75 mm test cubes shall be taken from the first batch of material mixed. Three (3) 75 mm cubes for every 100 kg of material used thereafter to test for compressive strength. The cubes shall be cured for seven days under laboratory-controlled conditions Test cubes shall be made in rigid steel moulds, cured and tested in accordance with AS 1478.2. The contact face of the concrete shall be flat and have a surface roughness between an amplitude of 0.5 mm to 1.5 mm, with a surface presenting similar to Grade 40 grit sandpaper. | Measure Visual | Each element | IP | SE/PE/SPE | This ITP
6 | Post-construction/installation Activities
6.1 | Grout Compressive strength test results | IFC Drawings | Two (2) cubes shall be tested at seven days and the third cube at 28 days to confirm compliance with the minimum compressive strength requirements. The minimum compressive strength of test cubes shall be50mpa At 28 days. ATTACH: Complete Test Results | Document Review | Each element | HP* | SE | This ITP
6.2 | As-built Survey | IFC Drawings 610.46 (a), Table 610.462 (November 2018) 610.47 (a) Table 610.472 (March/June 2019) | Provide record of dimensional measurements to demonstrate concrete members comply with tolerances as per the table 610.462 (November 2018) or 610.472 (March/June 2019) as applicable to the element. Attach: Survey As-builts / Survey Report | Document Review | Each element | IP | Surveyor SE/PE/SPE | This ITP
6.3 | Non-conformance Report (NCR) Closure | MRPA Quality Management Plan | Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed in CAMs. | Document Review | Once, prior to closure of this lot / element / Work area | HP* | SE/PE/SPE | This ITP
Final Inspection
On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
Print Name: Position: Signature: Date: / /