## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | ITP-034-STR-CAMMS-Precast Crosshead (Supply & Installation) | itp |  |  |  |  | ITP-034-STR-CAMMS-Precast Crosshead (Supply & Installation) Rev 0
section | Referenced Documentation
checkpoint | Referenced Documentation
label | Document Title: ITP-STR-CAMMS-Precast Crosshead (Supply & Installation)
label | ITP Description: CAMMS-Precast Crosshead (Supply & Installation)
label | Document Number (in Teambinder): MRP-0000-MRPA-ALT-ITP-00XX
label | Discipline (e.g. CIV/STR/RAIL): STR
label | Revision Number: 0
label | Revision Date: 17/05/2023
label | ITP created by: Isaac El Zayat
label | ITP approved for use by: Victor Mira
label | 1.1 Non Dependent
label | Reference: VicRoads Section 169 July 1993
label | 1.2 Non Dependent
label | Reference: VicRoads Section 610 March 2019
label | 1.3 Non Dependent
label | Reference: VicRoads Section 611 November 2018
label | 1.4 Non Dependent
label | Reference: VicRoads Section 613 June 2017
label | 1.5 Non Dependent
label | Reference: VicRoads Section 620 May 2009
section | Preliminaries - Materials
checkpoint | 2.1 Grout - Product Selection - Epoxy Grout
label | REFERENCE: IFC Drawings
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Details of the materials and the proportions of grout mixture shall be submitted for review. Product to be selected based on the following criteria:
label | i. have the required strength at 28 days as noted on the IFC drawings.
label | ii. have the characteristics capable of being applied to the minimum and maximum thickness as noted on the IFC drawings.
text | Enter: Teambinder Material Approval number
label | – – – – – – – – – – – – – – – – –
label | METHOD: Document Review
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Once, for each product, prior to placement of product
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: HP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: Nominated Authority
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: This ITP
text | Date Completed:
holdpoint | NOMINATED AUTHORITY HOLDPOINT
section | Preliminaries - Procedures & Documentation
checkpoint | 3.1 Precast Elements
label | REFERENCE: IFC Drawings 610.47 (a), Table 610.474, 620.09
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Precast supplier is required to provide the following Quality Assurance documentation for each element, typically this consists of:
label | i. Certificate of Compliance / Birth Certificate
label | ii. Compressive strength test results
label | iii. Precast Lifting Design
label | iv. Pre-pour check sheet / ITP
label | v. Pre-stressing check sheet / ITP
label | vi. Post-pour check sheet / ITP
label | vii. Covermeter check record
label | viii. Record of dimensional measurements to demonstrate compliance with dimensional tolerances of precast and bearing plates (where applicable) shown on table 610.473
label | Note: Different revisions of 610 have different clause numbers
label | Collate: Precast Quality Assurance Documentation so it can be uploaded into Teambinder (don't attach it here)
text | Enter: Teambinder Approval number
label | – – – – – – – – – – – – – – – – –
label | METHOD: Document Review
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Each element
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: IP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: PE/SPE
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: This ITP
text | Date Completed:
section | Pre-installation Activities
checkpoint | 4.1 Precast Element - Minimum Concrete Compressive Strength
label | REFERENCE: 620.03, Ancon Lifting Design
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Lifting of precast units to be minimum concrete compressive strength of 20 Mpa.
label | • Ancon lifting design requires minimum concrete compressive strength of 30 Mpa.
label | • Verify compressive strength test results prior to lift.
label | – – – – – – – – – – – – – – – – –
label | METHOD: Document review
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Each element
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: HP*
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: SE/PE/SPE
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: This ITP
text | Date Completed:
checkpoint | 4.2 IFC Drawings
label | REFERENCE: MRPA Quality Management Plan
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Revision of the IFC drawings are current as per the drawing register (on Teambinder)
label | – – – – – – – – – – – – – – – – –
label | METHOD: Document Review
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Prior to starting Works and at regular intervals
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: HP*
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: All
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: This ITP
text | Date Completed:
checkpoint | 4.3 Survey Set-out of Precast Elements
label | REFERENCE: IFC Drawings 610.47 (a), Table 610.472
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Survey activities undertaken to ensure and validate that all Works meet level and location requirements within the tolerances as per the Table 610.473 as applicable to the element.
label | – – – – – – – – – – – – – – – – –
label | METHOD: Measure
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Each element
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: IP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: Surveyor, PE/SPE
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: This ITP
text | Date Completed:
checkpoint | 4.4 Scabble (Green Cut) Column
label | REFERENCE: 610.2
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Construction joints shall be prepared to produce a well-bonded interface between hardened concrete and freshly placed concrete.
label | • 3mm of coarse aggregate to be exposed.
label | • Surface to be moistened, with excess water removed.
label | – – – – – – – – – – – – – – – – –
label | METHOD: Visual
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Each element
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: IP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: SE/PE/SPE
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: This ITP
text | Date Completed:
checkpoint | 4.5 Install Packers
label | REFERENCE: IFC Drawings, Temporary Works, Table 610.472
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Place packers to the survey marks at each column in accordance with approved temporary works and tolerances.
label | • Scabbled surface to be levelled where packers to be placed.
label | • Packers to be checked for survey tolerance of crosshead reduced level. (±10mm for reduced level for piers as per 610.472 (ix))
label | – – – – – – – – – – – – – – – – –
label | METHOD: Measure, Visual
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Each element
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: IP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: Surveyor, SE/PE/SPE
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: This ITP
text | Date Completed:
checkpoint | 4.6 Bleed tube
label | REFERENCE: IFC Drawings
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Minimum 3 No.Bleed tubes per pile are installed
label | – – – – – – – – – – – – – – – – –
label | METHOD: Visual
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Each pile
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: IP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: PE/SPE
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: This ITP
text | Date Completed:
checkpoint | 4.7 Sealant & Bleed Tubes
label | REFERENCE: IFC Drawings, Product TDS / Application Guide
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Seal perimeter of column, excluding 3 No. min bleed tubes per column to be equally spaced.
label | • Thin layer of wax compound to be applied to forms to minimise grout sticking.
label | • Do NOT pre-soak when using resin based grouts.
label | – – – – – – – – – – – – – – – – –
label | METHOD: Visual
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Each element
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: IP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: SE/PE/SPE
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: This ITP
text | Date Completed:
checkpoint | 4.8 Grout tubes
label | REFERENCE: IFC Drawings
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Grout tubes are inserted to the bottom of the corrugated sheath (Duct)
label | – – – – – – – – – – – – – – – – –
label | METHOD: Visual, Measure
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Each Duct
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: IP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: PE/SPE
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: This ITP
text | Date Completed:
section | Construction/Installation Activities
checkpoint | 5.1 Precast Handling
label | REFERENCE: 620.07, Crane Lift Study
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Unless otherwise specified, precast elements shall be lifted using the lifting points provided and supported with the top surface uppermost at all times.
label | – – – – – – – – – – – – – – – – –
label | METHOD: Visual
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Each element
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: IP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: PE/SPE
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: This ITP
text | Date Completed:
checkpoint | 5.2 Precast Placement
label | REFERENCE: IFC Drawings 610.27
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Precast elements shall be placed onto the bearing shims and not released from the crane until sufficiently braced in accordance with the approved temporary works design and/or IFC drawings.
label | ○ The Gap between precast crosshead and pile
label | • Min 15mm
label | • Max 30mm
label | – – – – – – – – – – – – – – – – –
label | METHOD: Measure, Visual
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Each element
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: IP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: Surveyor, SE/PE/SPE
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: This ITP
text | Date Completed:
checkpoint | 5.3 Grout mixing
label | REFERENCE: Manufacturer Instruction, Product TDS / Application Guide
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Pour the entire contents of the hardener pack into the base container. Mix the hardener slowly into the base using a slow speed heavy duty mixer.
label | • Once combined the product should be mixed at 350 to 400 RPM for 2 to 3 minutes until a uniform mix is obtained.
label | • Pot life @ 20 degrees celcius: 30mins
label | – – – – – – – – – – – – – – – – –
label | METHOD: Visual
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Each duct
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: HP*
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: PE/SPE
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: This ITP
text | Date Completed:
checkpoint | 5.4 Grout injection - Bleed tubes
label | REFERENCE: IFC Drawings
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Grout allowed to flow until all bleed water is expelled and grout flows freely from each bleed tube. Then lock off bleed tube.
label | – – – – – – – – – – – – – – – – –
label | METHOD: Visual
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Each duct
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: HP*
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: PE/SPE
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: This ITP
text | Date Completed:
checkpoint | 5.5 Grout injection - Ducts
label | REFERENCE: IFC Drawings
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Grout injected in a continuous pour until grout emerges from the top of all ducts
label | Attach: Completed Grout Pour Checklist
label | Attach: Completed Grout Pour Record
label | – – – – – – – – – – – – – – – – –
label | METHOD: Visual
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Each pile
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: HP*
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: PE/SPE
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: This ITP -Grout Pour Checklist
text | Date Completed:
checkpoint | 5.6 Testing - Sampling Frequency
label | REFERENCE: IFC Drawings 610.28, 610.33
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Three (3) 75 mm test cubes shall be taken from the first batch of material mixed.
label | • Three (3) 75 mm cubes for every 100 kg of material used thereafter to test for compressive strength.
label | • The cubes shall be cured for seven days under laboratory-controlled conditions
label | • Test cubes shall be made in rigid steel moulds, cured and tested in accordance with AS 1478.2.
label | • The contact face of the concrete shall be flat and have a surface roughness between an amplitude of 0.5 mm to 1.5 mm, with a surface presenting similar to Grade 40 grit sandpaper.
label | – – – – – – – – – – – – – – – – –
label | METHOD: Measure, Visual
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Each element
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: IP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: SE/PE/SPE
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: This ITP
text | Date Completed:
section | Post-construction/installation Activities
checkpoint | 6.1 Grout Compressive strength test results
label | REFERENCE: IFC Drawings
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Two (2) cubes shall be tested at seven days and the third cube at 28 days to confirm compliance with the minimum compressive strength requirements.
label | • The minimum compressive strength of test cubes shall be50mpa At 28 days.
label | ATTACH: Complete Test Results
label | – – – – – – – – – – – – – – – – –
label | METHOD: Document Review
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Each element
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: HP*
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: SE
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: This ITP
text | Date Completed:
checkpoint | 6.2 As-built Survey
label | REFERENCE: IFC Drawings
label | • 610.46 (a), Table 610.462 (November 2018)
label | • 610.47 (a), Table 610.472 (March/June 2019)
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Provide record of dimensional measurements to demonstrate concrete members comply with tolerances as per the table 610.462 (November 2018) or 610.472 (March/June 2019) as applicable to the element.
label | Attach: Survey As-builts / Survey Report
label | – – – – – – – – – – – – – – – – –
label | METHOD: Document Review
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Each element
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: IP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: Surveyor, SE/PE/SPE
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: This ITP
text | Date Completed:
checkpoint | 6.3 Non-conformance Report (NCR) Closure
label | REFERENCE: MRPA Quality Management Plan
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed in CAMs.
label | – – – – – – – – – – – – – – – – –
label | METHOD: Document Review
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Once, prior to closure of this lot / element / Work area
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: HP*
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: SE/PE/SPE
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: This ITP
text | Date Completed:
checkpoint | Final Inspection
label | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
text | Name:
text | Position:
text | Date Completed:
holdpoint | Sign ITP