## Folder Structure
South Elevation | Level 0 | A. Rear Dowsil Joint Sealant
C. Mid Dowsil Joint Sealant
D. External Spectrum 1
| Level 1 | A. Rear Dowsil Joint Sealant
C. Mid Dowsil Joint Sealant
D. External Spectrum 1
| Level 2 | A. Rear Dowsil Joint Sealant
C. Mid Dowsil Joint Sealant
D. External Spectrum 1
East Elevation | Level 0 | A. Rear Dowsil Joint Sealant
C. Mid Dowsil Joint Sealant
D. External Spectrum 1
| Level 1 | A. Rear Dowsil Joint Sealant
C. Mid Dowsil Joint Sealant
D. External Spectrum 1
| Level 2 | A. Rear Dowsil Joint Sealant
C. Mid Dowsil Joint Sealant
D. External Spectrum 1
West Elevation | Level 1 | A. Rear Dowsil Joint Sealant
B. External Dowsil Joint Sealant
| Level 2 | A. Internal Dowsil Joint Sealant
B. External Dowsil Joint Sealant
North Elevation | Level 0 | A. Rear Dowsil Joint Sealant
C. Mid Dowsil Joint Sealant
D. External Spectrum 1
| Level 1 | A. Rear Dowsil Joint Sealant
C. Mid Dowsil Joint Sealant
D. External Spectrum 1
| Level 2 | A. Rear Dowsil Joint Sealant
C. Mid Dowsil Joint Sealant
D. External Spectrum 1

## A. Rear Dowsil Joint Sealant
Type | Name | Value
Checklist | Internal Dowsil Joint Sealant Checklist
Checkpoint | Work Area/Substrate is clean, dry and ready to start | Photo Required
Checkpoint | Record product batch numbers | Photo Required
Checkpoint | Install PEF backing rod to horizontal & vertical joints | Photo Required
Checkpoint | Apply primer or complete an alcohol wipe
Checkpoint | Apply DOWSIL 700 to horizontal & vertical joints | Photo Required
Checkpoint | Joint sealant installed correctly and as per drawings/specification | Photo Required
Checkpoint | Work area is left clean & tidy | Photo Required

## B.External Dowsil Joint Sealant
Type | Name | Value
Checklist | External Dowsil Joint Sealant Checklist
Checkpoint | Work Area/Substrate is clean, dry and ready to start | Photo Required
Checkpoint | Record product batch numbers | Photo Required
Checkpoint | Install PEF backing rod to horizontal connection | Photo Required
Checkpoint | Apply primer or complete an alcohol wipe to horizontal connection | Photo Required
Checkpoint | Apply DOWSIL 700 to horizontal connection | Photo Required
Checkpoint | Install PEF backing rod to horizontal & vertical joints | Photo Required
Checkpoint | Apply primer or complete an alcohol wipe | Photo Required
Checkpoint | Form drainage holes with PEF rod | Photo Required
Checkpoint | Apply DOWSIL 700 to horizontal & vertical joints | Photo Required
Checkpoint | Joint sealant installed correctly and as per drawings/specification | Photo Required
Checkpoint | Work area is left clean & tidy | Photo Required

## C.Mid Dowsil Joint Sealant
Type | Name | Value
Checklist | Mid Dowsil Joint Sealant Checklist
Checkpoint | Work Area/Substrate is clean, dry and ready to start | Photo Required
Checkpoint | Record product batch number | Photo Required
Checkpoint | Install PEF backing rod to horizontal & vertical joints | Photo Required
Checkpoint | Apply primer or complete an alcohol wipe | Photo Required
Checkpoint | Apply Spectrum 1 sealant to horizontal & vertical joints | Photo Required
Checkpoint | Joint sealant installed correctly and as per drawings/specification | Photo Required
Checkpoint | Work area is left clean & tidy | Photo Required

## D.External Spectrum 1
Type | Name | Value
Checklist | External Spectrum 1 Joint Sealant Checklist
Checkpoint | Work Area/Substrate is clean, dry and ready to start | Photo Required
Checkpoint | Record product batch numbers | Photo Required
Checkpoint | Install PEF backing rod to horizontal & vertical joints | Photo Required
Checkpoint | Apply primer or complete an alcohol wipe | Photo Required
Checkpoint | Form drainage holes with PEF rod | Photo Required
Checkpoint | Apply Spectrum 1 to horizontal & vertical joints | Photo Required
Checkpoint | Joint sealant installed correctly and as per drawings/specification | Photo Required
Checkpoint | Work area is left clean & tidy | Photo Required