## GEO
Inspection and Test Plan
Project Information |  |  |  | Inspection and Test Plan Information
Project |  | Alamein, George and Main St Intersection Upgrades |  | Lot Number |  |  |  |  | Date | Start | Finish
Project No |  | 24 053 |  | Location
Client |  | Logan City Council | [6 empty] | Chainage | From | To
Contract No |  | CD70 |  | Description
Specification |  | MRTS57 July 2017 Geotextiles for Paving application |  | Activity | Geotextiles for paving applications
Acceptance of Activity
# | Acceptance Criteria |  |  |  |  | Reference | Item Check | QA | Client | Date | NCR
1 | Geotextile Filtration & Strength Class |  |  |  |  | Drawing Notes | Check and Verify |  | N/A
Geotextile to be used as specified in approved drawings
2 | Storage, packaging and identification on site |  |  |  |  | MRTS27 Clause 7 | Check and Verify |  | N/A
Geotextiles shall be stored under protective cover or wrapped with a waterproof, opaque UV protective sheeting to avoid any damage prior to installation. Geotextiles shall not be stored directly on the ground or in any manner in which they may be affected by heat. The method of storage shall be in accordance with any other recommendations set by the manufacturer. The protected geotextile rolls shall be clearly labelled showing manufacturer, type of geotextile and batch number identification number
3 | Geotextile Construction Procedure |  |  |  |  | MRTS57 Clause 5.2 | Milestone
A construction procedure detailing all work described in this Technical Specification shall be prepared. The construction procedure shall be consistent with the guidelines set out in the Transport and Main Road’s Pavement Rehabilitation Manual April 2012, Sections 4.4.6 to 4.4.6.8. The proposed construction procedure shall be submitted to the Administrator at least 14 days prior to the commencement of any works related to the placement of paving geotextile(s)
4 | Approval of construction Procedure |  |  |  |  | MRTS57 Clause 5.2 | Hold Point 1
No works related to the placement of paving geotextile(s) shall commence until the construction procedures have been approved by the Administrator and the Administrator has given the Contractor permission to proceed.
3 | Ordering - Technical Data |  |  |  |  | MRTS57 Cl 8.2 | Milestone
At least 14 days prior to the proposed ordering date of any geotextile, the Contractor shall submit to the Administrator a copy of the proposed manufacturer’s technical data sheet and a sample of the proposed geotextile from the manufacturer demonstrating compliance with this Technical Specification
4 | Ordering |  |  |  |  | MRTS57 Cl 8.2 | Hold Point 2
The Contractor shall not order any geotextile prior to the acceptance of that geotextile by the Administrator.
5 | Delivery |  |  |  |  | MRTS57 Cl 8.4 | Check and Verify |  | N/A
With each batch of geotextile incorporated in the Works, a certificate of compliance stating that the geotextile complies with all the requirements of this Technical Specification as appropriate to the application, together with test results reported on NATA endorsed test documents, shall be included in the Quality Records
5 | Surface Terperature |  |  |  |  | MRTS57 Cl 9.3 | Check and Verify |  | N/A
Spraying of bitumen or placement of geotextile shall not commence until the temperature of the surface of the pavement is above the temperature specified in MRTS11 Sprayed Bituminous Surfacing
6 | Overlapping and pinning |  |  |  |  | Drawing Notes NL-02 | Check and Verify |  | N/A
Edges of the geotextile seperator shall be overlapped by at least 300mm, and anchor pins placed at 1m minimum spacing along the geotextile seperator perimeter if required to maintain the position.
7 | Filling over installed geotextile |  |  |  |  | MRTS27 Clause 9.4 | Check and Verify |  | N/A
No construction equipment shall stand or travel directly on the laid geotextile. The initial layer of cover material shall be placed over the geotextile prior to construction equipment travelling over the area concerned.
Inspection and Test Plan
8 | Site sampling |  |  |  |  | MRTS27 Clause 10.2 | Check and Verify |  | N/A
Where the total required batch size is less than 5,000 m², Site sampling and testing need not be undertaken
9 | Acceptance |  |  |  |  | MRTS27 Clause 10.4 | HOLD POINT
Geotextile shall not be placed prior to acceptance of the test results by the Administrator.
Final Sign off and Approval - Conformance with the Specification
Name of Cient's Representative |  |  | Signature |  |  |  |  | Date
Name of Contractor's Representative |  |  | Signature |  |  |  |  | Date

## CAG
Inspection and Test Plan
Project Information |  |  |  | Inspection and Test Plan Information
Project |  | Alamein, George and Main St Intersection Upgrades |  | Lot Number |  |  |  |  | Date | Start | Finish
Project No |  | 24 053 |  | Location
Client |  | Logan City Council | [6 empty] | Chainage | From | To
Contract No |  | CD70 |  | Description | Clearing and Grubbing
Specification |  | LCC Standard Specification 1 (Earthworks) |  | Activity | Clearing and Grubbing
Acceptance of Activity
# | Acceptance Criteria |  |  |  |  | Reference | Item Check | QA | Client | Date | NCR
1 | Clearing Requirements |  |  |  |  | LCC SS 1 Part 2.1 | Check and Verify |  | N/A
Where an area of the premises are required to be cleared, the clearing includes the removal of all artificial obstructions including fences, rubbish unnecessary structures, building foundations, obsolete pipelines and the like plants (including stumps and boulders) other than the plants required to be retained as shown on the approved drawings;
2 | Extent of clearing and grubbing |  |  |  |  | LCC SS 1 Part 2.2 & 3.1 | Check and Verify |  | N/A
The extent of the cleared area is limited to the minimum area of the premises to be occupied by the completed earthworks or 1 metre on each side of the completed earthworks or the minimum area of the premises required to safely install a service. Grubbing, being the removal from the ground of trees, roots and stumps to a depth of 300mm below the surface of the ground, is carried out across the entire cleared area, any area which is identified as an area not to be disturbed, is to be fenced off.
3 | Removal of material from the premises |  |  |  |  | LCC SS 1 Part 2.4 | Check and Verify |  | N/A
Cleared plants are disposed of by mulching and reusing the mulch on the premises as far as possible. All material, other than plant material that is mulched and reused on the premises, is removed from the premises to a place approved by the local government, no material is to be burnt on site
4 | Material for Organic Mulch |  |  |  |  | MRTS04 Clause 7.2.4 | Check and Verify |  | N/A
Where site manufactured mulch is required in accordance with MRTS16 Landscape and Revegetation Works or MRTS52 Erosion and Sediment Control, processing of such material shall also be carried out in accordance with the Material and Construction requirements of MRTS16 Landscape and Revegetation Works.
4 | Fauna Habitat Logs |  |  |  |  | MRTS04 Clause 7.2.5 | Check and Verify |  | N/A
Hollow timber which is identified as being suitable for fauna habitat logs shall be relocated to areas clear of construction activities as follows: a) behind batters b) behind proposed safety barriers but not within any hazard free zone, and c) areas at least 9 m clear of carriageways. Fauna habitat log density shall not exceed 20 m length per 100 m² area. Logs shall not be placed in waterways or in any area where they are likely to be struck by errant vehicles.
Inspection and Test Plan
6 | Sugar Cane and Banana Plants |  |  |  |  | MRTS04 Clause 7.2.6 | Check and Verify |  | N/A
Particular attention shall be taken to ensure that sugar cane and banana plant root systems are completely removed and disposed of. Any regrowth of sugar cane and/or banana plants occurring during the Contract, including the Defects Liability Period, shall be removed.
7 | Disposal of Clear and Grub |  |  |  |  | MRTS04 Clause 7.2.8 | Check and Verify |  | N/A
Cleared and grubbed material other than that mulched under Clause 7.2.4 shall be disposed of in any areas stated in Clause 6 of Annexure MRTS04.1. If no such disposal instructions are stated, the cleared and grubbed material shall be removed from the Site and disposed of in accordance with all relevant Statutory Requirements including the requirements in MRTS51 Environmental Management.Any burning of cleared and grubbed materials shall be carried out strictly in accordance with the requirements of the Contract.
5 | Additional Requirements: |  |  |  |  | MRTS04 Clause 7.2.8 | Check and Verify |  | N/A
Within the limits of the clearing and grubbing, but clear of earthworks operations, any existing local irregularities of the natural surface are trimmed so as not to cause a hazard to errant vehicles. The surface is lightly compacted when necessary to provide a surface consistent with that existing prior to the Works
Final Sign off and Approval - Conformance with the Specification
Name of Cient's Representative |  |  | Signature |  |  |  |  | Date
Name of Contractor's Representative |  |  | Signature |  |  |  |  | Date

## Traffic
Inspection and Test Plan
Project Information |  |  |  | Inspection and Test Plan Information
Project |  | Alamein, George and Main St Intersection Upgrades |  | Lot Number |  |  |  |  | Date | Start | Finish
Project No |  | 24 053 |  | Location
Client |  | Logan City Council |  | Description |  |  |  |  | Chainage | From | To
Contract No |  | CD70
Specification |  | MRTS 02 November 2019 |  | Activity | Traffic Management on Site
Acceptance of Activity
# | Acceptance Criteria |  |  |  |  | Reference | Item Check | QA | Client | Date | NCR
1 | Nominated traffic officer training/experience requirements |  |  |  |  | MRTS02 Cl 5.2. | Check and Verify |  | N/A
The Contractor's Nominated Traffic Officer submitted to the Administrator and meets the requirements as specified
2 | Traffic management plan submission and approval |  |  |  |  | LCC SS 10 Part 2.1.1 | Hold Point
A traffic management plan for the works is provided to the local governement and approved prior to the commencement of work and complies with the MUTCD, any changes to the TMP will be provided
3 | Traffic guidance scheme submission and consideration |  |  |  |  | MRTS02 Cl 6.2 | Hold Point 2
All TGS's prepared by a suitably qualified person and submitted and approved by the Administrator
4 | Traffic Management Plan Alterations |  |  |  |  | LCC SS 10 Part 2.1.3 | Milestone
Any variation to the traffic management plan made during the work, is provided to the Administrator
4 | Dust Suppression |  |  |  |  | LCC SS 10 Part 2.5 | Check and Verify |  | N/A
Adequate precautions are taken to minimise dust or dust-related conditions during any activity which may affect the safety and general comfort of any person. Regular applications of water are applied to any roads or structures whilst completing earthworks
5 | Temporary road safety barriers |  |  |  |  | MRTS02 Cl 6.5.11 & Annexure 2.1 | Check and Verify |  | N/A
Temporary Road Safety Barriers (TRSB) shall be used to contain and redirect errant vehicles so as to reduce the likelihood of them entering the work site - Provision shall be made for TRSB At locations where work is to be close to traffic, and in accordance with Worker safety requirements in MUTCD Part 3; - Only those TRSB which are included in the Transport and Main Roads – Road Safety Barrier Systems, End Treatments and other related Road Safety Devices shall be used - All TRSB and end treatments shall be installed in accordance with the department's Standard Drawings and/or the manufacturer's specifications
6 | Temporary line marking |  |  |  |  | LCC SS 10 Part 2.8.4 | Check and Verify |  | N/A
Details of proposed temporary pavement markings are submitted to the local government for approval at least two working days prior to the proposed installation of the temporary pavement.
7 | Traffic Mmanement inspection reporting |  |  |  |  | MRTS02 Cl 7.5 | Milestone
The officer undertaking the Traffic Management Inspection shall provide a report to the Contractor for its action. The Contractor shall forward to the Administrator, within one week of the receipt of the report, the reports and findings, together with documentation of any actions taken in regard to the findings.
Final Sign off and Approval - Conformance with the Specification
Name of Client's Representative |  |  | Signature |  |  |  |  | Date
Name of Contractor's Representative |  |  | Signature |  |  |  |  | Date
Comments

## Environment Management
Inspection and Test Plan
Project Information |  |  |  | Inspection and Test Plan Information
Project |  | Alamein, George and Main St Intersection Upgrades |  | Lot Number | EM | CD70 |  |  | Date | Start | Finish
Project No |  | 24 053 |  | Location
Client |  | Logan City Council | [6 empty] | Chainage | From | To
Contract No |  | CD70 |  | Description
Specification |  | MRTS 51 Nov 2019 |  | Activity | Environmental Management Systems
Acceptance of Activity
# | Acceptance Criteria |  |  |  |  | Reference | Item Check | QA | Client | Date | NCR
1 | Environmental Inspection |  |  |  |  | Internal | Check and Verify |  | N/A
Enviromental site inspections to be conducted daily against all licences, permits, approvals and other environmental performance requirements all Inspection to be documented in donesafe. The Contractor’s Environmental Representative shall undertake and document Weekly Site Inspections.
2 | [6 empty] | Hold Point 1
3 | [6 empty] | Check and Verify |  | N/A
4 | [6 empty] | Hold Point 2
5 | [6 empty] | Check and Verify |  | N/A
6 | [6 empty] | Check and Verify |  | N/A
2 | Management Plan |  |  |  |  | MRTS51 Cl 6.3 | Hold Point 1
Environmental Management Plan (Construction) submitted in accordance with Conditions of Contract.
3 | Approval Environmental Management Plan |  |  |  |  | MRTS51 Cl 6.3 | Check and Verify |  | N/A
Works shall not commence until the Environmental Management Plan (Construction) has been assessed for suitability by the Administrator and approved.
4 | Amendments |  |  |  |  | MRTS51 Cl 6.4 | Hold Point 2
Amendments to the Environmental Management Plan (Construction) to be submitted on a monthly bases for assessment of suitability by the Administrator.
5 | Noise Monitoring |  |  |  |  | Internal | Check and Verify |  | N/A
Noise monitoring shall be undertaken as per the contract specifications
6 | Water quality |  |  |  |  | MRTS51 Cl 8.2 | Check and Verify |  | N/A
Water quality monitoring undertaken as per requirements in MRTS52 and otherwise specified in contract
7 | Erosion and Sediment Control |  |  |  |  | MRTS51 Cl 8.3 | Check and Verify |  | N/A
Requirements relating to Erosion and Sediment Control are contained within MRTS52
8 | Areas of cultural significance |  |  |  |  | MRTS51.1 Cl 2.2 | Check and Verify |  | N/A
Areas of cultural significance have been identified and are managed as per Clause 3 of Annexure MRTS51.1.
8 | Vibration monitoring condition survey |  |  |  |  | MRTS51 Cl 8.6.2.1 | Check and Verify |  | N/A
Vibration monitoring condition survey of premises, buildings and structures at risk of damage (including those listed in Clause 5 of Annexure MRTS51.1) vibration sensitive receptors.
9 | Dilapidation Report |  |  |  |  | MRTS51 Cl Clause 8.6.2.3 | Check and Verify |  | N/A
A copy of the condition/dilapidation survey for vibration has been given to the Administrator before any works that cause vibration start (5 days) - Condition surveys to be undertaken at the Locations listed in Cl 5.5 of the annexure
10 | Air Quality |  |  |  |  | MRTS51 Cl Clause 8.7.3 | Check and Verify |  | N/A
Construction activities have not resulted in air quality impacts that cause environmental nuisance or harm. Burning material not permitted on site
12 | [5 empty] | MRTS51 Cl 8.7.2 | Check and Verify |  | N/A
If burning of material is required, it was specifically allowed by Cl 6 of Annexure MRTS51.1 or approval obtained from Queensland Fire and Rescue Authority prior to burning.
Inspection and Test Plan
11 | Acid Sulphate Soil |  |  |  |  | MRTS51 Cl 8.8 | Check and Verify |  | N/A
Acid Sulphate Soils have been managed as per the requirements of MRTS04
12 | Contaminated sites |  |  |  |  | MRTS51 Cl 8.9.5 | Check and Verify |  | N/A
Contaminated sites (contaminated soils, waste dumps, unexploded ordinances ) within the worksite have been addressed as per requirements of MRTS04.
13 | Fauna |  |  |  |  | MRTS51 Cl 8.10.1 | Check and Verify |  | N/A
No harm caused to native fauna. Areas of significance and related management requirements are stated in contract. Contact details for emergency wildlife care shall be included on project emergency contact list.
16 | [5 empty] | MRTS51 Cl 8.10.2 | Check and Verify |  | N/A
Where stated in Cl 8.2 of Annexure MRTS51.1 the contractor shall engage persons authorised by Queensland Parks and Wildlife Service to attend the site to carry out an inspection of the site and subsequent capture or relocation of any fauna. Injury or death of fauna know as rare, endangered, or vulnerble shall be reported immediately to the Administrator and reported in the monthly report
14 | Vegitation |  |  |  |  | MRTS51 Cl 8.11.1 | Check and Verify |  | N/A
Management of vegetation within the worksite. The daily site inspections shall include visual assessments of vegetation management measures.
15 | Pest Management |  |  |  |  | MRTS51 Cl8.12.2 | Check and Verify |  | N/A
All declared pest known to occur within the worksite and any associated management requirements are stated in the contract have been managed and prevented from spreading on and off site
16 | Chemicals & Fulels |  |  |  |  | MRTS51 8.14.3 | Check and Verify |  | N/A
All chemicals and fuels within the worksite are contained so as not to cause environmental nuisance or harm. Spill kits response equipment are available on site for use in emergency
Inspection and Test Plan
Final Sign off and Approval - Conformance with the Specification
Name of Cient's Representative |  |  | Signature |  |  |  |  | Date
Name of Contractor's Representative |  |  | Signature |  |  |  |  | Date

## UP
Inspection and Test Plan
Project Information |  |  |  | Inspection and Test Plan Information
Project |  | Alamein, George and Main St Intersection Upgrades |  | Lot Number | UP | CD70 |  |  | Date | Start | Finish
Project No |  | 24 053 |  | Location
Client |  | Logan City Council |  | Description |  |  |  |  | Chainage | From | To
Contract No |  | CD70
Specification |  | MRTS 05 July 2022 |  | Activity | Unbound Pavement
Acceptance of Activity
# | Acceptance Criteria |  |  |  |  | Reference | Item Check | QA | Client | Date | NCR
1 | Acceptance of Construction Procedures for unbound pavement Works |  |  |  |  | MRTS05 Cl 5.2.1 | Hold Point 1
No unbound pavement Works shall commence until all relevant construction procedures have been accepted by the Administrator
2 | Submit Construction Procedure for aggregate production |  |  |  |  | MRTS05 Cl 5.2.2 | Milestone
The Material Production Procedures shall be submitted to the Administrator at least seven days prior to the commencement of material production for the Works
3 | Unbound Pavement construction procedure |  |  |  |  | MRTS05 Cl 5.2.3 | Milestone
The Unbound Pavement Construction Procedure shall be submitted to the Administrator at least 14 days prior to the commencement of unbound pavement Works.
4 | Supplier Registration and source Material assessment |  |  |  |  | MRTS05 Cl 6.1 | Hold Point 2
The written permission of the Administrator is required prior to material being supplied to or used in the Works from any source nad the current TMR registration certificate for all sources to be used in the works shall be submitted to the administror 7 days prior to works beginning
5 | Bitumen Binder |  |  |  |  | General | Ckeck and Verify |  | N/A
All asphalt shall be placed in accordance with design drawings and as per drawings GW001 & LS002
6 | Compaction |  |  |  |  | MRTS05 CL 8.4.3(a) | Check and Verify |  | N/A
Type 2.1 material shall be compacted to 100% modified compaction
7 | Alignment, Grade and Crossfall Tolerance for base course |  |  |  |  | LCC SS 6 Part 5.1.1 | Check and Verify |  | N/A
Tolerances for base cousre pavement are as follows: - Design Level: +15mm -10mm - Thickness tolerance: +15mm -15mm - Shape Tolerance: 15mm in 3 meters maximum
8 | Proof Rolling |  |  |  |  | MRTS05 Cl 9.4.7 | Witness Point 2
Each unbound pavement layer shall be tested for perceptible surface deformation by ‘proof rolling’ the pavement, in the presence of the Administrator. All areas of unbound pavements shall be ‘proof rolled’, including all trafficked lanes, shoulders and other areas
9 | Lot Acceptance |  |  |  |  | MRTS05 Cl 9.5.1 & LCC SS 6 4.2.1 | Hold Point 6
Unless otherwise approved by the Administrator, no unbound pavement layer shall be covered by a subsequent layer of pavement or by a surfacing until: a) all testing has been completed b) the surface finish of the layer complies with the requirements of Clause 8.3.5 c) all test results comply with the requirements of this Technical Specification, or any nonconformances have been submitted, with corrective actions proposed by the Contractor, and accepted by the Administrator d) the layer has been presented to the Administrator for inspection, and
10 | [8 empty] | N/A
11
6 | Temporary line marking |  |  |  |  | LCC SS 10 Part 2.8.4 | Check and Verify |  | N/A
Details of proposed temporary pavement markings are submitted to the local government for approval at least two working days prior to the proposed installation of the temporary pavement.
5 | Access |  |  |  |  | MRTS 28 Clause 4.5.6 | Check and Verify |  | N/A
The Contractor’s site facilities shall be located to provide safe ingress and egress of traffic to the Site and public roads and shall not deteriorate the existing traffic operation.
Final Sign off and Approval - Conformance with the Specification
Name of Client's Representative |  |  | Signature |  |  |  |  | Date
Name of Contractor's Representative |  |  | Signature |  |  |  |  | Date

## RCP
Inspection and Test Plan
Project Information |  |  |  | Inspection and Test Plan Information
Project |  | Alamein, George and Main St Intersection Upgrades |  | Lot Number | RCP | CD70 |  |  | Date | Start | Finish
Project No |  | 24 053 |  | Location
Client |  | Logan City Council |  | Description |  |  |  |  | Chainage | From | To
Contract No |  | CD70
Specification |  | LCC Standatd Specification No. 3 |  | Activity | Reinforced Concrete Pipe
Acceptance of Activity
# | Acceptance Criteria |  |  |  |  | Reference | Item Check | QA | Client | Date | NCR
Reinforced Concrete Pipe Works
1 | General |  |  |  |  | General | Check and Verify |  | N/A
All reinforced concrete pipes and pit shall be as per drawings unless an alternitive is approved, all pipes shall be laid in location and to levels specified in drawings. - Drawings specify
2 | Construction Procedure - Submission |  |  |  |  | MRTS03 Clause 11.3.1 | MILESTONE
Construction procedure for the construction of concrete pipes shall be provide at least 14 days prior to the administrator.
3 | Construction Procedure - Approval |  |  |  |  | MRTS03 Clause 11.3.2 | Hold Point 2
The contractor shall not commence construction of any culverts until the construction procedure has been submitted
2 | Material Conformance |  |  |  |  | LCC SS No.3 Part 2.1 | Check and Verify |  | N/A
Unless otherwise noted on the approved drawings all pipes are Class 2 and comply with the requirements of AS 4058–2007 and all matrial conformnace data shall be included in the lot submission to the administrator.
3 | Construction |  |  |  |  | LCC SS No.3 Part 6.3 | Check and Verify |  | N/A
All RCP will be constructed as per IPWEA-STD-DS-030 which covers excavation, bedding material and backfilling - Bottom of excavation shall be compacted to a 95% standard compaction unless insitu material is rock for all excavations. - Backfill material shall be either 5 or 10mm aggregate.
4 | Pipe Laying |  |  |  |  | LCC SS No.3 Part 4.2 | Check and Verify |  | N/A
Pipes are laid true to line and grade, and are free draining and firmly bedded and are laid from the discharge end upstream to the following tolerances: - invert levels - ±50mm; - gully locations - within 300mm of design. For pipes up to and including 600mm diameter, the socketed end of the pipe is laid upstream and a shallow excavation is made under the socket of each pipe so that the pipe fully rests for its full length of barrel upon the bedding material in the trench.
5 | Construction - Backfilling |  |  |  |  | LCC SS No.3 Part 5.1 | Hold Point
Pipe is not to be backfilled without being inspected and approved by administrator.
6 | Backfilling Material |  |  |  |  | LCC SS No.3 Part 4.1 | Hold Point/ Witness Point
Prior to incorporating any Backfill material into the Works, the Contractor shall submit stockpile or source tests results as specified in part 4 of Standard specification 3 and conforms with table 4.1.1 Bedding Material
7 | Backfilling Under Proposed Pavements |  |  |  |  | LCC No.3 Part 5.2.1.(a) | Check and Verify |  | N/A
backfilled with approved material of minimum 4 day soaked California bearing ratio of 15 and compacted to 100 percent standard compaction.
8 | Pipe Laying Compliance Testing |  |  |  |  | LCC SS No.3 Part 4.4 | Hold Point
All pipes lines are subject to internal inspection and approval, the inspection of all pipes is carried out using a remote controlled video camera and is submitted to the local government before being accepted on-maintenance. A report on the findings of a remote controlled video camera inspection is to be submitted to the local government in an electronic format suitable for utilisation in “Sewer Rat” compatible applications. Pipes must not show clearly visible cracks of more than one millimetre for a length of 300mm or more on the inside.
Insitu Gully Pit Works
9 | General |  |  |  |  | LCC SS No.3 Part 6.1 | Check and Verify |  | N/A
A drainage structure includes all work and materials necessary for the construction of gullies, inlet pits and manholes, including excavation, concrete rendering and all necessary frames, curves, gratings, precast units and surrounds, precast troughs, chambers, lintels and shafts for side entry gullies, as specified in the approved drawings and standard drawings. -IPWEA-STD-DS-60
10 | Materials - Gully Pit |  |  |  |  | LCC SS No.3 Part 6.2 | Check and Verify |  | N/A
All materials used in insitu drainage structure will ne N32 class concrete or otherewise specified. Concrete mix used - _________________
11 | Formwork Approval |  |  |  |  | LCC SS No.7 Part 4.1.1 | Hold Point
All concrete is placed in dry conditions and no concrete is placed until the formwork, falsework, and reinforcing materials have been inspected and approved by the local government.
12 | Construction of Gully Pit |  |  |  |  | LCC SS No.3 Part 6.3 | Check and Verify |  | N/A
Where the sides of the excavation are deemed to be in solid ground shafts may be constructed without the use of backforms, where concrete is placed without backforms the specified wall thickness is increased by 50mm minimum and not greater than 300mm of the design thickness. The finished concrete surface shall have smooth even and neat edges and will be shaped per the design intent.
Inspection and Test Plan
Final Sign off and Approval - Conformance with the Specification
Name of Cient's Representative |  |  | Signature |  |  |  |  | Date
Name of Contractor's Representative |  |  | Signature |  |  |  |  | Date
Hamish Hewitt

## CSF
Inspection and Test Plan
Project Information |  |  |  | Inspection and Test Plan Information
Project |  | Alamein, George and Main St Intersection Upgrades |  | Lot Number |  |  |  |  | Date | Start | Finish
Project No |  | 24 053 |  | Location
Client |  | Logan City Council |  | Description |  |  |  |  | Chainage | From | To
Contract No |  | CD70
Specification |  | MRTS 28 November 2019 |  | Activity | Contractor's Site Facilites
Acceptance of Activity
# | Acceptance Criteria |  |  |  |  | Reference | Item Check | QA | Client | Date | NCR
1 | General |  |  |  |  | MRTS 28 Clause 4.3 & MRTS 28 Clause 3, Clause 8 | Check and Verify |  | N/A
The Contractor shall provide properly constructed toilets, drinking water, eating and washing facilities at the Contractor’s site facilities for the use of personnel and connect to town sewer where possible and shall comply with AS 1547 On-site domestic wastewater management.
2 | Site Security |  |  |  |  | MRTS 28 Clause 4.3 | Check and Verify |  | N/A
The Contractor shall be responsible for the security of the buildings, construction plant and machinery. The Contractor shall also take all necessary precautions to make the area safe to the public, including provision of signs outlining relevant project contact details, safety requirements and any other relevant details on the main entry gate.
3 | Visibility to the public |  |  |  |  | MRTS 28 Clause 4.5.2 | Check and Verify |  | N/A
External lights on the facilities and camps should be positioned or shielded to minimise light overflow onto neighbouring properties.
4 | Noise |  |  |  |  | MRTS 28 Clause 4.5.3 | Check and Verify |  | N/A
Noise generated from the site facilities shall be kept to a minimum and the Contractor shall construct noise amelioration devices around the site facilities to bring the noise levels within specified criteria.
5 | Dust Suppression |  |  |  |  | MRTS 28 Clause 4.5.4 | Check and Verify |  | N/A
Adequate precautions are taken to minimise dust or dust-related conditions during any activity which may affect the safety and general comfort of any person. Regular applications of water are applied to any roads or structures whilst completing earthworks
5 | Temporary road safety barriers |  |  |  |  | MRTS02 Cl 6.5.11 & Annexure 2.1 | Check and Verify |  | N/A
Temporary Road Safety Barriers (TRSB) shall be used to contain and redirect errant vehicles so as to reduce the likelihood of them entering the work site - Provision shall be made for TRSB At locations where work is to be close to traffic, and in accordance with Worker safety requirements in MUTCD Part 3; - Only those TRSB which are included in the Transport and Main Roads – Road Safety Barrier Systems, End Treatments and other related Road Safety Devices shall be used - All TRSB and end treatments shall be installed in accordance with the department's Standard Drawings and/or the manufacturer's specifications
6 | Temporary line marking |  |  |  |  | LCC SS 10 Part 2.8.4 | Check and Verify |  | N/A
Details of proposed temporary pavement markings are submitted to the local government for approval at least two working days prior to the proposed installation of the temporary pavement.
5 | Access |  |  |  |  | MRTS 28 Clause 4.5.6 | Check and Verify |  | N/A
The Contractor’s site facilities shall be located to provide safe ingress and egress of traffic to the Site and public roads and shall not deteriorate the existing traffic operation.
Final Sign off and Approval - Conformance with the Specification
Name of Client's Representative |  |  | Signature |  |  |  |  | Date
Name of Contractor's Representative |  |  | Signature |  |  |  |  | Date

## DGA
Inspection and Test Plan
Project Information |  |  |  | Inspection and Test Plan Information
Project |  | Alamein, George and Main St Intersection Upgrades |  | Lot Number | DGA | CD70 |  |  | Date | Start | Finish
Project No |  | 24 053 |  | Location
Client |  | Logan City Council |  | Description |  |  |  |  | Chainage | From | To
Contract No |  | CD70
Specification |  | MRTS 30 March 2024, LCC Standard Specification 13 |  | Activity | Dense Grade Asphalt
Acceptance of Activity
# | Acceptance Criteria |  |  |  |  | Reference | Item Check | QA | Client | Date | NCR
1 | Submission of Asphalt Quality Plan |  |  |  |  | MRTS30 Cl 5.2 | Milestone
The Contractor must develop an Asphalt Quality Plan (AQP) for the asphalt work to the Administrator for consideration at least seven days prior to work commencing and must be implemented.
2 | Nomination of registered mix designs |  |  |  |  | MRTS30 Cl 7.3.3 | Milestone
At least seven days before asphalt is to be incorporated into the Works, the Contractor shall submit to the Administrator a copy of the mix design certificate(s) for each nominal size and type of asphalt mix to be incorporated into the Works.
3 | Asphalt Mix Properties |  |  |  |  | LCC SS 13 Part 2.6 & MRTS 30 | Check and Verify |  | N/A
The properties of asphalt mix must comply with Table 2.6.1 - Asphalt mix properties of LCC spec No. 13 Part 2.6.1 when tested in accordance with column 3, asphalt shall aslo comply with MRTS 30.
4 | General |  |  |  |  | General | Ckeck and Verify |  | N/A
All asphalt shall be placed in accordance with design drawings and as per drawings GW001 & LS001
5 | Bitumen Binder |  |  |  |  | General | Ckeck and Verify |  | N/A
All asphalt shall be placed in accordance with design drawings and as per drawings GW001 & LS002
6 | Production of Asphalt |  |  |  |  | MRTS30 Cl 7.4.1 | Hold Point 2
Asphalt shall be produced by a registered asphalt manufacturer from the nominated asphalt plant in accordance with the nominated mix design for the Works. Asphalt shall not be incorporated into the Works until the Contractor has demonstrated to the Administrator that the underlying lots conform to the specified requirements
7 | Production of Asphalt |  |  |  |  | MRTS30 Cl 8.2.2 | Witness Point 1
For asphalt placed over pavement constructed by others, the surface on which asphalt will be placed shall be tested for perceptible surface deformation by ‘proof rolling’ in the presence of the Administrator.
8 | Preparation |  |  |  |  | MRTS30 Cl 8.2.2 | Hold Point 4
Unless otherwise approved by the Administrator, asphalt shall not be placed over pavement exhibiting significant perceptible surface deformation.
9 | Preparation of pavement |  |  |  |  | MRTS30 Cl 8.2.2 | Check and Verify |  | N/A
Existing substrate shall not be wet and shall be swept thouroughly to remove and loose or deleterious material
10 | Application of Asphalt - Temperature |  |  |  |  | LCC SS 13 Part 3.1.1&2 | Check and Verify |  | N/A
The asphalt mix temperature is controlled so that it is between 135C and 175C when loaded into the delivery truck, the mix temperature is between 110C and 165C immediately behind the paver with compaction commencing before the temperature of the mix falls below a minimum of 95C.
11 | Asphalt Compaction |  |  |  |  | LCC SS 13 Part 3.4 & 3.5 | Hold Point
Compaction is commenced as soon as possible after spreading, and is completed in the shortest possible time except in the event of significant deformation or an irregularity occurring under the action of the roller in which case, rolling is delayed For compaction testing, a lot is the same as for a production lot and compaction testing is undertaken in accordance with Q302A, Q302B, Q306B and Q314. After completion of each job, core samples are taken from the compacted asphalt at the rate of one core per 1000m2 of asphalt laid, but with a minimum of three cores per job, asphalt compaction shall be greater than 95%
6 | Temporary line marking |  |  |  |  | LCC SS 10 Part 2.8.4 | Check and Verify |  | N/A
Details of proposed temporary pavement markings are submitted to the local government for approval at least two working days prior to the proposed installation of the temporary pavement.
5 | Access |  |  |  |  | MRTS 28 Clause 4.5.6 | Check and Verify |  | N/A
The Contractor’s site facilities shall be located to provide safe ingress and egress of traffic to the Site and public roads and shall not deteriorate the existing traffic operation.
Final Sign off and Approval - Conformance with the Specification
Name of Client's Representative |  |  | Signature |  |  |  |  | Date
Name of Contractor's Representative |  |  | Signature |  |  |  |  | Date

## PCD
Inspection and Test Plan
Project Information |  |  |  | Inspection and Test Plan Information
Project |  | Alamein, George and Main St Intersection Upgrades |  | Lot Number | PCD | CD70 |  |  | Date | Start | Finish
Project No |  | 24 053 |  | Location
Client |  | Logan City Council |  | Description |  |  |  |  | Chainage | From | To
Contract No |  | CD70
Specification |  | MRTS 03 July 2021 |  | Activity | Precast Concrete Channel Drain
Acceptance of Activity
# | Acceptance Criteria |  |  |  |  | Reference | Item Check | QA | Client | Date | NCR
1 | General |  |  |  |  | General | Check and Verify |  | N/A
Precast and/or preformed trough components shall be installed in the locations and in accordance with the details specified in the drawings and excavations shall be carried out in accordance with Clause 13 of MRTS04 General Earthworks.
2 | Bedding of drainage trough components |  |  |  |  | MRTS 03 Cl 12.3.2 | Check and Verify |  | N/A
Foundation bedding materials shall be placed in accordance with Clause 19 of MRTS04 General Earthworks. The foundation bedding shall provide continuous, even support to the drainage trough components
3 | Precast concrete drain assembly |  |  |  |  | MRTS 03 Cl 12.3.3 | Check and Verify |  | N/A
Drainage trough components shall be assembled in accordance with the manufacturer’s drawings and recommendations.
4 | Laying drainage trough components |  |  |  |  | MRTS 03 Cl 12.3.4 | Check and Verify |  | N/A
Drainage trough components shall be laid with the tops flush with the finished batter the laying of drainage trough components shall commence at the outlet end of the trough and progress to the inlet end. Where necessary, components shall be selected and arranged to give satisfactory fit the ends of components shall be free of any foreign matter at the time of jointing, when butt and flush joints are specified, the drainage trough components shall abut one another.
5 | Drainage trough bandages |  |  |  |  | MRTS 03 Cl 12.3.4 | Check and Verify |  | N/A
Bandage covers shall be applied to the outer surfaces of butt and flush joints. Bandage covers shall consist of: a) one layer of non-woven fabric, or b) three layers of woven fabric. Fabric covers shall have a width sufficient to overlap adjacent components by not less than 45 mm and shall not be applied until the ambient temperature exceeds 15°C. Fabric covers shall not be wrinkled and shall adhere to the outer surfaces of the adjacent components. The ends of the fabric in the covers shall be secured in accordance with the manufacturer’s recommendations.
6 | Cutting Draianage trough components |  |  |  |  | MRTS 03 Cl 12.3.5 | Check and Verify |  | N/A
Where the cutting of precast drainaage components is required the following actions shall be taken: - Cutting operations shall provide neat end surfaces, the cut surfaces of concrete drainage trough components shall be given two coats of a surface tolerant epoxy. - The cut surfaces of corrugated steel drainage trough components shall be given two coats of zinc-rich organic priming paint as specified in AS 3750.9. The coats shall have a combined thickness at least equivalent to the galvanised coating thickness. Each coat shall overlap adjacent uncut surfaces by not less than 25 mm.
7 | Installing holding down anchors |  |  |  |  | MRTS 03 Cl 12.3.6 | Check and Verify |  | N/A
Holding down anchors shall be installed in accordance with the requirements specified in the Standard Drawings and the manufacturer’s recommendations as relevant
8 | Water Test |  |  |  |  | MRTS 03 Cl 18.5 | Witness Point 1
Where the longitudinal grade of channels is less than 1%, a test shall be carried out by discharging water into the channel to check uniformity of flow along the channel. After the flow has ceased, water shall not pond to a depth of more than 5 mm in any section of the channel. The test shall be carried out as soon as possible after the concrete in the channel has hardened.
9
10 | [8 empty] | N/A
11
6 | Temporary line marking |  |  |  |  | LCC SS 10 Part 2.8.4 | Check and Verify |  | N/A
Details of proposed temporary pavement markings are submitted to the local government for approval at least two working days prior to the proposed installation of the temporary pavement.
5 | Access |  |  |  |  | MRTS 28 Clause 4.5.6 | Check and Verify |  | N/A
The Contractor’s site facilities shall be located to provide safe ingress and egress of traffic to the Site and public roads and shall not deteriorate the existing traffic operation.
Final Sign off and Approval - Conformance with the Specification
Name of Client's Representative |  |  | Signature |  |  |  |  | Date
Name of Contractor's Representative |  |  | Signature |  |  |  |  | Date

## SBS
Inspection and Test Plan
Project Information |  |  |  | Inspection and Test Plan Information
Project |  | Alamein, George and Main St Intersection Upgrades |  | Lot Number | SBS | CD70 |  |  | Date | Start | Finish
Project No |  | 24 053 |  | Location
Client |  | Logan City Council |  | Description |  |  |  |  | Chainage | From | To
Contract No |  | CD70
Specification |  | LCC Standard Specification 14 & MRTS 12 |  | Activity | Sprayed Bitumen Surfacing
Acceptance of Activity
# | Acceptance Criteria |  |  |  |  | Reference | Item Check | QA | Client | Date | NCR
1 | Construction Procedure |  |  |  |  | MRTS12 Cl 5.2 | Hold Point 1
Procedures shall be submitted to the Administrator not less than seven days prior to their use, and procedures shall not be implemented until permission to use has been granted by the Administrator.
2 | Plant Required |  |  |  |  | MRTS12 Cl 9 | Hold Point 4
The Contractor shall have on the Site and in use as required the plant necessary for the performance of the particular operation. The respective minimum requirements for the plant listed in Table 9 shall apply. Not less than seven days prior to sealing operations, the Contractor shall submit details of all plant to be used in the operations.
3 | Surface Preparation |  |  |  |  | LCC SS 14 Part 4.1.3 | Check & Verify
Any surface that is to be sprayed shall be prepared in a manner that all foreign and loose material, including lenses of pavement material, are removed from the surface, the surface is swept with a road broom until the larger particles in the surface of the pavement are slightly exposed without dislodgement and excessive erosion of the surrounding finer material, a light watering is carried out just prior to spraying; or all foreign and loose material is removed from the surface; the surface is swept with a road broom;
3 | Pavement Surface Temperature |  |  |  |  | LCC SS 14 Part 6.1.1 | Check & Verify
Spraying shall not commence until the temperature on the surface of the pavement is above the temperature given in Clause 4.2 of the Annexure MRTS12.1 or, if not so given, above 20ºC for at least one hour before spraying commences.
4 | Spraying Temperature |  |  |  |  | MRTS 12 Cl 12.5 | Witness Point 2
Bituminous emulsion shall be sprayed at a temperature consistent with the requirements detailed in Table 12.5
| General Standards |  |  |  |  | LCC SS 14 Part 4.1.3 | Check & Verify
Emulsion primers only to be used where approved by administrator and shall be used according to the manufacturers specifications.
| Details of spraying operations |  |  |  |  | LCC SS 14 Part 10.1.1 | Witness Point
After each spray run, all details of the sealing operations are recorded on a bituminous materials spraying record sheet. The bituminous materials spraying record sheet is signed by the local government and a copy of the completed bituminous materials spraying record sheet is provided to the local government at the end of each day's operation.
9
10 | [8 empty] | N/A
11
6 | Temporary line marking |  |  |  |  | LCC SS 10 Part 2.8.4 | Check and Verify |  | N/A
Details of proposed temporary pavement markings are submitted to the local government for approval at least two working days prior to the proposed installation of the temporary pavement.
5 | Access |  |  |  |  | MRTS 28 Clause 4.5.6 | Check and Verify |  | N/A
The Contractor’s site facilities shall be located to provide safe ingress and egress of traffic to the Site and public roads and shall not deteriorate the existing traffic operation.
Final Sign off and Approval - Conformance with the Specification
Name of Client's Representative |  |  | Signature |  |  |  |  | Date
Name of Contractor's Representative |  |  | Signature |  |  |  |  | Date

## HPC
Inspection and Test Plan
Project Information |  |  |  | Inspection and Test Plan Information
Project |  | Alamein, George and Main St Intersection Upgrades |  | Lot Number | HPC | CD70 |  |  | Date | Start | Finish
Project No |  | 24 053 |  | Location
Client |  | Logan City Council |  | Description |  |  |  |  | Chainage | From | To
Contract No |  | CD70
Specification |  | LCC Standard Specification 7 (Concret) & LCC Standard Specification 8 (Minor concrete works) |  | Activity | Hand Placed Concrete
Acceptance of Activity
# | Acceptance Criteria |  |  |  |  | Reference | Item Check | QA | Client | Date | NCR
1 | Design location |  |  |  |  | IFC Design Drawings | Check and Verify |  | N/A
All concrete works ar to be intalled in location and noted on a lot map attached to this document and accordance with the spcified drawings: Specified Drawing:
2 | Concrete Mix Design Submission |  |  |  |  | LCC SS No. 7 Part 2.3 | Milestone
All mix designs shall be submitted to the administrator prior to works beginning if insufficient testing history is available for the specified mix from an approved supplier, preliminary mixes for all grades of concrete are designed, made and tested.
3 | Concrete Mix Design Approval |  |  |  |  | LCC SS No. 7 Part 2 | Hold Point
Concrete Mix designs are approved prior to the usage in any works.
4 | Formwork Approval |  |  |  |  | LCC SS No. 7 Part 5.3.11 | Hold Point
All steel reinforcement that will be used in concrete works shall be inspected and approved by the local government prior to the placement of concrete, all formwork shall be inspected and checked against formwork checklist. When forms appear to be unsatisfactory in any way, either before or during the placing of concrete, the work does not proceed until the defects have been corrected to the approval of the local government.
5 | Footpath Contraction Joint |  |  |  |  | LCC SS No. 8 Part 3.1.4 | Check and Verify |  | N/A
Contraction joints: (a) are provided at centres matching the width of the footpath and not more than 3.0 metres; (b) are formed by a jointing tool; (c) do not exceed 35mm in depth or 6mm in width; (d) are at right angles to the edge of the path.
6 | Footpath Expansion Joint |  |  |  |  | LCC SS No. 8 Part 3.1.5 | Check and Verify |  | N/A
Expansion joints: (a) are placed at 15 metre centres except for 2.0m footpath which can be 16m to match dimension multiplier; (b) are at right angles to the edge of the path; (c) extend for the full depth of the concrete path and are 10mm in width. All expansion joints shall be as per LCC specifcations or where specified in standard darwings.
7 | Formwork
7 | Slump & Testing |  |  |  |  | LCC SS No. 7 Part 2.4 | Check and Verify |  | N/A
All concrete poured on site shall be slump tested by a NATA certified testing contractor, all slump testing values shall be recorded by a pour record sheet and provided to the administrator with the submission of the lot. All slump values shall comply with table 2.4.1 under Standard Specification 7. All concrete shall be tested for strength, concrete is sampled and tested in accordance with AS 1012.1-1993 Methods of testing concrete - Sampling of fresh concrete, by an approved NATA registered laboratory and the results are provided to the local government.
8 | Temperature and Timing |  |  |  |  | LCC SS No. 7 Part 4.2&4.3 | Check and Verify |  | N/A
Where the ambient temperature is likely to exceed 30°C, all practical precautions are taken to maintain the concrete at a temperature not exceeding 30°C at the time of placing to prevent shrinkage, settlement and presetting cracks. No concrete with a temperature higher than 30°C is placed unless otherwise approved by the local government. Ready mixed concrete is placed and compacted within 1 hour 15 minutes of charging the mixer for concrete temperatures up to 30°C and within 30 minutes of charging the mixer.
9 | Finishing |  |  |  |  | LCC SS No. 7 Part 6.1.2 | Check and Verify |  | N/A
All surfaces of concrete that are exposed to view in the completed structure are finished such that: (a) Immediately after the removal of forms, all fins and other projections are ground off, all pockets and honeycombs are cleaned and filled with a stiff cement mortar having the same proportion of cement and sand as the original concrete, and the surface of the patch is ground flush; (b) Decks are roughened slightly by brooming or other approved method before initial set; (c) Kerb and channel, invert crossings, vehicle crossings and industrial crossings are finished with an approved steel finishing tool; (d) Footpaths and pram ramps are finished with a wooden float and broomed.
10 | Curing |  |  |  |  | LCC SS No. 7 Part 6.3 | Check and Verify |  | N/A
Concrete surfaces are kept moist by spraying with an approved curing compound, or water sprays or wet sand in which case the surfaces are kept moist 24 hours a day for the full period specified without any breaks at weekends or holidays. Curing is commenced immediately on completion of the finishing of exposed surfaces or within 30 minutes of removal of the forms from other surfaces.
11
6 | Temporary line marking |  |  |  |  | LCC SS 10 Part 2.8.4 | Check and Verify |  | N/A
11 | Dimension Tolerances |  |  |  |  | LCC SS No. 7 Part 6.4 | Check and Verify |  | N/A
Where tolerances are not stated in the approved drawings for any individual structure or feature thereof, deviations from established lines, grades and dimensions are not greater than the tolerances listed in Table 6.4.1–Tolerances of this standard specification and are applied to the completed work. Size of member or thickness of slab: +7mm, -0 Cover of Concrete Over Reinforcement: +7mm, -3mm Contract dimensions: 0-20meters: +7mm Over 20meters: +13mm
Final Sign off and Approval - Conformance with the Specification
Name of Client's Representative |  |  | Signature |  |  |  |  | Date
Name of Contractor's Representative |  |  | Signature |  |  |  |  | Date

## LS
Inspection and Test Plan
Project Information |  |  |  | Inspection and Test Plan Information
Project |  | Alamein, George and Main St Intersection Upgrades |  | Lot Number | LS | CD70 |  |  | Date | Start | Finish
Project No |  | 24 053 |  | Location
Client |  | Logan City Council |  | Description |  |  |  |  | Chainage | From | To
Contract No |  | CD70
Specification |  | LCC Standard Specification No. 2 (Landscaping) |  | Activity | Landscaping
Acceptance of Activity
# | Acceptance Criteria |  |  |  |  | Reference | Item Check | QA | Client | Date | NCR
Topsoil & Turf
1 | Soil Type |  |  |  |  | LCC SS No. 2 Part 6.2.2 | Check and Verify |  | N/A
Alll topsoil imported to site shall comply wiht the following below (a) is a fine soil type in accordance with Table 6.2.1–Soil type by texture of this standard specification; (b) is friable; (c) is moderately free draining; (d) complies with AS 4419–2003 Soils for landscaping and garden use; (e) is free of fire ants; (f) is free from Nut Grass (Cyperus rotundus);
2 | [5 empty] | LCC SS No. 2 Part 6.2.3 | Check and Verify |  | N/A
3 | [5 empty] | LCC SS No. 2 Part 6.2.4 | Check and Verify |  | N/A
2 | Topsoil Provider |  |  |  |  | LCC SS No. 2 Part 6.2.3 | Hold Point
Soil is imported from a source approved by the local government or is provided from material upon the premises where approved by the local government. Soil from the premises which is improved to comply with Table 6.2.1–Soil type by texture of this standard specification by the use of additives such as Gypsum, may be used as topsoil where approved by the local government.
3 | Spreading Topsoil |  |  |  |  | LCC SS No. 2 Part 6.2.5 | Check and Verify |  | N/A
Soil is spread such that: (a) the finished surface of the soil is smooth, free of lumps and free draining; (b) the finished surface levels allows for the settling and spreading of mulch; (c) the soil is lightly compacted over the prepared sub-grade; (d) in a grassed area the edge of the soil is feathered into undisturbed ground.
4 | Topsoil Finish |  |  |  |  | LCC SS No. 2 Part 6.2.6 | Check and Verify |  | N/A
Where soil is next to a kerb, a path, a mowing strip or other hard paved surface: (a) the soil is finished flush for a seeded grass area and bevelled below the abutting finished grade to allow for turf or mulch; (b) the finished grade of the mulch is approximately 10mm below the abutting finished surface level; (c) the finished surface level of the turf is flush with the abutting finished surface level; (d) the finished surface level of a grass area, turf and a garden bed adjacent to a building or other structure is 125mm below the weepholes in the building or the structure.
5 | Topsoil Depth |  |  |  |  | Contract Drawings | Check and Verify |  | N/A
Topsoil depth is 75mm as per contract drawing GW001
6 | Fertiliser |  |  |  |  | LCC SS No. 2 Part 6.4.1 | Check and Verify |  | N/A
Fertiliser is to be applied as per manufacturer's specification to ensure healthy long term growth.
7 | Turfed Area |  |  |  |  | LCC SS No. 2 Part 6.4.3 | Check and Verify |  | N/A
A turf roll has a minimum soil thickness of 20mm. (2) The turf is delivered to the premises within 24 hours of being cut. (3) The turf is laid within 36 hours of being cut. (4) Where the laying of the turf is delayed, the turf is: (a) protected and watered to maintain its condition; (b) not allowed to dry out at any stage from cutting to laying.
Maintenance
8 | General Maintenance |  |  |  |  | LCC SS No.3 Part 7.1 | Check and Verify |  | N/A
The premises is to be kept free of weeds and rubbish and any damaged, defective or stolen landscaping item is to be repaired or replaced.
9 | Maintenance Period |  |  |  |  | LCC SS No.3 Part 7.3 | Check and Verify |  | N/A
All turfef areas are maintained through the maintenance period such that at the end of the establishment period a turfed area has 100 percent of turf coverage, the plant estabblishment period is a minimum period of 12 weeks from the date that PC is approved.
10 | Maintenance of Turf |  |  |  |  | LCC SS No.3 Part 7.4.2 | Check and Verify |  | N/A
A grassed area is maintained during the maintenance period by: (a) mowing grass to 50mm height when grass has grown no higher than 75mm and removing grass clippings from the landscape area or as otherwise approved by the local government; (b) applying water at regular intervals to ensure ongoing healthy growth
11 | Maintenance Program |  |  |  |  | LCC SS No.7 Part 8.3.4 | Milestone/ Hold Point
The Maintenance Program is to be prepared by the Contractor and submitted to the Superintendent for approval prior to commencement of work under the Contract and is to contian details about the frequency which the contractor proposes to carry out its obligation under section 7.4 SS 2
Inspection and Test Plan
Final Sign off and Approval - Conformance with the Specification
Name of Cient's Representative |  |  | Signature |  |  |  |  | Date
Name of Contractor's Representative |  |  | Signature |  |  |  |  | Date
Hamish Hewitt

## CP
Inspection and Test Plan
Project Information |  |  |  | Inspection and Test Plan Information
Project |  | Alamein, George and Main St Intersection Upgrades |  | Lot Number | CP |  |  |  | Date | Start | Finish
Project No |  | 24 053 |  | Location
Client |  | Logan City Council |  | Description |  |  |  |  | Chainage | From | To
Contract No |  | CD70
Specification |  | MRTS 91 July 2024 |  | Activity | Conduits and Pits
Acceptance of Activity
# | Acceptance Criteria |  |  |  |  | Reference | Item Check | QA | Client | Date | NCR
1 | General |  |  |  |  | MRTS 91 Clause 5.3 | Witness Point & Hold Point
A construction procedure for the installation of all conduits and pits shall be submitted to the Administrator at least 14 days prior to the commencement of installation. No excavation activity associated with the installation of conduits and pits shall commence until the expiration of the 14-day period.
2 | Asbestos Assessment |  |  |  |  | MRTS 91 Clause 6.1 | Hold Point
Asbestos is suspected or found in existing installation, work at this site must be stopped immediately, and the finding must be reported to the principal immediately for their decision and instruction on the work to be carried out at the site.
3 | Material Certification |  |  |  |  | MRTS 91 Clause 7.1 | Hold Point
All materials must comply strictly with the requirements of this Technical Specification. For all materials, a certificate of such compliance shall be provided to the Administrator before the materials are incorporated into the works
4 | Excavation for underground conduits and pits |  |  |  |  | MRTS 91 Claus 8.1 | Witness Point & Hold Point
Conduit runs and pit locations shall be set out and notice of such set out shall be provided to the principal at least 48 hours prior to the commencement of excavation. Construction shall not commence before the expirations of the period of notice.
5 | Bottom of trench |  |  |  |  | MRTS 91 Clause 8.4 | Witness Point
The bottom of the trench shall be compacted as per Standard Drawing 1149 to form a firm uniform surface free from loose material.
5 | Boring and Jacking |  |  |  |  | MRTS 91 Clause 8.7 | Hold Point
Work shall not commence until it has been demonstrated to the Administrator that the proposed equipment can accurately install the conduit in accordance with MRTS140 Horizontal Directional Drilling (HDD) and Standard Drawing 1149 Installation of Underground Electrical and Communication.
6 | Installation of conduits |  |  |  |  | MRTS 91 Clause 9.1 | Hold Point
The installation of conduits shall conform to the requirements of Standard Drawing 1149. The installation of communications conduits shall also comply with the requirements of AS/CA S009. Prior to installation, the Contractor shall inspect all conduit and conduit fittings to ensure that they are free of any defects that could damage the cables during installation. Conduits to be installed without dips/low points to ensure that drainage at pits operates as intended. The conduits are not to be lower than the pit it connects to unless approved by the Principal. Road crossing installed by ‘boring’ conduit to be installed level to facilitate correct drainage of conduit.
5 | Mandrel |  |  |  |  | MRTS 91 Clause 9.1 | Hold Point
After installation and backfilling, the conduit and conduit fittings shall be proved by drawing a mandrel having a diameter of at least 95% of the internal diameter of the conduit. The mandrel shall have a length sufficient to allow it to pass around any bends in the conduit, but not shorter than 95% of the diameter of the conduit being tested
6 | Draw rope |  |  |  |  | MRTS 91 Clause 9.13 | Witness point
Any joints made in the draw rope shall be capable of resisting the same tensile load as the draw rope without such a joint. The joint shall not appreciably increase the diameter of the rope.
7 | Vermin proofing of conduits |  |  |  |  | MRTS 91 Clause 10.9 | Hold Point
Any alternative proposed conduit sealing system shall be fit for purpose, and a proprietary system, and shall be submitted to the Administrator for consideration and approval prior to commencement of the installation of any cabling.
8 | Bedding of pit |  |  |  |  | MRTS 91 Clause 10.4 | Hold Point
The bottom of an excavation for a pit shall be compacted to at least 95% relative compaction.
9 | Compact bedding material |  |  |  |  | MRTS 91 Clause 10.4 | Check & Verify |  | N/A
Compact bedding material to density index 60.
10 | Drainage Holes |  |  |  |  | MRTS 91 Clause 10.11 | Witness Point
The lowest open end of conduits installed in poles and other field equipment enclosures shall be at least 50 mm higher than the surrounding finished surface level.
11 | Backfilling |  |  |  |  | MRTS 91 Clause 13.1 | Hold Point
Backfilling of trenches for conduits shall not commence until the conduit system has been inspected by the Administrator
Final Sign off and Approval - Conformance with the Specification
Name of Client's Representative |  |  | Signature |  |  |  |  | Date
Name of Contractor's Representative |  |  | Signature |  |  |  |  | Date

## LM
Inspection and Test Plan
Project Information |  |  |  | Inspection and Test Plan Information
Project |  | Alamein, George and Main St Intersection Upgrades |  | Lot Number | LM | CD70 |  |  | Date | Start | Finish
Project No |  | 24 053 |  | Location
Client |  | Logan City Council |  | Description |  |  |  |  | Chainage | From | To
Contract No |  | CD70
Specification |  | MRTS45, July 2018 |  | Activity | Linemarking
Acceptance of Activity
# | Acceptance Criteria |  |  |  |  | Reference | Item Check | QA | Client | Date | NCR
1 | General | [5 empty] | Check and Verify | ` | N/A
The Contractor shall provide properly constructed toilets, drinking water, eating and washing facilities at the Contractor’s site facilities for the use of personnel and connect to town sewer where possible and shall comply with AS 1547 On-site domestic wastewater management.
2 | Site Security | [5 empty] | Check and Verify |  | N/A
The Contractor shall be responsible for the security of the buildings, construction plant and machinery. The Contractor shall also take all necessary precautions to make the area safe to the public, including provision of signs outlining relevant project contact details, safety requirements and any other relevant details on the main entry gate.
3 | Visibility to the public | [5 empty] | Check and Verify |  | N/A
External lights on the facilities and camps should be positioned or shielded to minimise light overflow onto neighbouring properties.
4 | Noise | [5 empty] | Check and Verify |  | N/A
Noise generated from the site facilities shall be kept to a minimum and the Contractor shall construct noise amelioration devices around the site facilities to bring the noise levels within specified criteria.
5 | Dust Suppression | [5 empty] | Check and Verify |  | N/A
Adequate precautions are taken to minimise dust or dust-related conditions during any activity which may affect the safety and general comfort of any person. Regular applications of water are applied to any roads or structures whilst completing earthworks
5 | Temporary road safety barriers | [5 empty] | Check and Verify |  | N/A
Temporary Road Safety Barriers (TRSB) shall be used to contain and redirect errant vehicles so as to reduce the likelihood of them entering the work site - Provision shall be made for TRSB At locations where work is to be close to traffic, and in accordance with Worker safety requirements in MUTCD Part 3; - Only those TRSB which are included in the Transport and Main Roads – Road Safety Barrier Systems, End Treatments and other related Road Safety Devices shall be used - All TRSB and end treatments shall be installed in accordance with the department's Standard Drawings and/or the manufacturer's specifications
6 | Temporary line marking | [5 empty] | Check and Verify |  | N/A
Details of proposed temporary pavement markings are submitted to the local government for approval at least two working days prior to the proposed installation of the temporary pavement.
5 | Access | [5 empty] | Check and Verify |  | N/A
The Contractor’s site facilities shall be located to provide safe ingress and egress of traffic to the Site and public roads and shall not deteriorate the existing traffic operation.
Final Sign off and Approval - Conformance with the Specification
Name of Client's Representative |  |  | Signature |  |  |  |  | Date
Name of Contractor's Representative |  |  | Signature |  |  |  |  | Date

## Subsoil
Inspection and Test Plan
Project Information |  |  |  | Inspection and Test Plan Information
Project |  | Alamein, George and Main St Intersection Upgrades |  | Lot Number | SD |  |  |  | Date | Start | Finish
Project No |  | 24 053 |  | Location
Client |  | Logan City Council | [6 empty] | Chainage | From | To
Contract No |  | CD70 |  | Description
Specification |  | LCC Standard Specification 12 (Subsoil Drain) |  | Activity | Subsoil Drains
Acceptance of Activity
# | Acceptance Criteria |  |  |  |  | Reference | Item Check | QA | Client | Date | NCR
1 | Material Requirements - Perforated drainage pipes for Type B subsoil drains |  |  |  |  | MRTS03 Clause 22.2 | Check and Verify |  | N/A
Perforated drainage pipes used in Type B subsoil drains and associated fittings and jointing procedures shall comply with AS 2439.1. The pipe shall have a minimum diameter of 100 mm.
1 | Material Requirements - Standard subsoil drains |  |  |  |  | LCC SS 12 Part 2.5 | Check and Verify |  | N/A
A sub-soil drainage pipe is a class 400 perforated corrugated PVC pipe Type 1 in accordance with AS 2439.1-2007 Perforated plastics drainage and effluent pipe and fittings - Perforated drainage pipe and associated fittings. The diameter of a sub-soil drainage pipe is a minimum of 100mm and the perforations do not exceed 1.1mm in width and 7.4mm in length.
2 | Longitudinal subsoil drain in pavement |  |  |  |  | LCC SS 12 Part 2.2 | Check and Verify |  | N/A
Where a kerb and channel is constructed a sub-soil drainage pipe is constructed:Standard specification No. 12 (Sub-soil drainage) Ss12-2 (a) immediately below the back of the kerb in accordance with standard drawing IPWEAQ R-0140, (b) at least 150mm below the finished sub-grade level
3 | Subsoil Drain Excavation |  |  |  |  | LCC SS 12 Part 2.4 | Check and Verify |  | N/A
A trench for a sub-soil drainage pipe is excavated to 50mm below the invert level of the sub-soil drainage pipe and have a gradient which is specified in the approved drawings or which is a minimum of 0.5 percent. the excavated trench is to be a minimum of 100mm wider than the outside diameter of the sub-soil drainage pipe.
4 | Filter Material |  |  |  |  | IPWEA-RS-140 | Check and Verify |  | N/A
Fileter material shall be either 5mm or 10mm drainage aggregate as per standard drawing IPWEA - RS - 140
5 | Subsoil drain outlet |  |  |  |  | LCC SS 12 Part 4.3 | Check and Verify |  | N/A
A sub-soil drainage pipe: shall be connected to a gully pit, as specified in standard drawing IPWEAQ R-0140; or discharges to a culvert head wall or an open channel below the edge of the road shoulder or at the edge of an embankment. (a) If a sub-soil drainage pipe is not connected into a gully pit or a culvert headwall, a concrete headwall is provided to the sub-soil drainage pipe. (b) The headwall is at least 100mm thick and extends for a minimum of 150mm on all sides of the pipe. (c) Where the outlet is through a batter, the surface of the headwall conforms to the batter slope.
Inspection and Test Plan
Final Sign off and Approval - Conformance with the Specification
Name of Client's Representative |  |  | Signature |  |  |  |  | Date
Name of Contractor's Representative |  |  | Signature |  |  |  |  | Date

## EXC
Inspection and Test Plan
Project Information |  |  |  | Inspection and Test Plan Information
Project |  | Alamein, George and Main St Intersection Upgrades |  | Lot Number |  |  |  |  | Date | Start | Finish
Project No |  | 24 053 |  | Location
Client |  | Logan City Council | [6 empty] | Chainage | From | To
Contract No |  | CD70 |  | Description | Excavation, all materials (cut)
Specification |  | MRTS04 June 2023, LCC Specification No. 1 (Earthworks) |  | Activity | General Excavation
Acceptance of Activity
# | Acceptance Criteria |  |  |  |  | Reference | Item Check | QA | Client | Date | NCR
1 | Lot Boundries |  |  |  |  | MRTS 04 Cl 5.6 | Check and Verify |  | N/A
Lot Number established with the Lot boundaries of the works clearly defined for traceability within the works
2 | Services: |  |  |  |  | DBYD | Check and Verify |  | N/A
All services identified – shall be marked, potholed and/or protected as required - Permit to excavate issued by Project Engineer
3 | Erosion Sediment Control |  |  |  |  | MRTS51 Cl 10.3 | Check and Verify |  | N/A
Erosion and sediment controls in place - Due care taken to ensure native fauna is not harmed - Vibration and Air quality to be monitored as a direct result of construction activities
4 | Excavation Cutting |  |  |  |  | LCC SS No.1 Part 9.1 | Check and Verify |  | N/A
The bottom of excavations shall be trimmed to the tolerances specified in Clause 6 and any loose material removed from the surface. The existing soil is compacted to 95 percent relative dry density standard compaction, for a depth of 300mm below the sub-grade and care is taken to ensure that the topsoil and organic material is removed and replaced with approved selected material for a depth of 500mm and compacted to 95 percent relative dry density standard compaction where the sub-grade passes through the natural surfaceat the ends of the excavation or anywhere in cross-section.
5 | Unsuitable Material in Excavtion |  |  |  |  | LCC SS No.1 Part 9.3 | Check and Verify |  | N/A
Unsuitable material below the level of the sub-grade in an excavation is: (a) removed and run to spoil in accordance with section 12.1 of Specification 1,or replaced with select backfill in accordance with section 8.3–Selected gravel fill or selected backfill of this standard specification; (b) compacted to 95 percent relative dry density standard compaction
6 | Unsuitable Material Below Lines of Cuttings |  |  |  |  | MRTS04 Clause 13.3.2.2 | Check and Verify |  | N/A
Material below the finished lines and levels of cuttings, which is Unsuitable Material in accordance with the provisions of Clause 9.2, shall be removed and disposed of in accordance with the provisions of Clause 9.4. Where Unsuitable Material has been removed, the excavation shall be backfilled to the finished surface level with appropriate fill material as specified on the drawings or in accordance with Clause 18 and 19.
8 | Finished Cut Surface & Foundation |  |  |  |  | MRTS04 Clause 13.3.2.1 | HOLD POINT
When the level of excavation has reached Subgrade Level plus a nominal allowance determined by the Contractor, the Contractor shall carry out the requirements of the relevant provisions of Clause 18.3.3 and cease excavation until the Subgrade treatment type has been determined in accordance with Clause 18.3.3. At the foundation surface of the Mass Block Retaining, the bearing capacity shall be confirmed in accordance with the Drawings (150 kPa) via Dnynamic Cone Penetration. Improvement of the foundation is required if the allowable bearing pressure is found to be less than the calcualted bearing pressure. Following the above confirmation the founding surfaces for all structures, including base slab are to be inspected and approved by a suitably qualified Geotechnical Enginee and any necessary treatment is completed prior to any Drain works taking place.
7 | Finished Cut Surface Survey |  |  |  |  | MRTS04 Clause 13.3.2.1 | Check and Verify |  | N/A
Once Works are completed to Subgrade Level (including all Subgrade treatments), an As Constructed Survey of the bottom of the excavated area shall be undertaken as specified in MRTS56 Construction Surveying and notice of such Works provided to the Administrator.
8 | Lot Acceptance | [5 empty] | Check and Verify |  | N/A
Lot closure requires all relevant information to be attached to the Conformance Report this includes a Lot Plan, Survey Report, Hold Points/Approvals & any supporting documentation
Final Sign off and Approval - Conformance with the Specification
Name of Cient's Representative |  |  | Signature |  |  |  |  | Date
Name of Contractor's Representative |  |  | Signature |  |  |  |  | Date

## Subgrade
Inspection and Test Plan
Project Information |  |  |  | Inspection and Test Plan Information
Project |  | Alamein, George and Main St Intersection Upgrades |  | Lot Number |  |  |  |  | Date | Start | Finish
Project No |  | 24 053 |  | Location
Client |  | Logan City Council | [6 empty] | Chainage | From | To
Contract No |  | CD70 |  | Description
Specification |  | LCC Standard Specification No. 6 (Pavement) |  | Activity | Subgrade Treatment
Acceptance of Activity
# | Acceptance Criteria |  |  |  |  | Reference | Item Check | QA | Client | Date | NCR
1 | Lot Boundries |  |  |  |  | MRTS 04 Cl 5.6 | Check and Verify |  | N/A
Lot Number established with the Lot boundaries of the works clearly defined for traceability within the works
2 | Foundation Level |  |  |  |  | MRTS 04 Cl 13.3.2.1 | HOLD POINT
When the level of excavation has reached Subgrade Level plus a nominal allowance determined by the Contractor, the Contractor shall carry out the requirements of the relevant provisions of Clause 18.3.3 and cease excavation until the Subgrade treatment type has been determined in accordance with Clause 18.3.3.
3 | Proof Roll |  |  |  |  | LCC SS No.6 Part 4.1 | Hold Point
At the completion of earthworks to Subgrade Level, the Contractor shall test for perceptible surface deformation by undertaking proof rolling, Work on the pavement does not commence until the subgrade has been inspected and approved by the local government
5 | Subgrade Treament |  |  |  |  | MRTS 04 Cl 18.3.3 | HOLD POINT
Subgrade Treatment Ordered: ____________________
6 | Subgrade Treament Type A |  |  |  |  | MRTS 04 Cl 18.3.3 | Check and Verify |  | N/A
For Subgrade treatment Type A, excavation shall be completed to Subgrade Level in accordance with Clause 13.3.1. The material below Subgrade Level shall be compacted as specified in Clause 15.3 to a characteristic value of compaction as specified in Table 15.3(b). The depth of compaction shall be as specified in Clause 12.3 of Annexure MRTS04.1 to this Technical Specification or, where no such depth is specified, to a depth of 150 mm.
7 | Subgrade Treatment Type C |  |  |  |  | MRTS 04 Cl 18.3.3 | Check and Verify |  | N/A
For Subgrade treatment Type C, excavation shall be continued to a depth below Subgrade Level as specified in Clause 12.3 of Annexure MRTS04.1 to this Technical Specification or, where no such depth is specified, to a depth of 150 mm. Excavation shall comply with the requirements of Clause 13.3.1. The excavation shall be backfilled to Subgrade Level with unbound granular material, in accordance with Clause 18.2.2, and shall be constructed as specified in MRTS05 Unbound Pavements to a characteristic value of compaction of not less than that specified in Table 15.3(b).
8 | Testing - Compaction |  |  |  |  | LCC SS No. 6 Part 6.1 | Test Reports 1 per 500m2 4 per Lot |  | N/A
Subgrade shall be compacted and tested for a standard conpaction of 95% as per table 6.1.1
8 | Geometrics - Straight Edge |  |  |  |  | LCC SS No. 6 Part 6.2 | Test Reports 1 Per 20m |  | N/A
The gap beneath a three metre-long straight-edge placed anywhere on the surface at Subgrade Level shall not exceed 25 mm, due allowance being made for design shape where relevant.
8 | Geometrics - Survey |  |  |  |  | LCC SS No. 6 Part 5.1 | Survey 20m intervals |  | N/A
The heights of earthworks measured anywhere on a layer surface shall not vary from those shown on the drawings,by more than the tolerance stated in Table 5.1.1 unless specified otherwise. Subgrade Level tolerances as per table 5.1.1:- 30mm and +10mm
Final Sign off and Approval - Conformance with the Specification
Name of Cient's Representative |  |  | Signature |  |  |  |  | Date
Name of Contractor's Representative |  |  | Signature |  |  |  |  | Date

## KRB
Inspection and Test Plan
Project Information |  |  |  | Inspection and Test Plan Information
Project |  | Alamein, George and Main St Intersection Upgrades |  | Lot Number |  |  |  |  | Date | Start | Finish
Project No |  | 24 053 |  | Location
Client |  | Logan City Council | [6 empty] | Chainage | From | To
Contract No |  | CD70 |  | Description
Specification |  | Standard Specification No. 8 (Minor Concrete works) |  | Activity | Installation of Kerb, Channel & Kerb and Channel
Acceptance of Activity
# | Acceptance Criteria |  |  |  |  | Reference | Item Check | QA | Client | Date | NCR
1 | Kerb type |  |  |  |  | LCC SS No.8 Part 2.1 | Check and Verify |  | N/A
Kerb and channel complies with standard drawing number R-0080 and is one of the following profiles: B1, B2, SM5, M3, Median and Invert, and must be wet mix unless otherwise approvd by local government
2 | Design and Set-Out Locations |  |  |  |  | LCC SS No.8 Part 2.3 | Check and Verify |  | N/A
Concrete for kerb and kerb and channel is 32 MPa strength grade complying with the requirements of AS 1379-2007: The slump values of the concrete are machine finished (wet kerb)—12mm minimum—40mm maximum.
3 | Compaction of Materials |  |  |  |  | LCC SS No.8 Part 2.2 | Hold Point
Where pavement thickness exceeds 175mm in depth, the pavement extends under the kerb where the pavement thickness does not exceed 175mm in depth, the kerb and channel is firmly bedded on 100mm road base aggregate compacted to 95 percent modified dry density as required under AS 1289.0-2000 Methods of testing soils for engineering purposes - General requirements and list of methods. No concrete is placed until the foundations have been approved by the local government.
4 | Manual Construction |  |  |  |  | MRTS03 Clause 20.4 | Check and Verify |  | N/A
Manually-placed concrete shall be in accordance with Clause 6.1. Exposed surfaces shall have a steel-trowelled finish.
5 | Extruded Construction |  |  |  |  | MRTS03 Clause 20.5 | Check and Verify |  | N/A
Where kerb, channel and/or kerb and channel is constructed by an extrusion process, concrete shall comply with a maximum aggregate size not exceeding 20 mm and a minimum of 320 kg of cement per cubic metre of concrete. The extrusion machine shall be fitted with a tamper and an automatic control which allows adjustment of the position of the forming mould while the machine is in operation.
6 | Joining existing Kerb |  |  |  |  | LCC SS No.8 Part 2.5 | Check and Verify |  | N/A
The concrete kerb or kerb and channel joins neatly with the existing kerb or kerb and channel over a minimal transitional length of 2 metres
7 | Expansion Joints |  |  |  |  | LCC SS No.8 Part 2.4 | Check and Verify |  | N/A
In the case of kerb, a joint is cut and cork jointing is inserted every 20 metres with a cut joint midway between cork joints and jointing is placed in such a manner as to dissect the kerb for its full thickness.
8 | Contraction Joints |  |  |  |  | LCC SS No.8 Part 2.4 | Check and Verify |  | N/A
A contraction joint is provided at 4 metre centres which is finished square and at right angles to the section of kerb or kerb and channel. The kerb or kerb and channel at a contraction joint is guillotined to the full depth of the concrete and re-finished with a jointing tool to form neat joint lines not exceeding 3mm in width and 6mm in depth
9 | Curing |  |  |  |  | LCC SS No.8 Part 2.4 | Check and Verify |  | N/A
Concrete shall be cured for a period not less than seven days before any other roadworks operations are carried out adjacent to the kerb, channel or kerb and channel.
10 | Tolerances |  |  |  |  | LCC SS No.8 Part 2.4 | Check and Verify |  | N/A
The horizontal and vertical alignments of kerb, channel and/or kerb and channel shall not vary from those specified by more than ± 10 mm provided that the difference between the deviations from the correct levels at any two points 30 metres apart does not exceed 30mm. Crossfall is maintained within +/- 0.50 percent of the design
11 | Water Test |  |  |  |  | LCC SS No.8 Part 2.4.10 | WITNESS POINT
Notwithstanding the allowable tolerances, the invert of the channel is finished true to grade and alignment and channelling in which water is found to pond is not accepted and is removed immediately
Inspection and Test Plan
Final Sign off and Approval - Conformance with the Specification
Name of Cient's Representative |  |  | Signature |  |  |  |  | Date
Name of Contractor's Representative |  |  | Signature |  |  |  |  | Date