## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource Id
checklist | ITP - Geotextiles for paving applications | itp
section | Details
checkpoint | Geotextile Filtration & Strength Class
label | Acceptance Criteria and Frequency (Project Specific) - Geotextile to be used as specified in approved drawings
label | Reference - Drawing Notes
label | Item Check - Check and Verify
checkpoint | Storage, packaging and identification on site
label | Acceptance Criteria and Frequency (Project Specific) - Geotextiles shall be stored under protective cover or wrapped with a waterproof, opaque UV protective sheeting to avoid any damage prior to installation.
label | ○ Geotextiles shall not be stored directly on the ground or in any manner in which they may be affected by heat. The method of storage shall be in accordance with any other recommendations set by the manufacturer.
label | ○ The protected geotextile rolls shall be clearly labelled showing manufacturer, type of geotextile and batch number identification number
label | Reference - MRTS27 Clause 7
label | Item Check - Check and Verify
checkpoint | Geotextile Construction Procedure
label | Acceptance Criteria and Frequency (Project Specific) - A construction procedure detailing all work described in this Technical Specification shall be prepared. The construction procedure shall be consistent with the guidelines set out in the Transport and Main Road’s Pavement Rehabilitation Manual April 2012, Sections 4.4.6 to 4.4.6.8.
label | ○ The proposed construction procedure shall be submitted to the Administrator at least 14 days prior to the commencement of any works related to the placement of paving geotextile(s)
label | Reference - MRTS57 Clause 5.2
label | Item Check - Milestone
checkpoint | Approval of construction Procedure
label | Acceptance Criteria and Frequency (Project Specific) - No works related to the placement of paving geotextile(s) shall commence until the construction procedures have been approved by the Administrator and the Administrator has given the Contractor permission to proceed.
label | Reference - MRTS57 Clause 5.2
label | Item Check - Hold Point 1
holdpoint | HOLD POINT
checkpoint | Ordering - Technical Data
label | Acceptance Criteria and Frequency (Project Specific) - At least 14 days prior to the proposed ordering date of any geotextile, the Contractor shall submit to the Administrator a copy of the proposed manufacturer’s technical data sheet and a sample of the proposed geotextile from the manufacturer demonstrating compliance with this Technical Specification
label | Reference - MRTS57 Cl 8.2
label | Item Check - Milestone
checkpoint | Ordering
label | Acceptance Criteria and Frequency (Project Specific) - The Contractor shall not order any geotextile prior to the acceptance of that geotextile by the Administrator.
label | Reference - MRTS57 Cl 8.2
label | Item Check - Hold Point 2
holdpoint | HOLD POINT
checkpoint | Delivery
label | Acceptance Criteria and Frequency (Project Specific) - With each batch of geotextile incorporated in the Works, a certificate of compliance stating that the geotextile complies with all the requirements of this Technical Specification as appropriate to the application, together with test results reported on NATA endorsed test documents, shall be included in the Quality Records
label | Reference - MRTS57 Cl 8.4
label | Item Check - Check and Verify
checkpoint | Surface Terperature
label | Acceptance Criteria and Frequency (Project Specific) - Spraying of bitumen or placement of geotextile shall not commence until the temperature of the surface of the pavement is above the temperature specified in MRTS11 Sprayed Bituminous Surfacing
label | Reference - MRTS57 Cl 9.3
label | Item Check - Check and Verify
checkpoint | Final Sign off and Approval - Conformance with the Specification
textbox | Name of Cient's Representative
date | Date
textbox | Name of Contractor's Representative
date | Date
signoff | Signature
section | Final Sign Offs (to be completed at closure of Lot)
checkpoint | Agreed Quantities
signoff | Agreed Quantities Sign Off
checkpoint | Closure of Lot
signoff | Closure of Lot Sign Off
checklist |  | itp
section
checkpoint
label
label
label