## Sheet1
ConQA Team Notes:
Document Title: |  | ITP-223-CIV-PSDS-Sprayed seal
ITP Description: |  | PSDS-Sprayed seal
Discipline (e.g. CIV/STR/RAIL: |  | 223-CIV
Revision Number: |  | 0
Revision Date: |  | 2024-11-27
ITP created by: |  | Victor Mira
ITP approved for use by: |  | Victor Mira
Special Notes to ConQA Team : |  | ITP for Progress Street
Inspection & Test Plan - Hot Mix Asphalt
|  |  | Document No.: | [5 empty] | Revision: | 0
[9 empty] | Date: | 2024-11-27
Legend: HP: Hold Point, HP* Internal Hold Point, WP: Witness Point, IP: Inspection Point, SP: Surveillance Point
Item | Task/Activity Description | Reference | Acceptance Criteria | Inspection / Test |  |  | Responsibility | Verifying Documents | Date Completed | Sign-off
|  |  |  | Method | Frequency | Category
1 | Referenced Documentation
1.1 | Non Dependent | VR 407 - July 2022 | N/A | N/A | N/A | N/A | N/A | N/A | NA | N/A
1.2 | Non Dependent | VR 173 - Oct 2008 | N/A | N/A | N/A | N/A | N/A | N/A | NA | N/A
2 | Preliminaries - Materials
2.1 | Aggregate | VR 408.11 (a) VR 831.05 ( c) | Aggregate shall comply with VR 831 - Aggregate for Sprayed Seal Bituminous Surfacing. Enter: Teambinder Approval number [free text box] | Document Review | Each Material | HP | PE/Nominated authority | This ITP TeamBinder Approval
2.2 | Bitumen Emulsion | VR 408.08 | Bitumen emulsion shall comply with the requirements of AS 1160. The use of any non standard proprietary classes of bitumen emulsion shall be subject to the Contractor providing evidence that the product has demonstrated satisfactory field performance for a period of at least three years. The primer shall be cutback bitumen. Cutback bitumen shall comply with the requirements of AS 2157. An equivalent product may be used subject to the Contractor providing evidence satisfactory to the Superintendent that the proprietary product has demonstrated acceptable field performance for a period of at least three years. Enter: Teambinder Approval number [free text box] | Document Review | Each Material | HP | PE/Nominated authority | This ITP TeamBinder Approval
3 | Preliminaries - Procedures & Documentation
3.1 | Application of bituminous material and aggregate | VR 408.13 (a) | At least one week prior to the commencement of work, the Contractor shall submit the initial design rates of application for bituminous material, aggregate, and rates for pre-treatment for review by the Superintendent. Enter: Teambinder Approval number [free text box] | Document Review | Each Lot | HP | PE/Nominated authority | This ITP TeamBinder Approval
3.2 | Application of bituminous material and aggregate | VR 408.13 (f) | Where the Contractor proposes to use forward aggregate spreading plant, written approval is required from the Superintendent prior to use, unless written approval has been previously provided by the Department of Transport. Enter: Teambinder Approval number [free text box] | Document Review | Each Lot | HP | PE/Nominated authority | This ITP TeamBinder Approval
3.3 | Claibration of Bitumen Sprayer | VR 408.07 | All sprayers used for application of bituminous materials shall have a current Certificate of Calibration showing compliance with Austroads test methods AGPT T530 through to AGPT T536. The Certificate of Calibration shall be renewed every 12 months. If any sprayer has its spray equipment overhauled or replaced, it shall be calibrated and issued with a new Certificate of Calibration prior to use. Enter: Teambinder Approval number [free text box] | Document Review | Each Lot | HP | PE/Nominated authority | This ITP TeamBinder Approval
4 | Pre-construction Activities
4.1 | IFC Drawings | MRPA Quality Management Plan | Check the revision of the IFC drawings are current as per the drawing register (on Teambinder) | Document Review | Prior to starting Works and at regular intervals | HP* | PE/SE | This ITP
4.2 | Survey set out - Lot Map-and Lot size | 408.05 | Limits of work at the start and finish chainages plus the limit in any side road have been marked on the pavement surface. The Works shall include all existing tapers, bell mouths at intersecting roads, pavement widenings (turn lanes), traffic lanes and sealed shoulders, unless otherwise specified. ATTACH: Lot Map with planned location of Joints | Document review | Each Lot | HP* | PE/SE | attached Lot Map
4.3 | Pavement Preparation | VR 310.02 | The pavement shall be prepared to produce a surface that is: (a) constructed to meet specified shape and level requirements (b) homogenous and consistent with the material in the pavement base layer (c) uniform in texture (d) free of tearing and scabbing (e) free of lamination on or within 75 mm of the finished surface (f) level with adjacent sealed areas and edgings at the joints (g) a hard dense and tight surface capable of being swept with a rotary road broom or similar (h) free of loose and foreign materials | Visual | Each Lot | HP* | PE/SE | This ITP
4.4 | Dry back of Pavement | VR 310.03 | The mean Moisture Ratio shall be determined from six randomly selected sites as a percentage of the optimum moisture content based on Modified compactive effort, and determined in accordance with VicRoads Test Method RC 316.14 Scale B: Mean Moisture Ratio Less than 60% Scale C: mean Moisture Ratio Less than 65% No individual result more than 70% Attch: test results: | Measure | Each Lot | IP | PE/SE Tester | This ITP Attched results
5 | Construction Activities
5.1 | Acceptance of work - Rate of binder application | VR 408.15 (a) | Attach: evidence to show actual rate of application <0.1 L/m2 below design rate of application. | Document Review | Each Lot | IP | PE | This ITP Attached evidence
5.2 | Acceptace of work - Surface texture | VR 408.15 (b) | Acceptance of work for surface texture and surface enrichment shall be based on visual assessment. However, in marginal cases the Superintendent may request that nominated areas be tested in accordance with VicRoads Test Method RC 317.01 | Visual Document Review | Each Lot | IP | PE | This ITP
5.3 | Acceptance of work - aggregate retention | VR 408.15 ( c) | Acceptance of work for aggregate retention shall be based on visual assessment. However, in marginal cases the Superintendent may request that nominated areas be tested in accordance with the VicRoads Test Method RC 317.03 | Visual Document Review | Each Lot | IP | PE | This ITP
6 | Post-construction Activities
6.1 | Removal of loose aggregate | VR 408.14 | After the completion of a sprayed seal treatment, the Contractor shall remove and dispose of all loose aggregate within the maximum time limits as specified in Table 408.141. This includes loose aggregate on all trafficked areas, and areas where loose aggregate has been swept, or moved by traffic onto sealed shoulders or non trafficked areas, or into other areas such as concrete channels, traffic islands, medians, open drains, drainage pits, footpaths, nature strips, or verges. For seals of nominal size 7 mm and under,no more than 60 loose stones in any square metre of pavement shall remain. | Visual | Each Lot | IP | SE/PE | This ITP
6.2 | Records | VR 408.17 | The Contractor shall forward to the Superintendent a Job Completion Report (Sealing) using the proforma included as Attachment A to Section 408 Attach: Job Completion Report (Sealing) | Document Review | Each Lot | IP | Nominated authority | Attached records
Final Inspection
On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
Print Name: Position: Signature: Date: / /